## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-CV-CN-0003 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1778 |  |  | Transmital Date:01/10/2023
Document Title:Calculation Note For Oily Contaminated Water Drainage Channels |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-CV-TR-1778 |  |  | Transmital Date:01/10/2023
[5 empty] | CRS No:NISOC-CRS - D01-BK-GCS-PEDCO-120-CV-CN-0003 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مقتضی است پیرو جلسه بخش سیویل، مورخ 1401/11/08 در دفتر کارفرما، نقطه نظرات و تغییرات مقرر شده در آن جلسه در این مدرک اعمال گردد. |  | 1401-2294-444078 | 1401/11/19 | نظرات کارفرمای محترم به مطابق صورتجلسه ذکر شده اعمال گردید. استاندارد مربوطه پیوست گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: