## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-EL-CN-0002-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1371 |  |  | Transmital Date: 07-Sep-2022
Document Title: Calculation Note for UPS System - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-EL-TR-1371 |  |  | Transmital Date: 07-Sep-2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-EL-CN-0002-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به نامه شماره 47232 مورخ 1401/02/11 (پاسخ ذينفع اصلي پروژه به ترنسميتال 852) مبني بر عدم تاييد مدرك I&C Power consumption و همچنين نقطه نظر واحد ابزاردقيق پترو ايران به شرح زير، امكان بررسي محاسبات در اين مقطع وجود نداشته و لذا مقتضي است پيرو مذاكرات قبلي تا زمان نهايي شدن مدرك مذكور از ارسال مجدد اين مدرك خودداري شود. -مدرك I&C Power Consumption Summary - Extension of Binak B/C Manifold (BK-W007S-PEDCO-110-IN-LI-0007) بخش ابزاردقيق نهايي نيست لذا موارد ارائه شده در جدول بخش 5، قابل تاييد نمي باشد، لازم است كه مستندات و محاسبات در مدرك فوق بر اساس كامنت هاي مربوطه و نقطه نظرات فعلي، اصلاح، بروز و ارائه گردد. -در خصوص پروتكل هاي ارتباطي بين تمامي بسته هاي كاري (منيفولد و كمپرسور گازي) تا حد امكان يكسان سازي صورت پذيرد. -با توجه به مقادير ارائه شده در مدارك مهندسي پايه و مغايرت با موارد ارائه شده در مهندسي تفصيلي، مستندات مربوط به محاسبات مدرك فوق ارائه گردد. |  | BK-SUR-ENG-ELE-01-05735 | 2022-09-21 | آخرین ویرایش مدرک ابزاردقیق که با ترنسمیتال شماره 1899 برای آن کارفرمای محترم ارسال شده، مورد بهره برداری قرار گرفته و مدرک ویرایش شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 21-Sep-22 |  |  |  |  | Date: