## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-EL-DT-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1377 |  |  | Transmital Date: 07-Sep-2022
Document Title: Data Sheets for DC Charger - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-EL-TR-1377 |  |  | Transmital Date: 07-Sep-2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-EL-DT-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | This document shall be revised after finalizing or minor comments on following documents: -Calculation Note for DC Charger System - Extension of Binak B/C Manifold -DC Charger Single Line Diagram - Extension of Binak B/C Manifold -Electrical Power & Control Cable List - Extension of Binak B/C Manifold |  | BK-SUR-ENG-ELE-01-05737 | 2022-09-21 | آخرین ویرایش مدرک ابزاردقیق که با ترنسمیتال شماره 1899 برای آن کارفرمای محترم ارسال شده است، مورد بهره برداری قرار گرفته و محاسبات و برگه داده به روزرسانی شد.
2 | Item 16: Rated input power shall be modified. |  | BK-SUR-ENG-ELE-01-05737 | 2022-09-21
3 | Regarding to available options for feeding FACP such as internal battery and charger or using existing charger, this document shall not be reissued till finalizing best scenario by Instrument. |  | BK-SUR-ENG-ELE-01-05737 | 2022-09-21
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 21-Sep-22 |  |  |  |  | Date: