## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-SL-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0966 |  |  | Transmital Date: 17-May-2021
Document Title: Electrical Overall Single Line Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0102-EL-TR-0966 |  |  | Transmital Date: 17-May-2021
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اعمال نشدن نقطه نظرات قبلی این امور ( نامه شماره 43191)، مدرک قابل بررسی نبوده و عودت داده میشود .پیرو بند 3 فایل REPLY SHEETt لازم است که مدارک پس از نهایی شدن مدرک LV-SLD و MV-SLD با در نظر گرفتن اینترلاکهای بین بالاست ،پایین دست و حفاظت های مربوطه و با جزِییات کامل تکمیل گردد،جهت راهنمایی ازمدارک ارسالی در مکاتبات قبلی استفاده گردد. |  | 01-2294-94378 | 1401-03-18 | مطابق با جلسه برگزارشده در سالن جلسات 28 مخزن ناحیه گچساران در اهواز، نامه شماره 94378 مورد بررسی قرار گرفت و ملاحظات آن در نظر گرفته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 29-May-22 |  |  |  |  | Date: