## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0003-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0039 |  |  | Transmital Date: 09-Aug.-2021
Document Title: SPECIFICATION FOR THE DESIGN OF PIPING IN MECHANICAL PACKAGES |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0039 |  |  | Transmital Date: 09-Aug.-2021
[5 empty] | CRS No: CRS-BK-GNRAL-PEDCO-000-PI-SP-0003-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش 3.1 (codes and standards): استاندارهاي زير اضافه گردد. ASTM API ASME B16.25 ASME B16.11 ASME B36.10M ASME B36.19M IPS-E-PI-221 IPS-M-PI-110 IPS-M-PI-150 IPS-E-IN-110 IPS-E-IN-120 IPS-E-PR-190 IPS-E-PR-420 IPS-G-IN-200 NACE MR-0175/ ISO 1515 |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر کارفرمای محترم اعمال گردید.
2 | در بخش 4.2.12 عبارت زير اضافه شود : ,utilities connections, to orifice flanges,drains and vents. etc. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر کارفرمای محترم اعمال گردید.
3 | بخش 4.2.13 : Screwed connections to instruments shall not be seal .welded The space between the axis of two adjacent pipes shall be at least equal to the sum of . O.D of flanges (with higher rating) or . O.D. of each pipe plus 25 mm. This dimension (25 mm) shall be increased to 50 mm for insulated pipes. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر کارفرمای محترم اعمال گردید.
4 | بخش 4.2.15 : - 6.8 meter for over railways or main road - 6 meter for over access roads for heavy trucks |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر کارفرمای محترم اعمال گردید.
5 | در بخش 4.3.1 : (IPS-E-PI-200 & MB-GNRALPEDCO-100-PI-SP-3680 shall be followed in this case) |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | MB-GNRALPEDCO-100-PI-SP-3680 مربوط به این پروژه نیست.
6 | در بخش 4.3 : Piping flexibility shall be used in preference of any type of expansion joints. If a suitable piping configuration cannot be designed to eliminate the use of expansion joints, the matter shall be discussed with Client before proceeding with any work.A |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر کارفرمای محترم اعمال گردید.
7 | در بخش 6.1 : When welding slip-on flanges, the distance between pipe end and the flange face shall be equal to the thickness of the pipe plus 1/8” (3.2mm). |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر کارفرمای محترم اعمال گردید.
8 | در بخش 7 عبارت زير به عنوان يك آيتم جديد اضافه گردد : Inspection Data Sheets Inspection Data Sheets (IDS) indicate the extent of inspection and testing required for piping systems in accordance with the QCTM (Quality Control & Testing Manual). The QCTM shall be prepared by the vendor or contractor and submitted to client for approval. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر کارفرمای محترم اعمال گردید.
9 | در بخش 7.4 اضافه گردد : All shop fabricated piping shall be prepared for shipment in a manner that assures delivery to destination in good conditions. Vendor shall supply packing specification for Client’s approval. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:05-Sep.-2021 |  |  |  |  | Date: 05-Sep.-2021