## Financial-Delay (hidden)
شرح فعالیت | بخش اصلی / الحاقیه 1 | وزن | واحد | مبلغ پیمان یورو | ضمانت نامه ارائه شده به کار فرما - ریال |  |  |  | پرداخت پیش پرداخت به پیمانکار ( ریال) | پرداخت پیش پرداخت به پیمانکار ( یورو) | صورت وضعیت ارائه شده | صورت وضعیت کل ادعا شده(یورو) | صورت وضعیت تایید شده | پیشرفت مالی 100% | پیشرفت مالی نسبت به وزن | تاریخ رسید وجه | آخرین وضعیت |  |  | نرخ تسعیر ارز (ریال) | تاریخ پرداخت | 35909880.0474 |  | 2022-07-22 |  |  | مدت اولیه پیمان/مبلغ اولیه پیمان | مبلغ صورت وضعیت/دوره صورت وضعیت | مبلغ کل کارکرد اخرین صورت وضعیت/تفاصل تاریخ اخرین صورت وضعیت و تاریخ اولین دریافت پیش پرداخت | مدت اوليه پيمان/تفاصل تاريخ اخرين صورت وضعيت و دريافت اولين پيش پرداخت | مبلغ كاركرد تجمعي اخرين صورت وضعيت تا زمان ارائه ضمانت/مبلغ اوليه پيمان |  | 0.697
[9 empty] | شماره |  | تاریخ ارسال | مبلغ | مبلغ | شماره | تاریخ تائید | [9 empty] | تتا | دوره صورت وضعیت | 2.0384e-05 |  | 3537.5
پیش پرداخت | اصلی | - | - | 35909880 | 177988756617 |  |  |  | 177988756617 |  | 1400/06/03 | 718197 |  | 100% | 100% | 1400/06/16 | پرداخت شده |  |  |  | 1400/06/20 | 2021-08-25 | 2021-11-23 | 2021-09-11
قسط دوم پیش پرداخت (3% مبلغ پیمان) | اصلی |  |  | 35909880 |  |  |  |  | 280576460898 | 1077296.4 | 1400/09/15 | 1077296.4 |  | 3% | 100% | 1401/03/28 | پرداخت شده |  |  |  | 1401/03/28 | 2021-12-06 | 2022-03-06 | 2022-06-18 | 104 |  |  | 0.00212 | 7.4994 | 8.5116 | 0 | روش اول |  | روش دوم
برآوردکارکرد (WPA ) ﺑﺨﺶ ﻣﻬﻨﺪﺳﯽ از تاریخ 1400/04/02 الی G00-1400/09/20 | اصلی | - | - | 980000 | - |  |  |  | - |  | 1400/09/21 | 101.001 |  | 12.88% |  |  | عدم تایید | [5 empty] | 1900-03-30 |  | -90
برآورد کارکرد (WPA ) بخش مهندسی- شماره 1 (به روز شده)(BK-HD-WPA-E-0001_G01) | اصلی |  |  | 980000 | [6 empty] | 1400/11/23 | 133.934 |  | 13.67% |  |  | تایید جهت تهیه صورت وضعیت | [5 empty] | 1900-03-30 |  | -90
برآورد کارکرد (WPA ) بخش های عمومی واجرا - شماره 1 منتهی به تاریخ 1400/09/30 G00 | اصلی |  |  | 9311960 | [6 empty] | 1400/09/29 | 430049 |  | 4.62% |  |  | عدم تایید | [5 empty] | 1900-03-30 |  | -90
برآورد کارکرد (WPA ) بخش های عمومی و اجرا- شماره 1 (به روز شده) از تاریخ 1400/04/02 الی 1400/11/18 G01 | اصلی |  |  | 9311960 | [6 empty] | 1400/11/19 | 644323 |  | 6.92% |  |  | تایید جهت تهیه صورت وضعیت | [5 empty] | 1900-03-30 |  | -90
صورت وضعیت شماره 1 مهندسی (منتهی به تاریخ 1400/11/16) | اصلی |  |  | 980000 |  | 2021-06-23 | 2022-02-05 | 227 |  |  | 1400/12/09 | 167414 |  | 17.08% |  |  | بصورت الحساب و در چند قسط پرداخت شده |  |  |  |  | 2022-02-28 | 2022-05-29 | 2022-07-22 | 54 |  |  | 737.5066 | 0.010478 | 3.2247 | 0.0046621 | 0.56583
صورت وضعیت شماره 1 عمومی و اجرا (منتهی به تاریخ 1400/11/18) | اصلی |  |  | 9673613 |  | 2021-06-23 | 2022-02-07 | 229 |  |  | 1400/12/09 | 42319 |  | 4.54% |  |  | بصورت الحساب و در چند قسط پرداخت شده |  | 590.604 |  |  | 2022-02-28 | 2022-05-29 | 2022-07-22 | 54 |  |  | 184.7991 | 0.0026256 | 3.1965 | 0.0011785 | 0.14178
دریافت علی الحساب بابت صورت وضعیت 1 مهندسی و 1 اجرا | اصلی |  |  |  |  | 2021-06-23 |  |  | 75000000000 | 276344.88 | 1400/12/09 | [5 empty] | پرداختی |  |  | 271400 | 1400/12/09 | 2022-02-28 | 2022-05-29 | 2022-02-28 | -90
برآورد کارکرد (WPA ) شماره 2 مهندسی (منتهی به تاریخ 1400/12/29) | اصلی |  |  | 980000 |  | 2021-06-23 |  |  |  |  | 1401/01/16 | 187670 |  | 19.15% | [7 empty] | 2022-02-28 | 2022-05-29 |  | -44710
برآورد کارکرد (WPA ) شماره 2 عمومی و اجرا (منتهی به تاریخ 1400/12/29) | اصلی |  |  | 9673613 |  | 2021-06-23 |  |  |  |  | 1401/01/16 | 887892 |  | 9.18% | [7 empty] | 2022-02-28 | 2022-05-29 |  | -44710
دریافت علی الحساب بابت صورت وضعیت 1 مهندسی و 1 اجرا | اصلی |  |  |  |  | 2021-06-23 |  |  | 10000000000 | 37635.58 | 1401/01/28 | [5 empty] | پرداختی |  |  | 265706 | 1401/01/28 | 2022-02-28 | 2022-05-29 | 2022-04-17 | -42
دریافت علی الحساب بابت صورت وضعیت 1 مهندسی و 1 اجرا | اصلی |  |  |  |  | 2021-06-23 |  |  | 60589340647 | 229375.62 | 1401/02/07 | [5 empty] | پرداختی |  |  | 264149 | 1401/02/07 | 2022-02-28 | 2022-05-29 | 2022-04-27 | -32
صورت وضعیت شماره 2 مهندسی (منتهی به تاریخ 29/12/1400) | اصلی |  |  | 980000 |  | 2022-02-06 | 2022-03-20 | 42 |  |  | 1401/02/04 | 187670 |  | 19.15% |  |  | پرداخت نشده | 0358 |  |  |  | 2022-04-24 | 2022-07-22 | 2022-07-22
صورت وضعیت شماره 2 عمومی و اجرا (منتهی به تاریخ 29/12/1400) | اصلی |  |  | 9673613 |  | 2022-02-08 | 2022-03-20 | 40 |  |  | 1401/02/07 | 672125 |  | 6.95% |  |  | پرداخت نشده | 0368 |  |  |  | 2022-04-27 | 2022-07-26
برآورد کارکرد بخش مهندسی- شماره 3(BK-HD-WPA-E-0003_G00) | اصلی |  |  | 980000 |  |  | 2022-03-22 | 44642 |  |  | 1401/03/08 | 252452 |  | 25.76% | [8 empty] | 1900-03-30
برآورد کارکرد بخش های عمومی و اجرا- شماره 3(BK-HD-WPA-C-0003_G00) | اصلی |  |  | 9673613 |  |  | 2022-03-23 | 44643 |  |  | 1401/03/09 | 909.471 |  | 9.4% | [8 empty] | 1900-03-30
صورت وضعیت شماره 3 مهندسی (از 01/01/1401 تا 31/02/1401) |  |  |  | 980000 |  | 2022-03-21 | 2022-05-21 | 61 |  |  | 1401/03/25 | 252.452 |  | 25.76% |  |  | پرداخت نشده |  |  |  |  | 2022-06-15 | 2022-09-13
صورت وضعیت شماره 3 عمومی و اجرا (از 01/01/1401 تا 31/02/1401) |  |  |  | 9673613 |  | 2022-03-21 | 2022-05-21 | 61 |  |  | 1401/03/25 | 863.864 |  | 8.93% |  |  | پرداخت نشده |  |  |  |  | 2022-06-16 | 2022-09-14

## 1
جدول شماره 1 : شناسنامه پروژه
عنوان: مهندسی، تامین کالا و تجهیزات، ساختمان و نصب و راه اندازی (EPCC) ابنیه تحت الارض و تاسیسات سطح الارضی طرح نگهداشت و افزایش تولید میدان بینک
شماره قرارداد: BK-00-CO-0001
كارفرما: شرکت توسعه پتروایران
مجري طرح: منصور مهرشاد
مديريت طرح (مشاور):
پيمانكار: مشارکت "هیرگان انرژی- طرح و بازرسی"
مدير پروژه پيمانكار: محمد فخاریان
موضوع: بخش سطح الارض پروژه نگهداشت و افزایش تولید میدان نفتی بینک (بسته بینک) را در قالب پیمان EPCC
محل: میدان نفتی بينك در استان بوشهر در فاصله 20 كيلومتري شمال غربي شهرستان گناوه، واقع شده است
وضعيت: ساير£ متوقف/تعليق£ پايان مدت پيمان£ تكميل پروژه£ پيمان خاتمه داده شده£ در حال اجرا¢
پيشرفت فيزيكي تا پايان مدت ارائه لايحه تاخيرات 7/47 % درصد
مبلغ اوليه قرارداد (ميليون ريال): - |  | مبلغ اوليه قرارداد (يورو): 35,909,880
تعديل قرارداد دارد£ ندارد¢ |  | مدت تعليق قرارداد: -
مدت اوليه (ماه): 24 ماه |  | تاريخ خاتمه مدت اوليه: 1402/04/02
مدت تمديدهاي پيشين (ماه):- |  | تاريخ خاتمه:-
تاخيرات مجاز پيشين (ماه):-
تاريخ امضا قرارداد |  | تاريخ ابلاغ شروع به كار: | 1400/04/02
تاريخ تحويل موقت (بخشي-كلي) |  | تاريخ تحويل قطعي:

## 2
جدول شماره 2 : خلاصه لايحه تاخيرات پروژه
عنوان طرح: | طرح نگهداشت و افزایش تولید میدان بینک |  |  |  | شماره قرارداد : | BK-00-CO-0001
شماره لایحه تاخیرات : | 3 |  |  |  | تاریخ تنظیم لایحه تاخیرات: | 1401/09/30
نام مشاور : | -
نام پیمانکار : | مشارکت "هیرگان انرژی- طرح و بازرسی"
مبلغ پیمان : | - |  | ميليون ريال |  | 35909880.0474 | يورو
مدت اولیه پیمان (ماه): | 24 | تاریخ شروع: 1400/04/02 |  |  | تاریخ پايان اسمي: | 1402/04/02
تاریخ تحویل زمین: |  | مدت تمدیدهاي پیشین (ماه) : | - |  | تاریخ پایان برنامه ریزي شده: | -
تاریخ تحویل موقت: (بخشي و كلي) |  | مدت دوره تضمین (ماه): | 18 ماه |  | تاریخ تحویل قطعی: | -
تاخیرات (روز) | نوع |  | مجاز
| فني قراردادي |  | 546.1
| مالي |  | 239
| غير مترقبه |  | 0
| جمع كل* |  | 546.1
*جمع کل حاصل از همپوشانی است و حاصل از جمع جبري سه ردیف تأخیرات فنی-قراردادي، مالی و غيرمترقبه (ساير) نمی باشد.
مهر و امضاء پیمانکار |  |  |  | مهر و امضاء كارفرما

## 3
جدول شماره 3 : مستندات آيتم هاي تاخير
| كد آيتم تاخير |  |  | عنوان علل تاخير | [11 empty] | نتيجه
| رديف | مستندات | [6 empty] | NISOC Date |  | PEDCO Date |  | Hirgan Date |  | ترتيب مستندات
|  | نوع |  | موضوع |  |  |  |  | تاريخ | شماره | تاريخ | شماره | تاريخ | شماره
تاخير در دريافت پيش پرداخت-قسط اول | 1 | مالي |  | درخواست قسط اول پیش پرداخت (2% مبلغ پیمان) | 1400/04/07 | 2 | [6 empty] | 2021-06-28 | 2 | 1
| 2 | مالي |  | ارائه ضمانتنامه قسط اول پیش پرداخت (2% مبلغ کل پیمان) | 1400/05/04 | 23 | [6 empty] | 2021-07-26 | 23 | 2
| 3 | مالي |  | پیگیری دریافت قسط اول پیش پرداخت (2% مبلغ کل پیمان) | 1400/05/10 | 34 | [6 empty] | 2021-08-01 | 34 | 3
| 4 | مالي |  | پیگیری دوم دریافت قسط اول پیش پرداخت (2% مبلغ کل پیمان) | 1400/05/31 | [7 empty] | 2021-08-22 | 56 | 4
| 5 | مالي |  | پرداخت پيش پرداخت قسط اول | [6 empty] | 2021-09-11
تاخير در دريافت پيش پرداخت-قسط دوم | 1 | مالي |  | درخواست قسط دوم پیش پرداخت (3% مبلغ پیمان) | [8 empty] | 2021-12-05 | 202 | 1
| 2 | مالي |  | درخواست كارفرما بر تكميل مستندات | [6 empty] | 2022-01-04 | 21910 |  |  | 2
| 3 | مالي |  | ارائه مستندات مربوطه جهت دریافت قسط دوم پیش پرداخت (3% مبلغ پیمان)-پاسخ به نامه 21910 | [8 empty] | 2022-01-05 | 239 | 3
| 4 | مالي |  | پیگیری دریافت قسط دوم پیش پرداخت (3% مبلغ پیمان) | [8 empty] | 2022-01-26 | 268 | 4
| 5 | مالي |  | پیگیری دریافت قسط دوم پیش پرداخت (3% مبلغ پیمان) | [8 empty] | 2022-02-19 | 301 | 5
| 6 | مالي |  | پیگیری مجدد دریافت قسط دوم پیش پرداخت (3% مبلغ پیمان) | [8 empty] | 2022-03-27 | 329 | 6
| 7 | مالي |  | پیگیری سوم کارسازی و دریافت قسط دوم پیش پرداخت (3% مبلغ پیمان) | [8 empty] | 2022-04-27 | 366 | 7
| 8 | مالي |  | اعلام نرخ معادل ريالي ضمانت نامه توسط كارفرما جهت تهيه ضمانت نامه | [6 empty] | 2022-05-21 | 4241 |  |  | 8
| 9 | مالي |  | ارائه ضمانتنامه بابت علی الحساب قسط دوم پیش پرداخت (3% مبلغ کل پیمان) | [8 empty] | 2022-05-31 | 395 | 9
| 10 | مالي |  | پرداخت پيش پرداخت قسط دوم | [6 empty] | 2022-06-18 |  |  |  | 10
عدم وجود اطلاعات فرايندي در چاه ها در اسناد مناقصه | 1 | فني |  | عدم وجود اطلاعات فرايندي در چاه ها در اسناد مناقصه-دريافت فشار، دما، دبي چاه ها در حالت عملياتي | [6 empty] | 2021-09-13 | 12194 | 2021-08-09 | 44 | 1 | مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
| 2 | فني |  | دريافت اطلاعات فرآيندي فشار جرياني چاه ها قبل كاهنده |  |  |  |  | 2021-10-06 | 223853 | 2021-10-13 | 14622 |  |  | 2 | مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
| 3 | فني |  | دريافت اطلاعات جریانی خروجی از چاه ها | [6 empty] | 2021-11-15 | 17216 |  |  | 3 | * در پاسخ به نامه شماره 44 * مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
| 4 | فني |  | تناقض اطلاعات دریافتی با مدارک پایه | [6 empty] | 2021-12-26 | 21018 | 2021-11-23 | 192 | 4
| 5 | فني |  | انجام مجدد مطالعات پابه با توجه به تغییر در اطلاعات فرآیندی پروژه- نقطه نظرات کارفرما برای اضافه شدن مدرك مطالعات خوردگي به MDL |  |  |  |  | 2021-09-13 | MDL | 2021-09-13 |  |  |  | 5 | منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي كه نهايتا در MDL ويرايش G02 اضافه می گردد
| 6 | فني |  | ضرورت برگزاري جلسه در 00/10/19 و منوط شدن نهايي شدن موضوع به دريافت اطلاعات توليد آب از چاه ها |  |  |  |  | 2022-01-26 | 382258 | 2022-01-30 | 24325 |  |  | 6 | منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
مطالعات خوردگي | 1 | فني |  | توليد مجدد مدرك مطالعات خوردگي و انجام توافقات فني در اين خصوص و منوط شدن نهايي شدن موضوع به دريافت اطلاعات توليد آب از چاه ها |  |  |  |  | 2022-01-10 | 358499 | 2022-01-15 | 22782 |  |  | 1 | صورتجلسه مورخ 00/10/19 انجام مجدد مطالعات پایه در فاز مطالعات Detail
| 2 | فني |  | پيگيري دريافت اطلاعات توليد آب از چاه ها | [8 empty] | 2022-01-17 | 253 | 2 | پيگيري پيمانكار جهت دريافت اطلاعات فني كارفرما-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 3 | فني |  | پيگيري مجدد دريافت اطلاعات توليد آب از چاه ها | [8 empty] | 2022-01-25 | 264 | 3 | پيگيري پيمانكار جهت دريافت اطلاعات فني كارفرما-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 4 | فني |  | دريافت اطلاعات تغييرات برش آب همراه نفت در مخازن بينك در بازه زماني بيست ساله |  |  |  |  | 2022-01-26 | 382258 | 2022-01-30 | 24325 |  |  | 4 | دريافت اطلاعات فني كارفرما-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 5 | فني |  | درخواست عدم انجام مطالعات هيدروليك و صرفا تغيير مطالعات خوردگي بر اساس تغيير ميزان آب توليدي | [8 empty] | 2022-02-01 | 275 | 5 | ارائه پيشنهاد پيمانكار-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 6 |  |  | ارسال ويرايش D01 مدرك مطالعات خوردگي با ترانسميتال 766 | [8 empty] | 2022-03-30 | T-766 | 6 | ارسال مدرك-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 7 | فني |  | دريافت اطلاعات تغييرات برش آب همراه نفت در مخازن بينك در بازه زماني بيست ساله- ويرايش شده |  |  |  |  | 2022-04-04 | 8112 | 2022-04-06 | 709 |  |  | 7 | دريافت اطلاعات فني كارفرما-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 8 | فني |  | اعلام عدم حد مجاز خوردگي به ميزان 1 ميليمتر |  |  |  |  | 2022-03-16 | 453303 | 2022-04-03 | 200 | 2022-02-28 | T-658 | 8 | دريافت نظر فني كارفرما-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 9 | فني |  | ارائه پاسخ به نامه 453303 كارفرما و ارائه راه كار در خصوص جمع بندي نهايي موضوع خوردگي (كاهش فشار طراحي يا كاهش حد مجاز خوردگي يا كاهش قطر اسمي خطوط لوله جرياني) | [8 empty] | 2022-04-05 | 340 | 9 | ارائه پيشنهاد پيمانكار-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 10 | فني |  | پيگيري دريافت نظر كارفرما پيرو عدم دريافت پاسخ نامه 340 | [8 empty] | 2022-05-16 | 378 | 10 | پيگيري پيمانكار جهت دريافت نظر كارفرما-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 11 | فني |  | دريافت نقطه نظرات كارفرما بر روي ويرايش D01 و ضرورت ارائه راهكار براي مقابله با خوردگي حفره اي (پاسخ ترنسميتال 766) |  |  |  |  | 2022-05-29 | 78818 | 2022-06-08 | 5862 |  |  | 11 | دريافت نظر فني كارفرما-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 12 | فني |  | دريافت پاسخ نامه 340 و عدم تاييد حد ميزان مجاز خوردگي به ميزان يك ميلي متر |  |  |  |  | 2022-05-29 | 78826 | 2022-06-01 | 5421 |  |  | 12 | دريافت نظر فني كارفرما-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 13 | فني |  | درخواست از كارفرما جهت اعلام حد مجاز خوردگي پيرو نامه 78826 كارفرماي اصلي و پذيرش تبعات مالي افزايش ضخامت | [8 empty] | 2022-06-06 | 399 | 13 | ارائه پيشنهاد پيمانكار-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 14 | فني |  | ارسال گزارش مقايسه اي فني اقتصادي در خصوص پارامترهاي طراحي و درخواست از كارفرما جهت طراحي بر مبناي اسناد پايه؛ يا تغيير فشار طراحي يا ميزان آب توليدي از چاه ها يا پذيرش تبعات مالي | [8 empty] | 2022-06-27 | 425 | 14 | ارائه پيشنهاد پيمانكار-منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
| 15 | فني |  | برگزاري جلسه با كارفرما در 01/05/12 و تصميم نهايي به تغيير فشار طراحي به 1035 |  |  |  |  | 2022-08-09 | 169801 | 2022-08-13 | 10640 |  |  | 15 | دريافت صورتجلسه 01/05/12، و تصميم نهايي در خصوص مطالعات خوردگي
| 16 | فني |  | برگزاري جلسه با كارفرما در 01/05/26 و تصميم نهايي به تغيير فشار طراحي به 5000 و 3000 |  |  |  |  | 2022-09-02 | 205927 | 2022-09-05 | 12286 |  |  |  | دريافت صورتجلسه 01/05/12، و تصميم جدید در خصوص مطالعات خوردگي
طرح مديريت پسماند | 1 | فني |  | ارسال نقشه سلر و پلان پروفيل چاه 28 | [6 empty] | 2022-01-15 | 22814 | 2021-12-29 | 232 | 1 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 2 | فني |  | ابلاغ تاييديه طرح كلي مديريت پسماند جديد چاه 28 و درخواست ارسال برآورد تغيير كاري | [6 empty] | 2021-12-29 | 21361 |  |  | 2 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 3 | فني |  | ارسال برآورد تغيير كاري طرح مديريت پسماند چاه 28 به كارفرماي اصلي | [6 empty] | 2022-01-02 | 21696 |  |  | 3 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 4 | فني |  | دريافت نقطه نظرات كارفرما براي روي نقشه سلر و پلان پروفيل چاه 28 | [6 empty] | 2022-01-03 | 21800 |  |  | 4 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 5 | فني |  | ارسال نقشه سلر و پلان پروفيل ويرايش شده چاه 28 | [8 empty] | 2022-01-18 | 255 | 5 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 6 | فني |  | برگزاري جلسه با كارفرما در 00/11/15 و تصميم گيري طراحي مديريت پسماند چاه هاي 28، 35، 46،8 و 7 مطابق با طرح مديريت پسماند چاه 18 |  |  |  |  | 2022-01-30 | 387966 | 2022-02-05 | 24766 |  |  | 6 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 7 | فني |  | دريافت نقطه نظرات كارفرما براي روي نقشه سلر و پلان پروفيل چاه 28 |  |  |  |  | 2022-01-23 | 377369 | 2022-01-26 | 23991 |  |  | 7 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 8 | فني |  | دريافت نقطه نظرات كارفرما براي روي نقشه سلر و پلان پروفيل چاه 28 | [6 empty] | 2022-02-01 | 24543 |  |  | 8 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 9 | فني |  | ارسال مجدد اطلاعات نامه 255 | [8 empty] | 2022-02-05 | 280 | 9 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 10 | فني |  | دريافت نقطه نظرات كارفرما براي روي نقشه سلر و پلان پروفيل چاه 28 |  |  |  |  | 2022-02-07 | 400926 | 2022-02-13 | 25513 |  |  | 10 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 11 | فني |  | دريافت تاييديه نهايي طرح مديريت پسماند چاه 28 |  |  |  |  | 2022-02-26 | 425418 | 2022-02-28 | 26896 |  |  | 11 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 12 | فني |  | ارسال نقشه سلر و پلان پروفيل چاه 46 | [8 empty] | 2022-03-14 | 318 | 1 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 13 | فني |  | ارسال نقشه سلر و پلان پروفيل چاه 46 | [8 empty] | 2022-03-27 | 331 | 2 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 14 | فني |  | دريافت پاسخ كارفرما بر روي نقشه سلر و پلان پروفيل چاه 46 |  |  |  |  | 2022-03-30 | 6076 | 2022-04-06 | 690 |  |  | 3 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 15 | فني |  | ارسال طرح مديريت پسماند چاه 46 | [8 empty] | 2022-05-07 | 372 | 4 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 16 | فني |  | تاييديه طرح مديريت پسماند چاه 46 |  |  |  |  | 2022-05-31 | 84838 | 2022-06-08 | 5848 |  |  | 5 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 12 | فني |  | تایید طرح جدید مدیریت پسماند بسته موقعیت چاه غرب 046S |  |  |  |  | 2022-05-31 | 84838 | 2022-06-08 | 5848 |  |  | 12 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 13 | فني |  | درخواست تعیین تکلیف نهایی طرح جدید مدیریت پسماند بسته موقعیت چاه غرب 035 |  |  |  |  | 2022-08-16 | 10944 | 2022-07-24 | 9511 | 2022-07-20 | 451 | 13 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 14 | فني |  | تایید طرح جدید مدیریت پسماند بسته موقعیت چاه غرب 035 | [10 empty] | 14 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 15 | فني |  | درخواست تعیین تکلیف نهایی طرح جدید مدیریت پسماند بسته موقعیت چاه 008 | [10 empty] | 15 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 16 | فني |  | درخواست تعیین تکلیف نهایی طرح جدید مدیریت پسماند بسته موقعیت چاه 007 | [10 empty] | 16 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 17 | فني |  | ارسال طرح جدید مدیریت پسماند بسته موقعیت چاه BK14 | [6 empty] | 2022-11-05 | 16000 |  |  | 17 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 18 | فني |  | عدم وجود اطلاعات مدیریت پسماند چاه BK-05 | [10 empty] | 18 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 19 | فني |  | عدم وجود اطلاعات مدیریت پسماند چاه BK-15 | [10 empty] | 19 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
| 20 | فني |  | عدم وجود اطلاعات مدیریت پسماند چاه BK-12 | [10 empty] | 20 | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه-تطويل در روند نهايي سازي مدارك مرتبط و فعاليت هاي اجرايي
عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز | 1 | فني |  | درخواست رفع ابهامات اطلاعات فرآیندی ایستگاه گاز | [8 empty] | 2021-09-19 | 99 | 1
| 2 | فني |  | دریافت پاسخ کارفرما بر روی ابهامات اطلاعات فرآیندی ایستگاه گاز (پاسخ 99) | [6 empty] | 2021-10-04 | 13901 |  |  | 2
| 3 | فني |  | درخواست رفع ابهامات اطلاعات فرآیندی ایستگاه گاز | [8 empty] | 2021-10-10 | 133 | 3
| 4 | فني |  | تغییر دبی ورود به ایستگاه گاز |  |  |  |  | 2021-10-25 | 247891 |  |  |  |  | 4 | مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
| 5 | فني |  | پیگیری درخواست جلسه پیرو موارد فرایندی و ابزار دقیقی ایستگاه گاز | [8 empty] | 2021-11-07 | 170 | 5
| 6 | فني |  | دریافت پاسخ کارفرما پیرو ابهامات و موارد فرایندی و ابزار دقیقی ایستگاه گاز (پاسخ 170) |  |  |  |  | 2021-11-14 | 275271 | 2021-11-20 | 17661 |  |  | 6
| 7 | فني |  | دریافت نحوه اختصاص و میزان دبی جریان از واحدهای کلاستر گلخاری و بینک |  |  |  |  | 2021-11-10 | 270410 | 2021-11-15 | 17218 |  |  | 7
| 8 | فني |  | درخواست اطلاعات مورد نیاز خط لوله گاز ورودی از کلاستر گلخاری 3 | [8 empty] | 2021-12-01 | 197 | 8 | درخواست بازید از سایت 00/09/23 و 00/09/22
| 9 | فني |  | تغییر دمای خط ورودی به ایستگاه گاز از سمت تفکیک گر گلخاری |  |  |  |  | 2021-11-28 | 294976 | 2021-12-06 | 1920 |  |  | 9 | مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
| 10 | فني |  | اعلام تبعات مترتب از تغییر مشخصات فرآیندی ایستگاه گاز | [8 empty] | 2021-12-11 | 213 | 10
تغيير مشخصات فني كمپرسورها | 1 | فني |  | ارسال مكانيكال ديتا شيت كمپرسورها ويرايش D03 در تاريخ 22 دي 1400 بصورت Non-Lube | [8 empty] | 2022-01-12 | T-454 | 1 | ارسال مدرك به صورت Non-Lube
| 2 | فني |  | دريافت پاسخ كارفرما بر روي ويرايش D03 و درخواست اعلام دلايل Non-Lube بودن به همراه ساير كامنت هاي فني |  |  |  |  | 2022-02-22 | 421703 | 2022-02-27 | 26846 |  |  | 2 | درخواست كارفرما مبني بر توجيه Non-Lube بودن
| 3 | فني |  | ارسال مكانيكال ديتا شيت كمپرسورها ويرايش D04 در تاريخ 14 اسفند 1400 بصورت Non-Lube | [8 empty] | 2022-03-05 | T-675 | 3 | ارسال مدرك به صورت Non-Lube
| 4 | فني |  | دريافت پاسخ كارفرما بر روي ويرايش D04 و درخواست ادامه طراحي بر اساس اسناد پيمان بصورت Non-Lube |  |  |  |  | 2022-03-26 | 1309 | 2022-04-03 | 200 |  |  | 4 | پاسخ كارفرما مبني بر طراحي به صورت Non-Lube
| 5 | فني |  | اعلام تبعات Luboil شدن به كارفرما در تاريخ 10 فروردين 1401 و درخواست جمعبندي هرچه سريعتر موضوع با توجه به روند افزايش قيمت ها | [8 empty] | 2022-03-30 | 333 | 5 | پيگيري پيمانكار به منظور جمع بندي موضوع
| 6 | فني |  | برگزاري جلسه مشترك با نمايندگان كارفرماي اصلي و شركت پترو ايران در تاريخ 20 فروردين 1401 و جمعبندي موضوع جهت Lube-type شدن كمپرسورها |  |  |  |  | 2022-04-13 | 22620 | 2022-04-17 | 1579 |  |  | 6 | برگزاري جلسه مشترك به منظور جمع بندي و نظر جمع بندي به صورت Lube-Type
| 7 | فني |  | ارسال مكانيكال ديتا شيت كمپرسورها ويرايش D05 بصورت Non-Lube در تاريخ 31 فروردين 1401 | [8 empty] | 2022-04-20 | T-818 | 7 | ارسال مدرك به صورت Non-Lube-علي رغم توافقات در جلسه 20 فروردين به دليل اينكه پيمانكار به صورت غير رسمي در تاريخ 01/01/30 از نظر جديد كارفرما مبني بر ضرورت تصميم گيري در كميته تغييرات مطلع شده بود ويرايش D05 را به صورت non-Lube ارائه نمود
| 8 | فني |  | اعلام رسمي عدم موافقت كميته تغييرات كارفرما با مفاد جلسه 20 فروردين 1401 |  |  |  |  | 2022-04-22 | 33757 | 2022-04-26 | 2485 |  |  | 8 | دريافت نظر رسمي كارفرما مبني بر مخالفت كميته تغييرات با Lube Type َشدن
| 9 | فني |  | ارسال پيشنهاد پيمانكار در خصوص انحرافات بهينه و پيشنهاد به تغيير به Lube-type بودن كمپرسورها | [8 empty] | 2022-04-25 | 360 | 9 | ارسال پيشنهاد پيمانكار در خصوص Lube-Type شدن
| 10 | فني |  | پاسخ نامه 360-دريافت پاسخ كارفرما و اعلام ضرورت Non-Lube بودن |  |  |  |  | 2022-04-28 | 43151 | 2022-05-02 | 2970 |  |  | 10 | مخالفت كارفرما با Lube-Type شدن
| 11 | فني |  | پاسخ جديد 360-پذيرش انحرافات پيشنهادي پيمانكار در مشخصات فني |  |  |  |  | 2022-05-05 | 48187 | 2022-05-09 | 3309 |  |  | 11 | موافقت كارفرما با Lube-Type شدن
| 12 | فني |  | ارسال مكانيكال ديتا شيت كمپرسورها ويرايشD06 در تاريخ 18 ارديبهشت 1401 بصورت Lube-type جهت تاييديه نهايي | [8 empty] | 2022-05-08 | T-913 | 12 | ارسال مدرك به صورت Lube-Type
| 13 | فني |  | پيگيري درخواست بررسي و تاييد مكانيكال ديتا شيت كمپرسورها ويرايش D06 | [8 empty] | 2022-05-24 | 385 | 13 | پيگيري پيمانكار به منظور نهايي شدن مدرك
| 14 | فني |  | پاسخ به نامه 385-دريافت پاسخ كارفرما مبني بر تغيير كلاس فلنج ورودي كمپرسور بر روي ويرايش D06 (بدون اعلام نظر روي lube-Type شدن-Lube Type مورد تاييد است) |  |  |  |  | 2022-06-07 | 91109 | 2022-06-08 | 5852 |  |  | 14 | دريافت پاسخ فني كارفرما روي مدرك بدون اعلام نظر روي موضوع Lube Type (تاييديه Lube-Type)
| 15 | فني | 0 | ارسال TBE ويرايش D02 در تاريخ 21 خرداد 1401 به منظور اخذ تاييده كارفرما جهت عقد قرارداد | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-06-11 | T-1065 | 15 | ارسال TBE به صورت Lube-Type به منظور سفارش گذاري هر چه سريعتر | 0
| 16 | فني |  | پاسخ مجدد به نامه 385-(اعلام Lube-Typeَ شدن به اصرار پيمانكار بوده است و Non-Lube مطابق با اسناد پيمان است) |  |  |  |  | 2022-06-18 | 106302 | 2022-06-21 | 7170 |  |  | 16 | دريافت عدم تاييديه Lube-Type شدن
| 17 | فني |  | دريافت پاسخ بر روي ويرايش D06 و Reject كردن مدرك به دليل Lube-Type شدن |  |  |  |  | 2022-05-21 | 70331 | 2022-06-08 | 5862 |  |  | 17 | reject كردن مدرك به دليل Lube-Type بودن
| 18 | فني |  | عطف به نامه 7170 و دريافت پاسخ كارفرما مبني منوط شدن تغييرات انحرافات به دريافت تاييديه در كميته تغييرات و درخواست گزارش مالي - زماني |  |  |  |  | 2022-06-25 | 114060 | 2022-06-29 | 8072 |  |  | 18 | دريافت مجدد نظر كارفرما و منوط كردن موضوع تغيير مشخصات فني به كميته تغييرات
| 19 | فني |  | برگزاري جلسه مشترك به منظور جمع بندي نهايي در 01/04/07 | [10 empty] | 19 | برگزاري جلسه مشترك به منظور جمع بندي و نظر جمع بندي جهت ارسال گزارش فني اقتصادي
| 20 | فني |  | درخواست تغييرات مالي زماني مورد درخواست سازندگان كمپرسورها در خصوص تغيير مشخصات فني پيرو برگزاري جلسه مشترك در تاريخ 01/04/07 |  |  |  |  | 2022-07-03 | 128283 | 2022-07-06 | 8485 |  |  | 20 | دريافت صورتجلسه
| 21 | فني |  | ارسال تغييرات مالي زماني مورد درخواست سازندگان كمپرسورها در خصوص تغيير مشخصات فني | [8 empty] | 2022-07-06 | 439 | 21 | ارسال گزارش فني اقتصادي
| 22 | فني |  | در انتظار برگزاري كميته تغييرات | [10 empty] | 32 | در انتظار برگزاري جلسه كميته تغييرات
| 23 | فني |  | در انتظار تایید نهایی دیتاشیت کمپرسور ها و جاری سازی سفترش خرید آن | [11 empty] | پيگيري پيمانكار به منظور نهايي شدن مدرك
WHCP | 1 | فني |  | اعلام عدم در درسترس بودن اطلاعات SSV , SSSV و ادامه فرآيند مناقصه با فرضيات و دريافت تاييديه در زمان عقد قرارداد | [6 empty] | 2021-12-26 | 21018 |  |  | 1 | دستور به ادامه فرايند مناقصه
| 2 | فني |  | تاييديه نهايي مشخصات فني WHCP | [6 empty] | 2022-04-25 | 2286 |  |  | 2 | نهايي سازي مشخصات توسط كارفرما
| 3 | فني |  | انتخاب سازنده WHCP | [8 empty] | 2022-03-15 | 320 | 3
| 4 | فني |  | تاييديه سازندهWHCP | [6 empty] | 2022-04-06 | 715 |  |  | 4
| 5 | فني |  | نهايي سازي قرارداد WHCP | [8 empty] | 2022-05-24 | 384 | 5
| 6 | فني |  | پيگيري تاييد قرارداد WHCP | [8 empty] | 2022-07-02 | 429
| 7 | فني |  | تاييديه قرارداد WHCP |  |  |  |  | 2022-07-06 | 132668 | 2022-07-13 | 8906
| 8 | فني |  | برگزاري PIM و KOM در تاريخ 01/04/26 | [8 empty] | 2022-07-17
| 9 | فني |  | ارسال صورتجلسه PIM و KOM در تاريخ 01/04/26 | [8 empty] | 2022-07-20 | 454
الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي | 1 | مديريتي |  | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي |  |  |  |  | 2021-09-03 | 182921 | 2021-09-05 | 11561 | 2021-08-15 | 53 | 1 | *اعلام گزارش به کارفرما از یک سازنده داخلی توانمند جهت ساخت لوله ها و درخواست خرید از خارج در تاریخ 00/05/24 *برگزاری جلسه مشترک در تاریخ 00/06/02 *دریافت پاسخ کارفرما مبنی بر استعلام از سایر سازندگان و همچنین ثبت در سامانه توان ایران
| 2 | مديريتي |  | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي | [8 empty] | 2021-09-26 | 112 | 2 | ارسال گزارش جامع اول: -اعلام انصراف شرکت اسفراین در تاریخ 00/05/12 ، -گروه صنعتی فولاد در 00/06/22 - همچنین ثبت در سامانه توان ایران در تاریخ 00/06/17 و 00/06/22
| 3 | مديريتي |  | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي | [6 empty] | 2021-10-03 | 13825 | 2021-10-27 | 145 | 3 | ارسال گزارش جامع دوم و اعلام انصراف شرکت ها: - ضرورت انجام تغییرات در ثبت سامانه توان ایران پیرو نامه 13825 شرکت پترو ایران -انچام تغییرات در سایت توان ایران در تاریخ 00/07/18 -اعلام انصراف شرکت کوثر در تاریخ 00/06/22 ، -اعلام انصراف شرکت خدمات فنی آسماری 00/06/27 -اعلام انصراف شرکت سپنتا اهواز 00/07/26 - دریافت انصراف غیررسمی فولادنور، کالوپ لوله و سازه های فلزی نوین پارسیان جنوب
| 4 | مديريتي |  | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي | [6 empty] | 2021-10-03 | 13825 | 2021-12-08 | 206 | 4 | ارسال گزارش جامع سوم، بازدید از لوله سازی ها و نتیجه گیری در خصوص ناگزیر بودن پیمانکار به تامین لوله ها از خارج از کشور: - بازدید از لوله سازی اهواز در تاریخ 00/08/24 -بازدید از گروه صنعتی فولاد در تاریخ 00/08/25 -بازدید از لوله و نورد ساوه در تاریخ 00/09/09 -دریافت پیشنهاد از اسفراین در تاریخ 00/09/16 --دریافت توضیحات تکمیلی فولاد مبارکه در خصوص انحرافات از IPS-M-PI-190 ویرایش 4 --بازدید از فولاد مبارکه در تاریخ 00/09/23
| 5 | مديريتي |  | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي |  |  |  |  | 2021-12-20 | 327355 | 2021-12-22 | 20803 |  |  | 5 | تاکید کارفرما بر ادامه فرایند مذاکره با سازندگان داخلی و عدم نتیجه گیری به منظور سفارش گذاری (توضیح آنکه سازندگان داخلي توانمندي ساخت داخل لوله ها طبق مشخصات فني پروژه (مطابق با استاندارد IPS-M-PI-190-4) نداشتند و جلسات و مذاكرات متعددي جهت ايجاد انعطاف در معيارهاي سخت گيرانه در اين IPS با سازندگان، سازندگان متريال خام اوليه (فولاد مباركه اصفهان) و كارفرمايان برگزار گرديد و در نهايت از منظر ارزياب هاي اقتصادي و زمان تحويل سازندگان داخلي قادر به رقابت با سازندگان خارجي نشدند)
| 1 | مديريتي |  | ارسال گزارش جامع تامين لوله ها و درخواست خريد از خارج | [8 empty] | 2022-02-05 | 282 | 1 | ارسال گزارش جامع و درخواست خريد از خارج
| 2 | مديريتي |  | برگزاري جلسه اي جامع در تاريخ هاي 00/12/17 و 00/12/23 با نمايندگان وزارت صمت و تصميم بر خريد از خارج لوله هاي اصلي پروژه | [6 empty] | 2022-03-14 |  |  |  | 2 | برگزاري جلسه با نمايندگان صمت و تاييد خريد از خارج
| 3 | مديريتي |  | ارسال گزارش اصلاح شده تامين لوله ها پيرو جلسات برگزار شده با وزارت صمت و پيرو نامه 282 | [8 empty] | 2022-03-12 | 316 | 3 | ارسال گزارش جامع اصلاح شده جهت خريد از خارج
| 4 | مديريتي |  | پاسخ كارفرما به نامه 316 و اعلام نظر در خصوص استانداردهاي مورد استفاده براي خريد لوله ها (ويرايش سوم استاندارد 190) |  |  |  |  | 2022-03-29 | 5242 | 2022-04-03 | 205 |  |  | 4 | اعلام كارفرما مبني بر استفاده از ويرايش سوم استاندارد در گزارش
| 5 | مديريتي |  | ارسال پاسخ به كارفرما در مورد استاندارد ملاك عمل براي خريد لوله ها (استاندارد ويرايش چهارم قراردادي ولي از استاندارد ويرايش سوم در گزارش استفاده شده است) | [8 empty] | 2022-04-03 | 336 | 5 | پاسخ به كارفرما در خصوص گزارش
| 6 | مديريتي |  | دريافت پاسخ كارفرما و اعلام ضرورت استفاده از استاندارد ويرايش سوم |  |  |  |  | 2022-04-12 | 20729 | 2022-04-17 | 1575 |  |  | 6 | دريافت پاسخ كارفرما بر روي گزارش
| 7 | مديريتي |  | ارسال پاسخ به كارفرما در مورد استاندارد ملاك عمل براي خريد لوله ها (ضروت ابلاغ ويرايش سوم به صورت رسمي به دليل مغاير بودن با قرارداد) | [8 empty] | 2022-04-20 | 355 | 7 | پاسخ به كارفرما در خصوص گزارش
| 8 | مديريتي |  | دريافت پاسخ كارفرما بر روي نامه 355 و تاكيد بر روي استاندارد ويرايش سوم |  |  |  |  | 2022-05-09 | 52988 | 2022-05-14 | 3814 |  |  | 8 | پاسخ به كارفرما در خصوص گزارش
| 9 | مديريتي |  | دريافت پاسخ كارفرما بر روي نامه 316 و ارسال نامه ضميمه نمايندگان وزارت صمت و تغيير نقطه نظرات جهت خربد از داخل | [6 empty] | 2022-06-11 | 6001 |  |  | 9 | تغيير نظر وزارت صمت و ضرورت خريد از داخل
| 10 | مديريتي |  | تغيير در نمايندگان وزارت صمت و تاكيد مجدد بر تامين لوله ها از داخل و اعلام نارضايتي پيمانكار از تطويل5 ماهه در تصميم گيري در خصوص موضوع و درخواست تصميم گيري نهايي | [8 empty] | 2022-06-12 | 407 | 10 | درخواست كاهش كاري از SOW يا افزايش قيمت در صورت الزام خريد از داخل
مجوز نقشه برداري | 31 | اجرايي |  | تاخير در دريافت مجوز نقشه برداري هوايي |  |  |  |  | 2021-09-21 | 208118 | 2021-09-20 | 19846 | 2021-09-11 | 85 | 1 | معرفی گروه از طرف پیمانکار و درخواست کارفرما درخصوص اطلاعات تکمیلی
| 32 | اجرايي |  | تاخير در دريافت مجوز نقشه برداري هوايي | [6 empty] | 2021-11-15 | 17208 | 2021-09-25 | 108 | 2 | ارسال اطلاعات تکمیلی
| 33 | اجرايي |  | تاخير در دريافت مجوز نقشه برداري هوايي | [6 empty] | 2021-12-01 | 18860 | 2021-11-20 | 187 | 3 | دریافت مجوز نهایی
* كليه مستندات هر كدام از آيتم هاي تاخير مندرج در جدول شماره 3 در اين جدول مرتب و ارائه مي گردد.
| مهر و امضاء پیمانکار | [9 empty] | مهر و امضاء كارفرما
Formulas:
PEDCO Date = [NISOC Date]

## 4
2021-06-23 | 2022-12-20 |  |  |  | جدول شماره 4 : ليست علل تأخير پروژه |  |  |  |  | 2021-06-23 |  |  | 3 |  | 5 | 11 |  | 13 | 19 |  | 21 | 27 |  | 29 | 35 |  | 37 | 43 |  | 45 | 2021-12-23 | 183
| Code | كد | پایان | عنوان علل تاخيرات | شرح | دوره طبق واقعيت (در صورت عدم پايان موضوع در Cut-Off گزارش (01/09/30) تاريخ فرضي 01/09/29 به عنوان پايان در نظر گرفته شده است) |  |  | نوع علل |  |  |  | 0 |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5
| Code |  |  | عنوان علل تاخيرات |  | مدت (روز) | شروع | پايان |  | plan-Start |  | plan-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish
| F | F01 |  | تاخير در دريافت پيش پرداخت-قسط اول | تاخير در دريافت 2% پيش پرداخت با ضريب تاثير 0.9 | 75 | 2021-06-28 | 2021-09-03 12:00 | مالي | 2021-06-28 | 75 | 2021-09-11
|  | F02 |  | تاخير در دريافت پيش پرداخت-قسط دوم | تاخير در دريافت 3% پيش پرداخت با ضريب تاثير 0.9 | 164 | 2022-01-05 | 2022-06-01 14:24 | مالي | 2022-01-05 | 164 | 2022-06-18
BK-GCS-PEDCO-120-PR-PF-0001 | E | E01 | Process Flow Diagram (PFD) | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز از سوي كارفرما و بالتبع اثرات آن بر روی نهایی نشدن PFD ایستگاه گاز | 166 | 2021-06-23 | 2021-12-06 | فنی
BK-GCS-PEDCO-120-ME-DT-0031 | E | E03 | Mechanical Data Sheets For Gas Compressors Packages | عدم نهایی سازي ديتاشيت مكانيك پكيج هاي كمپرسور | تاخیر پیش نیازی | 313 | 2021-09-12 | 2022-07-22 | فنی | 2021-08-12 | 48 | 2021-09-29 | 2021-09-12 | 313 | 2022-07-22
BK-GCS-PEDCO-120-ME-TB-0001 | E | E04 | TBE For Gas Compressors | عدم نهايي سازي TBE كمپرسورها | تاخیر پیش نیازی | 170 | 2022-02-02 | 2022-07-22 | فنی | 2021-08-16 | 44 | 2021-09-29 | 2022-02-02 | 170 | 2022-07-22
BK-GCS-PEDCO-120-ME-MR-0001 | E | E05 | PMR For Gas Compressors | عدم نهايي سازي MR كمپرسورها | تاخیر پیش نیازی | 236 | 2021-11-28 | 2022-07-22 | فنی | 2021-09-03 | 10 | 2021-09-13 | 2021-11-28 | 236 | 2022-07-22
| P | P01 | Tendering & Selection For Gas Compressors | عدم انتخاب سازنده كمپرسورها | تاخیر پیش نیازی | 146 | 2022-02-26 | 2022-07-22 | کالا | 2021-08-11 | 59 | 2021-10-09 | 2022-02-26 | 146 | 2022-07-22
| P | P02 | Contract Effectiveness / PO For Gas Compressors | عدم عقد قرارداد براي تامين كمپرسورها | تاخیر پیش نیازی | 151 | 2022-07-22 | 2022-12-20 | کالا | 2021-10-10 | 29 | 2021-11-08 | 0 |  | 0
BK-GCS-PEDCO-120-ME-DT-0031 | E | E03 | Mechanical Data Sheets For Gas Compressors Packages | عدم نهایی سازي ديتاشيت مكانيك پكيج هاي كمپرسور | تاخير به دليل عدم تصميم گيري در خصوص Non-Lube يا Lube بودن سيلندر كمپرسورها | 464 | 2021-09-12 | 2022-12-20 | فنی | 2021-08-12 | 48 | 2021-09-29 | 2021-09-12 | 313 | 2022-07-22
BK-GCS-PEDCO-120-ME-TB-0001 | E | E04 | TBE For Gas Compressors | عدم نهايي سازي TBE كمپرسورها | تاخير در نهايي سازي پيش نيازي | 321 | 2022-02-02 | 2022-12-20 | فنی | 2021-08-16 | 44 | 2021-09-29 | 2022-02-02 | 170 | 2022-07-22
BK-GCS-PEDCO-120-ME-MR-0001 | E | E05 | PMR For Gas Compressors | عدم نهايي سازي MR كمپرسورها | تاخير در نهايي سازي پيش نيازي | 387 | 2021-11-28 | 2022-12-20 | فنی | 2021-09-03 | 10 | 2021-09-13 | 2021-11-28 | 236 | 2022-07-22
| P | P01 | Tendering & Selection For Gas Compressors | عدم انتخاب سازنده كمپرسورها | تاخير در نهايي سازي پيش نيازي | 297 | 2022-02-26 | 2022-12-20 | کالا | 2021-08-11 | 59 | 2021-10-09 | 2022-02-26 | 146 | 2022-07-22
BK-W018S-PEDCO-110-PR-PF-0001 | E | E06 | Process Flow Diagram - W018S | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 18 | عدم نهایی سازي اطلاعات فرآیندی چاه ها از سوي كارفرما و مطالعات خوردگي و بالتبع اثرات آن بر روی نهایی نشدن PFD و P&ID چاه ها- چاه 18 به عنوان نماينده چاه هاي دكل A اورده شده است | 112 | 2021-06-23 | 2021-10-13 | فنی | 2021-07-23 | 44 | 2021-09-05 | 2021-11-02 | 444 | 2023-01-20
BK-W028-PEDCO-110-PR-PF-0001 | E | E07 | Process Flow Diagram - W028 | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 28 | عدم نهایی سازي اطلاعات فرآیندی چاه ها از سوي كارفرما و مطالعات خوردگي و بالتبع اثرات آن بر روی نهایی نشدن PFD و P&ID چاه ها- چاه 28 به عنوان نماينده چاه هاي دكل B اورده شده است | 444 | 2021-11-02 | 2023-01-20 | فنی | 2021-07-23 | 39 | 2021-08-31 | 2021-11-02 | 444 | 2023-01-20
BK-SSGRL-PEDCO-110-PL-RT-0001 | E | E08 | Pipeline Corrosion Study & Material Selection Report-W018S | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 18 | تطويل در نهايي شدن فرآيند مطالعات خوردگي و منوط شدن نهايي شدن مدارك كليدي بخش فرايند ، مكانيك، ابزار دقيق و پايپينگ به مدرك مذكور-چاه 18 به عنوان نماينده كليه چاه هاي مربوط به دكل A اورده شده است | 215 | 2022-01-10 | 2022-08-13 | فنی
BK-SSGRL-PEDCO-110-PL-RT-0001 | E | E09 | Pipeline Corrosion Study & Material Selection Report - W028 | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 28 | تطويل در نهايي شدن فرآيند مطالعات خوردگي و منوط شدن نهايي شدن مدارك كليدي بخش فرايند ، مكانيك، ابزار دقيق و پايپينگ به مدرك مذكور-چاه 28 به عنوان نماينده كليه چاه هاي مربوط به دكل B اورده شده است | 215 | 2022-01-10 | 2022-08-13 | فنی
| P | P05 | Contract Effectiveness / PO- W018S-Line pipe | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریانی-چاه 18 | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي | 545 | 2021-06-23 | 2022-12-20 | کالا | 2021-10-08 | 4 | 2021-10-12 | 0 | 0 | 0
| P | P06 | Contract Effectiveness / PO- W028 - Line pipe | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریان-چاه 28 | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي | 545 | 2021-06-23 | 2022-12-20 | کالا | 2021-08-26 | 4 | 2021-08-30 | 0 | 0 | 0
| P | P07 | Manufacturing / Fabrication / Supply- W018S-Line pipe | عدم امکان آغاز ساخت لوله های جریانی-چاه 18 | تاخير در نهايي سازي پيش نيازي | 545 | 2021-06-23 | 2022-12-20 | کالا | 2021-10-13 | 69 | 2021-12-21 | 0 | 0 | 0
| P | P08 | Manufacturing / Fabrication / Supply- W028 - Line pipe | عدم امکان آغاز ساخت لوله های جریانی-چاه 28 | تاخير در نهايي سازي پيش نيازي | 545 | 2021-06-23 | 2022-12-20 | کالا | 2021-08-31 | 109 | 2021-12-18 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-SP-0001 | E | E14 | Specification For WHCP/HPU-W018S | تطويل در نهايي سازي Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | به دليل عدم دريافت اطلاعات شيرهاي سرچاهي از بخش حفاري كارفرما | 260 | 2021-08-08 | 2022-04-25 | فنی | 2021-07-23 | 37 | 2021-08-29 | 2021-08-08 | 231 | 2022-03-27
BK-W018S-PEDCO-110-IN-MR-0001 | E | E18 | PMR For WHCP/HPU - W018S | تطويل در نهايي سازي MR برای WHCP-چاه 18 | تاخير در نهايي سازي پيش نيازي | 431 | 2021-11-15 | 2023-01-20 | فنی | 2021-08-30 | 6 | 2021-09-05 | 2021-11-15 | 431 | 2023-01-20
BK-W028-PEDCO-110-IN-MR-0001 | E | E19 | PMR For WHCP/HPU - W028 | تطويل در نهايي سازي MR برای WHCP-چاه 28 | تاخير در نهايي سازي پيش نيازي | 431 | 2021-11-15 | 2023-01-20 | فنی | 2021-09-01 | 9 | 2021-09-10 | 2021-11-15 | 431 | 2023-01-20
| P | P09 | Tendering & Selection- W018S-WHCP | تطويل در نهايي سازي انتخاب سازنده برای WHCP-چاه 18 | تاخير در نهايي سازي پيش نيازي | 22 | 2022-03-15 | 2022-04-06 | کالا | 2021-09-23 | 9 | 2021-10-02 | 2022-03-15 | 71 | 2022-05-25
| P | P10 | Tendering & Selection- W028 - WHCP | تطويل در نهايي سازي انتخاب سازنده برای WHCP-چاه 28 | تاخير در نهايي سازي پيش نيازي | 22 | 2022-03-15 | 2022-04-06 | کالا | 2021-09-23 | 9 | 2021-10-02 | 2022-03-15 | 71 | 2022-05-25
| P | P11 | Contract Effectiveness / PO- W018S- WHCP | تطويل در نهايي سازي عقد قرارداد با سازنده برای WHCP-چاه 18 | تاخير در نهايي سازي پيش نيازي | 45 | 2022-05-29 | 2022-07-13 | کالا | 2021-10-03 | 4 | 2021-10-07 | 2022-05-29 | 14 | 2022-06-12
| P | P12 | Contract Effectiveness / PO- W028 - WHCP | تطويل در نهايي سازي عقد قرارداد با سازنده برای WHCP-چاه 28 | تاخير در نهايي سازي پيش نيازي | 45 | 2022-05-29 | 2022-07-13 | کالا | 2021-10-03 | 4 | 2021-10-07 | 2022-05-29 | 14 | 2022-06-12
BK-W018S-PEDCO-110-CV-PY-0001 | E | E20 | General Civil Layout - W018S | تطويل در نهايي سازي طرح مديريت پسماند چاه 18 | تطويل در نهايي سازي طرح مديريت پسماند چاه 18 و بالتبع عدم نهايي سازي مدارك Civil سرچاهي-چاه 18 به عنوان نماينده چاه هاي دكل A اورده شده است | 152 | 2021-07-28 | 2021-12-27 | فنی | 2021-08-12 | 19 | 2021-08-31 | 2021-07-28 | 152 | 2021-12-27
BK-W028-PEDCO-110-CV-PY-0001 | E | E23 | General Civil Layout -W028 | تطويل در نهايي سازي طرح مديريت پسماند چاه 28 | تطويل در نهايي سازي طرح مديريت پسماند چاه 28 و بالتبع عدم نهايي سازي مدارك Civil سرچاهي | 132 | 2021-10-19 | 2022-02-28 | فنی | 2021-07-23 | 24 | 2021-08-16 | 2021-10-19 | 458 | 2023-01-20
BK-BK14-PEDCO-110-CV-PY-0001 | E | E26 | General Civil Layout - BK14 | ارسال طرح جدید مدیریت پسماند بسته موقعیت چاه BK14 | عدم تعیین تکلیف طرح مديريت پسماند چاه 14 و بالتبع عدم نهايي سازي مدارك Civil سرچاهي | 47 | 2022-09-19 | 2022-11-05 | فنی |  |  |  | 2022-09-19
| C | C03 |  | تاخير در دريافت مجوزها | تاخير در دريافت مجوز نقشه برداري هوايي | 70 | 2021-09-11 | 2021-11-20 | اجرايي | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
BK-GNRAL-PEDCO-000-PM-RT-0001 | M | M01 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Endorsement Report For Basic Design & Scope of Work | 47 |  |  | مديريتي |  |  |  | 2021-08-14 | 24 | 2021-09-07 | 2021-10-03 | 23 | 2021-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-GCS-PEDCO-120-PR-PF-0001 |  | M02 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Process Flow Diagram (PFD) | 108 |  |  | مديريتي |  |  |  | 2021-08-28 | 9 | 2021-09-06 | 2021-10-31 | 14 | 2021-11-14 | 2021-12-14 | 19 | 2022-01-02 | 2022-01-22 | 31 | 2022-02-22 | 2022-03-26 | 35 | 2022-04-30 | 0 | 0 | 0
BK-GCS-PEDCO-120-ME-DT-0031 |  | M04 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Mechanical Data Sheets For Gas Compressors Packages | 76 |  |  | مديريتي |  |  |  | 2021-09-26 | 15 | 2021-10-11 | 2021-10-31 | 8 | 2021-11-08 | 2021-11-28 | 22 | 2021-12-20 | 2022-01-26 | 27 | 2022-02-22 | 2022-03-19 | 7 | 2022-03-26 | 2022-05-04 | -3 | 2022-05-01
BK-W018S-PEDCO-110-PI-PY-0001 |  | M08 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Plot Plan Drawing - W018S | 56 |  |  | مديريتي |  |  |  | 2021-09-05 | 24 | 2021-09-29 | 2021-11-29 | 13 | 2021-12-12 | 2022-02-14 | 19 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-PR-PI-0001 |  | M11 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | P&ID - W018S | 79 |  |  | مديريتي |  |  |  | 2021-08-23 | 14 | 2021-09-06 | 2021-11-15 | 12 | 2021-11-27 | 2021-12-29 | 5 | 2022-01-03 | 2022-03-14 | 48 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-IN-MR-0001 |  | M17 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | PMR For WHCP/HPU - W018S | 53 |  |  | مديريتي |  |  |  | 2021-11-29 | 8 | 2021-12-07 | 2022-01-30 | 2 | 2022-02-01 | 2022-07-04 | 43 | 2022-08-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-PI-DW-0001 |  | M20 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Plot Plan Drawing - W028 | 68 |  |  | مديريتي |  |  |  | 2022-02-16 | 68 | 2022-04-25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-PR-PI-0001 |  | M26 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | P&ID - W028 | 68 |  |  | مديريتي |  |  |  | 2021-09-05 | 3 | 2021-09-08 | 2021-11-15 | 12 | 2021-11-27 | 2021-12-29 | 5 | 2022-01-03 | 2022-03-14 | 48 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-IN-MR-0001 |  | M29 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | PMR For WHCP/HPU - W028 | 10 |  |  | مديريتي |  |  |  | 2021-11-29 | 8 | 2021-12-07 | 2022-01-30 | 2 | 2022-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-PI-SP-0001 |  | M30 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Piping Material Specification | 61 |  |  | مديريتي |  |  |  | 2021-12-12 | 14 | 2021-12-26 | 2022-04-13 | 47 | 2022-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-GCS-PEDCO-120-PR-DT-0030 |  | M03 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Process Data Sheets For Gas Compressors Packages | 20 |  |  | مديريتي |  |  |  | 2021-11-21 | 6 | 2021-11-27 | 2022-01-15 | 14 | 2022-01-29 | 2022-04-09 | 29 | 2022-05-08 | 2022-08-20 | -29 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0
BK-GCS-PEDCO-120-ME-TB-0001 |  | M05 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | TBE For Gas Compressors | 62 |  |  | مديريتي |  |  |  | 2022-02-16 | 11 | 2022-02-27 | 2022-03-19 | 49 | 2022-05-07 | 2022-06-25 | 2 | 2022-06-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-GCS-PEDCO-120-ME-MR-0001 |  | M06 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | PMR For Gas Compressors | 68 |  |  | مديريتي |  |  |  | 2021-12-12 | 3 | 2021-12-15 | 2022-01-18 | 12 | 2022-01-30 | 2022-02-27 | 6 | 2022-03-05 | 2022-06-20 | 47 | 2022-08-06 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-PR-PF-0001 |  | M07 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Process Flow Diagram - W018S | 189 |  |  | مديريتي |  |  |  | 2021-08-18 | 20 | 2021-09-07 | 2021-11-16 | 202 | 2022-06-06 | 2022-08-24 | -33 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-SP-0001 |  | M09 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Specification For WHCP/HPU | 114 |  |  | مديريتي |  |  |  | 2021-08-22 | 23 | 2021-09-14 | 2021-10-24 | 70 | 2022-01-02 | 2022-01-24 | 6 | 2022-01-30 | 2022-04-10 | 15 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0
BK-GNRAL-PEDCO-000-PI-SP-0017 |  | M12 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Specification For Piping Cleaning and Flushing | 233 |  |  | مديريتي |  |  |  | 2021-09-07 | 7 | 2021-09-14 | 2021-10-18 | 21 | 2021-11-08 | 2021-12-29 | 205 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-DT-0001 |  | M13 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Data Sheets For WHCP/HPU - Wellheads | 43 |  |  | مديريتي |  |  |  | 2021-09-05 | 15 | 2021-09-20 | 2021-11-23 | 4 | 2021-11-27 | 2022-01-04 | 4 | 2022-01-08 | 2022-07-02 | 20 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-CV-PY-0002 |  | M14 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Civil and Structural drawings - W018S | -134 |  |  | مديريتي |  |  |  | 2021-08-11 | -4 | 2021-08-07 | 2022-01-18 | -7 | 2022-01-11 | 2022-11-22 | -123 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-PL-RT-0001 |  | M16 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Pipeline Corrosion Study & Material Selection Report | 29 |  |  | مديريتي |  |  |  | 2021-11-10 | 11 | 2021-11-21 | 2021-12-18 |  | 0 | 2022-03-14 | 18 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-SP-0001 |  | M21 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Specification For WHCP/HPU | 114 |  |  | مديريتي |  |  |  | 2021-08-22 | 23 | 2021-09-14 | 2021-10-24 | 70 | 2022-01-02 | 2022-01-24 | 6 | 2022-01-30 | 2022-04-10 | 15 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-CV-PY-0001 |  | M22 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | General Civil Layout -W028 | 15 |  |  | مديريتي |  |  |  | 2021-11-02 | 20 | 2021-11-22 | 2022-03-26 | -1 | 2022-03-25 | 2022-06-15 | -4 | 2022-06-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-CV-PY-0002 |  | M23 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Civil and Structural drawings -W028 | 30 |  |  | مديريتي |  |  |  | 2021-11-02 | 25 | 2021-11-27 | 2021-12-04 | -3 | 2021-12-01 | 2022-03-28 | 6 | 2022-04-03 | 2022-06-21 | 4 | 2022-06-25 | 2022-07-02 | -3 | 2022-06-29 | 2022-07-31 | 1 | 2022-08-01
BK-W028-PEDCO-110-CV-DW-0001 |  | M24 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Rough Grading Plans -W028 | 80 |  |  | مديريتي |  |  |  | 2021-10-25 | -7 | 2021-10-18 | 2022-02-20 | -8 | 2022-02-12 | 2022-03-28 | 6 | 2022-04-03 | 2022-04-24 | 89 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-DT-0001 |  | M27 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Data Sheets For WHCP/HPU - Wellheads | 43 |  |  | مديريتي |  |  |  | 2021-09-05 | 15 | 2021-09-20 | 2021-11-23 | 4 | 2021-11-27 | 2022-01-04 | 4 | 2022-01-08 | 2022-07-02 | 20 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-PL-RT-0001 |  | M28 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Pipeline Corrosion Study & Material Selection Report | 108 |  |  | مديريتي |  |  |  | 2021-11-10 | 11 | 2021-11-21 | 2021-12-18 | 79 | 2022-03-07 | 2022-03-14 | 18 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-PI-SP-0001 |  | M30 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | Piping Material Specification | 61 |  |  | مديريتي |  |  |  | 2021-12-12 | 14 | 2021-12-26 | 2022-04-13 | 47 | 2022-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-BK14-PEDCO-110-CV-PY-0001 |  | M30 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | General Civil Layout - BK14 | 4 |  |  | مديريتي |  |  |  | 2022-10-03 | -1 | 2022-10-02 | 2022-10-25 | 5 | 2022-10-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on P56: md: تاريخ فرضي
Note on S59: md: تاريخ فرضي
Note on V48: md: تاريخ فرضي
Note on V50: md: تاريخ فرضي
Note on V52: md: تاريخ فرضي
Note on Y45: md: تاريخ فرضي
Note on Y51: md: تاريخ فرضي
Note on Y56: md: تاريخ فرضي
Note on Y57: md: تاريخ فرضي
Note on Y58: md: تاريخ فرضي

## S&F (hidden)
Description | Doc. No. |  | Actual Start Date | Actual Finish Date
Procurement & Services Contracting Plan | BK-GNRAL-HD-000-PM-CG-0001 | BK-GNRAL-HD-000-PM-CG-0001Procurement & Services Contracting Plan | 2022-05-29 | 2022-12-20
Master Document List (MDL) & Updating | BK-GNRAL-PEDCO-000-GE-DN-0001 | BK-GNRAL-PEDCO-000-GE-DN-0001Master Document List (MDL) & Updating | 2021-07-07 | 2022-12-20
EPC HSE Plan | BK-GNRAL-HD-000-PM-HP-0001 | BK-GNRAL-HD-000-PM-HP-0001EPC HSE Plan | 2021-07-28 | 2022-05-22
Project Emergency Response Plan (ERP) | BK-GNRAL-HD-000-PM-HP-0002 | BK-GNRAL-HD-000-PM-HP-0002Project Emergency Response Plan (ERP) | 2022-02-12 | 2022-06-01
Guideline on Permit To Work System(PTWS) | BK-GNRAL-HD-000-PM-HP-0003 | BK-GNRAL-HD-000-PM-HP-0003Guideline on Permit To Work System(PTWS) | 2021-12-01 | 0
HSE Operation Control Procedure | BK-GNRAL-HD-000-PM-HP-0004 | BK-GNRAL-HD-000-PM-HP-0004HSE Operation Control Procedure | 2022-07-26 | 2022-12-20
Environmental Management Plan (EMP) | BK-GNRAL-HD-000-PM-HP-0005 | BK-GNRAL-HD-000-PM-HP-0005Environmental Management Plan (EMP) | 2022-02-21 | 2022-05-10
Detailed Schedule & Updating | BK-GNRAL-HD-000-PM-SH-0001 | BK-GNRAL-HD-000-PM-SH-0001Detailed Schedule & Updating | 2021-12-08 | 2022-07-16
Work Breakdown Structure (WBS) | BK-GNRAL-HD-000-PM-WB-0001 | BK-GNRAL-HD-000-PM-WB-0001Work Breakdown Structure (WBS) | 2021-11-16 | 2022-02-02
Cost Breakdown Structure (CBS) | BK-GNRAL-HD-000-PM-WB-0002 | BK-GNRAL-HD-000-PM-WB-0002Cost Breakdown Structure (CBS) | 2021-11-16 | 2022-02-02
Material Equipment & Control Index (MCI) | BK-GNRAL-HD-000-PM-FO-0001 | BK-GNRAL-HD-000-PM-FO-0001Material Equipment & Control Index (MCI) | 2022-08-28 | 2022-12-20
Progress S-curves & Updating | BK-GNRAL-HD-000-PM-PG-0001 | BK-GNRAL-HD-000-PM-PG-0001Progress S-curves & Updating | 2022-02-20 | 2022-12-20
Production Capacity Realization Plan | BK-GNRAL-PEDCO-000-PM-PS-0001 | BK-GNRAL-PEDCO-000-PM-PS-0001Production Capacity Realization Plan | 0 | 0
Cash Flow Plan | BK-GNRAL-HD-000-PM-CP-0001 | BK-GNRAL-HD-000-PM-CP-0001Cash Flow Plan | 2022-09-18 | 0
Quality Plan | BK-GNRAL-PEDCO-000-PM-QP-0001 | BK-GNRAL-PEDCO-000-PM-QP-0001Quality Plan | 0 | 0
Project Organization Charts | BK-GNRAL-HD-000-PM-CH-0001 | BK-GNRAL-HD-000-PM-CH-0001Project Organization Charts | 2022-07-11 | 2021-05-24
Specification for Medical Services | BK-GNRAL-HD-000-PM-SP-0001 | BK-GNRAL-HD-000-PM-SP-0001Specification for Medical Services | 0 | 0
Project Coordination Procedure | BK-GNRAL-HD-000-PM-PR-0001 | BK-GNRAL-HD-000-PM-PR-0001Project Coordination Procedure | 2021-07-11 | 2022-06-01
Project Control Procedure (WBS, PMS,Invoicing) | BK-GNRAL-HD-000-PM-PR-0002 | BK-GNRAL-HD-000-PM-PR-0002Project Control Procedure (WBS, PMS,Invoicing) | 2021-07-24 | 0
Progress Measurement Procedure | BK-GNRAL-HD-000-PM-PR-0014 | BK-GNRAL-HD-000-PM-PR-0014Progress Measurement Procedure | 2021-11-20 | 2022-12-20
Document Numbering Procedure | BK-GNRAL-HD-000-PM-PR-0003 | BK-GNRAL-HD-000-PM-PR-0003Document Numbering Procedure | 2022-07-11 | 2021-05-24
Change Control Procedure | BK-GNRAL-HD-000-PM-PR-0004 | BK-GNRAL-HD-000-PM-PR-0004Change Control Procedure | 2021-07-24 | 2022-12-20
Invoicing Procedure | BK-GNRAL-HD-000-PM-PR-0005 | BK-GNRAL-HD-000-PM-PR-0005Invoicing Procedure | 2021-12-07 | 2022-12-20
Correspondence Procedure | BK-GNRAL-HD-000-PM-PR-0006 | BK-GNRAL-HD-000-PM-PR-0006Correspondence Procedure | 2022-07-11 | 2021-05-24
Meeting Procedure | BK-GNRAL-HD-000-PM-PR-0007 | BK-GNRAL-HD-000-PM-PR-0007Meeting Procedure | 2022-07-11 | 2021-05-24
Reporting Procedure | BK-GNRAL-HD-000-PM-PR-0008 | BK-GNRAL-HD-000-PM-PR-0008Reporting Procedure | 2022-07-11 | 2021-05-24
Procurement & Services Contracting Procedure | BK-GNRAL-HD-000-PM-PR-0009 | BK-GNRAL-HD-000-PM-PR-0009Procurement & Services Contracting Procedure | 2021-11-22 | 2021-12-29
Eng. Document Control Procedure | BK-GNRAL-HD-000-PM-PR-0010 | BK-GNRAL-HD-000-PM-PR-0010Eng. Document Control Procedure | 2022-07-11 | 2021-05-24
Material Control Procedure | BK-GNRAL-HD-000-PM-PR-0011 | BK-GNRAL-HD-000-PM-PR-0011Material Control Procedure | 2022-08-28 | 2022-12-20
Completion & Handover Procedure | BK-GNRAL-HD-000-PM-PR-0012 | BK-GNRAL-HD-000-PM-PR-0012Completion & Handover Procedure | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0001 | BK-GNRAL-HD-000-GE-RT-0001Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0002 | BK-GNRAL-HD-000-GE-RT-0002Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0003 | BK-GNRAL-HD-000-GE-RT-0003Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0004 | BK-GNRAL-HD-000-GE-RT-0004Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0005 | BK-GNRAL-HD-000-GE-RT-0005Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0006 | BK-GNRAL-HD-000-GE-RT-0006Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0007 | BK-GNRAL-HD-000-GE-RT-0007Monthly Progress Report | 2022-01-11 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0008 | BK-GNRAL-HD-000-GE-RT-0008Monthly Progress Report | 2022-02-13 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0009 | BK-GNRAL-HD-000-GE-RT-0009Monthly Progress Report | 2022-03-13 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0010 | BK-GNRAL-HD-000-GE-RT-0010Monthly Progress Report | 2022-04-11 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0011 | BK-GNRAL-HD-000-GE-RT-0011Monthly Progress Report | 2022-05-14 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0012 | BK-GNRAL-HD-000-GE-RT-0012Monthly Progress Report | 2022-06-12 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0013 | BK-GNRAL-HD-000-GE-RT-0013Monthly Progress Report | 2022-07-20 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0014 | BK-GNRAL-HD-000-GE-RT-0014Monthly Progress Report | 2022-08-15 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0015 | BK-GNRAL-HD-000-GE-RT-0015Monthly Progress Report | 2022-09-14 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0016 | BK-GNRAL-HD-000-GE-RT-0016Monthly Progress Report | 2022-10-16 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0017 | BK-GNRAL-HD-000-GE-RT-0017Monthly Progress Report | 2022-11-15 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0018 | BK-GNRAL-HD-000-GE-RT-0018Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0019 | BK-GNRAL-HD-000-GE-RT-0019Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0020 | BK-GNRAL-HD-000-GE-RT-0020Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0021 | BK-GNRAL-HD-000-GE-RT-0021Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0022 | BK-GNRAL-HD-000-GE-RT-0022Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0023 | BK-GNRAL-HD-000-GE-RT-0023Monthly Progress Report | 0 | 0
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0024 | BK-GNRAL-HD-000-GE-RT-0024Monthly Progress Report | 0 | 0
Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0050 | BK-GNRAL-HD-000-GE-RT-0050Delay Analysis Report | 2022-06-19 | 0
Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0051 | BK-GNRAL-HD-000-GE-RT-0051Delay Analysis Report | 2022-09-07 | 0
Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0052 | BK-GNRAL-HD-000-GE-RT-0052Delay Analysis Report | 0 | 0
Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0053 | BK-GNRAL-HD-000-GE-RT-0053Delay Analysis Report | 0 | 0
Plumbing & Sewage Piping Layout | BK-GNRAL-PEDCO-220-HV-PY-0001 | BK-GNRAL-PEDCO-220-HV-PY-0001Plumbing & Sewage Piping Layout | 2022-05-21 | 2022-12-20
HVAC System Layout | BK-GNRAL-PEDCO-220-HV-PY-0002 | BK-GNRAL-PEDCO-220-HV-PY-0002HVAC System Layout | 2022-05-14 | 2022-12-20
HVAC Equipment Schedule | BK-GNRAL-PEDCO-220-HV-LI-0001 | BK-GNRAL-PEDCO-220-HV-LI-0001 HVAC Equipment Schedule | 0 | 0
Safety & Fire Fighting Equipment Location Layout | BK-GNRAL-PEDCO-220-SA-PY-0001 | BK-GNRAL-PEDCO-220-SA-PY-0001Safety & Fire Fighting Equipment Location Layout | 2022-02-02 | 2022-12-20
Lighting & Small Power Layout For Camp Area | BK-GNRAL-PEDCO-220-EL-PY-0001 | BK-GNRAL-PEDCO-220-EL-PY-0001Lighting & Small Power Layout For Camp Area | 2022-01-04 | 2022-12-20
Earthing & Lightning Layout For Camp Area | BK-GNRAL-PEDCO-220-EL-PY-0002 | BK-GNRAL-PEDCO-220-EL-PY-0002Earthing & Lightning Layout For Camp Area | 2022-05-29 | 2022-12-20
Cable Route for For Camp Area | BK-GNRAL-PEDCO-220-EL-DW-0001 | BK-GNRAL-PEDCO-220-EL-DW-0001Cable Route for For Camp Area | 2022-01-04 | 2022-12-20
Electrical Load List | BK-GNRAL-PEDCO-220-EL-LI-0001 | BK-GNRAL-PEDCO-220-EL-LI-0001Electrical Load List | 2022-05-18 | 2022-12-20
Architectural Drawing For NISOC Office Building | BK-GNRAL-PEDCO-220-AR-DW-0001 | BK-GNRAL-PEDCO-220-AR-DW-0001Architectural Drawing For NISOC Office Building | 2021-07-24 | 2022-03-12
Architectural Drawing For NISOC Residental Building | BK-GNRAL-PEDCO-220-AR-DW-0002 | BK-GNRAL-PEDCO-220-AR-DW-0002Architectural Drawing For NISOC Residental Building | 2021-10-13 | 2022-05-11
Architectural Drawing For Petro Iran Office Building | BK-GNRAL-PEDCO-220-AR-DW-0003 | BK-GNRAL-PEDCO-220-AR-DW-0003Architectural Drawing For Petro Iran Office Building | 2021-06-28 | 2022-12-20
Architectural Drawing For Petro Iran Residental Building | BK-GNRAL-PEDCO-220-AR-DW-0007 | BK-GNRAL-PEDCO-220-AR-DW-0007Architectural Drawing For Petro Iran Residental Building | 2021-06-28 | 2022-12-20
Architectural Drawing For Petro Iran/Contractor Restaurant | BK-GNRAL-PEDCO-220-AR-DW-0004 | BK-GNRAL-PEDCO-220-AR-DW-0004Architectural Drawing For Petro Iran/Contractor Restaurant | 2021-08-22 | 2022-12-20
Architectural Drawing For Warehouse of Site Mobilization | BK-GNRAL-PEDCO-220-AR-DW-0005 | BK-GNRAL-PEDCO-220-AR-DW-0005Architectural Drawing For Warehouse of Site Mobilization | 2021-08-22 | 2022-02-02
Architectural Drawing For Drivers Rest Room | BK-GNRAL-PEDCO-220-AR-DW-0006 | BK-GNRAL-PEDCO-220-AR-DW-0006Architectural Drawing For Drivers Rest Room | 2021-06-28 | 2022-03-02
Overall Layout for Camp Area | BK-GNRAL-PEDCO-220-CV-PY-0001 | BK-GNRAL-PEDCO-220-CV-PY-0001Overall Layout for Camp Area | 2021-07-24 | 2022-12-20
Rough Grading Plan For Camp Area | BK-GNRAL-PEDCO-220-CV-DW-0001 | BK-GNRAL-PEDCO-220-CV-DW-0001Rough Grading Plan For Camp Area | 2021-09-20 | 2022-12-20
Foundation Location Drawing For Camp Area | BK-GNRAL-PEDCO-220-ST-DW-0001 | BK-GNRAL-PEDCO-220-ST-DW-0001Foundation Location Drawing For Camp Area | 2022-02-12 | 2022-12-20
Structural Drawing For NISOC Residental Building | BK-GNRAL-PEDCO-220-ST-DW-0002 | BK-GNRAL-PEDCO-220-ST-DW-0002Structural Drawing For NISOC Residental Building | 2021-11-10 | 2022-05-15
Structural Drawing For Warehouse | BK-GNRAL-PEDCO-220-ST-DW-0003 | BK-GNRAL-PEDCO-220-ST-DW-0003Structural Drawing For Warehouse | 2021-11-10 | 2022-12-20
Endorsement Report For Basic Design & Scope of Work | BK-GNRAL-PEDCO-000-PM-RT-0001 | BK-GNRAL-PEDCO-000-PM-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2022-12-20
Process Design Criteria | BK-GNRAL-PEDCO-000-PR-DC-0001 | BK-GNRAL-PEDCO-000-PR-DC-0001Process Design Criteria | 2021-07-27 | 2022-01-01
Process Basis Of Design | BK-GNRAL-PEDCO-000-PR-DB-0001 | BK-GNRAL-PEDCO-000-PR-DB-0001Process Basis Of Design | 2021-07-27 | 2022-12-20
Drainage Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0001 | BK-GNRAL-PEDCO-000-PR-PH-0001Drainage Philosophy | 2021-07-27 | 2022-12-20
Control Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0002 | BK-GNRAL-PEDCO-000-PR-PH-0002Control Philosophy | 2021-07-27 | 2022-12-20
Flare,Blow Down And Relief Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0003 | BK-GNRAL-PEDCO-000-PR-PH-0003Flare,Blow Down And Relief Philosophy | 2021-07-27 | 2022-12-20
Isolation Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0004 | BK-GNRAL-PEDCO-000-PR-PH-0004Isolation Philosophy | 2021-07-27 | 2022-12-20
ESD Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0005 | BK-GNRAL-PEDCO-000-PR-PH-0005ESD Philosophy | 2021-07-27 | 2022-12-20
Symbol & Legend For PFD and P&ID | BK-GNRAL-PEDCO-000-PR-PI-0001 | BK-GNRAL-PEDCO-000-PR-PI-0001Symbol & Legend For PFD and P&ID | 2021-08-04 | 2022-12-20
Mechanical Design Criteria | BK-GNRAL-PEDCO-000-ME-DC-0001 | BK-GNRAL-PEDCO-000-ME-DC-0001Mechanical Design Criteria | 2021-07-28 | 2022-12-20
Specification For Pressure Vessels | BK-GNRAL-PEDCO-000-ME-SP-0001 | BK-GNRAL-PEDCO-000-ME-SP-0001Specification For Pressure Vessels | 2021-07-28 | 2022-12-20
Specification For Atmospheric Above Ground Welded Steel Tanks | BK-GNRAL-PEDCO-000-ME-SP-0002 | BK-GNRAL-PEDCO-000-ME-SP-0002Specification For Atmospheric Above Ground Welded Steel Tanks | 2021-07-28 | 2022-12-20
Standard Detail Drawing For Pressure Vessels and Heat Exchangers | BK-GNRAL-PEDCO-000-ME-DW-0001 | BK-GNRAL-PEDCO-000-ME-DW-0001Standard Detail Drawing For Pressure Vessels and Heat Exchangers | 2021-07-28 | 0
Standard Detail Drawing For Storage Tanks | BK-GNRAL-PEDCO-000-ME-DW-0002 | BK-GNRAL-PEDCO-000-ME-DW-0002Standard Detail Drawing For Storage Tanks | 2021-07-28 | 0
HVAC & Plumbing Design Criteria | BK-GNRAL-PEDCO-000-HV-DC-0001 | BK-GNRAL-PEDCO-000-HV-DC-0001HVAC & Plumbing Design Criteria | 2021-07-24 | 2022-12-20
Specification For HVAC Equipment | BK-GNRAL-PEDCO-000-HV-SP-0001 | BK-GNRAL-PEDCO-000-HV-SP-0001Specification For HVAC Equipment | 2021-07-24 | 2021-10-10
Specification For Duct Work & Pipe Work | BK-GNRAL-PEDCO-000-HV-SP-0002 | BK-GNRAL-PEDCO-000-HV-SP-0002Specification For Duct Work & Pipe Work | 2021-07-24 | 2021-10-10
Standard Drawing For HVAC & Plumbing | BK-GNRAL-PEDCO-000-HV-DW-0001 | BK-GNRAL-PEDCO-000-HV-DW-0001Standard Drawing For HVAC & Plumbing | 2021-07-24 | 0
Symbol & Legend For HVAC & Plumbing | BK-GNRAL-PEDCO-000-HV-DW-0002 | BK-GNRAL-PEDCO-000-HV-DW-0002Symbol & Legend For HVAC & Plumbing | 2021-08-22 | 2022-09-05
Piping Design Criteria | BK-GNRAL-PEDCO-000-PI-DC-0001 | BK-GNRAL-PEDCO-000-PI-DC-0001Piping Design Criteria | 2021-07-24 | 2022-01-16
Specification For Color Coding and Marking | BK-GNRAL-PEDCO-000-PI-SP-0001 | BK-GNRAL-PEDCO-000-PI-SP-0001Specification For Color Coding and Marking | 2021-08-09 | 2022-12-20
Specification For Transportation, Handling, Storage of pipes | BK-GNRAL-PEDCO-000-PI-SP-0002 | BK-GNRAL-PEDCO-000-PI-SP-0002Specification For Transportation, Handling, Storage of pipes | 2021-12-12 | 2022-12-20
Specification For the Design of Piping in Mechanical Packages | BK-GNRAL-PEDCO-000-PI-SP-0003 | BK-GNRAL-PEDCO-000-PI-SP-0003Specification For the Design of Piping in Mechanical Packages | 2021-08-09 | 2022-12-20
Specification For Metallic Pipes | BK-GNRAL-PEDCO-000-PI-SP-0004 | BK-GNRAL-PEDCO-000-PI-SP-0004Specification For Metallic Pipes | 2021-07-24 | 2022-12-20
Specification For Fittings, Flanges, Gaskets and Bolts | BK-GNRAL-PEDCO-000-PI-SP-0005 | BK-GNRAL-PEDCO-000-PI-SP-0005Specification For Fittings, Flanges, Gaskets and Bolts | 2021-07-24 | 2021-11-07
Specification For Painting | BK-GNRAL-PEDCO-000-PI-SP-0006 | BK-GNRAL-PEDCO-000-PI-SP-0006Specification For Painting | 2021-07-24 | 2022-01-04
Specification For Lining (Internal Protection of Equipment by Painting) | BK-GNRAL-PEDCO-000-PI-SP-0007 | BK-GNRAL-PEDCO-000-PI-SP-0007Specification For Lining (Internal Protection of Equipment by Painting) | 2021-08-09 | 2022-12-20
Specification For Material Requirements in Sour service | BK-GNRAL-PEDCO-000-PI-SP-0008 | BK-GNRAL-PEDCO-000-PI-SP-0008Specification For Material Requirements in Sour service | 2021-08-09 | 2022-12-20
Specification For Manual Valves | BK-GNRAL-PEDCO-000-PI-SP-0009 | BK-GNRAL-PEDCO-000-PI-SP-0009Specification For Manual Valves | 2021-08-09 | 2022-12-20
Specification For Plant Piping Systems Pressure Testing | BK-GNRAL-PEDCO-000-PI-SP-0010 | BK-GNRAL-PEDCO-000-PI-SP-0010Specification For Plant Piping Systems Pressure Testing | 2021-08-09 | 2022-12-20
Specification For Welding of Plant Piping System | BK-GNRAL-PEDCO-000-PI-SP-0011 | BK-GNRAL-PEDCO-000-PI-SP-0011Specification For Welding of Plant Piping System | 2021-08-09 | 2022-12-20
Specification For Flexibility Analysis | BK-GNRAL-PEDCO-000-PI-SP-0012 | BK-GNRAL-PEDCO-000-PI-SP-0012Specification For Flexibility Analysis | 2021-08-09 | 2022-12-20
Specification For Coating Of Underground Piping | BK-GNRAL-PEDCO-000-PI-SP-0013 | BK-GNRAL-PEDCO-000-PI-SP-0013Specification For Coating Of Underground Piping | 2021-07-24 | 2022-02-23
Specification For Pipe Support | BK-GNRAL-PEDCO-000-PI-SP-0014 | BK-GNRAL-PEDCO-000-PI-SP-0014Specification For Pipe Support | 2021-08-09 | 2022-12-20
Specification For Piping Construction, Fabrication & Erection | BK-GNRAL-PEDCO-000-PI-SP-0015 | BK-GNRAL-PEDCO-000-PI-SP-0015Specification For Piping Construction, Fabrication & Erection | 2021-08-09 | 2022-12-20
Specification For Piping Design & Plant Layout | BK-GNRAL-PEDCO-000-PI-SP-0016 | BK-GNRAL-PEDCO-000-PI-SP-0016Specification For Piping Design & Plant Layout | 2021-08-09 | 2022-12-20
Specification For Cleaning and Flushing | BK-GNRAL-PEDCO-000-PI-SP-0017 | BK-GNRAL-PEDCO-000-PI-SP-0017Specification For Cleaning and Flushing | 2021-08-24 | 2021-12-15
Specification For HDPE Pipes | BK-GNRAL-PEDCO-000-PI-SP-0018 | BK-GNRAL-PEDCO-000-PI-SP-0018Specification For HDPE Pipes | 2021-08-24 | 2022-03-05
Specification For Insulation | BK-GNRAL-PEDCO-000-PI-SP-0019 | BK-GNRAL-PEDCO-000-PI-SP-0019Specification For Insulation | 2021-08-24 | 2021-11-07
3D-Model (PDMS) Review Procedure | BK-GNRAL-PEDCO-000-PI-PR-0001 | BK-GNRAL-PEDCO-000-PI-PR-00013D-Model (PDMS) Review Procedure | 2021-07-24 | 2022-01-16
Piping Hydrostatic Test Diagram - Sub Surface | BK-GNRAL-PEDCO-000-PI-PR-0002 | BK-GNRAL-PEDCO-000-PI-PR-0002Piping Hydrostatic Test Diagram - Sub Surface | 0 | 0
Pipeline Design Criteria | BK-GNRAL-PEDCO-000-PL-DC-0001 | BK-GNRAL-PEDCO-000-PL-DC-0001Pipeline Design Criteria | 2021-08-28 | 2022-02-02
Specification For Line Pipes | BK-GNRAL-PEDCO-000-PL-SP-0002 | BK-GNRAL-PEDCO-000-PL-SP-0002Specification For Line Pipes | 2021-07-24 | 2021-12-07
Specification For Pipeline Cold Bending | BK-GNRAL-PEDCO-000-PL-SP-0003 | BK-GNRAL-PEDCO-000-PL-SP-0003Specification For Pipeline Cold Bending | 2021-08-28 | 2022-12-20
Specification For Barred Tee | BK-GNRAL-PEDCO-000-PL-SP-0004 | BK-GNRAL-PEDCO-000-PL-SP-0004Specification For Barred Tee | 2021-08-28 | 2022-03-26
Specification For Fittings, Flanges, Gaskets and Bolts | BK-GNRAL-PEDCO-000-PL-SP-0005 | BK-GNRAL-PEDCO-000-PL-SP-0005Specification For Fittings, Flanges, Gaskets and Bolts | 2021-07-24 | 2021-12-07
Specification For Pipeline Valves | BK-GNRAL-PEDCO-000-PL-SP-0006 | BK-GNRAL-PEDCO-000-PL-SP-0006Specification For Pipeline Valves | 2021-08-28 | 2022-12-20
Specification For Pipeline Coating | BK-GNRAL-PEDCO-000-PL-SP-0007 | BK-GNRAL-PEDCO-000-PL-SP-0007Specification For Pipeline Coating | 2021-07-24 | 2021-12-07
Specification For Pipeline Flushing, Cleaning And Hydrostatic Testing | BK-GNRAL-PEDCO-000-PL-SP-0008 | BK-GNRAL-PEDCO-000-PL-SP-0008Specification For Pipeline Flushing, Cleaning And Hydrostatic Testing | 2021-07-24 | 2021-12-07
Specification For Welding of Transportation Pipeline | BK-GNRAL-PEDCO-000-PL-SP-0009 | BK-GNRAL-PEDCO-000-PL-SP-0009Specification For Welding of Transportation Pipeline | 2021-12-12 | 2022-12-20
Specification For Pipeline Stress Analysis | BK-GNRAL-PEDCO-000-PL-SP-0010 | BK-GNRAL-PEDCO-000-PL-SP-0010Specification For Pipeline Stress Analysis | 2021-07-24 | 2022-07-27
Specification For Pipeline Insulation Joint | BK-GNRAL-PEDCO-000-PL-SP-0011 | BK-GNRAL-PEDCO-000-PL-SP-0011Specification For Pipeline Insulation Joint | 2021-07-24 | 2021-12-07
Specification For Pipeline Construction | BK-GNRAL-PEDCO-000-PL-SP-0012 | BK-GNRAL-PEDCO-000-PL-SP-0012Specification For Pipeline Construction | 2022-01-25 | 2022-12-20
Specification For Pipeline Cleaning and Flushing | BK-GNRAL-PEDCO-000-PL-SP-0013 | BK-GNRAL-PEDCO-000-PL-SP-0013Specification For Pipeline Cleaning and Flushing | 2021-07-24 | 2022-12-20
Specification For Anchor Flanges | BK-GNRAL-PEDCO-000-PL-SP-0014 | BK-GNRAL-PEDCO-000-PL-SP-0014Specification For Anchor Flanges | 2021-08-28 | 2022-12-20
Specification For Pigs | BK-GNRAL-PEDCO-000-PL-SP-0015 | BK-GNRAL-PEDCO-000-PL-SP-0015Specification For Pigs | 2021-08-28 | 2022-12-20
Specification For LBV | BK-GNRAL-PEDCO-000-PL-SP-0016 | BK-GNRAL-PEDCO-000-PL-SP-0016Specification For LBV | 2021-10-06 | 2022-12-20
Pipeline Standard Drawing For Line Marker Post and Cathodic Protection System | BK-GNRAL-PEDCO-000-PL-DW-0001 | BK-GNRAL-PEDCO-000-PL-DW-0001Pipeline Standard Drawing For Line Marker Post and Cathodic Protection System | 2021-09-18 | 2022-12-20
Standard Drawing For Above Ground Pipeline Construction R.O.W | BK-GNRAL-PEDCO-000-PL-DW-0002 | BK-GNRAL-PEDCO-000-PL-DW-0002Standard Drawing For Above Ground Pipeline Construction R.O.W | 2021-11-27 | 2022-03-28
Standard Drawing For Under Ground Pipeline Construction R.O.W | BK-GNRAL-PEDCO-000-PL-DW-0003 | BK-GNRAL-PEDCO-000-PL-DW-0003Standard Drawing For Under Ground Pipeline Construction R.O.W | 2021-12-04 | 2022-02-02
Pipeline Standard Drawing For Anchor Support | BK-GNRAL-PEDCO-000-PL-DW-0004 | BK-GNRAL-PEDCO-000-PL-DW-0004Pipeline Standard Drawing For Anchor Support | 2021-12-22 | 2022-12-20
Standard Drawing For A/G Pipeline Road Crossing | BK-GNRAL-PEDCO-000-PL-DW-0005 | BK-GNRAL-PEDCO-000-PL-DW-0005Standard Drawing For A/G Pipeline Road Crossing | 2021-12-05 | 2022-05-16
Standard Drawing For Existing Pipeline Crossing | BK-GNRAL-PEDCO-000-PL-DW-0006 | BK-GNRAL-PEDCO-000-PL-DW-0006Standard Drawing For Existing Pipeline Crossing | 2021-12-18 | 2022-07-06
Pipeline Standard Drawing For Irish Crossing | BK-GNRAL-PEDCO-000-PL-DW-0007 | BK-GNRAL-PEDCO-000-PL-DW-0007Pipeline Standard Drawing For Irish Crossing | 2021-12-04 | 2022-07-20
Pipeline Standard Drawing For Water - Way Crossing | BK-GNRAL-PEDCO-000-PL-DW-0008 | BK-GNRAL-PEDCO-000-PL-DW-0008Pipeline Standard Drawing For Water - Way Crossing | 2021-11-22 | 2022-05-15
Pipeline Standard Drawing For Pig Signaller Concrete Pit | BK-GNRAL-PEDCO-000-PL-DW-0009 | BK-GNRAL-PEDCO-000-PL-DW-0009Pipeline Standard Drawing For Pig Signaller Concrete Pit | 2021-11-27 | 2022-05-21
Pipeline Standard Drawing For H-Pipe Support | BK-GNRAL-PEDCO-000-PL-DW-0010 | BK-GNRAL-PEDCO-000-PL-DW-0010Pipeline Standard Drawing For H-Pipe Support | 2021-11-27 | 2022-01-31
Pipeline Standard Drawing For Vent Valve Pre-cast Concrete Box | BK-GNRAL-PEDCO-000-PL-DW-0011 | BK-GNRAL-PEDCO-000-PL-DW-0011Pipeline Standard Drawing For Vent Valve Pre-cast Concrete Box | 2021-11-27 | 2022-05-25
Pipeline Standard Drawing For Cover Slabs And Set-On-Weight | BK-GNRAL-PEDCO-000-PL-DW-0013 | BK-GNRAL-PEDCO-000-PL-DW-0013Pipeline Standard Drawing For Cover Slabs And Set-On-Weight | 2021-12-21 | 2022-12-20
Pipeline Standard Drawing For River Crossing | BK-GNRAL-PEDCO-000-PL-DW-0014 | BK-GNRAL-PEDCO-000-PL-DW-0014Pipeline Standard Drawing For River Crossing | 2021-12-15 | 2022-07-13
Specification For Instrumentation | BK-GNRAL-PEDCO-000-IN-SP-0001 | BK-GNRAL-PEDCO-000-IN-SP-0001Specification For Instrumentation | 2021-07-26 | 2022-07-30
Specification For Control System | BK-GNRAL-PEDCO-000-IN-SP-0002 | BK-GNRAL-PEDCO-000-IN-SP-0002Specification For Control System | 2021-07-28 | 2022-08-09
Specification For ESD System | BK-GNRAL-PEDCO-000-IN-SP-0003 | BK-GNRAL-PEDCO-000-IN-SP-0003Specification For ESD System | 2021-07-28 | 2022-12-20
Specification For Instrument and Control of Package Unit System (PU) | BK-GNRAL-PEDCO-000-IN-SP-0004 | BK-GNRAL-PEDCO-000-IN-SP-0004Specification For Instrument and Control of Package Unit System (PU) | 2021-08-04 | 2022-12-20
Specification For Control Valves | BK-GNRAL-PEDCO-000-IN-SP-0005 | BK-GNRAL-PEDCO-000-IN-SP-0005Specification For Control Valves | 2021-07-24 | 2022-08-09
Specification For On-off /Shut Down Valves(ESDV/MOV) | BK-GNRAL-PEDCO-000-IN-SP-0006 | BK-GNRAL-PEDCO-000-IN-SP-0006Specification For On-off /Shut Down Valves(ESDV/MOV) | 2021-07-24 | 2022-08-06
Specification For Pressure Safety Valves(PSV) | BK-GNRAL-PEDCO-000-IN-SP-0007 | BK-GNRAL-PEDCO-000-IN-SP-0007Specification For Pressure Safety Valves(PSV) | 2021-07-24 | 2022-02-26
Specification For Fire & Gas Sensor and Devices | BK-GNRAL-PEDCO-000-IN-SP-0009 | BK-GNRAL-PEDCO-000-IN-SP-0009Specification For Fire & Gas Sensor and Devices | 2021-07-26 | 2022-08-21
Specification For Instrument/F&G Cables | BK-GNRAL-PEDCO-000-IN-SP-0010 | BK-GNRAL-PEDCO-000-IN-SP-0010Specification For Instrument/F&G Cables | 2021-08-04 | 2022-12-20
Specification For Control Panels and System Cabinets | BK-GNRAL-PEDCO-000-IN-SP-0011 | BK-GNRAL-PEDCO-000-IN-SP-0011Specification For Control Panels and System Cabinets | 2021-07-24 | 2022-12-20
Specification For Fire & Gas System | BK-GNRAL-PEDCO-000-IN-SP-0012 | BK-GNRAL-PEDCO-000-IN-SP-0012Specification For Fire & Gas System | 2021-07-28 | 2022-03-06
Specification For LBV | BK-GNRAL-PEDCO-000-IN-SP-0013 | BK-GNRAL-PEDCO-000-IN-SP-0013Specification For LBV | 2021-08-10 | 2022-12-20
Specification For CCTV | BK-GNRAL-PEDCO-000-IN-SP-0014 | BK-GNRAL-PEDCO-000-IN-SP-0014Specification For CCTV | 2021-09-25 | 2022-12-20
CCTV Typical Installation Details & Notes | BK-GNRAL-PEDCO-000-IN-DW-0001 | BK-GNRAL-PEDCO-000-IN-DW-0001CCTV Typical Installation Details & Notes | 2021-09-25 | 0
Specification For Fire Fighting Equipment | BK-GNRAL-PEDCO-000-SA-SP-0001 | BK-GNRAL-PEDCO-000-SA-SP-0001Specification For Fire Fighting Equipment | 2021-08-29 | 2021-12-29
Specification For Hazardous Area Classification | BK-GNRAL-PEDCO-000-SA-SP-0002 | BK-GNRAL-PEDCO-000-SA-SP-0002Specification For Hazardous Area Classification | 2021-07-24 | 2022-01-09
Specification For Fire Water System | BK-GNRAL-PEDCO-000-SA-SP-0003 | BK-GNRAL-PEDCO-000-SA-SP-0003Specification For Fire Water System | 2021-07-24 | 2022-12-20
Specification For Environmental Job | BK-GNRAL-PEDCO-000-SA-SP-0004 | BK-GNRAL-PEDCO-000-SA-SP-0004Specification For Environmental Job | 2021-08-11 | 2022-07-23
Specification For Total Flooding System | BK-GNRAL-PEDCO-000-SA-SP-0005 | BK-GNRAL-PEDCO-000-SA-SP-0005Specification For Total Flooding System | 2021-07-24 | 2022-02-26
Specification For Safety Equipment | BK-GNRAL-PEDCO-000-SA-SP-0006 | BK-GNRAL-PEDCO-000-SA-SP-0006Specification For Safety Equipment | 2021-08-29 | 2021-12-06
Specification For passive Fire protection | BK-GNRAL-PEDCO-000-SA-SP-0007 | BK-GNRAL-PEDCO-000-SA-SP-0007Specification For passive Fire protection | 2021-07-24 | 2022-03-05
Specification For Safety Signs | BK-GNRAL-PEDCO-000-SA-SP-0008 | BK-GNRAL-PEDCO-000-SA-SP-0008Specification For Safety Signs | 2021-07-24 | 2022-01-09
Typical Installation Detail for Safety & Fire Fighting Equipment | BK-GNRAL-PEDCO-000-SA-DW-0002 | BK-GNRAL-PEDCO-000-SA-DW-0002Typical Installation Detail for Safety & Fire Fighting Equipment | 2021-12-29 | 0
Symbol & Legend For Safety & Firefighting Systems | BK-GNRAL-PEDCO-000-SA-DW-0003 | BK-GNRAL-PEDCO-000-SA-DW-0003Symbol & Legend For Safety & Firefighting Systems | 2021-08-29 | 2021-12-08
Material Safety Data Sheets | BK-GNRAL-PEDCO-000-SA-DT-0001 | BK-GNRAL-PEDCO-000-SA-DT-0001Material Safety Data Sheets | 2021-09-21 | 2022-12-20
Electrical System Design Criteria | BK-GNRAL-PEDCO-000-EL-DC-0001 | BK-GNRAL-PEDCO-000-EL-DC-0001Electrical System Design Criteria | 2021-08-03 | 2022-02-21
Specification For LV Switchgear & Motor Control Centers | BK-GNRAL-PEDCO-000-EL-SP-0001 | BK-GNRAL-PEDCO-000-EL-SP-0001Specification For LV Switchgear & Motor Control Centers | 2021-07-24 | 2022-12-20
Specification For MV Switchgear | BK-GNRAL-PEDCO-000-EL-SP-0002 | BK-GNRAL-PEDCO-000-EL-SP-0002Specification For MV Switchgear | 2021-07-24 | 2022-12-20
Specification For UPS System | BK-GNRAL-PEDCO-000-EL-SP-0003 | BK-GNRAL-PEDCO-000-EL-SP-0003Specification For UPS System | 2021-08-04 | 2022-12-20
Specification For Transformers | BK-GNRAL-PEDCO-000-EL-SP-0004 | BK-GNRAL-PEDCO-000-EL-SP-0004Specification For Transformers | 2021-07-24 | 2022-03-08
Specification For DC Charger | BK-GNRAL-PEDCO-000-EL-SP-0005 | BK-GNRAL-PEDCO-000-EL-SP-0005Specification For DC Charger | 2021-08-04 | 2021-12-07
Specification For Earthing & Lightning System | BK-GNRAL-PEDCO-000-EL-SP-0006 | BK-GNRAL-PEDCO-000-EL-SP-0006Specification For Earthing & Lightning System | 2021-07-28 | 2021-11-02
Specification For Lighting & Small Power System | BK-GNRAL-PEDCO-000-EL-SP-0007 | BK-GNRAL-PEDCO-000-EL-SP-0007Specification For Lighting & Small Power System | 2021-07-28 | 2021-11-02
Specification For Bulk Materials | BK-GNRAL-PEDCO-000-EL-SP-0008 | BK-GNRAL-PEDCO-000-EL-SP-0008Specification For Bulk Materials | 2021-07-24 | 2022-03-07
Specification For Diesel Generator | BK-GNRAL-PEDCO-000-EL-SP-0009 | BK-GNRAL-PEDCO-000-EL-SP-0009Specification For Diesel Generator | 2021-07-28 | 2021-11-02
Specification For LV Induction Motors | BK-GNRAL-PEDCO-000-EL-SP-0010 | BK-GNRAL-PEDCO-000-EL-SP-0010Specification For LV Induction Motors | 2021-07-24 | 2022-12-20
Specification For Electrical Requirements of Packaged Units | BK-GNRAL-PEDCO-000-EL-SP-0011 | BK-GNRAL-PEDCO-000-EL-SP-0011Specification For Electrical Requirements of Packaged Units | 2021-07-28 | 2021-11-02
Specification For Capacitor Bank | BK-GNRAL-PEDCO-000-EL-SP-0012 | BK-GNRAL-PEDCO-000-EL-SP-0012Specification For Capacitor Bank | 2021-07-24 | 2022-12-20
Specification For Distribution & Lighting Panels | BK-GNRAL-PEDCO-000-EL-SP-0013 | BK-GNRAL-PEDCO-000-EL-SP-0013Specification For Distribution & Lighting Panels | 2021-07-28 | 2021-11-02
Specification For Power & Control Cables | BK-GNRAL-PEDCO-000-EL-SP-0014 | BK-GNRAL-PEDCO-000-EL-SP-0014Specification For Power & Control Cables | 2021-07-24 | 2022-12-20
Specification For Cathodic Protection System | BK-GNRAL-PEDCO-000-EL-SP-0016 | BK-GNRAL-PEDCO-000-EL-SP-0016Specification For Cathodic Protection System | 2021-07-31 | 2021-12-07
Specification For MV Induction Motors | BK-GNRAL-PEDCO-000-EL-SP-0017 | BK-GNRAL-PEDCO-000-EL-SP-0017Specification For MV Induction Motors | 2021-07-24 | 2022-12-20
Specification For NGR | BK-GNRAL-PEDCO-000-EL-SP-0018 | BK-GNRAL-PEDCO-000-EL-SP-0018Specification For NGR | 2021-07-24 | 2022-12-20
Specification For Overhead Transmission Lines | BK-GNRAL-PEDCO-000-EL-SP-0019 | BK-GNRAL-PEDCO-000-EL-SP-0019Specification For Overhead Transmission Lines | 2021-07-28 | 2022-12-20
Electrical Legend and Symbols | BK-GNRAL-PEDCO-000-EL-DW-0001 | BK-GNRAL-PEDCO-000-EL-DW-0001Electrical Legend and Symbols | 2021-08-09 | 2021-12-08
Typical Installation Details & Notes For Earthing and Lightning Protection System | BK-GNRAL-PEDCO-000-EL-DW-0002 | BK-GNRAL-PEDCO-000-EL-DW-0002Typical Installation Details & Notes For Earthing and Lightning Protection System | 2021-08-25 | 2022-10-25
Typical Installation Details & Notes For Lighting System | BK-GNRAL-PEDCO-000-EL-DW-0003 | BK-GNRAL-PEDCO-000-EL-DW-0003Typical Installation Details & Notes For Lighting System | 2021-08-25 | 2022-10-26
Typical Installation Details & Notes For Power System | BK-GNRAL-PEDCO-000-EL-DW-0004 | BK-GNRAL-PEDCO-000-EL-DW-0004Typical Installation Details & Notes For Power System | 2021-08-25 | 2022-10-25
Installation Details & Notes For Cathodic Protection Systems | BK-GNRAL-PEDCO-000-EL-DW-0005 | BK-GNRAL-PEDCO-000-EL-DW-0005Installation Details & Notes For Cathodic Protection Systems | 2021-08-25 | 2022-12-20
Telecom. Design Criteria | BK-GNRAL-PEDCO-000-TE-DC-0001 | BK-GNRAL-PEDCO-000-TE-DC-0001Telecom. Design Criteria | 2021-07-28 | 2021-12-07
Specification For CCTV | BK-GNRAL-PEDCO-000-TE-SP-0001 | BK-GNRAL-PEDCO-000-TE-SP-0001Specification For CCTV | 2021-08-10 | 2022-12-20
Specification For PABX | BK-GNRAL-PEDCO-000-TE-SP-0002 | BK-GNRAL-PEDCO-000-TE-SP-0002Specification For PABX | 2021-08-04 | 2021-12-07
Specification For PAGA | BK-GNRAL-PEDCO-000-TE-SP-0003 | BK-GNRAL-PEDCO-000-TE-SP-0003Specification For PAGA | 2021-08-04 | 2022-12-20
Specification For Radio | BK-GNRAL-PEDCO-000-TE-SP-0004 | BK-GNRAL-PEDCO-000-TE-SP-0004Specification For Radio | 2021-08-04 | 2022-12-20
Specification For Telecommunication Tower | BK-GNRAL-PEDCO-000-TE-SP-0005 | BK-GNRAL-PEDCO-000-TE-SP-0005Specification For Telecommunication Tower | 2021-08-04 | 2022-12-20
Specification For Telecom. Cable | BK-GNRAL-PEDCO-000-TE-SP-0006 | BK-GNRAL-PEDCO-000-TE-SP-0006Specification For Telecom. Cable | 2021-08-09 | 2021-12-08
Telecom Systems Legend and Symbols | BK-GNRAL-PEDCO-000-TE-DW-0001 | BK-GNRAL-PEDCO-000-TE-DW-0001Telecom Systems Legend and Symbols | 2021-08-01 | 2022-12-20
Telecom Typical Installation Details & Notes | BK-GNRAL-PEDCO-000-TE-DW-0002 | BK-GNRAL-PEDCO-000-TE-DW-0002Telecom Typical Installation Details & Notes | 2021-08-01 | 2022-12-20
CCTV Typical Installation Details & Notes | BK-GNRAL-PEDCO-000-TE-DW-0003 | BK-GNRAL-PEDCO-000-TE-DW-0003CCTV Typical Installation Details & Notes | 0 | 0
Architectural Design Criteria | BK-GNRAL-PEDCO-000-AR-DC-0001 | BK-GNRAL-PEDCO-000-AR-DC-0001Architectural Design Criteria | 2022-02-08 | 2022-07-30
Buildings General Specification | BK-GNRAL-PEDCO-000-AR-SP-0001 | BK-GNRAL-PEDCO-000-AR-SP-0001 Buildings General Specification | 2022-04-06 | 2022-12-20
Standard Drawing for Architectural Details | BK-GNRAL-PEDCO-000-AR-DW-0001 | BK-GNRAL-PEDCO-000-AR-DW-0001Standard Drawing for Architectural Details | 2021-12-18 | 2022-12-20
Civil Design Criteria | BK-GNRAL-PEDCO-000-CV-DC-0001 | BK-GNRAL-PEDCO-000-CV-DC-0001Civil Design Criteria | 0 | 2022-12-20
Design Criteria for Sewerage & Drainage | BK-GNRAL-PEDCO-000-CV-DC-0002 | BK-GNRAL-PEDCO-000-CV-DC-0002Design Criteria for Sewerage & Drainage | 0 | 0
Specification For Civil Works | BK-GNRAL-PEDCO-000-CV-SP-0001 | BK-GNRAL-PEDCO-000-CV-SP-0001Specification For Civil Works | 0 | 0
Specification For Road & Paving | BK-GNRAL-PEDCO-000-CV-SP-0002 | BK-GNRAL-PEDCO-000-CV-SP-0002Specification For Road & Paving | 2021-08-09 | 2022-05-22
Specification For Fence & Gate | BK-GNRAL-PEDCO-000-CV-SP-0003 | BK-GNRAL-PEDCO-000-CV-SP-0003Specification For Fence & Gate | 2021-09-18 | 2021-12-26
Specification For Earth Work | BK-GNRAL-PEDCO-000-CV-SP-0004 | BK-GNRAL-PEDCO-000-CV-SP-0004Specification For Earth Work | 2021-08-09 | 2022-04-25
Specification For Sewerage & Drainage | BK-GNRAL-PEDCO-000-CV-SP-0005 | BK-GNRAL-PEDCO-000-CV-SP-0005Specification For Sewerage & Drainage | 2021-08-09 | 2022-03-12
Specification For Geological & Geotechnical Survey | BK-GNRAL-PEDCO-000-CV-SP-0006 | BK-GNRAL-PEDCO-000-CV-SP-0006Specification For Geological & Geotechnical Survey | 2022-03-26 | 2022-12-20
Standard Drawing For Civil Works | BK-GNRAL-PEDCO-000-CV-DW-0001 | BK-GNRAL-PEDCO-000-CV-DW-0001Standard Drawing For Civil Works | 0 | 0
Standard Drawing For Slope Protection Details | BK-GNRAL-PEDCO-000-CV-DW-0002 | BK-GNRAL-PEDCO-000-CV-DW-0002Standard Drawing For Slope Protection Details | 2021-08-22 | 2022-12-20
Standard Drawing For Roads | BK-GNRAL-PEDCO-000-CV-DW-0003 | BK-GNRAL-PEDCO-000-CV-DW-0003Standard Drawing For Roads | 2021-08-22 | 2022-05-21
Standard Drawing For Electrical Cable Trench | BK-GNRAL-PEDCO-000-CV-DW-0004 | BK-GNRAL-PEDCO-000-CV-DW-0004Standard Drawing For Electrical Cable Trench | 2021-08-22 | 2022-12-20
Standard Drawing For Manholes | BK-GNRAL-PEDCO-000-CV-DW-0005 | BK-GNRAL-PEDCO-000-CV-DW-0005Standard Drawing For Manholes | 2021-08-22 | 2022-12-20
Standard Drawing For Catch Basins | BK-GNRAL-PEDCO-000-CV-DW-0006 | BK-GNRAL-PEDCO-000-CV-DW-0006Standard Drawing For Catch Basins | 2021-08-22 | 2022-12-20
Standard Drawing For Sewerage & Drainage Details | BK-GNRAL-PEDCO-000-CV-DW-0007 | BK-GNRAL-PEDCO-000-CV-DW-0007Standard Drawing For Sewerage & Drainage Details | 2022-02-02 | 2022-07-17
Standard Drawing For Civil Underground Crossings | BK-GNRAL-PEDCO-000-CV-DW-0008 | BK-GNRAL-PEDCO-000-CV-DW-0008Standard Drawing For Civil Underground Crossings | 2022-02-07 | 2022-12-20
Standard Drawing For Fence & Gate Details | BK-GNRAL-PEDCO-000-CV-DW-0009 | BK-GNRAL-PEDCO-000-CV-DW-0009Standard Drawing For Fence & Gate Details | 2021-09-18 | 2022-02-28
Standard Drawing For Concrete Continues Weight | BK-GNRAL-PEDCO-000-CV-DW-0010 | BK-GNRAL-PEDCO-000-CV-DW-0010Standard Drawing For Concrete Continues Weight | 0 | 0
Standard Drawing For Major Floodway Crossing | BK-GNRAL-PEDCO-000-CV-DW-0012 | BK-GNRAL-PEDCO-000-CV-DW-0012Standard Drawing For Major Floodway Crossing | 0 | 0
Standard Drawing For Culvert & Details | BK-GNRAL-PEDCO-000-CV-DW-0014 | BK-GNRAL-PEDCO-000-CV-DW-0014 Standard Drawing For Culvert & Details | 2021-09-25 | 2021-11-15
Standard Drawing For Valve Box | BK-GNRAL-PEDCO-000-CV-DW-0016 | BK-GNRAL-PEDCO-000-CV-DW-0016Standard Drawing For Valve Box | 2022-01-12 | 0
Standard Drawing For Fire Hydrant PAD | BK-GNRAL-PEDCO-000-CV-DW-0018 | BK-GNRAL-PEDCO-000-CV-DW-0018Standard Drawing For Fire Hydrant PAD | 2022-03-13 | 2022-12-20
Standard Drawing For Cable Pull Pit | BK-GNRAL-PEDCO-000-CV-DW-0020 | BK-GNRAL-PEDCO-000-CV-DW-0020Standard Drawing For Cable Pull Pit | 2022-04-11 | 2022-06-11
Standard Drawing For Pavings | BK-GNRAL-PEDCO-000-CV-DW-0035 | BK-GNRAL-PEDCO-000-CV-DW-0035Standard Drawing For Pavings | 2022-01-08 | 2022-12-20
Standard Drawing For Earth Pit | BK-GNRAL-PEDCO-000-CV-DW-0037 | BK-GNRAL-PEDCO-000-CV-DW-0037Standard Drawing For Earth Pit | 2022-02-13 | 2022-08-13
Standard Detail For Pipe Bedding | BK-GNRAL-PEDCO-000-CV-DW-0039 | BK-GNRAL-PEDCO-000-CV-DW-0039Standard Detail For Pipe Bedding | 2021-08-22 | 2022-12-20
Standard Details of Miscellaneous Items | BK-GNRAL-PEDCO-000-CV-DW-0040 | BK-GNRAL-PEDCO-000-CV-DW-0040Standard Details of Miscellaneous Items | 2022-03-06 | 2022-05-22
Typical Drawing For A/G Pipeline Road Crossing | BK-GNRAL-PEDCO-000-CV-DW-0025 | BK-GNRAL-PEDCO-000-CV-DW-0025Typical Drawing For A/G Pipeline Road Crossing | 0 | 0
Pipeline Typical Drawing For Irish Crossing | BK-GNRAL-PEDCO-000-CV-DW-0027 | BK-GNRAL-PEDCO-000-CV-DW-0027Pipeline Typical Drawing For Irish Crossing | 0 | 0
Pipeline Typical Drawing For Water - Way Crossing | BK-GNRAL-PEDCO-000-CV-DW-0028 | BK-GNRAL-PEDCO-000-CV-DW-0028Pipeline Typical Drawing For Water - Way Crossing | 0 | 0
Pipeline Typical Drawing For Pig Signaller Concrete Pit | BK-GNRAL-PEDCO-000-CV-DW-0029 | BK-GNRAL-PEDCO-000-CV-DW-0029Pipeline Typical Drawing For Pig Signaller Concrete Pit | 0 | 0
Pipeline Typical Drawing For H-Pipe Support | BK-GNRAL-PEDCO-000-CV-DW-0030 | BK-GNRAL-PEDCO-000-CV-DW-0030Pipeline Typical Drawing For H-Pipe Support | 0 | 0
Pipeline Typical Drawing For Vent Valve Pre-cast Concrete Box | BK-GNRAL-PEDCO-000-CV-DW-0031 | BK-GNRAL-PEDCO-000-CV-DW-0031Pipeline Typical Drawing For Vent Valve Pre-cast Concrete Box | 0 | 0
Standard Detail curbed Stone Bounded Area | BK-GNRAL-PEDCO-000-CV-DW-0038 | BK-GNRAL-PEDCO-000-CV-DW-0038Standard Detail curbed Stone Bounded Area | 0 | 0
Design Criteria For Concrete Works | BK-GNRAL-PEDCO-000-ST-DC-0001 | BK-GNRAL-PEDCO-000-ST-DC-0001Design Criteria For Concrete Works | 0 | 0
Specification For Concrete Work | BK-GNRAL-PEDCO-000-ST-SP-0001 | BK-GNRAL-PEDCO-000-ST-SP-0001Specification For Concrete Work | 2021-08-14 | 2022-12-20
Specification For Storage Tank Foundation | BK-GNRAL-PEDCO-000-ST-SP-0002 | BK-GNRAL-PEDCO-000-ST-SP-0002Specification For Storage Tank Foundation | 2021-11-23 | 2022-03-09
Specification for Fabrication of Steel Structures | BK-GNRAL-PEDCO-000-ST-SP-0003 | BK-GNRAL-PEDCO-000-ST-SP-0003Specification for Fabrication of Steel Structures | 2022-01-24 | 2022-02-28
Specification For Grouting | BK-GNRAL-PEDCO-000-ST-SP-0004 | BK-GNRAL-PEDCO-000-ST-SP-0004Specification For Grouting | 2021-08-14 | 2022-01-18
Specification for Erection of Steel Structures | BK-GNRAL-PEDCO-000-ST-SP-0005 | BK-GNRAL-PEDCO-000-ST-SP-0005Specification for Erection of Steel Structures | 2022-01-24 | 2022-02-28
Specification for Fireproofing | BK-GNRAL-PEDCO-000-ST-SP-0006 | BK-GNRAL-PEDCO-000-ST-SP-0006Specification for Fireproofing | 2021-09-18 | 2021-12-26
Specification for Design of Blast Resistant Buildings | BK-GNRAL-PEDCO-000-ST-SP-0007 | BK-GNRAL-PEDCO-000-ST-SP-0007Specification for Design of Blast Resistant Buildings | 2021-12-12 | 2022-12-20
Specification For Steel Structural Works | BK-GNRAL-PEDCO-000-ST-SP-0008 | BK-GNRAL-PEDCO-000-ST-SP-0008Specification For Steel Structural Works | 0 | 0
Standard Drawing For Fire Proofing | BK-GNRAL-PEDCO-000-ST-DW-0001 | BK-GNRAL-PEDCO-000-ST-DW-0001Standard Drawing For Fire Proofing | 2021-08-08 | 2022-01-18
Standard Drawing For Anchor Bolts | BK-GNRAL-PEDCO-000-ST-DW-0002 | BK-GNRAL-PEDCO-000-ST-DW-0002Standard Drawing For Anchor Bolts | 2021-12-15 | 2022-02-12
Standard Drawing For Steel Stairs | BK-GNRAL-PEDCO-000-ST-DW-0003 | BK-GNRAL-PEDCO-000-ST-DW-0003Standard Drawing For Steel Stairs | 2021-12-18 | 2022-02-13
Standard Drawing For Operating Platform | BK-GNRAL-PEDCO-000-ST-DW-0005 | BK-GNRAL-PEDCO-000-ST-DW-0005Standard Drawing For Operating Platform | 2021-12-27 | 2022-03-12
Standard Drawing For Handrail | BK-GNRAL-PEDCO-000-ST-DW-0006 | BK-GNRAL-PEDCO-000-ST-DW-0006Standard Drawing For Handrail | 2021-12-18 | 2022-02-09
Standard Drawing For Insert Plates in Concrete | BK-GNRAL-PEDCO-000-ST-DW-0007 | BK-GNRAL-PEDCO-000-ST-DW-0007Standard Drawing For Insert Plates in Concrete | 2021-08-08 | 2022-01-24
Standard Details For Ladder & Safety Cage | BK-GNRAL-PEDCO-000-ST-DW-0009 | BK-GNRAL-PEDCO-000-ST-DW-0009Standard Details For Ladder & Safety Cage | 2021-12-15 | 2022-02-16
Standard Drawing For Lighting pole foundation Plan & Details | BK-GNRAL-PEDCO-000-ST-DW-0010 | BK-GNRAL-PEDCO-000-ST-DW-0010Standard Drawing For Lighting pole foundation Plan & Details | 2022-01-29 | 2022-12-20
General Notes - Steel Structures | BK-GNRAL-PEDCO-000-ST-DW-0011 | BK-GNRAL-PEDCO-000-ST-DW-0011General Notes - Steel Structures | 2022-01-25 | 2022-03-12
General Notes - Reinforced Concrete Structures | BK-GNRAL-PEDCO-000-ST-DW-0012 | BK-GNRAL-PEDCO-000-ST-DW-0012General Notes - Reinforced Concrete Structures | 2021-12-20 | 2022-02-16
Standard Drawing For Structural Built-up Sections | BK-GNRAL-PEDCO-000-ST-DW-0014 | BK-GNRAL-PEDCO-000-ST-DW-0014Standard Drawing For Structural Built-up Sections | 2021-12-04 | 2022-05-23
Standard Drawing For Steel Flooring, Grating and Chequered Plate | BK-GNRAL-PEDCO-000-ST-DW-0015 | BK-GNRAL-PEDCO-000-ST-DW-0015Standard Drawing For Steel Flooring, Grating and Chequered Plate | 2022-01-05 | 2022-02-12
Concrete Reinforcement Shape Code | BK-GNRAL-PEDCO-000-ST-DW-0016 | BK-GNRAL-PEDCO-000-ST-DW-0016Concrete Reinforcement Shape Code | 0 | 0
Standard Drawing For Septic Tank | BK-GNRAL-PEDCO-000-ST-DW-0017 | BK-GNRAL-PEDCO-000-ST-DW-0017Standard Drawing For Septic Tank | 2022-01-22 | 2022-06-27
EPC Waste Management Plan | BK-GNRAL-HD-000-SA-HP-0001 | BK-GNRAL-HD-000-SA-HP-0001EPC Waste Management Plan | 2022-06-06 | 2022-12-20
HAZOP Study Procedure | BK-GNRAL-PEDCO-000-GE-PR-0001 | BK-GNRAL-PEDCO-000-GE-PR-0001HAZOP Study Procedure | 2021-10-25 | 2022-03-02
HAZID Study Procedure | BK-GNRAL-PEDCO-000-GE-PR-0002 | BK-GNRAL-PEDCO-000-GE-PR-0002HAZID Study Procedure | 2021-09-05 | 2021-10-27
SIL Study Procedure | BK-GNRAL-PEDCO-000-GE-PR-0003 | BK-GNRAL-PEDCO-000-GE-PR-0003SIL Study Procedure | 2021-10-25 | 2022-03-07
Crisis Management Plan | BK-GNRAL-HD-000-GE-PR-0004 | BK-GNRAL-HD-000-GE-PR-0004Crisis Management Plan | 2022-06-06 | 2022-12-20
EPC FMEA report | BK-GNRAL-HD-000-GE-PR-0005 | BK-GNRAL-HD-000-GE-PR-0005EPC FMEA report | 2021-12-28 | 2022-05-22
PSSR Procedure | BK-GNRAL-HD-000-GE-PR-0006 | BK-GNRAL-HD-000-GE-PR-0006PSSR Procedure | 2022-06-06 | 2022-12-20
Pigging Safety Requirement | BK-GNRAL-PEDCO-000-GE-PR-0007 | BK-GNRAL-PEDCO-000-GE-PR-0007Pigging Safety Requirement | 2022-04-09 | 2022-12-20
Project Quality Plan | BK-GNRAL-PEDCO-000-QC-PR-0001 | BK-GNRAL-PEDCO-000-QC-PR-0001Project Quality Plan | 2021-12-08 | 2022-12-20
Project Audit Procedure | BK-GNRAL-PEDCO-000-QC-PR-0003 | BK-GNRAL-PEDCO-000-QC-PR-0003Project Audit Procedure | 2022-08-09 | 2022-12-20
Non Conformance Control Procedure | BK-GNRAL-PEDCO-000-QC-PR-0042 | BK-GNRAL-PEDCO-000-QC-PR-0042Non Conformance Control Procedure | 2022-04-10 | 2022-12-20
Corrective Action Procedure | BK-GNRAL-PEDCO-000-QC-PR-0043 | BK-GNRAL-PEDCO-000-QC-PR-0043Corrective Action Procedure | 2022-08-09 | 2022-12-20
Material Reciving, Storage, Handling Procedure | BK-GNRAL-PEDCO-000-QC-PR-0044 | BK-GNRAL-PEDCO-000-QC-PR-0044Material Reciving, Storage, Handling Procedure | 2022-02-20 | 2022-12-20
Packing, Marking, Transportation Procedure | BK-GNRAL-PEDCO-000-QC-PR-0045 | BK-GNRAL-PEDCO-000-QC-PR-0045Packing, Marking, Transportation Procedure | 2022-04-24 | 2022-12-20
Criticality Assessment Procedure | BK-GNRAL-PEDCO-000-PM-PR-0013 | BK-GNRAL-PEDCO-000-PM-PR-0013Criticality Assessment Procedure | 0 | 0
Specification For Final Data Book (FDB) Requirements | BK-GNRAL-PEDCO-000-QC-PR-0022 | BK-GNRAL-PEDCO-000-QC-PR-0022Specification For Final Data Book (FDB) Requirements | 2022-04-03 | 2022-12-20
Technical Query Procedure | BK-GNRAL-PEDCO-000-QC-PR-0014 | BK-GNRAL-PEDCO-000-QC-PR-0014Technical Query Procedure | 2022-04-03 | 2022-12-20
Quality Control Plan (QCP) | BK-GNRAL-PEDCO-000-QC-PR-0002 | BK-GNRAL-PEDCO-000-QC-PR-0002Quality Control Plan (QCP) | 2021-11-28 | 2022-12-20
Specification for Welding Procedure | BK-GNRAL-PEDCO-000-QC-PR-0015 | BK-GNRAL-PEDCO-000-QC-PR-0015Specification for Welding Procedure | 2022-04-16 | 2022-12-20
Heat Treatment Procedure (Pre Heating , PWHT) | BK-GNRAL-PEDCO-000-QC-PR-0016 | BK-GNRAL-PEDCO-000-QC-PR-0016Heat Treatment Procedure (Pre Heating , PWHT) | 0 | 0
Welder Performance Qualification Test (WQT) Procedure | BK-GNRAL-PEDCO-000-QC-PR-0017 | BK-GNRAL-PEDCO-000-QC-PR-0017Welder Performance Qualification Test (WQT) Procedure | 2022-04-04 | 2022-12-20
NDT Procedure | BK-GNRAL-PEDCO-000-QC-PR-0018 | BK-GNRAL-PEDCO-000-QC-PR-0018NDT Procedure | 2022-07-30 | 2022-12-20
Surface Preparation and Coating/Painting Procedure | BK-GNRAL-PEDCO-000-QC-PR-0019 | BK-GNRAL-PEDCO-000-QC-PR-0019Surface Preparation and Coating/Painting Procedure | 2022-08-09 | 2022-12-20
Control of Inspection Measuring and Test Equipment Procedure | BK-GNRAL-PEDCO-000-QC-PR-0021 | BK-GNRAL-PEDCO-000-QC-PR-0021Control of Inspection Measuring and Test Equipment Procedure | 2022-04-10 | 2022-12-20
Field Joint Coating Procedure For Pipeline | BK-GNRAL-PEDCO-000-QC-PR-0035 | BK-GNRAL-PEDCO-000-QC-PR-0035Field Joint Coating Procedure For Pipeline | 2022-09-26 | 0
ITP For Piping Works | BK-GNRAL-PEDCO-000-QC-PR-0004 | BK-GNRAL-PEDCO-000-QC-PR-0004ITP For Piping Works | 2022-04-10 | 2022-12-20
PIPING PWPS (Preliminary Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0023 | BK-GNRAL-PEDCO-000-QC-PR-0023PIPING PWPS (Preliminary Welding Procedure Specification) | 0 | 0
PIPING WPS (Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0024 | BK-GNRAL-PEDCO-000-QC-PR-0024PIPING WPS (Welding Procedure Specification) | 0 | 0
PIPING PQR (Procedure Qualification Record) | BK-GNRAL-PEDCO-000-QC-PR-0025 | BK-GNRAL-PEDCO-000-QC-PR-0025PIPING PQR (Procedure Qualification Record) | 0 | 0
PIPING PWPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0026 | BK-GNRAL-PEDCO-000-QC-PR-0026PIPING PWPS (Preliminary Welding Procedure Specification) for Repair Welding | 0 | 0
PIPING WPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0027 | BK-GNRAL-PEDCO-000-QC-PR-0027PIPING WPS (Preliminary Welding Procedure Specification) for Repair Welding | 0 | 0
PIPING PQR (Procedure Qualification Record) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0028 | BK-GNRAL-PEDCO-000-QC-PR-0028PIPING PQR (Procedure Qualification Record) for Repair Welding | 0 | 0
ITP For Telecommunication Installation | BK-GNRAL-PEDCO-000-QC-PR-0012 | BK-GNRAL-PEDCO-000-QC-PR-0012ITP For Telecommunication Installation | 0 | 0
ITP For Safety Installation | BK-GNRAL-PEDCO-000-QC-PR-0013 | BK-GNRAL-PEDCO-000-QC-PR-0013ITP For Safety Installation | 0 | 0
ITP For Architectural Works | BK-GNRAL-PEDCO-000-QC-PR-0008 | BK-GNRAL-PEDCO-000-QC-PR-0008ITP For Architectural Works | 0 | 0
ITP For Mechanical Installation | BK-GNRAL-PEDCO-000-QC-PR-0009 | BK-GNRAL-PEDCO-000-QC-PR-0009ITP For Mechanical Installation | 0 | 0
ITP For Steel Structural Works | BK-GNRAL-PEDCO-000-QC-PR-0007 | BK-GNRAL-PEDCO-000-QC-PR-0007ITP For Steel Structural Works | 2022-05-21 | 2022-12-20
Steel Structure WPS (Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0036 | BK-GNRAL-PEDCO-000-QC-PR-0036Steel Structure WPS (Welding Procedure Specification) | 0 | 0
Steel Structure PQR (Procedure Qualification Record) | BK-GNRAL-PEDCO-000-QC-PR-0037 | BK-GNRAL-PEDCO-000-QC-PR-0037Steel Structure PQR (Procedure Qualification Record) | 0 | 0
Steel Structure WPS (Welding Procedure Specification) For Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0038 | BK-GNRAL-PEDCO-000-QC-PR-0038Steel Structure WPS (Welding Procedure Specification) For Repair Welding | 0 | 0
Steel Structure PQR (Procedure Qualification Record) For Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0039 | BK-GNRAL-PEDCO-000-QC-PR-0039Steel Structure PQR (Procedure Qualification Record) For Repair Welding | 0 | 0
Weld Map For Steel Structures | BK-GNRAL-PEDCO-000-QC-PR-0040 | BK-GNRAL-PEDCO-000-QC-PR-0040Weld Map For Steel Structures | 0 | 0
NDT Plan For steel Structures | BK-GNRAL-PEDCO-000-QC-PR-0041 | BK-GNRAL-PEDCO-000-QC-PR-0041NDT Plan For steel Structures | 0 | 0
ITP For I&C Installation | BK-GNRAL-PEDCO-000-QC-PR-0011 | BK-GNRAL-PEDCO-000-QC-PR-0011ITP For I&C Installation | 0 | 0
ITP For Pipeline | BK-GNRAL-PEDCO-000-QC-PR-0005 | BK-GNRAL-PEDCO-000-QC-PR-0005ITP For Pipeline | 2022-01-16 | 2022-12-20
PIPELINE PWPS (Preliminary Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0029 | BK-GNRAL-PEDCO-000-QC-PR-0029PIPELINE PWPS (Preliminary Welding Procedure Specification) | 2022-02-23 | 2022-12-20
PIPELINE WPS (Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0030 | BK-GNRAL-PEDCO-000-QC-PR-0030PIPELINE WPS (Welding Procedure Specification) | 0 | 0
PIPELINE PQR (Procedure Qualification Record) | BK-GNRAL-PEDCO-000-QC-PR-0031 | BK-GNRAL-PEDCO-000-QC-PR-0031PIPELINE PQR (Procedure Qualification Record) | 0 | 0
PIPELINE PWPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0032 | BK-GNRAL-PEDCO-000-QC-PR-0032PIPELINE PWPS (Preliminary Welding Procedure Specification) for Repair Welding | 0 | 0
PIPELINE WPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0033 | BK-GNRAL-PEDCO-000-QC-PR-0033PIPELINE WPS (Preliminary Welding Procedure Specification) for Repair Welding | 0 | 0
PIPELINE PQR (Procedure Qualification Record) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0034 | BK-GNRAL-PEDCO-000-QC-PR-0034PIPELINE PQR (Procedure Qualification Record) for Repair Welding | 0 | 0
ITP For Civil Works | BK-GNRAL-PEDCO-000-QC-PR-0006 | BK-GNRAL-PEDCO-000-QC-PR-0006ITP For Civil Works | 2021-09-20 | 2021-11-22
ITP For Electrical Installation | BK-GNRAL-PEDCO-000-QC-PR-0010 | BK-GNRAL-PEDCO-000-QC-PR-0010ITP For Electrical Installation | 0 | 0
Endorsement Report For Basic Design & Scope of Work | BK-SSGRL-PEDCO-110-GE-RT-0001 | BK-SSGRL-PEDCO-110-GE-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2022-12-20
Value Engineering Study Report | BK-SSGRL-PEDCO-110-GE-RT-0002 | BK-SSGRL-PEDCO-110-GE-RT-0002Value Engineering Study Report | 2022-02-01 | 2022-12-20
HAZID Report For WHF & Flow lines | BK-SSGRL-PEDCO-110-GE-RT-0003 | BK-SSGRL-PEDCO-110-GE-RT-0003HAZID Report For WHF & Flow lines | 2022-08-01 | 2022-11-19
HAZOP Report For Binak B/C Manifold Extension | BK-SSGRL-PEDCO-110-GE-RT-0004 | BK-SSGRL-PEDCO-110-GE-RT-0004HAZOP Report For Binak B/C Manifold Extension | 2022-08-01 | 2022-11-19
SIL Report For Binak B/C Manifold Extension | BK-SSGRL-PEDCO-110-GE-RT-0005 | BK-SSGRL-PEDCO-110-GE-RT-0005SIL Report For Binak B/C Manifold Extension | 2022-08-01 | 2022-11-19
Drainage Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0001 | BK-SSGRL-PEDCO-110-PR-PH-0001Drainage Philosophy | 2022-03-26 | 2022-05-10
Control Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0002 | BK-SSGRL-PEDCO-110-PR-PH-0002Control Philosophy | 2022-05-09 | 2022-12-20
Flare,Blow Down And Relief Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0003 | BK-SSGRL-PEDCO-110-PR-PH-0003Flare,Blow Down And Relief Philosophy | 2022-03-26 | 2022-05-10
Isolation Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0004 | BK-SSGRL-PEDCO-110-PR-PH-0004Isolation Philosophy | 2021-11-21 | 2022-12-20
ESD Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0005 | BK-SSGRL-PEDCO-110-PR-PH-0005ESD Philosophy | 2022-05-09 | 2022-12-20
Symbol & Legend For PFD and P&ID | BK-SSGRL-PEDCO-110-PR-PI-0001 | BK-SSGRL-PEDCO-110-PR-PI-0001Symbol & Legend For PFD and P&ID | 2021-10-30 | 2022-12-20
Consumption List | BK-SSGRL-PEDCO-110-PR-LI-0001 | BK-SSGRL-PEDCO-110-PR-LI-0001Consumption List | 2022-02-23 | 2022-12-20
Data Sheets For FUEL Oil Storage Drum of Well Pads | BK-SSGRL-PEDCO-110-ME-DT-0001 | BK-SSGRL-PEDCO-110-ME-DT-0001Data Sheets For FUEL Oil Storage Drum of Well Pads | 2022-01-16 | 2022-12-20
Data Sheets For Potable Water Tank of Well Pads | BK-SSGRL-PEDCO-110-ME-DT-0002 | BK-SSGRL-PEDCO-110-ME-DT-0002Data Sheets For Potable Water Tank of Well Pads | 2022-02-09 | 2022-12-20
Piping Material Specification | BK-SSGRL-PEDCO-110-PI-SP-0001 | BK-SSGRL-PEDCO-110-PI-SP-0001Piping Material Specification | 2021-11-28 | 0
Data Sheets For Stone Trap | BK-SSGRL-PEDCO-110-PI-DT-0001 | BK-SSGRL-PEDCO-110-PI-DT-0001Data Sheets For Stone Trap | 2021-12-27 | 2022-12-20
Standard Pipe Support Drawings | BK-SSGRL-PEDCO-110-PI-DW-0001 | BK-SSGRL-PEDCO-110-PI-DW-0001Standard Pipe Support Drawings | 2022-02-19 | 2022-12-20
Piping Assembly Drawing | BK-SSGRL-PEDCO-110-PI-DW-0002 | BK-SSGRL-PEDCO-110-PI-DW-0002Piping Assembly Drawing | 0 | 0
Piping Hydrostatic Test Diagram - Sub Surface | BK-SSGRL-PEDCO-110-PI-DW-0003 | BK-SSGRL-PEDCO-110-PI-DW-0003Piping Hydrostatic Test Diagram - Sub Surface | 0 | 0
Piping Wall Thickness Calculation | BK-SSGRL-PEDCO-110-PI-CN-0001 | BK-SSGRL-PEDCO-110-PI-CN-0001Piping Wall Thickness Calculation | 2021-11-28 | 0
Piping Corrosion Study & Material Selection Report | BK-SSGRL-PEDCO-110-PI-RT-0001 | BK-SSGRL-PEDCO-110-PI-RT-0001Piping Corrosion Study & Material Selection Report | 2021-11-28 | 2022-10-19
Pipeline Material Specification | BK-SSGRL-PEDCO-110-PL-SP-0001 | BK-SSGRL-PEDCO-110-PL-SP-0001Pipeline Material Specification | 2021-10-27 | 2022-10-19
Pipeline Standard Support Drawings | BK-SSGRL-PEDCO-110-PL-DW-0001 | BK-SSGRL-PEDCO-110-PL-DW-0001Pipeline Standard Support Drawings | 2021-07-27 | 2022-12-20
Pipeline Hydrostatic Test Diagram - Sub Surface | BK-SSGRL-PEDCO-110-PL-DG-0001 | BK-SSGRL-PEDCO-110-PL-DG-0001Pipeline Hydrostatic Test Diagram - Sub Surface | 0 | 0
Pipeline Wall Thickness Calculation | BK-SSGRL-PEDCO-110-PL-CN-0001 | BK-SSGRL-PEDCO-110-PL-CN-0001Pipeline Wall Thickness Calculation | 2021-10-27 | 2022-10-19
Pipeline Corrosion Study & Material Selection Report | BK-SSGRL-PEDCO-110-PL-RT-0001 | BK-SSGRL-PEDCO-110-PL-RT-0001Pipeline Corrosion Study & Material Selection Report | 2021-10-27 | 2022-10-19
Instrument & Control System Design Criteria | BK-SSGRL-PEDCO-110-IN-DC-0002 | BK-SSGRL-PEDCO-110-IN-DC-0002Instrument & Control System Design Criteria | 2022-01-03 | 2022-12-20
Fire & Gas Detection Design Criteria | BK-SSGRL-PEDCO-110-IN-DC-0001 | BK-SSGRL-PEDCO-110-IN-DC-0001Fire & Gas Detection Design Criteria | 2021-08-14 | 2022-01-01
Instrument & Control System Basis of Design | BK-SSGRL-PEDCO-110-IN-DB-0001 | BK-SSGRL-PEDCO-110-IN-DB-0001Instrument & Control System Basis of Design | 2021-08-22 | 2022-12-20
Specification For WHCP/HPU | BK-SSGRL-PEDCO-110-IN-SP-0001 | BK-SSGRL-PEDCO-110-IN-SP-0001Specification For WHCP/HPU | 2021-08-08 | 2022-03-27
Data Sheets For WHCP/HPU - Wellheads | BK-SSGRL-PEDCO-110-IN-DT-0001 | BK-SSGRL-PEDCO-110-IN-DT-0001Data Sheets For WHCP/HPU - Wellheads | 2021-08-22 | 2022-12-20
Data Sheets For Pressure Gauge - Wellheads | BK-SSGRL-PEDCO-110-IN-DT-0002 | BK-SSGRL-PEDCO-110-IN-DT-0002Data Sheets For Pressure Gauge - Wellheads | 2021-12-07 | 2022-12-20
Data Sheets For Temperature Gauge - Wellheads | BK-SSGRL-PEDCO-110-IN-DT-0003 | BK-SSGRL-PEDCO-110-IN-DT-0003Data Sheets For Temperature Gauge - Wellheads | 2021-12-07 | 2022-07-27
Instrument Hook-up Diagram - Wellheads | BK-SSGRL-PEDCO-110-IN-DG-0001 | BK-SSGRL-PEDCO-110-IN-DG-0001Instrument Hook-up Diagram - Wellheads | 2021-11-14 | 2022-12-20
WHCP HYDRAULIC\PNEUMATIC DIAGRAMS-WELLHEADS | BK-SSGRL-PEDCO-110-IN-DG-0002 | BK-SSGRL-PEDCO-110-IN-DG-0002WHCP HYDRAULIC\PNEUMATIC DIAGRAMS-WELLHEADS | 2021-08-22 | 2022-06-15
Instrument Index For New Wells & Manifold Extension | BK-SSGRL-PEDCO-110-IN-LI-0001 | BK-SSGRL-PEDCO-110-IN-LI-0001Instrument Index For New Wells & Manifold Extension | 2021-11-10 | 2022-12-20
Active Fire Protection and Safety Concept | BK-SSGRL-PEDCO-110-SA-DC-0001 | BK-SSGRL-PEDCO-110-SA-DC-0001Active Fire Protection and Safety Concept | 2021-08-29 | 2021-12-06
Data Sheets For Fire Fighting Equipment | BK-SSGRL-PEDCO-110-SA-DT-0001 | BK-SSGRL-PEDCO-110-SA-DT-0001Data Sheets For Fire Fighting Equipment | 2021-12-08 | 2022-04-06
Data Sheets For Safety Equipment | BK-SSGRL-PEDCO-110-SA-DT-0002 | BK-SSGRL-PEDCO-110-SA-DT-0002Data Sheets For Safety Equipment | 2021-12-08 | 2022-01-09
Data Sheets For Safety Sign | BK-SSGRL-PEDCO-110-SA-DT-0003 | BK-SSGRL-PEDCO-110-SA-DT-0003Data Sheets For Safety Sign | 2021-12-08 | 2022-01-09
Calculation Note For Lighting System of Well Pads Switchgear Building | BK-SSGRL-PEDCO-110-EL-CN-0002 | BK-SSGRL-PEDCO-110-EL-CN-0002Calculation Note For Lighting System of Well Pads Switchgear Building | 2022-05-11 | 2022-12-20
Calculation Note For Lighting System of Well Pads Security Building | BK-SSGRL-PEDCO-110-EL-CN-0003 | BK-SSGRL-PEDCO-110-EL-CN-0003Calculation Note For Lighting System of Well Pads Security Building | 2022-04-30 | 2022-12-20
Calculation Note For Lighting System of Well Pads Area | BK-SSGRL-PEDCO-110-EL-CN-0004 | BK-SSGRL-PEDCO-110-EL-CN-0004Calculation Note For Lighting System of Well Pads Area | 2022-05-14 | 2022-12-20
Calculation Note For Cable Sizing of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0005 | BK-SSGRL-PEDCO-110-EL-CN-0005Calculation Note For Cable Sizing of Well Pads | 2021-11-02 | 2022-12-20
Calculation Note For UPS System of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0006 | BK-SSGRL-PEDCO-110-EL-CN-0006Calculation Note For UPS System of Well Pads | 0 | 0
Calculation Note For Earthing & Lightning System of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0007 | BK-SSGRL-PEDCO-110-EL-CN-0007Calculation Note For Earthing & Lightning System of Well Pads | 2022-05-01 | 2022-12-20
Calculation Note For Diesel Generator Sizing of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0008 | BK-SSGRL-PEDCO-110-EL-CN-0008Calculation Note For Diesel Generator Sizing of Well Pads | 2022-01-26 | 2022-12-20
Calculation Note For DC Charger of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0009 | BK-SSGRL-PEDCO-110-EL-CN-0009Calculation Note For DC Charger of Well Pads | 2022-01-26 | 2022-12-20
Calculation Note For LV Capacitor Bank of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0010 | BK-SSGRL-PEDCO-110-EL-CN-0010Calculation Note For LV Capacitor Bank of Well Pads | 2022-01-29 | 2022-12-20
Calculation Note For 11 KV Over Head Line Sag and Tension | BK-SSGRL-PEDCO-110-EL-CN-0011 | BK-SSGRL-PEDCO-110-EL-CN-0011Calculation Note For 11 KV Over Head Line Sag and Tension | 2021-10-13 | 2022-12-20
Calculation Note For 33 KV Over Head Line Sag and Tension | BK-SSGRL-PEDCO-110-EL-CN-0012 | BK-SSGRL-PEDCO-110-EL-CN-0012Calculation Note For 33 KV Over Head Line Sag and Tension | 2021-10-11 | 2022-12-20
Data Sheets For UPS of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0002 | BK-SSGRL-PEDCO-110-EL-DT-0002Data Sheets For UPS of Well Pads | 0 | 0
Data Sheets For DC Charger of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0003 | BK-SSGRL-PEDCO-110-EL-DT-0003Data Sheets For DC Charger of Well Pads | 2022-01-29 | 2022-12-20
Data Sheets For Diesel Generator of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0004 | BK-SSGRL-PEDCO-110-EL-DT-0004Data Sheets For Diesel Generator of Well Pads | 2021-09-20 | 2022-12-20
Data Sheets For Local Control Stations (LCS) of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0005 | BK-SSGRL-PEDCO-110-EL-DT-0005Data Sheets For Local Control Stations (LCS) of Well Pads | 2021-08-30 | 2022-12-20
Data Sheets For LV Capacitor Bank of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0006 | BK-SSGRL-PEDCO-110-EL-DT-0006Data Sheets For LV Capacitor Bank of Well Pads | 2021-09-12 | 2022-12-20
Data Sheets For LV Switchgear of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0008 | BK-SSGRL-PEDCO-110-EL-DT-0008Data Sheets For LV Switchgear of Well Pads | 2022-02-19 | 2022-12-20
Data Sheets For Power & Control Cables of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0009 | BK-SSGRL-PEDCO-110-EL-DT-0009Data Sheets For Power & Control Cables of Well Pads | 2021-09-13 | 2022-12-20
Data Sheets For Power Transformers of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0010 | BK-SSGRL-PEDCO-110-EL-DT-0010Data Sheets For Power Transformers of Well Pads | 2021-09-15 | 2022-12-20
Data Sheets For Distribution & Lighting Panels of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0011 | BK-SSGRL-PEDCO-110-EL-DT-0011Data Sheets For Distribution & Lighting Panels of Well Pads | 2021-09-12 | 2022-12-20
Data Sheets For 11 KV Over Head Line Equipment | BK-SSGRL-PEDCO-110-EL-DT-0012 | BK-SSGRL-PEDCO-110-EL-DT-0012Data Sheets For 11 KV Over Head Line Equipment | 2021-11-10 | 2022-07-30
Data Sheets For 33 KV Over Head Line Equipment | BK-SSGRL-PEDCO-110-EL-DT-0013 | BK-SSGRL-PEDCO-110-EL-DT-0013Data Sheets For 33 KV Over Head Line Equipment | 2021-11-10 | 2022-07-30
Typical Installation Details For Over Head Line Equipment | BK-SSGRL-PEDCO-110-EL-DW-0001 | BK-SSGRL-PEDCO-110-EL-DW-0001Typical Installation Details For Over Head Line Equipment | 2021-08-22 | 2022-10-26
Installation Detail & Notes for Connection OHL to Gantries for Wells | BK-SSGRL-PEDCO-110-EL-DW-0002 | BK-SSGRL-PEDCO-110-EL-DW-0002Installation Detail & Notes for Connection OHL to Gantries for Wells | 2022-03-06 | 2022-12-20
Electrical Typical Schematic Diagrams For LV Panels of Well Pads | BK-SSGRL-PEDCO-110-EL-DG-0001 | BK-SSGRL-PEDCO-110-EL-DG-0001Electrical Typical Schematic Diagrams For LV Panels of Well Pads | 2021-08-30 | 2022-12-20
Control Logic Diagram For LV Incomers of Well Pads | BK-SSGRL-PEDCO-110-EL-LD-0001 | BK-SSGRL-PEDCO-110-EL-LD-0001Control Logic Diagram For LV Incomers of Well Pads | 2021-08-30 | 2022-12-20
Earthing Layout For Electrical Tower (Gantry) of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0001 | BK-SSGRL-PEDCO-110-EL-PY-0001Earthing Layout For Electrical Tower (Gantry) of Well Pads | 0 | 0
Cable Route Layout For Electrical Tower (Gantry) of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0002 | BK-SSGRL-PEDCO-110-EL-PY-0002Cable Route Layout For Electrical Tower (Gantry) of Well Pads | 0 | 0
Overall Single Line Diagram of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0001 | BK-SSGRL-PEDCO-110-EL-SL-0001Overall Single Line Diagram of Well Pads | 2022-03-02 | 2022-12-20
Single Line Diagram For LV Switchgear of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0002 | BK-SSGRL-PEDCO-110-EL-SL-0002Single Line Diagram For LV Switchgear of Well Pads | 2022-02-08 | 2022-12-20
Single Line Diagram For LV Power Distribution Panel of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0003 | BK-SSGRL-PEDCO-110-EL-SL-0003Single Line Diagram For LV Power Distribution Panel of Well Pads | 2022-05-14 | 2022-12-20
Single Line Diagram For DC Charger of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0004 | BK-SSGRL-PEDCO-110-EL-SL-0004Single Line Diagram For DC Charger of Well Pads | 2022-02-06 | 2022-12-20
Single Line Diagram For Capacitor Banks of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0005 | BK-SSGRL-PEDCO-110-EL-SL-0005Single Line Diagram For Capacitor Banks of Well Pads | 2022-02-02 | 2022-12-20
Interconnection Wiring Diagram of Well Pads | BK-SSGRL-PEDCO-110-EL-DG-0002 | BK-SSGRL-PEDCO-110-EL-DG-0002Interconnection Wiring Diagram of Well Pads | 0 | 0
Area Lighting & Small Power Layout of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0003 | BK-SSGRL-PEDCO-110-EL-PY-0003Area Lighting & Small Power Layout of Well Pads | 2022-05-14 | 2022-12-20
Lighting & Small Power Layout For Switchgear Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0004 | BK-SSGRL-PEDCO-110-EL-PY-0004Lighting & Small Power Layout For Switchgear Building of Well Pads | 2022-05-11 | 2022-12-20
Lighting & Small Power Layout For Security Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0005 | BK-SSGRL-PEDCO-110-EL-PY-0005Lighting & Small Power Layout For Security Building of Well Pads | 2022-05-07 | 2022-12-20
Area Electrical Cable Route & Section Layout of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0006 | BK-SSGRL-PEDCO-110-EL-PY-0006Area Electrical Cable Route & Section Layout of Well Pads | 2022-05-28 | 2022-12-20
Electrical Cable Route & Section Layout For Switchgear Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0007 | BK-SSGRL-PEDCO-110-EL-PY-0007Electrical Cable Route & Section Layout For Switchgear Building of Well Pads | 2022-05-25 | 2022-12-20
Electrical Equipment Arrangement Layout For Switchgear Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0008 | BK-SSGRL-PEDCO-110-EL-PY-0008Electrical Equipment Arrangement Layout For Switchgear Building of Well Pads | 2022-05-23 | 2022-12-20
Earthing & Lightning Layout for well pads | BK-SSGRL-PEDCO-110-EL-PY-0010 | BK-SSGRL-PEDCO-110-EL-PY-0010Earthing & Lightning Layout for well pads | 2022-10-11 | 0
Electrical Load List of Well Pads | BK-SSGRL-PEDCO-110-EL-LI-0001 | BK-SSGRL-PEDCO-110-EL-LI-0001Electrical Load List of Well Pads | 2022-01-25 | 2022-12-20
Electrical Power & Control Cable List of Well Pads | BK-SSGRL-PEDCO-110-EL-LI-0002 | BK-SSGRL-PEDCO-110-EL-LI-0002Electrical Power & Control Cable List of Well Pads | 2022-05-25 | 2022-12-20
Cable Drum Schedule and Cutting List of Well Pads | BK-SSGRL-PEDCO-110-EL-LI-0003 | BK-SSGRL-PEDCO-110-EL-LI-0003Cable Drum Schedule and Cutting List of Well Pads | 0 | 0
Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report of Well Pads | BK-SSGRL-PEDCO-110-EL-RT-0002 | BK-SSGRL-PEDCO-110-EL-RT-0002Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report of Well Pads | 0 | 0
Relay Coordination & Setting Study Report of Well Pads | BK-SSGRL-PEDCO-110-EL-RT-0003 | BK-SSGRL-PEDCO-110-EL-RT-0003Relay Coordination & Setting Study Report of Well Pads | 0 | 0
11KV Over Head Line Study Report | BK-SSGRL-PEDCO-110-EL-RT-0004 | BK-SSGRL-PEDCO-110-EL-RT-000411KV Over Head Line Study Report | 2022-03-29 | 2022-12-20
33KV Over Head Line Study Report | BK-SSGRL-PEDCO-110-EL-RT-0005 | BK-SSGRL-PEDCO-110-EL-RT-000533KV Over Head Line Study Report | 2022-03-29 | 2022-12-20
BINAK Oil Field Project Overall Well Location/Facilities Layout | BK-SSGRL-PEDCO-110-CV-PY-0001 | BK-SSGRL-PEDCO-110-CV-PY-0001BINAK Oil Field Project Overall Well Location/Facilities Layout | 2022-04-06 | 2022-08-28
Calculation Note For Flood Control | BK-SSGRL-PEDCO-110-CV-CN-0001 | BK-SSGRL-PEDCO-110-CV-CN-0001Calculation Note For Flood Control | 2021-12-05 | 2022-12-20
Typical Drawing For Rig Foundation Plan & Details | BK-SSGRL-PEDCO-110-ST-DW-0003 | BK-SSGRL-PEDCO-110-ST-DW-0003Typical Drawing For Rig Foundation Plan & Details | 0 | 0
Geotechnical Investigation Plan for Well Pads | BK-SSGRL-PEDCO-110-GT-PR-0001 | BK-SSGRL-PEDCO-110-GT-PR-0001Geotechnical Investigation Plan for Well Pads | 2021-08-11 | 2021-10-25
Process Flow Diagram - W018S | BK-W018S-PEDCO-110-PR-PF-0001 | BK-W018S-PEDCO-110-PR-PF-0001Process Flow Diagram - W018S | 2021-11-02 | 2022-12-20
P&ID - W018S | BK-W018S-PEDCO-110-PR-PI-0001 | BK-W018S-PEDCO-110-PR-PI-0001P&ID - W018S | 2021-11-01 | 2022-12-20
Line List - W018S | BK-W018S-PEDCO-110-PR-LI-0001 | BK-W018S-PEDCO-110-PR-LI-0001Line List - W018S | 2021-11-08 | 2022-12-20
Flow line Hydraulic Calculation Report | BK-W018S-PEDCO-110-PR-RT-0001 | BK-W018S-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-10-08
Process Data Sheets For Instrument Devices - W018S | BK-W018S-PEDCO-110-PR-DT-0001 | BK-W018S-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W018S | 2022-04-12 | 2022-12-20
Plot Plan Drawing - W018S | BK-W018S-PEDCO-110-PI-PY-0001 | BK-W018S-PEDCO-110-PI-PY-0001Plot Plan Drawing - W018S | 2021-08-22 | 2022-12-20
Piping Plan - W018S | BK-W018S-PEDCO-110-PI-DW-0001 | BK-W018S-PEDCO-110-PI-DW-0001Piping Plan - W018S | 0 | 0
Isometric Drawings - W018S | BK-W018S-PEDCO-110-PI-DW-0002 | BK-W018S-PEDCO-110-PI-DW-0002Isometric Drawings - W018S | 0 | 0
Material Flow Diagram - W018S | BK-W018S-PEDCO-110-PI-DG-0001 | BK-W018S-PEDCO-110-PI-DG-0001Material Flow Diagram - W018S | 2021-11-08 | 2022-12-20
Piping Support List - W018S | BK-W018S-PEDCO-110-PI-LI-0001 | BK-W018S-PEDCO-110-PI-LI-0001Piping Support List - W018S | 0 | 0
Critical Line List - W018S | BK-W018S-PEDCO-110-PI-LI-0002 | BK-W018S-PEDCO-110-PI-LI-0002Critical Line List - W018S | 2022-04-27 | 2022-12-20
PDMS Model Review Report (60%) - W018S | BK-W018S-PEDCO-110-PI-RT-0001 | BK-W018S-PEDCO-110-PI-RT-0001PDMS Model Review Report (60%) - W018S | 2022-04-04 | 2022-12-20
PDMS Model Review Report (90%) - W018S | BK-W018S-PEDCO-110-PI-RT-0002 | BK-W018S-PEDCO-110-PI-RT-0002PDMS Model Review Report (90%) - W018S | 0 | 0
MTO For Pipes - W018S | BK-W018S-PEDCO-110-PI-MT-0001 | BK-W018S-PEDCO-110-PI-MT-0001MTO For Pipes - W018S | 2021-12-04 | 0
MTO For Fittings - W018S | BK-W018S-PEDCO-110-PI-MT-0002 | BK-W018S-PEDCO-110-PI-MT-0002MTO For Fittings - W018S | 2021-12-20 | 0
MTO For Flanges - W018S | BK-W018S-PEDCO-110-PI-MT-0003 | BK-W018S-PEDCO-110-PI-MT-0003MTO For Flanges - W018S | 2021-12-20 | 0
MTO For Manual Valves - W018S | BK-W018S-PEDCO-110-PI-MT-0004 | BK-W018S-PEDCO-110-PI-MT-0004MTO For Manual Valves - W018S | 2021-12-20 | 0
MTO For Gaskets - W018S | BK-W018S-PEDCO-110-PI-MT-0005 | BK-W018S-PEDCO-110-PI-MT-0005MTO For Gaskets - W018S | 2021-12-20 | 0
MTO For Bolt & Nuts - W018S | BK-W018S-PEDCO-110-PI-MT-0006 | BK-W018S-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W018S | 2021-12-20 | 0
Flow line Transversal Drawings - W018S | BK-W018S-PEDCO-110-PL-DW-0002 | BK-W018S-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W018S | 0 | 0
Road Crossing Location List | BK-W018S-PEDCO-110-PL-LI-0001 | BK-W018S-PEDCO-110-PL-LI-0001Road Crossing Location List | 0 | 0
MTO For Line Pipes (Flow lines) - W018S | BK-W018S-PEDCO-110-PL-MT-0001 | BK-W018S-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W018S | 2021-08-22 | 2022-12-20
Instrument Location Layout Drawing - W018S | BK-W018S-PEDCO-110-IN-PY-0001 | BK-W018S-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W018S | 2022-02-23 | 2022-12-20
MTO For Instrument Tube and Fitting - W018S | BK-W018S-PEDCO-110-IN-MT-0001 | BK-W018S-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W018S | 2021-11-14 | 0
MTO For Instrument Cable Tray - W018S | BK-W018S-PEDCO-110-IN-MT-0002 | BK-W018S-PEDCO-110-IN-MT-0002MTO For Instrument Cable Tray - W018S | 2021-11-14 | 0
Hazardous Area Classification Layout - W018S | BK-W018S-PEDCO-110-SA-PY-0001 | BK-W018S-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W018S | 2021-11-15 | 2022-05-01
Safety & Fire Fighting Equipment Location Layout - W018S | BK-W018S-PEDCO-110-SA-PY-0002 | BK-W018S-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W018S | 2021-09-07 | 2022-04-19
Escape Route & Safety Sign Layout - W018S | BK-W018S-PEDCO-110-SA-PY-0003 | BK-W018S-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W018S | 2021-11-15 | 2022-05-16
Hazard Source List - W018S | BK-W018S-PEDCO-110-SA-LI-0001 | BK-W018S-PEDCO-110-SA-LI-0001Hazard Source List - W018S | 2021-11-09 | 2022-07-26
MTO For Fire Fighting & Safety Equipment - W018S | BK-W018S-PEDCO-110-SA-MT-0001 | BK-W018S-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W018S | 2021-11-15 | 0
MTO For Safety Sign - W018S | BK-W018S-PEDCO-110-SA-MT-0002 | BK-W018S-PEDCO-110-SA-MT-0002MTO For Safety Sign - W018S | 2021-11-15 | 0
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W018 | BK-W018S-PEDCO-110-AR-DW-0001 | BK-W018S-PEDCO-110-AR-DW-0001Architectural Drawing For WHCP/HPU Shelter of Well Pads - W018 | 2022-02-21 | 2022-12-20
General Civil Layout - W018S | BK-W018S-PEDCO-110-CV-PY-0001 | BK-W018S-PEDCO-110-CV-PY-0001General Civil Layout - W018S | 2021-07-28 | 2021-12-27
Civil and Structural drawings - W018S | BK-W018S-PEDCO-110-CV-PY-0002 | BK-W018S-PEDCO-110-CV-PY-0002Civil and Structural drawings - W018S | 2021-07-28 | 2022-11-08
Rough Grading Plans -W018S | BK-W018S-PEDCO-110-CV-DW-0001 | BK-W018S-PEDCO-110-CV-DW-0001Rough Grading Plans -W018S | 2021-10-30 | 2022-03-13
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W018S | BK-W018S-PEDCO-110-CV-CN-0001 | BK-W018S-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W018S | 2022-02-19 | 2022-12-20
MTO For Civil Works - W018S | BK-W018S-PEDCO-110-CV-MT-0001 | BK-W018S-PEDCO-110-CV-MT-0001MTO For Civil Works - W018S | 2022-05-15 | 0
Structure Drawing For WHCP/HPU Shelter - W018S | BK-W018S-PEDCO-110-ST-DW-0001 | BK-W018S-PEDCO-110-ST-DW-0001Structure Drawing For WHCP/HPU Shelter - W018S | 2022-03-27 | 2022-05-16
Platform Structure Drawing - W018S | BK-W018S-PEDCO-110-ST-DW-0002 | BK-W018S-PEDCO-110-ST-DW-0002Platform Structure Drawing - W018S | 2022-04-17 | 2022-09-26
CALCULATION NOTE WHCP/ HPU SHELTER | BK-W018S-PEDCO-110-ST-CN-0003 | BK-W018S-PEDCO-110-ST-CN-0003 CALCULATION NOTE WHCP/ HPU SHELTER | 2022-05-01 | 2022-05-22
MTO For Structural Works - W018S | BK-W018S-PEDCO-110-ST-MT-0001 | BK-W018S-PEDCO-110-ST-MT-0001MTO For Structural Works - W018S | 2022-05-02 | 2022-12-20
Geotechnical Investigation Report - W018S | BK-W018S-PEDCO-110-GT-RT-0001 | BK-W018S-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W018S | 2022-02-26 | 2022-12-20
Flow line Plan & Profile Drawings - W018S | BK-W018S-PEDCO-110-SU-DW-0001 | BK-W018S-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W018S | 2022-02-26 | 2022-12-20
PMR For Pipes - W018S | BK-W018S-PEDCO-110-PI-MR-0001 | BK-W018S-PEDCO-110-PI-MR-0001PMR For Pipes - W018S | 2021-12-06 | 2022-12-20
TBE For Pipes - W018S | BK-W018S-PEDCO-110-PI-TB-0001 | BK-W018S-PEDCO-110-PI-TB-0001TBE For Pipes - W018S | 0 | 0
PMR For Fittings - W018S | BK-W018S-PEDCO-110-PI-MR-0002 | BK-W018S-PEDCO-110-PI-MR-0002PMR For Fittings - W018S | 2022-09-04 | 0
TBE For Fitting - W018S | BK-W018S-PEDCO-110-PI-TB-0002 | BK-W018S-PEDCO-110-PI-TB-0002TBE For Fitting - W018S | 2022-08-20 | 0
PMR For Flanges - W018S | BK-W018S-PEDCO-110-PI-MR-0003 | BK-W018S-PEDCO-110-PI-MR-0003PMR For Flanges - W018S | 2022-09-04 | 0
TBE For Flanges - W018S | BK-W018S-PEDCO-110-PI-TB-0003 | BK-W018S-PEDCO-110-PI-TB-0003TBE For Flanges - W018S | 2022-02-13 | 2022-12-20
PMR For Manual Valves - W018S | BK-W018S-PEDCO-110-PI-MR-0004 | BK-W018S-PEDCO-110-PI-MR-0004PMR For Manual Valves - W018S | 2022-09-04 | 0
TBE For Manual Valves - W018S | BK-W018S-PEDCO-110-PI-TB-0004 | BK-W018S-PEDCO-110-PI-TB-0004TBE For Manual Valves - W018S | 2022-02-13 | 2022-12-20
PMR For Gaskets - W018S | BK-W018S-PEDCO-110-PI-MR-0005 | BK-W018S-PEDCO-110-PI-MR-0005PMR For Gaskets - W018S | 2022-09-04 | 0
TBE For Gaskets - W018S | BK-W018S-PEDCO-110-PI-TB-0005 | BK-W018S-PEDCO-110-PI-TB-0005TBE For Gaskets - W018S | 2022-02-13 | 2022-12-20
PMR For Bolt/Nuts - W018S | BK-W018S-PEDCO-110-PI-MR-0006 | BK-W018S-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W018S | 2022-09-04 | 0
TBE For Bolt/Nuts - W018S | BK-W018S-PEDCO-110-PI-TB-0006 | BK-W018S-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W018S | 0 | 0
PMR For Sampling Connection Set - W018S | BK-W018S-PEDCO-110-PI-MR-0007 | BK-W018S-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W018S | 2022-10-23 | 0
TBE For Sampling Connection | BK-W018S-PEDCO-110-PI-TB-0007 | BK-W018S-PEDCO-110-PI-TB-0007TBE For Sampling Connection | 2022-10-23 | 0
PMR For Stone Trap - W018S | BK-W018S-PEDCO-110-PI-MR-0008 | BK-W018S-PEDCO-110-PI-MR-0008PMR For Stone Trap - W018S | 2022-04-27 | 2022-12-20
TBE For Stone Trap - W018S | BK-W018S-PEDCO-110-PI-TB-0008 | BK-W018S-PEDCO-110-PI-TB-0008TBE For Stone Trap - W018S | 2022-05-24 | 2022-12-20
PMR For Pipe Support - W018S | BK-W018S-PEDCO-110-PI-MR-0010 | BK-W018S-PEDCO-110-PI-MR-0010PMR For Pipe Support - W018S | 0 | 0
TBE For Pipe Support - W018S | BK-W018S-PEDCO-110-PI-TB-0010 | BK-W018S-PEDCO-110-PI-TB-0010TBE For Pipe Support - W018S | 0 | 0
PMR For Line Pipes - W018S | BK-W018S-PEDCO-110-PL-MR-0001 | BK-W018S-PEDCO-110-PL-MR-0001PMR For Line Pipes - W018S | 2021-12-06 | 2022-12-20
TBE For Line Pipes - W018S | BK-W018S-PEDCO-110-PL-TB-0001 | BK-W018S-PEDCO-110-PL-TB-0001TBE For Line Pipes - W018S | 2022-02-19 | 2022-12-20
PMR For Flow Line Support - W018S | BK-W018S-PEDCO-110-PL-MR-0002 | BK-W018S-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W018S | 0 | 0
TBE For Flow Line Support - W018S | BK-W018S-PEDCO-110-PL-TB-0002 | BK-W018S-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W018S | 0 | 0
PMR For WHCP/HPU - W018S | BK-W018S-PEDCO-110-IN-MR-0001 | BK-W018S-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W018S | 2021-11-15 | 2022-12-20
TBE/TBA For WHCP/HPU - W018S | BK-W018S-PEDCO-110-IN-TB-0001 | BK-W018S-PEDCO-110-IN-TB-0001TBE/TBA For WHCP/HPU - W018S | 2021-11-30 | 0
PMR For Field Instrumentations - W018S | BK-W018S-PEDCO-110-IN-MR-0002 | BK-W018S-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W018S | 2021-12-13 | 0
TBE/TBA For Field Instrumentations - W018S | BK-W018S-PEDCO-110-IN-TB-0002 | BK-W018S-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W018S | 2022-10-26 | 0
PMR For Instrument Bulk Items - W018S | BK-W018S-PEDCO-110-IN-MR-0003 | BK-W018S-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W018S | 2022-01-18 | 0
TBE/TBA For Instrument Bulk Items - W018S | BK-W018S-PEDCO-110-IN-TB-0003 | BK-W018S-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items - W018S | 2022-02-02 | 2022-12-20
PMR For Fire Fighting and Safety Equipment - W018S | BK-W018S-PEDCO-110-SA-MR-0001 | BK-W018S-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W018S | 2021-12-08 | 2022-10-24
TBE For Fire Fighting and Safety Equipment - W018S | BK-W018S-PEDCO-110-SA-TB-0001 | BK-W018S-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W018S | 2022-03-12 | 2022-12-20
PMR For Fire Safety Sign - W018S | BK-W018S-PEDCO-110-SA-MR-0002 | BK-W018S-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W018S | 2021-12-08 | 0
TBE For Fire Safety Sign - W018S | BK-W018S-PEDCO-110-SA-TB-0002 | BK-W018S-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W018S | 2022-03-12 | 2022-12-20
PMR For Steel Structure Items - W018S | BK-W018S-PEDCO-110-ST-MR-0001 | BK-W018S-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W018S | 0 | 0
TBE For Steel Structure Items - W018S | BK-W018S-PEDCO-110-ST-TB-0001 | BK-W018S-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W018S | 0 | 0
PMR For Anchor Bolts - W018S | BK-W018S-PEDCO-110-ST-MR-0002 | BK-W018S-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W018S | 0 | 0
TBE For Anchor Bolts - W018S | BK-W018S-PEDCO-110-ST-TB-0002 | BK-W018S-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W018S | 0 | 0
PMR For Geomembrane - W018S | BK-W018S-PEDCO-110-CV-MR-0001 | BK-W018S-PEDCO-110-CV-MR-0001PMR For Geomembrane - W018S | 2022-04-03 | 2022-12-20
TBE For Geomembrane - W018S | BK-W018S-PEDCO-110-CV-TB-0001 | BK-W018S-PEDCO-110-CV-TB-0001TBE For Geomembrane - W018S | 0 | 0
PMR For Geotextile - W018S | BK-W018S-PEDCO-110-CV-MR-0002 | BK-W018S-PEDCO-110-CV-MR-0002PMR For Geotextile - W018S | 2022-04-03 | 2022-12-20
TBE For Geotextile - W018S | BK-W018S-PEDCO-110-CV-TB-0002 | BK-W018S-PEDCO-110-CV-TB-0002TBE For Geotextile - W018S | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - W018S | BK-W018S-PEDCO-110-CO-PR-0001 | BK-W018S-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W018S | 0 | 0
Technical/Site Queries | BK-W018S-PEDCO-110-GE-TQ-0001 | BK-W018S-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - W018S | BK-W018S-PEDCO-110-GE-DO-0001 | BK-W018S-PEDCO-110-GE-DO-0001As-Built Document Booklets - W018S | 0 | 0
Operating Manual - W018S | BK-W018S-PEDCO-110-GE-ML-0001 | BK-W018S-PEDCO-110-GE-ML-0001Operating Manual - W018S | 0 | 0
As-Built Document Booklets - W018S | BK-W018S-PEDCO-110-GE-DO-0001 | BK-W018S-PEDCO-110-GE-DO-0001As-Built Document Booklets - W018S | 0 | 0
Final Engineering Dossier - W018S | BK-W018S-PEDCO-110-GE-DO-0002 | BK-W018S-PEDCO-110-GE-DO-0002Final Engineering Dossier - W018S | 0 | 0
Process Flow Diagram - W028 | BK-W028-PEDCO-110-PR-PF-0001 | BK-W028-PEDCO-110-PR-PF-0001Process Flow Diagram - W028 | 2021-11-02 | 2022-12-20
P&ID - W028 | BK-W028-PEDCO-110-PR-PI-0001 | BK-W028-PEDCO-110-PR-PI-0001P&ID - W028 | 2021-11-01 | 2022-12-20
Line List - W028 | BK-W028-PEDCO-110-PR-LI-0001 | BK-W028-PEDCO-110-PR-LI-0001Line List - W028 | 2021-11-08 | 2022-12-20
Flow line Hydraulic Calculation Report | BK-W028-PEDCO-110-PR-RT-0001 | BK-W028-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-10-08
Process Data Sheets For Instrument Devices - W028 | BK-W028-PEDCO-110-PR-DT-0001 | BK-W028-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W028 | 2022-04-12 | 2022-12-20
Plot Plan Drawing - W028 | BK-W028-PEDCO-110-PI-DW-0001 | BK-W028-PEDCO-110-PI-DW-0001Plot Plan Drawing - W028 | 2022-02-02 | 2022-12-20
Piping Plan - W028 | BK-W028-PEDCO-110-PI-DW-0002 | BK-W028-PEDCO-110-PI-DW-0002Piping Plan - W028 | 0 | 0
Isometric Drawings - W028 | BK-W028-PEDCO-110-PI-DW-0003 | BK-W028-PEDCO-110-PI-DW-0003Isometric Drawings - W028 | 0 | 0
Material Flow Diagram - W028 | BK-W028-PEDCO-110-PI-DG-0001 | BK-W028-PEDCO-110-PI-DG-0001Material Flow Diagram - W028 | 2021-11-08 | 2022-12-20
Piping Support List - W028 | BK-W028-PEDCO-110-PI-LI-0001 | BK-W028-PEDCO-110-PI-LI-0001Piping Support List - W028 | 0 | 0
Critical Line List - W028 | BK-W028-PEDCO-110-PI-LI-0002 | BK-W028-PEDCO-110-PI-LI-0002Critical Line List - W028 | 2022-05-02 | 2022-12-20
PDMS Model Review Report (60%) - W028 | BK-W028-PEDCO-110-PI-RT-0001 | BK-W028-PEDCO-110-PI-RT-0001PDMS Model Review Report (60%) - W028 | 2022-07-03 | 2022-12-20
PDMS Model Review Report (90%) - W028 | BK-W028-PEDCO-110-PI-RT-0002 | BK-W028-PEDCO-110-PI-RT-0002PDMS Model Review Report (90%) - W028 | 0 | 0
MTO For Pipes - W028 | BK-W028-PEDCO-110-PI-MT-0001 | BK-W028-PEDCO-110-PI-MT-0001MTO For Pipes - W028 | 2021-12-04 | 0
MTO For Fittings - W028 | BK-W028-PEDCO-110-PI-MT-0002 | BK-W028-PEDCO-110-PI-MT-0002MTO For Fittings - W028 | 2021-12-20 | 0
MTO For Flanges - W028 | BK-W028-PEDCO-110-PI-MT-0003 | BK-W028-PEDCO-110-PI-MT-0003MTO For Flanges - W028 | 2021-12-20 | 0
MTO For Manual Valves - W028 | BK-W028-PEDCO-110-PI-MT-0004 | BK-W028-PEDCO-110-PI-MT-0004MTO For Manual Valves - W028 | 2021-12-20 | 0
MTO For Gaskets - W028 | BK-W028-PEDCO-110-PI-MT-0005 | BK-W028-PEDCO-110-PI-MT-0005MTO For Gaskets - W028 | 2021-12-20 | 0
MTO For Bolt & Nuts - W028 | BK-W028-PEDCO-110-PI-MT-0006 | BK-W028-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W028 | 2021-12-20 | 0
Flow line Transversal Drawings - W028 | BK-W028-PEDCO-110-PL-DW-0002 | BK-W028-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W028 | 0 | 0
Road Crossing Location List | BK-W028-PEDCO-110-PL-LI-0001 | BK-W028-PEDCO-110-PL-LI-0001Road Crossing Location List | 0 | 0
MTO For Line Pipes (Flow lines) - W028 | BK-W028-PEDCO-110-PL-MT-0001 | BK-W028-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W028 | 2021-08-22 | 2022-12-20
Instrument Location Layout Drawing - W028 | BK-W028-PEDCO-110-IN-PY-0001 | BK-W028-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W028 | 2022-05-16 | 2022-12-20
MTO For Instrument Tube and Fitting - W028 | BK-W028-PEDCO-110-IN-MT-0001 | BK-W028-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W028 | 2021-11-14 | 0
MTO For Instrument Cable Tray - W028 | BK-W028-PEDCO-110-IN-MT-0002 | BK-W028-PEDCO-110-IN-MT-0002MTO For Instrument Cable Tray - W028 | 2021-11-14 | 0
Hazardous Area Classification Layout - W028 | BK-W028-PEDCO-110-SA-PY-0001 | BK-W028-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W028 | 2022-05-07 | 2022-12-20
Safety & Fire Fighting Equipment Location Layout - W028 | BK-W028-PEDCO-110-SA-PY-0002 | BK-W028-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W028 | 2022-04-16 | 2022-12-20
Escape Route & Safety Sign Layout - W028 | BK-W028-PEDCO-110-SA-PY-0003 | BK-W028-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W028 | 2022-04-17 | 2022-12-20
Hazard Source List - W028 | BK-W028-PEDCO-110-SA-LI-0001 | BK-W028-PEDCO-110-SA-LI-0001Hazard Source List - W028 | 2021-11-09 | 2022-07-26
MTO For Fire Fighting & Safety Equipment - W028 | BK-W028-PEDCO-110-SA-MT-0001 | BK-W028-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W028 | 2021-12-08 | 0
MTO For Safety Sign - W028 | BK-W028-PEDCO-110-SA-MT-0002 | BK-W028-PEDCO-110-SA-MT-0002MTO For Safety Sign - W028 | 2021-12-08 | 0
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W028 | BK-W028-PEDCO-110-AR-DW-0001 | BK-W028-PEDCO-110-AR-DW-0001Architectural Drawing For WHCP/HPU Shelter of Well Pads - W028 | 2022-02-26 | 2022-12-20
General Civil Layout -W028 | BK-W028-PEDCO-110-CV-PY-0001 | BK-W028-PEDCO-110-CV-PY-0001General Civil Layout -W028 | 2021-10-19 | 2022-12-20
Civil and Structural drawings -W028 | BK-W028-PEDCO-110-CV-PY-0002 | BK-W028-PEDCO-110-CV-PY-0002Civil and Structural drawings -W028 | 2021-10-19 | 2022-12-20
Rough Grading Plans -W028 | BK-W028-PEDCO-110-CV-DW-0001 | BK-W028-PEDCO-110-CV-DW-0001Rough Grading Plans -W028 | 2021-10-11 | 2022-04-10
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W028 | BK-W028-PEDCO-110-CV-CN-0001 | BK-W028-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W028 | 0 | 0
MTO For Civil Works - W028 | BK-W028-PEDCO-110-CV-MT-0001 | BK-W028-PEDCO-110-CV-MT-0001MTO For Civil Works - W028 | 2022-05-09 | 2022-12-20
Platform Structure Drawing - W028 | BK-W028-PEDCO-110-ST-DW-0002 | BK-W028-PEDCO-110-ST-DW-0002Platform Structure Drawing - W028 | 2022-06-21 | 2022-12-20
MTO For Structural Works - W028 | BK-W028-PEDCO-110-ST-MT-0001 | BK-W028-PEDCO-110-ST-MT-0001MTO For Structural Works - W028 | 2022-05-02 | 2022-12-20
Geotechnical Investigation Report - W028 | BK-W028-PEDCO-110-GT-RT-0001 | BK-W028-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W028 | 2022-05-17 | 2022-12-20
Flow line Plan & Profile Drawings - W028 | BK-W028-PEDCO-110-SU-DW-0001 | BK-W028-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W028 | 2022-08-20 | 2022-12-20
PMR For Pipes - W028 | BK-W028-PEDCO-110-PI-MR-0001 | BK-W028-PEDCO-110-PI-MR-0001PMR For Pipes - W028 | 2021-12-06 | 2022-12-20
TBE For Pipes - W028 | BK-W028-PEDCO-110-PI-TB-0001 | BK-W028-PEDCO-110-PI-TB-0001TBE For Pipes - W028 | 0 | 0
PMR For Fittings - W028 | BK-W028-PEDCO-110-PI-MR-0002 | BK-W028-PEDCO-110-PI-MR-0002PMR For Fittings - W028 | 2022-09-04 | 0
TBE For Fitting - W028 | BK-W028-PEDCO-110-PI-TB-0002 | BK-W028-PEDCO-110-PI-TB-0002TBE For Fitting - W028 | 2022-08-20 | 0
PMR For Flanges - W028 | BK-W028-PEDCO-110-PI-MR-0003 | BK-W028-PEDCO-110-PI-MR-0003PMR For Flanges - W028 | 2022-09-04 | 0
TBE For Flanges - W028 | BK-W028-PEDCO-110-PI-TB-0003 | BK-W028-PEDCO-110-PI-TB-0003TBE For Flanges - W028 | 2022-02-13 | 2022-12-20
PMR For Manual Valves - W028 | BK-W028-PEDCO-110-PI-MR-0004 | BK-W028-PEDCO-110-PI-MR-0004PMR For Manual Valves - W028 | 2022-09-04 | 0
TBE For Manual Valves - W028 | BK-W028-PEDCO-110-PI-TB-0004 | BK-W028-PEDCO-110-PI-TB-0004TBE For Manual Valves - W028 | 2022-02-13 | 2022-12-20
PMR For Gaskets - W028 | BK-W028-PEDCO-110-PI-MR-0005 | BK-W028-PEDCO-110-PI-MR-0005PMR For Gaskets - W028 | 2022-09-04 | 0
TBE For Gaskets - W028 | BK-W028-PEDCO-110-PI-TB-0005 | BK-W028-PEDCO-110-PI-TB-0005TBE For Gaskets - W028 | 2022-02-13 | 2022-12-20
PMR For Bolt/Nuts - W028 | BK-W028-PEDCO-110-PI-MR-0006 | BK-W028-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W028 | 2022-09-04 | 0
TBE For Bolt/Nuts - W028 | BK-W028-PEDCO-110-PI-TB-0006 | BK-W028-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W028 | 0 | 0
PMR For Sampling Connection Set - W028 | BK-W028-PEDCO-110-PI-MR-0007 | BK-W028-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W028 | 2022-10-23 | 0
TBE For Sampling Connection Set - W028 | BK-W028-PEDCO-110-PI-TB-0007 | BK-W028-PEDCO-110-PI-TB-0007TBE For Sampling Connection Set - W028 | 2022-10-23 | 0
PMR For Stone Trap - W028 | BK-W028-PEDCO-110-PI-MR-0008 | BK-W028-PEDCO-110-PI-MR-0008PMR For Stone Trap - W028 | 2022-04-27 | 2022-12-20
TBE For Stone Trap - W028 | BK-W028-PEDCO-110-PI-TB-0008 | BK-W028-PEDCO-110-PI-TB-0008TBE For Stone Trap - W028 | 2022-05-24 | 2022-12-20
PMR For Pipe Support - W028 | BK-W028-PEDCO-110-PI-MR-0009 | BK-W028-PEDCO-110-PI-MR-0009PMR For Pipe Support - W028 | 0 | 0
TBE For Pipe Support - W028 | BK-W028-PEDCO-110-PI-TB-0009 | BK-W028-PEDCO-110-PI-TB-0009TBE For Pipe Support - W028 | 0 | 0
PMR For Line Pipes - W028 | BK-W028-PEDCO-110-PL-MR-0001 | BK-W028-PEDCO-110-PL-MR-0001PMR For Line Pipes - W028 | 2021-12-06 | 2022-12-20
TBE For Line Pipes - W028 | BK-W028-PEDCO-110-PL-TB-0001 | BK-W028-PEDCO-110-PL-TB-0001TBE For Line Pipes - W028 | 2022-02-19 | 2022-12-20
PMR For Flow Line Support - W028 | BK-W028-PEDCO-110-PL-MR-0002 | BK-W028-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W028 | 0 | 0
TBE For Flow Line Support - W028 | BK-W028-PEDCO-110-PL-TB-0002 | BK-W028-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W028 | 0 | 0
PMR For WHCP/HPU - W028 | BK-W028-PEDCO-110-IN-MR-0001 | BK-W028-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W028 | 2021-11-15 | 2022-12-20
TBE/TBA For WHCP/HPU - W028 | BK-W028-PEDCO-110-IN-TB-0001 | BK-W028-PEDCO-110-IN-TB-0001TBE/TBA For WHCP/HPU - W028 | 2021-12-01 | 0
PMR For Field Instrumentations - W028 | BK-W028-PEDCO-110-IN-MR-0002 | BK-W028-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W028 | 2021-12-13 | 0
TBE/TBA For Field Instrumentations - W028 | BK-W028-PEDCO-110-IN-TB-0002 | BK-W028-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W028 | 2022-10-26 | 0
PMR For Instrument Bulk Items - W028 | BK-W028-PEDCO-110-IN-MR-0003 | BK-W028-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W028 | 2022-01-16 | 0
TBE/TBA For Instrument Bulk Items - W028 | BK-W028-PEDCO-110-IN-TB-0003 | BK-W028-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items - W028 | 2022-02-02 | 2022-12-20
PMR For Fire Fighting and Safety Equipment - W028 | BK-W028-PEDCO-110-SA-MR-0001 | BK-W028-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W028 | 2021-12-08 | 0
TBE For Fire Fighting and Safety Equipment - W028 | BK-W028-PEDCO-110-SA-TB-0001 | BK-W028-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W028 | 0 | 0
PMR For Fire Safety Sign - W028 | BK-W028-PEDCO-110-SA-MR-0002 | BK-W028-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W028 | 2021-12-08 | 0
TBE For Fire Safety Sign - W028 | BK-W028-PEDCO-110-SA-TB-0002 | BK-W028-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W028 | 0 | 0
PMR For Steel Structure Items - W028 | BK-W028-PEDCO-110-ST-MR-0001 | BK-W028-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W028 | 0 | 0
TBE For Steel Structure Items - W028 | BK-W028-PEDCO-110-ST-TB-0001 | BK-W028-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W028 | 0 | 0
PMR For Anchor Bolts - W028 | BK-W028-PEDCO-110-ST-MR-0002 | BK-W028-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W028 | 0 | 0
TBE For Anchor Bolts - W028 | BK-W028-PEDCO-110-ST-TB-0002 | BK-W028-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W028 | 0 | 0
PMR For Geomembrane - W028 | BK-W028-PEDCO-110-CV-MR-0001 | BK-W028-PEDCO-110-CV-MR-0001PMR For Geomembrane - W028 | 2022-04-13 | 2022-12-20
TBE For Geomembrane - W028 | BK-W028-PEDCO-110-CV-TB-0001 | BK-W028-PEDCO-110-CV-TB-0001TBE For Geomembrane - W028 | 0 | 0
PMR For Geotextile - W028 | BK-W028-PEDCO-110-CV-MR-0002 | BK-W028-PEDCO-110-CV-MR-0002PMR For Geotextile - W028 | 2022-04-13 | 2022-12-20
TBE For Geotextile - W028 | BK-W028-PEDCO-110-CV-TB-0002 | BK-W028-PEDCO-110-CV-TB-0002TBE For Geotextile - W028 | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - W028 | BK-W028-PEDCO-110-CO-PR-0001 | BK-W028-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W028 | 0 | 0
Technical/Site Queries | BK-W028-PEDCO-110-GE-TQ-0001 | BK-W028-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - W028 | BK-W028-PEDCO-110-GE-DO-0001 | BK-W028-PEDCO-110-GE-DO-0001As-Built Document Booklets - W028 | 0 | 0
Operating Manual - W028 | BK-W028-PEDCO-110-GE-ML-0001 | BK-W028-PEDCO-110-GE-ML-0001Operating Manual - W028 | 0 | 0
As-Built Document Booklets - W028 | BK-W028-PEDCO-110-GE-DO-0001 | BK-W028-PEDCO-110-GE-DO-0001As-Built Document Booklets - W028 | 0 | 0
Final Engineering Dossier - W028 | BK-W028-PEDCO-110-GE-DO-0002 | BK-W028-PEDCO-110-GE-DO-0002Final Engineering Dossier - W028 | 0 | 0
Process Flow Diagram - W0046S | BK-W046S-PEDCO-110-PR-PF-0001 | BK-W046S-PEDCO-110-PR-PF-0001Process Flow Diagram - W0046S | 2021-11-01 | 0
P&ID - W0046S | BK-W046S-PEDCO-110-PR-PI-0001 | BK-W046S-PEDCO-110-PR-PI-0001P&ID - W0046S | 2021-11-01 | 2022-12-20
P&ID for Diesel Oil Drum- W0046S | BK-W046S-PEDCO-110-PR-PI-0002 | BK-W046S-PEDCO-110-PR-PI-0002P&ID for Diesel Oil Drum- W0046S | 2021-11-16 | 2022-12-20
P&ID for Potable Water Tank - W0046S | BK-W046S-PEDCO-110-PR-PI-0003 | BK-W046S-PEDCO-110-PR-PI-0003P&ID for Potable Water Tank - W0046S | 2021-11-16 | 2022-12-20
Line List - W0046S | BK-W046S-PEDCO-110-PR-LI-0001 | BK-W046S-PEDCO-110-PR-LI-0001Line List - W0046S | 2021-11-08 | 2022-12-20
Flow line Hydraulic Calculation Report | BK-W046S-PEDCO-110-PR-RT-0001 | BK-W046S-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-10-08
Process Data Sheets For Instrument Devices - W046S | BK-W046S-PEDCO-110-PR-DT-0001 | BK-W046S-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W046S | 2022-04-12 | 2022-12-20
HVAC Calculation Note For Switchgear Building - W046S | BK-W046S-PEDCO-110-HV-CN-0001 | BK-W046S-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - W046S | 2022-03-14 | 2022-12-20
HVAC Calculation Note For Security Building - W046S | BK-W046S-PEDCO-110-HV-CN-0002 | BK-W046S-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - W046S | 0 | 0
Data Sheets For Main HVAC Equipment - W046S | BK-W046S-PEDCO-110-HV-DT-0001 | BK-W046S-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - W046S | 0 | 0
HVAC System Layout For Switchgear Building - W046S | BK-W046S-PEDCO-110-HV-PY-0001 | BK-W046S-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - W046S | 2022-04-19 | 2022-12-20
HVAC System Layout For Security Building - W046S | BK-W046S-PEDCO-110-HV-PY-0002 | BK-W046S-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - W046S | 0 | 0
Plumbing & Sewage Piping Layout For Switchgear Building - W046S | BK-W046S-PEDCO-110-HV-PY-0003 | BK-W046S-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - W046S | 2022-10-18 | 0
Plumbing & Sewage Piping Layout For Security Building - W046S | BK-W046S-PEDCO-110-HV-PY-0004 | BK-W046S-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - W046S | 0 | 0
MTO For Building HVAC & Plumbing Systems - W046S | BK-W046S-PEDCO-110-HV-MT-0001 | BK-W046S-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - W046S | 0 | 0
Plot Plan Drawing - W046S | BK-W046S-PEDCO-110-PI-DW-0001 | BK-W046S-PEDCO-110-PI-DW-0001Plot Plan Drawing - W046S | 2022-05-09 | 2022-12-20
Piping Plan - W046S | BK-W046S-PEDCO-110-PI-DW-0002 | BK-W046S-PEDCO-110-PI-DW-0002Piping Plan - W046S | 0 | 0
Isometric Drawings - W046S | BK-W046S-PEDCO-110-PI-DW-0003 | BK-W046S-PEDCO-110-PI-DW-0003Isometric Drawings - W046S | 0 | 0
Material Flow Diagram - W046S | BK-W046S-PEDCO-110-PI-DG-0001 | BK-W046S-PEDCO-110-PI-DG-0001Material Flow Diagram - W046S | 2021-11-08 | 2022-12-20
Piping Support List - W046S | BK-W046S-PEDCO-110-PI-LI-0001 | BK-W046S-PEDCO-110-PI-LI-0001Piping Support List - W046S | 0 | 0
Critical Line List - W046S | BK-W046S-PEDCO-110-PI-LI-0002 | BK-W046S-PEDCO-110-PI-LI-0002Critical Line List - W046S | 0 | 0
PDMS Model Review Report (30%) - W046S | BK-W046S-PEDCO-110-PI-RT-0001 | BK-W046S-PEDCO-110-PI-RT-0001PDMS Model Review Report (30%) - W046S | 0 | 0
PDMS Model Review Report (60%) - W046S | BK-W046S-PEDCO-110-PI-RT-0002 | BK-W046S-PEDCO-110-PI-RT-0002PDMS Model Review Report (60%) - W046S | 0 | 0
PDMS Model Review Report (90%) - W046S | BK-W046S-PEDCO-110-PI-RT-0003 | BK-W046S-PEDCO-110-PI-RT-0003PDMS Model Review Report (90%) - W046S | 0 | 0
MTO For Pipes - W046S | BK-W046S-PEDCO-110-PI-MT-0001 | BK-W046S-PEDCO-110-PI-MT-0001MTO For Pipes - W046S | 2022-10-25 | 0
MTO For Fittings - W046S | BK-W046S-PEDCO-110-PI-MT-0002 | BK-W046S-PEDCO-110-PI-MT-0002MTO For Fittings - W046S | 0 | 0
MTO For Flanges - W046S | BK-W046S-PEDCO-110-PI-MT-0003 | BK-W046S-PEDCO-110-PI-MT-0003MTO For Flanges - W046S | 0 | 0
MTO For Manual Valves - W046S | BK-W046S-PEDCO-110-PI-MT-0004 | BK-W046S-PEDCO-110-PI-MT-0004MTO For Manual Valves - W046S | 0 | 0
MTO For Gaskets - W046S | BK-W046S-PEDCO-110-PI-MT-0005 | BK-W046S-PEDCO-110-PI-MT-0005MTO For Gaskets - W046S | 0 | 0
MTO For Bolt & Nuts - W046S | BK-W046S-PEDCO-110-PI-MT-0006 | BK-W046S-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W046S | 0 | 0
Flow line Transversal Drawings - W046S | BK-W046S-PEDCO-110-PL-DW-0002 | BK-W046S-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W046S | 0 | 0
Road Crossing Location List | BK-W046S-PEDCO-110-PL-LI-0001 | BK-W046S-PEDCO-110-PL-LI-0001Road Crossing Location List | 0 | 0
MTO For Line Pipes (Flow lines) - W046S | BK-W046S-PEDCO-110-PL-MT-0001 | BK-W046S-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W046S | 2021-08-22 | 2022-12-20
Instrument Location Layout Drawing - W046S | BK-W046S-PEDCO-110-IN-PY-0001 | BK-W046S-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W046S | 2022-05-16 | 2022-12-20
MTO For Instrument Tube and Fitting - W046S | BK-W046S-PEDCO-110-IN-MT-0001 | BK-W046S-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W046S | 2021-12-18 | 0
Hazardous Area Classification Layout - W046S | BK-W046S-PEDCO-110-SA-PY-0001 | BK-W046S-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W046S | 2022-05-25 | 2022-12-20
Safety & Fire Fighting Equipment Location Layout - W046S | BK-W046S-PEDCO-110-SA-PY-0002 | BK-W046S-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W046S | 2022-06-11 | 2022-12-20
Escape Route & Safety Sign Layout - W046S | BK-W046S-PEDCO-110-SA-PY-0003 | BK-W046S-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W046S | 2022-06-11 | 2022-12-20
Hazard Source List - W046S | BK-W046S-PEDCO-110-SA-LI-0001 | BK-W046S-PEDCO-110-SA-LI-0001Hazard Source List - W046S | 2021-11-09 | 2022-07-23
MTO For Fire Fighting & Safety Equipment - W046S | BK-W046S-PEDCO-110-SA-MT-0001 | BK-W046S-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W046S | 2022-06-14 | 2022-12-20
MTO For Safety Sign - W046S | BK-W046S-PEDCO-110-SA-MT-0002 | BK-W046S-PEDCO-110-SA-MT-0002MTO For Safety Sign - W046S | 2022-06-14 | 2022-12-20
MTO For Transmission Over Head Line - W046S | BK-W046S-PEDCO-110-EL-MT-0001 | BK-W046S-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - W046S | 2022-09-19 | 0
MTO For Earthing & Lightning Systems - W046S | BK-W046S-PEDCO-110-EL-MT-0002 | BK-W046S-PEDCO-110-EL-MT-0002MTO For Earthing & Lightning Systems - W046S | 2022-10-11 | 0
MTO For Lighting & Small Powers - W046S | BK-W046S-PEDCO-110-EL-MT-0003 | BK-W046S-PEDCO-110-EL-MT-0003MTO For Lighting & Small Powers - W046S | 2022-05-18 | 2022-12-20
MTO For Power & Control Cables - W046S | BK-W046S-PEDCO-110-EL-MT-0004 | BK-W046S-PEDCO-110-EL-MT-0004MTO For Power & Control Cables - W046S | 0 | 0
MTO For Tray/Ladder and Accessories - W046S | BK-W046S-PEDCO-110-EL-MT-0005 | BK-W046S-PEDCO-110-EL-MT-0005MTO For Tray/Ladder and Accessories - W046S | 0 | 0
MTO For Electrical Bulk Items - W046S | BK-W046S-PEDCO-110-EL-MT-0006 | BK-W046S-PEDCO-110-EL-MT-0006MTO For Electrical Bulk Items - W046S | 0 | 0
Architectural Drawing For Diesel Generator Shelter of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0001 | BK-W046S-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - W046S | 2022-05-01 | 2022-12-20
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0002 | BK-W046S-PEDCO-110-AR-DW-0002Architectural Drawing For WHCP/HPU Shelter of Well Pads - W046S | 0 | 0
Architectural Drawing For Switchgear Building of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0003 | BK-W046S-PEDCO-110-AR-DW-0003Architectural Drawing For Switchgear Building of Well Pads - W046S | 2022-09-07 | 0
Architectural Drawing For Security Building of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0004 | BK-W046S-PEDCO-110-AR-DW-0004Architectural Drawing For Security Building of Well Pads - W046S | 2022-09-19 | 2022-12-20
MTO For Architectural Works - W0046S | BK-W046S-PEDCO-110-AR-MT-0001 | BK-W046S-PEDCO-110-AR-MT-0001MTO For Architectural Works - W0046S | 0 | 0
General Civil Layout -W046S | BK-W046S-PEDCO-110-CV-PY-0001 | BK-W046S-PEDCO-110-CV-PY-0001General Civil Layout -W046S | 2022-05-02 | 2022-12-20
Civil and Structural drawings -W046S | BK-W046S-PEDCO-110-CV-PY-0002 | BK-W046S-PEDCO-110-CV-PY-0002Civil and Structural drawings -W046S | 2022-05-22 | 2022-12-20
Rough Grading Plans -W046S | BK-W046S-PEDCO-110-CV-DW-0001 | BK-W046S-PEDCO-110-CV-DW-0001Rough Grading Plans -W046S | 2021-12-12 | 2022-12-20
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W046S | BK-W046S-PEDCO-110-CV-CN-0001 | BK-W046S-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W046S | 0 | 0
MTO For Civil Works - W046S | BK-W046S-PEDCO-110-CV-MT-0001 | BK-W046S-PEDCO-110-CV-MT-0001MTO For Civil Works - W046S | 0 | 0
Fuel Oil Storage Drum Detail Drawing For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0003 | BK-W046S-PEDCO-110-ST-DW-0003Fuel Oil Storage Drum Detail Drawing For Well Pads - W046S | 0 | 0
Foundation Drawing For Security Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0004 | BK-W046S-PEDCO-110-ST-DW-0004Foundation Drawing For Security Building For Well Pads - W046S | 0 | 0
Structural Drawing For Security Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0005 | BK-W046S-PEDCO-110-ST-DW-0005Structural Drawing For Security Building For Well Pads - W046S | 0 | 0
Foundation Drawing For Switchgear Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0006 | BK-W046S-PEDCO-110-ST-DW-0006Foundation Drawing For Switchgear Building For Well Pads - W046S | 0 | 0
Structural Drawing For Switchgear Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0007 | BK-W046S-PEDCO-110-ST-DW-0007Structural Drawing For Switchgear Building For Well Pads - W046S | 0 | 0
Foundation Drawing For Potable Water Tank For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0008 | BK-W046S-PEDCO-110-ST-DW-0008Foundation Drawing For Potable Water Tank For Well Pads - W046S | 0 | 0
Foundation Drawing For Diesel Generator Shelter For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0009 | BK-W046S-PEDCO-110-ST-DW-0009Foundation Drawing For Diesel Generator Shelter For Well Pads - W046S | 0 | 0
Structural Drawing For Diesel Generator Shelter For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0010 | BK-W046S-PEDCO-110-ST-DW-0010Structural Drawing For Diesel Generator Shelter For Well Pads - W046S | 0 | 0
Platform Structure Drawing - W046S | BK-W046S-PEDCO-110-ST-DW-0012 | BK-W046S-PEDCO-110-ST-DW-0012Platform Structure Drawing - W046S | 0 | 0
Foundation Drawing For Transmission Line Tower - W046S | BK-W046S-PEDCO-110-ST-DW-0013 | BK-W046S-PEDCO-110-ST-DW-0013Foundation Drawing For Transmission Line Tower - W046S | 0 | 0
MTO For Structural Works - W046S | BK-W046S-PEDCO-110-ST-MT-0001 | BK-W046S-PEDCO-110-ST-MT-0001MTO For Structural Works - W046S | 0 | 0
Geotechnical Investigation Report - W046S | BK-W046S-PEDCO-110-GT-RT-0001 | BK-W046S-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W046S | 2022-08-03 | 2022-12-20
Flow line Plan & Profile Drawings - W046S | BK-W046S-PEDCO-110-SU-DW-0001 | BK-W046S-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W046S | 0 | 0
Over Head Line Plan and Profile - W046S | BK-W046S-PEDCO-110-SU-DW-0002 | BK-W046S-PEDCO-110-SU-DW-0002Over Head Line Plan and Profile - W046S | 2022-03-26 | 2022-12-20
PMR For Pipes - W046S | BK-W046S-PEDCO-110-PI-MR-0001 | BK-W046S-PEDCO-110-PI-MR-0001PMR For Pipes - W046S | 0 | 0
TBE For Pipes - W046S | BK-W046S-PEDCO-110-PI-TB-0001 | BK-W046S-PEDCO-110-PI-TB-0001TBE For Pipes - W046S | 0 | 0
PMR For Fittings - W046S | BK-W046S-PEDCO-110-PI-MR-0002 | BK-W046S-PEDCO-110-PI-MR-0002PMR For Fittings - W046S | 0 | 0
TBE For Fitting - W046S | BK-W046S-PEDCO-110-PI-TB-0002 | BK-W046S-PEDCO-110-PI-TB-0002TBE For Fitting - W046S | 0 | 0
PMR For Flanges - W046S | BK-W046S-PEDCO-110-PI-MR-0003 | BK-W046S-PEDCO-110-PI-MR-0003PMR For Flanges - W046S | 0 | 0
TBE For Flanges - W046S | BK-W046S-PEDCO-110-PI-TB-0003 | BK-W046S-PEDCO-110-PI-TB-0003TBE For Flanges - W046S | 0 | 0
PMR For Manual Valves - W046S | BK-W046S-PEDCO-110-PI-MR-0004 | BK-W046S-PEDCO-110-PI-MR-0004PMR For Manual Valves - W046S | 0 | 0
TBE For Manual Valves - W046S | BK-W046S-PEDCO-110-PI-TB-0004 | BK-W046S-PEDCO-110-PI-TB-0004TBE For Manual Valves - W046S | 0 | 0
PMR For Gaskets - W046S | BK-W046S-PEDCO-110-PI-MR-0005 | BK-W046S-PEDCO-110-PI-MR-0005PMR For Gaskets - W046S | 0 | 0
TBE For Gaskets - W046S | BK-W046S-PEDCO-110-PI-TB-0005 | BK-W046S-PEDCO-110-PI-TB-0005TBE For Gaskets - W046S | 0 | 0
PMR For Bolt/Nuts - W046S | BK-W046S-PEDCO-110-PI-MR-0006 | BK-W046S-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W046S | 0 | 0
TBE For Bolt/Nuts - W046S | BK-W046S-PEDCO-110-PI-TB-0006 | BK-W046S-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W046S | 0 | 0
PMR For Sampling Connection Set - W046S | BK-W046S-PEDCO-110-PI-MR-0007 | BK-W046S-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W046S | 0 | 0
TBE For Sampling Connection - W046S | BK-W046S-PEDCO-110-PI-TB-0007 | BK-W046S-PEDCO-110-PI-TB-0007TBE For Sampling Connection - W046S | 0 | 0
PMR For Stone Trap - W046S | BK-W046S-PEDCO-110-PI-MR-0008 | BK-W046S-PEDCO-110-PI-MR-0008PMR For Stone Trap - W046S | 0 | 0
TBE For Stone Trap - W046S | BK-W046S-PEDCO-110-PI-TB-0008 | BK-W046S-PEDCO-110-PI-TB-0008TBE For Stone Trap - W046S | 2022-05-25 | 2022-12-20
PMR For Pipe Support - W046S | BK-W046S-PEDCO-110-PI-MR-0009 | BK-W046S-PEDCO-110-PI-MR-0009PMR For Pipe Support - W046S | 0 | 0
TBE For Pipe Support - W046S | BK-W046S-PEDCO-110-PI-TB-0009 | BK-W046S-PEDCO-110-PI-TB-0009TBE For Pipe Support - W046S | 0 | 0
PMR For Main HVAC Equipment - W046S | BK-W046S-PEDCO-110-HV-MR-0001 | BK-W046S-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - W046S | 0 | 0
TBE For Main HVAC Equipment - W046S | BK-W046S-PEDCO-110-HV-TB-0001 | BK-W046S-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - W046S | 0 | 0
PMR For Line Pipes - W046S | BK-W046S-PEDCO-110-PL-MR-0001 | BK-W046S-PEDCO-110-PL-MR-0001PMR For Line Pipes - W046S | 2022-10-23 | 0
TBE For Line Pipes - W046S | BK-W046S-PEDCO-110-PL-TB-0001 | BK-W046S-PEDCO-110-PL-TB-0001TBE For Line Pipes - W046S | 2022-02-19 | 2022-12-20
PMR For Flow Line Support - W046S | BK-W046S-PEDCO-110-PL-MR-0002 | BK-W046S-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W046S | 0 | 0
TBE For Flow Line Support - W046S | BK-W046S-PEDCO-110-PL-TB-0002 | BK-W046S-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W046S | 0 | 0
PMR For Field Instrumentations - W046S | BK-W046S-PEDCO-110-IN-MR-0002 | BK-W046S-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W046S | 2021-12-13 | 0
TBE/TBA For Field Instrumentations - W046S | BK-W046S-PEDCO-110-IN-TB-0002 | BK-W046S-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W046S | 2022-10-26 | 0
PMR For Instrument Bulk Items - W046S | BK-W046S-PEDCO-110-IN-MR-0003 | BK-W046S-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W046S | 2022-01-16 | 0
TBE/TBA For Instrument Bulk Items - W046S | BK-W046S-PEDCO-110-IN-TB-0003 | BK-W046S-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items - W046S | 2022-02-02 | 2022-12-20
PMR For Fire Fighting and Safety Equipment - W046S | BK-W046S-PEDCO-110-SA-MR-0001 | BK-W046S-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W046S | 0 | 0
TBE For Fire Fighting and Safety Equipment - W046S | BK-W046S-PEDCO-110-SA-TB-0001 | BK-W046S-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W046S | 0 | 0
PMR For Fire Safety Sign - W046S | BK-W046S-PEDCO-110-SA-MR-0002 | BK-W046S-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W046S | 0 | 0
TBE For Fire Safety Sign - W046S | BK-W046S-PEDCO-110-SA-TB-0002 | BK-W046S-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W046S | 0 | 0
PMR For Transformers - W046S | BK-W046S-PEDCO-110-EL-MR-0001 | BK-W046S-PEDCO-110-EL-MR-0001PMR For Transformers - W046S | 2022-07-13 | 2022-12-20
TBE For Transformers - W046S | BK-W046S-PEDCO-110-EL-TB-0001 | BK-W046S-PEDCO-110-EL-TB-0001TBE For Transformers - W046S | 0 | 0
PMR For LV Switchgear & MCC - W046S | BK-W046S-PEDCO-110-EL-MR-0002 | BK-W046S-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - W046S | 2022-09-11 | 0
TBE For LV Switchgear & MCC - W046S | BK-W046S-PEDCO-110-EL-TB-0002 | BK-W046S-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - W046S | 0 | 0
PMR For Emergency Diesel Generator - W046S | BK-W046S-PEDCO-110-EL-MR-0003 | BK-W046S-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - W046S | 2022-08-20 | 0
TBE For Emergency Diesel Generator - W046S | BK-W046S-PEDCO-110-EL-TB-0003 | BK-W046S-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - W046S | 0 | 0
PMR For UPS System - W046S | BK-W046S-PEDCO-110-EL-MR-0004 | BK-W046S-PEDCO-110-EL-MR-0004PMR For UPS System - W046S | 0 | 0
TBE For UPS System - W046S | BK-W046S-PEDCO-110-EL-TB-0004 | BK-W046S-PEDCO-110-EL-TB-0004TBE For UPS System - W046S | 0 | 0
PMR For DC Charger - W046S | BK-W046S-PEDCO-110-EL-MR-0005 | BK-W046S-PEDCO-110-EL-MR-0005PMR For DC Charger - W046S | 2022-04-26 | 0
TBE For DC Charger - W046S | BK-W046S-PEDCO-110-EL-TB-0005 | BK-W046S-PEDCO-110-EL-TB-0005TBE For DC Charger - W046S | 0 | 0
PMR For Capacitor Bank - W046S | BK-W046S-PEDCO-110-EL-MR-0006 | BK-W046S-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - W046S | 0 | 0
TBE For Capacitor Bank - W046S | BK-W046S-PEDCO-110-EL-TB-0006 | BK-W046S-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - W046S | 0 | 0
PMR For Lighting & Distribution Main Panels - W046S | BK-W046S-PEDCO-110-EL-MR-0007 | BK-W046S-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - W046S | 0 | 0
TBE For Lighting & Distribution Main Panels - W046S | BK-W046S-PEDCO-110-EL-TB-0007 | BK-W046S-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - W046S | 0 | 0
PMR For Earthing & Lightning System - W046S | BK-W046S-PEDCO-110-EL-MR-0008 | BK-W046S-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - W046S | 0 | 0
TBE For Earthing & Lightning System - W046S | BK-W046S-PEDCO-110-EL-TB-0008 | BK-W046S-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - W046S | 0 | 0
PMR For Lighting and Small Power Equipment - W046S | BK-W046S-PEDCO-110-EL-MR-0009 | BK-W046S-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - W046S | 0 | 0
TBE For Lighting and Small Power Equipment - W046S | BK-W046S-PEDCO-110-EL-TB-0009 | BK-W046S-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - W046S | 0 | 0
PMR For Tray/Ladder and Accessories - W046S | BK-W046S-PEDCO-110-EL-MR-0010 | BK-W046S-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - W046S | 0 | 0
TBE For Tray/Ladder and Accessories - W046S | BK-W046S-PEDCO-110-EL-TB-0010 | BK-W046S-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - W046S | 0 | 0
PMR For Power & Control Cables - W046S | BK-W046S-PEDCO-110-EL-MR-0011 | BK-W046S-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - W046S | 0 | 0
TBE For Power & Control Cables - W046S | BK-W046S-PEDCO-110-EL-TB-0011 | BK-W046S-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - W046S | 0 | 0
PMR For Electrical Bulk Items - W046S | BK-W046S-PEDCO-110-EL-MR-0012 | BK-W046S-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - W046S | 0 | 0
TBE For Electrical Bulk Items - W046S | BK-W046S-PEDCO-110-EL-TB-0012 | BK-W046S-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - W046S | 0 | 0
PMR For Transmission Over head Line - W046S | BK-W046S-PEDCO-110-EL-MR-0013 | BK-W046S-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - W046S | 0 | 0
TBE For Transmission Over head Line - W046S | BK-W046S-PEDCO-110-EL-TB-0013 | BK-W046S-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - W046S | 0 | 0
PMR For Steel Structure Items - W046S | BK-W046S-PEDCO-110-ST-MR-0001 | BK-W046S-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W046S | 0 | 0
TBE For Steel Structure Items - W046S | BK-W046S-PEDCO-110-ST-TB-0001 | BK-W046S-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W046S | 0 | 0
PMR For Anchor Bolts - W046S | BK-W046S-PEDCO-110-ST-MR-0002 | BK-W046S-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W046S | 0 | 0
TBE For Anchor Bolts - W046S | BK-W046S-PEDCO-110-ST-TB-0002 | BK-W046S-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W046S | 0 | 0
PMR For Blast Proof Doors - W046S | BK-W046S-PEDCO-110-ST-MR-0003 | BK-W046S-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - W046S | 0 | 0
TBE For Blast Proof Doors - W046S | BK-W046S-PEDCO-110-ST-TB-0003 | BK-W046S-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - W046S | 0 | 0
PMR For Geomembrane - W046S | BK-W046S-PEDCO-110-CV-MR-0001 | BK-W046S-PEDCO-110-CV-MR-0001PMR For Geomembrane - W046S | 0 | 0
TBE For Geomembrane - W046S | BK-W046S-PEDCO-110-CV-TB-0001 | BK-W046S-PEDCO-110-CV-TB-0001TBE For Geomembrane - W046S | 0 | 0
PMR For Geotextile - W046S | BK-W046S-PEDCO-110-CV-MR-0002 | BK-W046S-PEDCO-110-CV-MR-0002PMR For Geotextile - W046S | 0 | 0
TBE For Geotextile - W046S | BK-W046S-PEDCO-110-CV-TB-0002 | BK-W046S-PEDCO-110-CV-TB-0002TBE For Geotextile - W046S | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - W046S | BK-W046S-PEDCO-110-CO-PR-0001 | BK-W046S-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W046S | 0 | 0
Technical/Site Queries | BK-W046S-PEDCO-110-GE-TQ-0001 | BK-W046S-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - W046S | BK-W046S-PEDCO-110-GE-DO-0001 | BK-W046S-PEDCO-110-GE-DO-0001As-Built Document Booklets - W046S | 0 | 0
Operating Manual - W046S | BK-W046S-PEDCO-110-GE-ML-0001 | BK-W046S-PEDCO-110-GE-ML-0001Operating Manual - W046S | 0 | 0
As-Built Document Booklets - W046S | BK-W046S-PEDCO-110-GE-DO-0001 | BK-W046S-PEDCO-110-GE-DO-0001As-Built Document Booklets - W046S | 0 | 0
Final Engineering Dossier - W046S | BK-W046S-PEDCO-110-GE-DO-0002 | BK-W046S-PEDCO-110-GE-DO-0002Final Engineering Dossier - W046S | 0 | 0
Process Flow Diagram - W035 | BK-W035-PEDCO-110-PR-PF-0001 | BK-W035-PEDCO-110-PR-PF-0001Process Flow Diagram - W035 | 2021-11-02 | 2022-12-20
P&ID - W035 | BK-W035-PEDCO-110-PR-PI-0001 | BK-W035-PEDCO-110-PR-PI-0001P&ID - W035 | 2021-11-01 | 2022-12-20
Line List - W035 | BK-W035-PEDCO-110-PR-LI-0001 | BK-W035-PEDCO-110-PR-LI-0001Line List - W035 | 2021-11-08 | 2022-12-20
Flow line Hydraulic Calculation Report | BK-W035-PEDCO-110-PR-RT-0001 | BK-W035-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-10-08
Process Data Sheets For Instrument Devices - W035 | BK-W035-PEDCO-110-PR-DT-0001 | BK-W035-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W035 | 2022-04-12 | 2022-12-20
Plot Plan Drawing - W035 | BK-W035-PEDCO-110-PI-DW-0001 | BK-W035-PEDCO-110-PI-DW-0001Plot Plan Drawing - W035 | 0 | 0
Piping Plan - W035 | BK-W035-PEDCO-110-PI-DW-0002 | BK-W035-PEDCO-110-PI-DW-0002Piping Plan - W035 | 0 | 0
Isometric Drawings - W035 | BK-W035-PEDCO-110-PI-DW-0003 | BK-W035-PEDCO-110-PI-DW-0003Isometric Drawings - W035 | 0 | 0
Material Flow Diagram - W035 | BK-W035-PEDCO-110-PI-DG-0001 | BK-W035-PEDCO-110-PI-DG-0001Material Flow Diagram - W035 | 2021-11-08 | 2022-12-20
Piping Support List - W035 | BK-W035-PEDCO-110-PI-LI-0001 | BK-W035-PEDCO-110-PI-LI-0001Piping Support List - W035 | 0 | 0
Critical Line List - W035 | BK-W035-PEDCO-110-PI-LI-0002 | BK-W035-PEDCO-110-PI-LI-0002Critical Line List - W035 | 0 | 0
PDMS Model Review Report (60%) - W035 | BK-W035-PEDCO-110-PI-RT-0001 | BK-W035-PEDCO-110-PI-RT-0001PDMS Model Review Report (60%) - W035 | 0 | 0
PDMS Model Review Report (90%) - W035 | BK-W035-PEDCO-110-PI-RT-0002 | BK-W035-PEDCO-110-PI-RT-0002PDMS Model Review Report (90%) - W035 | 0 | 0
MTO For Pipes - W035 | BK-W035-PEDCO-110-PI-MT-0001 | BK-W035-PEDCO-110-PI-MT-0001MTO For Pipes - W035 | 2022-10-25 | 0
MTO For Fittings - W035 | BK-W035-PEDCO-110-PI-MT-0002 | BK-W035-PEDCO-110-PI-MT-0002MTO For Fittings - W035 | 0 | 0
MTO For Flanges - W035 | BK-W035-PEDCO-110-PI-MT-0003 | BK-W035-PEDCO-110-PI-MT-0003MTO For Flanges - W035 | 0 | 0
MTO For Manual Valves - W035 | BK-W035-PEDCO-110-PI-MT-0004 | BK-W035-PEDCO-110-PI-MT-0004MTO For Manual Valves - W035 | 0 | 0
MTO For Gaskets - W035 | BK-W035-PEDCO-110-PI-MT-0005 | BK-W035-PEDCO-110-PI-MT-0005MTO For Gaskets - W035 | 0 | 0
MTO For Bolt & Nuts - W035 | BK-W035-PEDCO-110-PI-MT-0006 | BK-W035-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W035 | 0 | 0
Flow line Transversal Drawings - W035 | BK-W035-PEDCO-110-PL-DW-0002 | BK-W035-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W035 | 0 | 0
Road Crossing Location List | BK-W035-PEDCO-110-PL-LI-0001 | BK-W035-PEDCO-110-PL-LI-0001Road Crossing Location List | 0 | 0
MTO For Line Pipes (Flow lines) - W035 | BK-W035-PEDCO-110-PL-MT-0001 | BK-W035-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W035 | 2021-08-22 | 2022-12-20
Instrument Location Layout Drawing - W035 | BK-W035-PEDCO-110-IN-PY-0001 | BK-W035-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W035 | 2022-08-15 | 2022-12-20
MTO For Instrument Tube and Fitting - W035 | BK-W035-PEDCO-110-IN-MT-0001 | BK-W035-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W035 | 2021-11-14 | 0
MTO For Instrument Cable Tray - W035 | BK-W035-PEDCO-110-IN-MT-0002 | BK-W035-PEDCO-110-IN-MT-0002MTO For Instrument Cable Tray - W035 | 2021-11-14 | 0
Hazardous Area Classification Layout - W035 | BK-W035-PEDCO-110-SA-PY-0001 | BK-W035-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W035 | 0 | 0
Safety & Fire Fighting Equipment Location Layout - W035 | BK-W035-PEDCO-110-SA-PY-0002 | BK-W035-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W035 | 0 | 0
Escape Route & Safety Sign Layout - W035 | BK-W035-PEDCO-110-SA-PY-0003 | BK-W035-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W035 | 0 | 0
Hazard Source List - W035 | BK-W035-PEDCO-110-SA-LI-0001 | BK-W035-PEDCO-110-SA-LI-0001Hazard Source List - W035 | 2021-11-09 | 2022-07-26
MTO For Fire Fighting & Safety Equipment - W035 | BK-W035-PEDCO-110-SA-MT-0001 | BK-W035-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W035 | 0 | 0
MTO For Safety Sign - W035 | BK-W035-PEDCO-110-SA-MT-0002 | BK-W035-PEDCO-110-SA-MT-0002MTO For Safety Sign - W035 | 0 | 0
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W035 | BK-W035-PEDCO-110-AR-DW-0001 | BK-W035-PEDCO-110-AR-DW-0001Architectural Drawing For WHCP/HPU Shelter of Well Pads - W035 | 2022-02-26 | 2022-12-20
General Civil Layout -W035 | BK-W035-PEDCO-110-CV-PY-0001 | BK-W035-PEDCO-110-CV-PY-0001General Civil Layout -W035 | 2022-08-24 | 2022-12-20
Civil and Structural drawings -W035 | BK-W035-PEDCO-110-CV-PY-0002 | BK-W035-PEDCO-110-CV-PY-0002Civil and Structural drawings -W035 | 0 | 0
Rough Grading Plans -W035 | BK-W035-PEDCO-110-CV-DW-0001 | BK-W035-PEDCO-110-CV-DW-0001Rough Grading Plans -W035 | 2021-12-15 | 2022-12-20
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W035 | BK-W035-PEDCO-110-CV-CN-0001 | BK-W035-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W035 | 0 | 0
MTO For Civil Works - W035 | BK-W035-PEDCO-110-CV-MT-0001 | BK-W035-PEDCO-110-CV-MT-0001MTO For Civil Works - W035 | 0 | 0
Platform Structure Drawing - W035 | BK-W035-PEDCO-110-ST-DW-0002 | BK-W035-PEDCO-110-ST-DW-0002Platform Structure Drawing - W035 | 0 | 0
MTO For Structural Works - W035 | BK-W035-PEDCO-110-ST-MT-0001 | BK-W035-PEDCO-110-ST-MT-0001MTO For Structural Works - W035 | 0 | 0
Geotechnical Investigation Report - W035 | BK-W035-PEDCO-110-GT-RT-0001 | BK-W035-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W035 | 2022-06-11 | 2022-12-20
Flow line Plan & Profile Drawings - W035 | BK-W035-PEDCO-110-SU-DW-0001 | BK-W035-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W035 | 0 | 0
PMR For Pipes - W035 | BK-W035-PEDCO-110-PI-MR-0001 | BK-W035-PEDCO-110-PI-MR-0001PMR For Pipes - W035 | 0 | 0
TBE For Pipes - W035 | BK-W035-PEDCO-110-PI-TB-0001 | BK-W035-PEDCO-110-PI-TB-0001TBE For Pipes - W035 | 0 | 0
PMR For Fittings - W035 | BK-W035-PEDCO-110-PI-MR-0002 | BK-W035-PEDCO-110-PI-MR-0002PMR For Fittings - W035 | 0 | 0
TBE For Fitting - W035 | BK-W035-PEDCO-110-PI-TB-0002 | BK-W035-PEDCO-110-PI-TB-0002TBE For Fitting - W035 | 0 | 0
PMR For Flanges - W035 | BK-W035-PEDCO-110-PI-MR-0003 | BK-W035-PEDCO-110-PI-MR-0003PMR For Flanges - W035 | 0 | 0
TBE For Flanges - W035 | BK-W035-PEDCO-110-PI-TB-0003 | BK-W035-PEDCO-110-PI-TB-0003TBE For Flanges - W035 | 0 | 0
PMR For Manual Valves - W035 | BK-W035-PEDCO-110-PI-MR-0004 | BK-W035-PEDCO-110-PI-MR-0004PMR For Manual Valves - W035 | 0 | 0
TBE For Manual Valves - W035 | BK-W035-PEDCO-110-PI-TB-0004 | BK-W035-PEDCO-110-PI-TB-0004TBE For Manual Valves - W035 | 0 | 0
PMR For Gaskets - W035 | BK-W035-PEDCO-110-PI-MR-0005 | BK-W035-PEDCO-110-PI-MR-0005PMR For Gaskets - W035 | 0 | 0
TBE For Gaskets - W035 | BK-W035-PEDCO-110-PI-TB-0005 | BK-W035-PEDCO-110-PI-TB-0005TBE For Gaskets - W035 | 0 | 0
PMR For Bolt/Nuts - W035 | BK-W035-PEDCO-110-PI-MR-0006 | BK-W035-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W035 | 0 | 0
TBE For Bolt/Nuts - W035 | BK-W035-PEDCO-110-PI-TB-0006 | BK-W035-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W035 | 0 | 0
PMR For Sampling Connection Set - W035 | BK-W035-PEDCO-110-PI-MR-0007 | BK-W035-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W035 | 0 | 0
TBE For Sampling Connection Set - W035 | BK-W035-PEDCO-110-PI-TB-0007 | BK-W035-PEDCO-110-PI-TB-0007TBE For Sampling Connection Set - W035 | 0 | 0
PMR For Stone Trap - W035 | BK-W035-PEDCO-110-PI-MR-0008 | BK-W035-PEDCO-110-PI-MR-0008PMR For Stone Trap - W035 | 0 | 0
TBE For Stone Trap - W035 | BK-W035-PEDCO-110-PI-TB-0008 | BK-W035-PEDCO-110-PI-TB-0008TBE For Stone Trap - W035 | 2022-05-25 | 2022-12-20
PMR For Pipe Support - W035 | BK-W035-PEDCO-110-PI-MR-0009 | BK-W035-PEDCO-110-PI-MR-0009PMR For Pipe Support - W035 | 0 | 0
TBE For Pipe Support - W035 | BK-W035-PEDCO-110-PI-TB-0009 | BK-W035-PEDCO-110-PI-TB-0009TBE For Pipe Support - W035 | 0 | 0
PMR For Line Pipes - W035 | BK-W035-PEDCO-110-PL-MR-0001 | BK-W035-PEDCO-110-PL-MR-0001PMR For Line Pipes - W035 | 2022-10-23 | 0
TBE For Line Pipes - W035 | BK-W035-PEDCO-110-PL-TB-0001 | BK-W035-PEDCO-110-PL-TB-0001TBE For Line Pipes - W035 | 2022-02-19 | 2022-12-20
PMR For Flow Line Support - W035 | BK-W035-PEDCO-110-PL-MR-0002 | BK-W035-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W035 | 0 | 0
TBE For Flow Line Support - W035 | BK-W035-PEDCO-110-PL-TB-0002 | BK-W035-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W035 | 0 | 0
PMR For WHCP/HPU - W035 | BK-W035-PEDCO-110-IN-MR-0001 | BK-W035-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W035 | 2021-11-15 | 2022-12-20
TBE/TBA For WHCP/HPU - W035 | BK-W035-PEDCO-110-IN-TB-0001 | BK-W035-PEDCO-110-IN-TB-0001TBE/TBA For WHCP/HPU - W035 | 2021-12-01 | 0
PMR For Field Instrumentations - W035 | BK-W035-PEDCO-110-IN-MR-0002 | BK-W035-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W035 | 2021-12-13 | 0
TBE/TBA For Field Instrumentations - W035 | BK-W035-PEDCO-110-IN-TB-0002 | BK-W035-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W035 | 2022-10-26 | 0
PMR For Instrument Bulk Items - W035 | BK-W035-PEDCO-110-IN-MR-0003 | BK-W035-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W035 | 2022-01-16 | 0
TBE/TBA For Instrument Bulk Items - W035 | BK-W035-PEDCO-110-IN-TB-0003 | BK-W035-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items - W035 | 2022-02-02 | 2022-12-20
PMR For Fire Fighting and Safety Equipment - W035 | BK-W035-PEDCO-110-SA-MR-0001 | BK-W035-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W035 | 0 | 0
TBE For Fire Fighting and Safety Equipment - W035 | BK-W035-PEDCO-110-SA-TB-0001 | BK-W035-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W035 | 0 | 0
PMR For Fire Safety Sign - W035 | BK-W035-PEDCO-110-SA-MR-0002 | BK-W035-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W035 | 0 | 0
TBE For Fire Safety Sign - W035 | BK-W035-PEDCO-110-SA-TB-0002 | BK-W035-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W035 | 0 | 0
PMR For Steel Structure Items - W035 | BK-W035-PEDCO-110-ST-MR-0001 | BK-W035-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W035 | 0 | 0
TBE For Steel Structure Items - W035 | BK-W035-PEDCO-110-ST-TB-0001 | BK-W035-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W035 | 0 | 0
PMR For Anchor Bolts - W035 | BK-W035-PEDCO-110-ST-MR-0002 | BK-W035-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W035 | 0 | 0
TBE For Anchor Bolts - W035 | BK-W035-PEDCO-110-ST-TB-0002 | BK-W035-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W035 | 0 | 0
PMR For Geomembrane - W035 | BK-W035-PEDCO-110-CV-MR-0001 | BK-W035-PEDCO-110-CV-MR-0001PMR For Geomembrane - W035 | 0 | 0
TBE For Geomembrane - W035 | BK-W035-PEDCO-110-CV-TB-0001 | BK-W035-PEDCO-110-CV-TB-0001TBE For Geomembrane - W035 | 0 | 0
PMR For Geotextile - W035 | BK-W035-PEDCO-110-CV-MR-0002 | BK-W035-PEDCO-110-CV-MR-0002PMR For Geotextile - W035 | 0 | 0
TBE For Geotextile - W035 | BK-W035-PEDCO-110-CV-TB-0002 | BK-W035-PEDCO-110-CV-TB-0002TBE For Geotextile - W035 | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - W035 | BK-W035-PEDCO-110-CO-PR-0001 | BK-W035-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W035 | 0 | 0
Technical/Site Queries | BK-W035-PEDCO-110-GE-TQ-0001 | BK-W035-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - W035 | BK-W035-PEDCO-110-GE-DO-0001 | BK-W035-PEDCO-110-GE-DO-0001As-Built Document Booklets - W035 | 0 | 0
Operating Manual - W035 | BK-W035-PEDCO-110-GE-ML-0001 | BK-W035-PEDCO-110-GE-ML-0001Operating Manual - W035 | 0 | 0
As-Built Document Booklets - W035 | BK-W035-PEDCO-110-GE-DO-0001 | BK-W035-PEDCO-110-GE-DO-0001As-Built Document Booklets - W035 | 0 | 0
Final Engineering Dossier - W035 | BK-W035-PEDCO-110-GE-DO-0002 | BK-W035-PEDCO-110-GE-DO-0002Final Engineering Dossier - W035 | 0 | 0
Process Flow Diagram - W008N | BK-W008N-PEDCO-110-PR-PF-0001 | BK-W008N-PEDCO-110-PR-PF-0001Process Flow Diagram - W008N | 2021-11-02 | 2022-12-20
P&ID - W008N | BK-W008N-PEDCO-110-PR-PI-0001 | BK-W008N-PEDCO-110-PR-PI-0001P&ID - W008N | 2021-11-01 | 2022-12-20
Line List - W008N | BK-W008N-PEDCO-110-PR-LI-0001 | BK-W008N-PEDCO-110-PR-LI-0001Line List - W008N | 2021-11-08 | 2022-12-20
Flow line Hydraulic Calculation Report | BK-W008N-PEDCO-110-PR-RT-0001 | BK-W008N-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-10-08
Process Data Sheets For Instrument Devices - W008N | BK-W008N-PEDCO-110-PR-DT-0001 | BK-W008N-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W008N | 2022-04-12 | 2022-12-20
Plot Plan Drawing - W008N | BK-W008N-PEDCO-110-PI-DW-0001 | BK-W008N-PEDCO-110-PI-DW-0001Plot Plan Drawing - W008N | 0 | 0
Piping Plan - W008N | BK-W008N-PEDCO-110-PI-DW-0002 | BK-W008N-PEDCO-110-PI-DW-0002Piping Plan - W008N | 0 | 0
Isometric Drawings - W008N | BK-W008N-PEDCO-110-PI-DW-0003 | BK-W008N-PEDCO-110-PI-DW-0003Isometric Drawings - W008N | 0 | 0
Material Flow Diagram - W008N | BK-W008N-PEDCO-110-PI-DG-0001 | BK-W008N-PEDCO-110-PI-DG-0001Material Flow Diagram - W008N | 2021-11-08 | 2022-12-20
Piping Support List - W008N | BK-W008N-PEDCO-110-PI-LI-0001 | BK-W008N-PEDCO-110-PI-LI-0001Piping Support List - W008N | 0 | 0
Critical Line List - W008N | BK-W008N-PEDCO-110-PI-LI-0002 | BK-W008N-PEDCO-110-PI-LI-0002Critical Line List - W008N | 0 | 0
PDMS Model Review Report (60%) - W008N | BK-W008N-PEDCO-110-PI-RT-0001 | BK-W008N-PEDCO-110-PI-RT-0001PDMS Model Review Report (60%) - W008N | 0 | 0
PDMS Model Review Report (90%) - W008N | BK-W008N-PEDCO-110-PI-RT-0002 | BK-W008N-PEDCO-110-PI-RT-0002PDMS Model Review Report (90%) - W008N | 0 | 0
MTO For Pipes - W008N | BK-W008N-PEDCO-110-PI-MT-0001 | BK-W008N-PEDCO-110-PI-MT-0001MTO For Pipes - W008N | 2022-10-25 | 0
MTO For Fittings - W008N | BK-W008N-PEDCO-110-PI-MT-0002 | BK-W008N-PEDCO-110-PI-MT-0002MTO For Fittings - W008N | 0 | 0
MTO For Flanges - W008N | BK-W008N-PEDCO-110-PI-MT-0003 | BK-W008N-PEDCO-110-PI-MT-0003MTO For Flanges - W008N | 0 | 0
MTO For Manual Valves - W008N | BK-W008N-PEDCO-110-PI-MT-0004 | BK-W008N-PEDCO-110-PI-MT-0004MTO For Manual Valves - W008N | 0 | 0
MTO For Gaskets - W008N | BK-W008N-PEDCO-110-PI-MT-0005 | BK-W008N-PEDCO-110-PI-MT-0005MTO For Gaskets - W008N | 0 | 0
MTO For Bolt & Nuts - W008N | BK-W008N-PEDCO-110-PI-MT-0006 | BK-W008N-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W008N | 0 | 0
Flow line Transversal Drawings - W008N | BK-W008N-PEDCO-110-PL-DW-0002 | BK-W008N-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W008N | 0 | 0
Road Crossing Location List | BK-W008N-PEDCO-110-PL-LI-0001 | BK-W008N-PEDCO-110-PL-LI-0001Road Crossing Location List | 0 | 0
MTO For Line Pipes (Flow lines) - W008N | BK-W008N-PEDCO-110-PL-MT-0001 | BK-W008N-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W008N | 2021-08-22 | 2022-12-20
Instrument Location Layout Drawing - W008N | BK-W008N-PEDCO-110-IN-PY-0001 | BK-W008N-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W008N | 2022-08-15 | 2022-12-20
MTO For Instrument Tube and Fitting - W008N | BK-W008N-PEDCO-110-IN-MT-0001 | BK-W008N-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W008N | 2021-11-14 | 0
MTO For Instrument Cable Tray - W008N | BK-W008N-PEDCO-110-IN-MT-0002 | BK-W008N-PEDCO-110-IN-MT-0002MTO For Instrument Cable Tray - W008N | 2021-11-14 | 0
Hazardous Area Classification Layout - W008N | BK-W008N-PEDCO-110-SA-PY-0001 | BK-W008N-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W008N | 0 | 0
Safety & Fire Fighting Equipment Location Layout - W008N | BK-W008N-PEDCO-110-SA-PY-0002 | BK-W008N-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W008N | 0 | 0
Escape Route & Safety Sign Layout - W008N | BK-W008N-PEDCO-110-SA-PY-0003 | BK-W008N-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W008N | 0 | 0
Hazard Source List - W008N | BK-W008N-PEDCO-110-SA-LI-0001 | BK-W008N-PEDCO-110-SA-LI-0001Hazard Source List - W008N | 2021-11-09 | 2022-09-07
MTO For Fire Fighting & Safety Equipment - W008N | BK-W008N-PEDCO-110-SA-MT-0001 | BK-W008N-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W008N | 0 | 0
MTO For Safety Sign - W008N | BK-W008N-PEDCO-110-SA-MT-0002 | BK-W008N-PEDCO-110-SA-MT-0002MTO For Safety Sign - W008N | 0 | 0
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W008N | BK-W008N-PEDCO-110-AR-DW-0001 | BK-W008N-PEDCO-110-AR-DW-0001Architectural Drawing For WHCP/HPU Shelter of Well Pads - W008N | 2022-02-26 | 2022-12-20
General Civil Layout -W008N | BK-W008N-PEDCO-110-CV-PY-0001 | BK-W008N-PEDCO-110-CV-PY-0001General Civil Layout -W008N | 0 | 0
Civil and Structural drawings -W008N | BK-W008N-PEDCO-110-CV-PY-0002 | BK-W008N-PEDCO-110-CV-PY-0002Civil and Structural drawings -W008N | 0 | 0
Rough Grading Plans -W008N | BK-W008N-PEDCO-110-CV-DW-0001 | BK-W008N-PEDCO-110-CV-DW-0001Rough Grading Plans -W008N | 0 | 0
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W008N | BK-W008N-PEDCO-110-CV-CN-0001 | BK-W008N-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W008N | 0 | 0
MTO For Civil Works | BK-W008N-PEDCO-110-CV-MT-0001 | BK-W008N-PEDCO-110-CV-MT-0001MTO For Civil Works | 0 | 0
Platform Structure Drawing - W008N | BK-W008N-PEDCO-110-ST-DW-0002 | BK-W008N-PEDCO-110-ST-DW-0002Platform Structure Drawing - W008N | 0 | 0
MTO For Structural Works - W008N | BK-W008N-PEDCO-110-ST-MT-0001 | BK-W008N-PEDCO-110-ST-MT-0001MTO For Structural Works - W008N | 0 | 0
Geotechnical Investigation Report - W008N | BK-W008N-PEDCO-110-GT-RT-0001 | BK-W008N-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W008N | 2022-06-11 | 2022-12-20
Flow line Plan & Profile Drawings - W008N | BK-W008N-PEDCO-110-SU-DW-0001 | BK-W008N-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W008N | 0 | 0
PMR For Pipes - W008N | BK-W008N-PEDCO-110-PI-MR-0001 | BK-W008N-PEDCO-110-PI-MR-0001PMR For Pipes - W008N | 0 | 0
TBE For Pipes - W008N | BK-W008N-PEDCO-110-PI-TB-0001 | BK-W008N-PEDCO-110-PI-TB-0001TBE For Pipes - W008N | 0 | 0
PMR For Fittings - W008N | BK-W008N-PEDCO-110-PI-MR-0002 | BK-W008N-PEDCO-110-PI-MR-0002PMR For Fittings - W008N | 0 | 0
TBE For Fitting - W008N | BK-W008N-PEDCO-110-PI-TB-0002 | BK-W008N-PEDCO-110-PI-TB-0002TBE For Fitting - W008N | 0 | 0
PMR For Flanges - W008N | BK-W008N-PEDCO-110-PI-MR-0003 | BK-W008N-PEDCO-110-PI-MR-0003PMR For Flanges - W008N | 0 | 0
TBE For Flanges - W008N | BK-W008N-PEDCO-110-PI-TB-0003 | BK-W008N-PEDCO-110-PI-TB-0003TBE For Flanges - W008N | 0 | 0
PMR For Manual Valves - W008N | BK-W008N-PEDCO-110-PI-MR-0004 | BK-W008N-PEDCO-110-PI-MR-0004PMR For Manual Valves - W008N | 0 | 0
TBE For Manual Valves - W008N | BK-W008N-PEDCO-110-PI-TB-0004 | BK-W008N-PEDCO-110-PI-TB-0004TBE For Manual Valves - W008N | 0 | 0
PMR For Gaskets - W008N | BK-W008N-PEDCO-110-PI-MR-0005 | BK-W008N-PEDCO-110-PI-MR-0005PMR For Gaskets - W008N | 0 | 0
TBE For Gaskets - W008N | BK-W008N-PEDCO-110-PI-TB-0005 | BK-W008N-PEDCO-110-PI-TB-0005TBE For Gaskets - W008N | 0 | 0
PMR For Bolt/Nuts - W008N | BK-W008N-PEDCO-110-PI-MR-0006 | BK-W008N-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W008N | 0 | 0
TBE For Bolt/Nuts - W008N | BK-W008N-PEDCO-110-PI-TB-0006 | BK-W008N-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W008N | 0 | 0
PMR For Sampling Connection Set - W008N | BK-W008N-PEDCO-110-PI-MR-0007 | BK-W008N-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W008N | 0 | 0
TBE For Sampling Connection Set - W008N | BK-W008N-PEDCO-110-PI-TB-0007 | BK-W008N-PEDCO-110-PI-TB-0007TBE For Sampling Connection Set - W008N | 0 | 0
PMR For Stone Trap - W008N | BK-W008N-PEDCO-110-PI-MR-0008 | BK-W008N-PEDCO-110-PI-MR-0008PMR For Stone Trap - W008N | 0 | 0
TBE For Stone Trap - W008N | BK-W008N-PEDCO-110-PI-TB-0008 | BK-W008N-PEDCO-110-PI-TB-0008TBE For Stone Trap - W008N | 2022-05-24 | 2022-12-20
PMR For Pipe Support - W008N | BK-W008N-PEDCO-110-PI-MR-0009 | BK-W008N-PEDCO-110-PI-MR-0009PMR For Pipe Support - W008N | 0 | 0
TBE For Pipe Support - W008N | BK-W008N-PEDCO-110-PI-TB-0009 | BK-W008N-PEDCO-110-PI-TB-0009TBE For Pipe Support - W008N | 0 | 0
PMR For Line Pipes - W008N | BK-W008N-PEDCO-110-PL-MR-0001 | BK-W008N-PEDCO-110-PL-MR-0001PMR For Line Pipes - W008N | 2022-10-23 | 0
TBE For Line Pipes - W008N | BK-W008N-PEDCO-110-PL-TB-0001 | BK-W008N-PEDCO-110-PL-TB-0001TBE For Line Pipes - W008N | 2022-02-19 | 2022-12-20
PMR For Flow Line Support - W008N | BK-W008N-PEDCO-110-PL-MR-0002 | BK-W008N-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W008N | 0 | 0
TBE For Flow Line Support - W008N | BK-W008N-PEDCO-110-PL-TB-0002 | BK-W008N-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W008N | 0 | 0
PMR For WHCP/HPU - W008N | BK-W008N-PEDCO-110-IN-MR-0001 | BK-W008N-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W008N | 2021-11-15 | 2022-12-20
TBE/TBA For WHCP/HPU - W008N | BK-W008N-PEDCO-110-IN-TB-0001 | BK-W008N-PEDCO-110-IN-TB-0001TBE/TBA For WHCP/HPU - W008N | 2021-12-01 | 0
PMR For Field Instrumentations - W008N | BK-W008N-PEDCO-110-IN-MR-0002 | BK-W008N-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W008N | 2021-12-13 | 0
TBE/TBA For Field Instrumentations - W008N | BK-W008N-PEDCO-110-IN-TB-0002 | BK-W008N-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W008N | 2022-10-26 | 0
PMR For Instrument Bulk Items - W008N | BK-W008N-PEDCO-110-IN-MR-0003 | BK-W008N-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W008N | 2022-01-16 | 0
TBE/TBA For Instrument Bulk Items-W008N | BK-W008N-PEDCO-110-IN-TB-0003 | BK-W008N-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items-W008N | 2022-02-02 | 2022-12-20
PMR For Fire Fighting and Safety Equipment - W008N | BK-W008N-PEDCO-110-SA-MR-0001 | BK-W008N-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W008N | 0 | 0
TBE For Fire Fighting and Safety Equipment - W008N | BK-W008N-PEDCO-110-SA-TB-0001 | BK-W008N-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W008N | 0 | 0
PMR For Fire Safety Sign - W008N | BK-W008N-PEDCO-110-SA-MR-0002 | BK-W008N-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W008N | 0 | 0
TBE For Fire Safety Sign - W008N | BK-W008N-PEDCO-110-SA-TB-0002 | BK-W008N-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W008N | 0 | 0
PMR For Steel Structure Items - W008N | BK-W008N-PEDCO-110-ST-MR-0001 | BK-W008N-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W008N | 0 | 0
TBE For Steel Structure Items - W008N | BK-W008N-PEDCO-110-ST-TB-0001 | BK-W008N-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W008N | 0 | 0
PMR For Anchor Bolts - W008N | BK-W008N-PEDCO-110-ST-MR-0002 | BK-W008N-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W008N | 0 | 0
TBE For Anchor Bolts - W008N | BK-W008N-PEDCO-110-ST-TB-0002 | BK-W008N-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W008N | 0 | 0
PMR For Geomembrane - W008N | BK-W008N-PEDCO-110-CV-MR-0001 | BK-W008N-PEDCO-110-CV-MR-0001PMR For Geomembrane - W008N | 0 | 0
TBE For Geomembrane - W008N | BK-W008N-PEDCO-110-CV-TB-0001 | BK-W008N-PEDCO-110-CV-TB-0001TBE For Geomembrane - W008N | 0 | 0
PMR For Geotextile - W008N | BK-W008N-PEDCO-110-CV-MR-0002 | BK-W008N-PEDCO-110-CV-MR-0002PMR For Geotextile - W008N | 0 | 0
TBE For Geotextile - W008N | BK-W008N-PEDCO-110-CV-TB-0002 | BK-W008N-PEDCO-110-CV-TB-0002TBE For Geotextile - W008N | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - W008N | BK-W008N-PEDCO-110-CO-PR-0001 | BK-W008N-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W008N | 0 | 0
Technical/Site Queries | BK-W008N-PEDCO-110-GE-TQ-0001 | BK-W008N-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - W008N | BK-W008N-PEDCO-110-GE-DO-0001 | BK-W008N-PEDCO-110-GE-DO-0001As-Built Document Booklets - W008N | 0 | 0
Operating Manual - W008N | BK-W008N-PEDCO-110-GE-ML-0001 | BK-W008N-PEDCO-110-GE-ML-0001Operating Manual - W008N | 0 | 0
As-Built Document Booklets - W008N | BK-W008N-PEDCO-110-GE-DO-0001 | BK-W008N-PEDCO-110-GE-DO-0001As-Built Document Booklets - W008N | 0 | 0
Final Engineering Dossier - W008N | BK-W008N-PEDCO-110-GE-DO-0002 | BK-W008N-PEDCO-110-GE-DO-0002Final Engineering Dossier - W008N | 0 | 0
Process Description - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-DP-0001 | BK-W007S-PEDCO-110-PR-DP-0001Process Description - Extension of Binak B/C Manifold | 0 | 0
Calculation book for (CV,PSV,Pump & Line sizing) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-CN-0001 | BK-W007S-PEDCO-110-PR-CN-0001Calculation book for (CV,PSV,Pump & Line sizing) - Extension of Binak B/C Manifold | 2022-02-23 | 2022-12-20
ESD Block Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-DG-0001 | BK-W007S-PEDCO-110-PR-DG-0001ESD Block Diagram - Extension of Binak B/C Manifold | 2022-06-11 | 2022-12-20
Process Flow Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-PF-0001 | BK-W007S-PEDCO-110-PR-PF-0001Process Flow Diagram - Extension of Binak B/C Manifold | 2021-11-01 | 2022-12-20
P&ID - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-PI-0001 | BK-W007S-PEDCO-110-PR-PI-0001P&ID - Extension of Binak B/C Manifold | 2021-10-26 | 2022-12-20
Cause & Effect Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-DG-0002 | BK-W007S-PEDCO-110-PR-DG-0002Cause & Effect Diagram - Extension of Binak B/C Manifold | 2022-06-07 | 2022-12-20
Process Flow Diagram - W007S | BK-W007S-PEDCO-110-PR-PF-0002 | BK-W007S-PEDCO-110-PR-PF-0002Process Flow Diagram - W007S | 2021-11-02 | 2022-12-20
P&ID - W007S | BK-W007S-PEDCO-110-PR-PI-0002 | BK-W007S-PEDCO-110-PR-PI-0002P&ID - W007S | 2021-11-01 | 2022-12-20
P&ID for Diesel Oil Drum- W007S | BK-W007S-PEDCO-110-PR-PI-0003 | BK-W007S-PEDCO-110-PR-PI-0003P&ID for Diesel Oil Drum- W007S | 2021-11-16 | 2022-12-20
P&ID for Potable Water Tank - W007S | BK-W007S-PEDCO-110-PR-PI-0004 | BK-W007S-PEDCO-110-PR-PI-0004P&ID for Potable Water Tank - W007S | 2021-11-16 | 2022-12-20
Line List - W007S & Manifold Extension | BK-W007S-PEDCO-110-PR-LI-0001 | BK-W007S-PEDCO-110-PR-LI-0001Line List - W007S & Manifold Extension | 2022-04-20 | 2022-12-20
Tie-In List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-LI-0002 | BK-W007S-PEDCO-110-PR-LI-0002Tie-In List - Extension of Binak B/C Manifold | 2022-04-20 | 2022-12-20
Line List - W007S | BK-W007S-PEDCO-110-PR-LI-0003 | BK-W007S-PEDCO-110-PR-LI-0003Line List - W007S | 2021-11-08 | 2022-12-20
Flow line Hydraulic Calculation Report | BK-W007S-PEDCO-110-PR-RT-0001 | BK-W007S-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-10-08
Process Data Sheets For Instrument Devices - W007S & Extension Manifold | BK-W007S-PEDCO-110-PR-DT-0001 | BK-W007S-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W007S & Extension Manifold | 2022-04-12 | 2022-12-20
Specification For Positive Displacement Rotary Pumps | BK-W007S-PEDCO-110-ME-SP-0001 | BK-W007S-PEDCO-110-ME-SP-0001Specification For Positive Displacement Rotary Pumps | 2022-02-21 | 2022-12-20
Data Sheets For Oil Sump Pump - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ME-DT-0001 | BK-W007S-PEDCO-110-ME-DT-0001Data Sheets For Oil Sump Pump - Extension of Binak B/C Manifold | 2022-03-14 | 2022-12-20
HVAC Calculation Note For Switchgear Building - W007S | BK-W007S-PEDCO-110-HV-CN-0001 | BK-W007S-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - W007S | 2022-04-04 | 2022-12-20
HVAC Calculation Note For Security Building - W007S | BK-W007S-PEDCO-110-HV-CN-0002 | BK-W007S-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - W007S | 0 | 0
Data Sheets For Main HVAC Equipment - W007S | BK-W007S-PEDCO-110-HV-DT-0001 | BK-W007S-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - W007S | 0 | 0
HVAC System Layout For Switchgear Building - W007S | BK-W007S-PEDCO-110-HV-PY-0001 | BK-W007S-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - W007S | 2022-04-19 | 2022-12-20
HVAC System Layout For Security Building - W007S | BK-W007S-PEDCO-110-HV-PY-0002 | BK-W007S-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - W007S | 0 | 0
Plumbing & Sewage Piping Layout For Switchgear Building - W007S | BK-W007S-PEDCO-110-HV-PY-0003 | BK-W007S-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - W007S | 2022-10-18 | 0
Plumbing & Sewage Piping Layout For Security Building - W007S | BK-W007S-PEDCO-110-HV-PY-0004 | BK-W007S-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - W007S | 0 | 0
MTO For Building HVAC & Plumbing Systems - W007S | BK-W007S-PEDCO-110-HV-MT-0001 | BK-W007S-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - W007S | 0 | 0
Plot Plan Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-PY-0001 | BK-W007S-PEDCO-110-PI-PY-0001Plot Plan Drawing - Extension of Binak B/C Manifold | 2022-01-15 | 2022-12-20
Piping Plan Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-DW-0001 | BK-W007S-PEDCO-110-PI-DW-0001Piping Plan Drawing - Extension of Binak B/C Manifold | 2022-10-04 | 0
Isometric Drawings - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-DW-0002 | BK-W007S-PEDCO-110-PI-DW-0002Isometric Drawings - Extension of Binak B/C Manifold | 0 | 0
Plot Plan Drawing - W007S | BK-W007S-PEDCO-110-PI-PY-0002 | BK-W007S-PEDCO-110-PI-PY-0002Plot Plan Drawing - W007S | 0 | 0
Piping Plan - W007S | BK-W007S-PEDCO-110-PI-DW-0003 | BK-W007S-PEDCO-110-PI-DW-0003Piping Plan - W007S | 0 | 0
Isometric Drawings - W007S | BK-W007S-PEDCO-110-PI-DW-0004 | BK-W007S-PEDCO-110-PI-DW-0004Isometric Drawings - W007S | 0 | 0
Material Flow Diagram - W007S | BK-W007S-PEDCO-110-PI-DG-0001 | BK-W007S-PEDCO-110-PI-DG-0001Material Flow Diagram - W007S | 2021-11-08 | 2022-12-20
Material Flow Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-DG-0002 | BK-W007S-PEDCO-110-PI-DG-0002Material Flow Diagram - Extension of Binak B/C Manifold | 2022-05-11 | 2022-12-20
Critical Line List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-LI-0001 | BK-W007S-PEDCO-110-PI-LI-0001Critical Line List - Extension of Binak B/C Manifold | 0 | 0
Piping Tie-In List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-LI-0002 | BK-W007S-PEDCO-110-PI-LI-0002Piping Tie-In List - Extension of Binak B/C Manifold | 0 | 0
Piping Support List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-LI-0003 | BK-W007S-PEDCO-110-PI-LI-0003Piping Support List - Extension of Binak B/C Manifold | 2022-10-16 | 0
Piping Support List - W007S | BK-W007S-PEDCO-110-PI-LI-0004 | BK-W007S-PEDCO-110-PI-LI-0004Piping Support List - W007S | 0 | 0
Critical Line List - W007S | BK-W007S-PEDCO-110-PI-LI-0005 | BK-W007S-PEDCO-110-PI-LI-0005Critical Line List - W007S | 0 | 0
PDMS Model Review Report (30%) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-RT-0001 | BK-W007S-PEDCO-110-PI-RT-0001PDMS Model Review Report (30%) - Extension of Binak B/C Manifold | 2022-04-09 | 2022-12-20
PDMS Model Review Report (60%) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-RT-0002 | BK-W007S-PEDCO-110-PI-RT-0002PDMS Model Review Report (60%) - Extension of Binak B/C Manifold | 2022-07-05 | 2022-12-20
PDMS Model Review Report (90%) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-RT-0003 | BK-W007S-PEDCO-110-PI-RT-0003PDMS Model Review Report (90%) - Extension of Binak B/C Manifold | 0 | 0
PDMS Model Review Report | BK-W007S-PEDCO-110-PI-RT-0004 | BK-W007S-PEDCO-110-PI-RT-0004PDMS Model Review Report | 0 | 0
PDMS Model Review Report (60%) - W007S | BK-W007S-PEDCO-110-PI-RT-0005 | BK-W007S-PEDCO-110-PI-RT-0005PDMS Model Review Report (60%) - W007S | 0 | 0
PDMS Model Review Report (90%) - W007S | BK-W007S-PEDCO-110-PI-RT-0006 | BK-W007S-PEDCO-110-PI-RT-0006PDMS Model Review Report (90%) - W007S | 0 | 0
Stress Analysis Calculations Report For Manifold area | BK-W007S-PEDCO-110-PI-RT-0007 | BK-W007S-PEDCO-110-PI-RT-0007Stress Analysis Calculations Report For Manifold area | 2022-10-18 | 0
MTO For Pipes - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0001 | BK-W007S-PEDCO-110-PI-MT-0001MTO For Pipes - Manifold & W007S | 2022-10-25 | 0
MTO For Fittings - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0002 | BK-W007S-PEDCO-110-PI-MT-0002MTO For Fittings - Manifold & W007S | 0 | 0
MTO For Flanges - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0003 | BK-W007S-PEDCO-110-PI-MT-0003MTO For Flanges - Manifold & W007S | 0 | 0
MTO For Manual Valves - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0004 | BK-W007S-PEDCO-110-PI-MT-0004MTO For Manual Valves - Manifold & W007S | 0 | 0
MTO For Gaskets - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0005 | BK-W007S-PEDCO-110-PI-MT-0005MTO For Gaskets - Manifold & W007S | 0 | 0
MTO For Bolt & Nuts - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0006 | BK-W007S-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - Manifold & W007S | 0 | 0
Flow line Transversal Drawings - W007S | BK-W007S-PEDCO-110-PL-DW-0002 | BK-W007S-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W007S | 0 | 0
Road Crossing Location List | BK-W007S-PEDCO-110-PL-LI-0001 | BK-W007S-PEDCO-110-PL-LI-0001Road Crossing Location List | 0 | 0
MTO For Line Pipes (Flow lines) - W007S | BK-W007S-PEDCO-110-PL-MT-0001 | BK-W007S-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W007S | 2021-08-22 | 2022-12-20
Data Sheets For Temperature Gauge - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0001 | BK-W007S-PEDCO-110-IN-DT-0001Data Sheets For Temperature Gauge - Extension of Binak B/C Manifold | 2021-12-07 | 2022-09-05
Data Sheets For Pressure & Diff. Pressure Gauge - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0002 | BK-W007S-PEDCO-110-IN-DT-0002Data Sheets For Pressure & Diff. Pressure Gauge - Extension of Binak B/C Manifold | 2021-12-07 | 2022-09-05
Data Sheets For Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0003 | BK-W007S-PEDCO-110-IN-DT-0003Data Sheets For Pressure Transmitter - Extension of Binak B/C Manifold | 2021-12-07 | 2022-09-05
Data Sheets For Pressure & Safety Relief Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0004 | BK-W007S-PEDCO-110-IN-DT-0004Data Sheets For Pressure & Safety Relief Valves - Extension of Binak B/C Manifold | 2022-05-25 | 2022-12-20
Data Sheets For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0005 | BK-W007S-PEDCO-110-IN-DT-0005Data Sheets For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | 2022-03-09 | 2022-12-20
Data Sheets For Control/Regulator valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0006 | BK-W007S-PEDCO-110-IN-DT-0006Data Sheets For Control/Regulator valves - Extension of Binak B/C Manifold | 2022-03-07 | 2022-12-20
Data Sheets For Flow Transmitter/Diff. Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0007 | BK-W007S-PEDCO-110-IN-DT-0007Data Sheets For Flow Transmitter/Diff. Pressure Transmitter - Extension of Binak B/C Manifold | 2021-12-07 | 2022-12-20
Data Sheets For Orifice Plate/Restriction Orifice - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0008 | BK-W007S-PEDCO-110-IN-DT-0008Data Sheets For Orifice Plate/Restriction Orifice - Extension of Binak B/C Manifold | 0 | 0
Data Sheets For Corrosion Coupon/ Probe - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0009 | BK-W007S-PEDCO-110-IN-DT-0009Data Sheets For Corrosion Coupon/ Probe - Extension of Binak B/C Manifold | 2022-03-09 | 2022-12-20
Data Sheets For F&G Devices - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0010 | BK-W007S-PEDCO-110-IN-DT-0010Data Sheets For F&G Devices - Extension of Binak B/C Manifold | 2022-09-18 | 0
Data Sheets For Pressure Switch and Differential Pressure Switch - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0011 | BK-W007S-PEDCO-110-IN-DT-0011Data Sheets For Pressure Switch and Differential Pressure Switch - Extension of Binak B/C Manifold | 0 | 0
DATA SHEETS FOR DISPLACER LEVEL TRANSMITTER - EXTENSION OF BINAK BC MANIFOLD | BK-W007S-PEDCO-110-IN-DT-0012 | BK-W007S-PEDCO-110-IN-DT-0012DATA SHEETS FOR DISPLACER LEVEL TRANSMITTER - EXTENSION OF BINAK BC MANIFOLD | 2022-01-01 | 2022-08-28
Typical Instrument Installation Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DW-0001 | BK-W007S-PEDCO-110-IN-DW-0001Typical Instrument Installation Drawing - Extension of Binak B/C Manifold | 2022-03-09 | 0
Block Diagram Configuration For Control/ESD/F&G System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0001 | BK-W007S-PEDCO-110-IN-DG-0001Block Diagram Configuration For Control/ESD/F&G System - Extension of Binak B/C Manifold | 2021-09-01 | 2022-12-20
Instrument Earthing Typical Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0002 | BK-W007S-PEDCO-110-IN-DG-0002Instrument Earthing Typical Diagram - Extension of Binak B/C Manifold | 2022-01-01 | 0
Instrument Hook-up Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0003 | BK-W007S-PEDCO-110-IN-DG-0003Instrument Hook-up Diagram - Extension of Binak B/C Manifold | 2022-06-07 | 2022-12-20
ESD Level Hierarchy - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0004 | BK-W007S-PEDCO-110-IN-DG-0004ESD Level Hierarchy - Extension of Binak B/C Manifold | 2022-04-24 | 2022-12-20
ESD System Loop Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0005 | BK-W007S-PEDCO-110-IN-DG-0005ESD System Loop Diagram - Extension of Binak B/C Manifold | 2022-09-11 | 0
Control System Loop Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0006 | BK-W007S-PEDCO-110-IN-DG-0006Control System Loop Diagram - Extension of Binak B/C Manifold | 2022-09-05 | 2022-12-20
F&G System Loop Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0007 | BK-W007S-PEDCO-110-IN-DG-0007F&G System Loop Diagram - Extension of Binak B/C Manifold | 2022-09-20 | 0
Instrument Air Piping and Air Header Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0008 | BK-W007S-PEDCO-110-IN-DG-0008Instrument Air Piping and Air Header Diagram - Extension of Binak B/C Manifold | 0 | 0
Instrument & F&G Junction Box Termination Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0009 | BK-W007S-PEDCO-110-IN-DG-0009Instrument & F&G Junction Box Termination Diagram - Extension of Binak B/C Manifold | 2022-05-14 | 2022-12-20
F&G Cause and Effect Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0010 | BK-W007S-PEDCO-110-IN-DG-0010F&G Cause and Effect Diagram - Extension of Binak B/C Manifold | 2022-09-19 | 0
Control System Logic Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LD-0001 | BK-W007S-PEDCO-110-IN-LD-0001Control System Logic Diagram - Extension of Binak B/C Manifold | 2022-04-10 | 2022-12-20
ESD Logic Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LD-0002 | BK-W007S-PEDCO-110-IN-LD-0002ESD Logic Diagram - Extension of Binak B/C Manifold | 2022-05-25 | 2022-12-20
Control Room Layout & Arrangement Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0001 | BK-W007S-PEDCO-110-IN-PY-0001Control Room Layout & Arrangement Drawing - Extension of Binak B/C Manifold | 2022-05-11 | 2022-12-20
Control Room Cable Route Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0002 | BK-W007S-PEDCO-110-IN-PY-0002Control Room Cable Route Layout - Extension of Binak B/C Manifold | 2022-09-13 | 0
Instrument Location Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0003 | BK-W007S-PEDCO-110-IN-PY-0003Instrument Location Layout - Extension of Binak B/C Manifold | 2022-05-17 | 2022-12-20
Instrument/F&G Cable Trench/Route Layout Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0004 | BK-W007S-PEDCO-110-IN-PY-0004Instrument/F&G Cable Trench/Route Layout Drawing - Extension of Binak B/C Manifold | 2022-09-21 | 0
F&G Location Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0005 | BK-W007S-PEDCO-110-IN-PY-0005F&G Location Layout - Extension of Binak B/C Manifold | 2022-05-30 | 2022-12-20
Instrument Location Layout Drawing - W007S | BK-W007S-PEDCO-110-IN-PY-0006 | BK-W007S-PEDCO-110-IN-PY-0006Instrument Location Layout Drawing - W007S | 0 | 0
Wiring Diagram; Interposing Relay Panel (IRP) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0011 | BK-W007S-PEDCO-110-IN-DG-0011Wiring Diagram; Interposing Relay Panel (IRP) - Extension of Binak B/C Manifold | 0 | 0
I/O List For Control System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0002 | BK-W007S-PEDCO-110-IN-LI-0002I/O List For Control System - Extension of Binak B/C Manifold | 2021-11-03 | 2022-08-14
I/O List For ESD Systems - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0003 | BK-W007S-PEDCO-110-IN-LI-0003I/O List For ESD Systems - Extension of Binak B/C Manifold | 2021-11-03 | 2022-08-14
I/O List For F&G Systems - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0004 | BK-W007S-PEDCO-110-IN-LI-0004I/O List For F&G Systems - Extension of Binak B/C Manifold | 2022-08-17 | 2022-12-20
Panels & Junction Box List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0005 | BK-W007S-PEDCO-110-IN-LI-0005Panels & Junction Box List - Extension of Binak B/C Manifold | 2022-09-18 | 0
Set Point & Alarm List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0006 | BK-W007S-PEDCO-110-IN-LI-0006Set Point & Alarm List - Extension of Binak B/C Manifold | 0 | 0
I&C Power Consumption Summary - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0007 | BK-W007S-PEDCO-110-IN-LI-0007I&C Power Consumption Summary - Extension of Binak B/C Manifold | 2022-02-28 | 2022-12-20
F&G Detector List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0008 | BK-W007S-PEDCO-110-IN-LI-0008F&G Detector List - Extension of Binak B/C Manifold | 2022-09-14 | 0
Instrument /F&G Cable List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0009 | BK-W007S-PEDCO-110-IN-LI-0009Instrument /F&G Cable List - Extension of Binak B/C Manifold | 2022-08-22 | 2022-12-20
MTO for Bulk Item and Installation Accessories - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0001 | BK-W007S-PEDCO-110-IN-MT-0001MTO for Bulk Item and Installation Accessories - W007S & Manifold | 0 | 0
MTO For Instrument/F&G Cable - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0002 | BK-W007S-PEDCO-110-IN-MT-0002MTO For Instrument/F&G Cable - W007S & Manifold | 0 | 0
MTO For Instrument/F&G Junction box and Gland - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0003 | BK-W007S-PEDCO-110-IN-MT-0003MTO For Instrument/F&G Junction box and Gland - W007S & Manifold | 0 | 0
MTO For Instrument Tube and Fitting - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0004 | BK-W007S-PEDCO-110-IN-MT-0004MTO For Instrument Tube and Fitting - W007S & Manifold | 0 | 0
MTO For Instrument Cable Tray/Ladder - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0005 | BK-W007S-PEDCO-110-IN-MT-0005MTO For Instrument Cable Tray/Ladder - W007S & Manifold | 2022-08-23 | 0
Hazardous Area Classification Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-PY-0001 | BK-W007S-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - Extension of Binak B/C Manifold | 2022-03-12 | 2022-12-20
Safety & Fire Fighting Equipment Location Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-PY-0002 | BK-W007S-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - Extension of Binak B/C Manifold | 2022-04-17 | 2022-12-20
Escape Route & Safety Sign Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-PY-0003 | BK-W007S-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - Extension of Binak B/C Manifold | 2022-04-17 | 2022-12-20
Hazardous Area Classification Layout - W007S | BK-W007S-PEDCO-110-SA-PY-0004 | BK-W007S-PEDCO-110-SA-PY-0004Hazardous Area Classification Layout - W007S | 0 | 0
Safety & Fire Fighting Equipment Location Layout - W007S | BK-W007S-PEDCO-110-SA-PY-0005 | BK-W007S-PEDCO-110-SA-PY-0005Safety & Fire Fighting Equipment Location Layout - W007S | 0 | 0
Escape Route & Safety Sign Layout - W007S | BK-W007S-PEDCO-110-SA-PY-0006 | BK-W007S-PEDCO-110-SA-PY-0006Escape Route & Safety Sign Layout - W007S | 0 | 0
Hazard Source List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-LI-0001 | BK-W007S-PEDCO-110-SA-LI-0001Hazard Source List - Extension of Binak B/C Manifold | 2021-11-09 | 2022-12-20
Hazard Source List - W007S | BK-W007S-PEDCO-110-SA-LI-0002 | BK-W007S-PEDCO-110-SA-LI-0002Hazard Source List - W007S | 2021-11-09 | 2022-12-20
MTO For Fire Fighting & Safety Equipment - Manifold & W007S | BK-W007S-PEDCO-110-SA-MT-0002 | BK-W007S-PEDCO-110-SA-MT-0002MTO For Fire Fighting & Safety Equipment - Manifold & W007S | 0 | 0
MTO For Safety Sign - W007S | BK-W007S-PEDCO-110-SA-MT-0003 | BK-W007S-PEDCO-110-SA-MT-0003MTO For Safety Sign - W007S | 0 | 0
Earthing Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0001 | BK-W007S-PEDCO-110-EL-PY-0001Earthing Layout - Extension of Binak B/C Manifold | 0 | 0
LV Switchgear/MCC Expansion SLD - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-SL-0001 | BK-W007S-PEDCO-110-EL-SL-0001LV Switchgear/MCC Expansion SLD - Extension of Binak B/C Manifold | 2022-09-20 | 0
UPS Single Line Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-SL-0002 | BK-W007S-PEDCO-110-EL-SL-0002UPS Single Line Diagram - Extension of Binak B/C Manifold | 2022-03-26 | 2022-12-20
DC Charger Single Line Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-SL-0003 | BK-W007S-PEDCO-110-EL-SL-0003DC Charger Single Line Diagram - Extension of Binak B/C Manifold | 2022-03-26 | 2022-12-20
Interconnection Wiring Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-DG-0001 | BK-W007S-PEDCO-110-EL-DG-0001Interconnection Wiring Diagram - Extension of Binak B/C Manifold | 0 | 0
Area Electrical Cable Route & Section Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0002 | BK-W007S-PEDCO-110-EL-PY-0002Area Electrical Cable Route & Section Layout - Extension of Binak B/C Manifold | 0 | 0
Electrical Equipment Arrangement Layout In Switchgear Building - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0003 | BK-W007S-PEDCO-110-EL-PY-0003Electrical Equipment Arrangement Layout In Switchgear Building - Extension of Binak B/C Manifold | 2022-09-19 | 0
Earthing & Lightning Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0004 | BK-W007S-PEDCO-110-EL-PY-0004Earthing & Lightning Layout - Extension of Binak B/C Manifold | 0 | 0
Electrical Load List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-LI-0001 | BK-W007S-PEDCO-110-EL-LI-0001Electrical Load List - Extension of Binak B/C Manifold | 2022-03-07 | 2022-12-20
Electrical Power & Control Cable List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-LI-0002 | BK-W007S-PEDCO-110-EL-LI-0002Electrical Power & Control Cable List - Extension of Binak B/C Manifold | 0 | 0
MTO For Earthing & Lightning Systems - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0001 | BK-W007S-PEDCO-110-EL-MT-0001MTO For Earthing & Lightning Systems - Manifold & W007S | 2022-10-11 | 0
MTO For Lighting & Small Powers - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0002 | BK-W007S-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - Manifold & W007S | 2022-05-18 | 2022-12-20
MTO For Power & Control Cables - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0003 | BK-W007S-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - Manifold & W007S | 0 | 0
MTO For Tray/Ladder and Accessories - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0004 | BK-W007S-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - Manifold & W007S | 0 | 0
MTO For Electrical Bulk Items - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0005 | BK-W007S-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - Manifold & W007S | 0 | 0
MTO For Transmission Over Head Line - W007S | BK-W007S-PEDCO-110-EL-MT-0006 | BK-W007S-PEDCO-110-EL-MT-0006MTO For Transmission Over Head Line - W007S | 2022-09-19 | 0
Architectural Drawing For Diesel Generator Shelter of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0001 | BK-W007S-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - W007S | 2022-05-01 | 2022-12-20
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0002 | BK-W007S-PEDCO-110-AR-DW-0002Architectural Drawing For WHCP/HPU Shelter of Well Pads - W007S | 0 | 0
Architectural Drawing For Switchgear Building of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0003 | BK-W007S-PEDCO-110-AR-DW-0003Architectural Drawing For Switchgear Building of Well Pads - W007S | 2022-09-07 | 0
Architectural Drawing For Security Building of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0004 | BK-W007S-PEDCO-110-AR-DW-0004Architectural Drawing For Security Building of Well Pads - W007S | 2022-05-01 | 2022-12-20
MTO For Architectural Works - W007S | BK-W007S-PEDCO-110-AR-MT-0001 | BK-W007S-PEDCO-110-AR-MT-0001MTO For Architectural Works - W007S | 0 | 0
General Civil Layout - W007S | BK-W007S-PEDCO-110-CV-PY-0001 | BK-W007S-PEDCO-110-CV-PY-0001General Civil Layout - W007S | 0 | 0
Civil and Structural drawings - W007S | BK-W007S-PEDCO-110-CV-PY-0002 | BK-W007S-PEDCO-110-CV-PY-0002Civil and Structural drawings - W007S | 0 | 0
Rough Grading Plans -W007S | BK-W007S-PEDCO-110-CV-DW-0001 | BK-W007S-PEDCO-110-CV-DW-0001Rough Grading Plans -W007S | 0 | 0
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W007S | BK-W007S-PEDCO-110-CV-CN-0001 | BK-W007S-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W007S | 0 | 0
MTO For Civil Works - W007S | BK-W007S-PEDCO-110-CV-MT-0001 | BK-W007S-PEDCO-110-CV-MT-0001MTO For Civil Works - W007S | 0 | 0
SITE VISIT REPORT - MANIFOLD EXTENSION | BK-W007S-PEDCO-110-CV-RT-0001 | BK-W007S-PEDCO-110-CV-RT-0001SITE VISIT REPORT - MANIFOLD EXTENSION | #N/A | #N/A
Pipe Supports Foundation Drawing For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0001 | BK-W007S-PEDCO-110-ST-DW-0001Pipe Supports Foundation Drawing For Extension of Binak B/C Manifold | 0 | 0
Pipe Supports Structure Drawing For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0002 | BK-W007S-PEDCO-110-ST-DW-0002Pipe Supports Structure Drawing For Extension of Binak B/C Manifold | 0 | 0
Access Platforms Structure Plan & Details For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0003 | BK-W007S-PEDCO-110-ST-DW-0003Access Platforms Structure Plan & Details For Extension of Binak B/C Manifold | 2022-10-11 | 0
Access Platforms Foundation Drawing For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0004 | BK-W007S-PEDCO-110-ST-DW-0004Access Platforms Foundation Drawing For Extension of Binak B/C Manifold | 2022-10-11 | 0
Fuel Oil Storage Drum Detail Drawing For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0007 | BK-W007S-PEDCO-110-ST-DW-0007Fuel Oil Storage Drum Detail Drawing For Well Pads - W007S | 0 | 0
Foundation Drawing For Security Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0008 | BK-W007S-PEDCO-110-ST-DW-0008Foundation Drawing For Security Building For Well Pads - W007S | 0 | 0
Structural Drawing For Security Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0009 | BK-W007S-PEDCO-110-ST-DW-0009Structural Drawing For Security Building For Well Pads - W007S | 0 | 0
Foundation Drawing For Switchgear Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0010 | BK-W007S-PEDCO-110-ST-DW-0010Foundation Drawing For Switchgear Building For Well Pads - W007S | 0 | 0
Structural Drawing For Switchgear Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0011 | BK-W007S-PEDCO-110-ST-DW-0011Structural Drawing For Switchgear Building For Well Pads - W007S | 0 | 0
Foundation Drawing For Potable Water Tank For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0012 | BK-W007S-PEDCO-110-ST-DW-0012Foundation Drawing For Potable Water Tank For Well Pads - W007S | 0 | 0
Foundation Drawing For Diesel Generator Shelter For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0013 | BK-W007S-PEDCO-110-ST-DW-0013Foundation Drawing For Diesel Generator Shelter For Well Pads - W007S | 0 | 0
Structural Drawing For Diesel Generator Shelter For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0014 | BK-W007S-PEDCO-110-ST-DW-0014Structural Drawing For Diesel Generator Shelter For Well Pads - W007S | 0 | 0
Platform Structure Drawing - W007S | BK-W007S-PEDCO-110-ST-DW-0016 | BK-W007S-PEDCO-110-ST-DW-0016Platform Structure Drawing - W007S | 0 | 0
Foundation Drawing For Oil Pump | BK-W007S-PEDCO-110-ST-DW-0018 | BK-W007S-PEDCO-110-ST-DW-0018Foundation Drawing For Oil Pump | 0 | 0
Sump Pit Structural Drawing for Oil Pump | BK-W007S-PEDCO-110-ST-DW-0019 | BK-W007S-PEDCO-110-ST-DW-0019Sump Pit Structural Drawing for Oil Pump | 0 | 0
Foundation Drawing For Transmission Line Tower - W007S | BK-W007S-PEDCO-110-ST-DW-0020 | BK-W007S-PEDCO-110-ST-DW-0020Foundation Drawing For Transmission Line Tower - W007S | 0 | 0
MTO For Structural Works - W007S & Manifold Extension | BK-W007S-PEDCO-110-ST-MT-0001 | BK-W007S-PEDCO-110-ST-MT-0001MTO For Structural Works - W007S & Manifold Extension | 0 | 0
Geotechnical Investigation Report - W007S | BK-W007S-PEDCO-110-GT-RT-0001 | BK-W007S-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W007S | 2022-06-11 | 2022-12-20
Flow line Plan & Profile Drawings - W007S | BK-W007S-PEDCO-110-SU-DW-0001 | BK-W007S-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W007S | 0 | 0
Over Head Line Plan and Profile - W007S | BK-W007S-PEDCO-110-SU-DW-0002 | BK-W007S-PEDCO-110-SU-DW-0002Over Head Line Plan and Profile - W007S | 0 | 0
PMR For Pumps - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ME-MR-0001 | BK-W007S-PEDCO-110-ME-MR-0001PMR For Pumps - Extension of Binak B/C Manifold | 2022-09-11 | 0
TBE For Pumps - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ME-TB-0001 | BK-W007S-PEDCO-110-ME-TB-0001TBE For Pumps - Extension of Binak B/C Manifold | 0 | 0
PMR For Drums - W007S | BK-W007S-PEDCO-110-ME-MR-0002 | BK-W007S-PEDCO-110-ME-MR-0002PMR For Drums - W007S | 0 | 0
TBE For Drums - W007S | BK-W007S-PEDCO-110-ME-TB-0002 | BK-W007S-PEDCO-110-ME-TB-0002TBE For Drums - W007S | 0 | 0
PMR For Potable Tanks - W007S | BK-W007S-PEDCO-110-ME-MR-0003 | BK-W007S-PEDCO-110-ME-MR-0003PMR For Potable Tanks - W007S | 0 | 0
TBE For Potable Tanks - W007S | BK-W007S-PEDCO-110-ME-TB-0003 | BK-W007S-PEDCO-110-ME-TB-0003TBE For Potable Tanks - W007S | 0 | 0
PMR For Main HVAC Equipment - W007S | BK-W007S-PEDCO-110-HV-MR-0001 | BK-W007S-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - W007S | 0 | 0
TBE For Main HVAC Equipment - W007S | BK-W007S-PEDCO-110-HV-TB-0001 | BK-W007S-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - W007S | 0 | 0
PMR For Pipes - W007S | BK-W007S-PEDCO-110-PI-MR-0001 | BK-W007S-PEDCO-110-PI-MR-0001PMR For Pipes - W007S | 0 | 0
TBE For Pipes - W007S | BK-W007S-PEDCO-110-PI-TB-0001 | BK-W007S-PEDCO-110-PI-TB-0001TBE For Pipes - W007S | 0 | 0
PMR For Fittings - W007S | BK-W007S-PEDCO-110-PI-MR-0002 | BK-W007S-PEDCO-110-PI-MR-0002PMR For Fittings - W007S | 0 | 0
TBE For Fitting - W007S | BK-W007S-PEDCO-110-PI-TB-0002 | BK-W007S-PEDCO-110-PI-TB-0002TBE For Fitting - W007S | 0 | 0
PMR For Flanges - W007S | BK-W007S-PEDCO-110-PI-MR-0003 | BK-W007S-PEDCO-110-PI-MR-0003PMR For Flanges - W007S | 0 | 0
TBE For Flanges - W007S | BK-W007S-PEDCO-110-PI-TB-0003 | BK-W007S-PEDCO-110-PI-TB-0003TBE For Flanges - W007S | 0 | 0
PMR For Manual Valves - W007S | BK-W007S-PEDCO-110-PI-MR-0004 | BK-W007S-PEDCO-110-PI-MR-0004PMR For Manual Valves - W007S | 0 | 0
TBE For Manual Valves - W007S | BK-W007S-PEDCO-110-PI-TB-0004 | BK-W007S-PEDCO-110-PI-TB-0004TBE For Manual Valves - W007S | 0 | 0
PMR For Gaskets - W007S | BK-W007S-PEDCO-110-PI-MR-0005 | BK-W007S-PEDCO-110-PI-MR-0005PMR For Gaskets - W007S | 0 | 0
TBE For Gaskets - W007S | BK-W007S-PEDCO-110-PI-TB-0005 | BK-W007S-PEDCO-110-PI-TB-0005TBE For Gaskets - W007S | 0 | 0
PMR For Bolt/Nuts - W007S | BK-W007S-PEDCO-110-PI-MR-0006 | BK-W007S-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W007S | 0 | 0
TBE For Bolt/Nuts - W007S | BK-W007S-PEDCO-110-PI-TB-0006 | BK-W007S-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W007S | 0 | 0
PMR For Sampling Connection Set - W007S | BK-W007S-PEDCO-110-PI-MR-0007 | BK-W007S-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W007S | 0 | 0
TBE For Sampling Connection - W007S | BK-W007S-PEDCO-110-PI-TB-0007 | BK-W007S-PEDCO-110-PI-TB-0007TBE For Sampling Connection - W007S | 0 | 0
PMR For Stone Trap - W007S | BK-W007S-PEDCO-110-PI-MR-0008 | BK-W007S-PEDCO-110-PI-MR-0008PMR For Stone Trap - W007S | 0 | 0
TBE For Stone Trap - W007S | BK-W007S-PEDCO-110-PI-TB-0008 | BK-W007S-PEDCO-110-PI-TB-0008TBE For Stone Trap - W007S | 2022-05-24 | 2022-12-20
PMR For Pipe Support - W007S | BK-W007S-PEDCO-110-PI-MR-0009 | BK-W007S-PEDCO-110-PI-MR-0009PMR For Pipe Support - W007S | 2022-10-19 | 0
TBE For Pipe Support - W007S | BK-W007S-PEDCO-110-PI-TB-0009 | BK-W007S-PEDCO-110-PI-TB-0009TBE For Pipe Support - W007S | 0 | 0
PMR For Line Pipes - W007S | BK-W007S-PEDCO-110-PL-MR-0001 | BK-W007S-PEDCO-110-PL-MR-0001PMR For Line Pipes - W007S | 2022-10-23 | 0
TBE FOR LINE PIPES – W007S | BK-W007S-PEDCO-110-PL-TB-0001 | BK-W007S-PEDCO-110-PL-TB-0001TBE FOR LINE PIPES – W007S | 2022-02-19 | 2022-12-20
PMR For Flow Line Support - W007S | BK-W007S-PEDCO-110-PL-MR-0002 | BK-W007S-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W007S | 0 | 0
TBE For Flow Line Support - W007S | BK-W007S-PEDCO-110-PL-TB-0002 | BK-W007S-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W007S | 0 | 0
PMR For Control System/Console/Furniture - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0001 | BK-W007S-PEDCO-110-IN-MR-0001PMR For Control System/Console/Furniture - Extension of Binak B/C Manifold | 2022-08-01 | 0
TBE/TBA For Control System/Console/Furniture - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0001 | BK-W007S-PEDCO-110-IN-TB-0001TBE/TBA For Control System/Console/Furniture - Extension of Binak B/C Manifold | 0 | 0
PMR For ESD System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0002 | BK-W007S-PEDCO-110-IN-MR-0002PMR For ESD System - Extension of Binak B/C Manifold | 2022-08-03 | 0
TBE/TBA For ESD System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0002 | BK-W007S-PEDCO-110-IN-TB-0002TBE/TBA For ESD System - Extension of Binak B/C Manifold | 0 | 0
PMR For F&G System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0003 | BK-W007S-PEDCO-110-IN-MR-0003PMR For F&G System - Extension of Binak B/C Manifold | 0 | 0
TBE/TBA For F&G System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0003 | BK-W007S-PEDCO-110-IN-TB-0003TBE/TBA For F&G System - Extension of Binak B/C Manifold | 0 | 0
PMR For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0004 | BK-W007S-PEDCO-110-IN-MR-0004PMR For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | 2022-03-26 | 2022-12-20
TBE/TBA For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0004 | BK-W007S-PEDCO-110-IN-TB-0004TBE/TBA For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | 2022-10-12 | 0
PMR For Control Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0005 | BK-W007S-PEDCO-110-IN-MR-0005PMR For Control Valves - Extension of Binak B/C Manifold | 2022-03-14 | 0
TBE/TBA For Control Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0005 | BK-W007S-PEDCO-110-IN-TB-0005TBE/TBA For Control Valves - Extension of Binak B/C Manifold | 0 | 0
PMR For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0006 | BK-W007S-PEDCO-110-IN-MR-0006PMR For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold | 0 | 0
TBE/TBA For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0006 | BK-W007S-PEDCO-110-IN-TB-0006TBE/TBA For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold | 0 | 0
PMR For F&G Detector - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0007 | BK-W007S-PEDCO-110-IN-MR-0007PMR For F&G Detector - Extension of Binak B/C Manifold | 0 | 0
TBE/TBA For F&G Detector - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0007 | BK-W007S-PEDCO-110-IN-TB-0007TBE/TBA For F&G Detector - Extension of Binak B/C Manifold | 0 | 0
PMR For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0008 | BK-W007S-PEDCO-110-IN-MR-0008PMR For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold | 0 | 0
TBE/TBA For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0008 | BK-W007S-PEDCO-110-IN-TB-0008TBE/TBA For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold | 0 | 0
PMR For Corrosion Coupon/Probe - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0009 | BK-W007S-PEDCO-110-IN-MR-0009PMR For Corrosion Coupon/Probe - Extension of Binak B/C Manifold | 0 | 0
TBE/TBA For Corrosion Coupon/Probe - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0009 | BK-W007S-PEDCO-110-IN-TB-0009TBE/TBA For Corrosion Coupon/Probe - Extension of Binak B/C Manifold | 0 | 0
PMR For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0010 | BK-W007S-PEDCO-110-IN-MR-0010PMR For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold | 2022-01-16 | 2022-12-20
TBE/TBA For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0010 | BK-W007S-PEDCO-110-IN-TB-0010TBE/TBA For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold | 0 | 0
PMR For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0011 | BK-W007S-PEDCO-110-IN-MR-0011PMR For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold | 2022-01-16 | 0
TBE/TBA For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0011 | BK-W007S-PEDCO-110-IN-TB-0011TBE/TBA For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold | 0 | 0
PMR For Instrument/F&G Cable - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0012 | BK-W007S-PEDCO-110-IN-MR-0012PMR For Instrument/F&G Cable - Extension of Binak B/C Manifold | 0 | 0
TBE/TBA For Instrument/F&G Cable - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0012 | BK-W007S-PEDCO-110-IN-TB-0012TBE/TBA For Instrument/F&G Cable - Extension of Binak B/C Manifold | 0 | 0
PMR For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0013 | BK-W007S-PEDCO-110-IN-MR-0013PMR For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold | 0 | 0
TBE/TBA For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0013 | BK-W007S-PEDCO-110-IN-TB-0013TBE/TBA For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold | 0 | 0
PMR For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0014 | BK-W007S-PEDCO-110-IN-MR-0014PMR For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold | 0 | 0
TBE/TBA For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0014 | BK-W007S-PEDCO-110-IN-TB-0014TBE/TBA For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold | 0 | 0
PMR For Differential Pressure/Pressure Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0015 | BK-W007S-PEDCO-110-IN-MR-0015PMR For Differential Pressure/Pressure Gauge - Manifold & W007S | 2022-01-16 | 0
TBE/TBA For Differential Pressure/Pressure Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0015 | BK-W007S-PEDCO-110-IN-TB-0015TBE/TBA For Differential Pressure/Pressure Gauge - Manifold & W007S | 0 | 0
PMR For Temperature Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0016 | BK-W007S-PEDCO-110-IN-MR-0016PMR For Temperature Gauge - Manifold & W007S | 2022-01-16 | 0
TBE/TBA For Temperature Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0016 | BK-W007S-PEDCO-110-IN-TB-0016TBE/TBA For Temperature Gauge - Manifold & W007S | 0 | 0
PMR For Instrument Tube and Fitting - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0017 | BK-W007S-PEDCO-110-IN-MR-0017PMR For Instrument Tube and Fitting - Manifold & W007S | 0 | 0
TBE/TBA For Instrument Tube and Fitting - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0017 | BK-W007S-PEDCO-110-IN-TB-0017TBE/TBA For Instrument Tube and Fitting - Manifold & W007S | 0 | 0
PMR For Instrument Cable Tray/Ladder - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0018 | BK-W007S-PEDCO-110-IN-MR-0018PMR For Instrument Cable Tray/Ladder - Manifold & W007S | 0 | 0
TBE/TBA For Instrument Cable Tray/Ladder - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0018 | BK-W007S-PEDCO-110-IN-TB-0018TBE/TBA For Instrument Cable Tray/Ladder - Manifold & W007S | 0 | 0
PMR For Fire Fighting and Safety Equipment - Manifold & W007S | BK-W007S-PEDCO-110-SA-MR-0001 | BK-W007S-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - Manifold & W007S | 0 | 0
TBE For Fire Fighting and Safety Equipment - Manifold & W007S | BK-W007S-PEDCO-110-SA-TB-0001 | BK-W007S-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - Manifold & W007S | 0 | 0
PMR For Fire Safety Sign - Manifold & W007S | BK-W007S-PEDCO-110-SA-MR-0002 | BK-W007S-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - Manifold & W007S | 0 | 0
TBE For Fire Safety Sign - Manifold & W007S | BK-W007S-PEDCO-110-SA-TB-0002 | BK-W007S-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - Manifold & W007S | 0 | 0
PMR For LV Switchgear & MCC - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0001 | BK-W007S-PEDCO-110-EL-MR-0001PMR For LV Switchgear & MCC - Manifold & W007S | 0 | 0
TBE For LV Switchgear & MCC - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0001 | BK-W007S-PEDCO-110-EL-TB-0001TBE For LV Switchgear & MCC - Manifold & W007S | 0 | 0
PMR For UPS System - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0002 | BK-W007S-PEDCO-110-EL-MR-0002PMR For UPS System - Manifold & W007S | 0 | 0
TBE For UPS System - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0002 | BK-W007S-PEDCO-110-EL-TB-0002TBE For UPS System - Manifold & W007S | 0 | 0
PMR For DC Charger - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0003 | BK-W007S-PEDCO-110-EL-MR-0003PMR For DC Charger - Manifold & W007S | 0 | 0
TBE For DC Charger - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0003 | BK-W007S-PEDCO-110-EL-TB-0003TBE For DC Charger - Manifold & W007S | 0 | 0
PMR For Earthing & Lightning System - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0004 | BK-W007S-PEDCO-110-EL-MR-0004PMR For Earthing & Lightning System - Manifold & W007S | 0 | 0
TBE For Earthing & Lightning System - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0004 | BK-W007S-PEDCO-110-EL-TB-0004TBE For Earthing & Lightning System - Manifold & W007S | 0 | 0
PMR For Power & Control Cables - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0005 | BK-W007S-PEDCO-110-EL-MR-0005PMR For Power & Control Cables - Manifold & W007S | 0 | 0
TBE For Power & Control Cables - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0005 | BK-W007S-PEDCO-110-EL-TB-0005TBE For Power & Control Cables - Manifold & W007S | 0 | 0
PMR For Tray/Ladder and Accessories - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0006 | BK-W007S-PEDCO-110-EL-MR-0006PMR For Tray/Ladder and Accessories - Manifold & W007S | 0 | 0
TBE For Tray/Ladder and Accessories - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0006 | BK-W007S-PEDCO-110-EL-TB-0006TBE For Tray/Ladder and Accessories - Manifold & W007S | 0 | 0
PMR For Electrical Bulk Items - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0007 | BK-W007S-PEDCO-110-EL-MR-0007PMR For Electrical Bulk Items - Manifold & W007S | 0 | 0
TBE For Electrical Bulk Items - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0007 | BK-W007S-PEDCO-110-EL-TB-0007TBE For Electrical Bulk Items - Manifold & W007S | 0 | 0
PMR For Transformers - W007S | BK-W007S-PEDCO-110-EL-MR-0008 | BK-W007S-PEDCO-110-EL-MR-0008PMR For Transformers - W007S | 2022-07-13 | 2022-12-20
TBE For Transformers - W007S | BK-W007S-PEDCO-110-EL-TB-0008 | BK-W007S-PEDCO-110-EL-TB-0008TBE For Transformers - W007S | 0 | 0
PMR For Emergency Diesel Generator - W007S | BK-W007S-PEDCO-110-EL-MR-0009 | BK-W007S-PEDCO-110-EL-MR-0009PMR For Emergency Diesel Generator - W007S | 2022-08-20 | 0
TBE For Emergency Diesel Generator - W007S | BK-W007S-PEDCO-110-EL-TB-0009 | BK-W007S-PEDCO-110-EL-TB-0009TBE For Emergency Diesel Generator - W007S | 0 | 0
PMR For Lighting & Distribution Main Panels - W007S | BK-W007S-PEDCO-110-EL-MR-0010 | BK-W007S-PEDCO-110-EL-MR-0010PMR For Lighting & Distribution Main Panels - W007S | 0 | 0
TBE For Lighting & Distribution Main Panels - W007S | BK-W007S-PEDCO-110-EL-TB-0010 | BK-W007S-PEDCO-110-EL-TB-0010TBE For Lighting & Distribution Main Panels - W007S | 0 | 0
PMR For Lighting and Small Power Equipment - W007S | BK-W007S-PEDCO-110-EL-MR-0011 | BK-W007S-PEDCO-110-EL-MR-0011PMR For Lighting and Small Power Equipment - W007S | 0 | 0
TBE For Lighting and Small Power Equipment - W007S | BK-W007S-PEDCO-110-EL-TB-0011 | BK-W007S-PEDCO-110-EL-TB-0011TBE For Lighting and Small Power Equipment - W007S | 0 | 0
PMR For Capacitor Bank - W007S | BK-W007S-PEDCO-110-EL-MR-0012 | BK-W007S-PEDCO-110-EL-MR-0012PMR For Capacitor Bank - W007S | 0 | 0
TBE For Capacitor Bank - W007S | BK-W007S-PEDCO-110-EL-TB-0012 | BK-W007S-PEDCO-110-EL-TB-0012TBE For Capacitor Bank - W007S | 0 | 0
PMR For Transmission Over head Line Equipment - W007S | BK-W007S-PEDCO-110-EL-MR-0013 | BK-W007S-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line Equipment - W007S | 0 | 0
TBE For Transmission Over head Line Equipment - W007S | BK-W007S-PEDCO-110-EL-TB-0013 | BK-W007S-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line Equipment - W007S | 0 | 0
PMR For Steel Structure Items - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-MR-0001 | BK-W007S-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W007S/Manifold Extension | 0 | 0
TBE For Steel Structure Items - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-TB-0001 | BK-W007S-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W007S/Manifold Extension | 0 | 0
PMR For Anchor Bolts - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-MR-0002 | BK-W007S-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W007S/Manifold Extension | 0 | 0
TBE For Anchor Bolts - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-TB-0002 | BK-W007S-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W007S/Manifold Extension | 0 | 0
PMR For Blast Proof Doors - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-MR-0003 | BK-W007S-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - W007S/Manifold Extension | 0 | 0
TBE For Blast Proof Doors - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-TB-0003 | BK-W007S-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - W007S/Manifold Extension | 0 | 0
PMR For Geomembrane - W007S | BK-W007S-PEDCO-110-CV-MR-0001 | BK-W007S-PEDCO-110-CV-MR-0001PMR For Geomembrane - W007S | 0 | 0
TBE For Geomembrane - W007S | BK-W007S-PEDCO-110-CV-TB-0001 | BK-W007S-PEDCO-110-CV-TB-0001TBE For Geomembrane - W007S | 0 | 0
PMR For Geotextile - W007S | BK-W007S-PEDCO-110-CV-MR-0002 | BK-W007S-PEDCO-110-CV-MR-0002PMR For Geotextile - W007S | 0 | 0
TBE For Geotextile - W007S | BK-W007S-PEDCO-110-CV-TB-0002 | BK-W007S-PEDCO-110-CV-TB-0002TBE For Geotextile - W007S | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - Manifold & W007S | BK-W007S-PEDCO-110-CO-PR-0001 | BK-W007S-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - Manifold & W007S | 0 | 0
Technical/Site Queries | BK-W007S-PEDCO-110-GE-TQ-0001 | BK-W007S-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - Manifold & W007S | BK-W007S-PEDCO-110-GE-DO-0001 | BK-W007S-PEDCO-110-GE-DO-0001As-Built Document Booklets - Manifold & W007S | 0 | 0
Operating Manual - Manifold & W007S | BK-W007S-PEDCO-110-GE-ML-0001 | BK-W007S-PEDCO-110-GE-ML-0001Operating Manual - Manifold & W007S | 0 | 0
As-Built Document Booklets - Manifold & W007S | BK-W007S-PEDCO-110-GE-DO-0001 | BK-W007S-PEDCO-110-GE-DO-0001As-Built Document Booklets - Manifold & W007S | 0 | 0
Final Engineering Dossier - Manifold & W007S | BK-W007S-PEDCO-110-GE-DO-0002 | BK-W007S-PEDCO-110-GE-DO-0002Final Engineering Dossier - Manifold & W007S | 0 | 0
P&ID for Diesel Oil Drum- BK14 | BK-BK14-PEDCO-110-PR-PI-0001 | BK-BK14-PEDCO-110-PR-PI-0001P&ID for Diesel Oil Drum- BK14 | 2021-11-15 | 2022-12-20
P&ID for Potable Water Tank - BK14 | BK-BK14-PEDCO-110-PR-PI-0002 | BK-BK14-PEDCO-110-PR-PI-0002P&ID for Potable Water Tank - BK14 | 2021-11-15 | 2022-12-20
Line List - BK14 | BK-BK14-PEDCO-110-PR-LI-0001 | BK-BK14-PEDCO-110-PR-LI-0001Line List - BK14 | 2022-02-27 | 2022-12-20
Process Data Sheets For Instrument Devices - BK14 | BK-BK14-PEDCO-110-PR-DT-0001 | BK-BK14-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - BK14 | 2022-04-12 | 2022-12-20
HVAC Calculation Note For Switchgear Building - BK14 | BK-BK14-PEDCO-110-HV-CN-0001 | BK-BK14-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - BK14 | 0 | 0
HVAC Calculation Note For Security Building - BK14 | BK-BK14-PEDCO-110-HV-CN-0002 | BK-BK14-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - BK14 | 0 | 0
Data Sheets For Main HVAC Equipment - BK14 | BK-BK14-PEDCO-110-HV-DT-0001 | BK-BK14-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - BK14 | 0 | 0
HVAC System Layout For Switchgear Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0001 | BK-BK14-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - BK14 | 0 | 0
HVAC System Layout For Security Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0002 | BK-BK14-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - BK14 | 0 | 0
Plumbing & Sewage Piping Layout For Switchgear Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0003 | BK-BK14-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - BK14 | 0 | 0
Plumbing & Sewage Piping Layout For Security Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0004 | BK-BK14-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - BK14 | 0 | 0
MTO For Building HVAC & Plumbing Systems - BK14 | BK-BK14-PEDCO-110-HV-MT-0001 | BK-BK14-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - BK14 | 0 | 0
MTO For Pipes - BK14 | BK-BK14-PEDCO-110-PI-MT-0001 | BK-BK14-PEDCO-110-PI-MT-0001MTO For Pipes - BK14 | 2022-10-25 | 0
MTO For Transmission Over Head Line - BK14 | BK-BK14-PEDCO-110-EL-MT-0001 | BK-BK14-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - BK14 | 2022-09-14 | 0
MTO For Lighting & Small Powers - BK14 | BK-BK14-PEDCO-110-EL-MT-0002 | BK-BK14-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - BK14 | 2022-05-18 | 2022-12-20
MTO For Power & Control Cables - BK14 | BK-BK14-PEDCO-110-EL-MT-0003 | BK-BK14-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - BK14 | 0 | 0
MTO For Tray/Ladder and Accessories - BK14 | BK-BK14-PEDCO-110-EL-MT-0004 | BK-BK14-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - BK14 | 0 | 0
MTO For Electrical Bulk Items - BK14 | BK-BK14-PEDCO-110-EL-MT-0005 | BK-BK14-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - BK14 | 0 | 0
MTO For Earthing & Lightning Systems - BK14 | BK-BK14-PEDCO-110-EL-MT-0006 | BK-BK14-PEDCO-110-EL-MT-0006MTO For Earthing & Lightning Systems - BK14 | 2022-10-11 | 0
Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-14 | BK-BK14-PEDCO-110-AR-DW-0001 | BK-BK14-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-14 | 2022-05-01 | 2022-12-20
Architectural Drawing For Switchgear Building of Well Pads - BK-14 | BK-BK14-PEDCO-110-AR-DW-0002 | BK-BK14-PEDCO-110-AR-DW-0002Architectural Drawing For Switchgear Building of Well Pads - BK-14 | 2022-09-07 | 0
Architectural Drawing For Security Building of Well Pads - BK-14 | BK-BK14-PEDCO-110-AR-DW-0003 | BK-BK14-PEDCO-110-AR-DW-0003Architectural Drawing For Security Building of Well Pads - BK-14 | 2022-05-01 | 2022-12-20
MTO For Architectural Works - BK14 | BK-BK14-PEDCO-110-AR-MT-0001 | BK-BK14-PEDCO-110-AR-MT-0001MTO For Architectural Works - BK14 | 0 | 0
Civil and Structural drawings - BK14 | BK-BK14-PEDCO-110-CV-DW-0001 | BK-BK14-PEDCO-110-CV-DW-0001Civil and Structural drawings - BK14 | 2022-10-18 | 2022-12-20
General Civil Layout - BK14 | BK-BK14-PEDCO-110-CV-PY-0001 | BK-BK14-PEDCO-110-CV-PY-0001General Civil Layout - BK14 | 2022-09-19 | 2022-12-20
Rough Grading Plans -BK14 | BK-BK14-PEDCO-110-CV-PY-0003 | BK-BK14-PEDCO-110-CV-PY-0003Rough Grading Plans -BK14 | 0 | 2022-12-20
Site Visit Report (Civil Work) - BK14 | BK-BK14-PEDCO-110-CV-RT-0001 | BK-BK14-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - BK14 | 2021-11-09 | 2022-10-09
MTO For Civil Works - BK14 | BK-BK14-PEDCO-110-CV-MT-0001 | BK-BK14-PEDCO-110-CV-MT-0001MTO For Civil Works - BK14 | 0 | 0
Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0001 | BK-BK14-PEDCO-110-ST-DW-0001Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-14 | 0 | 0
Foundation Drawing For Security Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0002 | BK-BK14-PEDCO-110-ST-DW-0002Foundation Drawing For Security Building For Well Pads - BK-14 | 0 | 0
Structural Drawing For Security Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0003 | BK-BK14-PEDCO-110-ST-DW-0003Structural Drawing For Security Building For Well Pads - BK-14 | 0 | 0
Foundation Drawing For Switchgear Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0004 | BK-BK14-PEDCO-110-ST-DW-0004Foundation Drawing For Switchgear Building For Well Pads - BK-14 | 0 | 0
Structural Drawing For Switchgear Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0005 | BK-BK14-PEDCO-110-ST-DW-0005Structural Drawing For Switchgear Building For Well Pads - BK-14 | 0 | 0
Foundation Drawing For Potable Water Tank For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0006 | BK-BK14-PEDCO-110-ST-DW-0006Foundation Drawing For Potable Water Tank For Well Pads - BK-14 | 0 | 0
Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0007 | BK-BK14-PEDCO-110-ST-DW-0007Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-14 | 0 | 0
Structural Drawing For Diesel Generator Shelter For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0008 | BK-BK14-PEDCO-110-ST-DW-0008Structural Drawing For Diesel Generator Shelter For Well Pads - BK-14 | 0 | 0
MTO For Structural Works - BK14 | BK-BK14-PEDCO-110-ST-MT-0001 | BK-BK14-PEDCO-110-ST-MT-0001MTO For Structural Works - BK14 | 0 | 0
Geotechnical Investigation Report - BK14 | BK-BK14-PEDCO-110-GT-RT-0001 | BK-BK14-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - BK14 | 2022-06-15 | 2022-12-20
Over Head Line Plan and Profile - BK14 | BK-BK14-PEDCO-110-SU-DW-0001 | BK-BK14-PEDCO-110-SU-DW-0001Over Head Line Plan and Profile - BK14 | 2022-02-21 | 2022-12-20
PMR For Pipes - BK14 | BK-BK14-PEDCO-110-PI-MR-0001 | BK-BK14-PEDCO-110-PI-MR-0001PMR For Pipes - BK14 | 2022-10-25 | 0
TBE For Pipes - BK14 | BK-BK14-PEDCO-110-PI-TB-0001 | BK-BK14-PEDCO-110-PI-TB-0001TBE For Pipes - BK14 | 0 | 0
PMR For Pipe Support - BK14 | BK-BK14-PEDCO-110-PI-MR-0002 | BK-BK14-PEDCO-110-PI-MR-0002PMR For Pipe Support - BK14 | 0 | 0
TBE For Pipe Support - BK14 | BK-BK14-PEDCO-110-PI-TB-0002 | BK-BK14-PEDCO-110-PI-TB-0002TBE For Pipe Support - BK14 | 0 | 0
PMR For Main HVAC Equipment - BK14 | BK-BK14-PEDCO-110-HV-MR-0001 | BK-BK14-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - BK14 | 0 | 0
TBE For Main HVAC Equipment - BK14 | BK-BK14-PEDCO-110-HV-TB-0001 | BK-BK14-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - BK14 | 0 | 0
PMR For Transformers - BK14 | BK-BK14-PEDCO-110-EL-MR-0001 | BK-BK14-PEDCO-110-EL-MR-0001PMR For Transformers - BK14 | 2022-07-13 | 2022-12-20
TBE For Transformers - BK14 | BK-BK14-PEDCO-110-EL-TB-0001 | BK-BK14-PEDCO-110-EL-TB-0001TBE For Transformers - BK14 | 0 | 0
PMR For LV Switchgear & MCC - BK14 | BK-BK14-PEDCO-110-EL-MR-0002 | BK-BK14-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - BK14 | 2022-09-11 | 0
TBE For LV Switchgear & MCC - BK14 | BK-BK14-PEDCO-110-EL-TB-0002 | BK-BK14-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - BK14 | 0 | 0
PMR For Emergency Diesel Generator - BK14 | BK-BK14-PEDCO-110-EL-MR-0003 | BK-BK14-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - BK14 | 2022-08-20 | 0
TBE For Emergency Diesel Generator - BK14 | BK-BK14-PEDCO-110-EL-TB-0003 | BK-BK14-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - BK14 | 0 | 0
PMR For UPS System - BK14 | BK-BK14-PEDCO-110-EL-MR-0004 | BK-BK14-PEDCO-110-EL-MR-0004PMR For UPS System - BK14 | 0 | 0
TBE For UPS System - BK14 | BK-BK14-PEDCO-110-EL-TB-0004 | BK-BK14-PEDCO-110-EL-TB-0004TBE For UPS System - BK14 | 0 | 0
PMR For DC Charger - BK14 | BK-BK14-PEDCO-110-EL-MR-0005 | BK-BK14-PEDCO-110-EL-MR-0005PMR For DC Charger - BK14 | 2022-04-26 | 0
TBE For DC Charger - BK14 | BK-BK14-PEDCO-110-EL-TB-0005 | BK-BK14-PEDCO-110-EL-TB-0005TBE For DC Charger - BK14 | 0 | 0
PMR For Capacitor Bank - BK14 | BK-BK14-PEDCO-110-EL-MR-0006 | BK-BK14-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - BK14 | 0 | 0
TBE For Capacitor Bank - BK14 | BK-BK14-PEDCO-110-EL-TB-0006 | BK-BK14-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - BK14 | 0 | 0
PMR For Lighting & Distribution Main Panels - BK14 | BK-BK14-PEDCO-110-EL-MR-0007 | BK-BK14-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - BK14 | 0 | 0
TBE For Lighting & Distribution Main Panels - BK14 | BK-BK14-PEDCO-110-EL-TB-0007 | BK-BK14-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - BK14 | 0 | 0
PMR For Earthing & Lightning System - BK14 | BK-BK14-PEDCO-110-EL-MR-0008 | BK-BK14-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - BK14 | 0 | 0
TBE For Earthing & Lightning System - BK14 | BK-BK14-PEDCO-110-EL-TB-0008 | BK-BK14-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - BK14 | 0 | 0
PMR For Lighting and Small Power Equipment - BK14 | BK-BK14-PEDCO-110-EL-MR-0009 | BK-BK14-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - BK14 | 0 | 0
TBE For Lighting and Small Power Equipment - BK14 | BK-BK14-PEDCO-110-EL-TB-0009 | BK-BK14-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - BK14 | 0 | 0
PMR For Tray/Ladder and Accessories - BK14 | BK-BK14-PEDCO-110-EL-MR-0010 | BK-BK14-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - BK14 | 0 | 0
TBE For Tray/Ladder and Accessories - BK14 | BK-BK14-PEDCO-110-EL-TB-0010 | BK-BK14-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - BK14 | 0 | 0
PMR For Power & Control Cables - BK14 | BK-BK14-PEDCO-110-EL-MR-0011 | BK-BK14-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - BK14 | 0 | 0
TBE For Power & Control Cables - BK14 | BK-BK14-PEDCO-110-EL-TB-0011 | BK-BK14-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - BK14 | 0 | 0
PMR For Electrical Bulk Items - BK14 | BK-BK14-PEDCO-110-EL-MR-0012 | BK-BK14-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - BK14 | 0 | 0
TBE For Electrical Bulk Items - BK14 | BK-BK14-PEDCO-110-EL-TB-0012 | BK-BK14-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - BK14 | 0 | 0
PMR For Transmission Over head Line - BK14 | BK-BK14-PEDCO-110-EL-MR-0013 | BK-BK14-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - BK14 | 0 | 0
TBE For Transmission Over head Line - BK14 | BK-BK14-PEDCO-110-EL-TB-0013 | BK-BK14-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - BK14 | 0 | 0
PMR For Steel Structure Items - BK14 | BK-BK14-PEDCO-110-ST-MR-0001 | BK-BK14-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - BK14 | 0 | 0
TBE For Steel Structure Items - BK14 | BK-BK14-PEDCO-110-ST-TB-0001 | BK-BK14-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - BK14 | 0 | 0
PMR For Anchor Bolts - BK14 | BK-BK14-PEDCO-110-ST-MR-0002 | BK-BK14-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - BK14 | 0 | 0
TBE For Anchor Bolts - BK14 | BK-BK14-PEDCO-110-ST-TB-0002 | BK-BK14-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - BK14 | 0 | 0
PMR For Blast Proof Doors - BK14 | BK-BK14-PEDCO-110-ST-MR-0003 | BK-BK14-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - BK14 | 0 | 0
TBE For Blast Proof Doors - BK14 | BK-BK14-PEDCO-110-ST-TB-0003 | BK-BK14-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - BK14 | 0 | 0
PMR For Geomembrane - BK14 | BK-BK14-PEDCO-110-CV-MR-0001 | BK-BK14-PEDCO-110-CV-MR-0001PMR For Geomembrane - BK14 | 0 | 0
TBE For Geomembrane - BK14 | BK-BK14-PEDCO-110-CV-TB-0001 | BK-BK14-PEDCO-110-CV-TB-0001TBE For Geomembrane - BK14 | 0 | 0
PMR For Geotextile - BK14 | BK-BK14-PEDCO-110-CV-MR-0002 | BK-BK14-PEDCO-110-CV-MR-0002PMR For Geotextile - BK14 | 0 | 0
TBE For Geotextile - BK14 | BK-BK14-PEDCO-110-CV-TB-0002 | BK-BK14-PEDCO-110-CV-TB-0002TBE For Geotextile - BK14 | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - BK14 | BK-BK14-PEDCO-110-CO-PR-0001 | BK-BK14-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - BK14 | 0 | 0
Technical/Site Queries | BK-BK14-PEDCO-110-GE-TQ-0001 | BK-BK14-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - BK14 | BK-BK14-PEDCO-110-GE-DO-0001 | BK-BK14-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK14 | 0 | 0
Operating Manual - BK14 | BK-BK14-PEDCO-110-GE-ML-0001 | BK-BK14-PEDCO-110-GE-ML-0001Operating Manual - BK14 | 0 | 0
As-Built Document Booklets - BK14 | BK-BK14-PEDCO-110-GE-DO-0001 | BK-BK14-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK14 | 0 | 0
Final Engineering Dossier - BK14 | BK-BK14-PEDCO-110-GE-DO-0002 | BK-BK14-PEDCO-110-GE-DO-0002Final Engineering Dossier - BK14 | 0 | 0
P&ID for Diesel Oil Drum- BK12 | BK-BK12-PEDCO-110-PR-PI-0001 | BK-BK12-PEDCO-110-PR-PI-0001P&ID for Diesel Oil Drum- BK12 | 2021-11-15 | 2022-12-20
P&ID for Potable Water Tank - BK12 | BK-BK12-PEDCO-110-PR-PI-0002 | BK-BK12-PEDCO-110-PR-PI-0002P&ID for Potable Water Tank - BK12 | 2021-11-15 | 2022-12-20
Line List - BK12 | BK-BK12-PEDCO-110-PR-LI-0001 | BK-BK12-PEDCO-110-PR-LI-0001Line List - BK12 | 2022-02-27 | 2022-12-20
Process Data Sheets For Instrument Devices - BK12 | BK-BK12-PEDCO-110-PR-DT-0001 | BK-BK12-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - BK12 | 2022-04-12 | 2022-12-20
HVAC Calculation Note For Switchgear Building - BK12 | BK-BK12-PEDCO-110-HV-CN-0001 | BK-BK12-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - BK12 | 0 | 0
HVAC Calculation Note For Security Building - BK12 | BK-BK12-PEDCO-110-HV-CN-0002 | BK-BK12-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - BK12 | 0 | 0
Data Sheets For Main HVAC Equipment - BK12 | BK-BK12-PEDCO-110-HV-DT-0001 | BK-BK12-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - BK12 | 0 | 0
HVAC System Layout For Switchgear Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0001 | BK-BK12-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - BK12 | 0 | 0
HVAC System Layout For Security Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0002 | BK-BK12-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - BK12 | 0 | 0
Plumbing & Sewage Piping Layout For Switchgear Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0003 | BK-BK12-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - BK12 | 0 | 0
Plumbing & Sewage Piping Layout For Security Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0004 | BK-BK12-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - BK12 | 0 | 0
MTO For Building HVAC & Plumbing Systems - BK12 | BK-BK12-PEDCO-110-HV-MT-0001 | BK-BK12-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - BK12 | 0 | 0
MTO For Pipes - BK12 | BK-BK12-PEDCO-110-PI-MT-0001 | BK-BK12-PEDCO-110-PI-MT-0001MTO For Pipes - BK12 | 2022-10-25 | 0
MTO For Transmission Over Head Line - BK12 | BK-BK12-PEDCO-110-EL-MT-0001 | BK-BK12-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - BK12 | 2022-09-19 | 0
MTO For Lighting & Small Powers - BK12 | BK-BK12-PEDCO-110-EL-MT-0002 | BK-BK12-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - BK12 | 2022-05-18 | 2022-12-20
MTO For Power & Control Cables - BK12 | BK-BK12-PEDCO-110-EL-MT-0003 | BK-BK12-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - BK12 | 0 | 0
MTO For Tray/Ladder and Accessories - BK12 | BK-BK12-PEDCO-110-EL-MT-0004 | BK-BK12-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - BK12 | 0 | 0
MTO For Electrical Bulk Items - BK12 | BK-BK12-PEDCO-110-EL-MT-0005 | BK-BK12-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - BK12 | 0 | 0
MTO For Earthing & Lightning Systems - BK12 | BK-BK12-PEDCO-110-EL-MT-0006 | BK-BK12-PEDCO-110-EL-MT-0006MTO For Earthing & Lightning Systems - BK12 | 2022-10-11 | 0
Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-12 | BK-BK12-PEDCO-110-AR-DW-0001 | BK-BK12-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-12 | 2022-05-01 | 2022-12-20
Architectural Drawing For Switchgear Building of Well Pads - BK-12 | BK-BK12-PEDCO-110-AR-DW-0002 | BK-BK12-PEDCO-110-AR-DW-0002Architectural Drawing For Switchgear Building of Well Pads - BK-12 | 2022-09-07 | 0
Architectural Drawing For Security Building of Well Pads - BK-12 | BK-BK12-PEDCO-110-AR-DW-0003 | BK-BK12-PEDCO-110-AR-DW-0003Architectural Drawing For Security Building of Well Pads - BK-12 | 2022-05-01 | 2022-12-20
MTO For Architectural Works - BK12 | BK-BK12-PEDCO-110-AR-MT-0001 | BK-BK12-PEDCO-110-AR-MT-0001MTO For Architectural Works - BK12 | 0 | 0
Civil and Structural drawings - BK12 | BK-BK12-PEDCO-110-CV-DW-0001 | BK-BK12-PEDCO-110-CV-DW-0001Civil and Structural drawings - BK12 | 0 | 0
General Civil Layout - BK12 | BK-BK12-PEDCO-110-CV-PY-0001 | BK-BK12-PEDCO-110-CV-PY-0001General Civil Layout - BK12 | 0 | 0
Rough Grading Plans -BK12 | BK-BK12-PEDCO-110-CV-PY-0003 | BK-BK12-PEDCO-110-CV-PY-0003Rough Grading Plans -BK12 | 0 | 0
Site Visit Report (Civil Work) - BK12 | BK-BK12-PEDCO-110-CV-RT-0001 | BK-BK12-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - BK12 | 2022-06-25 | 2022-11-19
MTO For Civil Works - BK12 | BK-BK12-PEDCO-110-CV-MT-0001 | BK-BK12-PEDCO-110-CV-MT-0001MTO For Civil Works - BK12 | 0 | 0
Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0001 | BK-BK12-PEDCO-110-ST-DW-0001Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-12 | 0 | 0
Foundation Drawing For Security Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0002 | BK-BK12-PEDCO-110-ST-DW-0002Foundation Drawing For Security Building For Well Pads - BK-12 | 0 | 0
Structural Drawing For Security Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0003 | BK-BK12-PEDCO-110-ST-DW-0003Structural Drawing For Security Building For Well Pads - BK-12 | 0 | 0
Foundation Drawing For Switchgear Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0004 | BK-BK12-PEDCO-110-ST-DW-0004Foundation Drawing For Switchgear Building For Well Pads - BK-12 | 0 | 0
Structural Drawing For Switchgear Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0005 | BK-BK12-PEDCO-110-ST-DW-0005Structural Drawing For Switchgear Building For Well Pads - BK-12 | 0 | 0
Foundation Drawing For Potable Water Tank For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0006 | BK-BK12-PEDCO-110-ST-DW-0006Foundation Drawing For Potable Water Tank For Well Pads - BK-12 | 0 | 0
Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0007 | BK-BK12-PEDCO-110-ST-DW-0007Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-12 | 0 | 0
Structural Drawing For Diesel Generator Shelter For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0008 | BK-BK12-PEDCO-110-ST-DW-0008Structural Drawing For Diesel Generator Shelter For Well Pads - BK-12 | 0 | 0
MTO For Structural Works - BK12 | BK-BK12-PEDCO-110-ST-MT-0001 | BK-BK12-PEDCO-110-ST-MT-0001MTO For Structural Works - BK12 | 0 | 0
Geotechnical Investigation Report - BK12 | BK-BK12-PEDCO-110-GT-RT-0001 | BK-BK12-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - BK12 | 2022-06-15 | 2022-12-20
Over Head Line Plan and Profile - BK12 | BK-BK12-PEDCO-110-SU-DW-0001 | BK-BK12-PEDCO-110-SU-DW-0001Over Head Line Plan and Profile - BK12 | 2022-05-16 | 2022-12-20
PMR For Pipes - BK12 | BK-BK12-PEDCO-110-PI-MR-0001 | BK-BK12-PEDCO-110-PI-MR-0001PMR For Pipes - BK12 | 2022-10-25 | 0
TBE For Pipes - BK12 | BK-BK12-PEDCO-110-PI-TB-0001 | BK-BK12-PEDCO-110-PI-TB-0001TBE For Pipes - BK12 | 0 | 0
PMR For Pipe Support - BK12 | BK-BK12-PEDCO-110-PI-MR-0002 | BK-BK12-PEDCO-110-PI-MR-0002PMR For Pipe Support - BK12 | 0 | 0
TBE For Pipe Support - BK12 | BK-BK12-PEDCO-110-PI-TB-0002 | BK-BK12-PEDCO-110-PI-TB-0002TBE For Pipe Support - BK12 | 0 | 0
PMR For Main HVAC Equipment - BK12 | BK-BK12-PEDCO-110-HV-MR-0001 | BK-BK12-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - BK12 | 0 | 0
TBE For Main HVAC Equipment - BK12 | BK-BK12-PEDCO-110-HV-TB-0001 | BK-BK12-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - BK12 | 0 | 0
PMR For Transformers - BK12 | BK-BK12-PEDCO-110-EL-MR-0001 | BK-BK12-PEDCO-110-EL-MR-0001PMR For Transformers - BK12 | 2022-07-13 | 2022-12-20
TBE For Transformers - BK12 | BK-BK12-PEDCO-110-EL-TB-0001 | BK-BK12-PEDCO-110-EL-TB-0001TBE For Transformers - BK12 | 0 | 0
PMR For LV Switchgear & MCC - BK12 | BK-BK12-PEDCO-110-EL-MR-0002 | BK-BK12-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - BK12 | 2022-09-11 | 0
TBE For LV Switchgear & MCC - BK12 | BK-BK12-PEDCO-110-EL-TB-0002 | BK-BK12-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - BK12 | 0 | 0
PMR For Emergency Diesel Generator - BK12 | BK-BK12-PEDCO-110-EL-MR-0003 | BK-BK12-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - BK12 | 2022-08-20 | 0
TBE For Emergency Diesel Generator - BK12 | BK-BK12-PEDCO-110-EL-TB-0003 | BK-BK12-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - BK12 | 0 | 0
PMR For UPS System - BK12 | BK-BK12-PEDCO-110-EL-MR-0004 | BK-BK12-PEDCO-110-EL-MR-0004PMR For UPS System - BK12 | 0 | 0
TBE For UPS System - BK12 | BK-BK12-PEDCO-110-EL-TB-0004 | BK-BK12-PEDCO-110-EL-TB-0004TBE For UPS System - BK12 | 0 | 0
PMR For DC Charger - BK12 | BK-BK12-PEDCO-110-EL-MR-0005 | BK-BK12-PEDCO-110-EL-MR-0005PMR For DC Charger - BK12 | 2022-04-26 | 0
TBE For DC Charger - BK12 | BK-BK12-PEDCO-110-EL-TB-0005 | BK-BK12-PEDCO-110-EL-TB-0005TBE For DC Charger - BK12 | 0 | 0
PMR For Capacitor Bank - BK12 | BK-BK12-PEDCO-110-EL-MR-0006 | BK-BK12-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - BK12 | 0 | 0
TBE For Capacitor Bank - BK12 | BK-BK12-PEDCO-110-EL-TB-0006 | BK-BK12-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - BK12 | 0 | 0
PMR For Lighting & Distribution Main Panels - BK12 | BK-BK12-PEDCO-110-EL-MR-0007 | BK-BK12-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - BK12 | 0 | 0
TBE For Lighting & Distribution Main Panels - BK12 | BK-BK12-PEDCO-110-EL-TB-0007 | BK-BK12-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - BK12 | 0 | 0
PMR For Earthing & Lightning System - BK12 | BK-BK12-PEDCO-110-EL-MR-0008 | BK-BK12-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - BK12 | 0 | 0
TBE For Earthing & Lightning System - BK12 | BK-BK12-PEDCO-110-EL-TB-0008 | BK-BK12-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - BK12 | 0 | 0
PMR For Lighting and Small Power Equipment - BK12 | BK-BK12-PEDCO-110-EL-MR-0009 | BK-BK12-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - BK12 | 0 | 0
TBE For Lighting and Small Power Equipment - BK12 | BK-BK12-PEDCO-110-EL-TB-0009 | BK-BK12-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - BK12 | 0 | 0
PMR For Tray/Ladder and Accessories - BK12 | BK-BK12-PEDCO-110-EL-MR-0010 | BK-BK12-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - BK12 | 0 | 0
TBE For Tray/Ladder and Accessories - BK12 | BK-BK12-PEDCO-110-EL-TB-0010 | BK-BK12-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - BK12 | 0 | 0
PMR For Power & Control Cables - BK12 | BK-BK12-PEDCO-110-EL-MR-0011 | BK-BK12-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - BK12 | 0 | 0
TBE For Power & Control Cables - BK12 | BK-BK12-PEDCO-110-EL-TB-0011 | BK-BK12-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - BK12 | 0 | 0
PMR For Electrical Bulk Items - BK12 | BK-BK12-PEDCO-110-EL-MR-0012 | BK-BK12-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - BK12 | 0 | 0
TBE For Electrical Bulk Items - BK12 | BK-BK12-PEDCO-110-EL-TB-0012 | BK-BK12-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - BK12 | 0 | 0
PMR For Transmission Over head Line - BK12 | BK-BK12-PEDCO-110-EL-MR-0013 | BK-BK12-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - BK12 | 0 | 0
TBE For Transmission Over head Line - BK12 | BK-BK12-PEDCO-110-EL-TB-0013 | BK-BK12-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - BK12 | 0 | 0
PMR For Steel Structure Items - BK12 | BK-BK12-PEDCO-110-ST-MR-0001 | BK-BK12-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - BK12 | 0 | 0
TBE For Steel Structure Items - BK12 | BK-BK12-PEDCO-110-ST-TB-0001 | BK-BK12-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - BK12 | 0 | 0
PMR For Anchor Bolts - BK12 | BK-BK12-PEDCO-110-ST-MR-0002 | BK-BK12-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - BK12 | 0 | 0
TBE For Anchor Bolts - BK12 | BK-BK12-PEDCO-110-ST-TB-0002 | BK-BK12-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - BK12 | 0 | 0
PMR For Blast Proof Doors - BK12 | BK-BK12-PEDCO-110-ST-MR-0003 | BK-BK12-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - BK12 | 0 | 0
TBE For Blast Proof Doors - BK12 | BK-BK12-PEDCO-110-ST-TB-0003 | BK-BK12-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - BK12 | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - BK12 | BK-BK12-PEDCO-110-CO-PR-0001 | BK-BK12-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - BK12 | 0 | 0
Technical/Site Queries | BK-BK12-PEDCO-110-GE-TQ-0001 | BK-BK12-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - BK12 | BK-BK12-PEDCO-110-GE-DO-0001 | BK-BK12-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK12 | 0 | 0
Operating Manual - BK12 | BK-BK12-PEDCO-110-GE-ML-0001 | BK-BK12-PEDCO-110-GE-ML-0001Operating Manual - BK12 | 0 | 0
As-Built Document Booklets - BK12 | BK-BK12-PEDCO-110-GE-DO-0001 | BK-BK12-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK12 | 0 | 0
Final Engineering Dossier - BK12 | BK-BK12-PEDCO-110-GE-DO-0002 | BK-BK12-PEDCO-110-GE-DO-0002Final Engineering Dossier - BK12 | 0 | 0
P&ID for Diesel Oil Drum- BK15 | BK-BK15-PEDCO-110-PR-PI-0001 | BK-BK15-PEDCO-110-PR-PI-0001P&ID for Diesel Oil Drum- BK15 | 2021-11-15 | 2022-12-20
P&ID for Potable Water Tank - BK15 | BK-BK15-PEDCO-110-PR-PI-0002 | BK-BK15-PEDCO-110-PR-PI-0002P&ID for Potable Water Tank - BK15 | 2021-11-15 | 2022-12-20
Line List - BK15 | BK-BK15-PEDCO-110-PR-LI-0001 | BK-BK15-PEDCO-110-PR-LI-0001Line List - BK15 | 2022-02-27 | 2022-12-20
Process Data Sheets For Instrument Devices - BK15 | BK-BK15-PEDCO-110-PR-DT-0001 | BK-BK15-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - BK15 | 2022-04-12 | 2022-12-20
HVAC Calculation Note For Switchgear Building - BK15 | BK-BK15-PEDCO-110-HV-CN-0001 | BK-BK15-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - BK15 | 0 | 0
HVAC Calculation Note For Security Building - BK15 | BK-BK15-PEDCO-110-HV-CN-0002 | BK-BK15-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - BK15 | 0 | 0
Data Sheets For Main HVAC Equipment - BK15 | BK-BK15-PEDCO-110-HV-DT-0001 | BK-BK15-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - BK15 | 0 | 0
HVAC System Layout For Switchgear Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0001 | BK-BK15-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - BK15 | 0 | 0
HVAC System Layout For Security Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0002 | BK-BK15-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - BK15 | 0 | 0
Plumbing & Sewage Piping Layout For Switchgear Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0003 | BK-BK15-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - BK15 | 0 | 0
Plumbing & Sewage Piping Layout For Security Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0004 | BK-BK15-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - BK15 | 0 | 0
MTO For Building HVAC & Plumbing Systems - BK15 | BK-BK15-PEDCO-110-HV-MT-0001 | BK-BK15-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - BK15 | 0 | 0
MTO For Pipes - BK15 | BK-BK15-PEDCO-110-PI-MT-0001 | BK-BK15-PEDCO-110-PI-MT-0001MTO For Pipes - BK15 | 2022-10-25 | 0
MTO For Transmission Over Head Line - BK15 | BK-BK15-PEDCO-110-EL-MT-0001 | BK-BK15-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - BK15 | 2022-09-19 | 0
MTO For Lighting & Small Powers - BK15 | BK-BK15-PEDCO-110-EL-MT-0002 | BK-BK15-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - BK15 | 2022-05-18 | 2022-12-20
MTO For Power & Control Cables - BK15 | BK-BK15-PEDCO-110-EL-MT-0003 | BK-BK15-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - BK15 | 0 | 0
MTO For Tray/Ladder and Accessories - BK15 | BK-BK15-PEDCO-110-EL-MT-0004 | BK-BK15-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - BK15 | 0 | 0
MTO For Electrical Bulk Items - BK15 | BK-BK15-PEDCO-110-EL-MT-0005 | BK-BK15-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - BK15 | 0 | 0
MTO For Earthing & Lightning Systems - BK15 | BK-BK15-PEDCO-110-EL-MT-0006 | BK-BK15-PEDCO-110-EL-MT-0006MTO For Earthing & Lightning Systems - BK15 | 2022-10-11 | 0
Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-15 | BK-BK15-PEDCO-110-AR-DW-0001 | BK-BK15-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-15 | 2022-05-01 | 2022-12-20
Architectural Drawing For Switchgear Building of Well Pads - BK-15 | BK-BK15-PEDCO-110-AR-DW-0002 | BK-BK15-PEDCO-110-AR-DW-0002Architectural Drawing For Switchgear Building of Well Pads - BK-15 | 2022-09-07 | 0
Architectural Drawing For Security Building of Well Pads - BK-15 | BK-BK15-PEDCO-110-AR-DW-0003 | BK-BK15-PEDCO-110-AR-DW-0003Architectural Drawing For Security Building of Well Pads - BK-15 | 2022-05-01 | 2022-12-20
MTO For Architectural Works - BK15 | BK-BK15-PEDCO-110-AR-MT-0001 | BK-BK15-PEDCO-110-AR-MT-0001MTO For Architectural Works - BK15 | 0 | 0
Civil and Structural drawings - BK15 | BK-BK15-PEDCO-110-CV-DW-0001 | BK-BK15-PEDCO-110-CV-DW-0001Civil and Structural drawings - BK15 | 0 | 0
General Civil Layout - BK15 | BK-BK15-PEDCO-110-CV-PY-0001 | BK-BK15-PEDCO-110-CV-PY-0001General Civil Layout - BK15 | 0 | 0
Rough Grading Plans -BK15 | BK-BK15-PEDCO-110-CV-PY-0003 | BK-BK15-PEDCO-110-CV-PY-0003Rough Grading Plans -BK15 | 0 | 0
Site Visit Report (Civil Work) - BK15 | BK-BK15-PEDCO-110-CV-RT-0001 | BK-BK15-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - BK15 | 2022-06-25 | 2022-11-19
MTO For Civil Works - BK15 | BK-BK15-PEDCO-110-CV-MT-0001 | BK-BK15-PEDCO-110-CV-MT-0001MTO For Civil Works - BK15 | 0 | 0
Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0001 | BK-BK15-PEDCO-110-ST-DW-0001Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-15 | 0 | 0
Foundation Drawing For Security Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0002 | BK-BK15-PEDCO-110-ST-DW-0002Foundation Drawing For Security Building For Well Pads - BK-15 | 0 | 0
Structural Drawing For Security Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0003 | BK-BK15-PEDCO-110-ST-DW-0003Structural Drawing For Security Building For Well Pads - BK-15 | 0 | 0
Foundation Drawing For Switchgear Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0004 | BK-BK15-PEDCO-110-ST-DW-0004Foundation Drawing For Switchgear Building For Well Pads - BK-15 | 0 | 0
Structural Drawing For Switchgear Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0005 | BK-BK15-PEDCO-110-ST-DW-0005Structural Drawing For Switchgear Building For Well Pads - BK-15 | 0 | 0
Foundation Drawing For Potable Water Tank For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0006 | BK-BK15-PEDCO-110-ST-DW-0006Foundation Drawing For Potable Water Tank For Well Pads - BK-15 | 0 | 0
Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0007 | BK-BK15-PEDCO-110-ST-DW-0007Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-15 | 0 | 0
Structural Drawing For Diesel Generator Shelter For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0008 | BK-BK15-PEDCO-110-ST-DW-0008Structural Drawing For Diesel Generator Shelter For Well Pads - BK-15 | 0 | 0
MTO For Structural Works - BK15 | BK-BK15-PEDCO-110-ST-MT-0001 | BK-BK15-PEDCO-110-ST-MT-0001MTO For Structural Works - BK15 | 0 | 0
Geotechnical Investigation Report - BK15 | BK-BK15-PEDCO-110-GT-RT-0001 | BK-BK15-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - BK15 | 2022-07-06 | 2022-12-20
Over Head Line Plan and Profile - BK15 | BK-BK15-PEDCO-110-SU-DW-0001 | BK-BK15-PEDCO-110-SU-DW-0001Over Head Line Plan and Profile - BK15 | 2022-05-16 | 2022-12-20
PMR For Pipes - BK15 | BK-BK15-PEDCO-110-PI-MR-0001 | BK-BK15-PEDCO-110-PI-MR-0001PMR For Pipes - BK15 | 2022-10-25 | 0
TBE For Pipes - BK15 | BK-BK15-PEDCO-110-PI-TB-0001 | BK-BK15-PEDCO-110-PI-TB-0001TBE For Pipes - BK15 | 0 | 0
PMR For Pipe Support - BK15 | BK-BK15-PEDCO-110-PI-MR-0002 | BK-BK15-PEDCO-110-PI-MR-0002PMR For Pipe Support - BK15 | 0 | 0
TBE For Pipe Support - BK15 | BK-BK15-PEDCO-110-PI-TB-0002 | BK-BK15-PEDCO-110-PI-TB-0002TBE For Pipe Support - BK15 | 0 | 0
PMR For Main HVAC Equipment - BK15 | BK-BK15-PEDCO-110-HV-MR-0001 | BK-BK15-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - BK15 | 0 | 0
TBE For Main HVAC Equipment - BK15 | BK-BK15-PEDCO-110-HV-TB-0001 | BK-BK15-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - BK15 | 0 | 0
PMR For Transformers - BK15 | BK-BK15-PEDCO-110-EL-MR-0001 | BK-BK15-PEDCO-110-EL-MR-0001PMR For Transformers - BK15 | 2022-07-13 | 2022-12-20
TBE For Transformers - BK15 | BK-BK15-PEDCO-110-EL-TB-0001 | BK-BK15-PEDCO-110-EL-TB-0001TBE For Transformers - BK15 | 0 | 0
PMR For LV Switchgear & MCC - BK15 | BK-BK15-PEDCO-110-EL-MR-0002 | BK-BK15-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - BK15 | 2022-09-11 | 0
TBE For LV Switchgear & MCC - BK15 | BK-BK15-PEDCO-110-EL-TB-0002 | BK-BK15-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - BK15 | 0 | 0
PMR For Emergency Diesel Generator - BK15 | BK-BK15-PEDCO-110-EL-MR-0003 | BK-BK15-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - BK15 | 2022-08-20 | 0
TBE For Emergency Diesel Generator - BK15 | BK-BK15-PEDCO-110-EL-TB-0003 | BK-BK15-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - BK15 | 0 | 0
PMR For UPS System - BK15 | BK-BK15-PEDCO-110-EL-MR-0004 | BK-BK15-PEDCO-110-EL-MR-0004PMR For UPS System - BK15 | 0 | 0
TBE For UPS System - BK15 | BK-BK15-PEDCO-110-EL-TB-0004 | BK-BK15-PEDCO-110-EL-TB-0004TBE For UPS System - BK15 | 0 | 0
PMR For DC Charger - BK15 | BK-BK15-PEDCO-110-EL-MR-0005 | BK-BK15-PEDCO-110-EL-MR-0005PMR For DC Charger - BK15 | 2022-04-27 | 0
TBE For DC Charger - BK15 | BK-BK15-PEDCO-110-EL-TB-0005 | BK-BK15-PEDCO-110-EL-TB-0005TBE For DC Charger - BK15 | 0 | 0
PMR For Capacitor Bank - BK15 | BK-BK15-PEDCO-110-EL-MR-0006 | BK-BK15-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - BK15 | 0 | 0
TBE For Capacitor Bank - BK15 | BK-BK15-PEDCO-110-EL-TB-0006 | BK-BK15-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - BK15 | 0 | 0
PMR For Lighting & Distribution Main Panels - BK15 | BK-BK15-PEDCO-110-EL-MR-0007 | BK-BK15-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - BK15 | 0 | 0
TBE For Lighting & Distribution Main Panels - BK15 | BK-BK15-PEDCO-110-EL-TB-0007 | BK-BK15-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - BK15 | 0 | 0
PMR For Earthing & Lightning System - BK15 | BK-BK15-PEDCO-110-EL-MR-0008 | BK-BK15-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - BK15 | 0 | 0
TBE For Earthing & Lightning System - BK15 | BK-BK15-PEDCO-110-EL-TB-0008 | BK-BK15-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - BK15 | 0 | 0
PMR For Lighting and Small Power Equipment - BK15 | BK-BK15-PEDCO-110-EL-MR-0009 | BK-BK15-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - BK15 | 0 | 0
TBE For Lighting and Small Power Equipment - BK15 | BK-BK15-PEDCO-110-EL-TB-0009 | BK-BK15-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - BK15 | 0 | 0
PMR For Tray/Ladder and Accessories - BK15 | BK-BK15-PEDCO-110-EL-MR-0010 | BK-BK15-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - BK15 | 0 | 0
TBE For Tray/Ladder and Accessories - BK15 | BK-BK15-PEDCO-110-EL-TB-0010 | BK-BK15-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - BK15 | 0 | 0
PMR For Power & Control Cables - BK15 | BK-BK15-PEDCO-110-EL-MR-0011 | BK-BK15-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - BK15 | 0 | 0
TBE For Power & Control Cables - BK15 | BK-BK15-PEDCO-110-EL-TB-0011 | BK-BK15-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - BK15 | 0 | 0
PMR For Electrical Bulk Items - BK15 | BK-BK15-PEDCO-110-EL-MR-0012 | BK-BK15-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - BK15 | 0 | 0
TBE For Electrical Bulk Items - BK15 | BK-BK15-PEDCO-110-EL-TB-0012 | BK-BK15-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - BK15 | 0 | 0
PMR For Transmission Over head Line - BK15 | BK-BK15-PEDCO-110-EL-MR-0013 | BK-BK15-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - BK15 | 0 | 0
TBE For Transmission Over head Line - BK15 | BK-BK15-PEDCO-110-EL-TB-0013 | BK-BK15-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - BK15 | 0 | 0
PMR For Steel Structure Items - BK15 | BK-BK15-PEDCO-110-ST-MR-0001 | BK-BK15-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - BK15 | 0 | 0
TBE For Steel Structure Items - BK15 | BK-BK15-PEDCO-110-ST-TB-0001 | BK-BK15-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - BK15 | 0 | 0
PMR For Anchor Bolts - BK15 | BK-BK15-PEDCO-110-ST-MR-0002 | BK-BK15-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - BK15 | 0 | 0
TBE For Anchor Bolts - BK15 | BK-BK15-PEDCO-110-ST-TB-0002 | BK-BK15-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - BK15 | 0 | 0
PMR For Blast Proof Doors - BK15 | BK-BK15-PEDCO-110-ST-MR-0003 | BK-BK15-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - BK15 | 0 | 0
TBE For Blast Proof Doors - BK15 | BK-BK15-PEDCO-110-ST-TB-0003 | BK-BK15-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - BK15 | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - BK15 | BK-BK15-PEDCO-110-CO-PR-0001 | BK-BK15-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - BK15 | 0 | 0
Technical/Site Queries | BK-BK15-PEDCO-110-GE-TQ-0001 | BK-BK15-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - BK15 | BK-BK15-PEDCO-110-GE-DO-0001 | BK-BK15-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK15 | 0 | 0
Operating Manual - BK15 | BK-BK15-PEDCO-110-GE-ML-0001 | BK-BK15-PEDCO-110-GE-ML-0001Operating Manual - BK15 | 0 | 0
As-Built Document Booklets - BK15 | BK-BK15-PEDCO-110-GE-DO-0001 | BK-BK15-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK15 | 0 | 0
Final Engineering Dossier - BK15 | BK-BK15-PEDCO-110-GE-DO-0002 | BK-BK15-PEDCO-110-GE-DO-0002Final Engineering Dossier - BK15 | 0 | 0
P&ID for Diesel Oil Drum- BK05 | BK-BK05-PEDCO-110-PR-PI-0001 | BK-BK05-PEDCO-110-PR-PI-0001P&ID for Diesel Oil Drum- BK05 | 2021-11-15 | 2022-12-20
P&ID for Potable Water Tank - BK05 | BK-BK05-PEDCO-110-PR-PI-0002 | BK-BK05-PEDCO-110-PR-PI-0002P&ID for Potable Water Tank - BK05 | 2021-11-15 | 2022-12-20
Line List - BK05 | BK-BK05-PEDCO-110-PR-LI-0001 | BK-BK05-PEDCO-110-PR-LI-0001Line List - BK05 | 2022-02-27 | 2022-12-20
Process Data Sheets For Instrument Devices - BK05 | BK-BK05-PEDCO-110-PR-DT-0001 | BK-BK05-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - BK05 | 2022-04-12 | 2022-12-20
HVAC Calculation Note For Switchgear Building - BK05 | BK-BK05-PEDCO-110-HV-CN-0001 | BK-BK05-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - BK05 | 0 | 0
HVAC Calculation Note For Security Building - BK05 | BK-BK05-PEDCO-110-HV-CN-0002 | BK-BK05-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - BK05 | 0 | 0
Data Sheets For Main HVAC Equipment - BK05 | BK-BK05-PEDCO-110-HV-DT-0001 | BK-BK05-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - BK05 | 0 | 0
HVAC System Layout For Switchgear Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0001 | BK-BK05-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - BK05 | 0 | 0
HVAC System Layout For Security Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0002 | BK-BK05-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - BK05 | 0 | 0
Plumbing & Sewage Piping Layout For Switchgear Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0003 | BK-BK05-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - BK05 | 0 | 0
Plumbing & Sewage Piping Layout For Security Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0004 | BK-BK05-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - BK05 | 0 | 0
MTO For Building HVAC & Plumbing Systems - BK05 | BK-BK05-PEDCO-110-HV-MT-0001 | BK-BK05-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - BK05 | 0 | 0
MTO For Pipes - BK05 | BK-BK05-PEDCO-110-PI-MT-0001 | BK-BK05-PEDCO-110-PI-MT-0001MTO For Pipes - BK05 | 2022-10-25 | 0
MTO For Transmission Over Head Line - BK05 | BK-BK05-PEDCO-110-EL-MT-0001 | BK-BK05-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - BK05 | 2022-09-19 | 0
MTO For Lighting & Small Powers - BK05 | BK-BK05-PEDCO-110-EL-MT-0002 | BK-BK05-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - BK05 | 2022-05-18 | 2022-12-20
MTO For Power & Control Cables - BK05 | BK-BK05-PEDCO-110-EL-MT-0003 | BK-BK05-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - BK05 | 0 | 0
MTO For Tray/Ladder and Accessories - BK05 | BK-BK05-PEDCO-110-EL-MT-0004 | BK-BK05-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - BK05 | 0 | 0
MTO For Electrical Bulk Items - BK05 | BK-BK05-PEDCO-110-EL-MT-0005 | BK-BK05-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - BK05 | 0 | 0
MTO For Earthing & Lightning Systems - BK05 | BK-BK05-PEDCO-110-EL-MT-0006 | BK-BK05-PEDCO-110-EL-MT-0006MTO For Earthing & Lightning Systems - BK05 | 2022-10-11 | 0
Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-05 | BK-BK05-PEDCO-110-AR-DW-0001 | BK-BK05-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-05 | 2022-05-01 | 2022-12-20
Architectural Drawing For Switchgear Building of Well Pads - BK-05 | BK-BK05-PEDCO-110-AR-DW-0002 | BK-BK05-PEDCO-110-AR-DW-0002Architectural Drawing For Switchgear Building of Well Pads - BK-05 | 2022-09-07 | 0
Architectural Drawing For Security Building of Well Pads - BK-05 | BK-BK05-PEDCO-110-AR-DW-0003 | BK-BK05-PEDCO-110-AR-DW-0003Architectural Drawing For Security Building of Well Pads - BK-05 | 2022-05-01 | 2022-12-20
MTO For Architectural Works - BK05 | BK-BK05-PEDCO-110-AR-MT-0001 | BK-BK05-PEDCO-110-AR-MT-0001MTO For Architectural Works - BK05 | 0 | 0
Civil and Structural drawings - BK05 | BK-BK05-PEDCO-110-CV-DW-0001 | BK-BK05-PEDCO-110-CV-DW-0001Civil and Structural drawings - BK05 | 0 | 0
General Civil Layout - BK05 | BK-BK05-PEDCO-110-CV-PY-0001 | BK-BK05-PEDCO-110-CV-PY-0001General Civil Layout - BK05 | 0 | 0
Rough Grading Plans -BK05 | BK-BK05-PEDCO-110-CV-PY-0003 | BK-BK05-PEDCO-110-CV-PY-0003Rough Grading Plans -BK05 | 0 | 0
Site Visit Report (Civil Work) - BK05 | BK-BK05-PEDCO-110-CV-RT-0001 | BK-BK05-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - BK05 | 2022-07-05 | 2022-12-20
MTO For Civil Works - BK05 | BK-BK05-PEDCO-110-CV-MT-0001 | BK-BK05-PEDCO-110-CV-MT-0001MTO For Civil Works - BK05 | 0 | 0
Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0001 | BK-BK05-PEDCO-110-ST-DW-0001Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-05 | 0 | 0
Foundation Drawing For Security Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0002 | BK-BK05-PEDCO-110-ST-DW-0002Foundation Drawing For Security Building For Well Pads - BK-05 | 0 | 0
Structural Drawing For Security Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0003 | BK-BK05-PEDCO-110-ST-DW-0003Structural Drawing For Security Building For Well Pads - BK-05 | 0 | 0
Foundation Drawing For Switchgear Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0004 | BK-BK05-PEDCO-110-ST-DW-0004Foundation Drawing For Switchgear Building For Well Pads - BK-05 | 0 | 0
Structural Drawing For Switchgear Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0005 | BK-BK05-PEDCO-110-ST-DW-0005Structural Drawing For Switchgear Building For Well Pads - BK-05 | 0 | 0
Foundation Drawing For Potable Water Tank For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0006 | BK-BK05-PEDCO-110-ST-DW-0006Foundation Drawing For Potable Water Tank For Well Pads - BK-05 | 0 | 0
Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0007 | BK-BK05-PEDCO-110-ST-DW-0007Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-05 | 0 | 0
Structural Drawing For Diesel Generator Shelter For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0008 | BK-BK05-PEDCO-110-ST-DW-0008Structural Drawing For Diesel Generator Shelter For Well Pads - BK-05 | 0 | 0
MTO For Structural Works - BK05 | BK-BK05-PEDCO-110-ST-MT-0001 | BK-BK05-PEDCO-110-ST-MT-0001MTO For Structural Works - BK05 | 0 | 0
Geotechnical Investigation Report - BK05 | BK-BK05-PEDCO-110-GT-RT-0001 | BK-BK05-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - BK05 | 2022-08-03 | 2022-12-20
Over Head Line Plan and Profile - BK05 | BK-BK05-PEDCO-110-SU-DW-0001 | BK-BK05-PEDCO-110-SU-DW-0001Over Head Line Plan and Profile - BK05 | 2022-05-18 | 2022-12-20
PMR For Pipes - BK05 | BK-BK05-PEDCO-110-PI-MR-0001 | BK-BK05-PEDCO-110-PI-MR-0001PMR For Pipes - BK05 | 2022-10-25 | 0
TBE For Pipes - BK05 | BK-BK05-PEDCO-110-PI-TB-0001 | BK-BK05-PEDCO-110-PI-TB-0001TBE For Pipes - BK05 | 0 | 0
PMR For Pipe Support - BK05 | BK-BK05-PEDCO-110-PI-MR-0002 | BK-BK05-PEDCO-110-PI-MR-0002PMR For Pipe Support - BK05 | 0 | 0
TBE For Pipe Support - BK05 | BK-BK05-PEDCO-110-PI-TB-0002 | BK-BK05-PEDCO-110-PI-TB-0002TBE For Pipe Support - BK05 | 0 | 0
PMR For Main HVAC Equipment - BK05 | BK-BK05-PEDCO-110-HV-MR-0001 | BK-BK05-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - BK05 | 0 | 0
TBE For Main HVAC Equipment - BK05 | BK-BK05-PEDCO-110-HV-TB-0001 | BK-BK05-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - BK05 | 0 | 0
PMR For Transformers - BK05 | BK-BK05-PEDCO-110-EL-MR-0001 | BK-BK05-PEDCO-110-EL-MR-0001PMR For Transformers - BK05 | 2022-07-13 | 2022-12-20
TBE For Transformers - BK05 | BK-BK05-PEDCO-110-EL-TB-0001 | BK-BK05-PEDCO-110-EL-TB-0001TBE For Transformers - BK05 | 0 | 0
PMR For LV Switchgear & MCC - BK05 | BK-BK05-PEDCO-110-EL-MR-0002 | BK-BK05-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - BK05 | 2022-09-11 | 0
TBE For LV Switchgear & MCC - BK05 | BK-BK05-PEDCO-110-EL-TB-0002 | BK-BK05-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - BK05 | 0 | 0
PMR For Emergency Diesel Generator - BK05 | BK-BK05-PEDCO-110-EL-MR-0003 | BK-BK05-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - BK05 | 2022-08-20 | 0
TBE For Emergency Diesel Generator - BK05 | BK-BK05-PEDCO-110-EL-TB-0003 | BK-BK05-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - BK05 | 0 | 0
PMR For UPS System - BK05 | BK-BK05-PEDCO-110-EL-MR-0004 | BK-BK05-PEDCO-110-EL-MR-0004PMR For UPS System - BK05 | 0 | 0
TBE For UPS System - BK05 | BK-BK05-PEDCO-110-EL-TB-0004 | BK-BK05-PEDCO-110-EL-TB-0004TBE For UPS System - BK05 | 0 | 0
PMR For DC Charger - BK05 | BK-BK05-PEDCO-110-EL-MR-0005 | BK-BK05-PEDCO-110-EL-MR-0005PMR For DC Charger - BK05 | 2022-04-27 | 0
TBE For DC Charger - BK05 | BK-BK05-PEDCO-110-EL-TB-0005 | BK-BK05-PEDCO-110-EL-TB-0005TBE For DC Charger - BK05 | 0 | 0
PMR For Capacitor Bank - BK05 | BK-BK05-PEDCO-110-EL-MR-0006 | BK-BK05-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - BK05 | 0 | 0
TBE For Capacitor Bank - BK05 | BK-BK05-PEDCO-110-EL-TB-0006 | BK-BK05-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - BK05 | 0 | 0
PMR For Lighting & Distribution Main Panels - BK05 | BK-BK05-PEDCO-110-EL-MR-0007 | BK-BK05-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - BK05 | 0 | 0
TBE For Lighting & Distribution Main Panels - BK05 | BK-BK05-PEDCO-110-EL-TB-0007 | BK-BK05-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - BK05 | 0 | 0
PMR For Earthing & Lightning System - BK05 | BK-BK05-PEDCO-110-EL-MR-0008 | BK-BK05-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - BK05 | 0 | 0
TBE For Earthing & Lightning System - BK05 | BK-BK05-PEDCO-110-EL-TB-0008 | BK-BK05-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - BK05 | 0 | 0
PMR For Lighting and Small Power Equipment - BK05 | BK-BK05-PEDCO-110-EL-MR-0009 | BK-BK05-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - BK05 | 0 | 0
TBE For Lighting and Small Power Equipment - BK05 | BK-BK05-PEDCO-110-EL-TB-0009 | BK-BK05-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - BK05 | 0 | 0
PMR For Tray/Ladder and Accessories - BK05 | BK-BK05-PEDCO-110-EL-MR-0010 | BK-BK05-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - BK05 | 0 | 0
TBE For Tray/Ladder and Accessories - BK05 | BK-BK05-PEDCO-110-EL-TB-0010 | BK-BK05-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - BK05 | 0 | 0
PMR For Power & Control Cables - BK05 | BK-BK05-PEDCO-110-EL-MR-0011 | BK-BK05-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - BK05 | 0 | 0
TBE For Power & Control Cables - BK05 | BK-BK05-PEDCO-110-EL-TB-0011 | BK-BK05-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - BK05 | 0 | 0
PMR For Electrical Bulk Items - BK05 | BK-BK05-PEDCO-110-EL-MR-0012 | BK-BK05-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - BK05 | 0 | 0
TBE For Electrical Bulk Items - BK05 | BK-BK05-PEDCO-110-EL-TB-0012 | BK-BK05-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - BK05 | 0 | 0
PMR For Transmission Over head Line - BK05 | BK-BK05-PEDCO-110-EL-MR-0013 | BK-BK05-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - BK05 | 0 | 0
TBE For Transmission Over head Line - BK05 | BK-BK05-PEDCO-110-EL-TB-0013 | BK-BK05-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - BK05 | 0 | 0
PMR For Steel Structure Items - BK05 | BK-BK05-PEDCO-110-ST-MR-0001 | BK-BK05-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - BK05 | 0 | 0
TBE For Steel Structure Items - BK05 | BK-BK05-PEDCO-110-ST-TB-0001 | BK-BK05-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - BK05 | 0 | 0
PMR For Anchor Bolts - BK05 | BK-BK05-PEDCO-110-ST-MR-0002 | BK-BK05-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - BK05 | 0 | 0
TBE For Anchor Bolts - BK05 | BK-BK05-PEDCO-110-ST-TB-0002 | BK-BK05-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - BK05 | 0 | 0
PMR For Blast Proof Doors - BK05 | BK-BK05-PEDCO-110-ST-MR-0003 | BK-BK05-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - BK05 | 0 | 0
TBE For Blast Proof Doors - BK05 | BK-BK05-PEDCO-110-ST-TB-0003 | BK-BK05-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - BK05 | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure - BK05 | BK-BK05-PEDCO-110-CO-PR-0001 | BK-BK05-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - BK05 | 0 | 0
Technical/Site Queries | BK-BK05-PEDCO-110-GE-TQ-0001 | BK-BK05-PEDCO-110-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets - BK05 | BK-BK05-PEDCO-110-GE-DO-0001 | BK-BK05-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK05 | 0 | 0
Operating Manual - BK05 | BK-BK05-PEDCO-110-GE-ML-0001 | BK-BK05-PEDCO-110-GE-ML-0001Operating Manual - BK05 | 0 | 0
As-Built Document Booklets - BK05 | BK-BK05-PEDCO-110-GE-DO-0001 | BK-BK05-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK05 | 0 | 0
Final Engineering Dossier - BK05 | BK-BK05-PEDCO-110-GE-DO-0002 | BK-BK05-PEDCO-110-GE-DO-0002Final Engineering Dossier - BK05 | 0 | 0
Endorsement Report For Basic Design & Scope of Work | BK-PPL-PEDCO-320-GE-RT-0001 | BK-PPL-PEDCO-320-GE-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2022-12-20
Value Engineering Study Report | BK-PPL-PEDCO-320-GE-RT-0002 | BK-PPL-PEDCO-320-GE-RT-0002Value Engineering Study Report | 2022-02-01 | 2022-12-20
HAZID Report For Pipeline | BK-PPL-PEDCO-320-GE-RT-0003 | BK-PPL-PEDCO-320-GE-RT-0003HAZID Report For Pipeline | 2022-08-01 | 2022-11-19
HAZOP Report For Pipeline | BK-PPL-PEDCO-320-GE-RT-0004 | BK-PPL-PEDCO-320-GE-RT-0004HAZOP Report For Pipeline | 2022-08-01 | 2022-11-19
Drainage Philosophy | BK-PPL-PEDCO-320-PR-PH-0001 | BK-PPL-PEDCO-320-PR-PH-0001Drainage Philosophy | 2022-01-31 | 2022-12-20
Control Philosophy | BK-PPL-PEDCO-320-PR-PH-0002 | BK-PPL-PEDCO-320-PR-PH-0002Control Philosophy | 2022-05-09 | 2022-12-20
Flare,Blow Down And Relief Philosophy | BK-PPL-PEDCO-320-PR-PH-0003 | BK-PPL-PEDCO-320-PR-PH-0003Flare,Blow Down And Relief Philosophy | 0 | 0
Isolation Philosophy | BK-PPL-PEDCO-320-PR-PH-0004 | BK-PPL-PEDCO-320-PR-PH-0004Isolation Philosophy | 2021-11-21 | 2022-08-20
ESD Philosophy | BK-PPL-PEDCO-320-PR-PH-0005 | BK-PPL-PEDCO-320-PR-PH-0005ESD Philosophy | 2022-05-09 | 2022-12-20
Process Description | BK-PPL-PEDCO-320-PR-DP-0001 | BK-PPL-PEDCO-320-PR-DP-0001Process Description | 2022-02-19 | 2022-12-20
Calculation Note For PSV Sizing | BK-PPL-PEDCO-320-PR-CN-0001 | BK-PPL-PEDCO-320-PR-CN-0001Calculation Note For PSV Sizing | 2022-02-19 | 2022-12-20
Symbol & Legend For PFD and P&ID | BK-PPL-PEDCO-320-PR-PI-0003 | BK-PPL-PEDCO-320-PR-PI-0003Symbol & Legend For PFD and P&ID | 2022-01-24 | 2022-12-20
Process Flow Diagram For pipelines | BK-PPL-PEDCO-320-PR-PF-0001 | BK-PPL-PEDCO-320-PR-PF-0001Process Flow Diagram For pipelines | 2021-11-17 | 2022-12-20
P&ID - Gas Pipeline (to Siahmakan G.I. Station) | BK-PPL-PEDCO-320-PR-PI-0001 | BK-PPL-PEDCO-320-PR-PI-0001P&ID - Gas Pipeline (to Siahmakan G.I. Station) | 2021-11-17 | 2022-12-20
P&ID - Condensate Pipeline (to Binak PU) | BK-PPL-PEDCO-320-PR-PI-0002 | BK-PPL-PEDCO-320-PR-PI-0002P&ID - Condensate Pipeline (to Binak PU) | 2021-11-17 | 2022-12-20
ESD Block Diagram | BK-PPL-PEDCO-320-PR-BD-0001 | BK-PPL-PEDCO-320-PR-BD-0001ESD Block Diagram | 2022-05-30 | 2022-12-20
Cause & Effect Diagram | BK-PPL-PEDCO-320-PR-CE-0001 | BK-PPL-PEDCO-320-PR-CE-0001Cause & Effect Diagram | 2022-06-11 | 2022-12-20
Pipelines Hydraulic Calculation Report | BK-PPL-PEDCO-320-PR-RT-0001 | BK-PPL-PEDCO-320-PR-RT-0001Pipelines Hydraulic Calculation Report | 2021-11-17 | 2022-12-20
Equipment List | BK-PPL-PEDCO-320-PR-LI-0001 | BK-PPL-PEDCO-320-PR-LI-0001Equipment List | 2022-02-19 | 2022-12-20
Line List | BK-PPL-PEDCO-320-PR-LI-0002 | BK-PPL-PEDCO-320-PR-LI-0002Line List | 2022-02-16 | 2022-12-20
Relief Load Summary | BK-PPL-PEDCO-320-PR-LI-0003 | BK-PPL-PEDCO-320-PR-LI-0003Relief Load Summary | 2022-04-12 | 2022-12-20
Tie in list | BK-PPL-PEDCO-320-PR-LI-0004 | BK-PPL-PEDCO-320-PR-LI-0004Tie in list | 2022-02-19 | 2022-12-20
Process Data Sheets For Instrument Devices | BK-PPL-PEDCO-110-PR-DT-0001 | BK-PPL-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices | #N/A | #N/A
Specification For Pig Traps | BK-PPL-PEDCO-320-ME-SP-0001 | BK-PPL-PEDCO-320-ME-SP-0001Specification For Pig Traps | 2021-09-04 | 2022-01-31
Data Sheets For Pig Traps | BK-PPL-PEDCO-320-ME-DT-0001 | BK-PPL-PEDCO-320-ME-DT-0001Data Sheets For Pig Traps | 2021-12-13 | 2022-10-12
Piping Material Specification | BK-PPL-PEDCO-320-PI-SP-0001 | BK-PPL-PEDCO-320-PI-SP-0001Piping Material Specification | 2021-12-12 | 2022-12-20
Unit Plot Plan For Pig Receiver Area (in Siahmakan G.I. Station) | BK-PPL-PEDCO-320-PI-PY-0001 | BK-PPL-PEDCO-320-PI-PY-0001Unit Plot Plan For Pig Receiver Area (in Siahmakan G.I. Station) | 0 | 0
A/G Piping Plan | BK-PPL-PEDCO-320-PI-DW-0001 | BK-PPL-PEDCO-320-PI-DW-0001A/G Piping Plan | 0 | 0
A/G Piping Isometric | BK-PPL-PEDCO-320-PI-DW-0002 | BK-PPL-PEDCO-320-PI-DW-0002A/G Piping Isometric | 0 | 0
Unit Plot Plan For Binak Production Unit | BK-PPL-PEDCO-320-PI-PY-0002 | BK-PPL-PEDCO-320-PI-PY-0002Unit Plot Plan For Binak Production Unit | 0 | 0
Piping Hydrostatic Test Diagram - PPL | BK-PPL-PEDCO-320-PI-PR-0001 | BK-PPL-PEDCO-320-PI-PR-0001Piping Hydrostatic Test Diagram - PPL | 0 | 0
Corrosion Study & Material Selection Report | BK-PPL-PEDCO-320-PI-RT-0001 | BK-PPL-PEDCO-320-PI-RT-0001Corrosion Study & Material Selection Report | 2021-12-12 | 2022-07-31
Wall Thickness Calculation Report | BK-PPL-PEDCO-320-PI-RT-0002 | BK-PPL-PEDCO-320-PI-RT-0002Wall Thickness Calculation Report | 2021-12-12 | 2022-12-20
Stress Analysis Calculations Report | BK-PPL-PEDCO-320-PI-RT-0003 | BK-PPL-PEDCO-320-PI-RT-0003Stress Analysis Calculations Report | 0 | 0
PDMS Model Review Report (30%) | BK-PPL-PEDCO-320-PI-RT-0004 | BK-PPL-PEDCO-320-PI-RT-0004PDMS Model Review Report (30%) | 2022-09-05 | 0
PDMS Model Review Report (60%) | BK-PPL-PEDCO-320-PI-RT-0005 | BK-PPL-PEDCO-320-PI-RT-0005PDMS Model Review Report (60%) | 0 | 0
PDMS Model Review Report (90%) | BK-PPL-PEDCO-320-PI-RT-0006 | BK-PPL-PEDCO-320-PI-RT-0006PDMS Model Review Report (90%) | 0 | 0
Pipe Support List | BK-PPL-PEDCO-320-PI-LI-0001 | BK-PPL-PEDCO-320-PI-LI-0001Pipe Support List | 0 | 0
Piping Tie-In List | BK-PPL-PEDCO-320-PI-LI-0002 | BK-PPL-PEDCO-320-PI-LI-0002Piping Tie-In List | 0 | 0
MTO For Pipes | BK-PPL-PEDCO-320-PI-MT-0001 | BK-PPL-PEDCO-320-PI-MT-0001MTO For Pipes | 0 | 0
MTO For Fittings | BK-PPL-PEDCO-320-PI-MT-0002 | BK-PPL-PEDCO-320-PI-MT-0002MTO For Fittings | 0 | 0
MTO For Flanges | BK-PPL-PEDCO-320-PI-MT-0003 | BK-PPL-PEDCO-320-PI-MT-0003MTO For Flanges | 0 | 0
MTO For Manual Valves | BK-PPL-PEDCO-320-PI-MT-0004 | BK-PPL-PEDCO-320-PI-MT-0004MTO For Manual Valves | 0 | 0
MTO For Gaskets | BK-PPL-PEDCO-320-PI-MT-0005 | BK-PPL-PEDCO-320-PI-MT-0005MTO For Gaskets | 0 | 0
MTO For Bolt & Nuts | BK-PPL-PEDCO-320-PI-MT-0006 | BK-PPL-PEDCO-320-PI-MT-0006MTO For Bolt & Nuts | 0 | 0
MTO For Insulation Joints | BK-PPL-PEDCO-320-PI-MT-0007 | BK-PPL-PEDCO-320-PI-MT-0007MTO For Insulation Joints | 0 | 0
MTO For Insulation | BK-PPL-PEDCO-320-PI-MT-0008 | BK-PPL-PEDCO-320-PI-MT-0008MTO For Insulation | 0 | 0
MTO For Painting | BK-PPL-PEDCO-320-PI-MT-0009 | BK-PPL-PEDCO-320-PI-MT-0009MTO For Painting | 0 | 0
MTO For Coating of Underground Piping | BK-PPL-PEDCO-320-PI-MT-0010 | BK-PPL-PEDCO-320-PI-MT-0010MTO For Coating of Underground Piping | 0 | 0
Pipeline Material Specification | BK-PPL-PEDCO-320-PL-SP-0001 | BK-PPL-PEDCO-320-PL-SP-0001Pipeline Material Specification | 2021-12-12 | 2022-12-20
Calculation Note For Pipeline Wall Thickness | BK-PPL-PEDCO-320-PL-CN-0001 | BK-PPL-PEDCO-320-PL-CN-0001Calculation Note For Pipeline Wall Thickness | 2021-12-12 | 2022-12-20
Data Sheets For Anchor Flanges | BK-PPL-PEDCO-320-PL-DT-0001 | BK-PPL-PEDCO-320-PL-DT-0001Data Sheets For Anchor Flanges | 0 | 0
Data Sheets For Barred Tee | BK-PPL-PEDCO-320-PL-DT-0002 | BK-PPL-PEDCO-320-PL-DT-0002Data Sheets For Barred Tee | 2022-03-27 | 2022-12-20
Data Sheets For Insulation Joints | BK-PPL-PEDCO-320-PL-DT-0003 | BK-PPL-PEDCO-320-PL-DT-0003Data Sheets For Insulation Joints | 2022-06-06 | 2022-12-20
Data Sheets For Rock Shield | BK-PPL-PEDCO-320-PL-DT-0004 | BK-PPL-PEDCO-320-PL-DT-0004Data Sheets For Rock Shield | 0 | 0
Standard Support Drawings | BK-PPL-PEDCO-320-PL-DW-0001 | BK-PPL-PEDCO-320-PL-DW-0001Standard Support Drawings | 0 | 0
Pipeline Standard Drawings | BK-PPL-PEDCO-320-PL-DW-0006 | BK-PPL-PEDCO-320-PL-DW-0006Pipeline Standard Drawings | 0 | 0
Pipeline Hydrostatic Test Diagram - PPL | BK-PPL-PEDCO-320-PL-PR-0001 | BK-PPL-PEDCO-320-PL-PR-0001Pipeline Hydrostatic Test Diagram - PPL | 0 | 0
Stress Analysis Calculations Report For Pipelines | BK-PPL-PEDCO-320-PL-RT-0001 | BK-PPL-PEDCO-320-PL-RT-0001Stress Analysis Calculations Report For Pipelines | 0 | 0
MTO For Line Pipe | BK-PPL-PEDCO-320-PL-MT-0001 | BK-PPL-PEDCO-320-PL-MT-0001MTO For Line Pipe | 2021-08-22 | 2022-12-20
MTO For Pipeline Field Joints Coating | BK-PPL-PEDCO-320-PL-MT-0002 | BK-PPL-PEDCO-320-PL-MT-0002MTO For Pipeline Field Joints Coating | 0 | 0
MTO For Pipeline Flange, Fittings, Gasket and Bolt | BK-PPL-PEDCO-320-PL-MT-0003 | BK-PPL-PEDCO-320-PL-MT-0003MTO For Pipeline Flange, Fittings, Gasket and Bolt | 0 | 0
Instrument & Control System Basis of Design | BK-PPL-PEDCO-320-IN-DB-0001 | BK-PPL-PEDCO-320-IN-DB-0001Instrument & Control System Basis of Design | 0 | 0
Instrument & Control System Design Criteria | BK-PPL-PEDCO-320-IN-DC-0001 | BK-PPL-PEDCO-320-IN-DC-0001Instrument & Control System Design Criteria | 2022-01-03 | 2022-12-20
Fire & Gas Detection Design Criteria | BK-PPL-PEDCO-320-IN-DC-0002 | BK-PPL-PEDCO-320-IN-DC-0002Fire & Gas Detection Design Criteria | 2022-05-31 | 2022-08-22
Data Sheets For Pressure & Diff. Pressure Gauge | BK-PPL-PEDCO-320-IN-DT-0001 | BK-PPL-PEDCO-320-IN-DT-0001Data Sheets For Pressure & Diff. Pressure Gauge | 2022-02-02 | 2022-12-20
Data Sheets For Temperature Gauge | BK-PPL-PEDCO-320-IN-DT-0002 | BK-PPL-PEDCO-320-IN-DT-0002Data Sheets For Temperature Gauge | 2022-02-05 | 2022-12-20
Data Sheets For Pressure/Diff. Pressure Transmitter | BK-PPL-PEDCO-320-IN-DT-0003 | BK-PPL-PEDCO-320-IN-DT-0003Data Sheets For Pressure/Diff. Pressure Transmitter | 2022-02-13 | 2022-12-20
Data Sheets For Pressure & Safety Relief Valves | BK-PPL-PEDCO-320-IN-DT-0005 | BK-PPL-PEDCO-320-IN-DT-0005Data Sheets For Pressure & Safety Relief Valves | 2022-03-27 | 2022-12-20
Data Sheets For ON/OFF & Shutdown Valves | BK-PPL-PEDCO-320-IN-DT-0006 | BK-PPL-PEDCO-320-IN-DT-0006Data Sheets For ON/OFF & Shutdown Valves | 2022-05-28 | 2022-12-20
Data Sheets For Corrosion Coupon/ Probe | BK-PPL-PEDCO-320-IN-DT-0009 | BK-PPL-PEDCO-320-IN-DT-0009Data Sheets For Corrosion Coupon/ Probe | 2022-02-02 | 2022-12-20
Data Sheets For Pig Signaler | BK-PPL-PEDCO-320-IN-DT-0010 | BK-PPL-PEDCO-320-IN-DT-0010Data Sheets For Pig Signaler | 2022-02-02 | 2022-12-20
Data Sheets For F&G Detectors & Equipment | BK-PPL-PEDCO-320-IN-DT-0011 | BK-PPL-PEDCO-320-IN-DT-0011Data Sheets For F&G Detectors & Equipment | 0 | 0
Data Sheets For LBV | BK-PPL-PEDCO-320-IN-DT-0012 | BK-PPL-PEDCO-320-IN-DT-0012Data Sheets For LBV | 2022-03-27 | 2022-12-20
Typical Instrument Installation Drawing | BK-PPL-PEDCO-320-IN-DW-0001 | BK-PPL-PEDCO-320-IN-DW-0001Typical Instrument Installation Drawing | 0 | 0
Block Diagram Configuration For Control/ESD/F&G System | BK-PPL-PEDCO-320-IN-BD-0001 | BK-PPL-PEDCO-320-IN-BD-0001Block Diagram Configuration For Control/ESD/F&G System | 2021-09-01 | 2022-12-20
Instrument Earthing Typical Diagram | BK-PPL-PEDCO-320-IN-DG-0001 | BK-PPL-PEDCO-320-IN-DG-0001Instrument Earthing Typical Diagram | 2021-12-29 | 0
Instrument Hook-up Diagram | BK-PPL-PEDCO-320-IN-DG-0002 | BK-PPL-PEDCO-320-IN-DG-0002Instrument Hook-up Diagram | 2022-06-15 | 2022-12-20
ESD Level Hierarchy | BK-PPL-PEDCO-320-IN-DG-0003 | BK-PPL-PEDCO-320-IN-DG-0003ESD Level Hierarchy | 0 | 0
ESD System Loop Diagram | BK-PPL-PEDCO-320-IN-DG-0004 | BK-PPL-PEDCO-320-IN-DG-0004ESD System Loop Diagram | 0 | 0
Control System Loop Diagram | BK-PPL-PEDCO-320-IN-DG-0005 | BK-PPL-PEDCO-320-IN-DG-0005Control System Loop Diagram | 2022-06-25 | 2022-12-20
Instrument Air Piping and Air Header Diagram | BK-PPL-PEDCO-320-IN-DG-0006 | BK-PPL-PEDCO-320-IN-DG-0006Instrument Air Piping and Air Header Diagram | 0 | 0
Instrument & F&G Junction Box Termination Diagram | BK-PPL-PEDCO-320-IN-DG-0007 | BK-PPL-PEDCO-320-IN-DG-0007Instrument & F&G Junction Box Termination Diagram | 2022-06-19 | 2022-12-20
Control System Logic Diagram | BK-PPL-PEDCO-320-IN-LD-0001 | BK-PPL-PEDCO-320-IN-LD-0001Control System Logic Diagram | 2022-06-22 | 2022-12-20
ESD Logic Diagram | BK-PPL-PEDCO-320-IN-LD-0002 | BK-PPL-PEDCO-320-IN-LD-0002ESD Logic Diagram | 0 | 0
Control Room Cable Route Layout | BK-PPL-PEDCO-320-IN-PY-0001 | BK-PPL-PEDCO-320-IN-PY-0001Control Room Cable Route Layout | 0 | 0
Instrument Location Layout | BK-PPL-PEDCO-320-IN-PY-0002 | BK-PPL-PEDCO-320-IN-PY-0002Instrument Location Layout | 2022-07-23 | 2022-12-20
Instrument Cable Trench/Route Layout Drawing | BK-PPL-PEDCO-320-IN-PY-0003 | BK-PPL-PEDCO-320-IN-PY-0003Instrument Cable Trench/Route Layout Drawing | 2022-07-27 | 2022-12-20
Control Room Arrangement Layout | BK-PPL-PEDCO-320-IN-PY-0006 | BK-PPL-PEDCO-320-IN-PY-0006Control Room Arrangement Layout | 0 | 0
F&G System Loop Diagram | BK-PPL-PEDCO-320-IN-PY-0007 | BK-PPL-PEDCO-320-IN-PY-0007F&G System Loop Diagram | 0 | 0
F&G Cause and Effect Diagram | BK-PPL-PEDCO-320-IN-PY-0008 | BK-PPL-PEDCO-320-IN-PY-0008F&G Cause and Effect Diagram | 0 | 0
F&G Location Layout For Process Area | BK-PPL-PEDCO-320-IN-PY-0009 | BK-PPL-PEDCO-320-IN-PY-0009F&G Location Layout For Process Area | 0 | 0
Instrument Index | BK-PPL-PEDCO-320-IN-LI-0001 | BK-PPL-PEDCO-320-IN-LI-0001Instrument Index | 2022-02-02 | 2022-12-20
I/O List For Control System | BK-PPL-PEDCO-320-IN-LI-0002 | BK-PPL-PEDCO-320-IN-LI-0002I/O List For Control System | 2022-06-21 | 2022-12-20
I/O List For ESD /F&G System | BK-PPL-PEDCO-320-IN-LI-0003 | BK-PPL-PEDCO-320-IN-LI-0003I/O List For ESD /F&G System | 0 | 0
Panels & Junction Box List | BK-PPL-PEDCO-320-IN-LI-0004 | BK-PPL-PEDCO-320-IN-LI-0004Panels & Junction Box List | 2022-06-22 | 2022-12-20
Set Point & Alarm List | BK-PPL-PEDCO-320-IN-LI-0005 | BK-PPL-PEDCO-320-IN-LI-0005Set Point & Alarm List | 2022-06-22 | 2022-12-20
I&C Power Consumption Summary | BK-PPL-PEDCO-320-IN-LI-0006 | BK-PPL-PEDCO-320-IN-LI-0006I&C Power Consumption Summary | 0 | 0
Instrument and F&G Cable List | BK-PPL-PEDCO-320-IN-LI-0007 | BK-PPL-PEDCO-320-IN-LI-0007Instrument and F&G Cable List | 0 | 0
F&G Detector List | BK-PPL-PEDCO-320-IN-LI-0008 | BK-PPL-PEDCO-320-IN-LI-0008F&G Detector List | 0 | 0
MTO for Bulk Item and Installation Accessories | BK-PPL-PEDCO-320-IN-MT-0001 | BK-PPL-PEDCO-320-IN-MT-0001MTO for Bulk Item and Installation Accessories | 0 | 0
MTO For Instrument/F&G Cable | BK-PPL-PEDCO-320-IN-MT-0002 | BK-PPL-PEDCO-320-IN-MT-0002MTO For Instrument/F&G Cable | 0 | 0
MTO For Instrument/F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-MT-0003 | BK-PPL-PEDCO-320-IN-MT-0003MTO For Instrument/F&G Junction box and Gland | 0 | 0
MTO For Instrument Tube and Fitting | BK-PPL-PEDCO-320-IN-MT-0004 | BK-PPL-PEDCO-320-IN-MT-0004MTO For Instrument Tube and Fitting | 0 | 0
MTO For Instrument Cable Tray/Ladder | BK-PPL-PEDCO-320-IN-MT-0005 | BK-PPL-PEDCO-320-IN-MT-0005MTO For Instrument Cable Tray/Ladder | 0 | 0
MTO For Safety Sign | BK-PPL-PEDCO-320-SA-MT-0002 | BK-PPL-PEDCO-320-SA-MT-0002MTO For Safety Sign | 0 | 0
Active Fire Protection and Safety Concept | BK-PPL-PEDCO-320-SA-DB-0001 | BK-PPL-PEDCO-320-SA-DB-0001Active Fire Protection and Safety Concept | 2021-11-16 | 2022-12-20
Data Sheets For Safety Equipment | BK-PPL-PEDCO-320-SA-DT-0002 | BK-PPL-PEDCO-320-SA-DT-0002Data Sheets For Safety Equipment | 0 | 0
Data Sheets For fire fighting Equipment | BK-PPL-PEDCO-320-SA-DT-0003 | BK-PPL-PEDCO-320-SA-DT-0003Data Sheets For fire fighting Equipment | 0 | 0
Data Sheets For safety sign | BK-PPL-PEDCO-320-SA-DT-0004 | BK-PPL-PEDCO-320-SA-DT-0004Data Sheets For safety sign | 0 | 0
Hazardous Area Classification Layout | BK-PPL-PEDCO-320-SA-PY-0001 | BK-PPL-PEDCO-320-SA-PY-0001Hazardous Area Classification Layout | 0 | 0
Safety & Fire Fighting Equipment Location Layout | BK-PPL-PEDCO-320-SA-PY-0002 | BK-PPL-PEDCO-320-SA-PY-0002Safety & Fire Fighting Equipment Location Layout | 0 | 0
Escape Route & Safety Sign Layout | BK-PPL-PEDCO-320-SA-PY-0003 | BK-PPL-PEDCO-320-SA-PY-0003Escape Route & Safety Sign Layout | 0 | 0
QRA Report | BK-PPL-PEDCO-320-SA-RT-0003 | BK-PPL-PEDCO-320-SA-RT-0003QRA Report | 2022-08-06 | 2022-12-20
Hazard Source List | BK-PPL-PEDCO-320-SA-LI-0001 | BK-PPL-PEDCO-320-SA-LI-0001Hazard Source List | 2021-11-16 | 2022-12-20
MTO For Safety & Fire Fighting Equipment | BK-PPL-PEDCO-320-SA-MT-0001 | BK-PPL-PEDCO-320-SA-MT-0001MTO For Safety & Fire Fighting Equipment | 0 | 0
Calculation Note For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-CN-0001 | BK-PPL-PEDCO-320-EL-CN-0001Calculation Note For Cathodic Protection System for Siahmakan Gas Injection | 0 | 0
Data Sheets For Expansion of LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DT-0001 | BK-PPL-PEDCO-320-EL-DT-0001Data Sheets For Expansion of LV Switchgear in Siahmakan Gas Injection | 0 | 0
Data Sheets For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DT-0002 | BK-PPL-PEDCO-320-EL-DT-0002Data Sheets For Cathodic Protection System for Siahmakan Gas Injection | 0 | 0
Single Line Diagram For Expansion Of Upstream LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-SL-0001 | BK-PPL-PEDCO-320-EL-SL-0001Single Line Diagram For Expansion Of Upstream LV Switchgear in Siahmakan Gas Injection | 2022-05-31 | 2022-12-20
Interconnection Wiring Diagram in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DG-0002 | BK-PPL-PEDCO-320-EL-DG-0002Interconnection Wiring Diagram in Siahmakan Gas Injection | 0 | 0
Interconnection Wiring Diagrams For Cathodic Protection Systems for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DG-0003 | BK-PPL-PEDCO-320-EL-DG-0003Interconnection Wiring Diagrams For Cathodic Protection Systems for Siahmakan Gas Injection | 0 | 0
Area Earthing Layout in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-PY-0001 | BK-PPL-PEDCO-320-EL-PY-0001Area Earthing Layout in Siahmakan Gas Injection | 0 | 0
Area Electrical Cable Route & Section Layout in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-PY-0002 | BK-PPL-PEDCO-320-EL-PY-0002Area Electrical Cable Route & Section Layout in Siahmakan Gas Injection | 0 | 0
Layout For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-PY-0003 | BK-PPL-PEDCO-320-EL-PY-0003Layout For Cathodic Protection System for Siahmakan Gas Injection | 2022-05-02 | 2022-12-20
Electrical Load List in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-LI-0001 | BK-PPL-PEDCO-320-EL-LI-0001Electrical Load List in Siahmakan Gas Injection | 2022-05-30 | 2022-12-20
Electrical Power & Control Cable List in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-LI-0002 | BK-PPL-PEDCO-320-EL-LI-0002Electrical Power & Control Cable List in Siahmakan Gas Injection | 2022-05-31 | 2022-12-20
Cable Schedule For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-LI-0003 | BK-PPL-PEDCO-320-EL-LI-0003Cable Schedule For Cathodic Protection System for Siahmakan Gas Injection | 0 | 0
MTO For Earthing & Lightning Systems in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0001 | BK-PPL-PEDCO-320-EL-MT-0001MTO For Earthing & Lightning Systems in Siahmakan Gas Injection | 0 | 0
MTO For Power & Control Cables in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0002 | BK-PPL-PEDCO-320-EL-MT-0002MTO For Power & Control Cables in Siahmakan Gas Injection | 0 | 0
MTO For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0003 | BK-PPL-PEDCO-320-EL-MT-0003MTO For Cathodic Protection System for Siahmakan Gas Injection | 0 | 0
MTO For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0004 | BK-PPL-PEDCO-320-EL-MT-0004MTO For Electrical Bulk Items in Siahmakan Gas Injection | 0 | 0
MTO For Lighting & Small Powers in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0006 | BK-PPL-PEDCO-320-EL-MT-0006MTO For Lighting & Small Powers in Siahmakan Gas Injection | 0 | 0
Civil Layout For Pig Receiver Area (In Siahmakan G.I. Station) | BK-PPL-PEDCO-320-CV-PY-0001 | BK-PPL-PEDCO-320-CV-PY-0001Civil Layout For Pig Receiver Area (In Siahmakan G.I. Station) | 2022-06-14 | 2022-12-20
Civil Layout For LBV Stations | BK-PPL-PEDCO-320-CV-PY-0002 | BK-PPL-PEDCO-320-CV-PY-0002Civil Layout For LBV Stations | 2022-08-31 | 2022-12-20
Site Visit Report (Civil Work) - 8" & 4" Pipelines | BK-PPL-PEDCO-110-CV-RT-0001 | BK-PPL-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - 8" & 4" Pipelines | #N/A | #N/A
Foundation Drawing For Pig Receiver (PL-3101 In Siahmakan G.I. Station) | BK-PPL-PEDCO-320-ST-DW-0001 | BK-PPL-PEDCO-320-ST-DW-0001Foundation Drawing For Pig Receiver (PL-3101 In Siahmakan G.I. Station) | 0 | 0
Structural Drawing For LBV Pits | BK-PPL-PEDCO-320-ST-DW-0002 | BK-PPL-PEDCO-320-ST-DW-0002Structural Drawing For LBV Pits | 0 | 0
Geotechnical Investigation Plan for Pipelines | BK-PPL-PEDCO-320-GT-PR-0001 | BK-PPL-PEDCO-320-GT-PR-0001Geotechnical Investigation Plan for Pipelines | 2021-08-11 | 2021-10-25
Geotechnical Investigation Report for Pipelines | BK-PPL-PEDCO-320-GT-RT-0001 | BK-PPL-PEDCO-320-GT-RT-0001Geotechnical Investigation Report for Pipelines | 2022-08-16 | 2022-12-20
Plan & Profile Drawings For Gas Pipeline (to Siahmakan) | BK-PPL-PEDCO-320-SU-DW-0001 | BK-PPL-PEDCO-320-SU-DW-0001Plan & Profile Drawings For Gas Pipeline (to Siahmakan) | 2022-08-28 | 2022-12-20
Plan & Profile Drawings For Condensate Pipeline (to Binak PU) | BK-PPL-PEDCO-320-SU-DW-0002 | BK-PPL-PEDCO-320-SU-DW-0002Plan & Profile Drawings For Condensate Pipeline (to Binak PU) | 0 | 0
PMR For Pig Traps | BK-PPL-PEDCO-320-ME-MR-0001 | BK-PPL-PEDCO-320-ME-MR-0001PMR For Pig Traps | 2022-07-24 | 0
TBE For Pig Traps | BK-PPL-PEDCO-320-ME-TB-0001 | BK-PPL-PEDCO-320-ME-TB-0001TBE For Pig Traps | 2022-06-06 | 2022-12-20
PMR For Line Pipe | BK-PPL-PEDCO-320-PL-MR-0001 | BK-PPL-PEDCO-320-PL-MR-0001PMR For Line Pipe | 2021-12-06 | 0
TBE For Line Pipe | BK-PPL-PEDCO-320-PL-TB-0001 | BK-PPL-PEDCO-320-PL-TB-0001TBE For Line Pipe | 0 | 0
PMR For Line Insulation Joints | BK-PPL-PEDCO-320-PL-MR-0002 | BK-PPL-PEDCO-320-PL-MR-0002PMR For Line Insulation Joints | 0 | 0
TBE For Line Insulation Joints | BK-PPL-PEDCO-320-PL-TB-0002 | BK-PPL-PEDCO-320-PL-TB-0002TBE For Line Insulation Joints | 0 | 0
PMR For Anchor Flanges | BK-PPL-PEDCO-320-PL-MR-0003 | BK-PPL-PEDCO-320-PL-MR-0003PMR For Anchor Flanges | 0 | 0
TBE For Anchor Flanges | BK-PPL-PEDCO-320-PL-TB-0003 | BK-PPL-PEDCO-320-PL-TB-0003TBE For Anchor Flanges | 0 | 0
PMR For Pipeline Flange, Fittings, Gasket and Bolt | BK-PPL-PEDCO-320-PL-MR-0004 | BK-PPL-PEDCO-320-PL-MR-0004PMR For Pipeline Flange, Fittings, Gasket and Bolt | 0 | 0
TBE For Pipeline Flange, Fittings, Gasket and Bolt | BK-PPL-PEDCO-320-PL-TB-0004 | BK-PPL-PEDCO-320-PL-TB-0004TBE For Pipeline Flange, Fittings, Gasket and Bolt | 0 | 0
PMR For Pipeline Rock Shield | BK-PPL-PEDCO-320-PL-MR-0005 | BK-PPL-PEDCO-320-PL-MR-0005PMR For Pipeline Rock Shield | 0 | 0
TBE For Pipeline Rock Shield | BK-PPL-PEDCO-320-PL-TB-0005 | BK-PPL-PEDCO-320-PL-TB-0005TBE For Pipeline Rock Shield | 0 | 0
PMR For Control System/Console/Furniture | BK-PPL-PEDCO-320-IN-MR-0001 | BK-PPL-PEDCO-320-IN-MR-0001PMR For Control System/Console/Furniture | 0 | 0
TBE For Control System/Console/Furniture | BK-PPL-PEDCO-320-IN-TB-0001 | BK-PPL-PEDCO-320-IN-TB-0001TBE For Control System/Console/Furniture | 0 | 0
PMR For ESD System | BK-PPL-PEDCO-320-IN-MR-0002 | BK-PPL-PEDCO-320-IN-MR-0002PMR For ESD System | 0 | 0
TBE For ESD System | BK-PPL-PEDCO-320-IN-TB-0002 | BK-PPL-PEDCO-320-IN-TB-0002TBE For ESD System | 0 | 0
PMR For Corrosion Probe/Coupon | BK-PPL-PEDCO-320-IN-MR-0003 | BK-PPL-PEDCO-320-IN-MR-0003PMR For Corrosion Probe/Coupon | 0 | 0
TBE For Corrosion Probe/Coupon | BK-PPL-PEDCO-320-IN-TB-0003 | BK-PPL-PEDCO-320-IN-TB-0003TBE For Corrosion Probe/Coupon | 0 | 0
PMR For ON/OFF & Shutdown Valves | BK-PPL-PEDCO-320-IN-MR-0004 | BK-PPL-PEDCO-320-IN-MR-0004PMR For ON/OFF & Shutdown Valves | 0 | 0
TBE For ON/OFF & Shutdown Valves | BK-PPL-PEDCO-320-IN-TB-0004 | BK-PPL-PEDCO-320-IN-TB-0004TBE For ON/OFF & Shutdown Valves | 0 | 0
PMR For Pressure Safety Valves (PSV) | BK-PPL-PEDCO-320-IN-MR-0006 | BK-PPL-PEDCO-320-IN-MR-0006PMR For Pressure Safety Valves (PSV) | 0 | 0
TBE For Pressure Safety Valves (PSV) | BK-PPL-PEDCO-320-IN-TB-0006 | BK-PPL-PEDCO-320-IN-TB-0006TBE For Pressure Safety Valves (PSV) | 0 | 0
PMR For Differential Pressure/Pressure Gauge | BK-PPL-PEDCO-320-IN-MR-0008 | BK-PPL-PEDCO-320-IN-MR-0008PMR For Differential Pressure/Pressure Gauge | 0 | 0
TBE For Differential Pressure/Pressure Gauge | BK-PPL-PEDCO-320-IN-TB-0008 | BK-PPL-PEDCO-320-IN-TB-0008TBE For Differential Pressure/Pressure Gauge | 0 | 0
PMR For Pressure/Diff. Pressure Transmitter | BK-PPL-PEDCO-320-IN-MR-0009 | BK-PPL-PEDCO-320-IN-MR-0009PMR For Pressure/Diff. Pressure Transmitter | 0 | 0
TBE For Pressure/Diff. Pressure Transmitter | BK-PPL-PEDCO-320-IN-TB-0009 | BK-PPL-PEDCO-320-IN-TB-0009TBE For Pressure/Diff. Pressure Transmitter | 0 | 0
PMR For Temperature Gauge | BK-PPL-PEDCO-320-IN-MR-0010 | BK-PPL-PEDCO-320-IN-MR-0010PMR For Temperature Gauge | 0 | 0
TBE For Temperature Gauge | BK-PPL-PEDCO-320-IN-TB-0010 | BK-PPL-PEDCO-320-IN-TB-0010TBE For Temperature Gauge | 0 | 0
PMR For Pig Signaler | BK-PPL-PEDCO-320-IN-MR-0013 | BK-PPL-PEDCO-320-IN-MR-0013PMR For Pig Signaler | 0 | 0
TBE For Pig Signaler | BK-PPL-PEDCO-320-IN-TB-0013 | BK-PPL-PEDCO-320-IN-TB-0013TBE For Pig Signaler | 0 | 0
PMR For Instrument Installation Accessories | BK-PPL-PEDCO-320-IN-MR-0014 | BK-PPL-PEDCO-320-IN-MR-0014PMR For Instrument Installation Accessories | 0 | 0
TBE For Instrument Installation Accessories | BK-PPL-PEDCO-320-IN-TB-0014 | BK-PPL-PEDCO-320-IN-TB-0014TBE For Instrument Installation Accessories | 0 | 0
PMR For Instrument Cable Tray | BK-PPL-PEDCO-320-IN-MR-0015 | BK-PPL-PEDCO-320-IN-MR-0015PMR For Instrument Cable Tray | 0 | 0
TBE For Instrument Cable Tray | BK-PPL-PEDCO-320-IN-TB-0015 | BK-PPL-PEDCO-320-IN-TB-0015TBE For Instrument Cable Tray | 0 | 0
PMR For Instrument and F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-MR-0016 | BK-PPL-PEDCO-320-IN-MR-0016PMR For Instrument and F&G Junction box and Gland | 0 | 0
TBE For Instrument and F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-TB-0016 | BK-PPL-PEDCO-320-IN-TB-0016TBE For Instrument and F&G Junction box and Gland | 0 | 0
PMR For Instrument Tube and Fitting | BK-PPL-PEDCO-320-IN-MR-0017 | BK-PPL-PEDCO-320-IN-MR-0017PMR For Instrument Tube and Fitting | 0 | 0
TBE For Instrument Tube and Fitting | BK-PPL-PEDCO-320-IN-TB-0017 | BK-PPL-PEDCO-320-IN-TB-0017TBE For Instrument Tube and Fitting | 0 | 0
PMR For Instrument and F&G Cable | BK-PPL-PEDCO-320-IN-MR-0018 | BK-PPL-PEDCO-320-IN-MR-0018PMR For Instrument and F&G Cable | 0 | 0
TBE For Instrument and F&G Cable | BK-PPL-PEDCO-320-IN-TB-0018 | BK-PPL-PEDCO-320-IN-TB-0018TBE For Instrument and F&G Cable | 0 | 0
PMR For F&G Devices | BK-PPL-PEDCO-320-IN-MR-0019 | BK-PPL-PEDCO-320-IN-MR-0019PMR For F&G Devices | 0 | 0
TBE For F&G Devices | BK-PPL-PEDCO-320-IN-TB-0019 | BK-PPL-PEDCO-320-IN-TB-0019TBE For F&G Devices | 0 | 0
PMR For LBV | BK-PPL-PEDCO-320-IN-MR-0020 | BK-PPL-PEDCO-320-IN-MR-0020PMR For LBV | 0 | 0
TBE For LBV | BK-PPL-PEDCO-320-IN-TB-0020 | BK-PPL-PEDCO-320-IN-TB-0020TBE For LBV | 0 | 0
PMR For Safety Equipment | BK-PPL-PEDCO-320-SA-MR-0001 | BK-PPL-PEDCO-320-SA-MR-0001PMR For Safety Equipment | 0 | 0
TBE For Safety Equipment | BK-PPL-PEDCO-320-SA-TB-0001 | BK-PPL-PEDCO-320-SA-TB-0001TBE For Safety Equipment | 0 | 0
PMR For Fire Fighting Equipment | BK-PPL-PEDCO-320-SA-MR-0002 | BK-PPL-PEDCO-320-SA-MR-0002PMR For Fire Fighting Equipment | 0 | 0
TBE For Fire Fighting Equipment | BK-PPL-PEDCO-320-SA-TB-0002 | BK-PPL-PEDCO-320-SA-TB-0002TBE For Fire Fighting Equipment | 0 | 0
PMR For Safety Signs | BK-PPL-PEDCO-320-SA-MR-0003 | BK-PPL-PEDCO-320-SA-MR-0003PMR For Safety Signs | 0 | 0
TBE For Safety Signs | BK-PPL-PEDCO-320-SA-TB-0003 | BK-PPL-PEDCO-320-SA-TB-0003TBE For Safety Signs | 0 | 0
PMR For Expansion Of LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0001 | BK-PPL-PEDCO-320-EL-MR-0001PMR For Expansion Of LV Switchgear in Siahmakan Gas Injection | 0 | 0
TBE For Expansion Of LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0001 | BK-PPL-PEDCO-320-EL-TB-0001TBE For Expansion Of LV Switchgear in Siahmakan Gas Injection | 0 | 0
PMR For Power & Control Cables in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0002 | BK-PPL-PEDCO-320-EL-MR-0002PMR For Power & Control Cables in Siahmakan Gas Injection | 0 | 0
TBE For Power & Control Cables in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0002 | BK-PPL-PEDCO-320-EL-TB-0002TBE For Power & Control Cables in Siahmakan Gas Injection | 0 | 0
PMR For Cathodic Protection System | BK-PPL-PEDCO-320-EL-MR-0003 | BK-PPL-PEDCO-320-EL-MR-0003PMR For Cathodic Protection System | 0 | 0
TBE For Cathodic Protection System | BK-PPL-PEDCO-320-EL-TB-0003 | BK-PPL-PEDCO-320-EL-TB-0003TBE For Cathodic Protection System | 0 | 0
PMR For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0004 | BK-PPL-PEDCO-320-EL-MR-0004PMR For Electrical Bulk Items in Siahmakan Gas Injection | 0 | 0
TBE For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0004 | BK-PPL-PEDCO-320-EL-TB-0004TBE For Electrical Bulk Items in Siahmakan Gas Injection | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure | BK-PPL-PEDCO-320-CO-PR-0001 | BK-PPL-PEDCO-320-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure | 0 | 0
Technical/Site Queries | BK-PPL-PEDCO-320-GE-TQ-0001 | BK-PPL-PEDCO-320-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets | BK-PPL-PEDCO-320-GE-DO-0001 | BK-PPL-PEDCO-320-GE-DO-0001As-Built Document Booklets | 0 | 0
Operating Manual | BK-PPL-PEDCO-320-GE-ML-0001 | BK-PPL-PEDCO-320-GE-ML-0001Operating Manual | 0 | 0
As-Built Document Booklets | BK-PPL-PEDCO-320-GE-DO-0001 | BK-PPL-PEDCO-320-GE-DO-0001As-Built Document Booklets | 0 | 0
Final Engineering Dossier | BK-PPL-PEDCO-320-GE-DO-0002 | BK-PPL-PEDCO-320-GE-DO-0002Final Engineering Dossier | 0 | 0
Endorsement Report For Basic Design & Scope of Work | BK-GCS-PEDCO-120-GE-RT-0001 | BK-GCS-PEDCO-120-GE-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2022-12-20
Value Engineering Study Report | BK-GCS-PEDCO-120-GE-RT-0002 | BK-GCS-PEDCO-120-GE-RT-0002Value Engineering Study Report | 2022-02-01 | 2022-12-20
HAZID Report For Compressor Station | BK-GCS-PEDCO-120-GE-RT-0003 | BK-GCS-PEDCO-120-GE-RT-0003HAZID Report For Compressor Station | 2022-08-01 | 2022-11-19
HAZOP Report For Compressor Station | BK-GCS-PEDCO-120-GE-RT-0004 | BK-GCS-PEDCO-120-GE-RT-0004HAZOP Report For Compressor Station | 2022-08-01 | 2022-11-19
SIL Report For Compressor Station | BK-GCS-PEDCO-120-GE-RT-0005 | BK-GCS-PEDCO-120-GE-RT-0005SIL Report For Compressor Station | 2022-08-01 | 2022-11-19
Drainage Philosophy | BK-GCS-PEDCO-120-PR-PH-0001 | BK-GCS-PEDCO-120-PR-PH-0001Drainage Philosophy | 2021-11-21 | 2022-12-20
Control Philosophy | BK-GCS-PEDCO-120-PR-PH-0002 | BK-GCS-PEDCO-120-PR-PH-0002Control Philosophy | 2022-02-20 | 2022-12-20
Flare,Blow Down And Relief Philosophy | BK-GCS-PEDCO-120-PR-PH-0003 | BK-GCS-PEDCO-120-PR-PH-0003Flare,Blow Down And Relief Philosophy | 2021-11-21 | 2022-08-03
Isolation Philosophy | BK-GCS-PEDCO-120-PR-PH-0004 | BK-GCS-PEDCO-120-PR-PH-0004Isolation Philosophy | 2021-11-21 | 2022-05-22
ESD Philosophy | BK-GCS-PEDCO-120-PR-PH-0005 | BK-GCS-PEDCO-120-PR-PH-0005ESD Philosophy | 2022-02-20 | 2022-12-20
Chemical Regeneration Procedure | BK-GCS-PEDCO-120-PR-PR-0001 | BK-GCS-PEDCO-120-PR-PR-0001Chemical Regeneration Procedure | 0 | 0
Startup And Shutdown Procedure | BK-GCS-PEDCO-120-PR-PR-0002 | BK-GCS-PEDCO-120-PR-PR-0002Startup And Shutdown Procedure | 0 | 0
Process & Utility Description | BK-GCS-PEDCO-120-PR-DP-0001 | BK-GCS-PEDCO-120-PR-DP-0001Process & Utility Description | 2022-02-20 | 2022-12-20
Duty Specification For Gas Dehydration Package | BK-GCS-PEDCO-120-PR-SP-0001 | BK-GCS-PEDCO-120-PR-SP-0001Duty Specification For Gas Dehydration Package | 2021-12-08 | 2022-12-20
Duty Specification for Instrument/Plant Air & Nitrogen Packages | BK-GCS-PEDCO-120-PR-SP-0002 | BK-GCS-PEDCO-120-PR-SP-0002Duty Specification for Instrument/Plant Air & Nitrogen Packages | 2021-12-28 | 2022-12-20
Duty Specification for LP Flare Package | BK-GCS-PEDCO-120-PR-SP-0003 | BK-GCS-PEDCO-120-PR-SP-0003Duty Specification for LP Flare Package | 2022-03-09 | 2022-12-20
Duty Specification for Chemical Injection Package | BK-GCS-PEDCO-120-PR-SP-0004 | BK-GCS-PEDCO-120-PR-SP-0004Duty Specification for Chemical Injection Package | 2022-03-09 | 2022-12-20
Calculation Note For Pumps | BK-GCS-PEDCO-120-PR-CN-0001 | BK-GCS-PEDCO-120-PR-CN-0001Calculation Note For Pumps | 2021-12-13 | 2022-12-20
Calculation Note For Drum Sizing | BK-GCS-PEDCO-120-PR-CN-0002 | BK-GCS-PEDCO-120-PR-CN-0002Calculation Note For Drum Sizing | 2021-09-26 | 2022-12-20
Calculation Note For Flow Element Sizing | BK-GCS-PEDCO-120-PR-CN-0003 | BK-GCS-PEDCO-120-PR-CN-0003Calculation Note For Flow Element Sizing | 2022-06-12 | 2022-12-20
Calculation Note For PSV Sizing | BK-GCS-PEDCO-120-PR-CN-0004 | BK-GCS-PEDCO-120-PR-CN-0004Calculation Note For PSV Sizing | 2021-09-26 | 2022-12-20
Calculation Note For Line Sizing | BK-GCS-PEDCO-120-PR-CN-0005 | BK-GCS-PEDCO-120-PR-CN-0005Calculation Note For Line Sizing | 2021-09-26 | 2022-12-20
Calculation Note For Control Valve Sizing | BK-GCS-PEDCO-120-PR-CN-0006 | BK-GCS-PEDCO-120-PR-CN-0006Calculation Note For Control Valve Sizing | 2021-09-26 | 2022-12-20
Calculation Note For Depressurizing (Min. Design Temperature ) | BK-GCS-PEDCO-120-PR-CN-0007 | BK-GCS-PEDCO-120-PR-CN-0007Calculation Note For Depressurizing (Min. Design Temperature ) | 2021-12-13 | 2022-12-20
Process Data Sheets For Inlet Gas K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0001 | BK-GCS-PEDCO-120-PR-DT-0001Process Data Sheets For Inlet Gas K.O. Drum | 2021-11-10 | 2022-12-20
Process Data Sheets For 1st Stage G.C. Suction Drums | BK-GCS-PEDCO-120-PR-DT-0002 | BK-GCS-PEDCO-120-PR-DT-0002Process Data Sheets For 1st Stage G.C. Suction Drums | 2021-11-10 | 2022-12-20
Process Data Sheets For 1st Stage Gas Air Coolers | BK-GCS-PEDCO-120-PR-DT-0003 | BK-GCS-PEDCO-120-PR-DT-0003Process Data Sheets For 1st Stage Gas Air Coolers | 2021-11-07 | 2022-12-20
Process Data Sheets For 2nd Stage G.C. Suction Drums | BK-GCS-PEDCO-120-PR-DT-0004 | BK-GCS-PEDCO-120-PR-DT-0004Process Data Sheets For 2nd Stage G.C. Suction Drums | 2021-11-10 | 2022-12-20
Process Data Sheets For 2nd Stage Gas Air Coolers | BK-GCS-PEDCO-120-PR-DT-0005 | BK-GCS-PEDCO-120-PR-DT-0005Process Data Sheets For 2nd Stage Gas Air Coolers | 2021-11-07 | 2022-12-20
Process Data Sheets For Discharge Gas K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0006 | BK-GCS-PEDCO-120-PR-DT-0006Process Data Sheets For Discharge Gas K.O. Drum | 2021-11-10 | 2022-12-20
Process Data Sheets For Diesel Oil Drum | BK-GCS-PEDCO-120-PR-DT-0007 | BK-GCS-PEDCO-120-PR-DT-0007Process Data Sheets For Diesel Oil Drum | 2021-11-10 | 2022-12-20
Process Data Sheets For Instrument Air Receiver | BK-GCS-PEDCO-120-PR-DT-0008 | BK-GCS-PEDCO-120-PR-DT-0008Process Data Sheets For Instrument Air Receiver | 2021-11-10 | 2022-12-20
Process Data Sheets For Nitrogen Receiver | BK-GCS-PEDCO-120-PR-DT-0009 | BK-GCS-PEDCO-120-PR-DT-0009Process Data Sheets For Nitrogen Receiver | 2021-11-10 | 2022-12-20
Process Data Sheets For Close Drain Drum | BK-GCS-PEDCO-120-PR-DT-0010 | BK-GCS-PEDCO-120-PR-DT-0010Process Data Sheets For Close Drain Drum | 2021-11-10 | 2022-12-20
Process Data Sheets For Elevated Potable Water Tank | BK-GCS-PEDCO-120-PR-DT-0011 | BK-GCS-PEDCO-120-PR-DT-0011Process Data Sheets For Elevated Potable Water Tank | 2021-11-10 | 2022-12-20
Process Data Sheets For Flare K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0012 | BK-GCS-PEDCO-120-PR-DT-0012Process Data Sheets For Flare K.O. Drum | 2021-11-10 | 2022-12-20
Process Data Sheets For Fuel Gas K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0013 | BK-GCS-PEDCO-120-PR-DT-0013Process Data Sheets For Fuel Gas K.O. Drum | 2021-11-10 | 2022-12-20
Process Data Sheets For Slug Catcher | BK-GCS-PEDCO-120-PR-DT-0014 | BK-GCS-PEDCO-120-PR-DT-0014Process Data Sheets For Slug Catcher | 2021-11-10 | 2022-12-20
Process Data Sheets For Degassing Vessel | BK-GCS-PEDCO-120-PR-DT-0015 | BK-GCS-PEDCO-120-PR-DT-0015Process Data Sheets For Degassing Vessel | 2021-11-10 | 2022-12-20
Process Data Sheets For Lean Glycol Storage Tank | BK-GCS-PEDCO-120-PR-DT-0016 | BK-GCS-PEDCO-120-PR-DT-0016Process Data Sheets For Lean Glycol Storage Tank | 2021-11-27 | 2022-12-20
Process Data Sheets For Slug Storage Tank | BK-GCS-PEDCO-120-PR-DT-0018 | BK-GCS-PEDCO-120-PR-DT-0018Process Data Sheets For Slug Storage Tank | 2021-11-27 | 2022-12-20
Process Data Sheets For Glycol Sump Drum | BK-GCS-PEDCO-120-PR-DT-0019 | BK-GCS-PEDCO-120-PR-DT-0019Process Data Sheets For Glycol Sump Drum | 2021-12-28 | 2022-12-20
Process Data Sheets For Slug Pumps | BK-GCS-PEDCO-120-PR-DT-0020 | BK-GCS-PEDCO-120-PR-DT-0020Process Data Sheets For Slug Pumps | 2022-03-27 | 2022-12-20
Process Data Sheets For Glycol Transfer Pumps | BK-GCS-PEDCO-120-PR-DT-0021 | BK-GCS-PEDCO-120-PR-DT-0021Process Data Sheets For Glycol Transfer Pumps | 2022-03-28 | 2022-12-20
Process Data Sheets For Glycol Manual Pump | BK-GCS-PEDCO-120-PR-DT-0022 | BK-GCS-PEDCO-120-PR-DT-0022Process Data Sheets For Glycol Manual Pump | 2022-03-28 | 0
Process Data Sheets For Closed Drain Pumps | BK-GCS-PEDCO-120-PR-DT-0023 | BK-GCS-PEDCO-120-PR-DT-0023Process Data Sheets For Closed Drain Pumps | 2022-03-28 | 2022-12-20
Process Data Sheets For Sump Pumps | BK-GCS-PEDCO-120-PR-DT-0024 | BK-GCS-PEDCO-120-PR-DT-0024Process Data Sheets For Sump Pumps | 2022-03-28 | 0
Process Data Sheets For Flare KO Drum Pumps | BK-GCS-PEDCO-120-PR-DT-0025 | BK-GCS-PEDCO-120-PR-DT-0025Process Data Sheets For Flare KO Drum Pumps | 2022-03-28 | 2022-12-20
Process Data Sheets For Potable Water Pump | BK-GCS-PEDCO-120-PR-DT-0026 | BK-GCS-PEDCO-120-PR-DT-0026Process Data Sheets For Potable Water Pump | 2022-03-28 | 2022-11-14
Process Data Sheets For Glycol Sump Pumps | BK-GCS-PEDCO-120-PR-DT-0027 | BK-GCS-PEDCO-120-PR-DT-0027Process Data Sheets For Glycol Sump Pumps | 0 | 0
Process Data Sheets For Glycol Drain Pump | BK-GCS-PEDCO-120-PR-DT-0028 | BK-GCS-PEDCO-120-PR-DT-0028Process Data Sheets For Glycol Drain Pump | 2022-03-28 | 0
Process Data Sheets of Diesel Pump | BK-GCS-PEDCO-120-PR-DT-0028 | BK-GCS-PEDCO-120-PR-DT-0028Process Data Sheets of Diesel Pump | 2022-03-28 | 0
Process Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-PR-DT-0030 | BK-GCS-PEDCO-120-PR-DT-0030Process Data Sheets For Gas Compressors Packages | 2021-11-07 | 2022-12-20
Process Data Sheets For Chemical Injection Packages | BK-GCS-PEDCO-120-PR-DT-0031 | BK-GCS-PEDCO-120-PR-DT-0031Process Data Sheets For Chemical Injection Packages | 2022-05-09 | 2022-12-20
Process Data Sheets For Instrument Devices | BK-GCS-PEDCO-120-PR-DT-0032 | BK-GCS-PEDCO-120-PR-DT-0032Process Data Sheets For Instrument Devices | 2022-04-20 | 2022-12-20
Process Flow Diagram (PFD) | BK-GCS-PEDCO-120-PR-PF-0001 | BK-GCS-PEDCO-120-PR-PF-0001Process Flow Diagram (PFD) | 2021-08-14 | 2022-12-20
Utility Flow Diagrams (UFD) | BK-GCS-PEDCO-120-PR-UF-0001 | BK-GCS-PEDCO-120-PR-UF-0001Utility Flow Diagrams (UFD) | 2021-10-18 | 2022-12-20
Symbol & Legend For PFD and P&ID | BK-GCS-PEDCO-120-PR-PI-0001 | BK-GCS-PEDCO-120-PR-PI-0001Symbol & Legend For PFD and P&ID | 2021-10-04 | 2022-12-20
P&ID - Gas Compression Inlet Gas Pipeline (Binak) | BK-GCS-PEDCO-120-PR-PI-0002 | BK-GCS-PEDCO-120-PR-PI-0002P&ID - Gas Compression Inlet Gas Pipeline (Binak) | 2021-09-26 | 2022-12-20
P&ID - Gas Compression Inlet Gas Pipeline (Golkhari) | BK-GCS-PEDCO-120-PR-PI-0003 | BK-GCS-PEDCO-120-PR-PI-0003P&ID - Gas Compression Inlet Gas Pipeline (Golkhari) | 2021-09-26 | 2022-12-20
P&ID - Slug Catcher System | BK-GCS-PEDCO-120-PR-PI-0004 | BK-GCS-PEDCO-120-PR-PI-0004P&ID - Slug Catcher System | 2021-09-26 | 2022-12-20
P&ID - Gas Compression Inlet Knock Out Drum | BK-GCS-PEDCO-120-PR-PI-0005 | BK-GCS-PEDCO-120-PR-PI-0005P&ID - Gas Compression Inlet Knock Out Drum | 2021-09-26 | 2022-12-20
P&ID - 1st Stage Gas Compression Suction Drums | BK-GCS-PEDCO-120-PR-PI-0006 | BK-GCS-PEDCO-120-PR-PI-0006P&ID - 1st Stage Gas Compression Suction Drums | 2021-09-26 | 2022-12-20
P&ID - 1st Stage Gas Compression Compressors | BK-GCS-PEDCO-120-PR-PI-0007 | BK-GCS-PEDCO-120-PR-PI-0007P&ID - 1st Stage Gas Compression Compressors | 2021-09-26 | 2022-12-20
P&ID - 1st Stage Gas Compression Air Coolers | BK-GCS-PEDCO-120-PR-PI-0008 | BK-GCS-PEDCO-120-PR-PI-0008P&ID - 1st Stage Gas Compression Air Coolers | 2021-09-26 | 2022-12-20
P&ID - 2nd Stage Gas Compression Suction Drums | BK-GCS-PEDCO-120-PR-PI-0009 | BK-GCS-PEDCO-120-PR-PI-0009P&ID - 2nd Stage Gas Compression Suction Drums | 2021-09-26 | 2022-12-20
P&ID - 2nd Stage Gas Compression Compressors | BK-GCS-PEDCO-120-PR-PI-0010 | BK-GCS-PEDCO-120-PR-PI-0010P&ID - 2nd Stage Gas Compression Compressors | 2021-09-26 | 2022-12-20
P&ID - 2nd Stage Gas Compression Air Coolers | BK-GCS-PEDCO-120-PR-PI-0011 | BK-GCS-PEDCO-120-PR-PI-0011P&ID - 2nd Stage Gas Compression Air Coolers | 2021-09-26 | 2022-12-20
P&ID - 2nd Stage Gas Compression Discharge Drum | BK-GCS-PEDCO-120-PR-PI-0012 | BK-GCS-PEDCO-120-PR-PI-0012P&ID - 2nd Stage Gas Compression Discharge Drum | 2021-09-26 | 2022-12-20
P&ID - Gas Compression Dehydration Package | BK-GCS-PEDCO-120-PR-PI-0013 | BK-GCS-PEDCO-120-PR-PI-0013P&ID - Gas Compression Dehydration Package | 2021-09-26 | 2022-12-20
P&ID - Lean Glycol Storage Tank | BK-GCS-PEDCO-120-PR-PI-0014 | BK-GCS-PEDCO-120-PR-PI-0014P&ID - Lean Glycol Storage Tank | 2021-09-26 | 2022-12-20
P&ID - Instrument & Plant Air System | BK-GCS-PEDCO-120-PR-PI-0015 | BK-GCS-PEDCO-120-PR-PI-0015P&ID - Instrument & Plant Air System | 2022-01-03 | 2022-12-20
P&ID - Nitrogen Generation System | BK-GCS-PEDCO-120-PR-PI-0016 | BK-GCS-PEDCO-120-PR-PI-0016P&ID - Nitrogen Generation System | 2022-01-03 | 2022-12-20
P&ID - Close Drain System | BK-GCS-PEDCO-120-PR-PI-0017 | BK-GCS-PEDCO-120-PR-PI-0017P&ID - Close Drain System | 2021-10-18 | 2022-12-20
P&ID - Corrosion Inhibitor Package | BK-GCS-PEDCO-120-PR-PI-0018 | BK-GCS-PEDCO-120-PR-PI-0018P&ID - Corrosion Inhibitor Package | 2021-10-18 | 2022-12-20
P&ID - Methanol Injection Package | BK-GCS-PEDCO-120-PR-PI-0019 | BK-GCS-PEDCO-120-PR-PI-0019P&ID - Methanol Injection Package | 2021-10-18 | 2022-12-20
P&ID - LP Flare System | BK-GCS-PEDCO-120-PR-PI-0020 | BK-GCS-PEDCO-120-PR-PI-0020P&ID - LP Flare System | 2021-10-18 | 2022-12-20
P&ID - Oily Water Sewer | BK-GCS-PEDCO-120-PR-PI-0021 | BK-GCS-PEDCO-120-PR-PI-0021P&ID - Oily Water Sewer | 2021-10-18 | 2022-12-20
P&ID - Fuel Gas System | BK-GCS-PEDCO-120-PR-PI-0022 | BK-GCS-PEDCO-120-PR-PI-0022P&ID - Fuel Gas System | 2021-10-18 | 2022-12-20
P&ID - Diesel Oil System | BK-GCS-PEDCO-120-PR-PI-0023 | BK-GCS-PEDCO-120-PR-PI-0023P&ID - Diesel Oil System | 2021-10-18 | 2022-12-20
P&ID - Potable Water System | BK-GCS-PEDCO-120-PR-PI-0024 | BK-GCS-PEDCO-120-PR-PI-0024P&ID - Potable Water System | 2021-10-18 | 2022-12-20
P&ID - Glycol Sump Drum | BK-GCS-PEDCO-120-PR-PI-0025 | BK-GCS-PEDCO-120-PR-PI-0025P&ID - Glycol Sump Drum | 2021-09-26 | 2022-12-20
ESD Block Diagram | BK-GCS-PEDCO-120-PR-BD-0001 | BK-GCS-PEDCO-120-PR-BD-0001ESD Block Diagram | 2022-06-11 | 2022-12-20
Cause & Effect Diagram | BK-GCS-PEDCO-120-PR-CE-0001 | BK-GCS-PEDCO-120-PR-CE-0001Cause & Effect Diagram | 2022-05-30 | 2022-12-20
Chemical Injection Points Diagram | BK-GCS-PEDCO-120-PR-DG-0001 | BK-GCS-PEDCO-120-PR-DG-0001Chemical Injection Points Diagram | 0 | 0
Process Main Equipment List | BK-GCS-PEDCO-120-PR-LI-0001 | BK-GCS-PEDCO-120-PR-LI-0001Process Main Equipment List | 2022-02-20 | 2022-12-20
Process Electrical Load List | BK-GCS-PEDCO-120-PR-LI-0002 | BK-GCS-PEDCO-120-PR-LI-0002Process Electrical Load List | 2022-01-19 | 2022-12-20
Tie in list | BK-GCS-PEDCO-120-PR-LI-0003 | BK-GCS-PEDCO-120-PR-LI-0003Tie in list | 2022-02-20 | 2022-12-20
Line List | BK-GCS-PEDCO-120-PR-LI-0004 | BK-GCS-PEDCO-120-PR-LI-0004Line List | 2022-04-30 | 2022-12-20
Chemical Consumption List | BK-GCS-PEDCO-120-PR-LI-0005 | BK-GCS-PEDCO-120-PR-LI-0005Chemical Consumption List | 2022-03-09 | 2022-12-20
Utility Consumption List | BK-GCS-PEDCO-120-PR-LI-0006 | BK-GCS-PEDCO-120-PR-LI-0006Utility Consumption List | 2021-12-28 | 2022-12-20
Emission and Effluent Summary | BK-GCS-PEDCO-120-PR-LI-0007 | BK-GCS-PEDCO-120-PR-LI-0007Emission and Effluent Summary | 2022-06-12 | 2022-12-20
Relief Load Summery | BK-GCS-PEDCO-120-PR-LI-0008 | BK-GCS-PEDCO-120-PR-LI-0008Relief Load Summery | 2022-01-26 | 2022-12-20
Flare Network Study Report | BK-GCS-PEDCO-120-PR-RT-0001 | BK-GCS-PEDCO-120-PR-RT-0001Flare Network Study Report | 2022-01-05 | 2022-12-20
Flare Radiation & Dispersion Study Report | BK-GCS-PEDCO-120-PR-RT-0002 | BK-GCS-PEDCO-120-PR-RT-0002Flare Radiation & Dispersion Study Report | 2022-01-05 | 2022-12-20
Process Simulation Report | BK-GCS-PEDCO-120-PR-RT-0003 | BK-GCS-PEDCO-120-PR-RT-0003Process Simulation Report | 2021-10-17 | 2022-12-20
Specification For Air Cooled Heat Exchangers | BK-GCS-PEDCO-120-ME-SP-0001 | BK-GCS-PEDCO-120-ME-SP-0001Specification For Air Cooled Heat Exchangers | 2021-08-14 | 2022-12-20
Specification For Large Welded Low Pressure Storage Tanks | BK-GCS-PEDCO-120-ME-SP-0010 | BK-GCS-PEDCO-120-ME-SP-0010Specification For Large Welded Low Pressure Storage Tanks | 2021-08-24 | 2022-01-31
Specification For Reciprocating Compressor (API 618) | BK-GCS-PEDCO-120-ME-SP-0002 | BK-GCS-PEDCO-120-ME-SP-0002Specification For Reciprocating Compressor (API 618) | 2021-08-14 | 2022-03-07
Specification For Centrifugal Pumps For Process Services (API610) | BK-GCS-PEDCO-120-ME-SP-0003 | BK-GCS-PEDCO-120-ME-SP-0003Specification For Centrifugal Pumps For Process Services (API610) | 2021-08-22 | 2022-04-19
Specification For Centrifugal Pumps For General Services | BK-GCS-PEDCO-120-ME-SP-0004 | BK-GCS-PEDCO-120-ME-SP-0004Specification For Centrifugal Pumps For General Services | 2021-08-14 | 2022-08-15
Specification For Fire Water Pumps | BK-GCS-PEDCO-120-ME-SP-0005 | BK-GCS-PEDCO-120-ME-SP-0005Specification For Fire Water Pumps | 2021-08-22 | 2022-04-19
Specification For Overhead Travelling Cranes | BK-GCS-PEDCO-120-ME-SP-0009 | BK-GCS-PEDCO-120-ME-SP-0009Specification For Overhead Travelling Cranes | 2021-08-14 | 2022-12-20
Specification for Control Volume Pump (API 675) | BK-GCS-PEDCO-120-ME-SP-0011 | BK-GCS-PEDCO-120-ME-SP-0011Specification for Control Volume Pump (API 675) | 2021-08-24 | 2022-04-19
Specification For Diesel Engines | BK-GCS-PEDCO-120-ME-SP-0012 | BK-GCS-PEDCO-120-ME-SP-0012Specification For Diesel Engines | 2021-08-24 | 2022-03-06
Specification For Air Compressor Package | BK-GCS-PEDCO-120-ME-SP-0006 | BK-GCS-PEDCO-120-ME-SP-0006Specification For Air Compressor Package | 2021-08-14 | 2022-03-07
Specification For Air Dryer Package | BK-GCS-PEDCO-120-ME-SP-0007 | BK-GCS-PEDCO-120-ME-SP-0007Specification For Air Dryer Package | 2021-08-14 | 2022-12-20
Specification For Chemical Injection Package | BK-GCS-PEDCO-120-ME-SP-0008 | BK-GCS-PEDCO-120-ME-SP-0008Specification For Chemical Injection Package | 2022-07-24 | 2022-12-20
Specification For Flare Package | BK-GCS-PEDCO-120-ME-SP-0013 | BK-GCS-PEDCO-120-ME-SP-0013Specification For Flare Package | 2021-08-24 | 2022-03-09
Specification For Nitrogen Package | BK-GCS-PEDCO-120-ME-SP-0014 | BK-GCS-PEDCO-120-ME-SP-0014Specification For Nitrogen Package | 2021-10-06 | 2022-12-20
Mechanical Data Sheets For Inlet Gas K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0001 | BK-GCS-PEDCO-120-ME-DT-0001Mechanical Data Sheets For Inlet Gas K.O. Drum | 2021-12-07 | 2022-12-20
Mechanical Data Sheets For 1st Stage G.C. Suction Drums | BK-GCS-PEDCO-120-ME-DT-0002 | BK-GCS-PEDCO-120-ME-DT-0002Mechanical Data Sheets For 1st Stage G.C. Suction Drums | 2021-12-13 | 2022-12-20
Mechanical Data Sheets For 1st Stage Gas Air Coolers | BK-GCS-PEDCO-120-ME-DT-0003 | BK-GCS-PEDCO-120-ME-DT-0003Mechanical Data Sheets For 1st Stage Gas Air Coolers | 2021-12-29 | 2022-12-20
Mechanical Data Sheets For 2nd Stage G.C. Suction Drums | BK-GCS-PEDCO-120-ME-DT-0004 | BK-GCS-PEDCO-120-ME-DT-0004Mechanical Data Sheets For 2nd Stage G.C. Suction Drums | 2021-12-13 | 2022-12-20
Mechanical Data Sheets For 2nd Stage Gas Air Coolers | BK-GCS-PEDCO-120-ME-DT-0005 | BK-GCS-PEDCO-120-ME-DT-0005Mechanical Data Sheets For 2nd Stage Gas Air Coolers | 2021-12-29 | 2022-12-20
Mechanical Data Sheets For Discharge Gas K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0006 | BK-GCS-PEDCO-120-ME-DT-0006Mechanical Data Sheets For Discharge Gas K.O. Drum | 2021-12-27 | 2022-12-20
Mechanical Data Sheets For Diesel Oil Drum | BK-GCS-PEDCO-120-ME-DT-0007 | BK-GCS-PEDCO-120-ME-DT-0007Mechanical Data Sheets For Diesel Oil Drum | 2021-12-13 | 2022-12-20
Mechanical Data Sheets For Instrument Air Receiver | BK-GCS-PEDCO-120-ME-DT-0008 | BK-GCS-PEDCO-120-ME-DT-0008Mechanical Data Sheets For Instrument Air Receiver | 2021-12-07 | 2022-12-20
Mechanical Data Sheets For Nitrogen Receiver | BK-GCS-PEDCO-120-ME-DT-0009 | BK-GCS-PEDCO-120-ME-DT-0009Mechanical Data Sheets For Nitrogen Receiver | 2021-11-27 | 2022-12-20
Mechanical Data Sheets For Close Drain Drum | BK-GCS-PEDCO-120-ME-DT-0010 | BK-GCS-PEDCO-120-ME-DT-0010Mechanical Data Sheets For Close Drain Drum | 2021-12-13 | 2022-12-20
Mechanical Data Sheets For Elevated Potable Water Tank | BK-GCS-PEDCO-120-ME-DT-0011 | BK-GCS-PEDCO-120-ME-DT-0011Mechanical Data Sheets For Elevated Potable Water Tank | 2021-11-27 | 2022-12-20
Mechanical Data Sheets For Flare K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0012 | BK-GCS-PEDCO-120-ME-DT-0012Mechanical Data Sheets For Flare K.O. Drum | 2022-01-03 | 2022-12-20
Mechanical Data Sheets For Fuel Gas K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0013 | BK-GCS-PEDCO-120-ME-DT-0013Mechanical Data Sheets For Fuel Gas K.O. Drum | 2021-12-13 | 2022-12-20
Mechanical Data Sheets For Slug Catcher | BK-GCS-PEDCO-120-ME-DT-0014 | BK-GCS-PEDCO-120-ME-DT-0014Mechanical Data Sheets For Slug Catcher | 2021-12-28 | 2022-12-20
Mechanical Data Sheets For Degassing Vessel | BK-GCS-PEDCO-120-ME-DT-0015 | BK-GCS-PEDCO-120-ME-DT-0015Mechanical Data Sheets For Degassing Vessel | 2022-03-06 | 2022-12-20
Mechanical Data Sheets For Lean Glycol Storage Tank | BK-GCS-PEDCO-120-ME-DT-0016 | BK-GCS-PEDCO-120-ME-DT-0016Mechanical Data Sheets For Lean Glycol Storage Tank | 2021-11-28 | 2022-12-20
Mechanical Data Sheets For Fire Water Storage Tank | BK-GCS-PEDCO-120-ME-DT-0017 | BK-GCS-PEDCO-120-ME-DT-0017Mechanical Data Sheets For Fire Water Storage Tank | 2022-06-19 | 2022-12-20
Mechanical Data Sheets For Slug Storage Tank | BK-GCS-PEDCO-120-ME-DT-0018 | BK-GCS-PEDCO-120-ME-DT-0018Mechanical Data Sheets For Slug Storage Tank | 2021-12-14 | 2022-12-20
Mechanical Data Sheets For Slug Pumps | BK-GCS-PEDCO-120-ME-DT-0019 | BK-GCS-PEDCO-120-ME-DT-0019Mechanical Data Sheets For Slug Pumps | 2021-12-07 | 2022-09-07
Mechanical Data Sheets For Glycol Transfer Pumps | BK-GCS-PEDCO-120-ME-DT-0020 | BK-GCS-PEDCO-120-ME-DT-0020Mechanical Data Sheets For Glycol Transfer Pumps | 2021-11-27 | 2022-09-07
Mechanical Data Sheets For Glycol Manual Pump | BK-GCS-PEDCO-120-ME-DT-0021 | BK-GCS-PEDCO-120-ME-DT-0021Mechanical Data Sheets For Glycol Manual Pump | 2021-11-27 | 2022-09-07
Mechanical Data Sheets For Closed Drain Pumps | BK-GCS-PEDCO-120-ME-DT-0022 | BK-GCS-PEDCO-120-ME-DT-0022Mechanical Data Sheets For Closed Drain Pumps | 2021-11-27 | 2022-12-20
Mechanical Data Sheets For Sump Pumps | BK-GCS-PEDCO-120-ME-DT-0023 | BK-GCS-PEDCO-120-ME-DT-0023Mechanical Data Sheets For Sump Pumps | 2021-12-07 | 2022-09-07
Mechanical Data Sheets For Flare KO Drum Pumps | BK-GCS-PEDCO-120-ME-DT-0024 | BK-GCS-PEDCO-120-ME-DT-0024Mechanical Data Sheets For Flare KO Drum Pumps | 2021-11-27 | 2022-12-20
Mechanical Data Sheets For Potable Water Pump | BK-GCS-PEDCO-120-ME-DT-0025 | BK-GCS-PEDCO-120-ME-DT-0025Mechanical Data Sheets For Potable Water Pump | 2021-12-07 | 2022-09-07
Mechanical Data Sheets For Diesel Pump | BK-GCS-PEDCO-120-ME-DT-0026 | BK-GCS-PEDCO-120-ME-DT-0026Mechanical Data Sheets For Diesel Pump | 2021-11-27 | 2022-09-07
Mechanical Data Sheets For Overhead Traveling Cranes | BK-GCS-PEDCO-120-ME-DT-0027 | BK-GCS-PEDCO-120-ME-DT-0027Mechanical Data Sheets For Overhead Traveling Cranes | 2022-02-13 | 2022-12-20
Mechanical Data Sheets For Fire Water Jockey Pumps | BK-GCS-PEDCO-120-ME-DT-0028 | BK-GCS-PEDCO-120-ME-DT-0028Mechanical Data Sheets For Fire Water Jockey Pumps | 2022-02-21 | 2022-12-20
Mechanical Data Sheets For Fire Water Main Pumps - Elect. Motor Driven | BK-GCS-PEDCO-120-ME-DT-0029 | BK-GCS-PEDCO-120-ME-DT-0029Mechanical Data Sheets For Fire Water Main Pumps - Elect. Motor Driven | 2022-02-21 | 2022-12-20
Mechanical Data Sheets For Fire Water Main Pumps - Diesel Engine Driven | BK-GCS-PEDCO-120-ME-DT-0030 | BK-GCS-PEDCO-120-ME-DT-0030Mechanical Data Sheets For Fire Water Main Pumps - Diesel Engine Driven | 2022-02-16 | 2022-12-20
Mechanical Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-ME-DT-0031 | BK-GCS-PEDCO-120-ME-DT-0031Mechanical Data Sheets For Gas Compressors Packages | 2021-09-12 | 2022-07-22
Mechanical Data Sheets For Glycol Sump Pumps | BK-GCS-PEDCO-120-ME-DT-0034 | BK-GCS-PEDCO-120-ME-DT-0034Mechanical Data Sheets For Glycol Sump Pumps | 2021-12-08 | 2022-12-20
Mechanical Data Sheets For Glycol Drain Pump | BK-GCS-PEDCO-120-ME-DT-0035 | BK-GCS-PEDCO-120-ME-DT-0035Mechanical Data Sheets For Glycol Drain Pump | 2021-12-08 | 2022-12-20
Mechanical Data Sheets For Glycol Sump Drum | BK-GCS-PEDCO-120-ME-DT-0036 | BK-GCS-PEDCO-120-ME-DT-0036Mechanical Data Sheets For Glycol Sump Drum | 2022-01-05 | 2022-12-20
HVAC Calculation Note For Control Building | BK-GCS-PEDCO-120-HV-CN-0001 | BK-GCS-PEDCO-120-HV-CN-0001HVAC Calculation Note For Control Building | 2022-03-30 | 2022-12-20
HVAC Calculation Note For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-CN-0002 | BK-GCS-PEDCO-120-HV-CN-0002HVAC Calculation Note For Extension of Existing Elect. Building | 2022-06-06 | 2022-12-20
Data Sheets For Main HVAC Equipment of Control Building | BK-GCS-PEDCO-120-HV-DT-0001 | BK-GCS-PEDCO-120-HV-DT-0001Data Sheets For Main HVAC Equipment of Control Building | 0 | 0
Data Sheets For Main HVAC Equipment of Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-DT-0002 | BK-GCS-PEDCO-120-HV-DT-0002Data Sheets For Main HVAC Equipment of Extension of Existing Elect. Building | 0 | 0
Plumbing & Sewage Piping Layout For Control Building | BK-GCS-PEDCO-120-HV-PY-0001 | BK-GCS-PEDCO-120-HV-PY-0001Plumbing & Sewage Piping Layout For Control Building | 2022-06-07 | 2022-12-20
HVAC Flow Diagram For Control Building | BK-GCS-PEDCO-120-HV-DG-0001 | BK-GCS-PEDCO-120-HV-DG-0001HVAC Flow Diagram For Control Building | 2022-06-11 | 2022-12-20
HVAC Room Layout & Section For Control Building | BK-GCS-PEDCO-120-HV-PY-0002 | BK-GCS-PEDCO-120-HV-PY-0002HVAC Room Layout & Section For Control Building | 0 | 0
HVAC System Duct Plan For Control Building | BK-GCS-PEDCO-120-HV-PY-0003 | BK-GCS-PEDCO-120-HV-PY-0003HVAC System Duct Plan For Control Building | 2022-07-20 | 2022-12-20
HVAC System Roof Layout For Control Building | BK-GCS-PEDCO-120-HV-PY-0004 | BK-GCS-PEDCO-120-HV-PY-0004HVAC System Roof Layout For Control Building | 2022-10-23 | 0
HVAC I&C Diagram For Control Building | BK-GCS-PEDCO-120-HV-DG-0002 | BK-GCS-PEDCO-120-HV-DG-0002HVAC I&C Diagram For Control Building | 2022-07-20 | 2022-12-20
Plumbing & Sewage Piping Layout For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0005 | BK-GCS-PEDCO-120-HV-PY-0005Plumbing & Sewage Piping Layout For Extension of Existing Elect. Building | 0 | 0
HVAC Flow Diagram For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-DG-0003 | BK-GCS-PEDCO-120-HV-DG-0003HVAC Flow Diagram For Extension of Existing Elect. Building | 0 | 2022-12-20
HVAC System Layout & Section For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0006 | BK-GCS-PEDCO-120-HV-PY-0006HVAC System Layout & Section For Extension of Existing Elect. Building | 0 | 2022-12-20
HVAC System Duct Plan For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0007 | BK-GCS-PEDCO-120-HV-PY-0007HVAC System Duct Plan For Extension of Existing Elect. Building | 0 | 0
HVAC System Roof Layout For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0008 | BK-GCS-PEDCO-120-HV-PY-0008HVAC System Roof Layout For Extension of Existing Elect. Building | 0 | 0
HVAC I&C Diagram For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-DG-0004 | BK-GCS-PEDCO-120-HV-DG-0004HVAC I&C Diagram For Extension of Existing Elect. Building | 2022-06-11 | 2022-12-20
MTO For HVAC & Plumbing For Control Building | BK-GCS-PEDCO-120-HV-MT-0001 | BK-GCS-PEDCO-120-HV-MT-0001MTO For HVAC & Plumbing For Control Building | 0 | 0
MTO For HVAC & Plumbing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-MT-0002 | BK-GCS-PEDCO-120-HV-MT-0002MTO For HVAC & Plumbing For Extension of Existing Elect. Building | 0 | 0
Piping Material Specification | BK-GCS-PEDCO-120-PI-SP-0001 | BK-GCS-PEDCO-120-PI-SP-0001Piping Material Specification | 2021-12-06 | 2022-12-20
Data Sheets For Strainers | BK-GCS-PEDCO-120-PI-DT-0001 | BK-GCS-PEDCO-120-PI-DT-0001Data Sheets For Strainers | 2022-06-18 | 2022-12-20
Data Sheets For Manual valves | BK-GCS-PEDCO-120-PI-DT-0002 | BK-GCS-PEDCO-120-PI-DT-0002Data Sheets For Manual valves | 2022-07-19 | 2022-12-20
Data Sheets and MTO For Piping Special Items | BK-GCS-PEDCO-120-PI-DT-0003 | BK-GCS-PEDCO-120-PI-DT-0003Data Sheets and MTO For Piping Special Items | 2022-06-28 | 2022-12-20
Data Sheets For Special Pipe Supports | BK-GCS-PEDCO-120-PI-DT-0004 | BK-GCS-PEDCO-120-PI-DT-0004Data Sheets For Special Pipe Supports | 0 | 0
Data Sheets For Piping Insulation Joints | BK-GCS-PEDCO-120-PI-DT-0005 | BK-GCS-PEDCO-120-PI-DT-0005Data Sheets For Piping Insulation Joints | 2022-06-06 | 2022-12-20
Data Sheets For Expansion Joints | BK-GCS-PEDCO-120-PI-DT-0006 | BK-GCS-PEDCO-120-PI-DT-0006Data Sheets For Expansion Joints | 0 | 0
Unit Plot Plan Drawing | BK-GCS-PEDCO-120-PI-PY-0001 | BK-GCS-PEDCO-120-PI-PY-0001Unit Plot Plan Drawing | 2021-09-12 | 2022-12-20
Standard Pipe Support Drawings | BK-GCS-PEDCO-120-PI-DW-0001 | BK-GCS-PEDCO-120-PI-DW-0001Standard Pipe Support Drawings | 2022-06-11 | 2022-12-20
Piping Assembly Drawing | BK-GCS-PEDCO-120-PI-DW-0002 | BK-GCS-PEDCO-120-PI-DW-0002Piping Assembly Drawing | 0 | 0
Piping Key Plan | BK-GCS-PEDCO-120-PI-DW-0003 | BK-GCS-PEDCO-120-PI-DW-0003Piping Key Plan | 2022-06-14 | 2022-12-20
A/G Piping Plan | BK-GCS-PEDCO-120-PI-DW-0004 | BK-GCS-PEDCO-120-PI-DW-0004A/G Piping Plan | 0 | 2022-12-20
U/G Piping Plan | BK-GCS-PEDCO-120-PI-DW-0005 | BK-GCS-PEDCO-120-PI-DW-0005U/G Piping Plan | 2022-07-02 | 2022-12-20
A/G Piping Isometric | BK-GCS-PEDCO-120-PI-DW-0006 | BK-GCS-PEDCO-120-PI-DW-0006A/G Piping Isometric | 0 | 0
U/G Piping Isometric | BK-GCS-PEDCO-120-PI-DW-0007 | BK-GCS-PEDCO-120-PI-DW-0007U/G Piping Isometric | 0 | 0
Overall Plot Plan Drawing | BK-GCS-PEDCO-120-PI-DW-0008 | BK-GCS-PEDCO-120-PI-DW-0008Overall Plot Plan Drawing | 0 | 0
Special Pipe Support Drawings | BK-GCS-PEDCO-120-PI-DW-0009 | BK-GCS-PEDCO-120-PI-DW-0009Special Pipe Support Drawings | 0 | 0
Material flow Diagram | BK-GCS-PEDCO-120-PI-DG-0001 | BK-GCS-PEDCO-120-PI-DG-0001Material flow Diagram | 2022-05-11 | 2022-12-20
Piping Hydrostatic Test Diagram - GCS | BK-GCS-PEDCO-120-PI-DW-0010 | BK-GCS-PEDCO-120-PI-DW-0010Piping Hydrostatic Test Diagram - GCS | 0 | 0
Critical Line List | BK-GCS-PEDCO-120-PI-LI-0001 | BK-GCS-PEDCO-120-PI-LI-0001Critical Line List | 2022-05-28 | 2022-12-20
Pipe Support List | BK-GCS-PEDCO-120-PI-LI-0002 | BK-GCS-PEDCO-120-PI-LI-0002Pipe Support List | 0 | 0
Piping Tie-In Schedule List | BK-GCS-PEDCO-120-PI-LI-0003 | BK-GCS-PEDCO-120-PI-LI-0003Piping Tie-In Schedule List | 2022-08-22 | 2022-12-20
Piping Corrosion Study & Material Selection Report | BK-GCS-PEDCO-120-PI-RT-0001 | BK-GCS-PEDCO-120-PI-RT-0001Piping Corrosion Study & Material Selection Report | 2021-12-06 | 2022-12-20
Stress Analysis Calculations Report | BK-GCS-PEDCO-120-PI-RT-0002 | BK-GCS-PEDCO-120-PI-RT-0002Stress Analysis Calculations Report | 0 | 0
PDMS Model Review Report (30%) | BK-GCS-PEDCO-120-PI-RT-0003 | BK-GCS-PEDCO-120-PI-RT-0003PDMS Model Review Report (30%) | 2022-03-26 | 2022-12-20
PDMS Model Review Report (60%) | BK-GCS-PEDCO-120-PI-RT-0004 | BK-GCS-PEDCO-120-PI-RT-0004PDMS Model Review Report (60%) | 2022-06-22 | 2022-12-20
PDMS Model Review Report (90%) | BK-GCS-PEDCO-120-PI-RT-0005 | BK-GCS-PEDCO-120-PI-RT-0005PDMS Model Review Report (90%) | 0 | 0
Wall Thickness Calculation Report | BK-GCS-PEDCO-120-PI-RT-0006 | BK-GCS-PEDCO-120-PI-RT-0006Wall Thickness Calculation Report | 2021-12-06 | 2022-12-20
MTO For Pipes | BK-GCS-PEDCO-120-PI-MT-0001 | BK-GCS-PEDCO-120-PI-MT-0001MTO For Pipes | 2022-06-27 | 2022-12-20
MTO For Fittings | BK-GCS-PEDCO-120-PI-MT-0002 | BK-GCS-PEDCO-120-PI-MT-0002MTO For Fittings | 2022-10-11 | 0
MTO For Flanges | BK-GCS-PEDCO-120-PI-MT-0003 | BK-GCS-PEDCO-120-PI-MT-0003MTO For Flanges | 2022-10-11 | 0
MTO For Manual Valves | BK-GCS-PEDCO-120-PI-MT-0004 | BK-GCS-PEDCO-120-PI-MT-0004MTO For Manual Valves | 2022-10-12 | 0
MTO For Gaskets | BK-GCS-PEDCO-120-PI-MT-0005 | BK-GCS-PEDCO-120-PI-MT-0005MTO For Gaskets | 2022-06-27 | 2022-12-20
MTO For Bolt & Nuts | BK-GCS-PEDCO-120-PI-MT-0006 | BK-GCS-PEDCO-120-PI-MT-0006MTO For Bolt & Nuts | 0 | 0
MTO For Insulation | BK-GCS-PEDCO-120-PI-MT-0008 | BK-GCS-PEDCO-120-PI-MT-0008MTO For Insulation | 2022-08-03 | 0
MTO For Painting | BK-GCS-PEDCO-120-PI-MT-0009 | BK-GCS-PEDCO-120-PI-MT-0009MTO For Painting | 0 | 0
MTO For Coating of Underground Piping | BK-GCS-PEDCO-120-PI-MT-0010 | BK-GCS-PEDCO-120-PI-MT-0010MTO For Coating of Underground Piping | 0 | 0
Instrument & Control System Basis of Design | BK-GCS-PEDCO-120-IN-DB-0001 | BK-GCS-PEDCO-120-IN-DB-0001Instrument & Control System Basis of Design | 2021-08-22 | 2022-12-20
Fire & Gas Detection Design Criteria | BK-GCS-PEDCO-120-IN-DC-0001 | BK-GCS-PEDCO-120-IN-DC-0001Fire & Gas Detection Design Criteria | 2021-08-30 | 2022-12-20
Instrument & Control System Design Criteria | BK-GCS-PEDCO-120-IN-DC-0002 | BK-GCS-PEDCO-120-IN-DC-0002Instrument & Control System Design Criteria | 2022-01-03 | 2022-12-20
Data Sheets For Pressure & Diff. Pressure Gauge | BK-GCS-PEDCO-120-IN-DT-0001 | BK-GCS-PEDCO-120-IN-DT-0001Data Sheets For Pressure & Diff. Pressure Gauge | 2022-03-27 | 2022-12-20
Data Sheets For Temperature Gauge | BK-GCS-PEDCO-120-IN-DT-0002 | BK-GCS-PEDCO-120-IN-DT-0002Data Sheets For Temperature Gauge | 2022-03-27 | 2022-12-20
Data Sheets For Level Gauges | BK-GCS-PEDCO-120-IN-DT-0003 | BK-GCS-PEDCO-120-IN-DT-0003Data Sheets For Level Gauges | 2022-04-05 | 2022-12-20
Data Sheets For Pressure/Diff. Pressure Transmitter | BK-GCS-PEDCO-120-IN-DT-0004 | BK-GCS-PEDCO-120-IN-DT-0004Data Sheets For Pressure/Diff. Pressure Transmitter | 2022-04-10 | 2022-12-20
Data Sheets For Temperature Transmitter/Switch | BK-GCS-PEDCO-120-IN-DT-0005 | BK-GCS-PEDCO-120-IN-DT-0005Data Sheets For Temperature Transmitter/Switch | 2022-03-27 | 2022-12-20
Data Sheets For Displacer Level Transmitter | BK-GCS-PEDCO-120-IN-DT-0006 | BK-GCS-PEDCO-120-IN-DT-0006Data Sheets For Displacer Level Transmitter | 2022-04-05 | 2022-12-20
Data Sheets For Pressure/ Differential Pressure Switch | BK-GCS-PEDCO-120-IN-DT-0007 | BK-GCS-PEDCO-120-IN-DT-0007Data Sheets For Pressure/ Differential Pressure Switch | 0 | 0
Data Sheets For Level Switch | BK-GCS-PEDCO-120-IN-DT-0008 | BK-GCS-PEDCO-120-IN-DT-0008Data Sheets For Level Switch | 2022-04-10 | 2022-12-20
Data Sheets For Pressure & Safety Relief Valves | BK-GCS-PEDCO-120-IN-DT-0009 | BK-GCS-PEDCO-120-IN-DT-0009Data Sheets For Pressure & Safety Relief Valves | 2022-05-17 | 2022-12-20
Data Sheets For ON/OFF & Shutdown Valves | BK-GCS-PEDCO-120-IN-DT-0010 | BK-GCS-PEDCO-120-IN-DT-0010Data Sheets For ON/OFF & Shutdown Valves | 2022-05-08 | 2022-12-20
Data Sheets For Control/Regulator Valves | BK-GCS-PEDCO-120-IN-DT-0011 | BK-GCS-PEDCO-120-IN-DT-0011Data Sheets For Control/Regulator Valves | 2022-06-25 | 2022-12-20
Data Sheets For Diff. Pressure Flow Transmitter | BK-GCS-PEDCO-120-IN-DT-0012 | BK-GCS-PEDCO-120-IN-DT-0012Data Sheets For Diff. Pressure Flow Transmitter | 2022-04-05 | 2022-12-20
Data Sheets For Orifice Plate/Restriction Orifice | BK-GCS-PEDCO-120-IN-DT-0013 | BK-GCS-PEDCO-120-IN-DT-0013Data Sheets For Orifice Plate/Restriction Orifice | 2022-07-23 | 2022-12-20
Data Sheets For Corrosion Coupon/ Probe | BK-GCS-PEDCO-120-IN-DT-0014 | BK-GCS-PEDCO-120-IN-DT-0014Data Sheets For Corrosion Coupon/ Probe | 2022-03-27 | 2022-12-20
Data Sheets For F&G Detectors & Equipment | BK-GCS-PEDCO-120-IN-DT-0016 | BK-GCS-PEDCO-120-IN-DT-0016Data Sheets For F&G Detectors & Equipment | 2022-05-09 | 2022-12-20
Data Sheets For ESD Console/F&G Matrix Panel | BK-GCS-PEDCO-120-IN-DT-0017 | BK-GCS-PEDCO-120-IN-DT-0017Data Sheets For ESD Console/F&G Matrix Panel | #REF! | 2022-12-20
Data Sheets For Rotameter | BK-GCS-PEDCO-120-IN-DT-0018 | BK-GCS-PEDCO-120-IN-DT-0018Data Sheets For Rotameter | 2022-04-05 | 2022-12-20
Data Sheets For Diff. Pressure Type Level Transmitter | BK-GCS-PEDCO-120-IN-DT-0019 | BK-GCS-PEDCO-120-IN-DT-0019Data Sheets For Diff. Pressure Type Level Transmitter | 2022-04-05 | 2022-12-20
Data Sheets For CCTV | BK-GCS-PEDCO-120-IN-DT-0020 | BK-GCS-PEDCO-120-IN-DT-0020Data Sheets For CCTV | 2021-10-13 | 2022-12-20
Data Sheets For IRP Panel | BK-GCS-PEDCO-120-IN-DT-0021 | BK-GCS-PEDCO-120-IN-DT-0021Data Sheets For IRP Panel | 2022-06-13 | 2022-12-20
Typical Instrument Installation Drawing | BK-GCS-PEDCO-120-IN-DW-0001 | BK-GCS-PEDCO-120-IN-DW-0001Typical Instrument Installation Drawing | 2022-03-09 | 2022-12-20
Control/ESD/F&G System Block Diagram Configuration | BK-GCS-PEDCO-120-IN-BD-0001 | BK-GCS-PEDCO-120-IN-BD-0001Control/ESD/F&G System Block Diagram Configuration | 2021-08-30 | 2022-12-20
Instrument Earthing Typical Diagram | BK-GCS-PEDCO-120-IN-DG-0001 | BK-GCS-PEDCO-120-IN-DG-0001Instrument Earthing Typical Diagram | 2021-12-29 | 0
Instrument Hook-up Diagram | BK-GCS-PEDCO-120-IN-DG-0002 | BK-GCS-PEDCO-120-IN-DG-0002Instrument Hook-up Diagram | 2022-03-02 | 2022-12-20
ESD Level Hierarchy | BK-GCS-PEDCO-120-IN-DG-0003 | BK-GCS-PEDCO-120-IN-DG-0003ESD Level Hierarchy | 2022-05-28 | 2022-12-20
ESD System Loop Diagram | BK-GCS-PEDCO-120-IN-DG-0004 | BK-GCS-PEDCO-120-IN-DG-0004ESD System Loop Diagram | 2022-06-06 | 2022-12-20
Control System Loop Diagram | BK-GCS-PEDCO-120-IN-DG-0005 | BK-GCS-PEDCO-120-IN-DG-0005Control System Loop Diagram | 2022-06-15 | 2022-12-20
F&G System Loop Diagram | BK-GCS-PEDCO-120-IN-DG-0006 | BK-GCS-PEDCO-120-IN-DG-0006F&G System Loop Diagram | 2022-07-02 | 2022-12-20
Instrument Air Piping and Air Header Diagram | BK-GCS-PEDCO-120-IN-DG-0007 | BK-GCS-PEDCO-120-IN-DG-0007Instrument Air Piping and Air Header Diagram | 0 | 0
Instrument & F&G Junction Box Termination Diagram | BK-GCS-PEDCO-120-IN-DG-0008 | BK-GCS-PEDCO-120-IN-DG-0008Instrument & F&G Junction Box Termination Diagram | 2022-02-13 | 2022-12-20
F&G Cause and Effect Diagram For Process Area | BK-GCS-PEDCO-120-IN-DG-0009 | BK-GCS-PEDCO-120-IN-DG-0009F&G Cause and Effect Diagram For Process Area | 2022-05-30 | 2022-12-20
F&G Cause and Effect Diagram For Buildings | BK-GCS-PEDCO-120-IN-DG-0010 | BK-GCS-PEDCO-120-IN-DG-0010F&G Cause and Effect Diagram For Buildings | 2022-06-14 | 2022-12-20
Control System Logic Diagram | BK-GCS-PEDCO-120-IN-LD-0001 | BK-GCS-PEDCO-120-IN-LD-0001Control System Logic Diagram | 2022-07-23 | 2022-12-20
ESD Logic Diagram | BK-GCS-PEDCO-120-IN-LD-0002 | BK-GCS-PEDCO-120-IN-LD-0002ESD Logic Diagram | 2022-06-12 | 2022-12-20
Control Room Layout & Arrangement Drawing | BK-GCS-PEDCO-120-IN-PY-0001 | BK-GCS-PEDCO-120-IN-PY-0001Control Room Layout & Arrangement Drawing | 2022-02-02 | 2022-12-20
Control Room Cable Route Layout | BK-GCS-PEDCO-120-IN-PY-0002 | BK-GCS-PEDCO-120-IN-PY-0002Control Room Cable Route Layout | 2022-05-23 | 2022-12-20
Instrument Location Layout | BK-GCS-PEDCO-120-IN-PY-0003 | BK-GCS-PEDCO-120-IN-PY-0003Instrument Location Layout | 2022-08-23 | 2022-12-20
Instrument/F&G Cable Trench/Route Layout Drawing | BK-GCS-PEDCO-120-IN-PY-0004 | BK-GCS-PEDCO-120-IN-PY-0004Instrument/F&G Cable Trench/Route Layout Drawing | 2022-01-25 | 2022-12-20
F&G Location Layout For Process Area | BK-GCS-PEDCO-120-IN-PY-0005 | BK-GCS-PEDCO-120-IN-PY-0005F&G Location Layout For Process Area | 2022-02-07 | 2022-12-20
F&G Location Layout For Buildings | BK-GCS-PEDCO-120-IN-PY-0006 | BK-GCS-PEDCO-120-IN-PY-0006F&G Location Layout For Buildings | 2022-04-18 | 2022-12-20
Block Diagram For CCTV | BK-GCS-PEDCO-120-IN-BD-0002 | BK-GCS-PEDCO-120-IN-BD-0002Block Diagram For CCTV | 2022-06-27 | 2022-12-20
Block Diagram For CCTV in Binak DU | BK-GCS-PEDCO-120-IN-BD-0003 | BK-GCS-PEDCO-120-IN-BD-0003Block Diagram For CCTV in Binak DU | 0 | 0
CCTV Equipment Layout for GCS Area | BK-GCS-PEDCO-120-IN-PY-0007 | BK-GCS-PEDCO-120-IN-PY-0007 CCTV Equipment Layout for GCS Area | 2022-04-09 | 2022-12-20
CCTV Equipment Layout For Desalting Unit Area | BK-GCS-PEDCO-120-IN-PY-0008 | BK-GCS-PEDCO-120-IN-PY-0008CCTV Equipment Layout For Desalting Unit Area | 0 | 0
Wiring Diagram For Interposing Relay Panel (IRP) | BK-GCS-PEDCO-120-EL-DG-0011 | BK-GCS-PEDCO-120-EL-DG-0011Wiring Diagram For Interposing Relay Panel (IRP) | 2022-06-20 | 2022-12-20
Instrument Index | BK-GCS-PEDCO-120-IN-LI-0001 | BK-GCS-PEDCO-120-IN-LI-0001Instrument Index | 2022-04-27 | 2022-12-20
I/O List For Control System | BK-GCS-PEDCO-120-IN-LI-0002 | BK-GCS-PEDCO-120-IN-LI-0002I/O List For Control System | 2022-01-25 | 2022-12-20
I/O List For ESD Systems | BK-GCS-PEDCO-120-IN-LI-0003 | BK-GCS-PEDCO-120-IN-LI-0003I/O List For ESD Systems | 2022-01-25 | 2022-12-20
I/O List For F&G Systems | BK-GCS-PEDCO-120-IN-LI-0004 | BK-GCS-PEDCO-120-IN-LI-0004I/O List For F&G Systems | 2022-02-07 | 2022-12-20
Panels & Junction Box List | BK-GCS-PEDCO-120-IN-LI-0005 | BK-GCS-PEDCO-120-IN-LI-0005Panels & Junction Box List | 2022-02-13 | 2022-12-20
Set Point & Alarm List | BK-GCS-PEDCO-120-IN-LI-0006 | BK-GCS-PEDCO-120-IN-LI-0006Set Point & Alarm List | 2022-05-09 | 2022-12-20
I&C Power Consumption Summary | BK-GCS-PEDCO-120-IN-LI-0007 | BK-GCS-PEDCO-120-IN-LI-0007I&C Power Consumption Summary | 2022-02-23 | 2022-12-20
F&G Detector List | BK-GCS-PEDCO-120-IN-LI-0008 | BK-GCS-PEDCO-120-IN-LI-0008F&G Detector List | 2022-02-07 | 2022-12-20
Instrument /F&G Cable List | BK-GCS-PEDCO-120-IN-LI-0009 | BK-GCS-PEDCO-120-IN-LI-0009Instrument /F&G Cable List | 2022-02-13 | 2022-12-20
Cable Schedule For CCTV | BK-GCS-PEDCO-120-IN-LI-0010 | BK-GCS-PEDCO-120-IN-LI-0010Cable Schedule For CCTV | 2022-06-27 | 2022-12-20
Cable Schedule For CCTV in Binak DU Area | BK-GCS-PEDCO-120-IN-LI-0011 | BK-GCS-PEDCO-120-IN-LI-0011Cable Schedule For CCTV in Binak DU Area | 0 | 0
MTO for Bulk Item and Installation Accessories | BK-GCS-PEDCO-120-IN-MT-0001 | BK-GCS-PEDCO-120-IN-MT-0001MTO for Bulk Item and Installation Accessories | 2022-06-28 | 2022-12-20
MTO For Instrument/F&G Cable | BK-GCS-PEDCO-120-IN-MT-0002 | BK-GCS-PEDCO-120-IN-MT-0002MTO For Instrument/F&G Cable | 0 | 0
MTO For Instrument/F&G Junction box and Gland | BK-GCS-PEDCO-120-IN-MT-0003 | BK-GCS-PEDCO-120-IN-MT-0003MTO For Instrument/F&G Junction box and Gland | 2022-06-28 | 2022-12-20
MTO For Instrument Tube and Fitting | BK-GCS-PEDCO-120-IN-MT-0004 | BK-GCS-PEDCO-120-IN-MT-0004MTO For Instrument Tube and Fitting | 0 | 0
MTO For Instrument Cable Tray/Ladder | BK-GCS-PEDCO-120-IN-MT-0005 | BK-GCS-PEDCO-120-IN-MT-0005MTO For Instrument Cable Tray/Ladder | 2022-07-31 | 0
MTO For CCTV | BK-GCS-PEDCO-120-IN-MT-0006 | BK-GCS-PEDCO-120-IN-MT-0006MTO For CCTV | 2021-12-12 | 0
MTO For CCTV in Binak DU Area | BK-GCS-PEDCO-120-IN-MT-0007 | BK-GCS-PEDCO-120-IN-MT-0007MTO For CCTV in Binak DU Area | 2021-12-13 | 0
Active Fire Protection and Safety Concept | BK-GCS-PEDCO-120-SA-DB-0001 | BK-GCS-PEDCO-120-SA-DB-0001Active Fire Protection and Safety Concept | 2021-09-14 | 2022-12-20
Calculation Note For Total Flooding Demand For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-SA-CN-0001 | BK-GCS-PEDCO-120-SA-CN-0001Calculation Note For Total Flooding Demand For Extension of Existing Elect. Building | 2022-01-16 | 2022-03-09
Calculation Note For Fire Water Demand | BK-GCS-PEDCO-120-SA-CN-0002 | BK-GCS-PEDCO-120-SA-CN-0002Calculation Note For Fire Water Demand | 2021-12-13 | 2022-12-20
Fire Water Hydraulic Calculation Note | BK-GCS-PEDCO-120-SA-CN-0003 | BK-GCS-PEDCO-120-SA-CN-0003Fire Water Hydraulic Calculation Note | 2022-05-22 | 2022-12-20
Data Sheets For Safety Equipment | BK-GCS-PEDCO-120-SA-DT-0002 | BK-GCS-PEDCO-120-SA-DT-0002Data Sheets For Safety Equipment | 2022-04-19 | 2022-12-20
Data Sheets For Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-DT-0003 | BK-GCS-PEDCO-120-SA-DT-0003Data Sheets For Fire Fighting Equipment | 2022-04-18 | 2022-12-20
Data Sheets For Deluge valves | BK-GCS-PEDCO-120-SA-DT-0004 | BK-GCS-PEDCO-120-SA-DT-0004Data Sheets For Deluge valves | 2022-01-16 | 2022-12-20
Data Sheets For Water Spray Nozzles | BK-GCS-PEDCO-120-SA-DT-0005 | BK-GCS-PEDCO-120-SA-DT-0005Data Sheets For Water Spray Nozzles | 2022-05-22 | 2022-12-20
Data Sheets For Safety Sign | BK-GCS-PEDCO-120-SA-DT-0006 | BK-GCS-PEDCO-120-SA-DT-0006Data Sheets For Safety Sign | 2021-09-20 | 2022-12-20
PFD - Fire Water System | BK-GCS-PEDCO-120-SA-PF-0001 | BK-GCS-PEDCO-120-SA-PF-0001PFD - Fire Water System | 2021-12-13 | 2022-12-20
P&ID - Fire Water Network | BK-GCS-PEDCO-120-SA-PI-0001 | BK-GCS-PEDCO-120-SA-PI-0001P&ID - Fire Water Network | 2022-02-12 | 2022-12-20
P&ID - Total Flooding System For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-SA-PI-0002 | BK-GCS-PEDCO-120-SA-PI-0002P&ID - Total Flooding System For Extension of Existing Elect. Building | 2022-01-16 | 2022-12-20
Fire Water Network Layout | BK-GCS-PEDCO-120-SA-PY-0001 | BK-GCS-PEDCO-120-SA-PY-0001Fire Water Network Layout | 2021-12-13 | 2022-12-20
Hazardous Area Classification Layout | BK-GCS-PEDCO-120-SA-PY-0002 | BK-GCS-PEDCO-120-SA-PY-0002Hazardous Area Classification Layout | 2022-03-12 | 2022-12-20
Fire Proofing Zone Layout | BK-GCS-PEDCO-120-SA-PY-0003 | BK-GCS-PEDCO-120-SA-PY-0003Fire Proofing Zone Layout | 2022-05-22 | 2022-12-20
Safety & Fire Fighting Equipment Location Layout | BK-GCS-PEDCO-120-SA-PY-0004 | BK-GCS-PEDCO-120-SA-PY-0004Safety & Fire Fighting Equipment Location Layout | 2022-02-12 | 2022-12-20
Escape Route & Safety Sign Layout | BK-GCS-PEDCO-120-SA-PY-0005 | BK-GCS-PEDCO-120-SA-PY-0005Escape Route & Safety Sign Layout | 2022-05-10 | 2022-12-20
Hazard Source List | BK-GCS-PEDCO-120-SA-LI-0001 | BK-GCS-PEDCO-120-SA-LI-0001Hazard Source List | 2022-02-23 | 2022-12-20
Fire Fighting Line List | BK-GCS-PEDCO-120-SA-LI-0002 | BK-GCS-PEDCO-120-SA-LI-0002Fire Fighting Line List | 0 | 0
Consequence Modeling Report | BK-GCS-PEDCO-120-SA-RT-0003 | BK-GCS-PEDCO-120-SA-RT-0003Consequence Modeling Report | 2021-11-21 | 2022-12-20
MTO For Safety & Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-MT-0001 | BK-GCS-PEDCO-120-SA-MT-0001MTO For Safety & Fire Fighting Equipment | 2022-05-22 | 2022-12-20
MTO For Safety Sign | BK-GCS-PEDCO-120-SA-MT-0002 | BK-GCS-PEDCO-120-SA-MT-0002MTO For Safety Sign | 2022-05-15 | 2022-12-20
Calculation Note For Outdoor Area Lighting System | BK-GCS-PEDCO-120-EL-CN-0001 | BK-GCS-PEDCO-120-EL-CN-0001Calculation Note For Outdoor Area Lighting System | 2022-06-22 | 2022-12-20
Calculation Note For Indoor Area Lighting System | BK-GCS-PEDCO-120-EL-CN-0002 | BK-GCS-PEDCO-120-EL-CN-0002Calculation Note For Indoor Area Lighting System | 2022-04-27 | 2022-12-20
Calculation Note For Cable Sizing | BK-GCS-PEDCO-120-EL-CN-0003 | BK-GCS-PEDCO-120-EL-CN-0003Calculation Note For Cable Sizing | 2022-06-06 | 2022-12-20
Calculation Note For UPS System | BK-GCS-PEDCO-120-EL-CN-0004 | BK-GCS-PEDCO-120-EL-CN-0004Calculation Note For UPS System | 2021-11-22 | 2022-12-20
Calculation Note For DC Charger System | BK-GCS-PEDCO-120-EL-CN-0005 | BK-GCS-PEDCO-120-EL-CN-0005Calculation Note For DC Charger System | 2021-12-15 | 2022-12-20
Calculation Note For Earthing & Lightning System | BK-GCS-PEDCO-120-EL-CN-0006 | BK-GCS-PEDCO-120-EL-CN-0006Calculation Note For Earthing & Lightning System | 2022-04-30 | 2022-12-20
Calculation Note For Diesel Generator Sizing | BK-GCS-PEDCO-120-EL-CN-0007 | BK-GCS-PEDCO-120-EL-CN-0007Calculation Note For Diesel Generator Sizing | 2021-11-16 | 2022-12-20
Calculation Note For Cathodic Protection System | BK-GCS-PEDCO-120-EL-CN-0008 | BK-GCS-PEDCO-120-EL-CN-0008Calculation Note For Cathodic Protection System | 2022-05-01 | 2022-12-20
Calculation Note For NGR Sizing | BK-GCS-PEDCO-120-EL-CN-0009 | BK-GCS-PEDCO-120-EL-CN-0009Calculation Note For NGR Sizing | 2022-04-11 | 2022-12-20
Calculation Note for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-CN-0010 | BK-GCS-PEDCO-120-EL-CN-0010Calculation Note for UPS of CCTV in Desalting, Production & CS Unit | 0 | 0
Calculation Note for Capacitor Banks | BK-GCS-PEDCO-120-EL-CN-0011 | BK-GCS-PEDCO-120-EL-CN-0011Calculation Note for Capacitor Banks | 2021-11-22 | 2022-12-20
Data Sheets For UPS | BK-GCS-PEDCO-120-EL-DT-0001 | BK-GCS-PEDCO-120-EL-DT-0001Data Sheets For UPS | 2021-12-26 | 2022-12-20
Data Sheets For DC Charger | BK-GCS-PEDCO-120-EL-DT-0002 | BK-GCS-PEDCO-120-EL-DT-0002Data Sheets For DC Charger | 2021-12-19 | 2022-12-20
Data Sheets For Diesel Generator | BK-GCS-PEDCO-120-EL-DT-0003 | BK-GCS-PEDCO-120-EL-DT-0003Data Sheets For Diesel Generator | 2022-05-31 | 2022-12-20
Data Sheets For Expansion of MV Switchgear | BK-GCS-PEDCO-120-EL-DT-0004 | BK-GCS-PEDCO-120-EL-DT-0004Data Sheets For Expansion of MV Switchgear | 2022-01-22 | 2022-12-20
Data Sheets For LV Switchgear | BK-GCS-PEDCO-120-EL-DT-0005 | BK-GCS-PEDCO-120-EL-DT-0005Data Sheets For LV Switchgear | 2022-02-19 | 2022-12-20
Data Sheets For Local Control Stations (LCS) | BK-GCS-PEDCO-120-EL-DT-0006 | BK-GCS-PEDCO-120-EL-DT-0006Data Sheets For Local Control Stations (LCS) | 2022-02-06 | 2022-07-05
Data Sheets For Capacitor Bank | BK-GCS-PEDCO-120-EL-DT-0007 | BK-GCS-PEDCO-120-EL-DT-0007Data Sheets For Capacitor Bank | 2022-02-27 | 2022-12-20
Data Sheets For LV Induction Motors | BK-GCS-PEDCO-120-EL-DT-0008 | BK-GCS-PEDCO-120-EL-DT-0008Data Sheets For LV Induction Motors | 2021-09-12 | 2022-12-20
Data Sheets For MV Induction Motors | BK-GCS-PEDCO-120-EL-DT-0009 | BK-GCS-PEDCO-120-EL-DT-0009Data Sheets For MV Induction Motors | 2021-09-12 | 2022-12-20
Data Sheets For Power & Control Cables | BK-GCS-PEDCO-120-EL-DT-0010 | BK-GCS-PEDCO-120-EL-DT-0010Data Sheets For Power & Control Cables | 2022-02-19 | 2022-12-20
Data Sheets For Power Transformers | BK-GCS-PEDCO-120-EL-DT-0011 | BK-GCS-PEDCO-120-EL-DT-0011Data Sheets For Power Transformers | 2022-02-02 | 2022-12-20
Data Sheets For Cathodic Protection System | BK-GCS-PEDCO-120-EL-DT-0012 | BK-GCS-PEDCO-120-EL-DT-0012Data Sheets For Cathodic Protection System | 0 | 0
Data Sheets For NGR | BK-GCS-PEDCO-120-EL-DT-0013 | BK-GCS-PEDCO-120-EL-DT-0013Data Sheets For NGR | 2022-04-11 | 2022-07-05
Data Sheets For Remote Control Panel | BK-GCS-PEDCO-120-EL-DT-0015 | BK-GCS-PEDCO-120-EL-DT-0015Data Sheets For Remote Control Panel | 2022-06-01 | 2022-12-20
Data Sheets For Distribution & Lighting Panels | BK-GCS-PEDCO-120-EL-DT-0016 | BK-GCS-PEDCO-120-EL-DT-0016Data Sheets For Distribution & Lighting Panels | 2022-05-17 | 2022-12-20
Data Sheet for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-DT-0017 | BK-GCS-PEDCO-120-EL-DT-0017Data Sheet for UPS of CCTV in Desalting, Production & CS Unit | 2022-03-02 | 2022-12-20
Electrical Overall Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0001 | BK-GCS-PEDCO-120-EL-SL-0001Electrical Overall Single Line Diagram | 2022-01-24 | 2022-12-20
LV Switchgear/MCC Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0002 | BK-GCS-PEDCO-120-EL-SL-0002LV Switchgear/MCC Single Line Diagram | 2021-12-27 | 2022-12-20
Existent MV Switchgear Expansion Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0003 | BK-GCS-PEDCO-120-EL-SL-0003Existent MV Switchgear Expansion Single Line Diagram | 2022-01-12 | 2022-12-20
Distribution and Lighting Panels Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0004 | BK-GCS-PEDCO-120-EL-SL-0004Distribution and Lighting Panels Single Line Diagram | 0 | 0
UPS Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0005 | BK-GCS-PEDCO-120-EL-SL-0005UPS Single Line Diagram | 2021-12-26 | 2022-12-20
DC Charger Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0006 | BK-GCS-PEDCO-120-EL-SL-0006DC Charger Single Line Diagram | 2021-12-18 | 2022-12-20
Electrical Typical Schematic Diagrams For MV panel | BK-GCS-PEDCO-120-EL-DG-0001 | BK-GCS-PEDCO-120-EL-DG-0001Electrical Typical Schematic Diagrams For MV panel | 2022-01-12 | 0
Electrical Typical Schematic Diagrams For LV panel | BK-GCS-PEDCO-120-EL-DG-0002 | BK-GCS-PEDCO-120-EL-DG-0002Electrical Typical Schematic Diagrams For LV panel | 2021-12-13 | 0
Interconnection Wiring Diagram | BK-GCS-PEDCO-120-EL-DG-0003 | BK-GCS-PEDCO-120-EL-DG-0003Interconnection Wiring Diagram | 0 | 0
Wiring Diagram For Remote Control Panel (RCP) | BK-GCS-PEDCO-120-EL-DG-0005 | BK-GCS-PEDCO-120-EL-DG-0005Wiring Diagram For Remote Control Panel (RCP) | 2022-09-07 | 0
Wiring Diagrams For Cathodic Protection Systems | BK-GCS-PEDCO-120-EL-DG-0006 | BK-GCS-PEDCO-120-EL-DG-0006Wiring Diagrams For Cathodic Protection Systems | 0 | 0
Control Logic Diagram For LV Incomers and bus tie | BK-GCS-PEDCO-120-EL-LD-0001 | BK-GCS-PEDCO-120-EL-LD-0001Control Logic Diagram For LV Incomers and bus tie | 2022-01-16 | 2022-12-20
Overall Earthing Layout | BK-GCS-PEDCO-120-EL-PY-0001 | BK-GCS-PEDCO-120-EL-PY-0001Overall Earthing Layout | 2022-10-03 | 0
Earthing & Lightning Layout For Building & Shelter | BK-GCS-PEDCO-120-EL-PY-0002 | BK-GCS-PEDCO-120-EL-PY-0002Earthing & Lightning Layout For Building & Shelter | 2022-10-25 | 0
Area Lighting & Small Power Layout | BK-GCS-PEDCO-120-EL-PY-0003 | BK-GCS-PEDCO-120-EL-PY-0003Area Lighting & Small Power Layout | 2022-06-22 | 2022-12-20
Lighting & Small Power Layout For Building & Shelter | BK-GCS-PEDCO-120-EL-PY-0004 | BK-GCS-PEDCO-120-EL-PY-0004Lighting & Small Power Layout For Building & Shelter | 2022-05-15 | 2022-12-20
Area Electrical Cable Route & Section Layout | BK-GCS-PEDCO-120-EL-PY-0005 | BK-GCS-PEDCO-120-EL-PY-0005Area Electrical Cable Route & Section Layout | 2022-07-13 | 2022-12-20
Electrical Cable Route & Section Layout For Building & Shelter | BK-GCS-PEDCO-120-EL-PY-0006 | BK-GCS-PEDCO-120-EL-PY-0006Electrical Cable Route & Section Layout For Building & Shelter | 2022-07-25 | 2022-12-20
HVAC Power Cabling Arrangement Layout For Building | BK-GCS-PEDCO-120-EL-PY-0007 | BK-GCS-PEDCO-120-EL-PY-0007HVAC Power Cabling Arrangement Layout For Building | 0 | 0
Electrical Equipment Arrangement Layout For Building | BK-GCS-PEDCO-120-EL-PY-0008 | BK-GCS-PEDCO-120-EL-PY-0008Electrical Equipment Arrangement Layout For Building | 2022-05-09 | 2022-12-20
Cathodic Protection System Layout | BK-GCS-PEDCO-120-EL-PY-0009 | BK-GCS-PEDCO-120-EL-PY-0009Cathodic Protection System Layout | 0 | 0
Capacitor Banks Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0007 | BK-GCS-PEDCO-120-EL-SL-0007Capacitor Banks Single Line Diagram | 2022-03-02 | 2022-12-20
Power & Control Cables Termination Diagrams | BK-GCS-PEDCO-120-EL-DG-0007 | BK-GCS-PEDCO-120-EL-DG-0007Power & Control Cables Termination Diagrams | 0 | 0
Single Line Diagram for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-SL-0009 | BK-GCS-PEDCO-120-EL-SL-0009Single Line Diagram for UPS of CCTV in Desalting, Production & CS Unit | 0 | 0
SLD for Supplying UPS of CCTV Panel in Desalting Unit | BK-GCS-PEDCO-120-EL-SL-0008 | BK-GCS-PEDCO-120-EL-SL-0008SLD for Supplying UPS of CCTV Panel in Desalting Unit | 2022-08-15 | 2022-12-20
SLD for Supplying UPS of CCTV Panel in Production Unit | BK-GCS-PEDCO-120-EL-SL-0010 | BK-GCS-PEDCO-120-EL-SL-0010SLD for Supplying UPS of CCTV Panel in Production Unit | 2022-08-15 | 2022-12-20
Equipment Arrangement Layout for UPS of CCTV in Desalting Unit | BK-GCS-PEDCO-120-EL-PY-0010 | BK-GCS-PEDCO-120-EL-PY-0010Equipment Arrangement Layout for UPS of CCTV in Desalting Unit | 2022-08-28 | 2022-12-20
Equipment Arrangement Layout for UPS of CCTV in Production Unit | BK-GCS-PEDCO-120-EL-PY-0011 | BK-GCS-PEDCO-120-EL-PY-0011Equipment Arrangement Layout for UPS of CCTV in Production Unit | 2022-08-28 | 2022-12-20
Cable Route Layout for Desalting Unit | BK-GCS-PEDCO-120-EL-PY-0012 | BK-GCS-PEDCO-120-EL-PY-0012Cable Route Layout for Desalting Unit | 2022-10-22 | 0
Cable Route layout for Production Unit | BK-GCS-PEDCO-120-EL-PY-0013 | BK-GCS-PEDCO-120-EL-PY-0013Cable Route layout for Production Unit | 2022-10-22 | 0
Earthing Layout for Desalting Unit | BK-GCS-PEDCO-120-EL-PY-0014 | BK-GCS-PEDCO-120-EL-PY-0014Earthing Layout for Desalting Unit | 2022-10-25 | 0
Earthing Layout for Production Unit | BK-GCS-PEDCO-120-EL-PY-0015 | BK-GCS-PEDCO-120-EL-PY-0015Earthing Layout for Production Unit | 2022-10-25 | 0
Electrical Load List | BK-GCS-PEDCO-120-EL-LI-0001 | BK-GCS-PEDCO-120-EL-LI-0001Electrical Load List | 2021-11-16 | 2022-12-20
Electrical Power & Control Cable Schedule | BK-GCS-PEDCO-120-EL-LI-0002 | BK-GCS-PEDCO-120-EL-LI-0002Electrical Power & Control Cable Schedule | 2022-06-15 | 2022-12-20
Electrical Power & Control Drum Schedule & Cutting List | BK-GCS-PEDCO-120-EL-LI-0003 | BK-GCS-PEDCO-120-EL-LI-0003Electrical Power & Control Drum Schedule & Cutting List | 0 | 0
Cable Schedule For Cathodic Protection System | BK-GCS-PEDCO-120-EL-LI-0004 | BK-GCS-PEDCO-120-EL-LI-0004Cable Schedule For Cathodic Protection System | 0 | 0
Electrical I/O Signal List | BK-GCS-PEDCO-120-EL-LI-0005 | BK-GCS-PEDCO-120-EL-LI-0005Electrical I/O Signal List | 2022-06-20 | 2022-12-20
Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report | BK-GCS-PEDCO-120-EL-RT-0001 | BK-GCS-PEDCO-120-EL-RT-0001Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report | 2022-06-15 | 2022-12-20
Relay Coordination & Setting Study Report | BK-GCS-PEDCO-120-EL-RT-0002 | BK-GCS-PEDCO-120-EL-RT-0002Relay Coordination & Setting Study Report | 0 | 0
MTO For Earthing & Lightning Systems | BK-GCS-PEDCO-120-EL-MT-0001 | BK-GCS-PEDCO-120-EL-MT-0001MTO For Earthing & Lightning Systems | 2022-10-25 | 0
MTO For Lighting & Small Powers | BK-GCS-PEDCO-120-EL-MT-0002 | BK-GCS-PEDCO-120-EL-MT-0002MTO For Lighting & Small Powers | 0 | 0
MTO For Power & Control Cables | BK-GCS-PEDCO-120-EL-MT-0003 | BK-GCS-PEDCO-120-EL-MT-0003MTO For Power & Control Cables | 0 | 0
MTO For Tray/Ladder and Accessories | BK-GCS-PEDCO-120-EL-MT-0004 | BK-GCS-PEDCO-120-EL-MT-0004MTO For Tray/Ladder and Accessories | 0 | 0
MTO For Cathodic Protection System | BK-GCS-PEDCO-120-EL-MT-0005 | BK-GCS-PEDCO-120-EL-MT-0005MTO For Cathodic Protection System | 2022-05-01 | 2022-12-20
MTO For Electrical Bulk Items | BK-GCS-PEDCO-120-EL-MT-0006 | BK-GCS-PEDCO-120-EL-MT-0006MTO For Electrical Bulk Items | 0 | 0
Data Sheets For CCTV | BK-GCS-PEDCO-120-TE-DT-0001 | BK-GCS-PEDCO-120-TE-DT-0001Data Sheets For CCTV | 0 | 0
Data Sheets For PABX | BK-GCS-PEDCO-120-TE-DT-0002 | BK-GCS-PEDCO-120-TE-DT-0002Data Sheets For PABX | 2021-10-13 | 2022-12-20
Data Sheets For PAGA | BK-GCS-PEDCO-120-TE-DT-0003 | BK-GCS-PEDCO-120-TE-DT-0003Data Sheets For PAGA | 2021-10-13 | 2022-12-20
Data Sheets For Radio | BK-GCS-PEDCO-120-TE-DT-0004 | BK-GCS-PEDCO-120-TE-DT-0004Data Sheets For Radio | 2021-11-21 | 2022-12-20
Data Sheets For Telecom. Cable | BK-GCS-PEDCO-120-TE-DT-0005 | BK-GCS-PEDCO-120-TE-DT-0005Data Sheets For Telecom. Cable | 2021-10-13 | 2022-12-20
Data Sheets For Telecommunication Tower | BK-GCS-PEDCO-120-TE-DT-0006 | BK-GCS-PEDCO-120-TE-DT-0006Data Sheets For Telecommunication Tower | 2021-10-13 | 2022-12-20
Telecom Overall Block Diagram | BK-GCS-PEDCO-120-TE-BD-0001 | BK-GCS-PEDCO-120-TE-BD-0001Telecom Overall Block Diagram | 0 | 0
Typical Installation Details & Notes For Telecommunication Tower | BK-GCS-PEDCO-120-TE-DW-0001 | BK-GCS-PEDCO-120-TE-DW-0001Typical Installation Details & Notes For Telecommunication Tower | 0 | 0
Block Diagram For CCTV | BK-GCS-PEDCO-120-TE-BD-0002 | BK-GCS-PEDCO-120-TE-BD-0002Block Diagram For CCTV | 0 | 0
Block Diagram For CCTV in Binak DU | BK-GCS-PEDCO-120-TE-BD-0003 | BK-GCS-PEDCO-120-TE-BD-0003Block Diagram For CCTV in Binak DU | 0 | 0
Block Diagram For PABX | BK-GCS-PEDCO-120-TE-BD-0004 | BK-GCS-PEDCO-120-TE-BD-0004Block Diagram For PABX | 2021-07-28 | 2022-03-08
Block Diagram For PAGA | BK-GCS-PEDCO-120-TE-BD-0005 | BK-GCS-PEDCO-120-TE-BD-0005Block Diagram For PAGA | 2021-07-28 | 2022-03-08
Block Diagram For Radio | BK-GCS-PEDCO-120-TE-BD-0006 | BK-GCS-PEDCO-120-TE-BD-0006Block Diagram For Radio | 2021-07-28 | 2021-09-25
Telecomm. Equipment Layout For Electrical Building | BK-GCS-PEDCO-120-TE-PY-0001 | BK-GCS-PEDCO-120-TE-PY-0001Telecomm. Equipment Layout For Electrical Building | 2022-04-17 | 2022-12-20
Telecomm. Equipment Layout For Control Building | BK-GCS-PEDCO-120-TE-PY-0002 | BK-GCS-PEDCO-120-TE-PY-0002Telecomm. Equipment Layout For Control Building | 2022-06-11 | 2022-12-20
CCTV Equipment Layout For Area | BK-GCS-PEDCO-120-TE-PY-0003 | BK-GCS-PEDCO-120-TE-PY-0003CCTV Equipment Layout For Area | 0 | 0
CCTV Equipment Layout For Desalting Unit Area | BK-GCS-PEDCO-120-TE-PY-0004 | BK-GCS-PEDCO-120-TE-PY-0004CCTV Equipment Layout For Desalting Unit Area | 0 | 0
Telecomm Equipment Layout For Area | BK-GCS-PEDCO-120-TE-PY-0005 | BK-GCS-PEDCO-120-TE-PY-0005Telecomm Equipment Layout For Area | 2022-04-04 | 2022-12-20
PAGA Equipment Layout For Area | BK-GCS-PEDCO-120-TE-PY-0006 | BK-GCS-PEDCO-120-TE-PY-0006PAGA Equipment Layout For Area | 2022-04-06 | 2022-12-20
Cable Schedule For CCTV | BK-GCS-PEDCO-120-TE-LI-0001 | BK-GCS-PEDCO-120-TE-LI-0001Cable Schedule For CCTV | 0 | 0
Cable Schedule For PABX | BK-GCS-PEDCO-120-TE-LI-0003 | BK-GCS-PEDCO-120-TE-LI-0003Cable Schedule For PABX | 2022-06-07 | 2022-12-20
Cable Schedule For PAGA | BK-GCS-PEDCO-120-TE-LI-0004 | BK-GCS-PEDCO-120-TE-LI-0004Cable Schedule For PAGA | 2022-06-07 | 2022-12-20
MTO For CCTV | BK-GCS-PEDCO-120-TE-MT-0001 | BK-GCS-PEDCO-120-TE-MT-0001MTO For CCTV | 0 | 0
MTO For CCTV in Binak DU Area | BK-GCS-PEDCO-120-TE-MT-0002 | BK-GCS-PEDCO-120-TE-MT-0002MTO For CCTV in Binak DU Area | 0 | 0
MTO For PABX | BK-GCS-PEDCO-120-TE-MT-0003 | BK-GCS-PEDCO-120-TE-MT-0003MTO For PABX | 2022-05-25 | 2022-12-20
MTO For PAGA | BK-GCS-PEDCO-120-TE-MT-0004 | BK-GCS-PEDCO-120-TE-MT-0004MTO For PAGA | 2022-05-25 | 2022-12-20
MTO For Radio | BK-GCS-PEDCO-120-TE-MT-0005 | BK-GCS-PEDCO-120-TE-MT-0005MTO For Radio | 2021-12-13 | 0
MTO For Telecom. Cable | BK-GCS-PEDCO-120-TE-MT-0006 | BK-GCS-PEDCO-120-TE-MT-0006MTO For Telecom. Cable | 0 | 0
Architectural Detail Drawing For Control Building | BK-GCS-PEDCO-120-AR-DW-0001 | BK-GCS-PEDCO-120-AR-DW-0001Architectural Detail Drawing For Control Building | 2022-08-03 | 2022-12-20
Architectural Detail Drawing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-AR-DW-0002 | BK-GCS-PEDCO-120-AR-DW-0002Architectural Detail Drawing For Extension of Existing Elect. Building | 2022-01-15 | 2022-12-20
Architectural Drawing For Gas Compressors Shelter | BK-GCS-PEDCO-120-AR-DW-0003 | BK-GCS-PEDCO-120-AR-DW-0003Architectural Drawing For Gas Compressors Shelter | 2022-06-11 | 2022-12-20
Architectural Drawing For Chemical Inj. Packages/Chemical Storage Shelter | BK-GCS-PEDCO-120-AR-DW-0004 | BK-GCS-PEDCO-120-AR-DW-0004Architectural Drawing For Chemical Inj. Packages/Chemical Storage Shelter | 0 | 2022-12-20
Architectural Drawing For Utility Shelter | BK-GCS-PEDCO-120-AR-DW-0005 | BK-GCS-PEDCO-120-AR-DW-0005Architectural Drawing For Utility Shelter | 2022-10-26 | 0
Architectural Drawing For Fire Water Pumps Shelter | BK-GCS-PEDCO-120-AR-DW-0006 | BK-GCS-PEDCO-120-AR-DW-0006Architectural Drawing For Fire Water Pumps Shelter | 0 | 0
Architectural Drawing For Fire Shed | BK-GCS-PEDCO-120-AR-DW-0007 | BK-GCS-PEDCO-120-AR-DW-0007Architectural Drawing For Fire Shed | 2022-05-01 | 2022-12-20
MTO For Architectural Works | BK-GCS-PEDCO-120-AR-MT-0001 | BK-GCS-PEDCO-120-AR-MT-0001MTO For Architectural Works | 0 | 0
MTO For Blast Proof Doors | BK-GCS-PEDCO-120-AR-MT-0002 | BK-GCS-PEDCO-120-AR-MT-0002MTO For Blast Proof Doors | 0 | 0
Site Sewarage System Layout & Details | BK-GCS-PEDCO-120-CV-PY-0001 | BK-GCS-PEDCO-120-CV-PY-0001Site Sewarage System Layout & Details | 0 | 0
Cable Trench and Duct Bank Layout | BK-GCS-PEDCO-120-CV-PY-0002 | BK-GCS-PEDCO-120-CV-PY-0002Cable Trench and Duct Bank Layout | 2022-07-25 | 2022-12-20
Oil Contaminated Water System Layout | BK-GCS-PEDCO-120-CV-PY-0003 | BK-GCS-PEDCO-120-CV-PY-0003Oil Contaminated Water System Layout | 2022-05-29 | 2022-12-20
Plant Clean Water Drainage System Layout & Details | BK-GCS-PEDCO-120-CV-PY-0004 | BK-GCS-PEDCO-120-CV-PY-0004Plant Clean Water Drainage System Layout & Details | 2022-05-31 | 2022-12-20
Road, Paving And Plant Finish Grading Layout & Sections | BK-GCS-PEDCO-120-CV-PY-0005 | BK-GCS-PEDCO-120-CV-PY-0005Road, Paving And Plant Finish Grading Layout & Sections | 0 | 0
Plant Underground Composite Layout | BK-GCS-PEDCO-120-CV-PY-0006 | BK-GCS-PEDCO-120-CV-PY-0006Plant Underground Composite Layout | 0 | 0
Rough Grading Plan and Details | BK-GCS-PEDCO-120-CV-PY-0007 | BK-GCS-PEDCO-120-CV-PY-0007Rough Grading Plan and Details | 2022-05-23 | 2022-12-20
Calculation Note For Inside Surface Water Drainage Channels | BK-GCS-PEDCO-120-CV-CN-0001 | BK-GCS-PEDCO-120-CV-CN-0001Calculation Note For Inside Surface Water Drainage Channels | 2022-08-22 | 2022-12-20
Calculation Note for offsite flood control system | BK-GCS-PEDCO-120-CV-CN-0002 | BK-GCS-PEDCO-120-CV-CN-0002Calculation Note for offsite flood control system | 2022-07-20 | 2022-12-20
Site Visit Report (Civil Work) - GCS | BK-GCS-PEDCO-110-CV-RT-0001 | BK-GCS-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - GCS | #N/A | #N/A
MTO For Civil Work | BK-GCS-PEDCO-120-CV-MT-0001 | BK-GCS-PEDCO-120-CV-MT-0001MTO For Civil Work | 0 | 0
Structural Calculation Note For Control Building | BK-GCS-PEDCO-120-ST-CN-0002 | BK-GCS-PEDCO-120-ST-CN-0002Structural Calculation Note For Control Building | 0 | 0
Calculation Report for Gas Compressors Shelter | BK-GCS-PEDCO-120-ST-CN-0003 | BK-GCS-PEDCO-120-ST-CN-0003Calculation Report for Gas Compressors Shelter | 0 | 0
Calculation Report for Extension of Existing Elect. Building | BK-GCS-PEDCO-120-ST-CN-0005 | BK-GCS-PEDCO-120-ST-CN-0005Calculation Report for Extension of Existing Elect. Building | 0 | 2022-12-20
Calculation Note for Gas Compressors Foundation | BK-GCS-PEDCO-120-ST-CN-0006 | BK-GCS-PEDCO-120-ST-CN-0006Calculation Note for Gas Compressors Foundation | 0 | 0
Calculation Note for Tank Foundation (TK-2301 A/B) | BK-GCS-PEDCO-120-ST-CN-0007 | BK-GCS-PEDCO-120-ST-CN-0007Calculation Note for Tank Foundation (TK-2301 A/B) | 0 | 0
Calculation Note for Utility Shelter | BK-GCS-PEDCO-120-ST-CN-0008 | BK-GCS-PEDCO-120-ST-CN-0008Calculation Note for Utility Shelter | 0 | 0
Calculation Note for Fire Water Pump Shelter | BK-GCS-PEDCO-120-ST-CN-0009 | BK-GCS-PEDCO-120-ST-CN-0009Calculation Note for Fire Water Pump Shelter | 0 | 0
Calculation Note for Foundation of Slug Catcher Drum (V-2104) | BK-GCS-PEDCO-120-ST-CN-0010 | BK-GCS-PEDCO-120-ST-CN-0010Calculation Note for Foundation of Slug Catcher Drum (V-2104) | 0 | 0
Calculation Note for Foundation of Dehydration Package (PK-2101) | BK-GCS-PEDCO-120-ST-CN-0011 | BK-GCS-PEDCO-120-ST-CN-0011Calculation Note for Foundation of Dehydration Package (PK-2101) | 0 | 0
Calculation Note for Close Drain Sump Pit (SU-2201 A) | BK-GCS-PEDCO-120-ST-CN-0012 | BK-GCS-PEDCO-120-ST-CN-0012Calculation Note for Close Drain Sump Pit (SU-2201 A) | 0 | 0
Calculation Note for Oily Water Sump Pit (SU-2201 B) | BK-GCS-PEDCO-120-ST-CN-0013 | BK-GCS-PEDCO-120-ST-CN-0013Calculation Note for Oily Water Sump Pit (SU-2201 B) | 0 | 0
Calculation Note For Compressor Area Main Sleepers | BK-GCS-PEDCO-120-ST-CN-0014 | BK-GCS-PEDCO-120-ST-CN-0014Calculation Note For Compressor Area Main Sleepers | 0 | 0
Calculation Note For Flare Area Sleepers | BK-GCS-PEDCO-120-ST-CN-0015 | BK-GCS-PEDCO-120-ST-CN-0015Calculation Note For Flare Area Sleepers | 0 | 0
Calculation Note For Special Pipe Supports | BK-GCS-PEDCO-120-ST-CN-0016 | BK-GCS-PEDCO-120-ST-CN-0016Calculation Note For Special Pipe Supports | 0 | 0
Calculation Note for1st Stage Air Coolers (AE-2101 A/B/C) | BK-GCS-PEDCO-120-ST-CN-0017 | BK-GCS-PEDCO-120-ST-CN-0017Calculation Note for1st Stage Air Coolers (AE-2101 A/B/C) | 0 | 0
Calculation Note for 2nd Stage Air Coolers (AE-2102 A/B/C) | BK-GCS-PEDCO-120-ST-CN-0018 | BK-GCS-PEDCO-120-ST-CN-0018Calculation Note for 2nd Stage Air Coolers (AE-2102 A/B/C) | 0 | 0
Calculation Note for Elevated Potable Water Tank (TK-2209) | BK-GCS-PEDCO-120-ST-CN-0019 | BK-GCS-PEDCO-120-ST-CN-0019Calculation Note for Elevated Potable Water Tank (TK-2209) | 0 | 0
Calculation Note for Lean Glycol Storage Tank (TK-2102) | BK-GCS-PEDCO-120-ST-CN-0020 | BK-GCS-PEDCO-120-ST-CN-0020Calculation Note for Lean Glycol Storage Tank (TK-2102) | 0 | 0
Calculation Note for Nitrogen Package (PK-2204A/B) | BK-GCS-PEDCO-120-ST-CN-0021 | BK-GCS-PEDCO-120-ST-CN-0021Calculation Note for Nitrogen Package (PK-2204A/B) | 0 | 0
Calculation Note for Glycol Sump Pit (SU-2101) | BK-GCS-PEDCO-120-ST-CN-0022 | BK-GCS-PEDCO-120-ST-CN-0022Calculation Note for Glycol Sump Pit (SU-2101) | 0 | 0
Calculation Note for Slug Pumps (P-2101A/B) | BK-GCS-PEDCO-120-ST-CN-0023 | BK-GCS-PEDCO-120-ST-CN-0023Calculation Note for Slug Pumps (P-2101A/B) | 0 | 0
Calculation Note for Utility Area Sleepers | BK-GCS-PEDCO-120-ST-CN-0024 | BK-GCS-PEDCO-120-ST-CN-0024Calculation Note for Utility Area Sleepers | 0 | 0
Calculation Note for Pipe rack | BK-GCS-PEDCO-120-ST-CN-0025 | BK-GCS-PEDCO-120-ST-CN-0025Calculation Note for Pipe rack | 0 | 0
Calculation Note for Chemical Injection and Storage Shelter | BK-GCS-PEDCO-120-ST-CN-0026 | BK-GCS-PEDCO-120-ST-CN-0026Calculation Note for Chemical Injection and Storage Shelter | 0 | 2022-12-20
Foundation Location Plan | BK-GCS-PEDCO-120-ST-DW-0003 | BK-GCS-PEDCO-120-ST-DW-0003Foundation Location Plan | 0 | 0
Foundation Drawing For 1st Stage Gas Compressor (C-2101A/B/C) | BK-GCS-PEDCO-120-ST-DW-0004 | BK-GCS-PEDCO-120-ST-DW-0004Foundation Drawing For 1st Stage Gas Compressor (C-2101A/B/C) | 0 | 0
Foundation Drawing For 2nd Stage Gas Compressor (C-2102A/B/C) | BK-GCS-PEDCO-120-ST-DW-0005 | BK-GCS-PEDCO-120-ST-DW-0005Foundation Drawing For 2nd Stage Gas Compressor (C-2102A/B/C) | 0 | 0
Foundation Drawing For 1st Stage Air Coolers (AE-2101 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0007 | BK-GCS-PEDCO-120-ST-DW-0007Foundation Drawing For 1st Stage Air Coolers (AE-2101 A/B/C) | 0 | 0
Foundation Drawing For 2nd Stage Air Coolers (AE-2102 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0008 | BK-GCS-PEDCO-120-ST-DW-0008Foundation Drawing For 2nd Stage Air Coolers (AE-2102 A/B/C) | 0 | 0
Foundation Drawing For Inlet Gas K.O. Drum (V-2105) | BK-GCS-PEDCO-120-ST-DW-0009 | BK-GCS-PEDCO-120-ST-DW-0009Foundation Drawing For Inlet Gas K.O. Drum (V-2105) | 0 | 0
Foundation Drawing For For 1st Stage G.C. Suction Drums (V-2101 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0010 | BK-GCS-PEDCO-120-ST-DW-0010Foundation Drawing For For 1st Stage G.C. Suction Drums (V-2101 A/B/C) | 0 | 0
Foundation Drawing For For 2nd Stage G.C. Suction Drums (V-2102 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0011 | BK-GCS-PEDCO-120-ST-DW-0011Foundation Drawing For For 2nd Stage G.C. Suction Drums (V-2102 A/B/C) | 0 | 0
Foundation Drawing For 2nd Stage G.C. Discharge Drum (V-2103) | BK-GCS-PEDCO-120-ST-DW-0012 | BK-GCS-PEDCO-120-ST-DW-0012Foundation Drawing For 2nd Stage G.C. Discharge Drum (V-2103) | 0 | 0
Foundation Drawing For Fuel Oil Drum (V-2206) | BK-GCS-PEDCO-120-ST-DW-0013 | BK-GCS-PEDCO-120-ST-DW-0013Foundation Drawing For Fuel Oil Drum (V-2206) | 0 | 0
Foundation Drawing For Instrument Air Receiver (V-2203) | BK-GCS-PEDCO-120-ST-DW-0014 | BK-GCS-PEDCO-120-ST-DW-0014Foundation Drawing For Instrument Air Receiver (V-2203) | 0 | 0
Foundation Drawing For Elevated Potable Water Tank (TK-2209) | BK-GCS-PEDCO-120-ST-DW-0015 | BK-GCS-PEDCO-120-ST-DW-0015Foundation Drawing For Elevated Potable Water Tank (TK-2209) | 0 | 0
Structural Drawing For Close Drain Sump Pit (SU-2201 A) | BK-GCS-PEDCO-120-ST-DW-0016 | BK-GCS-PEDCO-120-ST-DW-0016Structural Drawing For Close Drain Sump Pit (SU-2201 A) | 0 | 0
Foundation Drawing For Fuel Gas K.O Drum (V-2205) | BK-GCS-PEDCO-120-ST-DW-0017 | BK-GCS-PEDCO-120-ST-DW-0017Foundation Drawing For Fuel Gas K.O Drum (V-2205) | 0 | 0
Foundation Drawing For Slug Catcher Drum (V-2104) | BK-GCS-PEDCO-120-ST-DW-0018 | BK-GCS-PEDCO-120-ST-DW-0018Foundation Drawing For Slug Catcher Drum (V-2104) | 0 | 0
Foundation Drawing For Degassing Drum (V-2106) | BK-GCS-PEDCO-120-ST-DW-0019 | BK-GCS-PEDCO-120-ST-DW-0019Foundation Drawing For Degassing Drum (V-2106) | 0 | 0
Foundation Drawing For Nitrogen Receiver Drum (V-2204) | BK-GCS-PEDCO-120-ST-DW-0020 | BK-GCS-PEDCO-120-ST-DW-0020Foundation Drawing For Nitrogen Receiver Drum (V-2204) | 0 | 0
Structural Drawing For Oily Water Sump Pit (SU-2201 B) | BK-GCS-PEDCO-120-ST-DW-0021 | BK-GCS-PEDCO-120-ST-DW-0021Structural Drawing For Oily Water Sump Pit (SU-2201 B) | 0 | 0
Foundation Drawing For Lean Glycol Storage Tank (TK-2102) | BK-GCS-PEDCO-120-ST-DW-0023 | BK-GCS-PEDCO-120-ST-DW-0023Foundation Drawing For Lean Glycol Storage Tank (TK-2102) | 0 | 0
Foundation Drawing For Fire Water Storage Tanks (TK-2301A/B) | BK-GCS-PEDCO-120-ST-DW-0024 | BK-GCS-PEDCO-120-ST-DW-0024Foundation Drawing For Fire Water Storage Tanks (TK-2301A/B) | 0 | 0
Foundation Drawing For Slug Storage Tank (TK-2101) | BK-GCS-PEDCO-120-ST-DW-0025 | BK-GCS-PEDCO-120-ST-DW-0025Foundation Drawing For Slug Storage Tank (TK-2101) | 0 | 0
Foundation Drawing For Dehydration Package (PK-2101) | BK-GCS-PEDCO-120-ST-DW-0026 | BK-GCS-PEDCO-120-ST-DW-0026Foundation Drawing For Dehydration Package (PK-2101) | 0 | 0
Foundation Drawing For Diesel Generator (PK-2206) | BK-GCS-PEDCO-120-ST-DW-0027 | BK-GCS-PEDCO-120-ST-DW-0027Foundation Drawing For Diesel Generator (PK-2206) | 0 | 0
Foundation Drawing For Instrument & Plant Air Package (PK-C-2203A/B) | BK-GCS-PEDCO-120-ST-DW-0028 | BK-GCS-PEDCO-120-ST-DW-0028Foundation Drawing For Instrument & Plant Air Package (PK-C-2203A/B) | 0 | 0
Foundation Drawing For Corrosion Inhibitor Injection Package (PK-2207) | BK-GCS-PEDCO-120-ST-DW-0029 | BK-GCS-PEDCO-120-ST-DW-0029Foundation Drawing For Corrosion Inhibitor Injection Package (PK-2207) | 0 | 0
Foundation Drawing For Methanol Injection Package (PK-2208) | BK-GCS-PEDCO-120-ST-DW-0030 | BK-GCS-PEDCO-120-ST-DW-0030Foundation Drawing For Methanol Injection Package (PK-2208) | 0 | 0
Foundation Drawing For LP Flare Package (PK-2201) | BK-GCS-PEDCO-120-ST-DW-0031 | BK-GCS-PEDCO-120-ST-DW-0031Foundation Drawing For LP Flare Package (PK-2201) | 0 | 0
Foundation Drawing For Nitrogen Package (PK-2204A/B) | BK-GCS-PEDCO-120-ST-DW-0032 | BK-GCS-PEDCO-120-ST-DW-0032Foundation Drawing For Nitrogen Package (PK-2204A/B) | 0 | 0
Dike Wall Drawing For Lean Glycol Storage Tank (TK-2102) | BK-GCS-PEDCO-120-ST-DW-0033 | BK-GCS-PEDCO-120-ST-DW-0033Dike Wall Drawing For Lean Glycol Storage Tank (TK-2102) | 0 | 0
Dike Wall Drawing For Slug Storage Tank (TK-2101) | BK-GCS-PEDCO-120-ST-DW-0034 | BK-GCS-PEDCO-120-ST-DW-0034Dike Wall Drawing For Slug Storage Tank (TK-2101) | 0 | 0
Foundation Drawing For Glycol Sump Pit (SU-2101) | BK-GCS-PEDCO-120-ST-DW-0035 | BK-GCS-PEDCO-120-ST-DW-0035Foundation Drawing For Glycol Sump Pit (SU-2101) | 0 | 0
Foundation Drawing For Glycol Transfer Pumps (P-2103 A/B) | BK-GCS-PEDCO-120-ST-DW-0036 | BK-GCS-PEDCO-120-ST-DW-0036Foundation Drawing For Glycol Transfer Pumps (P-2103 A/B) | 0 | 0
Foundation Drawing For Glycol Manual Pump (P-2102) | BK-GCS-PEDCO-120-ST-DW-0037 | BK-GCS-PEDCO-120-ST-DW-0037Foundation Drawing For Glycol Manual Pump (P-2102) | 0 | 0
Foundation Drawing For Fire Water Jockey Pumps (P-2302A/B) | BK-GCS-PEDCO-120-ST-DW-0038 | BK-GCS-PEDCO-120-ST-DW-0038Foundation Drawing For Fire Water Jockey Pumps (P-2302A/B) | 0 | 0
Foundation Drawing For Fire Water Electrical Pump (P-2301 A) | BK-GCS-PEDCO-120-ST-DW-0039 | BK-GCS-PEDCO-120-ST-DW-0039Foundation Drawing For Fire Water Electrical Pump (P-2301 A) | 0 | 0
Foundation Drawing For Fire Water Diesel Pumps (P-2302 B/C) | BK-GCS-PEDCO-120-ST-DW-0040 | BK-GCS-PEDCO-120-ST-DW-0040Foundation Drawing For Fire Water Diesel Pumps (P-2302 B/C) | 0 | 0
Foundation Drawing For Potable Water Pump (P-2209) | BK-GCS-PEDCO-120-ST-DW-0041 | BK-GCS-PEDCO-120-ST-DW-0041Foundation Drawing For Potable Water Pump (P-2209) | 0 | 0
Foundation Drawing For Fuel Oil Pump (P-2206) | BK-GCS-PEDCO-120-ST-DW-0042 | BK-GCS-PEDCO-120-ST-DW-0042Foundation Drawing For Fuel Oil Pump (P-2206) | 0 | 0
Foundation Drawing For Slug Pumps (P-2101A/B) | BK-GCS-PEDCO-120-ST-DW-0043 | BK-GCS-PEDCO-120-ST-DW-0043Foundation Drawing For Slug Pumps (P-2101A/B) | 0 | 0
Foundation Drawing For Compressor Area Main Sleepers | BK-GCS-PEDCO-120-ST-DW-0044 | BK-GCS-PEDCO-120-ST-DW-0044Foundation Drawing For Compressor Area Main Sleepers | 0 | 0
Foundation Drawing For Compressor Area Secondary Sleepers | BK-GCS-PEDCO-120-ST-DW-0045 | BK-GCS-PEDCO-120-ST-DW-0045Foundation Drawing For Compressor Area Secondary Sleepers | 0 | 0
Foundation Drawing For Utility Area Sleepers | BK-GCS-PEDCO-120-ST-DW-0046 | BK-GCS-PEDCO-120-ST-DW-0046Foundation Drawing For Utility Area Sleepers | 0 | 0
Foundation Drawing For Flare Area Sleepers | BK-GCS-PEDCO-120-ST-DW-0047 | BK-GCS-PEDCO-120-ST-DW-0047Foundation Drawing For Flare Area Sleepers | 0 | 0
Foundation Drawing For Transformer & Shelters | BK-GCS-PEDCO-120-ST-DW-0048 | BK-GCS-PEDCO-120-ST-DW-0048Foundation Drawing For Transformer & Shelters | 0 | 0
Foundation Drawing For Pipe Supports | BK-GCS-PEDCO-120-ST-DW-0049 | BK-GCS-PEDCO-120-ST-DW-0049Foundation Drawing For Pipe Supports | 0 | 0
Structural Drawing For Special Pipe Supports | BK-GCS-PEDCO-120-ST-DW-0050 | BK-GCS-PEDCO-120-ST-DW-0050Structural Drawing For Special Pipe Supports | 0 | 0
Culvert Detail Drawing | BK-GCS-PEDCO-120-ST-DW-0051 | BK-GCS-PEDCO-120-ST-DW-0051Culvert Detail Drawing | 0 | 0
Foundation Drawing For Access Platforms | BK-GCS-PEDCO-120-ST-DW-0052 | BK-GCS-PEDCO-120-ST-DW-0052Foundation Drawing For Access Platforms | 0 | 0
Structural Drawing For Access Platforms | BK-GCS-PEDCO-120-ST-DW-0053 | BK-GCS-PEDCO-120-ST-DW-0053Structural Drawing For Access Platforms | 0 | 0
Foundation Drawing For Pipe rack | BK-GCS-PEDCO-120-ST-DW-0054 | BK-GCS-PEDCO-120-ST-DW-0054Foundation Drawing For Pipe rack | 0 | 0
Structural Drawing For Pipe rack | BK-GCS-PEDCO-120-ST-DW-0055 | BK-GCS-PEDCO-120-ST-DW-0055Structural Drawing For Pipe rack | 0 | 0
Foundation Drawing For Lighting Poles and Towers | BK-GCS-PEDCO-120-ST-DW-0056 | BK-GCS-PEDCO-120-ST-DW-0056Foundation Drawing For Lighting Poles and Towers | 0 | 0
Foundation Drawing For Chemical Injection and Storage Shelter | BK-GCS-PEDCO-120-ST-DW-0057 | BK-GCS-PEDCO-120-ST-DW-0057Foundation Drawing For Chemical Injection and Storage Shelter | 0 | 2022-12-20
Structural Drawing For Chemical Injection and Storage Shelter | BK-GCS-PEDCO-120-ST-DW-0058 | BK-GCS-PEDCO-120-ST-DW-0058Structural Drawing For Chemical Injection and Storage Shelter | 0 | 2022-12-20
Foundation Drawing For Gas Compressor Shelter | BK-GCS-PEDCO-120-ST-DW-0059 | BK-GCS-PEDCO-120-ST-DW-0059Foundation Drawing For Gas Compressor Shelter | 0 | 0
Structural Drawing For Gas Compressor Shelter | BK-GCS-PEDCO-120-ST-DW-0060 | BK-GCS-PEDCO-120-ST-DW-0060Structural Drawing For Gas Compressor Shelter | 0 | 0
Foundation Drawing For Control Building | BK-GCS-PEDCO-120-ST-DW-0061 | BK-GCS-PEDCO-120-ST-DW-0061Foundation Drawing For Control Building | 0 | 0
Structural Drawing For Control Building | BK-GCS-PEDCO-120-ST-DW-0062 | BK-GCS-PEDCO-120-ST-DW-0062Structural Drawing For Control Building | 0 | 0
Foundation Drawing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-ST-DW-0063 | BK-GCS-PEDCO-120-ST-DW-0063Foundation Drawing For Extension of Existing Elect. Building | 0 | 2022-12-20
Structural Drawing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-ST-DW-0064 | BK-GCS-PEDCO-120-ST-DW-0064Structural Drawing For Extension of Existing Elect. Building | 0 | 2022-12-20
Foundation Drawing For Fire Water Pump Shelter | BK-GCS-PEDCO-120-ST-DW-0065 | BK-GCS-PEDCO-120-ST-DW-0065Foundation Drawing For Fire Water Pump Shelter | 0 | 0
Structural Drawing For Fire Water Pump Shelter | BK-GCS-PEDCO-120-ST-DW-0066 | BK-GCS-PEDCO-120-ST-DW-0066Structural Drawing For Fire Water Pump Shelter | 0 | 0
Foundation Drawing For Utility Shelter | BK-GCS-PEDCO-120-ST-DW-0067 | BK-GCS-PEDCO-120-ST-DW-0067Foundation Drawing For Utility Shelter | 0 | 0
Structural Drawing For Utility Shelter | BK-GCS-PEDCO-120-ST-DW-0068 | BK-GCS-PEDCO-120-ST-DW-0068Structural Drawing For Utility Shelter | 0 | 0
Foundation Drawing For Air Dryer Packages (PK-D-2203A/B) | BK-GCS-PEDCO-120-ST-DW-0069 | BK-GCS-PEDCO-120-ST-DW-0069Foundation Drawing For Air Dryer Packages (PK-D-2203A/B) | 0 | 0
Foundation Drawing For Pig Launcher (PL-3101) | BK-GCS-PEDCO-120-ST-DW-0070 | BK-GCS-PEDCO-120-ST-DW-0070Foundation Drawing For Pig Launcher (PL-3101) | 0 | 0
Foundation Drawing For Ignition Package | BK-GCS-PEDCO-120-ST-DW-0071 | BK-GCS-PEDCO-120-ST-DW-0071Foundation Drawing For Ignition Package | 0 | 0
Foundation Drawing For Fire Shed | BK-GCS-PEDCO-120-ST-DW-0072 | BK-GCS-PEDCO-120-ST-DW-0072Foundation Drawing For Fire Shed | 2022-03-07 | 2022-06-21
Structural Drawing For Fire Shed | BK-GCS-PEDCO-120-ST-DW-0073 | BK-GCS-PEDCO-120-ST-DW-0073Structural Drawing For Fire Shed | 2022-03-07 | 2022-06-21
Structural Drawing For Shelter of Transformers | BK-GCS-PEDCO-120-ST-DW-0074 | BK-GCS-PEDCO-120-ST-DW-0074Structural Drawing For Shelter of Transformers | 0 | 0
MTO For Steel Structures Works | BK-GCS-PEDCO-120-ST-MT-0001 | BK-GCS-PEDCO-120-ST-MT-0001MTO For Steel Structures Works | 0 | 0
MTO For Structural Concrete Works | BK-GCS-PEDCO-120-ST-MT-0002 | BK-GCS-PEDCO-120-ST-MT-0002MTO For Structural Concrete Works | 0 | 0
Topographical Map | BK-GCS-PEDCO-120-SU-MP-0001 | BK-GCS-PEDCO-120-SU-MP-0001Topographical Map | 2022-04-30 | 0
Geotechnical Investigation Plan for Compressor Station | BK-GCS-PEDCO-120-GT-PR-0001 | BK-GCS-PEDCO-120-GT-PR-0001Geotechnical Investigation Plan for Compressor Station | 2021-12-19 | 2022-01-18
Geotechnical Investigation Report for Compressor Station | BK-GCS-PEDCO-120-GT-RT-0001 | BK-GCS-PEDCO-120-GT-RT-0001Geotechnical Investigation Report for Compressor Station | 2022-05-17 | 2022-12-20
PMR For Gas Compressors | BK-GCS-PEDCO-120-ME-MR-0001 | BK-GCS-PEDCO-120-ME-MR-0001PMR For Gas Compressors | 2021-11-28 | 2022-07-22
TBE For Gas Compressors | BK-GCS-PEDCO-120-ME-TB-0001 | BK-GCS-PEDCO-120-ME-TB-0001TBE For Gas Compressors | 2022-02-02 | 2022-07-22
PMR For Gas Dehydration Package | BK-GCS-PEDCO-120-ME-MR-0002 | BK-GCS-PEDCO-120-ME-MR-0002PMR For Gas Dehydration Package | 2021-12-19 | 2022-12-20
TBE For Gas Dehydration Package | BK-GCS-PEDCO-120-ME-TB-0002 | BK-GCS-PEDCO-120-ME-TB-0002TBE For Gas Dehydration Package | 2022-03-28 | 0
PMR For Pressure Vessels | BK-GCS-PEDCO-120-ME-MR-0003 | BK-GCS-PEDCO-120-ME-MR-0003PMR For Pressure Vessels | 2022-09-18 | 0
TBE For Pressure Vessels | BK-GCS-PEDCO-120-ME-TB-0003 | BK-GCS-PEDCO-120-ME-TB-0003TBE For Pressure Vessels | 0 | 0
PMR For Gas Air Coolers | BK-GCS-PEDCO-120-ME-MR-0004 | BK-GCS-PEDCO-120-ME-MR-0004PMR For Gas Air Coolers | 2022-08-03 | 0
TBE For Gas Air Coolers | BK-GCS-PEDCO-120-ME-TB-0004 | BK-GCS-PEDCO-120-ME-TB-0004TBE For Gas Air Coolers | 2022-08-29 | 0
PMR For Storage Tanks | BK-GCS-PEDCO-120-ME-MR-0005 | BK-GCS-PEDCO-120-ME-MR-0005PMR For Storage Tanks | 0 | 0
TBE For Storage Tanks | BK-GCS-PEDCO-120-ME-TB-0005 | BK-GCS-PEDCO-120-ME-TB-0005TBE For Storage Tanks | 0 | 0
PMR For Instrument/Plant Air & Nitrogen Packages | BK-GCS-PEDCO-120-ME-MR-0006 | BK-GCS-PEDCO-120-ME-MR-0006PMR For Instrument/Plant Air & Nitrogen Packages | 2022-08-09 | 0
TBE For Instrument/Plant Air & Nitrogen Packages | BK-GCS-PEDCO-120-ME-TB-0006 | BK-GCS-PEDCO-120-ME-TB-0006TBE For Instrument/Plant Air & Nitrogen Packages | 0 | 0
PMR For Chemical Injection Packages | BK-GCS-PEDCO-120-ME-MR-0008 | BK-GCS-PEDCO-120-ME-MR-0008PMR For Chemical Injection Packages | 2022-08-09 | 0
TBE For Chemical Injection Packages | BK-GCS-PEDCO-120-ME-TB-0008 | BK-GCS-PEDCO-120-ME-TB-0008TBE For Chemical Injection Packages | 0 | 0
PMR For Centrifugal Pumps For Process Services | BK-GCS-PEDCO-120-ME-MR-0009 | BK-GCS-PEDCO-120-ME-MR-0009PMR For Centrifugal Pumps For Process Services | 2022-09-11 | 0
TBE For Centrifugal Pumps For Process Services | BK-GCS-PEDCO-120-ME-TB-0009 | BK-GCS-PEDCO-120-ME-TB-0009TBE For Centrifugal Pumps For Process Services | 0 | 0
PMR For Centrifugal Pumps For General Services | BK-GCS-PEDCO-120-ME-MR-0010 | BK-GCS-PEDCO-120-ME-MR-0010PMR For Centrifugal Pumps For General Services | 2022-09-11 | 0
TBE For Centrifugal Pumps For General Services | BK-GCS-PEDCO-120-ME-TB-0010 | BK-GCS-PEDCO-120-ME-TB-0010TBE For Centrifugal Pumps For General Services | 0 | 0
PMR For Fire Water Pump | BK-GCS-PEDCO-120-ME-MR-0011 | BK-GCS-PEDCO-120-ME-MR-0011PMR For Fire Water Pump | 2022-07-31 | 0
TBE For Fire Water Pump | BK-GCS-PEDCO-120-ME-TB-0011 | BK-GCS-PEDCO-120-ME-TB-0011TBE For Fire Water Pump | 0 | 0
PMR For Flare Packages | BK-GCS-PEDCO-120-ME-MR-0012 | BK-GCS-PEDCO-120-ME-MR-0012PMR For Flare Packages | 0 | 0
TBE For Flare Packages | BK-GCS-PEDCO-120-ME-TB-0012 | BK-GCS-PEDCO-120-ME-TB-0012TBE For Flare Packages | 0 | 0
PMR For Overhead Travelling Cranes | BK-GCS-PEDCO-120-ME-MR-0013 | BK-GCS-PEDCO-120-ME-MR-0013PMR For Overhead Travelling Cranes | 2022-09-07 | 0
TBE For Overhead Travelling Cranes | BK-GCS-PEDCO-120-ME-TB-0013 | BK-GCS-PEDCO-120-ME-TB-0013TBE For Overhead Travelling Cranes | 0 | 0
PMR For Main HVAC Equipment | BK-GCS-PEDCO-120-HV-MR-0001 | BK-GCS-PEDCO-120-HV-MR-0001PMR For Main HVAC Equipment | 0 | 0
TBE For Main HVAC Equipment | BK-GCS-PEDCO-120-HV-TB-0001 | BK-GCS-PEDCO-120-HV-TB-0001TBE For Main HVAC Equipment | 0 | 0
PMR For Pipes | BK-GCS-PEDCO-120-PI-MR-0001 | BK-GCS-PEDCO-120-PI-MR-0001PMR For Pipes | 2022-11-21 | 0
TBE For Pipes | BK-GCS-PEDCO-120-PI-TB-0001 | BK-GCS-PEDCO-120-PI-TB-0001TBE For Pipes | 0 | 0
PMR For Fittings | BK-GCS-PEDCO-120-PI-MR-0002 | BK-GCS-PEDCO-120-PI-MR-0002PMR For Fittings | 2022-11-21 | 0
TBE For Fitting | BK-GCS-PEDCO-120-PI-TB-0002 | BK-GCS-PEDCO-120-PI-TB-0002TBE For Fitting | 0 | 0
PMR For Flanges | BK-GCS-PEDCO-120-PI-MR-0003 | BK-GCS-PEDCO-120-PI-MR-0003PMR For Flanges | 2022-11-21 | 0
TBE For Flanges | BK-GCS-PEDCO-120-PI-TB-0003 | BK-GCS-PEDCO-120-PI-TB-0003TBE For Flanges | 0 | 0
PMR For Manual Valves | BK-GCS-PEDCO-120-PI-MR-0004 | BK-GCS-PEDCO-120-PI-MR-0004PMR For Manual Valves | 2022-11-21 | 0
TBE For Manual Valves | BK-GCS-PEDCO-120-PI-TB-0004 | BK-GCS-PEDCO-120-PI-TB-0004TBE For Manual Valves | 0 | 0
PMR For Gaskets | BK-GCS-PEDCO-120-PI-MR-0005 | BK-GCS-PEDCO-120-PI-MR-0005PMR For Gaskets | 2022-11-21 | 0
TBE For Gaskets | BK-GCS-PEDCO-120-PI-TB-0005 | BK-GCS-PEDCO-120-PI-TB-0005TBE For Gaskets | 0 | 0
PMR For Bolt/Nuts | BK-GCS-PEDCO-120-PI-MR-0006 | BK-GCS-PEDCO-120-PI-MR-0006PMR For Bolt/Nuts | 0 | 0
PMR For Bolt/Nuts | BK-GCS-PEDCO-120-PI-TB-0006 | BK-GCS-PEDCO-120-PI-TB-0006PMR For Bolt/Nuts | 0 | 0
PMR For Insulation Joints | BK-GCS-PEDCO-120-PI-MR-0007 | BK-GCS-PEDCO-120-PI-MR-0007PMR For Insulation Joints | 0 | 0
TBE For Insulation Joints | BK-GCS-PEDCO-120-PI-TB-0007 | BK-GCS-PEDCO-120-PI-TB-0007TBE For Insulation Joints | 0 | 0
PMR For Strainers | BK-GCS-PEDCO-120-PI-MR-0008 | BK-GCS-PEDCO-120-PI-MR-0008PMR For Strainers | 0 | 0
TBE For Strainers | BK-GCS-PEDCO-120-PI-TB-0008 | BK-GCS-PEDCO-120-PI-TB-0008TBE For Strainers | 0 | 0
PMR For Special Pipe Supports | BK-GCS-PEDCO-120-PI-MR-0009 | BK-GCS-PEDCO-120-PI-MR-0009PMR For Special Pipe Supports | 0 | 0
TBE For Special Pipe Supports | BK-GCS-PEDCO-120-PI-TB-0009 | BK-GCS-PEDCO-120-PI-TB-0009TBE For Special Pipe Supports | 0 | 0
PMR For Insulation | BK-GCS-PEDCO-120-PI-MR-0010 | BK-GCS-PEDCO-120-PI-MR-0010PMR For Insulation | 2022-08-10 | 0
TBE For Insulation | BK-GCS-PEDCO-120-PI-TB-0010 | BK-GCS-PEDCO-120-PI-TB-0010TBE For Insulation | 0 | 0
PMR For Painting | BK-GCS-PEDCO-120-PI-MR-0011 | BK-GCS-PEDCO-120-PI-MR-0011PMR For Painting | 0 | 0
TBE For Painting | BK-GCS-PEDCO-120-PI-TB-0011 | BK-GCS-PEDCO-120-PI-TB-0011TBE For Painting | 0 | 0
PMR For Coating of Underground Piping | BK-GCS-PEDCO-120-PI-MR-0012 | BK-GCS-PEDCO-120-PI-MR-0012PMR For Coating of Underground Piping | 0 | 0
TBE For Coating of Underground Piping | BK-GCS-PEDCO-120-PI-TB-0012 | BK-GCS-PEDCO-120-PI-TB-0012TBE For Coating of Underground Piping | 0 | 0
PMR For Control System/Console/Furniture | BK-GCS-PEDCO-120-IN-MR-0001 | BK-GCS-PEDCO-120-IN-MR-0001PMR For Control System/Console/Furniture | 2022-08-22 | 0
TBE For Control System/Console/Furniture | BK-GCS-PEDCO-120-IN-TB-0001 | BK-GCS-PEDCO-120-IN-TB-0001TBE For Control System/Console/Furniture | 0 | 0
PMR For ESD System | BK-GCS-PEDCO-120-IN-MR-0002 | BK-GCS-PEDCO-120-IN-MR-0002PMR For ESD System | 2022-08-22 | 0
TBE For ESD System | BK-GCS-PEDCO-120-IN-TB-0002 | BK-GCS-PEDCO-120-IN-TB-0002TBE For ESD System | 0 | 0
PMR For F&G System | BK-GCS-PEDCO-120-IN-MR-0003 | BK-GCS-PEDCO-120-IN-MR-0003PMR For F&G System | 0 | 0
TBE For F&G System | BK-GCS-PEDCO-120-IN-TB-0003 | BK-GCS-PEDCO-120-IN-TB-0003TBE For F&G System | 0 | 0
PMR For On/off & Shutdown Valves | BK-GCS-PEDCO-120-IN-MR-0004 | BK-GCS-PEDCO-120-IN-MR-0004PMR For On/off & Shutdown Valves | 2022-08-23 | 0
TBE For On/off & Shutdown Valves | BK-GCS-PEDCO-120-IN-TB-0004 | BK-GCS-PEDCO-120-IN-TB-0004TBE For On/off & Shutdown Valves | 0 | 0
PMR For Control Valves | BK-GCS-PEDCO-120-IN-MR-0005 | BK-GCS-PEDCO-120-IN-MR-0005PMR For Control Valves | 2022-08-22 | 0
TBE For Control Valves | BK-GCS-PEDCO-120-IN-TB-0005 | BK-GCS-PEDCO-120-IN-TB-0005TBE For Control Valves | 0 | 0
PMR For Pressure Safety Valves (PSV) | BK-GCS-PEDCO-120-IN-MR-0006 | BK-GCS-PEDCO-120-IN-MR-0006PMR For Pressure Safety Valves (PSV) | 2022-08-22 | 0
TBE For Pressure Safety Valves (PSV) | BK-GCS-PEDCO-120-IN-TB-0006 | BK-GCS-PEDCO-120-IN-TB-0006TBE For Pressure Safety Valves (PSV) | 0 | 0
PMR For F&G Devices | BK-GCS-PEDCO-120-IN-MR-0007 | BK-GCS-PEDCO-120-IN-MR-0007PMR For F&G Devices | 0 | 0
TBE For F&G Devices | BK-GCS-PEDCO-120-IN-TB-0007 | BK-GCS-PEDCO-120-IN-TB-0007TBE For F&G Devices | 0 | 0
PMR For Corrosion Probe/Coupon | BK-GCS-PEDCO-120-IN-MR-0008 | BK-GCS-PEDCO-120-IN-MR-0008PMR For Corrosion Probe/Coupon | 2022-08-29 | 0
TBE For Corrosion Probe/Coupon | BK-GCS-PEDCO-120-IN-TB-0008 | BK-GCS-PEDCO-120-IN-TB-0008TBE For Corrosion Probe/Coupon | 0 | 0
PMR For Orifice and Restriction Orifice Plate | BK-GCS-PEDCO-120-IN-MR-0009 | BK-GCS-PEDCO-120-IN-MR-0009PMR For Orifice and Restriction Orifice Plate | 2022-08-27 | 0
TBE For Orifice and Restriction Orifice Plate | BK-GCS-PEDCO-120-IN-TB-0009 | BK-GCS-PEDCO-120-IN-TB-0009TBE For Orifice and Restriction Orifice Plate | 0 | 0
PMR For Differential Pressure/Pressure Gauge | BK-GCS-PEDCO-120-IN-MR-0010 | BK-GCS-PEDCO-120-IN-MR-0010PMR For Differential Pressure/Pressure Gauge | 2022-08-27 | 0
TBE For Differential Pressure/Pressure Gauge | BK-GCS-PEDCO-120-IN-TB-0010 | BK-GCS-PEDCO-120-IN-TB-0010TBE For Differential Pressure/Pressure Gauge | 0 | 0
PMR For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter | BK-GCS-PEDCO-120-IN-MR-0011 | BK-GCS-PEDCO-120-IN-MR-0011PMR For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter | 2022-08-23 | 0
TBE For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter" | BK-GCS-PEDCO-120-IN-TB-0011 | BK-GCS-PEDCO-120-IN-TB-0011TBE For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter" | 0 | 0
PMR For Pressure/ Differential Pressure Switch | BK-GCS-PEDCO-120-IN-MR-0012 | BK-GCS-PEDCO-120-IN-MR-0012PMR For Pressure/ Differential Pressure Switch | 0 | 0
TBE For Pressure/ Differential Pressure Switch | BK-GCS-PEDCO-120-IN-TB-0012 | BK-GCS-PEDCO-120-IN-TB-0012TBE For Pressure/ Differential Pressure Switch | 0 | 0
PMR For Temperature Gauge | BK-GCS-PEDCO-120-IN-MR-0013 | BK-GCS-PEDCO-120-IN-MR-0013PMR For Temperature Gauge | 2022-08-27 | 0
TBE For Temperature Gauge | BK-GCS-PEDCO-120-IN-TB-0013 | BK-GCS-PEDCO-120-IN-TB-0013TBE For Temperature Gauge | 0 | 0
PMR For Temperature Transmitter/Switch | BK-GCS-PEDCO-120-IN-MR-0014 | BK-GCS-PEDCO-120-IN-MR-0014PMR For Temperature Transmitter/Switch | 2022-08-27 | 0
TBE For Temperature Transmitter/Switch | BK-GCS-PEDCO-120-IN-TB-0014 | BK-GCS-PEDCO-120-IN-TB-0014TBE For Temperature Transmitter/Switch | 0 | 0
PMR For Level Gauge | BK-GCS-PEDCO-120-IN-MR-0015 | BK-GCS-PEDCO-120-IN-MR-0015PMR For Level Gauge | 2022-08-27 | 0
TBE For Level Gauge | BK-GCS-PEDCO-120-IN-TB-0015 | BK-GCS-PEDCO-120-IN-TB-0015TBE For Level Gauge | 0 | 0
PMR For Level Switch | BK-GCS-PEDCO-120-IN-MR-0016 | BK-GCS-PEDCO-120-IN-MR-0016PMR For Level Switch | 2022-08-27 | 0
TBE For Level Switch | BK-GCS-PEDCO-120-IN-TB-0016 | BK-GCS-PEDCO-120-IN-TB-0016TBE For Level Switch | 0 | 0
PMR For Displacer Level Transmitter | BK-GCS-PEDCO-120-IN-MR-0017 | BK-GCS-PEDCO-120-IN-MR-0017PMR For Displacer Level Transmitter | 2022-08-22 | 0
TBE For Displacer Level Transmitter | BK-GCS-PEDCO-120-IN-TB-0017 | BK-GCS-PEDCO-120-IN-TB-0017TBE For Displacer Level Transmitter | 0 | 0
PMR For Rotameter | BK-GCS-PEDCO-120-IN-MR-0019 | BK-GCS-PEDCO-120-IN-MR-0019PMR For Rotameter | 0 | 0
TBE For Rotameter | BK-GCS-PEDCO-120-IN-TB-0019 | BK-GCS-PEDCO-120-IN-TB-0019TBE For Rotameter | 0 | 0
PMR For Instrument/F&G cable | BK-GCS-PEDCO-120-IN-MR-0020 | BK-GCS-PEDCO-120-IN-MR-0020PMR For Instrument/F&G cable | 0 | 0
TBE For Instrument/F&G cable | BK-GCS-PEDCO-120-IN-TB-0020 | BK-GCS-PEDCO-120-IN-TB-0020TBE For Instrument/F&G cable | 0 | 0
PMR For Instrument Cable Tray | BK-GCS-PEDCO-120-IN-MR-0021 | BK-GCS-PEDCO-120-IN-MR-0021PMR For Instrument Cable Tray | 0 | 0
TBE For Instrument Cable Tray | BK-GCS-PEDCO-120-IN-TB-0021 | BK-GCS-PEDCO-120-IN-TB-0021TBE For Instrument Cable Tray | 0 | 0
PMR For Instrument/F&G Junction box and Gland | BK-GCS-PEDCO-120-IN-MR-0022 | BK-GCS-PEDCO-120-IN-MR-0022PMR For Instrument/F&G Junction box and Gland | 0 | 0
TBE For Instrument/F&G Junction box and Gland | BK-GCS-PEDCO-120-IN-TB-0022 | BK-GCS-PEDCO-120-IN-TB-0022TBE For Instrument/F&G Junction box and Gland | 0 | 0
PMR For Instrument Tube and Fitting | BK-GCS-PEDCO-120-IN-MR-0023 | BK-GCS-PEDCO-120-IN-MR-0023PMR For Instrument Tube and Fitting | 0 | 0
TBE For Instrument Tube and Fitting | BK-GCS-PEDCO-120-IN-TB-0023 | BK-GCS-PEDCO-120-IN-TB-0023TBE For Instrument Tube and Fitting | 0 | 0
PMR For Instrument Installation Accessories | BK-GCS-PEDCO-120-IN-MR-0024 | BK-GCS-PEDCO-120-IN-MR-0024PMR For Instrument Installation Accessories | 0 | 0
TBE For Instrument Installation Accessories | BK-GCS-PEDCO-120-IN-TB-0024 | BK-GCS-PEDCO-120-IN-TB-0024TBE For Instrument Installation Accessories | 0 | 0
PMR For CCTV System | BK-GCS-PEDCO-120-IN-MR-0025 | BK-GCS-PEDCO-120-IN-MR-0025PMR For CCTV System | 2021-12-20 | 0
TBE For CCTV System | BK-GCS-PEDCO-120-IN-TB-0025 | BK-GCS-PEDCO-120-IN-TB-0025TBE For CCTV System | 2022-05-02 | 2022-12-20
PMR For IRP Panel | BK-GCS-PEDCO-120-IN-MR-0026 | BK-GCS-PEDCO-120-IN-MR-0026PMR For IRP Panel | 0 | 0
TBE For IRP Panel | BK-GCS-PEDCO-120-IN-TB-0026 | BK-GCS-PEDCO-120-IN-TB-0026TBE For IRP Panel | 0 | 0
PMR For Total Flooding System | BK-GCS-PEDCO-120-SA-MR-0001 | BK-GCS-PEDCO-120-SA-MR-0001PMR For Total Flooding System | 2022-05-14 | 0
TBE For Total Flooding System | BK-GCS-PEDCO-120-SA-TB-0001 | BK-GCS-PEDCO-120-SA-TB-0001TBE For Total Flooding System | 0 | 0
PMR For Deluge Valve & Water Spray | BK-GCS-PEDCO-120-SA-MR-0002 | BK-GCS-PEDCO-120-SA-MR-0002PMR For Deluge Valve & Water Spray | 2022-06-14 | 2022-12-20
TBE For Deluge Valve & Water Spray | BK-GCS-PEDCO-120-SA-TB-0002 | BK-GCS-PEDCO-120-SA-TB-0002TBE For Deluge Valve & Water Spray | 0 | 0
PMR For Safety Equipment | BK-GCS-PEDCO-120-SA-MR-0003 | BK-GCS-PEDCO-120-SA-MR-0003PMR For Safety Equipment | 2022-06-14 | 2022-12-20
TBE For Safety Equipment | BK-GCS-PEDCO-120-SA-TB-0003 | BK-GCS-PEDCO-120-SA-TB-0003TBE For Safety Equipment | 0 | 0
PMR For Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-MR-0004 | BK-GCS-PEDCO-120-SA-MR-0004PMR For Fire Fighting Equipment | 2022-06-11 | 2022-12-20
TBE For Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-TB-0004 | BK-GCS-PEDCO-120-SA-TB-0004TBE For Fire Fighting Equipment | 0 | 0
PMR For Safety Signs | BK-GCS-PEDCO-120-SA-MR-0005 | BK-GCS-PEDCO-120-SA-MR-0005PMR For Safety Signs | 2022-06-14 | 2022-12-20
TBE For Safety Signs | BK-GCS-PEDCO-120-SA-TB-0005 | BK-GCS-PEDCO-120-SA-TB-0005TBE For Safety Signs | 0 | 0
PMR For Transformers | BK-GCS-PEDCO-120-EL-MR-0001 | BK-GCS-PEDCO-120-EL-MR-0001PMR For Transformers | 2022-08-09 | 0
TBE For Transformers | BK-GCS-PEDCO-120-EL-TB-0001 | BK-GCS-PEDCO-120-EL-TB-0001TBE For Transformers | 0 | 0
PMR For LV Switchgear, MCC | BK-GCS-PEDCO-120-EL-MR-0002 | BK-GCS-PEDCO-120-EL-MR-0002PMR For LV Switchgear, MCC | 2022-09-05 | 0
TBE For LV Switchgear, MCC | BK-GCS-PEDCO-120-EL-TB-0002 | BK-GCS-PEDCO-120-EL-TB-0002TBE For LV Switchgear, MCC | 0 | 0
PMR For Existent MV Switchgear Expansion & RCP | BK-GCS-PEDCO-120-EL-MR-0003 | BK-GCS-PEDCO-120-EL-MR-0003PMR For Existent MV Switchgear Expansion & RCP | 0 | 0
TBE For Existent MV Switchgear Expansion & RCP | BK-GCS-PEDCO-120-EL-TB-0003 | BK-GCS-PEDCO-120-EL-TB-0003TBE For Existent MV Switchgear Expansion & RCP | 0 | 0
PMR For Emergency Diesel Generator | BK-GCS-PEDCO-120-EL-MR-0004 | BK-GCS-PEDCO-120-EL-MR-0004PMR For Emergency Diesel Generator | 0 | 0
TBE For Emergency Diesel Generator | BK-GCS-PEDCO-120-EL-TB-0004 | BK-GCS-PEDCO-120-EL-TB-0004TBE For Emergency Diesel Generator | 0 | 0
PMR For UPS System | BK-GCS-PEDCO-120-EL-MR-0005 | BK-GCS-PEDCO-120-EL-MR-0005PMR For UPS System | 2022-08-03 | 0
TBE For UPS System | BK-GCS-PEDCO-120-EL-TB-0005 | BK-GCS-PEDCO-120-EL-TB-0005TBE For UPS System | 0 | 0
PMR For DC Charger | BK-GCS-PEDCO-120-EL-MR-0006 | BK-GCS-PEDCO-120-EL-MR-0006PMR For DC Charger | 2022-08-03 | 0
TBE For DC Charger | BK-GCS-PEDCO-120-EL-TB-0006 | BK-GCS-PEDCO-120-EL-TB-0006TBE For DC Charger | 0 | 0
PMR For Lighting & Distribution Panels | BK-GCS-PEDCO-120-EL-MR-0007 | BK-GCS-PEDCO-120-EL-MR-0007PMR For Lighting & Distribution Panels | 0 | 0
TBE For Lighting & Distribution Panels | BK-GCS-PEDCO-120-EL-TB-0007 | BK-GCS-PEDCO-120-EL-TB-0007TBE For Lighting & Distribution Panels | 0 | 0
PMR For Lighting and Small Power Equipment | BK-GCS-PEDCO-120-EL-MR-0008 | BK-GCS-PEDCO-120-EL-MR-0008PMR For Lighting and Small Power Equipment | 0 | 0
TBE For Lighting and Small Power Equipment | BK-GCS-PEDCO-120-EL-TB-0008 | BK-GCS-PEDCO-120-EL-TB-0008TBE For Lighting and Small Power Equipment | 0 | 0
PMR For Earthing & Lightning System | BK-GCS-PEDCO-120-EL-MR-0009 | BK-GCS-PEDCO-120-EL-MR-0009PMR For Earthing & Lightning System | 0 | 0
TBE For Earthing & Lightning System | BK-GCS-PEDCO-120-EL-TB-0009 | BK-GCS-PEDCO-120-EL-TB-0009TBE For Earthing & Lightning System | 0 | 0
PMR For Local Control Station (LCS) | BK-GCS-PEDCO-120-EL-MR-0010 | BK-GCS-PEDCO-120-EL-MR-0010PMR For Local Control Station (LCS) | 2022-06-27 | 2022-12-20
TBE For Local Control Station (LCS) | BK-GCS-PEDCO-120-EL-TB-0010 | BK-GCS-PEDCO-120-EL-TB-0010TBE For Local Control Station (LCS) | 0 | 0
PMR For Capacitor Bank | BK-GCS-PEDCO-120-EL-MR-0011 | BK-GCS-PEDCO-120-EL-MR-0011PMR For Capacitor Bank | 0 | 0
TBE For Capacitor Bank | BK-GCS-PEDCO-120-EL-TB-0011 | BK-GCS-PEDCO-120-EL-TB-0011TBE For Capacitor Bank | 0 | 0
PMR For NGR | BK-GCS-PEDCO-120-EL-MR-0012 | BK-GCS-PEDCO-120-EL-MR-0012PMR For NGR | 0 | 0
TBE For NGR | BK-GCS-PEDCO-120-EL-TB-0012 | BK-GCS-PEDCO-120-EL-TB-0012TBE For NGR | 0 | 0
PMR For Cathodic Protection System | BK-GCS-PEDCO-120-EL-MR-0013 | BK-GCS-PEDCO-120-EL-MR-0013PMR For Cathodic Protection System | 0 | 0
TBE For Cathodic Protection System | BK-GCS-PEDCO-120-EL-TB-0013 | BK-GCS-PEDCO-120-EL-TB-0013TBE For Cathodic Protection System | 0 | 0
PMR For Power & Control Cables | BK-GCS-PEDCO-120-EL-MR-0014 | BK-GCS-PEDCO-120-EL-MR-0014PMR For Power & Control Cables | 0 | 0
TBE For Power & Control Cables | BK-GCS-PEDCO-120-EL-TB-0014 | BK-GCS-PEDCO-120-EL-TB-0014TBE For Power & Control Cables | 0 | 0
PMR For Tray/Ladder and Accessories | BK-GCS-PEDCO-120-EL-MR-0015 | BK-GCS-PEDCO-120-EL-MR-0015PMR For Tray/Ladder and Accessories | 0 | 0
TBE For Tray/Ladder and Accessories | BK-GCS-PEDCO-120-EL-TB-0015 | BK-GCS-PEDCO-120-EL-TB-0015TBE For Tray/Ladder and Accessories | 0 | 0
PMR For Electrical Bulk Items | BK-GCS-PEDCO-120-EL-MR-0016 | BK-GCS-PEDCO-120-EL-MR-0016PMR For Electrical Bulk Items | 0 | 0
TBE For Electrical Bulk Items | BK-GCS-PEDCO-120-EL-TB-0016 | BK-GCS-PEDCO-120-EL-TB-0016TBE For Electrical Bulk Items | 0 | 0
PMR For UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-MR-0017 | BK-GCS-PEDCO-120-EL-MR-0017PMR For UPS of CCTV in Desalting, Production & CS Unit | 0 | 0
TBE for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-TB-0017 | BK-GCS-PEDCO-120-EL-TB-0017TBE for UPS of CCTV in Desalting, Production & CS Unit | 0 | 0
PMR For CCTV System | BK-GCS-PEDCO-120-TE-MR-0001 | BK-GCS-PEDCO-120-TE-MR-0001PMR For CCTV System | 0 | 0
TBE For CCTV System | BK-GCS-PEDCO-120-TE-TB-0001 | BK-GCS-PEDCO-120-TE-TB-0001TBE For CCTV System | 0 | 0
PMR For PAGA System | BK-GCS-PEDCO-120-TE-MR-0002 | BK-GCS-PEDCO-120-TE-MR-0002PMR For PAGA System | 0 | 0
TBE For PAGA System | BK-GCS-PEDCO-120-TE-TB-0002 | BK-GCS-PEDCO-120-TE-TB-0002TBE For PAGA System | 0 | 0
PMR For PABX System | BK-GCS-PEDCO-120-TE-MR-0003 | BK-GCS-PEDCO-120-TE-MR-0003PMR For PABX System | 0 | 0
TBE For PABX System | BK-GCS-PEDCO-120-TE-TB-0003 | BK-GCS-PEDCO-120-TE-TB-0003TBE For PABX System | 0 | 0
PMR For Radio System | BK-GCS-PEDCO-120-TE-MR-0004 | BK-GCS-PEDCO-120-TE-MR-0004PMR For Radio System | 2021-12-20 | 0
TBE For Radio System | BK-GCS-PEDCO-120-TE-TB-0004 | BK-GCS-PEDCO-120-TE-TB-0004TBE For Radio System | 0 | 0
PMR For Telecomm. Cable | BK-GCS-PEDCO-120-TE-MR-0005 | BK-GCS-PEDCO-120-TE-MR-0005PMR For Telecomm. Cable | 0 | 0
TBE For Telecomm. Cable | BK-GCS-PEDCO-120-TE-TB-0005 | BK-GCS-PEDCO-120-TE-TB-0005TBE For Telecomm. Cable | 0 | 0
PMR For Telecommunication Tower | BK-GCS-PEDCO-120-TE-MR-0006 | BK-GCS-PEDCO-120-TE-MR-0006PMR For Telecommunication Tower | 0 | 0
TBE For Telecommunication Tower | BK-GCS-PEDCO-120-TE-TB-0006 | BK-GCS-PEDCO-120-TE-TB-0006TBE For Telecommunication Tower | 0 | 0
PMR For Steel Structure Items | BK-GCS-PEDCO-120-ST-MR-0001 | BK-GCS-PEDCO-120-ST-MR-0001PMR For Steel Structure Items | 0 | 0
TBE For Steel Structure Items | BK-GCS-PEDCO-120-ST-TB-0001 | BK-GCS-PEDCO-120-ST-TB-0001TBE For Steel Structure Items | 0 | 0
PMR For Anchor Bolts | BK-GCS-PEDCO-120-ST-MR-0002 | BK-GCS-PEDCO-120-ST-MR-0002PMR For Anchor Bolts | 0 | 0
TBE For Anchor Bolts | BK-GCS-PEDCO-120-ST-TB-0002 | BK-GCS-PEDCO-120-ST-TB-0002TBE For Anchor Bolts | 0 | 0
PMR For Blast Proof Doors | BK-GCS-PEDCO-120-ST-MR-0003 | BK-GCS-PEDCO-120-ST-MR-0003PMR For Blast Proof Doors | 0 | 0
TBE For Blast Proof Doors | BK-GCS-PEDCO-120-ST-TB-0003 | BK-GCS-PEDCO-120-ST-TB-0003TBE For Blast Proof Doors | 0 | 0
Pre-Commissioning, Commissioning & Startup Procedure | BK-GCS-PEDCO-120-CO-PR-0001 | BK-GCS-PEDCO-120-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure | 0 | 0
Technical/Site Queries | BK-GCS-PEDCO-120-GE-TQ-0001 | BK-GCS-PEDCO-120-GE-TQ-0001Technical/Site Queries | 0 | 0
As-Built Document Booklets | BK-GCS-PEDCO-120-GE-DO-0001 | BK-GCS-PEDCO-120-GE-DO-0001As-Built Document Booklets | 0 | 0
Operating Manual | BK-GCS-PEDCO-120-GE-ML-0001 | BK-GCS-PEDCO-120-GE-ML-0001Operating Manual | 0 | 0
As-Built Document Booklets | BK-GCS-PEDCO-120-GE-DO-0001 | BK-GCS-PEDCO-120-GE-DO-0001As-Built Document Booklets | 0 | 0
Final Engineering Dossier | BK-GCS-PEDCO-120-GE-DO-0002 | BK-GCS-PEDCO-120-GE-DO-0002Final Engineering Dossier | 0 | 0
Civil and Structural drawings - BK14 | BK-BK14-PEDCO-110-CV-DW-0001 | BK-BK14-PEDCO-110-CV-DW-0001Civil and Structural drawings - BK14 |  | 2022-12-20
General Civil Layout - BK14 | BK-BK14-PEDCO-110-CV-PY-0001 | BK-BK14-PEDCO-110-CV-PY-0001General Civil Layout - BK14 |  | 2022-12-20
Rough Grading Plans -BK14 | BK-BK14-PEDCO-110-CV-PY-0003 | BK-BK14-PEDCO-110-CV-PY-0003Rough Grading Plans -BK14 |  | 2022-12-20
Formulas:
Actual Start Date = VLOOKUP([Doc. No.],DCI!$L:$BV,62,0)
Actual Finish Date = VLOOKUP([Doc. No.],DCI!$L:$BV,63,0)
Note on E2: md:تاريخ فرضي
Note on E3: md:تاريخ فرضي
Note on E7: md:تاريخ فرضي
Note on E12: md:تاريخ فرضي
Note on E13: md:تاريخ فرضي
Note on E21: md:تاريخ فرضي
Note on E23: md:تاريخ فرضي
Note on E24: md:تاريخ فرضي
Note on E30: md:تاريخ فرضي
Note on E60: md:تاريخ فرضي
Note on E61: md:تاريخ فرضي
Note on E63: md:تاريخ فرضي
Note on E64: md:تاريخ فرضي
Note on E65: md:تاريخ فرضي
Note on E66: md:تاريخ فرضي
Note on E67: md:تاريخ فرضي
Note on E70: md:تاريخ فرضي
Note on E71: md:تاريخ فرضي
Note on E72: md:تاريخ فرضي
Note on E75: md:تاريخ فرضي
Note on E76: md:تاريخ فرضي
Note on E77: md:تاريخ فرضي
Note on E79: md:تاريخ فرضي
Note on E80: md:تاريخ فرضي
Note on E82: md:تاريخ فرضي
Note on E83: md:تاريخ فرضي
Note on E84: md:تاريخ فرضي
Note on E85: md:تاريخ فرضي
Note on E86: md:تاريخ فرضي
Note on E87: md:تاريخ فرضي
Note on E88: md:تاريخ فرضي
Note on E89: md:تاريخ فرضي
Note on E90: md:تاريخ فرضي
Note on E91: md:تاريخ فرضي
Note on E94: md:تاريخ فرضي
Note on E100: md:تاريخ فرضي
Note on E101: md:تاريخ فرضي
Note on E102: md:تاريخ فرضي
Note on E103: md:تاريخ فرضي
Note on E106: md:تاريخ فرضي
Note on E107: md:تاريخ فرضي
Note on E108: md:تاريخ فرضي
Note on E109: md:تاريخ فرضي
Note on E110: md:تاريخ فرضي
Note on E111: md:تاريخ فرضي
Note on E113: md:تاريخ فرضي
Note on E114: md:تاريخ فرضي
Note on E115: md:تاريخ فرضي
Note on E123: md:تاريخ فرضي
Note on E126: md:تاريخ فرضي
Note on E129: md:تاريخ فرضي
Note on E132: md:تاريخ فرضي
Note on E133: md:تاريخ فرضي
Note on E134: md:تاريخ فرضي
Note on E135: md:تاريخ فرضي
Note on E136: md:تاريخ فرضي
Note on E137: md:تاريخ فرضي
Note on E140: md:تاريخ فرضي
Note on E148: md:تاريخ فرضي
Note on E152: md:تاريخ فرضي
Note on E153: md:تاريخ فرضي
Note on E158: md:تاريخ فرضي
Note on E159: md:تاريخ فرضي
Note on E161: md:تاريخ فرضي
Note on E162: md:تاريخ فرضي
Note on E166: md:تاريخ فرضي
Note on E174: md:تاريخ فرضي
Note on E176: md:تاريخ فرضي
Note on E177: md:تاريخ فرضي
Note on E178: md:تاريخ فرضي
Note on E185: md:تاريخ فرضي
Note on E187: md:تاريخ فرضي
Note on E189: md:تاريخ فرضي
Note on E191: md:تاريخ فرضي
Note on E192: md:تاريخ فرضي
Note on E193: md:تاريخ فرضي
Note on E198: md:تاريخ فرضي
Note on E200: md:تاريخ فرضي
Note on E202: md:تاريخ فرضي
Note on E203: md:تاريخ فرضي
Note on E204: md:تاريخ فرضي
Note on E206: md:تاريخ فرضي
Note on E207: md:تاريخ فرضي
Note on E210: md:تاريخ فرضي
Note on E211: md:تاريخ فرضي
Note on E212: md:تاريخ فرضي
Note on E219: md:تاريخ فرضي
Note on E221: md:تاريخ فرضي
Note on E223: md:تاريخ فرضي
Note on E224: md:تاريخ فرضي
Note on E225: md:تاريخ فرضي
Note on E227: md:تاريخ فرضي
Note on E233: md:تاريخ فرضي
Note on E235: md:تاريخ فرضي
Note on E237: md:تاريخ فرضي
Note on E247: md:تاريخ فرضي
Note on E253: md:تاريخ فرضي
Note on E262: md:تاريخ فرضي
Note on E269: md:تاريخ فرضي
Note on E273: md:تاريخ فرضي
Note on E275: md:تاريخ فرضي
Note on E276: md:تاريخ فرضي
Note on E277: md:تاريخ فرضي
Note on E278: md:تاريخ فرضي
Note on E279: md:تاريخ فرضي
Note on E280: md:تاريخ فرضي
Note on E281: md:تاريخ فرضي
Note on E282: md:تاريخ فرضي
Note on E284: md:تاريخ فرضي
Note on E285: md:تاريخ فرضي
Note on E286: md:تاريخ فرضي
Note on E287: md:تاريخ فرضي
Note on E289: md:تاريخ فرضي
Note on E290: md:تاريخ فرضي
Note on E291: md:تاريخ فرضي
Note on E292: md:تاريخ فرضي
Note on E294: md:تاريخ فرضي
Note on E305: md:تاريخ فرضي
Note on E313: md:تاريخ فرضي
Note on E314: md:تاريخ فرضي
Note on E322: md:تاريخ فرضي
Note on E323: md:تاريخ فرضي
Note on E328: md:تاريخ فرضي
Note on E330: md:تاريخ فرضي
Note on E331: md:تاريخ فرضي
Note on E332: md:تاريخ فرضي
Note on E333: md:تاريخ فرضي
Note on E334: md:تاريخ فرضي
Note on E335: md:تاريخ فرضي
Note on E337: md:تاريخ فرضي
Note on E338: md:تاريخ فرضي
Note on E344: md:تاريخ فرضي
Note on E348: md:تاريخ فرضي
Note on E350: md:تاريخ فرضي
Note on E352: md:تاريخ فرضي
Note on E353: md:تاريخ فرضي
Note on E355: md:تاريخ فرضي
Note on E357: md:تاريخ فرضي
Note on E362: md:تاريخ فرضي
Note on E363: md:تاريخ فرضي
Note on E364: md:تاريخ فرضي
Note on E365: md:تاريخ فرضي
Note on E367: md:تاريخ فرضي
Note on E368: md:تاريخ فرضي
Note on E369: md:تاريخ فرضي
Note on E370: md:تاريخ فرضي
Note on E371: md:تاريخ فرضي
Note on E372: md:تاريخ فرضي
Note on E374: md:تاريخ فرضي
Note on E375: md:تاريخ فرضي
Note on E376: md:تاريخ فرضي
Note on E377: md:تاريخ فرضي
Note on E378: md:تاريخ فرضي
Note on E379: md:تاريخ فرضي
Note on E380: md:تاريخ فرضي
Note on E381: md:تاريخ فرضي
Note on E385: md:تاريخ فرضي
Note on E386: md:تاريخ فرضي
Note on E387: md:تاريخ فرضي
Note on E390: md:تاريخ فرضي
Note on E391: md:تاريخ فرضي
Note on E392: md:تاريخ فرضي
Note on E393: md:تاريخ فرضي
Note on E394: md:تاريخ فرضي
Note on E396: md:تاريخ فرضي
Note on E397: md:تاريخ فرضي
Note on E398: md:تاريخ فرضي
Note on E399: md:تاريخ فرضي
Note on E400: md:تاريخ فرضي
Note on E401: md:تاريخ فرضي
Note on E403: md:تاريخ فرضي
Note on E404: md:تاريخ فرضي
Note on E408: md:تاريخ فرضي
Note on E409: md:تاريخ فرضي
Note on E411: md:تاريخ فرضي
Note on E414: md:تاريخ فرضي
Note on E415: md:تاريخ فرضي
Note on E416: md:تاريخ فرضي
Note on E418: md:تاريخ فرضي
Note on E419: md:تاريخ فرضي
Note on E422: md:تاريخ فرضي
Note on E424: md:تاريخ فرضي
Note on E425: md:تاريخ فرضي
Note on E435: md:تاريخ فرضي
Note on E436: md:تاريخ فرضي
Note on E445: md:تاريخ فرضي
Note on E449: md:تاريخ فرضي
Note on E454: md:تاريخ فرضي
Note on E455: md:تاريخ فرضي
Note on E456: md:تاريخ فرضي
Note on E457: md:تاريخ فرضي
Note on E462: md:تاريخ فرضي
Note on E464: md:تاريخ فرضي
Note on E466: md:تاريخ فرضي
Note on E471: md:تاريخ فرضي
Note on E472: md:تاريخ فرضي
Note on E475: md:تاريخ فرضي
Note on E476: md:تاريخ فرضي
Note on E479: md:تاريخ فرضي
Note on E484: md:تاريخ فرضي
Note on E486: md:تاريخ فرضي
Note on E488: md:تاريخ فرضي
Note on E493: md:تاريخ فرضي
Note on E495: md:تاريخ فرضي
Note on E503: md:تاريخ فرضي
Note on E504: md:تاريخ فرضي
Note on E505: md:تاريخ فرضي
Note on E507: md:تاريخ فرضي
Note on E508: md:تاريخ فرضي
Note on E511: md:تاريخ فرضي
Note on E513: md:تاريخ فرضي
Note on E514: md:تاريخ فرضي
Note on E524: md:تاريخ فرضي
Note on E525: md:تاريخ فرضي
Note on E528: md:تاريخ فرضي
Note on E529: md:تاريخ فرضي
Note on E530: md:تاريخ فرضي
Note on E534: md:تاريخ فرضي
Note on E535: md:تاريخ فرضي
Note on E536: md:تاريخ فرضي
Note on E539: md:تاريخ فرضي
Note on E540: md:تاريخ فرضي
Note on E541: md:تاريخ فرضي
Note on E542: md:تاريخ فرضي
Note on E543: md:تاريخ فرضي
Note on E544: md:تاريخ فرضي
Note on E549: md:تاريخ فرضي
Note on E551: md:تاريخ فرضي
Note on E553: md:تاريخ فرضي
Note on E558: md:تاريخ فرضي
Note on E559: md:تاريخ فرضي
Note on E562: md:تاريخ فرضي
Note on E563: md:تاريخ فرضي
Note on E566: md:تاريخ فرضي
Note on E571: md:تاريخ فرضي
Note on E580: md:تاريخ فرضي
Note on E582: md:تاريخ فرضي
Note on E591: md:تاريخ فرضي
Note on E592: md:تاريخ فرضي
Note on E593: md:تاريخ فرضي
Note on E594: md:تاريخ فرضي
Note on E596: md:تاريخ فرضي
Note on E597: md:تاريخ فرضي
Note on E600: md:تاريخ فرضي
Note on E605: md:تاريخ فرضي
Note on E608: md:تاريخ فرضي
Note on E622: md:تاريخ فرضي
Note on E623: md:تاريخ فرضي
Note on E625: md:تاريخ فرضي
Note on E626: md:تاريخ فرضي
Note on E627: md:تاريخ فرضي
Note on E629: md:تاريخ فرضي
Note on E630: md:تاريخ فرضي
Note on E633: md:تاريخ فرضي
Note on E637: md:تاريخ فرضي
Note on E640: md:تاريخ فرضي
Note on E642: md:تاريخ فرضي
Note on E643: md:تاريخ فرضي
Note on E644: md:تاريخ فرضي
Note on E658: md:تاريخ فرضي
Note on E660: md:تاريخ فرضي
Note on E676: md:تاريخ فرضي
Note on E682: md:تاريخ فرضي
Note on E688: md:تاريخ فرضي
Note on E693: md:تاريخ فرضي
Note on E735: md:تاريخ فرضي
Note on E736: md:تاريخ فرضي
Note on E737: md:تاريخ فرضي
Note on E739: md:تاريخ فرضي
Note on E743: md:تاريخ فرضي
Note on E756: md:تاريخ فرضي
Note on E757: md:تاريخ فرضي
Note on E766: md:تاريخ فرضي
Note on E767: md:تاريخ فرضي
Note on E769: md:تاريخ فرضي
Note on E774: md:تاريخ فرضي
Note on E791: md:تاريخ فرضي
Note on E795: md:تاريخ فرضي
Note on E798: md:تاريخ فرضي
Note on E803: md:تاريخ فرضي
Note on E822: md:تاريخ فرضي
Note on E823: md:تاريخ فرضي
Note on E824: md:تاريخ فرضي
Note on E826: md:تاريخ فرضي
Note on E830: md:تاريخ فرضي
Note on E843: md:تاريخ فرضي
Note on E844: md:تاريخ فرضي
Note on E853: md:تاريخ فرضي
Note on E861: md:تاريخ فرضي
Note on E878: md:تاريخ فرضي
Note on E882: md:تاريخ فرضي
Note on E885: md:تاريخ فرضي
Note on E890: md:تاريخ فرضي
Note on E910: md:تاريخ فرضي
Note on E911: md:تاريخ فرضي
Note on E912: md:تاريخ فرضي
Note on E913: md:تاريخ فرضي
Note on E914: md:تاريخ فرضي
Note on E915: md:تاريخ فرضي
Note on E916: md:تاريخ فرضي
Note on E917: md:تاريخ فرضي
Note on E918: md:تاريخ فرضي
Note on E919: md:تاريخ فرضي
Note on E920: md:تاريخ فرضي
Note on E921: md:تاريخ فرضي
Note on E923: md:تاريخ فرضي
Note on E924: md:تاريخ فرضي
Note on E925: md:تاريخ فرضي
Note on E926: md:تاريخ فرضي
Note on E929: md:تاريخ فرضي
Note on E934: md:تاريخ فرضي
Note on E940: md:تاريخ فرضي
Note on E941: md:تاريخ فرضي
Note on E947: md:تاريخ فرضي
Note on E948: md:تاريخ فرضي
Note on E962: md:تاريخ فرضي
Note on E966: md:تاريخ فرضي
Note on E967: md:تاريخ فرضي
Note on E968: md:تاريخ فرضي
Note on E969: md:تاريخ فرضي
Note on E971: md:تاريخ فرضي
Note on E976: md:تاريخ فرضي
Note on E978: md:تاريخ فرضي
Note on E979: md:تاريخ فرضي
Note on E981: md:تاريخ فرضي
Note on E984: md:تاريخ فرضي
Note on E986: md:تاريخ فرضي
Note on E987: md:تاريخ فرضي
Note on E988: md:تاريخ فرضي
Note on E990: md:تاريخ فرضي
Note on E992: md:تاريخ فرضي
Note on E997: md:تاريخ فرضي
Note on E1000: md:تاريخ فرضي
Note on E1002: md:تاريخ فرضي
Note on E1008: md:تاريخ فرضي
Note on E1009: md:تاريخ فرضي
Note on E1010: md:تاريخ فرضي
Note on E1014: md:تاريخ فرضي
Note on E1015: md:تاريخ فرضي
Note on E1020: md:تاريخ فرضي
Note on E1021: md:تاريخ فرضي
Note on E1026: md:تاريخ فرضي
Note on E1029: md:تاريخ فرضي
Note on E1034: md:تاريخ فرضي
Note on E1037: md:تاريخ فرضي
Note on E1062: md:تاريخ فرضي
Note on E1088: md:تاريخ فرضي
Note on E1092: md:تاريخ فرضي
Note on E1101: md:تاريخ فرضي
Note on E1113: md:تاريخ فرضي
Note on E1149: md:تاريخ فرضي
Note on E1177: md:تاريخ فرضي
Note on E1178: md:تاريخ فرضي
Note on E1179: md:تاريخ فرضي
Note on E1180: md:تاريخ فرضي
Note on E1191: md:تاريخ فرضي
Note on E1196: md:تاريخ فرضي
Note on E1198: md:تاريخ فرضي
Note on E1200: md:تاريخ فرضي
Note on E1201: md:تاريخ فرضي
Note on E1202: md:تاريخ فرضي
Note on E1214: md:تاريخ فرضي
Note on E1215: md:تاريخ فرضي
Note on E1222: md:تاريخ فرضي
Note on E1264: md:تاريخ فرضي
Note on E1265: md:تاريخ فرضي
Note on E1266: md:تاريخ فرضي
Note on E1267: md:تاريخ فرضي
Note on E1278: md:تاريخ فرضي
Note on E1283: md:تاريخ فرضي
Note on E1285: md:تاريخ فرضي
Note on E1301: md:تاريخ فرضي
Note on E1302: md:تاريخ فرضي
Note on E1309: md:تاريخ فرضي
Note on E1347: md:تاريخ فرضي
Note on E1348: md:تاريخ فرضي
Note on E1349: md:تاريخ فرضي
Note on E1350: md:تاريخ فرضي
Note on E1361: md:تاريخ فرضي
Note on E1366: md:تاريخ فرضي
Note on E1368: md:تاريخ فرضي
Note on E1384: md:تاريخ فرضي
Note on E1385: md:تاريخ فرضي
Note on E1392: md:تاريخ فرضي
Note on E1430: md:تاريخ فرضي
Note on E1431: md:تاريخ فرضي
Note on E1432: md:تاريخ فرضي
Note on E1433: md:تاريخ فرضي
Note on E1444: md:تاريخ فرضي
Note on E1449: md:تاريخ فرضي
Note on E1451: md:تاريخ فرضي
Note on E1456: md:تاريخ فرضي
Note on E1467: md:تاريخ فرضي
Note on E1468: md:تاريخ فرضي
Note on E1475: md:تاريخ فرضي
Note on E1513: md:تاريخ فرضي
Note on E1514: md:تاريخ فرضي
Note on E1517: md:تاريخ فرضي
Note on E1518: md:تاريخ فرضي
Note on E1521: md:تاريخ فرضي
Note on E1522: md:تاريخ فرضي
Note on E1523: md:تاريخ فرضي
Note on E1524: md:تاريخ فرضي
Note on E1525: md:تاريخ فرضي
Note on E1526: md:تاريخ فرضي
Note on E1527: md:تاريخ فرضي
Note on E1528: md:تاريخ فرضي
Note on E1529: md:تاريخ فرضي
Note on E1530: md:تاريخ فرضي
Note on E1531: md:تاريخ فرضي
Note on E1532: md:تاريخ فرضي
Note on E1533: md:تاريخ فرضي
Note on E1534: md:تاريخ فرضي
Note on E1538: md:تاريخ فرضي
Note on E1545: md:تاريخ فرضي
Note on E1562: md:تاريخ فرضي
Note on E1563: md:تاريخ فرضي
Note on E1565: md:تاريخ فرضي
Note on E1566: md:تاريخ فرضي
Note on E1572: md:تاريخ فرضي
Note on E1576: md:تاريخ فرضي
Note on E1578: md:تاريخ فرضي
Note on E1579: md:تاريخ فرضي
Note on E1580: md:تاريخ فرضي
Note on E1581: md:تاريخ فرضي
Note on E1582: md:تاريخ فرضي
Note on E1583: md:تاريخ فرضي
Note on E1584: md:تاريخ فرضي
Note on E1586: md:تاريخ فرضي
Note on E1588: md:تاريخ فرضي
Note on E1590: md:تاريخ فرضي
Note on E1593: md:تاريخ فرضي
Note on E1595: md:تاريخ فرضي
Note on E1596: md:تاريخ فرضي
Note on E1599: md:تاريخ فرضي
Note on E1600: md:تاريخ فرضي
Note on E1605: md:تاريخ فرضي
Note on E1606: md:تاريخ فرضي
Note on E1608: md:تاريخ فرضي
Note on E1609: md:تاريخ فرضي
Note on E1619: md:تاريخ فرضي
Note on E1626: md:تاريخ فرضي
Note on E1627: md:تاريخ فرضي
Note on E1632: md:تاريخ فرضي
Note on E1637: md:تاريخ فرضي
Note on E1638: md:تاريخ فرضي
Note on E1639: md:تاريخ فرضي
Note on E1646: md:تاريخ فرضي
Note on E1647: md:تاريخ فرضي
Note on E1652: md:تاريخ فرضي
Note on E1653: md:تاريخ فرضي
Note on E1656: md:تاريخ فرضي
Note on E1719: md:تاريخ فرضي
Note on E1720: md:تاريخ فرضي
Note on E1724: md:تاريخ فرضي
Note on E1725: md:تاريخ فرضي
Note on E1728: md:تاريخ فرضي
Note on E1731: md:تاريخ فرضي
Note on E1732: md:تاريخ فرضي
Note on E1733: md:تاريخ فرضي
Note on E1734: md:تاريخ فرضي
Note on E1735: md:تاريخ فرضي
Note on E1736: md:تاريخ فرضي
Note on E1737: md:تاريخ فرضي
Note on E1738: md:تاريخ فرضي
Note on E1739: md:تاريخ فرضي
Note on E1740: md:تاريخ فرضي
Note on E1741: md:تاريخ فرضي
Note on E1742: md:تاريخ فرضي
Note on E1743: md:تاريخ فرضي
Note on E1744: md:تاريخ فرضي
Note on E1745: md:تاريخ فرضي
Note on E1746: md:تاريخ فرضي
Note on E1747: md:تاريخ فرضي
Note on E1748: md:تاريخ فرضي
Note on E1749: md:تاريخ فرضي
Note on E1750: md:تاريخ فرضي
Note on E1751: md:تاريخ فرضي
Note on E1752: md:تاريخ فرضي
Note on E1753: md:تاريخ فرضي
Note on E1754: md:تاريخ فرضي
Note on E1755: md:تاريخ فرضي
Note on E1756: md:تاريخ فرضي
Note on E1757: md:تاريخ فرضي
Note on E1758: md:تاريخ فرضي
Note on E1759: md:تاريخ فرضي
Note on E1760: md:تاريخ فرضي
Note on E1761: md:تاريخ فرضي
Note on E1762: md:تاريخ فرضي
Note on E1764: md:تاريخ فرضي
Note on E1766: md:تاريخ فرضي
Note on E1771: md:تاريخ فرضي
Note on E1772: md:تاريخ فرضي
Note on E1773: md:تاريخ فرضي
Note on E1774: md:تاريخ فرضي
Note on E1775: md:تاريخ فرضي
Note on E1776: md:تاريخ فرضي
Note on E1777: md:تاريخ فرضي
Note on E1778: md:تاريخ فرضي
Note on E1779: md:تاريخ فرضي
Note on E1780: md:تاريخ فرضي
Note on E1781: md:تاريخ فرضي
Note on E1782: md:تاريخ فرضي
Note on E1783: md:تاريخ فرضي
Note on E1784: md:تاريخ فرضي
Note on E1785: md:تاريخ فرضي
Note on E1786: md:تاريخ فرضي
Note on E1787: md:تاريخ فرضي
Note on E1788: md:تاريخ فرضي
Note on E1789: md:تاريخ فرضي
Note on E1790: md:تاريخ فرضي
Note on E1791: md:تاريخ فرضي
Note on E1792: md:تاريخ فرضي
Note on E1793: md:تاريخ فرضي
Note on E1794: md:تاريخ فرضي
Note on E1795: md:تاريخ فرضي
Note on E1796: md:تاريخ فرضي
Note on E1797: md:تاريخ فرضي
Note on E1798: md:تاريخ فرضي
Note on E1799: md:تاريخ فرضي
Note on E1800: md:تاريخ فرضي
Note on E1801: md:تاريخ فرضي
Note on E1802: md:تاريخ فرضي
Note on E1804: md:تاريخ فرضي
Note on E1805: md:تاريخ فرضي
Note on E1806: md:تاريخ فرضي
Note on E1807: md:تاريخ فرضي
Note on E1808: md:تاريخ فرضي
Note on E1809: md:تاريخ فرضي
Note on E1810: md:تاريخ فرضي
Note on E1811: md:تاريخ فرضي
Note on E1812: md:تاريخ فرضي
Note on E1813: md:تاريخ فرضي
Note on E1814: md:تاريخ فرضي
Note on E1815: md:تاريخ فرضي
Note on E1821: md:تاريخ فرضي
Note on E1825: md:تاريخ فرضي
Note on E1826: md:تاريخ فرضي
Note on E1828: md:تاريخ فرضي
Note on E1829: md:تاريخ فرضي
Note on E1830: md:تاريخ فرضي
Note on E1831: md:تاريخ فرضي
Note on E1832: md:تاريخ فرضي
Note on E1833: md:تاريخ فرضي
Note on E1834: md:تاريخ فرضي
Note on E1835: md:تاريخ فرضي
Note on E1836: md:تاريخ فرضي
Note on E1837: md:تاريخ فرضي
Note on E1838: md:تاريخ فرضي
Note on E1839: md:تاريخ فرضي
Note on E1840: md:تاريخ فرضي
Note on E1841: md:تاريخ فرضي
Note on E1842: md:تاريخ فرضي
Note on E1843: md:تاريخ فرضي
Note on E1844: md:تاريخ فرضي
Note on E1845: md:تاريخ فرضي
Note on E1846: md:تاريخ فرضي
Note on E1850: md:تاريخ فرضي
Note on E1852: md:تاريخ فرضي
Note on E1855: md:تاريخ فرضي
Note on E1856: md:تاريخ فرضي
Note on E1857: md:تاريخ فرضي
Note on E1858: md:تاريخ فرضي
Note on E1860: md:تاريخ فرضي
Note on E1861: md:تاريخ فرضي
Note on E1862: md:تاريخ فرضي
Note on E1863: md:تاريخ فرضي
Note on E1864: md:تاريخ فرضي
Note on E1867: md:تاريخ فرضي
Note on E1868: md:تاريخ فرضي
Note on E1870: md:تاريخ فرضي
Note on E1872: md:تاريخ فرضي
Note on E1874: md:تاريخ فرضي
Note on E1875: md:تاريخ فرضي
Note on E1878: md:تاريخ فرضي
Note on E1881: md:تاريخ فرضي
Note on E1882: md:تاريخ فرضي
Note on E1883: md:تاريخ فرضي
Note on E1884: md:تاريخ فرضي
Note on E1886: md:تاريخ فرضي
Note on E1888: md:تاريخ فرضي
Note on E1889: md:تاريخ فرضي
Note on E1891: md:تاريخ فرضي
Note on E1892: md:تاريخ فرضي
Note on E1893: md:تاريخ فرضي
Note on E1898: md:تاريخ فرضي
Note on E1900: md:تاريخ فرضي
Note on E1902: md:تاريخ فرضي
Note on E1903: md:تاريخ فرضي
Note on E1905: md:تاريخ فرضي
Note on E1906: md:تاريخ فرضي
Note on E1908: md:تاريخ فرضي
Note on E1909: md:تاريخ فرضي
Note on E1913: md:تاريخ فرضي
Note on E1918: md:تاريخ فرضي
Note on E1919: md:تاريخ فرضي
Note on E1920: md:تاريخ فرضي
Note on E1921: md:تاريخ فرضي
Note on E1922: md:تاريخ فرضي
Note on E1923: md:تاريخ فرضي
Note on E1924: md:تاريخ فرضي
Note on E1925: md:تاريخ فرضي
Note on E1926: md:تاريخ فرضي
Note on E1928: md:تاريخ فرضي
Note on E1929: md:تاريخ فرضي
Note on E1930: md:تاريخ فرضي
Note on E1931: md:تاريخ فرضي
Note on E1932: md:تاريخ فرضي
Note on E1933: md:تاريخ فرضي
Note on E1934: md:تاريخ فرضي
Note on E1935: md:تاريخ فرضي
Note on E1936: md:تاريخ فرضي
Note on E1937: md:تاريخ فرضي
Note on E1938: md:تاريخ فرضي
Note on E1939: md:تاريخ فرضي
Note on E1940: md:تاريخ فرضي
Note on E1941: md:تاريخ فرضي
Note on E1942: md:تاريخ فرضي
Note on E1944: md:تاريخ فرضي
Note on E1945: md:تاريخ فرضي
Note on E1946: md:تاريخ فرضي
Note on E1947: md:تاريخ فرضي
Note on E1948: md:تاريخ فرضي
Note on E1950: md:تاريخ فرضي
Note on E1951: md:تاريخ فرضي
Note on E1952: md:تاريخ فرضي
Note on E1953: md:تاريخ فرضي
Note on E1954: md:تاريخ فرضي
Note on E1955: md:تاريخ فرضي
Note on E1956: md:تاريخ فرضي
Note on E1957: md:تاريخ فرضي
Note on E1958: md:تاريخ فرضي
Note on E1959: md:تاريخ فرضي
Note on E1960: md:تاريخ فرضي
Note on E1961: md:تاريخ فرضي
Note on E1963: md:تاريخ فرضي
Note on E1965: md:تاريخ فرضي
Note on E1966: md:تاريخ فرضي
Note on E1967: md:تاريخ فرضي
Note on E1968: md:تاريخ فرضي
Note on E1969: md:تاريخ فرضي
Note on E1970: md:تاريخ فرضي
Note on E1971: md:تاريخ فرضي
Note on E1972: md:تاريخ فرضي
Note on E1973: md:تاريخ فرضي
Note on E1974: md:تاريخ فرضي
Note on E1975: md:تاريخ فرضي
Note on E1977: md:تاريخ فرضي
Note on E1979: md:تاريخ فرضي
Note on E1984: md:تاريخ فرضي
Note on E1986: md:تاريخ فرضي
Note on E1987: md:تاريخ فرضي
Note on E1988: md:تاريخ فرضي
Note on E1989: md:تاريخ فرضي
Note on E1990: md:تاريخ فرضي
Note on E1991: md:تاريخ فرضي
Note on E1992: md:تاريخ فرضي
Note on E1993: md:تاريخ فرضي
Note on E1994: md:تاريخ فرضي
Note on E1995: md:تاريخ فرضي
Note on E1996: md:تاريخ فرضي
Note on E1997: md:تاريخ فرضي
Note on E1998: md:تاريخ فرضي
Note on E1999: md:تاريخ فرضي
Note on E2000: md:تاريخ فرضي
Note on E2001: md:تاريخ فرضي
Note on E2003: md:تاريخ فرضي
Note on E2004: md:تاريخ فرضي
Note on E2005: md:تاريخ فرضي
Note on E2006: md:تاريخ فرضي
Note on E2007: md:تاريخ فرضي
Note on E2008: md:تاريخ فرضي
Note on E2009: md:تاريخ فرضي
Note on E2010: md:تاريخ فرضي
Note on E2011: md:تاريخ فرضي
Note on E2012: md:تاريخ فرضي
Note on E2013: md:تاريخ فرضي
Note on E2014: md:تاريخ فرضي
Note on E2016: md:تاريخ فرضي
Note on E2017: md:تاريخ فرضي
Note on E2018: md:تاريخ فرضي
Note on E2019: md:تاريخ فرضي
Note on E2020: md:تاريخ فرضي
Note on E2021: md:تاريخ فرضي
Note on E2023: md:تاريخ فرضي
Note on E2024: md:تاريخ فرضي
Note on E2025: md:تاريخ فرضي
Note on E2026: md:تاريخ فرضي
Note on E2027: md:تاريخ فرضي
Note on E2030: md:تاريخ فرضي
Note on E2031: md:تاريخ فرضي
Note on E2032: md:تاريخ فرضي
Note on E2033: md:تاريخ فرضي
Note on E2034: md:تاريخ فرضي
Note on E2035: md:تاريخ فرضي
Note on E2037: md:تاريخ فرضي
Note on E2038: md:تاريخ فرضي
Note on E2044: md:تاريخ فرضي
Note on E2047: md:تاريخ فرضي
Note on E2048: md:تاريخ فرضي
Note on E2049: md:تاريخ فرضي
Note on E2050: md:تاريخ فرضي
Note on E2052: md:تاريخ فرضي
Note on E2054: md:تاريخ فرضي
Note on E2057: md:تاريخ فرضي
Note on E2058: md:تاريخ فرضي
Note on E2059: md:تاريخ فرضي
Note on E2060: md:تاريخ فرضي
Note on E2065: md:تاريخ فرضي
Note on E2066: md:تاريخ فرضي
Note on E2069: md:تاريخ فرضي
Note on E2070: md:تاريخ فرضي
Note on E2076: md:تاريخ فرضي
Note on E2079: md:تاريخ فرضي
Note on E2080: md:تاريخ فرضي
Note on E2081: md:تاريخ فرضي
Note on E2082: md:تاريخ فرضي
Note on E2083: md:تاريخ فرضي
Note on E2091: md:تاريخ فرضي
Note on E2092: md:تاريخ فرضي
Note on E2095: md:تاريخ فرضي
Note on E2096: md:تاريخ فرضي
Note on E2098: md:تاريخ فرضي
Note on E2099: md:تاريخ فرضي
Note on E2102: md:تاريخ فرضي
Note on E2103: md:تاريخ فرضي
Note on E2106: md:تاريخ فرضي
Note on E2107: md:تاريخ فرضي
Note on E2108: md:تاريخ فرضي
Note on E2109: md:تاريخ فرضي
Note on E2112: md:تاريخ فرضي
Note on E2116: md:تاريخ فرضي
Note on E2117: md:تاريخ فرضي
Note on E2118: md:تاريخ فرضي
Note on E2121: md:تاريخ فرضي
Note on E2122: md:تاريخ فرضي
Note on E2123: md:تاريخ فرضي
Note on E2128: md:تاريخ فرضي
Note on E2149: md:تاريخ فرضي
Note on E2202: md:تاريخ فرضي
Note on E2203: md:تاريخ فرضي
Note on E2208: md:تاريخ فرضي
Note on E2209: md:تاريخ فرضي
Note on E2224: md:تاريخ فرضي
Note on E2227: md:تاريخ فرضي
Note on E2322: md:تاريخ فرضي
Note on E2327: md:تاريخ فرضي
Note on E2329: md:تاريخ فرضي
Note on E2331: md:تاريخ فرضي
Note on E2333: md:تاريخ فرضي
Note on E2353: md:تاريخ فرضي
Note on E2393: md:تاريخ فرضي
Note on E2394: md:تاريخ فرضي
Note on E2395: md:تاريخ فرضي

## 5
|  | جدول شماره 5 : لیست فعالیت هاي اصلی و بحرانی پروژه متاثر از علل تاخيرات | [12 empty] | 2022-05-25 |  | 1 |  |  |  | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24
 | time axis 2021-06-01 to 2023-06-22 12:00
شماره (ID A s) | نام بسته كاري | فاز | برنامه/واقعي | نام فعالیت اصلی | دوره طبق برنامه مصوب |  |  |  | دوره اصلاح شده |  | درصد پیشرفت فیزیکی | دوره طبق واقعیت | time axis 2021-06-01 to 2023-06-22 12:00
[5 empty] | مدت (روز) | شروع | پايان | شناوري | شروع اصلاح شده | پایان اصلاح شده |  | مدت (روز) | شروع | پايان |  | 2021-07-01: شش ماهه اول سال اول; 2021-12-31 09:36: شش ماهه دوم سال اول; 2022-06-30 07:12: شش ماهه اول سال دوم; 2022-12-29 16:48: شش ماهه دوم سال دوم
P12-EPC-E1000 | ايستگاه گاز | E | P | Endorsement Report For Basic Design & Scope of Work | 29 | 2021-06-23 | 2021-07-22 | 0 | 2021-06-23 | 2021-07-22 | 100% | 538 | 2021-07-31 | 2023-01-20 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1000 | ايستگاه گاز | E | A | Endorsement Report For Basic Design & Scope of Work | 538 | 2021-07-31 | 2023-01-20 | 0 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1570 | ايستگاه گاز | E | P | Process Flow Diagram (PFD) | 53 | 2021-07-04 | 2021-08-26 | 0 | 2021-07-04 | 2021-08-26 | 80% | 524 | 2021-08-14 | 2023-01-20 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1570 | ايستگاه گاز | E | A | Process Flow Diagram (PFD) | 524 | 2021-08-14 | 2023-01-20 | 0 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1540 | ايستگاه گاز | E | P | Process Data Sheets For Gas Compressors Packages | 43 | 2021-07-31 | 2021-09-12 | 0 | 2021-07-31 | 2021-09-12 | 60% | 439 | 2021-11-07 | 2023-01-20 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1540 | ايستگاه گاز | E | A | Process Data Sheets For Gas Compressors Packages | 439 | 2021-11-07 | 2023-01-20 | 0 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E2480 | ايستگاه گاز | E | P | Mechanical Data Sheets For Gas Compressors Packages | 48 | 2021-08-12 | 2021-09-29 | 0 | 2021-08-12 | 2021-09-29 | 80% | 313 | 2021-09-12 | 2022-07-22 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E2480 | ايستگاه گاز | E | A | Mechanical Data Sheets For Gas Compressors Packages | 313 | 2021-09-12 | 2022-07-22 | 0 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E7980 | ايستگاه گاز | E | P | TBE For Gas Compressors | 44 | 2021-08-16 | 2021-09-29 | 0 | 2021-08-16 | 2021-09-29 | 0% | 170 | 2022-02-02 | 2022-07-22 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E7980 | ايستگاه گاز | E | A | TBE For Gas Compressors | 170 | 2022-02-02 | 2022-07-22 | 0 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E7970 | ايستگاه گاز | E | P | PMR For Gas Compressors | 10 | 2021-09-03 | 2021-09-13 | 0 | 2021-09-03 | 2021-09-13 | 100% | 236 | 2021-11-28 | 2022-07-22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E7970 | ايستگاه گاز | E | A | PMR For Gas Compressors | 236 | 2021-11-28 | 2022-07-22 | 0 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1000 | ايستگاه گاز | P | P | Tendering & Selection For Gas Compressors | 59 | 2021-08-11 | 2021-10-09 | 0 | 2021-08-11 | 2021-10-09 | 0% | 146 | 2022-02-26 | 2022-07-22 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1000 | ايستگاه گاز | P | A | Tendering & Selection For Gas Compressors | 146 | 2022-02-26 | 2022-07-22 | 0 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1010 | ايستگاه گاز | P | P | Contract Effectiveness / PO For Gas Compressors | 29 | 2021-10-10 | 2021-11-08 | 0 | 2021-10-10 | 2021-11-08 | 0% |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1010 | ايستگاه گاز | P | A | Contract Effectiveness / PO For Gas Compressors |  | 0 |  | 0 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1020 | ايستگاه گاز | P | P | Manufacturing / Fabrication / Supply For Gas Compressors | 419 | 2021-11-09 | 2023-01-02 | 0 | 2021-11-09 | 2023-01-02 | 0% |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1020 | ايستگاه گاز | P | A | Manufacturing / Fabrication / Supply For Gas Compressors |  | 0 | 0 | 0 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1060 | چاه شماره 18 | E | P | Process Flow Diagram - W018S | 44 | 2021-07-23 | 2021-09-05 | 39 | 2021-08-31 | 2021-10-14 | 60% | 444 | 2021-11-02 | 2023-01-20 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1060 | چاه شماره 18 | E | A | Process Flow Diagram - W018S | 444 | 2021-11-02 | 2023-01-20 | 39 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1070 | چاه شماره 18 | E | P | P&ID - W018S | 44 | 2021-08-02 | 2021-09-15 | 39 | 2021-09-10 | 2021-10-24 | 80% | 445 | 2021-11-01 | 2023-01-20 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1070 | چاه شماره 18 | E | A | P&ID - W018S | 445 | 2021-11-01 | 2023-01-20 | 39 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1860 | چاه شماره 18 | E | P | Specification For WHCP/HPU-W018S | 37 | 2021-07-23 | 2021-08-29 | 22 | 2021-08-14 | 2021-09-20 | 80% | 231 | 2021-08-08 | 2022-03-27 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1860 | چاه شماره 18 | E | A | Specification For WHCP/HPU-W018S | 231 | 2021-08-08 | 2022-03-27 | 22 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2470 | چاه شماره 18 | E | P | Rough Grading Plans -W018S | 39 | 2021-07-28 | 2021-09-05 | 9 | 2021-08-06 | 2021-09-14 | 60% | 134 | 2021-10-30 | 2022-03-13 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2470 | چاه شماره 18 | E | A | Rough Grading Plans -W018S | 134 | 2021-10-30 | 2022-03-13 | 9 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1300 | چاه شماره 18 | E | P | Piping Material Specification-W018S | 29 | 2021-08-02 | 2021-08-31 | 153 | 2022-01-02 | 2022-01-31 | 100% | 113 | 2021-08-24 | 2021-12-15 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1300 | چاه شماره 18 | E | A | Piping Material Specification-W018S | 113 | 2021-08-24 | 2021-12-15 | 153 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1870 | چاه شماره 18 | E | P | Data Sheets For WHCP/HPU - Wellheads-W018S | 29 | 2021-08-02 | 2021-08-31 | 22 | 2021-08-24 | 2021-09-22 | 80% | 516 | 2021-08-22 | 2023-01-20 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1870 | چاه شماره 18 | E | A | Data Sheets For WHCP/HPU - Wellheads-W018S | 516 | 2021-08-22 | 2023-01-20 | 22 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2450 | چاه شماره 18 | E | P | General Civil Layout - W018S | 19 | 2021-08-12 | 2021-08-31 | 14 | 2021-08-26 | 2021-09-14 | 100% | 152 | 2021-07-28 | 2021-12-27 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2450 | چاه شماره 18 | E | A | General Civil Layout - W018S | 152 | 2021-07-28 | 2021-12-27 | 14 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1810 | چاه شماره 18 | E | P | Pipeline Corrosion Study & Material Selection Report-W018S | 43 | 2021-08-22 | 2021-10-04 | 192 | 2022-03-02 | 2022-04-14 | 0% | 357 | 2021-10-27 | 2022-10-19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1810 | چاه شماره 18 | E | A | Pipeline Corrosion Study & Material Selection Report-W018S | 357 | 2021-10-27 | 2022-10-19 | 192 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E3590 | چاه شماره 18 | E | P | PMR For WHCP/HPU - W018S | 6 | 2021-08-30 | 2021-09-05 | 22 | 2021-09-21 | 2021-09-27 | 100% | 431 | 2021-11-15 | 2023-01-20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E3590 | چاه شماره 18 | E | A | PMR For WHCP/HPU - W018S | 431 | 2021-11-15 | 2023-01-20 | 22 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E3560 | چاه شماره 18 | E | P | PMR For Line pipes - W018S | 4 | 2021-10-06 | 2021-10-10 | 40 | 2021-11-15 | 2021-11-19 | 100% | 410 | 2021-12-06 | 2023-01-20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E3560 | چاه شماره 18 | E | A | PMR For Line pipes - W018S | 410 | 2021-12-06 | 2023-01-20 | 40 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1670 | چاه شماره 18 | P | P | Tendering & Selection- W018S-WHCP | 9 | 2021-09-23 | 2021-10-02 | 22 | 2021-10-15 | 2021-10-24 | 0% | 71 | 2022-03-15 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1670 | چاه شماره 18 | P | A | Tendering & Selection- W018S-WHCP | 71 | 2022-03-15 | 2022-05-25 | 22 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1550 | چاه شماره 18 | P | P | Tendering & Selection- W018S- Line pipe | 6 | 2021-10-01 | 2021-10-07 | 26 | 2021-10-27 | 2021-11-02 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1550 | چاه شماره 18 | P | A | Tendering & Selection- W018S- Line pipe | 0 | 0 | 0 | 26 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1680 | چاه شماره 18 | P | P | Contract Effectiveness / PO- W018S- WHCP | 4 | 2021-10-03 | 2021-10-07 | 22 | 2021-10-25 | 2021-10-29 | 0% | 14 | 2022-05-29 | 2022-06-12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1680 | چاه شماره 18 | P | A | Contract Effectiveness / PO- W018S- WHCP | 14 | 2022-05-29 | 2022-06-12 | 22 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1560 | چاه شماره 18 | P | P | Contract Effectiveness / PO- W018S-Line pipe | 4 | 2021-10-08 | 2021-10-12 | 26 | 2021-11-03 | 2021-11-07 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1560 | چاه شماره 18 | P | A | Contract Effectiveness / PO- W018S-Line pipe | 0 | 0 | 0 | 26 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1690 | چاه شماره 18 | P | P | Manufacturing / Fabrication / Supply- W018S-WHCP | 89 | 2021-10-08 | 2022-01-05 | 22 | 2021-10-30 | 2022-01-27 | 0% |  | 2022-06-13 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1690 | چاه شماره 18 | P | A | Manufacturing / Fabrication / Supply- W018S-WHCP | -44725 | 2022-06-13 | 0 | 22 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1570 | چاه شماره 18 | P | P | Manufacturing / Fabrication / Supply- W018S-Line pipe | 69 | 2021-10-13 | 2021-12-21 | 26 | 2021-11-08 | 2022-01-16 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1570 | چاه شماره 18 | P | A | Manufacturing / Fabrication / Supply- W018S-Line pipe | 0 | 0 | 0 | 26 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1150 | چاه شماره 18 | C | P | Supply & Installation sealling Layer of Mud pit- W018S | 7 | 2021-09-20 | 2021-09-27 | 12 | 2021-10-02 | 2021-10-09 | 0% | 80 | 2021-09-20 | 2021-12-09 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1150 | چاه شماره 18 | C | A | Supply & Installation sealling Layer of Mud pit- W018S | 80 | 2021-09-20 | 2021-12-09 | 12 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1330 | چاه شماره 18 | C | P | Construction of Right of Way- W018S | 19 | 2021-10-09 | 2021-10-28 | 94 | 2022-01-11 | 2022-01-30 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1330 | چاه شماره 18 | C | A | Construction of Right of Way- W018S | 0 | 0 | 0 | 94 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1350 | چاه شماره 18 | C | P | Construction & Installation of Shelter for Wellhead Control Panel-W018S | 14 | 2021-12-20 | 2022-01-03 | 57 | 2022-02-15 | 2022-03-01 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1350 | چاه شماره 18 | C | A | Construction & Installation of Shelter for Wellhead Control Panel-W018S | 0 | 0 | 0 | 57 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1060 | چاه شماره 28 | E | P | Process Flow Diagram - W028 | 39 | 2021-07-23 | 2021-08-31 | 44 | 2021-09-05 | 2021-10-14 | 60% | 444 | 2021-11-02 | 2023-01-20 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1060 | چاه شماره 28 | E | A | Process Flow Diagram - W028 | 444 | 2021-11-02 | 2023-01-20 | 44 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1070 | چاه شماره 28 | E | P | P&ID - W028 | 39 | 2021-08-02 | 2021-09-10 | 44 | 2021-09-15 | 2021-10-24 | 80% | 414 | 2021-11-01 | 2022-12-20 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1070 | چاه شماره 28 | E | A | P&ID - W028 | 414 | 2021-11-01 | 2022-12-20 | 44 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1860 | چاه شماره 28 | E | P | Specification For WHCP/HPU - W028 | 37 | 2021-07-23 | 2021-08-29 | 197 | 2022-02-05 | 2022-03-14 | 80% | 231 | 2021-08-08 | 2022-03-27 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1860 | چاه شماره 28 | E | A | Specification For WHCP/HPU - W028 | 231 | 2021-08-08 | 2022-03-27 | 197 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2460 | چاه شماره 28 | E | P | General Civil Layout -W028 | 24 | 2021-07-23 | 2021-08-16 | 0 | 2021-07-23 | 2021-08-16 | 60% | 458 | 2021-10-19 | 2023-01-20 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2460 | چاه شماره 28 | E | A | General Civil Layout -W028 | 458 | 2021-10-19 | 2023-01-20 | 0 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2480 | چاه شماره 28 | E | P | Rough Grading Plans -W028 | 24 | 2021-07-23 | 2021-08-16 | 0 | 2021-07-23 | 2021-08-16 | 60% | 181 | 2021-10-11 | 2022-04-10 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2480 | چاه شماره 28 | E | A | Rough Grading Plans -W028 | 181 | 2021-10-11 | 2022-04-10 | 0 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E3530 | چاه شماره 28 | E | P | PMR For Line Pipes - W028 | 9 | 2021-07-30 | 2021-08-08 | 50 | 2021-09-18 | 2021-09-27 | 100% | 410 | 2021-12-06 | 2023-01-20 |  |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E3530 | چاه شماره 28 | E | A | PMR For Line Pipes - W028 | 410 | 2021-12-06 | 2023-01-20 | 50 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1880 | چاه شماره 28 | E | P | Data Sheets For WHCP/HPU - Wellheads - W028 | 48 | 2021-08-12 | 2021-09-29 | 197 | 2022-02-25 | 2022-04-14 | 80% | 516 | 2021-08-22 | 2023-01-20 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1880 | چاه شماره 28 | E | A | Data Sheets For WHCP/HPU - Wellheads - W028 | 516 | 2021-08-22 | 2023-01-20 | 197 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1820 | چاه شماره 28 | E | P | Pipeline Corrosion Study & Material Selection Report - W028 | 43 | 2021-08-22 | 2021-10-04 | 192 | 2022-03-02 | 2022-04-14 | 0% | 357 | 2021-10-27 | 2022-10-19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1820 | چاه شماره 28 | E | A | Pipeline Corrosion Study & Material Selection Report - W028 | 357 | 2021-10-27 | 2022-10-19 | 192 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E3590 | چاه شماره 28 | E | P | PMR For WHCP/HPU - W028 | 9 | 2021-09-01 | 2021-09-10 | 45 | 2021-10-16 | 2021-10-25 | 100% | 431 | 2021-11-15 | 2023-01-20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E3590 | چاه شماره 28 | E | A | PMR For WHCP/HPU - W028 | 431 | 2021-11-15 | 2023-01-20 | 45 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1180 | چاه شماره 28 | E | P | Piping Material Specification - W028 | 63 | 2021-10-22 | 2021-12-24 | 111 | 2022-02-10 | 2022-04-14 | 60% | -44528 | 2021-11-28 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1180 | چاه شماره 28 | E | A | Piping Material Specification - W028 | -44528 | 2021-11-28 | 0 | 111 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1550 | چاه شماره 28 | P | P | Tendering & Selection- W028 - Line pipe | 6 | 2021-08-19 | 2021-08-25 | 50 | 2021-10-08 | 2021-10-14 | 0% | 71 | 2022-03-15 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1550 | چاه شماره 28 | P | A | Tendering & Selection- W028 - Line pipe | 71 | 2022-03-15 | 2022-05-25 | 50 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1560 | چاه شماره 28 | P | P | Contract Effectiveness / PO- W028 - Line pipe | 4 | 2021-08-26 | 2021-08-30 | 50 | 2021-10-15 | 2021-10-19 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1560 | چاه شماره 28 | P | A | Contract Effectiveness / PO- W028 - Line pipe | 0 | 0 | 0 | 50 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1570 | چاه شماره 28 | P | P | Manufacturing / Fabrication / Supply- W028 - Line pipe | 109 | 2021-08-31 | 2021-12-18 | 50 | 2021-10-20 | 2022-02-06 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1570 | چاه شماره 28 | P | A | Manufacturing / Fabrication / Supply- W028 - Line pipe | 0 | 0 | 0 | 50 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1670 | چاه شماره 28 | P | P | Tendering & Selection- W028 - WHCP | 9 | 2021-09-23 | 2021-10-02 | 45 | 2021-11-07 | 2021-11-16 | 0% | 71 | 2022-03-15 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1670 | چاه شماره 28 | P | A | Tendering & Selection- W028 - WHCP | 71 | 2022-03-15 | 2022-05-25 | 45 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1680 | چاه شماره 28 | P | P | Contract Effectiveness / PO- W028 - WHCP | 4 | 2021-10-03 | 2021-10-07 | 45 | 2021-11-17 | 2021-11-21 | 0% | 14 | 2022-05-29 | 2022-06-12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1680 | چاه شماره 28 | P | A | Contract Effectiveness / PO- W028 - WHCP | 14 | 2022-05-29 | 2022-06-12 | 45 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1690 | چاه شماره 28 | P | P | Manufacturing / Fabrication / Supply- W028 - WHCP | 89 | 2021-10-08 | 2022-01-05 | 45 | 2021-11-22 | 2022-02-19 | 0% | 221 | 2022-06-13 | 2023-01-20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1690 | چاه شماره 28 | P | A | Manufacturing / Fabrication / Supply- W028 - WHCP | 221 | 2022-06-13 | 2023-01-20 | 45 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1170 | چاه شماره 28 | C | P | Site Preparation W028 | 19 | 2021-08-17 | 2021-09-05 | 0 | 2021-08-17 | 2021-09-05 | 53% | 492 | 2021-09-15 | 2023-01-20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1170 | چاه شماره 28 | C | A | Site Preparation W028 | 492 | 2021-09-15 | 2023-01-20 | 0 |  |  | 53% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1440 | چاه شماره 28 | C | P | Construction of Right of Way - W028 | 14 | 2021-10-11 | 2021-10-25 | 131 | 2022-02-19 | 2022-03-05 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1440 | چاه شماره 28 | C | A | Construction of Right of Way - W028 | 0 | 0 | 0 | 131 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1240 | چاه شماره 28 | C | P | Excavation of Mud Channel- W028 | 6 | 2021-08-30 | 2021-09-05 | 25 | 2021-09-24 | 2021-09-30 | 0% | 28 | 2022-02-28 | 2022-03-28 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1240 | چاه شماره 28 | C | A | Excavation of Mud Channel- W028 | 28 | 2022-02-28 | 2022-03-28 | 25 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1310 | چاه شماره 28 | C | P | Installation sealling Layer of Mud Pit- W028 | 6 | 2021-08-29 | 2021-09-04 | 37 | 2021-10-05 | 2021-10-11 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1310 | چاه شماره 28 | C | A | Installation sealling Layer of Mud Pit- W028 | 0 | 0 | 0 | 37 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1460 | چاه شماره 28 | C | P | Construction & Installation of Shelter for Wellhead Control Panel- W028 | 4 | 2021-11-05 | 2021-11-09 | 131 | 2022-03-16 | 2022-03-20 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1460 | چاه شماره 28 | C | A | Construction & Installation of Shelter for Wellhead Control Panel- W028 | 0 | 0 | 0 | 131 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P07-EPC-E2580 | چاه شماره 14 | E | P | General Civil Layout - BK14 | 24 | 2021-07-23 | 2021-08-16 | 346 | 2022-07-04 | 2022-07-28 | 60% | 123 | 2022-09-19 | 2023-01-20 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P07-EPC-E2580 | چاه شماره 14 | E | A | General Civil Layout - BK14 | 123 | 2022-09-19 | 2023-01-20 | 346 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مهر امضا پيمانكار | [8 empty] | مهر امضاء كارفرما
Formulas:
شروع = IFERROR(VLOOKUP([شماره (ID A s)]&[برنامه/واقعي],Gas!$B:$I,7,0),"")
شروع = [شروع, row below]
پايان = IFERROR(VLOOKUP([شماره (ID A s)]&[برنامه/واقعي],Gas!$B:$I,8,0),"")
پايان = [پايان, row below]
دوره اصلاح شده = [شروع]+[شناوري]
پایان اصلاح شده = [دوره اصلاح شده]+[دوره طبق برنامه مصوب]
درصد پیشرفت فیزیکی = VLOOKUP([شماره (ID A s)],'Well-28'!$A:$M,13,0)
Note on I6: Mahsa Aref: تاریخ پایان فرضی
Note on I8: Mahsa Aref: تاریخ پایان فرضی
Note on I10: Mahsa Aref: تاریخ پایان فرضی
Note on I24: Mahsa Aref: تاریخ پایان فرضی
Note on I26: Mahsa Aref: تاریخ پایان فرضی
Note on I34: Mahsa Aref: تاریخ پایان فرضی
Note on I40: Mahsa Aref: تاریخ پایان فرضی
Note on I42: Mahsa Aref: تاریخ پایان فرضی
Note on I62: Mahsa Aref: تاریخ پایان فرضی
Note on I68: Mahsa Aref: تاریخ پایان فرضی
Note on I72: Mahsa Aref: تاریخ پایان فرضی
Note on I74: Mahsa Aref: تاریخ پایان فرضی
Note on I78: Mahsa Aref: تاریخ پایان فرضی
Note on I92: Mahsa Aref: تاریخ پایان فرضی
Note on I94: Mahsa Aref: تاریخ پایان فرضی
Note on I104: Mahsa Aref: تاریخ پایان فرضی

## List of delay (hidden)
شماره (ID A s) | نام بسته كاري | فاز | برنامه/واقعي | نام فعالیت اصلی | دوره طبق برنامه مصوب |  |  |  | دوره اصلاح شده |  | درصد پیشرفت فیزیکی | دوره طبق واقعیت
[5 empty] | مدت (روز) | شروع | پايان | شناوري | شروع اصلاح شده | پایان اصلاح شده |  | مدت (روز) | شروع | پايان
P12-EPC-E1000 | ايستگاه گاز | E | A | Endorsement Report For Basic Design & Scope of Work | 50 | 2021-07-31 | 2021-09-19 | 0 |  |  | 100%
P12-EPC-E1570 | ايستگاه گاز | E | A | Process Flow Diagram (PFD) | 284 | 2021-08-14 | 2022-05-25 | 0 |  |  | 80%
P12-EPC-E1540 | ايستگاه گاز | E | A | Process Data Sheets For Gas Compressors Packages | 199 | 2021-11-07 | 2022-05-25 | 0 |  |  | 60%
P12-EPC-E2480 | ايستگاه گاز | E | A | Mechanical Data Sheets For Gas Compressors Packages | 238 | 2021-09-12 | 2022-05-08 | 0 |  |  | 80%
P12-EPC-E7980 | ايستگاه گاز | E | A | TBE For Gas Compressors | 31 | 2022-02-02 | 2022-03-05 | 0 |  |  | 0%
P12-EPC-E7970 | ايستگاه گاز | E | A | PMR For Gas Compressors | 77 | 2021-11-28 | 2022-02-13 | 0 |  |  | 100%
P12-EPC-P1000 | ايستگاه گاز | P | A | Tendering & Selection For Gas Compressors | #VALUE! |  |  | 0 |  |  | 0%
P12-EPC-P1010 | ايستگاه گاز | P | A | Contract Effectiveness / PO For Gas Compressors | #VALUE! |  |  | 0 |  |  | 0%
P12-EPC-P1020 | ايستگاه گاز | P | A | Manufacturing / Fabrication / Supply For Gas Compressors | #VALUE! |  |  | 0 |  |  | 0%
P01-EPC-E1060 | چاه شماره 18 | E | A | Process Flow Diagram - W018S | 294 | 2021-08-04 | 2022-05-25 | 39 |  |  | 60%
P01-EPC-E1370 | چاه شماره 18 | E | A | Plot Plan Drawing - W018S | 276 | 2021-08-22 | 2022-05-25 | 14 |  |  | 80%
P01-EPC-E1860 | چاه شماره 18 | E | A | Specification For WHCP/HPU-W018S | 231 | 2021-08-08 | 2022-03-27 | 22 |  |  | 80%
P01-EPC-E2470 | چاه شماره 18 | E | A | Rough Grading Plans -W018S | 228 | 2021-07-28 | 2022-03-13 | 9 |  |  | 60%
P01-EPC-E1070 | چاه شماره 18 | E | A | P&ID - W018S | 289 | 2021-08-09 | 2022-05-25 | 39 |  |  | 80%
P01-EPC-E1300 | چاه شماره 18 | E | A | Piping Material Specification-W018S | 113 | 2021-08-24 | 2021-12-15 | 153 |  |  | 100%
P01-EPC-E1870 | چاه شماره 18 | E | A | Data Sheets For WHCP/HPU - Wellheads-W018S | 276 | 2021-08-22 | 2022-05-25 | 22 |  |  | 80%
P01-EPC-E2460 | چاه شماره 18 | E | A | Civil and Structural drawings - W018S | 220 | 2021-07-28 | 2022-03-05 | 16 |  |  | 60%
P01-EPC-E2450 | چاه شماره 18 | E | A | General Civil Layout - W018S | 152 | 2021-07-28 | 2021-12-27 | 14 |  |  | 100%
P01-EPC-E1810 | چاه شماره 18 | E | A | Pipeline Corrosion Study & Material Selection Report-W018S | 210 | 2021-10-27 | 2022-05-25 | 192 |  |  | 0%
P01-EPC-E3590 | چاه شماره 18 | E | A | PMR For WHCP/HPU - W018S | 62 | 2021-11-15 | 2022-01-16 | 22 |  |  | 100%
P01-EPC-E3560 | چاه شماره 18 | E | A | PMR For Flowline Support - W018S | 0 |  |  | 26 |  |  | 100%
P01-EPC-P1670 | چاه شماره 18 | P | A | Tendering & Selection- W018S-WHCP | 0 |  |  | 22 |  |  | 0%
P01-EPC-P1550 | چاه شماره 18 | P | A | Tendering & Selection- W018S- Line pipe | 0 |  |  | 26 |  |  | 0%
P01-EPC-P1680 | چاه شماره 18 | P | A | Contract Effectiveness / PO- W018S- WHCP | 0 |  |  | 22 |  |  | 0%
P01-EPC-P1560 | چاه شماره 18 | P | A | Contract Effectiveness / PO- W018S-Line pipe | 0 |  |  | 26 |  |  | 0%
P01-EPC-P1690 | چاه شماره 18 | P | A | Manufacturing / Fabrication / Supply- W018S-WHCP | 0 |  |  | 22 |  |  | 0%
P01-EPC-P1570 | چاه شماره 18 | P | A | Manufacturing / Fabrication / Supply- W018S-Line pipe | 0 |  |  | 26 |  |  | 0%
P01-EPC-C1150 | چاه شماره 18 | C | A | Supply & Installation sealling Layer of Mud pit- W018S | 0 |  |  | 12 |  |  | 0%
P01-EPC-C1330 | چاه شماره 18 | C | A | Construction of Right of Way- W018S | 0 |  |  | 94 |  |  | 0%
P01-EPC-C1350 | چاه شماره 18 | C | A | Construction & Installation of Shelter for Wellhead Control Panel-W018S | 0 |  |  | 57 |  |  | 0%
P02-EPC-E1060 | چاه شماره 28 | E | A | Process Flow Diagram - W028 | 284 | 2021-08-14 | 2022-05-25 | 44 |  |  | 60%
P02-EPC-E1380 | چاه شماره 28 | E | A | Plot Plan Drawing - W028 | 112 | 2022-02-02 | 2022-05-25 | 44 |  |  | 0%
P02-EPC-E1860 | چاه شماره 28 | E | A | Specification For WHCP/HPU - W028 | 231 | 2021-08-08 | 2022-03-27 | 197 |  |  | 80%
P02-EPC-E2460 | چاه شماره 28 | E | A | General Civil Layout -W028 | 218 | 2021-10-19 | 2022-05-25 | 0 |  |  | 60%
P02-EPC-E2470 | چاه شماره 28 | E | A | Civil and Structural drawings -W028 | 218 | 2021-10-19 | 2022-05-25 | 181 |  |  | 80%
P02-EPC-E2480 | چاه شماره 28 | E | A | Rough Grading Plans -W028 | 181 | 2021-10-11 | 2022-04-10 | 0 |  |  | 60%
P02-EPC-E3530 | چاه شماره 28 | E | A | PMR For Line Pipes - W028 | 0 | 2021-12-06 | 2021-12-06 | 50 |  |  | 100%
P02-EPC-E1070 | چاه شماره 28 | E | A | P&ID - W028 | 276 | 2021-08-22 | 2022-05-25 | 44 |  |  | 80%
P02-EPC-E1880 | چاه شماره 28 | E | A | Data Sheets For WHCP/HPU - Wellheads - W028 | 276 | 2021-08-22 | 2022-05-25 | 197 |  |  | 80%
P02-EPC-E1820 | چاه شماره 28 | E | A | Pipeline Corrosion Study & Material Selection Report - W028 | 210 | 2021-10-27 | 2022-05-25 | 192 |  |  | 0%
P02-EPC-E3590 | چاه شماره 28 | E | A | PMR For WHCP/HPU - W028 | 62 | 2021-11-15 | 2022-01-16 | 45 |  |  | 100%
P02-EPC-E1180 | چاه شماره 28 | E | A | Piping Material Specification - W028 | 178 | 2021-11-28 | 2022-05-25 | 111 |  |  | 60%
P02-EPC-P1550 | چاه شماره 28 | P | A | Tendering & Selection- W028 - Line pipe | #VALUE! |  |  | 50 |  |  | 0%
P02-EPC-P1560 | چاه شماره 28 | P | A | Contract Effectiveness / PO- W028 - Line pipe | #VALUE! |  |  | 50 |  |  | 0%
P02-EPC-P1570 | چاه شماره 28 | P | A | Manufacturing / Fabrication / Supply- W028 - Line pipe | #VALUE! |  |  | 50 |  |  | 0%
P02-EPC-P1670 | چاه شماره 28 | P | A | Tendering & Selection- W028 - WHCP | #VALUE! |  |  | 45 |  |  | 0%
P02-EPC-P1680 | چاه شماره 28 | P | A | Contract Effectiveness / PO- W028 - WHCP | #VALUE! |  |  | 45 |  |  | 0%
P02-EPC-P1690 | چاه شماره 28 | P | A | Manufacturing / Fabrication / Supply- W028 - WHCP | #VALUE! |  |  | 45 |  |  | 0%
P02-EPC-C1170 | چاه شماره 28 | C | A | Site Preparation W028 | #VALUE! |  |  | 0 |  |  | 53%
P02-EPC-C1440 | چاه شماره 28 | C | A | Construction of Right of Way - W028 | #VALUE! |  |  | 131 |  |  | 0%
P02-EPC-C1240 | چاه شماره 28 | C | A | Excavation of Mud Channel- W028 | 0 | 0 | 0 | 25 |  |  | 0%
P02-EPC-C1310 | چاه شماره 28 | C | A | Installation sealling Layer of Mud Pit- W028 | 0 | 0 | 0 | 1900-02-05 |  |  | 0
P02-EPC-C1460 | چاه شماره 28 | C | A | Construction & Installation of Shelter for Wellhead Control Panel- W028 | 0 | 0 | 0 | 1900-05-10 |  |  | 0

## 6
0 |  |  |  | جدول شماره 6 : ماتریس علل تأخیرات پروژه |  |  |  | 12 | 14 | 15 | 17 | 18 | 20 | 21 | 23 | 24 | 26 | 27 | 29 | 1 |  |  |  | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24
| كد فعاليت/بسته (ID A s) | نام فعاليت/بسته | بسته كاري | علل تأخیر متأثر در هر فعالیت |  | شروع | پایان | شروع | پایان | شروع | پایان | شروع | پایان | شروع | پایان | شروع | پایان | شروع | پایان | time axis 2021-07-01 to 2023-06-22 12:00
|  |  |  | كد تاخير (ID D s) | عنوان علل تأخیر | time axis 2021-07-01 to 2023-06-22 12:00
[20 empty] | شش ماهه اول سال اول | [23 empty] | شش ماهه دوم سال اول | [23 empty] | شش ماهه اول سال دوم | [23 empty] | شش ماهه دوم سال دوم
| P12-EPC-E1000 | Endorsement Report For Basic Design & Scope of Work | ايستگاه گاز | M01 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-14 | 2021-09-07 | 2021-10-03 | 2021-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | P12-EPC-E1000 | 1P12-EPC-E1000 | ايستگاه گاز | M01-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-09-07 | 2021-06-23 | 2021-09-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E1570 | Process Flow Diagram (PFD) | ايستگاه گاز | E01 | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز | 2021-06-23 | 2021-12-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | M02 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-28 | 2021-09-06 | 2021-10-31 | 2021-11-14 | 2021-12-14 | 2022-01-02 | 2022-01-22 | 2022-02-22 | 2022-03-26 | 2022-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | P12-EPC-E1570 | 2P12-EPC-E1570 | ايستگاه گاز | E01-M02- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-07-04 | 2021-12-06 | 2021-07-04 | 2021-09-06 | 2021-07-04 | 2021-11-14 | 2021-07-04 | 2022-01-02 | 2021-07-04 | 2022-02-22 | 2021-07-04 | 2022-04-30 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E1540 | Process Data Sheets For Gas Compressors Packages | ايستگاه گاز | M03 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-11-21 | 2021-11-27 | 2022-01-15 | 2022-01-29 | 2022-04-09 | 2022-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E01 | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز | 2021-06-23 | 2021-12-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | P12-EPC-E1540 | 3P12-EPC-E1540 | ايستگاه گاز | M03-E01- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-07-31 | 2021-12-06 | 2021-07-31 | 2021-11-27 | 2021-07-31 | 2022-01-29 | 2021-07-31 | 2022-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E2480 | Mechanical Data Sheets For Gas Compressors Packages | ايستگاه گاز | M04 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-09-26 | 2021-10-11 | 2021-10-31 | 2021-11-08 | 2021-11-28 | 2021-12-20 | 2022-01-26 | 2022-02-22 | 2022-03-19 | 2022-03-26 | 2022-05-04 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E01 | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز | 2021-06-23 | 2021-12-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E03 | عدم نهایی سازي ديتاشيت مكانيك پكيج هاي كمپرسور | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | P12-EPC-E2480 | 4P12-EPC-E2480 | ايستگاه گاز | M04-E01-E03 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-12 | 2022-07-22 | 2021-08-12 | 2022-07-22 | 2021-08-12 | 2021-11-08 | 2021-08-12 | 2021-12-20 | 2021-08-12 | 2022-02-22 | 2021-08-12 | 2022-03-26 | 2021-08-12 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E7980 | TBE For Gas Compressors | ايستگاه گاز | M05 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2022-02-16 | 2022-02-27 | 2022-03-19 | 2022-05-07 | 2022-06-25 | 2022-06-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E05 | عدم نهايي سازي MR كمپرسورها | 2021-11-28 | 2022-07-22 | 2021-11-28 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E03 | عدم نهایی سازي ديتاشيت مكانيك پكيج هاي كمپرسور | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-02-02 | 2022-07-22 | 2022-02-02 | 2022-07-22 | 2022-02-02 | 2022-07-22 | 2022-02-02 | 2022-07-22 | 2022-02-02 | 2022-07-22 | 2022-02-02 | 2022-07-22 | 2022-02-02 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | P12-EPC-E7980 | 5P12-EPC-E7980 | ايستگاه گاز | M05-E05-E03 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-16 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 2021-08-16 | 2022-05-07 | 2021-08-16 | 2022-06-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E7970 | PMR For Gas Compressors | ايستگاه گاز | M06 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-12-12 | 2021-12-15 | 2022-01-18 | 2022-01-30 | 2022-02-27 | 2022-03-05 | 2022-06-20 | 2022-08-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E03 | عدم نهایی سازي ديتاشيت مكانيك پكيج هاي كمپرسور | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-28 | 2022-07-22 | 2021-11-28 | 2022-07-22 | 2021-11-28 | 2022-07-22 | 2021-11-28 | 2022-07-22 | 2021-11-28 | 2022-07-22 | 2021-11-28 | 2022-07-22 | 2021-11-28 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | P12-EPC-E7970 | 6P12-EPC-E7970 | ايستگاه گاز | M06-E02-E03 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-03 | 2022-07-22 | 2021-09-03 | 2022-07-22 | 2021-09-03 | 2022-01-30 | 2021-09-03 | 2022-03-05 | 2021-09-03 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-P1000 | Tendering & Selection For Gas Compressors | ايستگاه گاز | E04 | عدم نهايي سازي TBE كمپرسورها | 2022-02-02 | 2022-07-22 | 2022-02-02 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E03 | عدم نهایی سازي ديتاشيت مكانيك پكيج هاي كمپرسور | 2021-09-12 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-02-26 | 2022-07-22 | 2022-02-26 | 2022-07-22 | 2022-02-26 | 2022-07-22 | 2022-02-26 | 2022-07-22 | 2022-02-26 | 2022-07-22 | 2022-02-26 | 2022-07-22 | 2022-02-26 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | P12-EPC-P1000 | 7P12-EPC-P1000 | ايستگاه گاز | E04-E03- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 0 | 2022-07-22 | 2021-08-11 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-P1010 | Contract Effectiveness / PO For Gas Compressors | ايستگاه گاز | P01 | عدم انتخاب سازنده كمپرسورها | 2022-02-26 | 2022-07-22 | 2022-02-26 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت-قسط اول | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F02 | تاخير در دريافت پيش پرداخت-قسط دوم | 2022-01-05 | 2022-06-01 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | P12-EPC-P1010 | 8P12-EPC-P1010 | ايستگاه گاز | P01-F01-F02 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-10 | 0 | 2021-10-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-P1020 | Manufacturing / Fabrication / Supply For Gas Compressors | ايستگاه گاز | P02 | عدم عقد قرارداد براي تامين كمپرسورها | 2022-07-22 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | P12-EPC-P1020 | 9P12-EPC-P1020 | ايستگاه گاز | P02-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-09 | 2022-12-20 | 2021-11-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1060 | Process Flow Diagram - W018S | چاه شماره 18 | M07 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-18 | 2021-09-07 | 2021-11-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E06 | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 18 | 2021-06-23 | 2021-10-13 | 2021-08-04 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | P01-EPC-E1060 | 10P01-EPC-E1060 | چاه شماره 18 | M07-E06- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-31 | 2021-10-13 | 2021-08-31 | 2022-05-25 | 2021-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1860 | Specification For WHCP/HPU-W018S | چاه شماره 18 | M09 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-08-22 | 2021-09-14 | 2021-10-24 | 2022-01-02 | 2022-01-24 | 2022-01-30 | 2022-04-10 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E14 | تطويل در نهايي سازي Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-04-25 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | P01-EPC-E1860 | 11P01-EPC-E1860 | چاه شماره 18 | M09-E14- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-14 | 2022-03-27 | 2021-08-14 | 2022-03-27 | 2021-08-14 | 2022-01-02 | 2021-08-14 | 2022-01-30 | 2021-08-14 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E2470 | Rough Grading Plans -W018S | چاه شماره 18 | E20 | تطويل در نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-30 | 2022-03-13 | 2021-10-30 | 2022-03-13 | 2021-10-30 | 2022-03-13 | 2021-10-30 | 2022-03-13 | 2021-10-30 | 2022-03-13 | 2021-10-30 | 2022-03-13 | 2021-10-30 | 2022-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | P01-EPC-E2470 | 12P01-EPC-E2470 | چاه شماره 18 | E20-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1070 | P&ID - W018S | چاه شماره 18 | M11 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-23 | 2021-09-06 | 2021-11-15 | 2021-11-27 | 2021-12-29 | 2022-01-03 | 2022-03-14 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E10 | عدم نهايي سازي PMS-چاه 18 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | P01-EPC-E1070 | 13P01-EPC-E1070 | چاه شماره 18 | M11-E10- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-10 | 2021-12-15 | 2021-09-10 | 2021-12-15 | 2021-09-10 | 2021-11-27 | 2021-09-10 | 2022-01-03 | 2021-09-10 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1300 | Piping Material Specification-W018S | چاه شماره 18 | M12 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-09-07 | 2021-09-14 | 2021-10-18 | 2021-11-08 | 2021-12-29 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E08 | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 18 | 2022-01-10 | 2022-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | P01-EPC-E1300 | 14P01-EPC-E1300 | چاه شماره 18 | M12-E08- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-01-02 | 2021-12-15 | 2022-01-02 | 2021-09-14 | 2022-01-02 | 2021-11-08 | 2022-01-02 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1870 | Data Sheets For WHCP/HPU - Wellheads-W018S | چاه شماره 18 | M13 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-09-05 | 2021-09-20 | 2021-11-23 | 2021-11-27 | 2022-01-04 | 2022-01-08 | 2022-07-02 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E14 | تطويل در نهايي سازي Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-04-25 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | P01-EPC-E1870 | 15P01-EPC-E1870 | چاه شماره 18 | M13-E14- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-24 | 2022-04-25 | 2021-08-24 | 2022-03-27 | 2021-08-24 | 2021-11-27 | 2021-08-24 | 2022-01-08 | 2021-08-24 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E2450 | General Civil Layout - W018S | چاه شماره 18 | E20 | تطويل در نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | P01-EPC-E2450 | 16P01-EPC-E2450 | چاه شماره 18 | E20-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-26 | 2021-12-27 | 2021-08-26 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1810 | Pipeline Corrosion Study & Material Selection Report-W018S | چاه شماره 18 | M16 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-11-10 | 2021-11-21 | 2021-12-18 | 0 | 2022-03-14 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E08 | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 18 | 2022-01-10 | 2022-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | P01-EPC-E1810 | 17P01-EPC-E1810 | چاه شماره 18 | M16-E08- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-03-02 | 2022-08-13 | 2022-03-02 | 2021-11-21 | 2022-03-02 | 0 | 2022-03-02 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E3590 | PMR For WHCP/HPU - W018S | چاه شماره 18 | M17 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-11-29 | 2021-12-07 | 2022-01-30 | 2022-02-01 | 2022-07-04 | 2022-08-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E14 | تطويل در نهايي سازي Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-04-25 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | P01-EPC-E3590 | 18P01-EPC-E3590 | چاه شماره 18 | M17-E14- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-21 | 2022-04-25 | 2021-09-21 | 2022-03-27 | 2021-09-21 | 2022-02-01 | 2021-09-21 | 2022-08-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E3560 | PMR For Flowline - W018S | چاه شماره 18 | E08 | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 18 | 2022-01-10 | 2022-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | P05 | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریانی-چاه 18 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | P01-EPC-E3560 | 19P01-EPC-E3560 | چاه شماره 18 | E08-P05- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-15 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1670 | Tendering & Selection- W018S-WHCP | چاه شماره 18 | E18 | تطويل در نهايي سازي MR برای WHCP-چاه 18 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E14 | تطويل در نهايي سازي Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-04-25 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | P01-EPC-P1670 | 20P01-EPC-P1670 | چاه شماره 18 | E18-E14- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-15 | 2022-05-25 | 2021-10-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1550 | Tendering & Selection- W018S- Line pipe | چاه شماره 18 | E08 | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 18 | 2022-01-10 | 2022-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | P05 | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریانی-چاه 18 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | P01-EPC-P1550 | 21P01-EPC-P1550 | چاه شماره 18 | E08-P05- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1680 | Contract Effectiveness / PO- W018S- WHCP | چاه شماره 18 | E18 | تطويل در نهايي سازي MR برای WHCP-چاه 18 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F02 | تاخير در دريافت پيش پرداخت-قسط دوم | 2022-01-05 | 2022-06-01 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت-قسط اول | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | P01-EPC-P1680 | 22P01-EPC-P1680 | چاه شماره 18 | E18-F02-F01 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-25 | 2022-06-12 | 2021-10-25 | 2022-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1560 | Contract Effectiveness / PO- W018S-Line pipe | چاه شماره 18 | P05 | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریانی-چاه 18 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F02 | تاخير در دريافت پيش پرداخت-قسط دوم | 2022-01-05 | 2022-06-01 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت-قسط اول | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | P01-EPC-P1560 | 23P01-EPC-P1560 | چاه شماره 18 | P05-F02-F01 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1690 | Manufacturing / Fabrication / Supply- W018S-WHCP | چاه شماره 18 | P11 | تطويل در نهايي سازي عقد قرارداد با سازنده برای WHCP-چاه 18 | 2022-05-29 | 2022-07-13 | 2022-05-29 | 2022-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت-قسط اول | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F02 | تاخير در دريافت پيش پرداخت-قسط دوم | 2022-01-05 | 2022-06-01 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-06-13 | 0 | 2022-06-13 | 0 | 2022-06-13 | 0 | 2022-06-13 | 0 | 2022-06-13 | 0 | 2022-06-13 | 0 | 2022-06-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | P01-EPC-P1690 | 24P01-EPC-P1690 | چاه شماره 18 | P11-F01-F02 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-30 | 0 | 2021-10-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1570 | Manufacturing / Fabrication / Supply- W018S-Line pipe | چاه شماره 18 | P05 | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریانی-چاه 18 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت-قسط اول | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F02 | تاخير در دريافت پيش پرداخت-قسط دوم | 2022-01-05 | 2022-06-01 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | P01-EPC-P1570 | 25P01-EPC-P1570 | چاه شماره 18 | P05-F01-F02 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-C1150 | Supply & Installation sealling Layer of Mud pit- W018S | چاه شماره 18 | E20 | تطويل در نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-09-20 | 2021-12-09 | 2021-09-20 | 2021-12-09 | 2021-09-20 | 2021-12-09 | 2021-09-20 | 2021-12-09 | 2021-09-20 | 2021-12-09 | 2021-09-20 | 2021-12-09 | 2021-09-20 | 2021-12-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | P01-EPC-C1150 | 26P01-EPC-C1150 | چاه شماره 18 | E20-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-02 | 2021-12-09 | 2021-10-02 | 2021-12-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-C1330 | Construction of Right of Way- W018S | چاه شماره 18 | P07 | عدم امکان آغاز ساخت لوله های جریانی-چاه 18 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | P01-EPC-C1330 | 27P01-EPC-C1330 | چاه شماره 18 | P07-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-01-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-C1350 | Construction & Installation of Shelter for Wellhead Control Panel-W018S | چاه شماره 18 | P11 | تطويل در نهايي سازي عقد قرارداد با سازنده برای WHCP-چاه 18 | 2022-05-29 | 2022-07-13 | 2022-05-29 | 2022-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | P01-EPC-C1350 | 28P01-EPC-C1350 | چاه شماره 18 | P11-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-15 | 0 | 2022-02-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1060 | Process Flow Diagram - W028 | چاه شماره 28 | M19 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-28 | 2021-09-06 | 2021-11-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E07 | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 28 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | P02-EPC-E1060 | 29P02-EPC-E1060 | چاه شماره 28 | M19-E07- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-05 | 2022-05-25 | 2021-09-05 | 2022-05-25 | 2021-09-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1860 | Specification For WHCP/HPU - W028 | چاه شماره 28 | M21 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-08-22 | 2021-09-14 | 2021-10-24 | 2022-01-02 | 2022-01-24 | 2022-01-30 | 2022-04-10 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E14 | تطويل در نهايي سازي Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-04-25 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | P02-EPC-E1860 | 30P02-EPC-E1860 | چاه شماره 28 | M21-E14- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-05 | 2022-03-27 | 2022-02-05 | 2022-03-27 | 2022-02-05 | 2022-01-02 | 2022-02-05 | 2022-01-30 | 2022-02-05 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E2460 | General Civil Layout -W028 | چاه شماره 28 | M22 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-11-02 | 2021-11-22 | 2022-03-26 | 2022-03-25 | 2022-06-15 | 2022-06-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E20 | تطويل در نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-19 | 2023-01-20 | 2021-10-19 | 2023-01-20 | 2021-10-19 | 2023-01-20 | 2021-10-19 | 2023-01-20 | 2021-10-19 | 2023-01-20 | 2021-10-19 | 2023-01-20 | 2021-10-19 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | P02-EPC-E2460 | 31P02-EPC-E2460 | چاه شماره 28 | M22-E20- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-07-23 | 2021-12-27 | 2021-07-23 | 2021-12-27 | 2021-07-23 | 2022-03-25 | 2021-07-23 | 2022-06-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E2480 | Rough Grading Plans -W028 | چاه شماره 28 | M24 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-10-25 | 2021-10-18 | 2022-02-20 | 2022-02-12 | 2022-03-28 | 2022-04-03 | 2022-04-24 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E23 | تطويل در نهايي سازي طرح مديريت پسماند چاه 28 | 2021-10-19 | 2022-02-28 | 2021-10-19 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | P02-EPC-E2480 | 32P02-EPC-E2480 | چاه شماره 28 | M24-E23- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-07-23 | 2022-02-28 | 2021-07-23 | 2022-04-10 | 2021-07-23 | 2022-02-12 | 2021-07-23 | 2022-04-03 | 2021-07-23 | 2022-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E3530 | PMR For Line Pipes - W028 | چاه شماره 28 | P08 | عدم امکان آغاز ساخت لوله های جریانی-چاه 28 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E09 | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 28 | 2022-01-10 | 2022-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 2021-12-06 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | P02-EPC-E3530 | 33P02-EPC-E3530 | چاه شماره 28 | P08-E09- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-18 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1070 | P&ID - W028 | چاه شماره 28 | M26 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-09-05 | 2021-09-08 | 2021-11-15 | 2021-11-27 | 2021-12-29 | 2022-01-03 | 2022-03-14 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E11 | عدم نهايي سازي PMS چاه 28 | 2021-11-28 | 2022-05-25 | 2021-11-28 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E07 | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 28 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | P02-EPC-E1070 | 34P02-EPC-E1070 | چاه شماره 28 | M26-E11-E07 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-15 | 2022-05-25 | 2021-09-15 | 2022-05-25 | 2021-09-15 | 2021-11-27 | 2021-09-15 | 2022-01-03 | 2021-09-15 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1880 | Data Sheets For WHCP/HPU - Wellheads - W028 | چاه شماره 28 | M27 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-09-05 | 2021-09-20 | 2021-11-23 | 2021-11-27 | 2022-01-04 | 2022-01-08 | 2022-07-02 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E14 | تطويل در نهايي سازي Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-04-25 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 2021-08-22 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | P02-EPC-E1880 | 35P02-EPC-E1880 | چاه شماره 28 | M27-E14- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-25 | 2022-04-25 | 2022-02-25 | 2022-03-27 | 2022-02-25 | 2021-11-27 | 2022-02-25 | 2022-01-08 | 2022-02-25 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1820 | Pipeline Corrosion Study & Material Selection Report - W028 | چاه شماره 28 | M28 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-11-10 | 2021-11-21 | 2021-12-18 | 2022-03-07 | 2022-03-14 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E09 | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 28 | 2022-01-10 | 2022-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 2021-10-27 | 2022-10-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | P02-EPC-E1820 | 36P02-EPC-E1820 | چاه شماره 28 | M28-E09- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-03-02 | 2022-08-13 | 2022-03-02 | 2021-11-21 | 2022-03-02 | 2022-03-07 | 2022-03-02 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E3590 | PMR For WHCP/HPU - W028 | چاه شماره 28 | M29 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-11-29 | 2021-12-07 | 2022-01-30 | 2022-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E14 | تطويل در نهايي سازي Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-04-25 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 2021-11-15 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | P02-EPC-E3590 | 37P02-EPC-E3590 | چاه شماره 28 | M29-E14- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-16 | 2022-04-25 | 2021-10-16 | 2022-03-27 | 2021-10-16 | 2022-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1180 | Piping Material Specification - W028 | چاه شماره 28 | M30 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی واقع در مسير بحراني | 0 | 0 | 2021-12-12 | 2021-12-26 | 2022-04-13 | 2022-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E09 | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 28 | 2022-01-10 | 2022-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-28 | 0 | 2021-11-28 | 0 | 2021-11-28 | 0 | 2021-11-28 | 0 | 2021-11-28 | 0 | 2021-11-28 | 0 | 2021-11-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | P02-EPC-E1180 | 38P02-EPC-E1180 | چاه شماره 28 | M30-E09- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-10 | 2022-08-13 | 2022-02-10 | 2021-12-26 | 2022-02-10 | 2022-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1550 | Tendering & Selection- W028 - Line pipe | چاه شماره 28 | E09 | انجام مجدد مطالعات پایه در فاز مطالعات Detail و تطويل در نهايي شدن مطالعات خوردگي-چاه 28 | 2022-01-10 | 2022-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | P06 | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریان-چاه 28 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | P02-EPC-P1550 | 39P02-EPC-P1550 | چاه شماره 28 | E09-P06- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-08 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1560 | Contract Effectiveness / PO- W028 - Line pipe | چاه شماره 28 | P06 | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریان-چاه 28 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت-قسط اول | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F02 | تاخير در دريافت پيش پرداخت-قسط دوم | 2022-01-05 | 2022-06-01 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | P02-EPC-P1560 | 40P02-EPC-P1560 | چاه شماره 28 | P06-F01-F02 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1570 | Manufacturing / Fabrication / Supply- W028 - Line pipe | چاه شماره 28 | P06 | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریان-چاه 28 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | P02-EPC-P1570 | 41P02-EPC-P1570 | چاه شماره 28 | P06-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1670 | Tendering & Selection- W028 - WHCP | چاه شماره 28 | E14 | تطويل در نهايي سازي Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-04-25 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | P02-EPC-P1670 | 42P02-EPC-P1670 | چاه شماره 28 | E14-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-07 | 2022-04-25 | 2021-11-07 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1680 | Contract Effectiveness / PO- W028 - WHCP | چاه شماره 28 | P06 | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریان-چاه 28 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت-قسط اول | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 2022-05-29 | 2022-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | P02-EPC-P1680 | 43P02-EPC-P1680 | چاه شماره 28 | P06-F01- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-17 | 2022-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1690 | Manufacturing / Fabrication / Supply- W028 - WHCP | چاه شماره 28 | P06 | عدم امکان تعيين تكليف مشخصات لوله ها و سازنده خريد لوله های جریان-چاه 28 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-06-13 | 2023-01-20 | 2022-06-13 | 2023-01-20 | 2022-06-13 | 2023-01-20 | 2022-06-13 | 2023-01-20 | 2022-06-13 | 2023-01-20 | 2022-06-13 | 2023-01-20 | 2022-06-13 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | P02-EPC-P1690 | 44P02-EPC-P1690 | چاه شماره 28 | P06-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-22 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1170 | Site Preparation W028 | چاه شماره 28 | F01 | تاخير در دريافت پيش پرداخت-قسط اول | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F02 | تاخير در دريافت پيش پرداخت-قسط دوم | 2022-01-05 | 2022-06-01 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-09-15 | 2023-01-20 | 2021-09-15 | 2023-01-20 | 2021-09-15 | 2023-01-20 | 2021-09-15 | 2023-01-20 | 2021-09-15 | 2023-01-20 | 2021-09-15 | 2023-01-20 | 2021-09-15 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | P02-EPC-C1170 | 45P02-EPC-C1170 | چاه شماره 28 | F01-F02- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-17 | 2022-06-01 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1440 | Construction of Right of Way - W028 | چاه شماره 28 | P08 | عدم امکان آغاز ساخت لوله های جریانی-چاه 28 | 2021-06-23 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | P02-EPC-C1440 | 46P02-EPC-C1440 | چاه شماره 28 | P08-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1240 | Excavation of Mud Channel- W028 | چاه شماره 28 | E23 | تطويل در نهايي سازي طرح مديريت پسماند چاه 28 | 2021-10-19 | 2022-02-28 | 2021-10-19 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | P02-EPC-C1240 | 47P02-EPC-C1240 | چاه شماره 28 | E23-E24- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-24 | 2022-02-28 | 2021-09-24 | 2022-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1310 | Installation sealling Layer of Mud Pit- W028 | چاه شماره 28 | E23 | تطويل در نهايي سازي طرح مديريت پسماند چاه 28 | 2021-10-19 | 2022-02-28 | 2021-10-19 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | P02-EPC-C1310 | 48P02-EPC-C1310 | چاه شماره 28 | E23-E24-E25 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-05 | 0 | 2021-10-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1460 | Construction & Installation of Shelter for Wellhead Control Panel- W028 | چاه شماره 28 | P14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | P02-EPC-C1460 | 49P02-EPC-C1460 | چاه شماره 28 | P14-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P07-EPC-E2580 | General Civil Layout - BK14 | چاه شماره 14 | E26 | ارسال طرح جدید مدیریت پسماند بسته موقعیت چاه BK14 | 2022-09-19 | 2022-11-05 | 2022-09-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-07-04 | 2022-07-28 | 2022-07-04 | 2022-07-28 | 2022-07-04 | 2022-07-28 | 2022-07-04 | 2022-07-28 | 2022-07-04 | 2022-07-28 | 2022-07-04 | 2022-07-28 | 2022-07-04 | 2022-07-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-09-19 | 2023-01-20 | 2022-09-19 | 2023-01-20 | 2022-09-19 | 2023-01-20 | 2022-09-19 | 2023-01-20 | 2022-09-19 | 2023-01-20 | 2022-09-19 | 2023-01-20 | 2022-09-19 | 2023-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | P07-EPC-E2580 | 50P07-EPC-E2580 | چاه شماره 14 | E26-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-07-04 | 2022-11-05 | 2022-07-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| مهر امضا پيمانكار | [8 empty] | مهر امضاء كارفرما | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
عنوان علل تأخیر = IFERROR(VLOOKUP([كد تاخير (ID D s)],'4'!$C:$H,3,0),0)

## 7
|  |  |  | جدول شماره 7 : گانت چارت تأخیرات پروژه | [15 empty] | 1 |  |  |  | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18
رديف | كد تاخير | نوع تاخير | كد فعاليت | عنوان فعاليت/بسته متاثر از تاخيرات | بحراني/ غيربحراني | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | Total Float | طول دوره تاثير (ماه) | time axis 2021-07-01 to 2022-12-22 02:24
[8 empty] | شماره 1 | شماره 1 | شماره 2 | شماره 2 | شماره 3 | شماره 3 | شماره 4 | شماره 4 | شماره 5 | شماره 5 | time axis 2021-07-01 to 2022-12-22 02:24
[6 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | time axis 2021-07-01 to 2022-12-22 02:24
1 | M01-- | مديريتي | P12-EPC-E1000 | Endorsement Report For Basic Design & Scope of Work | بحراني | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-09-07 | 2021-06-23 | 2021-09-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.377 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | E01-M02- | مديريتي مهندسي | P12-EPC-E1570 | Process Flow Diagram (PFD) | بحراني | 2021-07-04 | 2021-12-06 | 2021-07-04 | 2021-09-06 | 2021-07-04 | 2021-11-14 | 2021-07-04 | 2022-01-02 | 2021-07-04 | 2022-02-22 | 2021-07-04 | 2022-04-30 | 0 | 29.9016 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | M03-E01- | مديريتي مهندسي | P12-EPC-E1540 | Process Data Sheets For Gas Compressors Packages | بحراني | 2021-07-31 | 2021-12-06 | 2021-07-31 | 2021-11-27 | 2021-07-31 | 2022-01-29 | 2021-07-31 | 2022-05-08 | 0 | 0 | 0 | 0 | 0 | 19.082 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | M04-E01-E03 | مديريتي مهندسي | P12-EPC-E2480 | Mechanical Data Sheets For Gas Compressors Packages | بحراني | 2021-08-12 | 2022-07-22 | 2021-08-12 | 2022-07-22 | 2021-08-12 | 2021-11-08 | 2021-08-12 | 2021-12-20 | 2021-08-12 | 2022-02-22 | 2021-08-12 | 2022-03-26 | 0 | 32.1967 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | M05-E05-E03 | مديريتي مهندسي | P12-EPC-E7980 | TBE For Gas Compressors | بحراني | 2021-08-16 | 2022-07-22 | 2021-09-12 | 2022-07-22 | 2021-08-16 | 2022-05-07 | 2021-08-16 | 2022-06-27 | 0 | 0 | 0 | 0 | 0 | 29.2459 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | M06-E02-E03 | مديريتي مهندسي | P12-EPC-E7970 | PMR For Gas Compressors | بحراني | 2021-09-03 | 2022-07-22 | 2021-09-03 | 2022-07-22 | 2021-09-03 | 2022-01-30 | 2021-09-03 | 2022-03-05 | 2021-09-03 | 2022-07-22 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | E04-E03- | مهندسي | P12-EPC-P1000 | Tendering & Selection For Gas Compressors | بحراني | 0 | 2022-07-22 | 2021-08-11 | 2022-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.3115 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | P01-F01-F02 | كالا مالي | P12-EPC-P1010 | Contract Effectiveness / PO For Gas Compressors | بحراني | 2021-10-10 | 0 | 2021-10-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1458.3279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | P02-- | كالا | P12-EPC-P1020 | Manufacturing / Fabrication / Supply For Gas Compressors | بحراني | 2021-11-09 | 2022-12-20 | 2021-11-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1459.3115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
10 | M07-E06- | مديريتي مهندسي | P01-EPC-E1060 | Process Flow Diagram - W018S | غير بحراني | 2021-08-31 | 2021-10-13 | 2021-08-31 | 2022-05-25 | 2021-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | -1448.2623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | M09-E14- | مديريتي مهندسي | P01-EPC-E1860 | Specification For WHCP/HPU-W018S | غير بحراني | 2021-08-14 | 2022-03-27 | 2021-08-14 | 2022-03-27 | 2021-08-14 | 2022-01-02 | 2021-08-14 | 2022-01-30 | 2021-08-14 | 2022-03-27 | 0 | 0 | 22 | 24.918 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | E20-- | مهندسي | P01-EPC-E2470 | Rough Grading Plans -W018S | غير بحراني | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 4.6885 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | M11-E10- | مديريتي مهندسي | P01-EPC-E1070 | P&ID - W018S | غير بحراني | 2021-09-10 | 2021-12-15 | 2021-09-10 | 2021-12-15 | 2021-09-10 | 2021-11-27 | 2021-09-10 | 2022-01-03 | 2021-09-10 | 2022-05-01 | 0 | 0 | 39 | 17.1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | M12-E08- | مديريتي مهندسي | P01-EPC-E1300 | Piping Material Specification-W018S | غير بحراني | 2022-01-02 | 2021-12-15 | 2022-01-02 | 2021-09-14 | 2022-01-02 | 2021-11-08 | 2022-01-02 | 2021-12-15 | 0 | 0 | 0 | 0 | 153 | -6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | M13-E14- | مديريتي مهندسي | P01-EPC-E1870 | Data Sheets For WHCP/HPU - Wellheads-W018S | غير بحراني | 2021-08-24 | 2022-04-25 | 2021-08-24 | 2022-03-27 | 2021-08-24 | 2021-11-27 | 2021-08-24 | 2022-01-08 | 2021-08-24 | 2022-07-22 | 0 | 0 | 22 | 25.541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | E20-- | مهندسي | P01-EPC-E2450 | General Civil Layout - W018S | غير بحراني | 2021-08-26 | 2021-12-27 | 2021-08-26 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 4.0328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | M16-E08- | مديريتي مهندسي | P01-EPC-E1810 | Pipeline Corrosion Study & Material Selection Report-W018S | غير بحراني | 2022-03-02 | 2022-08-13 | 2022-03-02 | 2021-11-21 | 2022-03-02 | 0 | 2022-03-02 | 2022-04-01 | 0 | 0 | 0 | 0 | 192 | -1465.3443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | M17-E14- | مديريتي مهندسي | P01-EPC-E3590 | PMR For WHCP/HPU - W018S | غير بحراني | 2021-09-21 | 2022-04-25 | 2021-09-21 | 2022-03-27 | 2021-09-21 | 2022-02-01 | 2021-09-21 | 2022-08-16 | 0 | 0 | 0 | 0 | 22 | 21.2787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | E08-P05- | مهندسي كالا | P01-EPC-E3560 | PMR For Line pipes - W018S | غير بحراني | 2021-11-15 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
20 | E18-E14- | مهندسي | P01-EPC-P1670 | Tendering & Selection- W018S-WHCP | غير بحراني | 2021-10-15 | 2022-05-25 | 2021-10-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 7.2787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | E08-P05- | مهندسي كالا | P01-EPC-P1550 | Tendering & Selection- W018S- Line pipe | غير بحراني | 2021-10-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | E18-F02-F01 | مهندسي مالي | P01-EPC-P1680 | Contract Effectiveness / PO- W018S- WHCP | غير بحراني | 2021-10-25 | 2022-06-12 | 2021-10-25 | 2022-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 7.541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | P05-F02-F01 | كالا مالي | P01-EPC-P1560 | Contract Effectiveness / PO- W018S-Line pipe | غير بحراني | 2021-11-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | P11-F01-F02 | كالا مالي | P01-EPC-P1690 | Manufacturing / Fabrication / Supply- W018S-WHCP | غير بحراني | 2021-10-30 | 0 | 2021-10-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -1458.9836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | P05-F01-F02 | كالا مالي | P01-EPC-P1570 | Manufacturing / Fabrication / Supply- W018S-Line pipe | غير بحراني | 2021-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | E20-- | مهندسي | P01-EPC-C1150 | Supply & Installation sealling Layer of Mud pit- W018S | غير بحراني | 2021-10-02 | 2021-12-09 | 2021-10-02 | 2021-12-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2.2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | P07-- | كالا | P01-EPC-C1330 | Construction of Right of Way- W018S | غير بحراني | 2022-01-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | P11-- | كالا | P01-EPC-C1350 | Construction & Installation of Shelter for Wellhead Control Panel-W018S | غير بحراني | 2022-02-15 | 0 | 2022-02-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | -1462.5246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | M19-E07- | مديريتي مهندسي | P02-EPC-E1060 | Process Flow Diagram - W028 | غير بحراني | 2021-09-05 | 2022-05-25 | 2021-09-05 | 2022-05-25 | 2021-09-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | -1448.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | M21-E14- | مديريتي مهندسي | P02-EPC-E1860 | Specification For WHCP/HPU - W028 | غير بحراني | 2022-02-05 | 2022-03-27 | 2022-02-05 | 2022-03-27 | 2022-02-05 | 2022-01-02 | 2022-02-05 | 2022-01-30 | 2022-02-05 | 2022-03-27 | 0 | 0 | 197 | 1.9672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | M22-E20- | مديريتي مهندسي | P02-EPC-E2460 | General Civil Layout -W028 | بحراني | 2021-07-23 | 2021-12-27 | 2021-07-23 | 2021-12-27 | 2021-07-23 | 2022-03-25 | 2021-07-23 | 2022-06-11 | 0 | 0 | 0 | 0 | 0 | 23.7705 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | M24-E23- | مديريتي مهندسي | P02-EPC-E2480 | Rough Grading Plans -W028 | بحراني | 2021-07-23 | 2022-02-28 | 2021-07-23 | 2022-04-10 | 2021-07-23 | 2022-02-12 | 2021-07-23 | 2022-04-03 | 2021-07-23 | 2022-04-10 | 0 | 0 | 0 | 32.1311 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | P08-E09- | مهندسي كالا | P02-EPC-E3530 | PMR For Line Pipes - W028 | غير بحراني | 2021-09-18 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
34 | M26-E11-E07 | مديريتي مهندسي | P02-EPC-E1070 | P&ID - W028 | غير بحراني | 2021-09-15 | 2022-05-25 | 2021-09-15 | 2022-05-25 | 2021-09-15 | 2021-11-27 | 2021-09-15 | 2022-01-03 | 2021-09-15 | 2022-05-01 | 0 | 0 | 44 | 21.7377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | M27-E14- | مديريتي مهندسي | P02-EPC-E1880 | Data Sheets For WHCP/HPU - Wellheads - W028 | غير بحراني | 2022-02-25 | 2022-04-25 | 2022-02-25 | 2022-03-27 | 2022-02-25 | 2021-11-27 | 2022-02-25 | 2022-01-08 | 2022-02-25 | 2022-07-22 | 0 | 0 | 197 | 1.2787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | M28-E09- | مديريتي مهندسي | P02-EPC-E1820 | Pipeline Corrosion Study & Material Selection Report - W028 | غير بحراني | 2022-03-02 | 2022-08-13 | 2022-03-02 | 2021-11-21 | 2022-03-02 | 2022-03-07 | 2022-03-02 | 2022-04-01 | 0 | 0 | 0 | 0 | 192 | -2.1639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | M29-E14- | مديريتي مهندسي | P02-EPC-E3590 | PMR For WHCP/HPU - W028 | غير بحراني | 2021-10-16 | 2022-04-25 | 2021-10-16 | 2022-03-27 | 2021-10-16 | 2022-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 8.8525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | M30-E09- | مديريتي مهندسي | P02-EPC-E1180 | Piping Material Specification - W028 | غير بحراني | 2022-02-10 | 2022-08-13 | 2022-02-10 | 2021-12-26 | 2022-02-10 | 2022-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 2.0656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | E09-P06- | مهندسي كالا | P02-EPC-P1550 | Tendering & Selection- W028 - Line pipe | غير بحراني | 2021-10-08 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | P06-F01-F02 | كالا مالي | P02-EPC-P1560 | Contract Effectiveness / PO- W028 - Line pipe | غير بحراني | 2021-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | P06-- | كالا | P02-EPC-P1570 | Manufacturing / Fabrication / Supply- W028 - Line pipe | غير بحراني | 2021-10-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | E14-- | مهندسي | P02-EPC-P1670 | Tendering & Selection- W028 - WHCP | غير بحراني | 2021-11-07 | 2022-04-25 | 2021-11-07 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 4.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | P06-F01- | كالا مالي | P02-EPC-P1680 | Contract Effectiveness / PO- W028 - WHCP | غير بحراني | 2021-11-17 | 2022-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | P06-- | كالا | P02-EPC-P1690 | Manufacturing / Fabrication / Supply- W028 - WHCP | غير بحراني | 2021-11-22 | 2022-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
45 | F01-F02- | مالي | P02-EPC-C1170 | Site Preparation W028 | بحراني | 2021-08-17 | 2022-06-01 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | P08-- | كالا | P02-EPC-C1440 | Construction of Right of Way - W028 | غير بحراني | 2022-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | E23-E24- | مهندسي | P02-EPC-C1240 | Excavation of Mud Channel- W028 | غير بحراني | 2021-09-24 | 2022-02-28 | 2021-09-24 | 2022-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 6.0656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | E23-E24-E25 | مهندسي | P02-EPC-C1310 | Installation sealling Layer of Mud Pit- W028 | غير بحراني | 2021-10-05 | 0 | 2021-10-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | -1458.1639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | P14-- | كالا | P02-EPC-C1460 | Construction & Installation of Shelter for Wellhead Control Panel- W028 | غير بحراني | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | E26-- | مهندسي | P07-EPC-E2580 | General Civil Layout - BK14 | غير بحراني | 2022-07-04 | 2022-11-05 | 2022-07-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346 | -1467.082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
هم پوشاني كل تاخيرات | [18 empty] | 0 | 3 | 3 | 5 | 6 | 7 | 10 | 11 | 14 | 16 | 18 | 20 | 20 | 23 | 26 | 25 | 27 | 28 | 28 | 30 | 30 | 30 | 30 | 29 | 29 | 28 | 28 | 27 | 27 | 28 | 29 | 31 | 30 | 32 | 33 | 32 | 32 | 29 | 29 | 28 | 28 | 25 | 23 | 23 | 23 | 18 | 17 | 14 | 14 | 15 | 15 | 15 | 9 | 9 | 9 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 0
محاسبه تعداد روز هم پوشاني كل تاخيرات بر مبناي گانت |  |  | 497 |  | 497 | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
محاسبه تعداد روز هم پوشاني كل تاخيرات بر مبناي تاريخ هاي پروژه |  |  | 546.1 |  | 546.1 | [14 empty] | 2021-07-01: 2021-06-23; 2022-12-22 02:24: 2022-12-21 02:24
[20 empty] | شروع پروژه | [70 empty] | Cut-Off گزارش
مهر امضا پيمانكار | [16 empty] | مهر امضاء كارفرما
Formulas:
شروع ميلادي = VLOOKUP([رديف]&[كد فعاليت],'6'!$C:$T,'7'!H$4,0)
شروع ميلادي = VLOOKUP([رديف]&[كد فعاليت],'6'!$C:$T,'7'!J$4,0)
پايان ميلادي = VLOOKUP([رديف]&[كد فعاليت],'6'!$C:$T,'7'!I$4,0)
پايان ميلادي = VLOOKUP([رديف]&[كد فعاليت],'6'!$C:$T,'7'!K$4,0)

## Delay COde (hidden)
Code | M | مديريتي | I | فصول مشترك | E | مهندسي | P | كالا | C | اجرا | F | مالي | كد نهايي
M01-- | TRUE | مديريتي | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | مديريتي
E01-M02- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M03-E01- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M04-E01-E03 | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M05-E05-E03 | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M06-E02-E03 | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
E04-E03- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
P01-F01-F02 | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
P02-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
M07-E06- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M09-E14- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
E20-- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
M11-E10- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M12-E08- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M13-E14- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
E20-- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
M16-E08- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M17-E14- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
E08-P05- | FALSE |  | FALSE |  | TRUE | مهندسي | TRUE | كالا | FALSE |  | FALSE |  | مهندسي كالا
E18-E14- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
E08-P05- | FALSE |  | FALSE |  | TRUE | مهندسي | TRUE | كالا | FALSE |  | FALSE |  | مهندسي كالا
E18-F02-F01 | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | TRUE | مالي | مهندسي مالي
P05-F02-F01 | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
P11-F01-F02 | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
#VALUE! | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
P05-F01-F02 | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
E20-- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
P07-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
P11-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
M19-E07- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M21-E14- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M22-E20- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M24-E23- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
P08-E09- | FALSE |  | FALSE |  | TRUE | مهندسي | TRUE | كالا | FALSE |  | FALSE |  | مهندسي كالا
M26-E11-E07 | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M27-E14- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M28-E09- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M29-E14- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M30-E09- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
E09-P06- | FALSE |  | FALSE |  | TRUE | مهندسي | TRUE | كالا | FALSE |  | FALSE |  | مهندسي كالا
P06-F01-F02 | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
P06-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
E14-- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
P06-F01- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
P06-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
F01-F02- | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | TRUE | مالي | مالي
P08-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
E23-E24- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
E23-E24-E25 | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
P14-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
E26-- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
مهر و امضاء پیمانکار

## DCI (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | [67 empty] | Last Status | Last Status | [32 empty] | D00 | Rev. D00 | [32 empty] | D01 | Rev. D01 | [32 empty] | D02 | Rev. D02 | [32 empty] | D03 | Rev. D03 | [32 empty] | D04 | Rev. D04 | [32 empty] | D05 | Rev. D05 | [32 empty] | D06 | Rev. D06 | [32 empty] | D07 | Rev. D07 | [32 empty] | D08 | Rev. D08 | [32 empty] | D09 | Rev. D09 | [32 empty] | D10 | Rev. D10 | [20 empty] | c | [6 empty] | c
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [12 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2
[8 empty] | Doc. No. | Description | OLD - Description | Doc. No. | Doc. No. | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | F-Number | Final Status | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | Total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | Total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay |  | Actual Start Date | Actual Finish Date |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK | REMARK | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK | REMARK | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK | REMARK | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK | REMARK | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK
1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | GENERAL | [54 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 |  |  |  |  | GP | [17 empty] | GP
1 | 1 | 0 | 0 | 0 | 0 | 0 | 1.1 |  | Project Management | [65 empty] | GP | [17 empty] | GP
1 | 1 | 0 | 0 | 0 | 1 | 0 | 1.1.1 |  | Project Plans | [65 empty] | GP | [17 empty] | GP
1 | 1 | 0 | 0 | 0 | 1 | 1 | 1.1.1.1 | BK-GNRAL-HD-000-PM-CG-0001 | Procurement & Services Contracting Plan |  | BK-GNRAL-HD-000-PM-CG-0001 | BK-GNRAL-HD-000-PM-CG-0001 | BK | GNRAL | HD | 000 | PM | CG | 0001 | F0Z-707035 | AFD | IFC | 2022-06-12 | 0 | 0 | -44724 | 0 | -44724 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-29 |  |  | G00 | IFC | T-1016 | 44710 | 1401/03/08 | 0 | 0 | 0 | Comment Sheets\PEDCO\2-Comment sheets\5336.pdf | 44712 | 1401/03/10 | CM | 0 | BK-SUR-PRC-GEN-01-06094 | 44871 | 1401/08/15 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-1016 | 2022-05-29 | 1401/03/08 |  |  |  | Comment Sheets\PEDCO\2-Comment sheets\5336.pdf | 44712 | 1401/03/10 | CM |  | BK-SUR-PRC-GEN-01-06094 | 44871 | 1401/08/15 | CM-C2
1 | 1 | 0 | 0 | 0 | 1 | 2 | 1.1.1.2 | BK-GNRAL-PEDCO-000-GE-DN-0001 | Master Document List (MDL) & Updating |  | BK-GNRAL-PEDCO-000-GE-DN-0001 | BK-GNRAL-PEDCO-000-GE-DN-0001 | BK | GNRAL | PEDCO | 000 | GE | DN | 0001 | F0Z-707037 | AFD | IFC | 2021-07-21 | 2021-07-20 | 2021-07-18 | -1 | -2 | -3 | IFA | 2021-08-25 | 2021-09-12 | 0 | 18 | -44451 | -44433 | IFA | 2021-10-02 | 2021-10-11 | 0 | 9 | -44480 | -44471 | IFA | 2021-11-03 | 2021-10-31 | 0 | -3 | -44500 | -44503 | AFD | 2021-11-21 | 2021-12-14 | 0 | 23 | -44544 | -44521 | AFD | 2022-01-11 | 2022-01-21 | 2022-04-01 | 10 | 70 | 80 | [7 empty] | Modify | 2021-07-07 | 2022-10-29 |  | G07 | AFD | T-1566 | 44863 | 1401/08/07 | T-1566 | 44863 | 1401/08/08 | BK-SUR-ENG-GEN-01-06205 | 44884 | 1401/08/28 | CM | PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2021-07-07 | 1400/04/16 |  |  |  | L-8317 | 44403 | 1400/05/04 | CM |  | MOM-14001005 | 44411 | 1400/05/12 | CM |  | 1400/2291/136301 | 2021-07-20 | 1400/04/29 | 44395 | 1400/04/27 | CM | [10 empty] | G01-Rep | IFA | T-0032 | 44419 | 1400/05/20 |  |  |  | MDR-G01(Civil) | 44417 | 1400/05/18 | CM |  | MDR-G01(QC) | 44418 | 1400/05/19 | CM | BK-HD-PEDCO-CRS-0002(QC) | 1400-2290-180615 | 44439 | 1400/06/09 |  |  | CM | BK-PEDCO-NISOC-CRS-0002 | MOM-1400.06.21 | 44451 | 1400/06/21 |  |  | CM |  | MOM-QAQC |  | G02 | IFA | T-0097 | 44457 | 1400/06/27 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDEC-000-GE-DN-0001_G01 | [5 empty] | 1400-2290-225508 | 44475 | 1400/07/14 |  |  | CM | NISOC-CRS-BK-GNRAL-PEDEC-000-GE-DN-0001_G01 | 1400-2290-230666 | 44480 | 1400/07/19 |  |  | CM |  |  |  | G03 | IFA | T-0176 | 44489 | 1400/07/28 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDEC-000-GE-DN-0001_G02 | [5 empty] | صورتجلسه بررسی MDL-G03 (نظرات NISOC) | 44500 | 1400/08/09 |  |  | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G02 | [9 empty] | G04 | AFD | T-0211 | 44507 | 1400/08/16 |  |  |  | BK-SUR-ENG-GEN-00-02026 | 44516 | 1400/08/25 | CM | [6 empty] | 1400-2290-278160 | 44544 | 1400/08/23 |  |  | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G03 | [9 empty] | G05 | AFD | T-0397 | 44558 | 1400/10/07 |  |  |  | Comment Sheets\PEDCO\1-Letters\27286.pdf | 44625 | 1400/12/14 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G04 | [5 empty] | 1400-2294-379373 | 44582 | 1400/11/04 | 44652 | 1401/01/14 | AP | [10 empty] | G06 | AFD | T-1047 | 44719 | 1401/03/17 | T-1047 | 44719 | 1401/03/17 | Comment Sheets\PEDCO\2-Comment sheets\1047 | 44762 | 1401/04/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G05 | [5 empty] | 1401-2290-111800 | 44734 | 1401/04/01 | 44745 | 1401/04/12 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G05 | [9 empty] | G07 | AFD | T-1566 | 44863 | 1401/08/07 | T-1566 | 44863 | 1401/08/08 | BK-SUR-ENG-GEN-01-06205 | 44884 | 1401/08/28 | CM | PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G06 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G06
1 | 1 | 0 | 0 | 0 | 1 | 3 | 1.1.1.3 | BK-GNRAL-HD-000-PM-HP-0001 | EPC HSE Plan |  | BK-GNRAL-HD-000-PM-HP-0001 | BK-GNRAL-HD-000-PM-HP-0001 | BK | GNRAL | HD | 000 | PM | HP | 0001 | F0Z-707044 | AFC | IFC | 2021-08-11 | 0 | 0 | -44419 | 0 | -44419 | IFC | 2021-12-04 | 0 | 0 | -44534 | 0 | -44534 | IFA | 2022-01-19 | 0 | 0 | -44580 | 0 | -44580 | IFA | 2022-02-19 | 0 | 0 | -44611 | 0 | -44611 | AFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2022-05-22 |  | G03 | AFC | T-0983 | 44703 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0022 | 2021-07-28 | 1400/05/06 |  |  |  | L-9878 | 44419 | 1400/05/20 | RJ-C4 | [22 empty] | G00 | IFC | T-0260 | 44520 | 1400/08/29 |  |  |  | BK-SUR-HSE-HSE-00-02241 | 44541 | 1400/09/20 | CM-C2 | PEDCO-CRS-BK-HD-PEDCO-CRS-0001-G00 | [21 empty] | G01 | IFA | T-0435 | 44566 | 1400/10/15 |  |  |  | BK-SUR-HSE-HSE-00-02704 | 44577 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-HD-000-PM-HP 0001_G00 | [21 empty] | G02 | IFA | T-0553 | 44597 | 1400/11/16 |  |  |  | BK-SUR-HSE-HSE-01-04311 | 44699 | 1401/02/28 | AP | PEDCO-CRS-BK-GNRAL-HD-000-PM-HP 0001_G01 | [21 empty] | G03 | AFC | T-0983 | 44703 | 1401/03/01
1 | 1 | 0 | 0 | 0 | 1 | 4 | 1.1.1.4 | BK-GNRAL-HD-000-PM-HP-0002 | Project Emergency Response Plan (ERP) |  | BK-GNRAL-HD-000-PM-HP-0002 | BK-GNRAL-HD-000-PM-HP-0002 | BK | GNRAL | HD | 000 | PM | HP | 0002 | F0Z-707045 | AFC | IFC | 2022-02-26 | 0 | 0 | -44618 | 0 | -44618 | IFA | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | AFC | 2022-06-15 | 0 | 0 | -44727 | 0 | -44727 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-12 | 2022-06-01 |  | G02 | AFC | T-1034 | 44713 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0002_G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0577 | 2022-02-12 | 1400/11/23 |  |  |  | BK-SUR-HSE-HSE-00-03369 | 44625 | 1400/12/15 | RJ-C4 | [22 empty] | G01 | IFA | T-0984 | 44703 | 1401/03/01 |  |  |  | BK-SUR-HSE-HSE-01-04497 | 44713 | 1401/03/10 | AP | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0002_G00 | [21 empty] | G02 | AFC | T-1034 | 44713 | 1401/03/11 | [7 empty] | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0002_G00
1 | 1 | 0 | 0 | 0 | 1 | 5 | 1.1.1.5 | BK-GNRAL-HD-000-PM-HP-0003 | Guideline on Permit To Work System(PTWS) |  | BK-GNRAL-HD-000-PM-HP-0003 | BK-GNRAL-HD-000-PM-HP-0003 | BK | GNRAL | HD | 000 | PM | HP | 0003 | F0Z-707046 | IFI | IFI | 2021-12-15 | 0 | 0 | -44545 | 0 | -44545 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-01 |  |  | D00 | IFI | T-0287 | 44531 | 1400/09/10 | 0 | 0 | 0 | BK-SUR-HSE-HSE-00-02240 | 44541 | 1400/09/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0287 | 2021-12-01 | 1400/09/10 |  |  |  | BK-SUR-HSE-HSE-00-02240 | 44541 | 1400/09/11 | AP
1 | 1 | 0 | 0 | 0 | 1 | 6 | 1.1.1.6 | BK-GNRAL-HD-000-PM-HP-0004 | HSE Operation Control Procedure |  | BK-GNRAL-HD-000-PM-HP-0004 | BK-GNRAL-HD-000-PM-HP-0004 | BK | GNRAL | HD | 000 | PM | HP | 0004 | F0Z-707047 | AFC | IFC | 2022-08-09 | 0 | 0 | -44782 | 0 | -44782 | IFA | 2022-09-03 | 0 | 0 | -44807 | 0 | -44807 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-26 |  |  | G01 | IFA | T-1289 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-HSE-HSE-01-05507 | 44796 | 1401/06/01 | AP | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0004_G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-1200 | 2022-07-26 | 1401/05/04 |  |  |  | BK-SUR-HSE-HSE-01-05281 | 44772 | 1401/05/08 | CM-C2 | [22 empty] | G01 | IFA | T-1289 | 44793 | 1401/05/29 |  |  |  | BK-SUR-HSE-HSE-01-05507 | 44796 | 1401/06/01 | AP | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0004_G00
1 | 1 | 0 | 0 | 0 | 1 | 7 | 1.1.1.7 | BK-GNRAL-HD-000-PM-HP-0005 | Environmental Management Plan (EMP) |  | BK-GNRAL-HD-000-PM-HP-0005 | BK-GNRAL-HD-000-PM-HP-0005 | BK | GNRAL | HD | 000 | PM | HP | 0005 | F0Z-707048 | AFC | IFC | 2022-03-07 | 0 | 0 | -44627 | 0 | -44627 | IFA | 2022-03-27 | 0 | 0 | -44647 | 0 | -44647 | IFA | 2022-04-11 | 0 | 0 | -44662 | 0 | -44662 | AFC | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-21 | 2022-05-10 |  | G03 | AFC | T-0924 | 44691 | 1401/02/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0620 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-HSE-HSE-00-03362 | 44626 | 1400/12/15 | CM-C2 | [22 empty] | G01 | IFA | T-0726 | 44633 | 1400/12/22 |  |  |  | BK-SUR-HSE-HSE-00-03553 | 44634 | 1400/12/23 | CM-C3 | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0005_G00 | [21 empty] | G02 | IFA | T-0758 | 44648 | 1401/01/08 |  |  |  | BK-SUR-HSE-HSE-01-03697 | 44646 | 1401/01/09 | AP | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0005_G01 | BK-SUR-HSE-HSE-01-03848 | 44662 | 1401/01/22 | AP | [17 empty] | G03 | AFC | T-0924 | 44691 | 1401/02/20
1 | 1 | 0 | 0 | 0 | 1 | 8 | 1.1.1.8 | BK-GNRAL-HD-000-PM-SH-0001 | Detailed Schedule & Updating |  | BK-GNRAL-HD-000-PM-SH-0001 | BK-GNRAL-HD-000-PM-SH-0001 | BK | GNRAL | HD | 000 | PM | SH | 0001 | F0Z-707039 | AFD | IFC | 2021-12-22 | 2022-12-04 | 0 | 347 | -44899 | -44552 | IFC | 2022-02-22 | 0 | 0 | -44614 | 0 | -44614 | IFA | 2022-04-10 | 0 | 0 | -44661 | 0 | -44661 | IFA | 2022-05-08 | 0 | 0 | -44689 | 0 | -44689 | AFD | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | AFD | 2022-06-29 | 0 | 0 | -44741 | 0 | -44741 | [7 empty] | Modify | 2021-12-08 | 2022-07-16 |  | G05 | AFD | T-1162 | 44758 | 1401/04/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS- BK-GNRAL-HD-000-PM-SH-0001_G04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0321 | 2021-12-08 | 1400/09/17 |  |  |  | BK-SUR-PLN-GEN-00-03227 | 44618 | 1400/12/07 | CM-C3 | [6 empty] | Comment Sheets\NISOC\19764 | 2021-12-12 | 1400/09/21 |  |  | RJ |  | MOM | 44899 | 1400/09/13 |  |  | CM |  |  |  | G00 | IFC | T-0567 | 44600 | 1400/11/19 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-SH-0001_G00 | [21 empty] | G01 | IFA | T-0747 | 44647 | 1401/01/07 |  |  |  | BK-SUR-PLN-GEN-01-03733 | 44657 | 1401/01/16 | RJ-C4 | PEDCO-CRS- BK-GNRAL-HD-000-PM-SH-0001-G01 | [21 empty] | G02 | IFA | T-0854 | 44675 | 1401/02/04 |  |  |  | Comment Sheets\PEDCO\2-Comment sheets\2406.pdf | 44677 | 1401/02/06 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-SH-0001_G01 | [21 empty] | G03 | AFD | T-0916 | 44690 | 1401/02/19 | [29 empty] | G04 | AFD | T-1079 | 44727 | 1401/03/25 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-SH-0001-G03 | [21 empty] | G05 | AFD | T-1162 | 44758 | 1401/04/25 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-SH-0001_G04
1 | 1 | 0 | 0 | 0 | 1 | 9 | 1.1.1.9 | BK-GNRAL-HD-000-PM-WB-0001 | Work Breakdown Structure (WBS) |  | BK-GNRAL-HD-000-PM-WB-0001 | BK-GNRAL-HD-000-PM-WB-0001 | BK | GNRAL | HD | 000 | PM | WB | 0001 | F0Z-707036 | AFD | IFC | 2021-11-30 | 0 | 0 | -44530 | 0 | -44530 | IFA | 2021-12-11 | 0 | 0 | -44541 | 0 | -44541 | IFA | 2022-01-11 | 0 | 0 | -44572 | 0 | -44572 | IFA | 2022-02-05 | 0 | 0 | -44597 | 0 | -44597 | AFD | 2022-02-16 | 0 | 0 | -44608 | 0 | -44608 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-16 | 2022-02-02 |  | G04 | AFD | T-0548 | 44594 | 1400/11/13 | 0 | 0 | 0 | Comment Sheets\PEDCO\1-Letters\25017 | 44600 | 1400/11/19 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0249 | 2021-11-16 | 1400/08/25 |  |  |  | Comment Sheets\PEDCO\1-Letters\17815 | 44522 | 1400/09/01 | CM | [22 empty] | G01 | IFA | T-0274 | 44527 | 1400/09/06 |  |  |  | Comment Sheets\PEDCO\1-Letters\19703 | 44542 | 1400/09/21 | CM | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0001-G01 | [21 empty] | G02 | IFA | T-0394 | 44558 | 1400/10/07 |  |  |  | BK-000-PLN-GEN-00-02632 | 44572 | 1400/10/21 | CM-C2 | [22 empty] | G03 | IFA | T-0484 | 44583 | 1400/11/02 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0001-G02 | [21 empty] | G04 | AFD | T-0548 | 44594 | 1400/11/13 |  |  |  | Comment Sheets\PEDCO\1-Letters\25017 | 44600 | 1400/11/19 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0001_G03
1 | 1 | 0 | 0 | 0 | 1 | 10 | 1.1.1.10 | BK-GNRAL-HD-000-PM-WB-0002 | Cost Breakdown Structure (CBS) |  | BK-GNRAL-HD-000-PM-WB-0002 | BK-GNRAL-HD-000-PM-WB-0002 | BK | GNRAL | HD | 000 | PM | WB | 0002 | F0Z-707043 | AFD | IFC | 2021-11-30 | 0 | 0 | -44530 | 0 | -44530 | IFA | 2021-12-11 | 0 | 0 | -44541 | 0 | -44541 | IFA | 2022-01-11 | 0 | 0 | -44572 | 0 | -44572 | IFA | 2022-02-05 | 0 | 0 | -44597 | 0 | -44597 | AFD | 2022-02-16 | 0 | 0 | -44608 | 0 | -44608 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-16 | 2022-02-02 |  | G04 | AFD | T-0548 | 44594 | 1400/11/13 | 0 | 0 | 0 | Comment Sheets\PEDCO\1-Letters\25017 | 44600 | 1400/11/19 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0002_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0249 | 2021-11-16 | 1400/08/25 | [29 empty] | G01 | IFA | T-0274 | 44527 | 1400/09/06 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0002-G01 | [21 empty] | G02 | IFA | T-0394 | 44558 | 1400/10/07 |  |  |  | BK-000-PLN-GEN-00-02631 | 44572 | 1400/10/21 | CM-C2 | [22 empty] | G03 | IFA | T-0484 | 44583 | 1400/11/02 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0002-G02 | [21 empty] | G04 | AFD | T-0548 | 44594 | 1400/11/13 |  |  |  | Comment Sheets\PEDCO\1-Letters\25017 | 44600 | 1400/11/19 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0002_G03
1 | 1 | 0 | 0 | 0 | 1 | 11 | 1.1.1.11 | BK-GNRAL-HD-000-PM-FO-0001 | Material Equipment & Control Index (MCI) |  | BK-GNRAL-HD-000-PM-FO-0001 | BK-GNRAL-HD-000-PM-FO-0001 | BK | GNRAL | HD | 000 | PM | FO | 0001 | F0Z-707038 | AFD | IFC | 2022-09-11 | 0 | 0 | -44815 | 0 | -44815 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-28 |  |  | G00 | IFC | T-1321 | 44801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-1321 | 2022-08-28
1 | 1 | 0 | 0 | 0 | 1 | 12 | 1.1.1.12 | BK-GNRAL-HD-000-PM-PG-0001 | Progress S-curves & Updating |  | BK-GNRAL-HD-000-PM-PG-0001 | BK-GNRAL-HD-000-PM-PG-0001 | BK | GNRAL | HD | 000 | PM | PG | 0001 | F0Z-707040 | AFD | IFC | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | IFC | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | IFA | 2022-07-09 | 0 | 0 | -44751 | 0 | -44751 | IFA | 2022-07-30 | 0 | 0 | -44772 | 0 | -44772 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-20 |  |  | G03 | IFA | T-1163 | 44758 | 1401/04/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS- BK-GNRAL-HD-000-PM-PG-0001_G04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0609 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-PLN-GEN-01-03734 | 44657 | 1401/01/17 | RJ-C4 | [22 empty] | G01 | IFC | T-0928 | 44691 | 1401/02/20 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-PG-0001-G00 | [21 empty] | G02 | IFA | T-1114 | 44737 | 1401/04/04 | [29 empty] | G03 | IFA | T-1163 | 44758 | 1401/04/25 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-PG-0001_G04
1 | 1 | 0 | 0 | 0 | 1 | 13 | 1.1.1.13 | BK-GNRAL-PEDCO-000-PM-PS-0001 | Production Capacity Realization Plan |  | BK-GNRAL-PEDCO-000-PM-PS-0001 | BK-GNRAL-PEDCO-000-PM-PS-0001 | BK | GNRAL | PEDCO | 000 | PM | PS | 0001 | 0 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 1 | 14 | 1.1.1.14 | BK-GNRAL-HD-000-PM-CP-0001 | Cash Flow Plan |  | BK-GNRAL-HD-000-PM-CP-0001 | BK-GNRAL-HD-000-PM-CP-0001 | BK | GNRAL | HD | 000 | PM | CP | 0001 | F0Z-707041 | IFI | IFI | 2022-10-02 | 0 | 0 | -44836 | 0 | -44836 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-18 |  |  | G00 | IFI | T-1411 | 44822 | 1401/06/27 | 0 | 0 | 0 | BK-SUR-PLN-GEN-01-05769 | 44830 | 1401/07/04 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-1411 | 2022-09-18 | 1401/06/27 |  |  |  | BK-SUR-PLN-GEN-01-05769 | 44830 | 1401/07/04 | CM-C2
1 | 1 | 0 | 0 | 0 | 1 | 15 | 1.1.1.15 | BK-GNRAL-PEDCO-000-PM-QP-0001 | Quality Plan |  | BK-GNRAL-PEDCO-000-PM-QP-0001 | [8 empty] | 0 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 1 | 16 | 1.1.1.16 | BK-GNRAL-HD-000-PM-CH-0001 | Project Organization Charts |  | BK-GNRAL-HD-000-PM-CH-0001 | BK-GNRAL-HD-000-PM-CH-0001 | BK | GNRAL | HD | 000 | PM | CH | 0001 | F0Z-707042 | AFD | IFC | 2022-07-25 | 0 | 0 | -44767 | 0 | -44767 | IFA | 2021-08-09 | 0 | 0 | -44417 | 0 | -44417 | IFA | 2022-12-04 | 0 | 0 | -44899 | 0 | -44899 | AFD | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | AFD | 2021-06-07 | 0 | 0 | -44354 | 0 | -44354 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-11 | 2021-05-24 |  | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2022-07-11 | 1400/04/20 | 0 | 0 | 0 | L-8318 | 44768 | 1400/05/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G01 | IFA | T-0012 | 44403 | 1400/05/04 | 0 | 0 | 0 | RS-BK-GNRAL-HD-000-PM-PR-0001-G01 | 44453 | 1400/06/23 | CM | BK-HD-PEDCO-CRS-0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G02 | IFA | T-0259 | 44885 | 1400/08/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO -CRS-BK-GNRAL-HD-000-PM-PR-0001_G01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G03 | AFD | T-0608 | 44612 | 1400/12/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1 | 0 | 0 | 0 | 1 | 17 | 1.1.1.17 | BK-GNRAL-HD-000-PM-SP-0001 | Specification for Medical Services |  | BK-GNRAL-HD-000-PM-SP-0001 | BK-GNRAL-HD-000-PM-SP-0001 | BK | GNRAL | HD | 000 | PM | SP | 0001 | F0Z-707049 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 2 | 0 | 1.1.2 |  | Project Procedures
1 | 1 | 0 | 0 | 0 | 2 | 1 | 1.1.2.1 | BK-GNRAL-HD-000-PM-PR-0001 | Project Coordination Procedure |  | BK-GNRAL-HD-000-PM-PR-0001 | BK-GNRAL-HD-000-PM-PR-0001 | BK | GNRAL | HD | 000 | PM | PR | 0001 | F0Z-707055 | AFD | IFC | 2021-07-25 | 0 | 0 | -44402 | 0 | -44402 | IFA | 2021-08-09 | 0 | 0 | -44417 | 0 | -44417 | IFA | 2021-12-04 | 0 | 0 | -44534 | 0 | -44534 | AFD | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | AFD | 2022-06-15 | 0 | 0 | -44727 | 0 | -44727 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-11 | 2022-06-01 |  | G04 | AFD | T-1032 | 44713 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2021-07-11 | 1400/04/20 |  |  |  | L-8318 | 44403 | 1400/05/04 | CM | [22 empty] | G01 | IFA | T-0012 | 44403 | 1400/05/04 |  |  |  | RS-BK-GNRAL-HD-000-PM-PR-0001-G01 | 44453 | 1400/06/23 | CM | BK-HD-PEDCO-CRS-0001 | [21 empty] | G02 | IFA | T-0259 | 44520 | 1400/08/29 | [7 empty] | PEDCO -CRS-BK-GNRAL-HD-000-PM-PR-0001_G01 | [21 empty] | G03 | AFD | T-0608 | 44612 | 1400/12/01 | [29 empty] | G04 | AFD | T-1032 | 44713 | 1401/03/11 | [7 empty] | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03
1 | 1 | 0 | 0 | 0 | 2 | 2 | 1.1.2.2 | BK-GNRAL-HD-000-PM-PR-0002 | Project Control Procedure (WBS, PMS,Invoicing) |  | BK-GNRAL-HD-000-PM-PR-0002 | [8 empty] | - | AFD | IFC | 2021-08-07 | 0 | 0 | -44415 | 0 | -44415 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | G00 | IFC | T-0010 | 44401 | 1400/05/02 | 0 | 0 | 0 | BK-SUR-PLN-GEN-01-03735 | 44657 | 1401/01/17 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0010 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-PLN-GEN-01-03735 | 44657 | 1401/01/17 | RJ-C4
1 | 1 | 0 | 0 | 0 | 2 | 3 | 1.1.2.3 | BK-GNRAL-HD-000-PM-PR-0014 | Progress Measurement Procedure |  | BK-GNRAL-HD-000-PM-PR-0014 | BK-GNRAL-HD-000-PM-PR-0014 | BK | GNRAL | HD | 000 | PM | PR | 0014 | F0Z-707056 | AFD | IFC | 2021-12-04 | 2022-06-08 | 2022-06-11 | 186 | 3 | 189 | IFC | 2022-05-15 | 0 | 0 | -44696 | 0 | -44696 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-20 |  |  | G01 | IFC | T-0889 | 44682 | 1401/02/11 | 0 | 0 | 0 | Comment Sheets\PEDCO\2-Comment sheets\5336.pdf | 44710 | 1401/03/09 | AP | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0014_G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0256 | 2021-11-20 | 1400/08/29 |  |  |  | BK-SUR-PLN-GEN-01-03736 | 44657 | 1401/01/17 | RJ-C4 | [6 empty] | 1401-2294-94251 | 2022-06-08 | 1401/03/18 | 44723 | 1401/03/21 | CM | [10 empty] | G01 | IFC | T-0889 | 44682 | 1401/02/11 |  |  |  | Comment Sheets\PEDCO\2-Comment sheets\5336.pdf | 44710 | 1401/03/09 | AP | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0014_G00
1 | 1 | 0 | 0 | 0 | 2 | 4 | 1.1.2.4 | BK-GNRAL-HD-000-PM-PR-0003 | Document Numbering Procedure |  | BK-GNRAL-HD-000-PM-PR-0003 | BK-GNRAL-HD-000-PM-PR-0003 | BK | GNRAL | HD | 000 | PM | PR | 0003 | F0Z-707057 | AFD | IFC | 2022-07-25 | 0 | 0 | -44767 | 0 | -44767 | IFA | 2021-08-09 | 0 | 0 | -44417 | 0 | -44417 | IFA | 2022-12-04 | 0 | 0 | -44899 | 0 | -44899 | AFD | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | AFD | 2021-06-07 | 0 | 0 | -44354 | 0 | -44354 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-11 | 2021-05-24 |  | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2022-07-11 | 1400/04/20 | 0 | 0 | 0 | L-8318 | 44768 | 1400/05/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G01 | IFA | T-0012 | 44403 | 1400/05/04 | 0 | 0 | 0 | RS-BK-GNRAL-HD-000-PM-PR-0001-G01 | 44453 | 1400/06/23 | CM | BK-HD-PEDCO-CRS-0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G02 | IFA | T-0259 | 44885 | 1400/08/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO -CRS-BK-GNRAL-HD-000-PM-PR-0001_G01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G03 | AFD | T-0608 | 44612 | 1400/12/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [101 empty] | 0 | [33 empty] | 0 | [33 empty] | 0
1 | 1 | 0 | 0 | 0 | 2 | 5 | 1.1.2.5 | BK-GNRAL-HD-000-PM-PR-0004 | Change Control Procedure |  | BK-GNRAL-HD-000-PM-PR-0004 | BK-GNRAL-HD-000-PM-PR-0004 | BK | GNRAL | HD | 000 | PM | PR | 0004 | F0Z-707058 | AFD | IFC | 2021-08-07 | 2022-06-08 | 2022-06-11 | 305 | 3 | 308 | IFC | 2022-05-15 | 0 | 0 | -44696 | 0 | -44696 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | G01 | IFC | T-0889 | 44682 | 1401/02/11 | 0 | 0 | 0 | Comment Sheets\PEDCO\2-Comment sheets\5336.pdf | 44710 | 1401/03/09 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-PR-0004_G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0010 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-PLN-GEN-01-03735 | 44657 | 1401/01/17 | RJ-C4 | [6 empty] | 1401-2294-94251 | 2022-06-08 | 1401/03/18 | 44723 | 1401/03/21 | CM | [10 empty] | G01 | IFC | T-0889 | 44682 | 1401/02/11 |  |  |  | Comment Sheets\PEDCO\2-Comment sheets\5336.pdf | 44710 | 1401/03/09 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-PR-0004_G00
1 | 1 | 0 | 0 | 0 | 2 | 6 | 1.1.2.6 | BK-GNRAL-HD-000-PM-PR-0005 | Invoicing Procedure |  | BK-GNRAL-HD-000-PM-PR-0005 | BK-GNRAL-HD-000-PM-PR-0005 | BK | GNRAL | HD | 000 | PM | PR | 0005 | F0Z-707059 | AFD | IFC | 2021-12-21 | 0 | 0 | -44551 | 0 | -44551 | IFA | 2022-05-09 | 0 | 0 | -44690 | 0 | -44690 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 |  |  | G01 | IFA | T-0859 | 44676 | 1401/02/06 | 0 | 0 | 0 | 5336 | 44712 | 1401/03/10 | CM | PEDCO-CRS- BK-GNRAL-HD-000-PM-PR-0005_G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0301 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-PLN-GEN-01-03737 | 44657 | 1401/01/17 | RJ-C4 | [22 empty] | G01 | IFA | T-0859 | 44676 | 1401/02/06 |  |  |  | 5336 | 44712 | 1401/03/10 | CM | PEDCO-CRS- BK-GNRAL-HD-000-PM-PR-0005_G00
1 | 1 | 0 | 0 | 0 | 2 | 7 | 1.1.2.7 | BK-GNRAL-HD-000-PM-PR-0006 | Correspondence Procedure |  | BK-GNRAL-HD-000-PM-PR-0006 | BK-GNRAL-HD-000-PM-PR-0006 | BK | GNRAL | HD | 000 | PM | PR | 0006 | F0Z-707060 | AFD | IFC | 2022-07-25 | 0 | 0 | -44767 | 0 | -44767 | IFA | 2021-08-09 | 0 | 0 | -44417 | 0 | -44417 | IFA | 2022-12-04 | 0 | 0 | -44899 | 0 | -44899 | AFD | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | AFD | 2021-06-07 | 0 | 0 | -44354 | 0 | -44354 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-11 | 2021-05-24 |  | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2022-07-11 | 1400/04/20 | 0 | 0 | 0 | L-8318 | 44768 | 1400/05/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G01 | IFA | T-0012 | 44403 | 1400/05/04 | 0 | 0 | 0 | RS-BK-GNRAL-HD-000-PM-PR-0001-G01 | 44453 | 1400/06/23 | CM | BK-HD-PEDCO-CRS-0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G02 | IFA | T-0259 | 44885 | 1400/08/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO -CRS-BK-GNRAL-HD-000-PM-PR-0001_G01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G03 | AFD | T-0608 | 44612 | 1400/12/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [101 empty] | 0 | [33 empty] | 0 | [33 empty] | 0
1 | 1 | 0 | 0 | 0 | 2 | 8 | 1.1.2.8 | BK-GNRAL-HD-000-PM-PR-0007 | Meeting Procedure |  | BK-GNRAL-HD-000-PM-PR-0007 | BK-GNRAL-HD-000-PM-PR-0007 | BK | GNRAL | HD | 000 | PM | PR | 0007 | F0Z-707061 | AFD | IFC | 2022-07-25 | 0 | 0 | -44767 | 0 | -44767 | IFA | 2021-08-09 | 0 | 0 | -44417 | 0 | -44417 | IFA | 2022-12-04 | 0 | 0 | -44899 | 0 | -44899 | AFD | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | AFD | 2021-06-07 | 0 | 0 | -44354 | 0 | -44354 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-11 | 2021-05-24 |  | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2022-07-11 | 1400/04/20 | 0 | 0 | 0 | L-8318 | 44768 | 1400/05/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G01 | IFA | T-0012 | 44403 | 1400/05/04 | 0 | 0 | 0 | RS-BK-GNRAL-HD-000-PM-PR-0001-G01 | 44453 | 1400/06/23 | CM | BK-HD-PEDCO-CRS-0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G02 | IFA | T-0259 | 44885 | 1400/08/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO -CRS-BK-GNRAL-HD-000-PM-PR-0001_G01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G03 | AFD | T-0608 | 44612 | 1400/12/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [101 empty] | 0 | [33 empty] | 0 | [33 empty] | 0
1 | 1 | 0 | 0 | 0 | 2 | 9 | 1.1.2.9 | BK-GNRAL-HD-000-PM-PR-0008 | Reporting Procedure |  | BK-GNRAL-HD-000-PM-PR-0008 | BK-GNRAL-HD-000-PM-PR-0008 | BK | GNRAL | HD | 000 | PM | PR | 0008 | F0Z-707062 | AFD | IFC | 2022-07-25 | 0 | 0 | -44767 | 0 | -44767 | IFA | 2021-08-09 | 0 | 0 | -44417 | 0 | -44417 | IFA | 2022-12-04 | 0 | 0 | -44899 | 0 | -44899 | AFD | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | AFD | 2021-06-07 | 0 | 0 | -44354 | 0 | -44354 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-11 | 2021-05-24 |  | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2022-07-11 | 1400/04/20 | 0 | 0 | 0 | L-8318 | 44768 | 1400/05/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G01 | IFA | T-0012 | 44403 | 1400/05/04 | 0 | 0 | 0 | RS-BK-GNRAL-HD-000-PM-PR-0001-G01 | 44453 | 1400/06/23 | CM | BK-HD-PEDCO-CRS-0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G02 | IFA | T-0259 | 44885 | 1400/08/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO -CRS-BK-GNRAL-HD-000-PM-PR-0001_G01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G03 | AFD | T-0608 | 44612 | 1400/12/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [101 empty] | 0 | [33 empty] | 0 | [33 empty] | 0
1 | 1 | 0 | 0 | 0 | 2 | 10 | 1.1.2.10 | BK-GNRAL-HD-000-PM-PR-0009 | Procurement & Services Contracting Procedure |  | BK-GNRAL-HD-000-PM-PR-0009 | BK-GNRAL-HD-000-PM-PR-0009 | BK | GNRAL | HD | 000 | PM | PR | 0009 | F0Z-707063 | AFD | IFC | 2021-12-06 | 0 | 0 | -44536 | 0 | -44536 | AFD | 2022-01-12 | 0 | 0 | -44573 | 0 | -44573 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-22 | 2021-12-29 |  | G01 | AFD | T-0402 | 44559 | 1400/10/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0265 | 2021-11-22 | 1400/09/01 |  |  |  | BK-SUR-ENG-MNG-00-02460 | 44557 | 1400/10/06 | AP | [22 empty] | G01 | AFD | T-0402 | 44559 | 1400/10/08
1 | 1 | 0 | 0 | 0 | 2 | 11 | 1.1.2.11 | BK-GNRAL-HD-000-PM-PR-0010 | Eng. Document Control Procedure |  | BK-GNRAL-HD-000-PM-PR-0010 | BK-GNRAL-HD-000-PM-PR-0010 | BK | GNRAL | HD | 000 | PM | PR | 0010 | F0Z-707064 | AFC | IFC | 2022-07-25 | 0 | 0 | -44767 | 0 | -44767 | IFA | 2021-08-09 | 0 | 0 | -44417 | 0 | -44417 | IFA | 2022-12-04 | 0 | 0 | -44899 | 0 | -44899 | AFD | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | AFD | 2021-06-07 | 0 | 0 | -44354 | 0 | -44354 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-11 | 2021-05-24 |  | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2022-07-11 | 1400/04/20 | 0 | 0 | 0 | L-8318 | 44768 | 1400/05/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G01 | IFA | T-0012 | 44403 | 1400/05/04 | 0 | 0 | 0 | RS-BK-GNRAL-HD-000-PM-PR-0001-G01 | 44453 | 1400/06/23 | CM | BK-HD-PEDCO-CRS-0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G02 | IFA | T-0259 | 44885 | 1400/08/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO -CRS-BK-GNRAL-HD-000-PM-PR-0001_G01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G03 | AFD | T-0608 | 44612 | 1400/12/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G04 | AFD | T-1032 | 44340 | 1401/03/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [101 empty] | 0 | [33 empty] | 0 | [33 empty] | 0
1 | 1 | 0 | 0 | 0 | 2 | 12 | 1.1.2.12 | BK-GNRAL-HD-000-PM-PR-0011 | Material Control Procedure |  | BK-GNRAL-HD-000-PM-PR-0011 | BK-GNRAL-HD-000-PM-PR-0011 | BK | GNRAL | HD | 000 | PM | PR | 0011 | F0Z-707065 | AFD | IFC | 2022-09-11 | 0 | 0 | -44815 | 0 | -44815 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-28 |  |  | G00 | IFC | T-1321 | 44801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-1321 | 2022-08-28
1 | 1 | 0 | 0 | 0 | 2 | 13 | 1.1.2.13 | BK-GNRAL-HD-000-PM-PR-0012 | Completion & Handover Procedure |  | BK-GNRAL-HD-000-PM-PR-0012 | BK-GNRAL-HD-000-PM-PR-0012 | BK | GNRAL | HD | 000 | PM | PR | 0012 | F0Z-707066 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 3 | 0 | 1.1.3 |  | Project Performance Report
1 | 1 | 0 | 0 | 0 | 3 | 1 | 1.1.3.1 | BK-GNRAL-HD-000-GE-RT-0001 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0001 | BK-GNRAL-HD-000-GE-RT-0001 | BK | GNRAL | HD | 000 | GE | RT | 0001 | F0Z-707067 | IFI | IFI | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | D00 | IFI
1 | 1 | 0 | 0 | 0 | 3 | 2 | 1.1.3.2 | BK-GNRAL-HD-000-GE-RT-0002 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0002 | BK-GNRAL-HD-000-GE-RT-0002 | BK | GNRAL | HD | 000 | GE | RT | 0002 | F0Z-707068 | IFI | IFI | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | D00 | IFI
1 | 1 | 0 | 0 | 0 | 3 | 3 | 1.1.3.3 | BK-GNRAL-HD-000-GE-RT-0003 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0003 | BK-GNRAL-HD-000-GE-RT-0003 | BK | GNRAL | HD | 000 | GE | RT | 0003 | F0Z-707069 | IFI | IFI | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | D00 | IFI
1 | 1 | 0 | 0 | 0 | 3 | 4 | 1.1.3.4 | BK-GNRAL-HD-000-GE-RT-0004 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0004 | BK-GNRAL-HD-000-GE-RT-0004 | BK | GNRAL | HD | 000 | GE | RT | 0004 | F0Z-707070 | IFI | IFI | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | D00 | IFI
1 | 1 | 0 | 0 | 0 | 3 | 5 | 1.1.3.5 | BK-GNRAL-HD-000-GE-RT-0005 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0005 | BK-GNRAL-HD-000-GE-RT-0005 | BK | GNRAL | HD | 000 | GE | RT | 0005 | F0Z-707071 | IFI | IFI | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | D00 | IFI
1 | 1 | 0 | 0 | 0 | 3 | 6 | 1.1.3.6 | BK-GNRAL-HD-000-GE-RT-0006 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0006 | BK-GNRAL-HD-000-GE-RT-0006 | BK | GNRAL | HD | 000 | GE | RT | 0006 | F0Z-707072 | IFI | IFI | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | D00 | IFI
1 | 1 | 0 | 0 | 0 | 3 | 7 | 1.1.3.7 | BK-GNRAL-HD-000-GE-RT-0007 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0007 | BK-GNRAL-HD-000-GE-RT-0007 | BK | GNRAL | HD | 000 | GE | RT | 0007 | F0Z-707073 | IFI | IFI | 2022-01-25 | 0 | 0 | -44586 | 0 | -44586 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-11 |  |  | D00 | IFI | T-0449 | 44572 | 1400/10/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0449 | 2022-01-11 | 1400/10/20
1 | 1 | 0 | 0 | 0 | 3 | 8 | 1.1.3.8 | BK-GNRAL-HD-000-GE-RT-0008 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0008 | BK-GNRAL-HD-000-GE-RT-0008 | BK | GNRAL | HD | 000 | GE | RT | 0008 | F0Z-707074 | IFI | IFI | 2022-02-27 | 0 | 0 | -44619 | 0 | -44619 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 |  |  | G00 | IFI | T-0585 | 44605 | 1400/11/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-0585 | 2022-02-13 | 1400/11/24
1 | 1 | 0 | 0 | 0 | 3 | 9 | 1.1.3.9 | BK-GNRAL-HD-000-GE-RT-0009 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0009 | BK-GNRAL-HD-000-GE-RT-0009 | BK | GNRAL | HD | 000 | GE | RT | 0009 | F0Z-707075 | IFI | IFI | 2022-03-27 | 0 | 0 | -44647 | 0 | -44647 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-13 |  |  | G00 | IFI | T-0728 | 44633 | 1400/12/22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-0728 | 2022-03-13 | 1400/12/22
1 | 1 | 0 | 0 | 0 | 3 | 10 | 1.1.3.10 | BK-GNRAL-HD-000-GE-RT-0010 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0010 | BK-GNRAL-HD-000-GE-RT-0010 | BK | GNRAL | HD | 000 | GE | RT | 0010 | F0Z-707076 | IFI | IFI | 2022-04-25 | 0 | 0 | -44676 | 0 | -44676 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-11 |  |  | G00 | IFI | T-0805 | 44662 | 1401/01/22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-0805 | 2022-04-11 | 1401/01/22
1 | 1 | 0 | 0 | 0 | 3 | 11 | 1.1.3.11 | BK-GNRAL-HD-000-GE-RT-0011 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0011 | BK-GNRAL-HD-000-GE-RT-0011 | BK | GNRAL | HD | 000 | GE | RT | 0011 | F0Z-707077 | IFI | IFI | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-14 |  |  | G00 | IFI | T-0937 | 44695 | 1401/02/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-0937 | 2022-05-14 | 1401/02/24
1 | 1 | 0 | 0 | 0 | 3 | 12 | 1.1.3.12 | BK-GNRAL-HD-000-GE-RT-0012 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0012 | BK-GNRAL-HD-000-GE-RT-0012 | BK | GNRAL | HD | 000 | GE | RT | 0012 | F0Z-707078 | IFI | IFI | 2022-06-26 | 0 | 0 | -44738 | 0 | -44738 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-12 |  |  | G00 | IFI | T-1070 | 44724 | 1401/03/22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-1070 | 2022-06-12 | 1401/03/22
1 | 1 | 0 | 0 | 0 | 3 | 13 | 1.1.3.13 | BK-GNRAL-HD-000-GE-RT-0013 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0013 | BK-GNRAL-HD-000-GE-RT-0013 | BK | GNRAL | HD | 000 | GE | RT | 0013 | F0Z-707079 | IFI | IFI | 2022-08-03 | 0 | 0 | -44776 | 0 | -44776 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-20 |  |  | D00 | IFI | T-1174 | 44762 | 1401/04/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1174 | 2022-07-20 | 1401/04/29
1 | 1 | 0 | 0 | 0 | 3 | 14 | 1.1.3.14 | BK-GNRAL-HD-000-GE-RT-0014 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0014 | BK-GNRAL-HD-000-GE-RT-0014 | BK | GNRAL | HD | 000 | GE | RT | 0014 | F0Z-707080 | IFI | IFI | 2022-08-29 | 0 | 0 | -44802 | 0 | -44802 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-15 |  |  | D00 | IFI | T-1275 | 44788 | 1401/05/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1275 | 2022-08-15 | 1401/05/24
1 | 1 | 0 | 0 | 0 | 3 | 15 | 1.1.3.15 | BK-GNRAL-HD-000-GE-RT-0015 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0015 | BK-GNRAL-HD-000-GE-RT-0015 | BK | GNRAL | HD | 000 | GE | RT | 0015 | F0Z-707081 | IFI | IFI | 2022-09-28 | 0 | 0 | -44832 | 0 | -44832 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-14 |  |  | D00 | IFI | T-1405 | 44818 | 1401/06/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1405 | 2022-09-14 | 1401/06/23
1 | 1 | 0 | 0 | 0 | 3 | 16 | 1.1.3.16 | BK-GNRAL-HD-000-GE-RT-0016 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0016 | BK-GNRAL-HD-000-GE-RT-0016 | BK | GNRAL | HD | 000 | GE | RT | 0016 | F0Z-707082 | IFI | IFI | 2022-10-30 | 0 | 0 | -44864 | 0 | -44864 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-16 |  |  | G00 | IFI | T-1501 | 44850 | 1401/07/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-1501 | 2022-10-16 | 1401/07/24
1 | 1 | 0 | 0 | 0 | 3 | 17 | 1.1.3.17 | BK-GNRAL-HD-000-GE-RT-0017 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0017 | BK-GNRAL-HD-000-GE-RT-0017 | BK | GNRAL | HD | 000 | GE | RT | 0017 | F0Z-707083 | IFI | IFI | 2022-11-29 | 0 | 0 | -44894 | 0 | -44894 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-11-15 |  |  | G00 | IFI | T-1588 | 44880 | 1401/08/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-1588 | 2022-11-15 | 1401/08/24
1 | 1 | 0 | 0 | 0 | 3 | 18 | 1.1.3.18 | BK-GNRAL-HD-000-GE-RT-0018 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0018 | BK-GNRAL-HD-000-GE-RT-0018 | BK | GNRAL | HD | 000 | GE | RT | 0018 | F0Z-707084 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 3 | 19 | 1.1.3.19 | BK-GNRAL-HD-000-GE-RT-0019 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0019 | BK-GNRAL-HD-000-GE-RT-0019 | BK | GNRAL | HD | 000 | GE | RT | 0019 | F0Z-707085 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 3 | 20 | 1.1.3.20 | BK-GNRAL-HD-000-GE-RT-0020 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0020 | BK-GNRAL-HD-000-GE-RT-0020 | BK | GNRAL | HD | 000 | GE | RT | 0020 | F0Z-707086 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 3 | 21 | 1.1.3.21 | BK-GNRAL-HD-000-GE-RT-0021 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0021 | BK-GNRAL-HD-000-GE-RT-0021 | BK | GNRAL | HD | 000 | GE | RT | 0021 | F0Z-707087 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 3 | 22 | 1.1.3.22 | BK-GNRAL-HD-000-GE-RT-0022 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0022 | BK-GNRAL-HD-000-GE-RT-0022 | BK | GNRAL | HD | 000 | GE | RT | 0022 | F0Z-707088 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 3 | 23 | 1.1.3.23 | BK-GNRAL-HD-000-GE-RT-0023 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0023 | BK-GNRAL-HD-000-GE-RT-0023 | BK | GNRAL | HD | 000 | GE | RT | 0023 | F0Z-707089 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 3 | 24 | 1.1.3.24 | BK-GNRAL-HD-000-GE-RT-0024 | Monthly Progress Report |  | BK-GNRAL-HD-000-GE-RT-0024 | BK-GNRAL-HD-000-GE-RT-0024 | BK | GNRAL | HD | 000 | GE | RT | 0024 | F0Z-707090 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 3 | 31 | 1.1.3.31 | BK-GNRAL-HD-000-GE-RT-0050 | Delay Analysis Report |  | BK-GNRAL-HD-000-GE-RT-0050 | BK-GNRAL-HD-000-GE-RT-0050 | BK | GNRAL | HD | 000 | GE | RT | 0050 | F0Z-707091 | IFI | IFI | 2022-07-03 | 0 | 0 | -44745 | 0 | -44745 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-19 |  |  | G00 | IFI | T-1090 | 44731 | 1401/03/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-1090 | 2022-06-19 | 1401/03/30
1 | 1 | 0 | 0 | 0 | 3 | 32 | 1.1.3.32 | BK-GNRAL-HD-000-GE-RT-0051 | Delay Analysis Report |  | BK-GNRAL-HD-000-GE-RT-0051 | BK-GNRAL-HD-000-GE-RT-0051 | BK | GNRAL | HD | 000 | GE | RT | 0051 | F0Z-707092 | IFI | IFI | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D00 | IFI | T-1372 | 44811 | 1401/06/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1372 | 2022-09-07 | 1401/06/16
1 | 1 | 0 | 0 | 0 | 3 | 33 | 1.1.3.33 | BK-GNRAL-HD-000-GE-RT-0052 | Delay Analysis Report |  | BK-GNRAL-HD-000-GE-RT-0052 | BK-GNRAL-HD-000-GE-RT-0052 | BK | GNRAL | HD | 000 | GE | RT | 0052 | F0Z-707093 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 0 | 0 | 0 | 3 | 34 | 1.1.3.34 | BK-GNRAL-HD-000-GE-RT-0053 | Delay Analysis Report |  | BK-GNRAL-HD-000-GE-RT-0053 | BK-GNRAL-HD-000-GE-RT-0053 | BK | GNRAL | HD | 000 | GE | RT | 0053 | F0Z-707094 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 1 | 0 | 0 | 0 | 0 | 1.1.1 |  | Camp Engineering Documents
1 | 1 | 1 | 1 | 0 | 0 | 0 | 1.1.1.1 |  | HVAC/Plumbing
1 | 1 | 1 | 1 | 0 | 1 | 0 | 1.1.1.1.1 |  | Drawing/Diagram
1 | 1 | 1 | 1 | 0 | 1 | 1 | 1.1.1.1.1.1 | BK-GNRAL-PEDCO-220-HV-PY-0001 | Plumbing & Sewage Piping Layout |  | BK-GNRAL-PEDCO-220-HV-PY-0001 | BK-GNRAL-PEDCO-220-HV-PY-0001 | BK | GNRAL | PEDCO | 220 | HV | PY | 0001 | F4B-707095 | AFC | IFC | 2022-06-04 | 2022-06-21 | 2022-06-26 | 17 | 5 | 22 | IFA | 2022-09-19 | 0 | 0 | -44823 | 0 | -44823 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-21 |  |  | D01 | IFA | T-1361 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-05842 | 44842 | 1401/07/16 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-220-HV-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-220-HV-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0978 | 2022-05-21 | 1401/02/31 | T-0978 | 44702 | 1401/02/31 | BK-SUR-ENG-HVC-01-04924 | 44741 | 1401/04/08 | CM-C2 | [6 empty] | 1401-2294-111558 | 2022-06-21 | 1401/03/31 | 44738 | 1401/04/06 | CM | [10 empty] | D01 | IFA | T-1361 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-HVC-01-05842 | 44842 | 1401/07/16 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-220-HV-PY-0001_D00 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-220-HV-PY-0001_D00
1 | 1 | 1 | 1 | 0 | 1 | 2 | 1.1.1.1.1.2 | BK-GNRAL-PEDCO-220-HV-PY-0002 | HVAC System Layout |  | BK-GNRAL-PEDCO-220-HV-PY-0002 | BK-GNRAL-PEDCO-220-HV-PY-0002 | BK | GNRAL | PEDCO | 220 | HV | PY | 0002 | F4B-707096 | AFC | IFC | 2022-05-28 | 2022-06-07 | 2022-06-11 | 10 | 4 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-14 |  |  | D00 | IFC | T-0938 | 44695 | 1401/02/24 | T-0938 | 44695 | 1401/02/24 | BK-SUR-ENG-HVC-01-04925 | 44741 | 1401/04/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-92177 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0938 | 2022-05-14 | 1401/02/24 | T-0938 | 44695 | 1401/02/24 | BK-SUR-ENG-HVC-01-04925 | 44741 | 1401/04/08 | CM-C2 | [6 empty] | 1400-2294-92177 | 2022-06-07 | 1401/03/17 | 44723 | 1401/03/21 | CM
1 | 1 | 1 | 1 | 0 | 2 | 0 | 1.1.1.1.2 |  | List
1 | 1 | 1 | 1 | 0 | 2 | 1 | 1.1.1.1.2.1 | BK-GNRAL-PEDCO-220-HV-LI-0001 | HVAC Equipment Schedule |  | BK-GNRAL-PEDCO-220-HV-LI-0001 | BK-GNRAL-PEDCO-220-HV-LI-0001 | BK | GNRAL | PEDCO | 220 | HV | LI | 0001 | F0Z-707097 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 1 | 1 | 2 | 0 | 0 | 0 | 1.1.1.2 |  | Safety & Fire Fighting
1 | 1 | 1 | 2 | 0 | 1 | 0 | 1.1.1.2.1 |  | Drawing/Diagram
1 | 1 | 1 | 2 | 0 | 1 | 1 | 1.1.1.2.1.1 | BK-GNRAL-PEDCO-220-SA-PY-0001 | Safety & Fire Fighting Equipment Location Layout |  | BK-GNRAL-PEDCO-220-SA-PY-0001 | BK-GNRAL-PEDCO-220-SA-PY-0001 | BK | GNRAL | PEDCO | 220 | SA | PY | 0001 | F2B-707098 | AFC | IFC | 2022-02-16 | 2022-02-26 | 2022-02-21 | 10 | -5 | 5 | IFA | 2022-05-22 | 2022-06-08 | 2022-06-11 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-02 |  |  | D01 | IFA | T-0908 | 44689 | 1401/02/18 | T-0908 | 44689 | 1401/02/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94376 | 44720 | 1401/03/18 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-220-SA-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0543 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-419386 | 2022-02-26 | 1400/12/07 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0908 | 44689 | 1401/02/18 | T-0908 | 44689 | 1401/02/18 | [10 empty] | 1401-2294-94376 | 44720 | 1401/03/18 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-220-SA-PY-0001_D00
1 | 1 | 1 | 3 | 0 | 0 | 0 | 1.1.1.3 |  | Electrical
1 | 1 | 1 | 3 | 0 | 1 | 0 | 1.1.1.3.1 |  | Drawing/Diagram
1 | 1 | 1 | 3 | 0 | 1 | 1 | 1.1.1.3.1.1 | BK-GNRAL-PEDCO-220-EL-PY-0001 | Lighting & Small Power Layout For Camp Area |  | BK-GNRAL-PEDCO-220-EL-PY-0001 | BK-GNRAL-PEDCO-220-EL-PY-0001 | BK | GNRAL | PEDCO | 220 | EL | PY | 0001 | F4P-707101 | AFC | IFC | 2022-01-18 | 2022-03-26 | 2022-04-01 | 67 | 6 | 73 | IFA | 2022-08-23 | 2022-08-31 | 2022-09-04 | 8 | 4 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-04 |  |  | D01 | IFA | T-1259 | 44782 | 1401/05/18 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05505 | 44796 | 1401/06/01 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-EL-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205622 | 44804 | 1401/06/09 | 44808 | 1401/06/13 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0428 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-ELE-00-02677 | 44576 | 1400/10/25 | CM-C2 | [6 empty] | 1401-2294-5251 | 2022-03-26 | 1401/01/09 | 44652 | 1401/01/14 | AP | [10 empty] | D01 | IFA | T-1259 | 44782 | 1401/05/18 |  |  |  | BK-SUR-ENG-ELE-01-05505 | 44796 | 1401/06/01 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-EL-PY-0001_D00 | [5 empty] | 1401-2294-205622 | 44804 | 1401/06/09 | 44808 | 1401/06/13 | AP
1 | 1 | 1 | 3 | 0 | 1 | 2 | 1.1.1.3.1.2 | BK-GNRAL-PEDCO-220-EL-PY-0002 | Earthing & Lightning Layout For Camp Area |  | BK-GNRAL-PEDCO-220-EL-PY-0002 | BK-GNRAL-PEDCO-220-EL-PY-0002 | BK | GNRAL | PEDCO | 220 | EL | PY | 0002 | F4P-707102 | AFC | IFC | 2022-06-12 | 2022-06-22 | 2022-07-02 | 10 | 10 | 20 | IFA | 2022-10-08 | 2022-10-19 | 2022-10-23 | 11 | 4 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-29 |  |  | D01 | IFA | T-1436 | 44828 | 1401/07/02 | T-1436 | 44828 | 1401/07/02 | BK-SUR-ENG-ELE-01-05861 | 44842 | 1401/07/16 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-220-EL-PY-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-271651 | 44853 | 1401/07/27 | 44857 | 1401/08/01 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-EL-PY-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1021 | 2022-05-29 | 1401/03/08 | T-1021 | 44710 | 1401/03/08 | BK-SUR-ENG-ELE-01-04636 | 44723 | 1401/03/21 | CM-C3 | [6 empty] | 1401-2294-111529 | 2022-06-22 | 1401/03/31 | 44744 | 1401/04/11 | CM | [10 empty] | D01 | IFA | T-1436 | 44828 | 1401/07/02 | T-1436 | 44828 | 1401/07/02 | BK-SUR-ENG-ELE-01-05861 | 44842 | 1401/07/16 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-220-EL-PY-0002_D00 | [5 empty] | 1401-2294-271651 | 44853 | 1401/07/27 | 44857 | 1401/08/01 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-EL-PY-0002_D00
1 | 1 | 1 | 3 | 0 | 1 | 3 | 1.1.1.3.1.3 | BK-GNRAL-PEDCO-220-EL-DW-0001 | Cable Route For Camp Area |  | BK-GNRAL-PEDCO-220-EL-DW-0001 | BK-GNRAL-PEDCO-220-EL-DW-0001 | BK | GNRAL | PEDCO | 220 | EL | DW | 0001 | F4P-707103 | AFC | IFC | 2022-01-18 | 2022-03-26 | 2022-04-01 | 67 | 6 | 73 | IFA | 2022-08-23 | 2022-08-31 | 2022-09-04 | 8 | 4 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-04 |  |  | D01 | IFA | T-1259 | 44782 | 1401/05/18 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05505 | 44796 | 1401/06/01 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-EL-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205622 | 44804 | 1401/06/09 | 44808 | 1401/06/13 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0428 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-ELE-00-02677 | 44576 | 1400/10/25 | CM-C3 | [6 empty] | 1401-2294-5251 | 2022-03-26 | 1401/01/09 | 44652 | 1401/01/14 | AP | [10 empty] | D01 | IFA | T-1259 | 44782 | 1401/05/18 |  |  |  | BK-SUR-ENG-ELE-01-05505 | 44796 | 1401/06/01 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-EL-DW-0001_D00 | [5 empty] | 1401-2294-205622 | 44804 | 1401/06/09 | 44808 | 1401/06/13 | AP
1 | 1 | 1 | 3 | 0 | 2 | 0 | 1.1.1.3.2 |  | List
1 | 1 | 1 | 3 | 0 | 2 | 1 | 1.1.1.3.2.1 | BK-GNRAL-PEDCO-220-EL-LI-0001 | Electrical Load List |  | BK-GNRAL-PEDCO-220-EL-LI-0001 | BK-GNRAL-PEDCO-220-EL-LI-0001 | BK | GNRAL | PEDCO | 220 | EL | LI | 0001 | F0Z-707104 | AFC | IFC | 2022-06-01 | 2022-06-10 | 2022-06-12 | 9 | 2 | 11 | AFC | 2022-07-17 | 2022-08-16 | 2022-08-17 | 30 | 1 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-18 |  |  | D01 | AFC | T-1135 | 44745 | 1401/04/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05112 | 44758 | 1401/04/25 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-EL-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2290-179273 | 44789 | 1401/05/25 | 44790 | 1401/05/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0970 | 2022-05-18 | 1401/02/28 | T-0970 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04485 | 44710 | 1401/03/09 | CM-C3 | [6 empty] | 1401-2294-94634 | 2022-06-10 | 1401/03/20 | 44724 | 1401/03/22 | AP | [10 empty] | D01 | AFC | T-1135 | 44745 | 1401/04/12 |  |  |  | BK-SUR-ENG-ELE-01-05112 | 44758 | 1401/04/25 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-EL-LI-0001_D00 | [5 empty] | 1401-2290-179273 | 44789 | 1401/05/25 | 44790 | 1401/05/26 | CM
1 | 1 | 1 | 4 | 0 | 0 | 0 | 1.1.1.4 |  | Architecture
1 | 1 | 1 | 4 | 0 | 1 | 0 | 1.1.1.4.1 |  | Drawing/Diagram
1 | 1 | 1 | 4 | 0 | 1 | 1 | 1.1.1.4.1.1 | BK-GNRAL-PEDCO-220-AR-DW-0001 | Architectural Drawing For NISOC Office Building |  | BK-GNRAL-PEDCO-220-AR-DW-0001 | BK-GNRAL-PEDCO-220-AR-DW-0001 | BK | GNRAL | PEDCO | 220 | AR | DW | 0001 | F4B-707105 | AFC | IFC | 2021-08-07 | 2021-08-04 | 2021-08-07 | -3 | 3 | 0 | IFA | 2021-10-25 | 2021-10-19 | 2021-10-30 | -6 | 11 | 5 | AFC | 2021-11-23 | 2021-11-16 | 2021-11-17 | -7 | 1 | -6 | AFC | 2022-03-26 | 2022-03-14 | 2022-03-26 | -12 | 12 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-03-12 |  | D03 | AFC | T-0714 | 44632 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03627 | 44636 | 1400/12/25 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448452 | 44634 | 1400/12/23 | 44646 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0009 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ARC-00-01223 | 44408 | 1400/05/09 | CM-C2 | [6 empty] | 1400-2294-153629 | 2021-08-04 | 1400/05/13 | 44415 | 1400/05/16 | CM | [10 empty] | D01 | IFA | T-0150 | 44480 | 1400/07/19 |  |  |  | BK-SUR-ENG-ARC-00-01864 | 44499 | 1400/08/08 | CM-C2 | PEDCO-BK-GNRAL-PEDCO-220-AR-DW-0001_D01 | [5 empty] | 1400-2294-241759 | 44488 | 1400/07/27 | 44499 | 1400/08/08 | AP | NISOC-BK-GNRAL-PEDCO-220-AR-DW-0001_D01 | [9 empty] | D02 | AFC | T-0222 | 44509 | 1400/08/18 |  |  |  | BK-SUR-ENG-ARC-00-02010 | 44515 | 1400/08/24 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0001_D01 | [5 empty] | 1400-2294-277423 | 44516 | 1400/08/25 | 44517 | 1400/08/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0001_D01 | [9 empty] | D03 | AFC | T-0714 | 44632 | 1400/12/21 |  |  |  | BK-SUR-ENG-ARC-00-03627 | 44636 | 1400/12/25 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0001_D02 | [5 empty] | 1400-2294-448452 | 44634 | 1400/12/23 | 44646 | 1401/01/09 | AP
1 | 1 | 1 | 4 | 0 | 1 | 2 | 1.1.1.4.1.2 | BK-GNRAL-PEDCO-220-AR-DW-0002 | Architectural Drawing For NISOC Residental Building |  | BK-GNRAL-PEDCO-220-AR-DW-0002 | BK-GNRAL-PEDCO-220-AR-DW-0002 | BK | GNRAL | PEDCO | 220 | AR | DW | 0002 | F4B-707106 | AFC | IFC | 2021-10-27 | 2021-10-19 | 2022-01-22 | -8 | 95 | 87 | IFA | 2022-02-14 | 2022-02-05 | 2022-02-08 | -9 | 3 | -6 | AFC | 2022-02-26 | 2022-03-12 | 2022-03-14 | 14 | 2 | 16 | AFC | 2022-05-25 | 2022-05-21 | 2022-05-23 | -4 | 2 | -2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-13 | 2022-05-11 |  | D03 | AFC | T-0929 | 44692 | 1401/02/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-69692 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0159 | 2021-10-13 | 1400/07/21 |  |  |  | BK-SUR-ENG-ARC-00-02012 | 44515 | 1400/08/24 | CM-C2 | [6 empty] | 1400-2294-241755 | 2021-10-19 | 1400/07/27 | 44583 | 1400/11/02 | CM | [10 empty] | D01 | IFA | T-0529 | 44592 | 1400/11/11 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0002_D00 | [5 empty] | 1400-2294-397250 | 44597 | 1400/11/16 | 44600 | 1400/11/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0002_D00 | [9 empty] | D02 | AFC | T-0570 | 44604 | 1400/11/23 | [13 empty] | 1400-2294-445206 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP | [10 empty] | D03 | AFC | T-0929 | 44692 | 1401/02/21 | [13 empty] | 1401-2294-69692 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP
1 | 1 | 1 | 4 | 0 | 1 | 3 | 1.1.1.4.1.3 | BK-GNRAL-PEDCO-220-AR-DW-0003 | Architectural Drawing For Petro Iran Office Building |  | BK-GNRAL-PEDCO-220-AR-DW-0003 | BK-GNRAL-PEDCO-220-AR-DW-0003 | BK | GNRAL | PEDCO | 220 | AR | DW | 0003 | F4B-707107 | AFC | IFC | 2021-07-12 | 0 | 0 | -44389 | 0 | -44389 | IFA | 2021-08-14 | 0 | 0 | -44422 | 0 | -44422 | IFA | 2021-08-16 | 2021-08-11 | 0 | -5 | -44419 | -44424 | AFC | 2021-10-18 | 2021-09-14 | 2021-10-18 | -34 | 34 | 0 | AFC | 2021-11-21 | 0 | 0 | -44521 | 0 | -44521 | AFC | 2022-03-06 | 2022-11-09 | 2022-07-31 | 248 | -101 | 147 | [7 empty] | Modify | 2021-06-28 |  |  | D05 | AFC | T-0611 | 44612 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03415 | 44628 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0003_D04 | 0 | 0 | 0 | 0 | 0 | 1401-2294-2692299 | 44874 | 1400/08/18 | 44773 | 1401/05/08 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0003 | 2021-06-28 | 1400/04/07 | [29 empty] | D01 | IFA | L-0029 | 44408 | 1400/05/09 | [29 empty] | D02 | IFA | L-0036 | 44410 | 1400/05/11 |  |  |  | L-10907 | 44436 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 44419 | 1400/05/20 |  |  | AP | [10 empty] | D03 | AFC | T-0136 | 44473 | 1400/07/12 |  |  |  | BK-SUR-ENG-ARC-00-01757 | 44487 | 1400/07/26 | CM-C2 | [6 empty] | 1400-2294-234322 | 44453 | 1400/07/22 | 44487 | 1400/07/26 | CM | [10 empty] | D04 | AFC | T-0213 | 44507 | 1400/08/16 |  |  |  | BK-SUR-ENG-ARC-00-01951 | 44508 | 1400/08/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0003_D03 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0003_D03 | [9 empty] | D05 | AFC | T-0611 | 44612 | 1400/12/01 |  |  |  | BK-SUR-ENG-CIV-00-03415 | 44628 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0003_D04 | [5 empty] | 1401-2294-2692299 | 44874 | 1400/08/18 | 44773 | 1401/05/08 | RJ
1 | 1 | 1 | 4 | 0 | 1 | 4 | 1.1.1.4.1.4 | BK-GNRAL-PEDCO-220-AR-DW-0007 | Architectural Drawing For Petro Iran Residental Building |  | BK-GNRAL-PEDCO-220-AR-DW-0007 | BK-GNRAL-PEDCO-220-AR-DW-0007 | BK | GNRAL | PEDCO | 220 | AR | DW | 0007 | F4B-707111 | AFC | IFC | 2021-07-12 | 0 | 0 | -44389 | 0 | -44389 | IFA | 2021-08-14 | 0 | 0 | -44422 | 0 | -44422 | IFA | 2021-08-16 | 2021-08-11 | 0 | -5 | -44419 | -44424 | AFC | 2021-10-18 | 2021-09-14 | 2021-10-18 | -34 | 34 | 0 | AFC | 2021-11-21 | 0 | 0 | -44521 | 0 | -44521 | AFC | 2022-02-26 | 2022-11-09 | 2022-07-31 | 256 | -101 | 155 | [7 empty] | Modify | 2021-06-28 |  |  | D05 | AFC | T-0575 | 44604 | 1400/11/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0007_D04 | 0 | 0 | 0 | 0 | 0 | 1401-2294-2692299 | 44874 | 1400/08/18 | 44773 | 1401/05/08 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0003 | 2021-06-28 | 1400/04/07 | [29 empty] | D01 | IFA | L-0029 | 44408 | 1400/05/09 | [29 empty] | D02 | IFA | L-0036 | 44410 | 1400/05/11 |  |  |  | L-10907 | 44436 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 44419 | 1400/05/20 |  |  | AP | [10 empty] | D03 | AFC | T-0136 | 44473 | 1400/07/12 |  |  |  | BK-SUR-ENG-ARC-00-01757 | 44487 | 1400/07/26 | CM-C2 | [6 empty] | 1400-2294-234322 | 44453 | 1400/07/22 | 44487 | 1400/07/26 | CM | [10 empty] | D04 | AFC | T-0213 | 44507 | 1400/08/16 |  |  |  | BK-SUR-ENG-ARC-00-01951 | 44508 | 1400/08/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0007_D03 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0007_D03 | [9 empty] | D05 | AFC | T-0575 | 44604 | 1400/11/23 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0007_D04 | [5 empty] | 1401-2294-2692299 | 44874 | 1400/08/18 | 44773 | 1401/05/08 | RJ
1 | 1 | 1 | 4 | 0 | 1 | 5 | 1.1.1.4.1.5 | BK-GNRAL-PEDCO-220-AR-DW-0004 | Architectural Drawing For Petro Iran/Contractor Restaurant |  | BK-GNRAL-PEDCO-220-AR-DW-0004 | BK-GNRAL-PEDCO-220-AR-DW-0004 | BK | GNRAL | PEDCO | 220 | AR | DW | 0004 | F4B-707108 | AFC | IFC | 2021-09-05 | 2021-08-11 | 0 | -25 | -44419 | -44444 | AFC | 2021-10-18 | 2021-09-14 | 2021-10-18 | -34 | 34 | 0 | AFC | 2022-03-12 | 2022-03-03 | 2022-03-07 | -9 | 4 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D02 | AFC | T-0642 | 44618 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03414 | 44628 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-432759 | 44623 | 1400/12/12 | 44627 | 1400/12/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0060 | 2021-08-22 | 1400/05/31 |  |  |  | L-10907 | 44436 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 2021-08-11 | 1400/05/20 |  |  | AP | [10 empty] | D01 | AFC | T-0136 | 44473 | 1400/07/12 |  |  |  | BK-SUR-ENG-ARC-00-01757 | 44487 | 1400/07/26 | CM-C2 | [6 empty] | 1400-2294-234322 | 44453 | 1400/07/22 | 44487 | 1400/07/26 | RJ | [10 empty] | D02 | AFC | T-0642 | 44618 | 1400/12/07 |  |  |  | BK-SUR-ENG-ARC-00-03414 | 44628 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0004_D01 | [5 empty] | 1400-2294-432759 | 44623 | 1400/12/12 | 44627 | 1400/12/16 | CM
1 | 1 | 1 | 4 | 0 | 1 | 6 | 1.1.1.4.1.6 | BK-GNRAL-PEDCO-220-AR-DW-0005 | Architectural Drawing For Warehouse of Site Mobilization |  | BK-GNRAL-PEDCO-220-AR-DW-0005 | BK-GNRAL-PEDCO-220-AR-DW-0005 | BK | GNRAL | PEDCO | 220 | AR | DW | 0005 | F4B-707109 | AFC | IFC | 2021-09-05 | 2021-08-11 | 0 | -25 | -44419 | -44444 | AFC | 2022-01-12 | 2021-01-02 | 2022-01-04 | -375 | 367 | -8 | AFC | 2022-02-16 | 0 | 0 | -44608 | 0 | -44608 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 | 2022-02-02 |  | D02 | AFC | T-0538 | 44594 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0061 | 2021-08-22 | 1400/05/31 |  |  |  | L-10907 | 44436 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 2021-08-11 | 1400/05/20 |  |  | AP | [10 empty] | D01 | AFC | T-0398 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-ARC-00-02553 | 44564 | 1400/10/13 | CM-C2 | [6 empty] | 1400-2294-346187 | 44198 | 1400/10/12 | 44565 | 1400/10/14 | AP | [10 empty] | D02 | AFC | T-0538 | 44594 | 1400/11/13 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0005_D01 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0005_D01
1 | 1 | 1 | 4 | 0 | 1 | 7 | 1.1.1.4.1.7 | BK-GNRAL-PEDCO-220-AR-DW-0006 | Architectural Drawing For Drivers Rest Room |  | BK-GNRAL-PEDCO-220-AR-DW-0006 | BK-GNRAL-PEDCO-220-AR-DW-0006 | BK | GNRAL | PEDCO | 220 | AR | DW | 0006 | F4B-707110 | AFC | IFC | 2021-07-12 | 0 | 0 | -44389 | 0 | -44389 | IFA | 2021-08-14 | 0 | 0 | -44422 | 0 | -44422 | IFA | 2021-08-16 | 2021-08-11 | 0 | -5 | -44419 | -44424 | AFC | 2021-10-18 | 2021-09-14 | 2021-10-18 | -34 | 34 | 0 | AFC | 2022-03-16 | 0 | 0 | -44636 | 0 | -44636 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-06-28 | 2022-03-02 |  | D04 | AFC | T-0659 | 44622 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03417 | 44628 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0006_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0003 | 2021-06-28 | 1400/04/07 | [29 empty] | D01 | IFA | L-0029 | 44408 | 1400/05/09 | [29 empty] | D02 | IFA | L-0036 | 44410 | 1400/05/11 |  |  |  | L-10907 | 44436 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 44419 | 1400/05/20 |  |  | AP | [10 empty] | D03 | AFC | T-0136 | 44473 | 1400/07/12 |  |  |  | BK-SUR-ENG-ARC-00-01757 | 44487 | 1400/07/26 | CM-C2 | [6 empty] | 1400-2294-234322 | 44453 | 1400/07/22 | 44487 | 1400/07/26 | RJ | [10 empty] | D04 | AFC | T-0659 | 44622 | 1400/12/11 |  |  |  | BK-SUR-ENG-CIV-00-03417 | 44628 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0006_D03
1 | 1 | 1 | 5 | 0 | 0 | 0 | 1.1.1.5 |  | Civil
1 | 1 | 1 | 5 | 0 | 1 | 0 | 1.1.1.5.1 |  | Drawing/Diagram
1 | 1 | 1 | 5 | 0 | 1 | 1 | 1.1.1.5.1.1 | BK-GNRAL-PEDCO-220-CV-PY-0001 | Overall Layout for Camp Area |  | BK-GNRAL-PEDCO-220-CV-PY-0001 | BK-GNRAL-PEDCO-220-CV-PY-0001 | BK | GNRAL | PEDCO | 220 | CV | PY | 0001 | F4A-707112 | AFC | IFC | 2021-08-07 | 2021-08-04 | 2021-08-07 | -3 | 3 | 0 | IFA | 2021-10-31 | 2021-10-19 | 2021-10-30 | -12 | 11 | -1 | AFC | 2021-11-29 | 2021-11-18 | 2021-11-21 | -11 | 3 | -8 | AFC | 2021-12-26 | 2021-11-15 | 2021-12-18 | -41 | 33 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D03 | AFC | T-0325 | 44542 | 1400/09/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-PY-0001-D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320633 | 44515 | 1400/09/24 | 44548 | 1400/09/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0008 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-CIV-00-01222 | 44408 | 1400/05/09 | CM-C2 | [6 empty] | 1400-2294-153664 | 2021-08-04 | 1400/05/13 | 44415 | 1400/05/16 | CM | [10 empty] | D01 | IFA | T-0165 | 44486 | 1400/07/25 |  |  |  | BK-SUR-ENG-CIV-00-01801 | 44489 | 1400/07/28 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-PY-0001-D00 | [5 empty] | 1400-2294-241712 | 44488 | 1400/07/27 | 44499 | 1400/08/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO--220-CV-DW-0001-D00 | [9 empty] | D02 | AFC | T-0244 | 44515 | 1400/08/24 |  |  |  | BK-SUR-ENG-CIV-00-02054 | 44521 | 1400/08/30 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001-D01 | [5 empty] | 1400-2294-281432 | 44518 | 1400/08/27 | 44521 | 1400/08/30 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001-D01 | [9 empty] | D03 | AFC | T-0325 | 44542 | 1400/09/21 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-PY-0001-D02 | [5 empty] | 1400-2294-320633 | 44515 | 1400/09/24 | 44548 | 1400/09/27 | CM
1 | 1 | 1 | 5 | 0 | 1 | 2 | 1.1.1.5.1.2 | BK-GNRAL-PEDCO-220-CV-DW-0001 | Rough Grading Plan For Camp Area |  | BK-GNRAL-PEDCO-220-CV-DW-0001 | BK-GNRAL-PEDCO-220-CV-DW-0001 | BK | GNRAL | PEDCO | 220 | CV | DW | 0001 | F4S-707113 | AFC | IFC | 2021-10-04 | 2021-09-25 | 2021-09-29 | -9 | 4 | -5 | IFA | 2021-10-23 | 2021-10-14 | 0 | -9 | -44483 | -44492 | AFC | 2021-11-09 | 2021-10-30 | 2021-11-02 | -10 | 3 | -7 | AFC | 2021-11-20 | 2021-11-09 | 2021-11-14 | -11 | 5 | -6 | AFC | 2021-12-26 | 2021-11-15 | 2021-12-18 | -41 | 33 | -8 | AFC | 2022-10-15 | 2022-10-10 | 2022-10-12 | -5 | 2 | -3 | [7 empty] | Modify | 2021-09-20 | 2022-10-01 |  | D05 | AFC | T-1443 | 44835 | 1401/07/09 | T-1443 | 44835 | 1401/07/09 | BK-SUR-ENG-CIV-01-05884 | 44845 | 1401/07/19 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256223 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0110 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SUR-ENG-CIV-00-01586 | 44464 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-212146 | 2021-09-25 | 1400/07/03 | 44468 | 1400/07/07 | CM | [10 empty] | D01 | IFA | T-0141 | 44478 | 1400/07/17 |  |  |  | BK-SUR-ENG-CIV-00-01689 | 44488 | 1400/07/27 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001-D00 | [5 empty] | 1400-2294-234323 | 44483 | 1400/07/22 |  |  | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001-D00 | [9 empty] | D02 | AFC | T-0185 | 44495 | 1400/08/04 |  |  |  | BK-SUR-ENG-CIV-00-01872 | 44500 | 1400/08/09 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D01 | [5 empty] | 1400-2294-253891 | 44499 | 1400/08/08 | 44502 | 1400/08/11 | AP | [10 empty] | D03 | AFC | T-0210 | 44506 | 1400/08/15 |  |  |  | BK-SUR-ENG-CIV-00-01925 | 44507 | 1400/08/16 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D02 | [5 empty] | 1400-2294-269293 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | CM | [10 empty] | D04 | AFC | T-0325 | 44542 | 1400/09/21 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D03 | [5 empty] | 1400-2294-320633 | 44515 | 1400/09/24 | 44548 | 1400/09/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D03 | [9 empty] | D05 | AFC | T-1443 | 44835 | 1401/07/09 | T-1443 | 44835 | 1401/07/09 | BK-SUR-ENG-CIV-01-05884 | 44845 | 1401/07/19 | AP | [6 empty] | 1401-2294-256223 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP
1 | 1 | 1 | 6 | 0 | 0 | 0 | 1.1.1.6 |  | Structure
1 | 1 | 1 | 6 | 0 | 1 | 0 | 1.1.1.6.1 |  | Drawing/Diagram
1 | 1 | 1 | 6 | 0 | 1 | 1 | 1.1.1.6.1.1 | BK-GNRAL-PEDCO-220-ST-DW-0001 | Foundation Location Drawing For Camp Area |  | BK-GNRAL-PEDCO-220-ST-DW-0001 | BK-GNRAL-PEDCO-220-ST-DW-0001 | BK | GNRAL | PEDCO | 220 | ST | DW | 0001 | F4Q-707114 | AFC | IFC | 2022-02-26 | 2022-02-16 | 2022-02-21 | -10 | 5 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-12 |  |  | D00 | IFC | T-0576 | 44604 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03160 | 44613 | 1400/12/02 | cm-c2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-413074 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0576 | 2022-02-12 | 1400/11/23 |  |  |  | BK-SUR-ENG-CIV-00-03160 | 44613 | 1400/12/02 | cm-c2 | [6 empty] | 1400-2294-413074 | 2022-02-16 | 1400/11/27 | 44613 | 1400/12/02 | AP
1 | 1 | 1 | 6 | 0 | 1 | 2 | 1.1.1.6.1.2 | BK-GNRAL-PEDCO-220-ST-DW-0002 | Structural Drawing For NISOC Residental Building |  | BK-GNRAL-PEDCO-220-ST-DW-0002 | BK-GNRAL-PEDCO-220-ST-DW-0002 | BK | GNRAL | PEDCO | 220 | ST | DW | 0002 | F4M-707115 | AFC | IFC | 2021-11-24 | 2021-11-14 | 2021-11-16 | -10 | 2 | -8 | IFA | 2021-12-26 | 2021-12-15 | 2021-12-18 | -11 | 3 | -8 | AFC | 2022-02-06 | 2022-03-12 | 2022-03-14 | 34 | 2 | 36 | AFC | 2022-05-29 | 2022-05-21 | 2022-05-23 | -8 | 2 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-05-15 |  | D03 | AFC | T-0953 | 44696 | 1401/02/25 | T-0953 | 44696 | 1401/02/25 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-69912 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0224 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-STR-00-02017 | 44515 | 1400/08/24 | CM-C3 | [6 empty] | 1400-2294-275236 | 2021-11-14 | 1400/08/23 | 44516 | 1400/08/25 | CM | [10 empty] | D01 | IFA | T-0326 | 44542 | 1400/09/21 |  |  |  | BK-SUR-ENG-STR-00-02346 | 44548 | 1400/09/27 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002-D01 | [5 empty] | 1400-2294-320636 | 44545 | 1400/09/24 | 44548 | 1400/09/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002-D01 | [9 empty] | D02 | AFC | T-0494 | 44584 | 1400/11/03 |  |  |  | BK-SUR-ENG-STR-00-02861 | 44591 | 1400/11/10 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002_D01 | [5 empty] | 1400-2294-445105 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP | [10 empty] | D03 | AFC | T-0953 | 44696 | 1401/02/25 | T-0953 | 44696 | 1401/02/25 |  |  |  |  | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002_D02 | [5 empty] | 1401-2294-69912 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP
1 | 1 | 1 | 6 | 0 | 1 | 3 | 1.1.1.6.1.3 | BK-GNRAL-PEDCO-220-ST-DW-0003 | Structural Drawing For Warehouse |  | BK-GNRAL-PEDCO-220-ST-DW-0003 | BK-GNRAL-PEDCO-220-ST-DW-0003 | BK | GNRAL | PEDCO | 220 | ST | DW | 0003 | F4M-707116 | AFC | IFC | 2021-11-24 | 2022-04-10 | 2022-04-11 | 137 | 1 | 138 | IFA | 2022-05-22 | 2022-05-16 | 2022-05-23 | -6 | 7 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 |  |  | D01 | IFA | T-0911 | 44689 | 1401/02/18 | T-0911 | 44689 | 1401/02/18 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-63887 | 44697 | 1401/02/26 | 44704 | 1401/03/03 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0349 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-STR-00-01964 | 44510 | 1400/08/19 | RJ-C4 | [6 empty] | 1401-2294-16809 | 2022-04-10 | 1401/01/21 | 44662 | 1401/01/22 | AP | [10 empty] | D01 | IFA | T-0911 | 44689 | 1401/02/18 | T-0911 | 44689 | 1401/02/18 |  |  |  |  | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0003_D00 | [5 empty] | 1401-2294-63887 | 44697 | 1401/02/26 | 44704 | 1401/03/03 | RJ
1 | 2 | 0 | 0 | 0 | 0 | 0 | 1.2 |  | Project Common Docs (Eng. & QA/QC)
1 | 2 | 0 | 1 | 0 | 0 | 0 | 1.2.1 |  | Basic Design Endorsement
1 | 2 | 0 | 1 | 0 | 0 | 1 | 1.2.1.1 | BK-GNRAL-PEDCO-000-PM-RT-0001 | Endorsement Report For Basic Design & Scope of Work |  | BK-GNRAL-PEDCO-000-PM-RT-0001 | BK-GNRAL-PEDCO-000-PM-RT-0001 | BK | GNRAL | PEDCO | 000 | PM | RT | 0001 | F0Z-707117 | IFI | IFC | 2021-08-14 | 2021-08-28 | 2021-09-07 | 14 | 10 | 24 | AFD | 2021-10-03 | 2021-10-06 | 2021-10-26 | 3 | 20 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-31 |  |  | D03 | AFD | T-0102 | 44458 | 1400/06/28 | 0 | 0 | 0 | BK-SUR-ENG-GEN-00-01620 | 44467 | 1400/07/06 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2290-223853 | 44475 | 1400/07/14 | 44495 | 1400/08/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | [13 empty] | 1400/2294/176098 | 2021-08-28 | 1400/06/06 | 44446 | 1400/06/16 | CM | [8 empty] | B00-Reject |  | D03 | AFD | T-0102 | 44458 | 1400/06/28 |  |  |  | BK-SUR-ENG-GEN-00-01620 | 44467 | 1400/07/06 | AP | [6 empty] | 1400-2290-223853 | 44475 | 1400/07/14 | 44495 | 1400/08/04 | CM
1 | 2 | 0 | 2 | 0 | 0 | 0 | 1.2.2 |  | Process
1 | 2 | 0 | 2 | 0 | 1 | 0 | 1.2.2.1 |  | Basis/Criteria
1 | 2 | 0 | 2 | 0 | 1 | 1 | 1.2.2.1.1 | BK-GNRAL-PEDCO-000-PR-DC-0001 | Process Design Criteria |  | BK-GNRAL-PEDCO-000-PR-DC-0001 | BK-GNRAL-PEDCO-000-PR-DC-0001 | BK | GNRAL | PEDCO | 000 | PR | DC | 0001 | F0Z-707118 | AFD | IFC | 2021-08-10 | 2021-08-10 | 2021-08-08 | 0 | -2 | -2 | IFA | 2021-10-31 | 2021-11-28 | 2021-11-10 | 28 | -18 | 10 | AFD | 2022-01-15 | 2022-01-17 | 2022-01-19 | 2 | 2 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-27 | 2022-01-01 |  | D02 | AFD | T-0411 | 44562 | 1400/10/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-368526 | 44578 | 1400/10/27 | 44580 | 1400/10/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9966 | 44423 | 1400/05/24 | CM | [6 empty] | 1400/2294/159308 | 2021-08-10 | 1400/05/19 | 44416 | 1400/05/17 | CM | [10 empty] | D01 | IFA | T-0160 | 44486 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01969 | 44510 | 1400/08/19 | AP | PEDCOCRS-BK-00-HD-000-PR-DC-0001_D00 | [5 empty] | 1400-2294-261463 | 44504 | 1400/08/13 | 44510 | 1400/08/19 | AP | NISOC-CRS-BK-00-HD-000-PR-DC-0001_D00 | 1400-2290-294976 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D02 | AFD | T-0411 | 44562 | 1400/10/11 | [13 empty] | 1400-2294-368526 | 44578 | 1400/10/27 | 44580 | 1400/10/29 | AP
1 | 2 | 0 | 2 | 0 | 1 | 2 | 1.2.2.1.2 | BK-GNRAL-PEDCO-000-PR-DB-0001 | Process Basis Of Design |  | BK-GNRAL-PEDCO-000-PR-DB-0001 | BK-GNRAL-PEDCO-000-PR-DB-0001 | BK | GNRAL | PEDCO | 000 | PR | DB | 0001 | F0Z-707119 | AFD | IFC | 2021-08-10 | 2021-08-10 | 2021-08-08 | 0 | -2 | -2 | IFA | 2021-10-31 | 2021-11-04 | 2021-11-10 | 4 | 6 | 10 | IFA | 2021-12-14 | 2021-12-30 | 2022-01-02 | 16 | 3 | 19 | IFA | 2022-02-07 | 2022-02-26 | 2022-02-20 | 19 | -6 | 13 | IFA | 2022-03-22 | 2022-04-19 | 2022-04-30 | 28 | 11 | 39 | IFA | 2022-05-24 | 2022-06-11 | 2022-06-18 | 18 | 7 | 25 | [7 empty] | Modify | 2021-07-27 | 2022-10-09 |  | D08 | AFD | T-1473 | 44843 | 1401/07/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9966 | 44423 | 1400/05/24 | CM | [6 empty] | 1400/2294/159308 | 2021-08-10 | 1400/05/19 | 44416 | 1400/05/17 | CM | [10 empty] | D01 | IFA | T-0160 | 44486 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01969 | 44510 | 1400/08/19 | CM-C3 | PEDCO-CRS-BK-00-HD-000-PR-DB-0001_D00 | [5 empty] | 1400-2294-261463 | 44504 | 1400/08/13 | 44510 | 1400/08/19 | CM | NISOC-CRS-BK-00-HD-000-PR-DB-0001_D00 | [9 empty] | D02 | IFA | T-0285 | 44530 | 1400/09/09 |  |  |  | BK-SUR-ENG-PCS-00-02363 | 44549 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001-D01 | [5 empty] | 1400-2294-342083 | 44560 | 1400/10/09 | 44563 | 1400/10/12 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001-D01 | [9 empty] | D03 | IFA | T-0503 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-PCS-00-03096 | 44611 | 1400/11/30 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D02 | [5 empty] | 1400-2294-416040 | 44618 | 1400/12/07 | 44612 | 1400/12/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D02 | [9 empty] | D04 | IFA | T-0700 | 44628 | 1400/12/17 |  |  |  | BK-SUR-ENG-PCS-01-03783 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D03 | [5 empty] | 1401-2294-33692 | 44670 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D03 | [9 empty] | D05 | IFA | T-0925 | 44691 | 1401/02/20 |  |  |  | BK-SSR-ENG-PCS-01-04702 | 44727 | 1401/03/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D04 | [5 empty] | 1401-2294-95837 | 44723 | 1401/03/21 | 44730 | 1401/03/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D04 | [9 empty] | D06 | IFA | T-1157 | 44755 | 1401/04/22 |  |  |  | BK-SUR-ENG-PCS-01-05270 | 44772 | 1401/5/08 | CM | [6 empty] | 1401-2294-163039 | 44774 | 1401/05/10 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D05 | [9 empty] | D07 | IFA | T-1262 | 44782 | 1401/05/18 |  |  |  | BK-SUR-ENG-PCS-01-05493 | 44793 | 1401/05/29 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D06 | [5 empty] | 1401-2294-233568 | 44826 | 1401/06/31 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D06 | [9 empty] | D08 | AFD | T-1473 | 44843 | 1401/07/17
1 | 2 | 0 | 2 | 0 | 2 | 0 | 1.2.2.2 |  | Philosophy
1 | 2 | 0 | 2 | 0 | 2 | 1 | 1.2.2.2.1 | BK-GNRAL-PEDCO-000-PR-PH-0001 | Drainage Philosophy |  | BK-GNRAL-PEDCO-000-PR-PH-0001 | [59 empty] | Deleted | 2021-07-27 |  |  | D00 | IFC | T-0014 | 44404 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 44418 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01352 | 44430 | 1400/05/31 | CM-C3 | 0 | 1400-2294-150565 | 44411 | 1400/05/12 | 44416 | 1400/05/17 | CM | 0 | 1400-2294-186540 | 44445 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 44418 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01352 | 44430 | 1400/05/31 | CM-C3 |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 44416 | 1400/05/17 | CM |  | 1400-2294-186540 | 44445 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 2 | 2 | 1.2.2.2.2 | BK-GNRAL-PEDCO-000-PR-PH-0002 | Control Philosophy |  | BK-GNRAL-PEDCO-000-PR-PH-0002 | [59 empty] | Deleted | 2021-07-27 |  |  | D00 | IFC | T-0014 | 44404 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 44418 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01353 | 44430 | 1400/05/31 | RJ-C4 | 0 | 1400-2294-150565 | 44411 | 1400/05/12 | 44416 | 1400/05/17 | CM | 0 | 1400-2294-186540 | 44445 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 44418 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01353 | 44430 | 1400/05/31 | RJ-C4 |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 44416 | 1400/05/17 | CM |  | 1400-2294-186540 | 44445 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 2 | 3 | 1.2.2.2.3 | BK-GNRAL-PEDCO-000-PR-PH-0003 | Flare,Blow Down And Relief Philosophy |  | BK-GNRAL-PEDCO-000-PR-PH-0003 | [59 empty] | Deleted | 2021-07-27 |  |  | D00 | IFC | T-0014 | 44404 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 44418 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01356 | 44430 | 1400/05/31 | CM-C3 | 0 | 1400-2294-150565 | 44411 | 1400/05/12 | 44416 | 1400/05/17 | CM | 0 | 14002294-186540 | 44445 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 44418 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01356 | 44430 | 1400/05/31 | CM-C3 |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 44416 | 1400/05/17 | CM |  | 14002294-186540 | 44445 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 2 | 4 | 1.2.2.2.4 | BK-GNRAL-PEDCO-000-PR-PH-0004 | Isolation Philosophy |  | BK-GNRAL-PEDCO-000-PR-PH-0004 | [59 empty] | Deleted | 2021-07-27 |  |  | D00 | IFC | T-0014 | 44404 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 44418 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01358 | 44430 | 1400/05/31 | CM-C2 | 0 | 1400-2294-150565 | 44411 | 1400/05/12 | 44416 | 1400/05/17 | CM | 0 | 1400-2294-186540 | 44445 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 44418 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01358 | 44430 | 1400/05/31 | CM-C2 |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 44416 | 1400/05/17 | CM |  | 1400-2294-186540 | 44445 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 2 | 5 | 1.2.2.2.5 | BK-GNRAL-PEDCO-000-PR-PH-0005 | ESD Philosophy |  | BK-GNRAL-PEDCO-000-PR-PH-0005 | [59 empty] | Deleted | 2021-07-27 |  |  | D00 | IFC | T-0014 | 44404 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 44418 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01362 | 44430 | 1400/05/31 | CM-C2 | 0 | 1400-2294-150565 | 44411 | 1400/05/12 | 44416 | 1400/05/17 | CM | 0 | 1400-2294-186540 | 44445 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 44418 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01362 | 44430 | 1400/05/31 | CM-C2 |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 44416 | 1400/05/17 | CM |  | 1400-2294-186540 | 44445 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 3 | 0 | 1.2.2.3 |  | Drawing/Diagram
1 | 2 | 0 | 2 | 0 | 3 | 1 | 1.2.2.3.1 | BK-GNRAL-PEDCO-000-PR-PI-0001 | Symbol & Legend For PFD and P&ID |  | BK-GNRAL-PEDCO-000-PR-PI-0001 | [59 empty] | Deleted | 2021-08-04 |  |  | D00 | IFC | T-0030 | 44412 | 1400/05/13 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-01391 | 44432 | 1400/06/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179417 | 44438 | 1400/06/08 | 44446 | 1400/06/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0030 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-PCS-00-01391 | 44432 | 1400/06/02 | CM-C3 | [6 empty] | 1400-2294-179417 | 2021-08-30 | 1400/06/08 | 44446 | 1400/06/16 | CM
1 | 2 | 0 | 3 | 0 | 0 | 0 | 1.2.3 |  | Mechanical
1 | 2 | 0 | 3 | 0 | 1 | 0 | 1.2.3.1 |  | Basis/Criteria
1 | 2 | 0 | 3 | 0 | 1 | 1 | 1.2.3.1.1 | BK-GNRAL-PEDCO-000-ME-DC-0001 | Mechanical Design Criteria |  | BK-GNRAL-PEDCO-000-ME-DC-0001 | BK-GNRAL-PEDCO-000-ME-DC-0001 | BK | GNRAL | PEDCO | 000 | ME | DC | 0001 | F0Z-707120 | AFD | IFC | 2021-08-11 | 2022-08-12 | 2022-06-11 | 366 | -62 | 304 | IFA | 2022-07-05 | 2022-08-09 | 2022-08-13 | 35 | 4 | 39 | IFA | 2022-09-27 | 0 | 0 | -44831 | 0 | -44831 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 |  |  | D02 | IFA | T-1396 | 44817 | 1401/06/22 | T-1396 | 44817 | 1401/06/22 | BK-SUR-ENG-MEC-01-05928 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-DC-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DC-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0015 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-FXE-00-01277 | 44416 | 1400/05/17 | CM-C3 | [6 empty] | 1400-2294-162504 | 2022-08-12 | 1401/05/21 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1104 | 44733 | 1401/03/31 |  |  |  | BK-SUR-ENG-MEC-01-04973 | 44745 | 1401/04/12 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-DC-0001_D00 | [5 empty] | 1401-2294-170190 | 44782 | 1401/05/18 | 44786 | 1401/05/22 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DC-0001_D00 | [9 empty] | D02 | IFA | T-1396 | 44817 | 1401/06/22 | T-1396 | 44817 | 1401/06/22 | BK-SUR-ENG-MEC-01-05928 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-DC-0001_D01 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DC-0001_D01
1 | 2 | 0 | 3 | 0 | 2 | 0 | 1.2.3.2 |  | Specification
1 | 2 | 0 | 3 | 0 | 2 | 1 | 1.2.3.2.1 | BK-GNRAL-PEDCO-000-ME-SP-0001 | Specification For Pressure Vessels |  | BK-GNRAL-PEDCO-000-ME-SP-0001 | BK-GNRAL-PEDCO-000-ME-SP-0001 | BK | GNRAL | PEDCO | 000 | ME | SP | 0001 | F0Z-707121 | AFD | IFC | 2021-08-11 | 2022-08-12 | 2022-06-11 | 366 | -62 | 304 | IFA | 2022-07-27 | 2022-08-16 | 2022-08-21 | 20 | 5 | 25 | IFA | 2022-09-25 | 2022-09-13 | 2022-09-19 | -12 | 6 | -6 | AFD | 2022-11-12 | 0 | 0 | -44877 | 0 | -44877 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2022-10-29 |  | D03 | AFD | T-1565 | 44863 | 1401/08/07 | T-1565 | 44863 | 1401/08/07 | BK-SUR-ENG-MEC-01-06059 | 44835 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-SP-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0015 | 2021-07-28 | 1400/05/06 | [13 empty] | 1400-2294-162504 | 2022-08-12 | 1401/05/21 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1147 | 44755 | 1401/04/20 | [13 empty] | 1401-2294-180896 | 44789 | 1401/05/25 | 44794 | 1401/05/30 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0001_D00 | [9 empty] | D02 | IFA | T-1394 | 44815 | 1401/06/20 | T-1394 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05953 | 44857 | 1401/08/01 | CM-C3 | [6 empty] | 1401-2294-223839 | 44817 | 1401/06/22 | 44823 | 1401/06/28 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0001_D01 | [9 empty] | D03 | AFD | T-1565 | 44863 | 1401/08/07 | T-1565 | 44863 | 1401/08/07 | BK-SUR-ENG-MEC-01-06059 | 44835 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-SP-0001_D02 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0001_D02
1 | 2 | 0 | 3 | 0 | 2 | 2 | 1.2.3.2.2 | BK-GNRAL-PEDCO-000-ME-SP-0002 | Specification For Atmospheric Above Ground Welded Steel Tanks |  | BK-GNRAL-PEDCO-000-ME-SP-0002 | BK-GNRAL-PEDCO-000-ME-SP-0002 | BK | GNRAL | PEDCO | 000 | ME | SP | 0002 | F0Z-707122 | AFD | IFC | 2021-08-11 | 2022-08-12 | 2022-06-11 | 366 | -62 | 304 | IFA | 2022-08-07 | 2022-09-07 | 2022-09-12 | 31 | 5 | 36 | IFA | 2022-10-17 | 2022-10-10 | 2022-10-16 | -7 | 6 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 |  |  | D02 | IFA | T-1449 | 44837 | 1401/07/11 | T-1449 | 44837 | 1401/07/11 | BK-SUR-ENG-MEC-01-05961 | 44858 | 1401/08/02 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-SP-0002-D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256218 | 44844 | 1401/07/18 | 44850 | 1401/07/24 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0002-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0015 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-FXE-00-01277 | 44416 | 1400/05/17 | CM-C3 | [6 empty] | 1400-2294-162504 | 2022-08-12 | 1401/05/21 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1187 | 44766 | 1401/05/02 |  |  |  | BK-SUR-ENG-MEC-01-05754 | 44828 | 1401/07/02 | C4-RJ | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-SP-0002_D00 | [5 empty] | 1401-2294-210043 | 44811 | 1401/06/13 | 44816 | 1401/06/21 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0002_D00 | [9 empty] | D02 | IFA | T-1449 | 44837 | 1401/07/11 | T-1449 | 44837 | 1401/07/11 | BK-SUR-ENG-MEC-01-05961 | 44858 | 1401/08/02 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-SP-0002-D01 | [5 empty] | 1401-2294-256218 | 44844 | 1401/07/18 | 44850 | 1401/07/24 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0002-D01
1 | 2 | 0 | 3 | 0 | 3 | 0 | 1.2.3.3 |  | Drawing/Diagram
1 | 2 | 0 | 3 | 0 | 3 | 1 | 1.2.3.3.1 | BK-GNRAL-PEDCO-000-ME-DW-0001 | Standard Detail Drawing For Pressure Vessels and Heat Exchangers |  | BK-GNRAL-PEDCO-000-ME-DW-0001 | BK-GNRAL-PEDCO-000-ME-DW-0001 | BK | GNRAL | PEDCO | 000 | ME | DW | 0001 | F2C-707123 | IFI | IFI | 2021-08-11 | 2022-08-12 | 2022-06-11 | 366 | -62 | 304 | IFI | 2022-08-17 | 2022-09-12 | 2022-09-14 | 26 | 2 | 28 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 |  |  | D01 | IFI | T-1240 | 44776 | 1401/05/12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-220567 | 44816 | 1401/06/21 | 44818 | 1401/06/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0015 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-FXE-00-01277 | 44416 | 1400/05/17 | CM-C3 | [6 empty] | 1400-2294-162504 | 2022-08-12 | 1401/05/21 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFI | T-1240 | 44776 | 1401/05/12 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-DW-0001_D00 | [5 empty] | 1401-2294-220567 | 44816 | 1401/06/21 | 44818 | 1401/06/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DW-0001_D00
1 | 2 | 0 | 3 | 0 | 3 | 2 | 1.2.3.3.2 | BK-GNRAL-PEDCO-000-ME-DW-0002 | Standard Detail Drawing For Storage Tanks |  | BK-GNRAL-PEDCO-000-ME-DW-0002 | BK-GNRAL-PEDCO-000-ME-DW-0002 | BK | GNRAL | PEDCO | 000 | ME | DW | 0002 | F2D-707124 | IFI | IFI | 2021-08-11 | 2022-08-12 | 2022-06-11 | 366 | -62 | 304 | IFI | 2022-08-17 | 2022-09-08 | 2022-09-12 | 22 | 4 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 |  |  | D01 | IFI | T-1246 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05825 | 44837 | 1401/07/11 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216173 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0015 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-FXE-00-01277 | 44416 | 1400/05/17 | AP | [6 empty] | 1400-2294-162504 | 2022-08-12 | 1400/05/21 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFI | T-1246 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-MEC-01-05825 | 44837 | 1401/07/11 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-DW-0002_D00 | [5 empty] | 1401-2294-216173 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DW-0002_D00
1 | 2 | 0 | 4 | 0 | 0 | 0 | 1.2.4 |  | HVAC/Plumbing
1 | 2 | 0 | 4 | 0 | 1 | 0 | 1.2.4.1 |  | Basis/Criteria
1 | 2 | 0 | 4 | 0 | 1 | 1 | 1.2.4.1.1 | BK-GNRAL-PEDCO-000-HV-DC-0001 | HVAC & Plumbing Design Criteria |  | BK-GNRAL-PEDCO-000-HV-DC-0001 | BK-GNRAL-PEDCO-000-HV-DC-0001 | BK | GNRAL | PEDCO | 000 | HV | DC | 0001 | F0Z-707125 | AFC | IFC | 2021-08-07 | 2021-08-25 | 0 | 18 | -44433 | -44415 | IFA | 2021-09-26 | 2021-09-13 | 2021-09-15 | -13 | 2 | -11 | AFD | 2022-03-08 | 2022-03-10 | 2022-03-13 | 2 | 3 | 5 | AFC | 2022-08-09 | 2022-08-04 | 2022-08-10 | -5 | 6 | 1 | AFC | 2022-09-25 | 2022-09-21 | 2022-10-03 | -4 | 12 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D04 | AFC | T-1387 | 44815 | 1401/06/20 | T-1387 | 44816 | 1401/06/21 | BK-SUR-ENG-ELE-01-05738 | 44825 | 1401/06/30 | AP | 0 | BK-SUR-ENG-HVC-01-05902 | 44850 | 1401/07/24 | CM-C3 | 0 | 1401-2294-233338 | 44825 | 1401/06/30 | 44837 | 1401/07/11 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-HV-DC-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0005 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/173327 | 2021-08-25 | 1400/06/03 |  |  | AP | [10 empty] | D01 | IFA | T-0085 | 44451 | 1400/06/21 |  |  |  | BK-SUR-ENG-HVC-00-01522 | 44457 | 1400/06/27 | CM-C2 | [6 empty] | 1400-2294-197387 | 44452 | 1400/06/22 | 44454 | 1400/06/24 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-HV-DC-0001_D00 | [9 empty] | D02 | AFD | T-0624 | 44614 | 1400/12/03 |  |  |  | BK-SUR-ENG-HVC-00-03493 | 44633 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-DC-0001_D01 | [5 empty] | 1400-2294-443215 | 44630 | 1400/12/19 | 44633 | 1400/12/22 | RJ | [10 empty] | D03 | AFC | T-1201 | 44768 | 1401/05/04 | [13 empty] | 1401-2294-167299 | 44777 | 1401/05/13 | 44783 | 1401/05/19 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-HV-DC-0001_D03 | [9 empty] | D04 | AFC | T-1387 | 44815 | 1401/06/20 | T-1387 | 44816 | 1401/06/21 | BK-SUR-ENG-ELE-01-05738 | 44825 | 1401/06/30 | AP |  | BK-SUR-ENG-HVC-01-05902 | 44850 | 1401/07/24 | CM-C3 |  | 1401-2294-233338 | 44825 | 1401/06/30 | 44837 | 1401/07/11 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-HV-DC-0001_D03
1 | 2 | 0 | 4 | 0 | 2 | 0 | 1.2.4.2 |  | Specification
1 | 2 | 0 | 4 | 0 | 2 | 1 | 1.2.4.2.1 | BK-GNRAL-PEDCO-000-HV-SP-0001 | Specification For HVAC Equipment |  | BK-GNRAL-PEDCO-000-HV-SP-0001 | BK-GNRAL-PEDCO-000-HV-SP-0001 | BK | GNRAL | PEDCO | 000 | HV | SP | 0001 | F0Z-707126 | AFD | IFC | 2021-08-07 | 2021-08-25 | 0 | 18 | -44433 | -44415 | AFD | 2021-09-26 | 2021-09-13 | 2021-09-15 | -13 | 2 | -11 | AFD | 2021-10-24 | 2021-10-17 | 2021-10-19 | -7 | 2 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2021-10-10 |  | D02 | AFD | T-0144 | 44479 | 1400/07/18 | 0 | 0 | 0 | BK-SUR-ENG-HVC-00-01791 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-SP-0001-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-237984 | 44486 | 1400/07/25 | 44488 | 1400/07/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0005 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/173327 | 2021-08-25 | 1400/06/03 |  |  | AP | [10 empty] | D01 | AFD | T-0086 | 44451 | 1400/06/21 |  |  |  | BK-SUR-ENG-HVC-00-01519 | 44454 | 1400/06/24 | CM-C2 | [6 empty] | 1400-2294-197389 | 44452 | 1400/06/22 | 44454 | 1400/06/24 | AP | [10 empty] | D02 | AFD | T-0144 | 44479 | 1400/07/18 |  |  |  | BK-SUR-ENG-HVC-00-01791 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-SP-0001-D01 | [5 empty] | 1400-2294-237984 | 44486 | 1400/07/25 | 44488 | 1400/07/27 | AP
1 | 2 | 0 | 4 | 0 | 2 | 2 | 1.2.4.2.2 | BK-GNRAL-PEDCO-000-HV-SP-0002 | Specification For Duct Work & Pipe Work |  | BK-GNRAL-PEDCO-000-HV-SP-0002 | BK-GNRAL-PEDCO-000-HV-SP-0002 | BK | GNRAL | PEDCO | 000 | HV | SP | 0002 | F0Z-707127 | AFD | IFC | 2021-08-07 | 2021-08-25 | 0 | 18 | -44433 | -44415 | AFD | 2021-09-26 | 2021-09-13 | 2021-09-15 | -13 | 2 | -11 | AFD | 2021-10-24 | 2021-10-17 | 2021-10-19 | -7 | 2 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2021-10-10 |  | D02 | AFD | T-0144 | 44479 | 1400/07/18 | 0 | 0 | 0 | BK-SUR-ENG-HVC-00-01791 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-SP-0002-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-237984 | 44486 | 1400/07/25 | 44488 | 1400/07/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0005 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/173327 | 2021-08-25 | 1400/06/03 |  |  | AP | [10 empty] | D01 | AFD | T-0086 | 44451 | 1400/06/21 |  |  |  | BK-SUR-ENG-HVC-00-01519 | 44454 | 1400/06/24 | CM-C2 | [6 empty] | 1400-2294-197389 | 44452 | 1400/06/22 | 44454 | 1400/06/24 | AP | [10 empty] | D02 | AFD | T-0144 | 44479 | 1400/07/18 |  |  |  | BK-SUR-ENG-HVC-00-01791 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-SP-0002-D01 | [5 empty] | 1400-2294-237984 | 44486 | 1400/07/25 | 44488 | 1400/07/27 | AP
1 | 2 | 0 | 4 | 0 | 3 | 0 | 1.2.4.3 |  | Drawing/Diagram
1 | 2 | 0 | 4 | 0 | 3 | 1 | 1.2.4.3.1 | BK-GNRAL-PEDCO-000-HV-DW-0001 | Standard Drawing For HVAC & Plumbing |  | BK-GNRAL-PEDCO-000-HV-DW-0001 | BK-GNRAL-PEDCO-000-HV-DW-0001 | BK | GNRAL | PEDCO | 000 | HV | DW | 0001 | F4B-707128 | IFI | IFC | 2021-08-07 | 2021-08-25 | 0 | 18 | -44433 | -44415 | IFI | 2021-09-26 | 2021-09-13 | 2021-09-15 | -13 | 2 | -11 | IFI | 2021-10-24 | 2021-10-17 | 2021-10-19 | -7 | 2 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D02 | IFI | T-0145 | 44479 | 1400/07/18 | 0 | 0 | 0 | BK-SUR-ENG-HVC-00-01791 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-DW-0001-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-238019 | 44486 | 1400/07/25 | 44488 | 1400/07/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0005 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/173327 | 2021-08-25 | 1400/06/03 |  |  | AP | [10 empty] | D01 | IFI | T-0086 | 44451 | 1400/06/21 |  |  |  | BK-SUR-ENG-HVC-00-01519 | 44454 | 1400/06/24 | CM-C2 | [6 empty] | 1400-2294-197389 | 44452 | 1400/06/22 | 44454 | 1400/06/24 | AP | [10 empty] | D02 | IFI | T-0145 | 44479 | 1400/07/18 |  |  |  | BK-SUR-ENG-HVC-00-01791 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-DW-0001-D01 | [5 empty] | 1400-2294-238019 | 44486 | 1400/07/25 | 44488 | 1400/07/27 | AP
1 | 2 | 0 | 4 | 0 | 3 | 2 | 1.2.4.3.2 | BK-GNRAL-PEDCO-000-HV-DW-0002 | Symbol & Legend For HVAC & Plumbing |  | BK-GNRAL-PEDCO-000-HV-DW-0002 | BK-GNRAL-PEDCO-000-HV-DW-0002 | BK | GNRAL | PEDCO | 000 | HV | DW | 0002 | F4B-707129 | AFC | IFC | 2021-09-05 | 2022-08-23 | 2022-06-09 | 352 | -75 | 277 | AFC | 2022-09-19 | 2022-10-20 | 2022-10-24 | 31 | 4 | 35 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 | 2022-09-05 |  | D01 | AFC | T-1364 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-05841 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-271833 | 44854 | 1401/07/28 | 44858 | 1401/08/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0055 | 2021-08-22 | 1400/05/31 | [13 empty] | 1400-2294-170584 | 2022-08-23 | 1400/06/01 | 44721 | 1401/03/19 | CM |  | 1400-2294-173888 | 44436 | 1400/06/03 | 44719 | 1401/03/17 | AP |  |  |  | D01 | AFC | T-1364 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-HVC-01-05841 | 44842 | 1401/07/16 | AP | [6 empty] | 1401-2294-271833 | 44854 | 1401/07/28 | 44858 | 1401/08/02 | AP
1 | 2 | 0 | 5 | 0 | 0 | 0 | 1.2.5 |  | Piping
1 | 2 | 0 | 5 | 0 | 1 | 0 | 1.2.5.1 |  | Basis/Criteria
1 | 2 | 0 | 5 | 0 | 1 | 1 | 1.2.5.1.1 | BK-GNRAL-PEDCO-000-PI-DC-0001 | Piping Design Criteria |  | BK-GNRAL-PEDCO-000-PI-DC-0001 | BK-GNRAL-PEDCO-000-PI-DC-0001 | BK | GNRAL | PEDCO | 000 | PI | DC | 0001 | F0Z-707130 | AFD | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-10-26 | 2021-10-24 | 2021-11-22 | -2 | 29 | 27 | IFA | 2022-01-02 | 2021-12-29 | 2022-01-02 | -4 | 4 | 0 | AFD | 2022-01-30 | 2022-01-23 | 2022-01-25 | -7 | 2 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-01-16 |  | D03 | AFD | T-0466 | 44577 | 1400/10/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-377387 | 44584 | 1400/11/03 | 44586 | 1400/11/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0153 | 44481 | 1400/07/12 |  |  |  | BK-SUR-ENG-PIP-00-01776 | 44487 | 1400/07/26 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-DC-0001 | [5 empty] | 1400-2294-245975 | 44493 | 1400/08/02 | 44522 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-DC-0001 | [9 empty] | D02 | IFA | T-0365 | 44549 | 1400/09/28 |  |  |  | BK-SUR-ENG-PIP-00-02490 | 44348 | 1400/10/11 | AP | [6 empty] | 1400-2294-341974 | 44559 | 1400/10/08 | 44563 | 1400/10/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-DC-0001_D01 | [9 empty] | D03 | AFD | T-0466 | 44577 | 1400/10/26 | [13 empty] | 1400-2294-377387 | 44584 | 1400/11/03 | 44586 | 1400/11/05 | AP
1 | 2 | 0 | 5 | 0 | 2 | 0 | 1.2.5.2 |  | Specification
1 | 2 | 0 | 5 | 0 | 2 | 1 | 1.2.5.2.1 | BK-GNRAL-PEDCO-000-PI-SP-0001 | Specification For Color Coding and Marking |  | BK-GNRAL-PEDCO-000-PI-SP-0001 | BK-GNRAL-PEDCO-000-PI-SP-0001 | BK | GNRAL | PEDCO | 000 | PI | SP | 0001 | F0Z-707131 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C2 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 2 | 1.2.5.2.2 | BK-GNRAL-PEDCO-000-PI-SP-0002 | Specification For Transportation, Handling, Storage of pipes |  | BK-GNRAL-PEDCO-000-PI-SP-0002 | BK-GNRAL-PEDCO-000-PI-SP-0002 | BK | GNRAL | PEDCO | 000 | PI | SP | 0002 | F0Z-707132 | AFD | IFC | 2021-12-26 | 2021-12-20 | 2021-12-26 | -6 | 6 | 0 | IFA | 2022-03-20 | 2022-01-17 | 2022-04-19 | -62 | 92 | 30 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-12 |  |  | D01 | IFA | T-0677 | 44626 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03538 | 44634 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27248 | 44578 | 1401/01/28 | 44670 | 1401/01/30 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0330 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02422 | 44556 | 1400/10/05 | CM-C3 | [6 empty] | 1400-2294-327385 | 2021-12-20 | 1400/09/29 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0677 | 44626 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 44634 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0002_D00 | [5 empty] | 1401-2294-27248 | 44578 | 1401/01/28 | 44670 | 1401/01/30 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0002_D00
1 | 2 | 0 | 5 | 0 | 2 | 3 | 1.2.5.2.3 | BK-GNRAL-PEDCO-000-PI-SP-0003 | Specification For the Design of Piping in Mechanical Packages |  | BK-GNRAL-PEDCO-000-PI-SP-0003 | BK-GNRAL-PEDCO-000-PI-SP-0003 | BK | GNRAL | PEDCO | 000 | PI | SP | 0003 | F0Z-707133 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 4 | 1.2.5.2.4 | BK-GNRAL-PEDCO-000-PI-SP-0004 | Specification For Metallic Pipes |  | BK-GNRAL-PEDCO-000-PI-SP-0004 | BK-GNRAL-PEDCO-000-PI-SP-0004 | BK | GNRAL | PEDCO | 000 | PI | SP | 0004 | F0Z-707134 | AFD | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | IFA | 2021-11-21 | 2021-11-24 | 2021-11-27 | 3 | 3 | 6 | IFA | 2021-12-21 | 2021-12-22 | 2021-12-26 | 1 | 4 | 5 | IFA | 2022-01-18 | 2022-01-16 | 2022-01-16 | -2 | 0 | -2 | IFA | 2022-03-09 | 2022-03-13 | 2022-04-03 | 4 | 21 | 25 | [7 empty] | Modify | 2021-07-24 |  |  | D05 | IFA | T-0637 | 44615 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03402 | 44628 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-447219 | 44633 | 1400/12/22 | 44654 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0124 | 44468 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 44482 | 1400/07/21 | CM-C2 | [6 empty] | 1400-2294-236255 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004_D00 | [9 empty] | D02 | IFA | T-0214 | 44507 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01985 | 44514 | 1400/08/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004-D01 | [5 empty] | 1400-2294-290052 | 44524 | 1400/09/03 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004-D01 | [9 empty] | D03 | IFA | T-0310 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02442 | 44556 | 1400/10/05 | AP | [6 empty] | 1400-2294-331639 | 44552 | 1400/10/01 | 44556 | 1400/10/05 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004-D02 | [9 empty] | D04 | IFA | T-0424 | 44565 | 1400/10/14 |  |  |  | BK-SUR-ENG-PIP-00-02583 | 44566 | 1400/10/15 | AP | [6 empty] | 1400-2294-365876 | 44577 | 1400/10/26 | 44577 | 1400/10/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004-D03 | [9 empty] | D05 | IFA | T-0637 | 44615 | 1400/12/04 |  |  |  | BK-SUR-ENG-PIP-00-03402 | 44628 | 1400/12/17 | AP | [6 empty] | 1400-2294-447219 | 44633 | 1400/12/22 | 44654 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004_D04
1 | 2 | 0 | 5 | 0 | 2 | 5 | 1.2.5.2.5 | BK-GNRAL-PEDCO-000-PI-SP-0005 | Specification For Fittings, Flanges, Gaskets and Bolts |  | BK-GNRAL-PEDCO-000-PI-SP-0005 | BK-GNRAL-PEDCO-000-PI-SP-0005 | BK | GNRAL | PEDCO | 000 | PI | SP | 0005 | F0Z-707135 | AFD | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | AFD | 2021-11-21 | 2021-11-09 | 2021-11-14 | -12 | 5 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2021-11-07 |  | D02 | AFD | T-0216 | 44507 | 1400/08/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01983 | 44513 | 1400/08/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0005-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-269292 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0124 | 44468 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 44482 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0005_D00 | [5 empty] | 1400-2294-236255 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0005_D00 | [9 empty] | D02 | AFD | T-0216 | 44507 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01983 | 44513 | 1400/08/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0005-D01 | [5 empty] | 1400-2294-269292 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP
1 | 2 | 0 | 5 | 0 | 2 | 6 | 1.2.5.2.6 | BK-GNRAL-PEDCO-000-PI-SP-0006 | Specification For Painting |  | BK-GNRAL-PEDCO-000-PI-SP-0006 | BK-GNRAL-PEDCO-000-PI-SP-0006 | BK | GNRAL | PEDCO | 000 | PI | SP | 0006 | F0Z-707136 | AFD | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | IFA | 2021-11-21 | 2021-11-24 | 2021-11-27 | 3 | 3 | 6 | IFA | 2021-12-21 | 2021-12-22 | 2021-12-26 | 1 | 4 | 5 | AFD | 2022-01-18 | 2022-01-16 | 2022-01-16 | -2 | 0 | -2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-01-04 |  | D04 | AFD | T-0424 | 44565 | 1400/10/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02583 | 44566 | 1400/10/15 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-365876 | 44577 | 1400/10/26 | 44577 | 1400/10/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0124 | 44468 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 44482 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006-D00 | [5 empty] | 1400-2294-236255 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006_D00 | [9 empty] | D02 | IFA | T-0214 | 44507 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01985 | 44514 | 1400/08/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006-D01 | [5 empty] | 1400-2294-290052 | 44524 | 1400/09/03 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006-D01 | [9 empty] | D03 | IFA | T-0310 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02442 | 44556 | 1400/10/05 | AP | [6 empty] | 1400-2294-331639 | 44552 | 1400/10/01 | 44556 | 1400/10/05 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006-D02 | [9 empty] | D04 | AFD | T-0424 | 44565 | 1400/10/14 |  |  |  | BK-SUR-ENG-PIP-00-02583 | 44566 | 1400/10/15 | AP | [6 empty] | 1400-2294-365876 | 44577 | 1400/10/26 | 44577 | 1400/10/26 | AP
1 | 2 | 0 | 5 | 0 | 2 | 7 | 1.2.5.2.7 | BK-GNRAL-PEDCO-000-PI-SP-0007 | Specification For Lining (Internal Protection of Equipment by Painting) |  | BK-GNRAL-PEDCO-000-PI-SP-0007 | BK-GNRAL-PEDCO-000-PI-SP-0007 | BK | GNRAL | PEDCO | 000 | PI | SP | 0007 | F0Z-707137 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 8 | 1.2.5.2.8 | BK-GNRAL-PEDCO-000-PI-SP-0008 | Specification For Material Requirements in Sour service |  | BK-GNRAL-PEDCO-000-PI-SP-0008 | BK-GNRAL-PEDCO-000-PI-SP-0008 | BK | GNRAL | PEDCO | 000 | PI | SP | 0008 | F0Z-707138 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 9 | 1.2.5.2.9 | BK-GNRAL-PEDCO-000-PI-SP-0009 | Specification For Manual Valves |  | BK-GNRAL-PEDCO-000-PI-SP-0009 | BK-GNRAL-PEDCO-000-PI-SP-0009 | BK | GNRAL | PEDCO | 000 | PI | SP | 0009 | F0Z-707139 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 10 | 1.2.5.2.10 | BK-GNRAL-PEDCO-000-PI-SP-0010 | Specification For Plant Piping Systems Pressure Testing |  | BK-GNRAL-PEDCO-000-PI-SP-0010 | BK-GNRAL-PEDCO-000-PI-SP-0010 | BK | GNRAL | PEDCO | 000 | PI | SP | 0010 | F0Z-707140 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 11 | 1.2.5.2.11 | BK-GNRAL-PEDCO-000-PI-SP-0011 | Specification For Welding of Plant Piping System |  | BK-GNRAL-PEDCO-000-PI-SP-0011 | BK-GNRAL-PEDCO-000-PI-SP-0011 | BK | GNRAL | PEDCO | 000 | PI | SP | 0011 | F0Z-707141 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C2 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 12 | 1.2.5.2.12 | BK-GNRAL-PEDCO-000-PI-SP-0012 | Specification For Flexibility Analysis |  | BK-GNRAL-PEDCO-000-PI-SP-0012 | BK-GNRAL-PEDCO-000-PI-SP-0012 | BK | GNRAL | PEDCO | 000 | PI | SP | 0012 | F0Z-707142 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 13 | 1.2.5.2.13 | BK-GNRAL-PEDCO-000-PI-SP-0013 | Specification For Coating Of Underground Piping |  | BK-GNRAL-PEDCO-000-PI-SP-0013 | BK-GNRAL-PEDCO-000-PI-SP-0013 | BK | GNRAL | PEDCO | 000 | PI | SP | 0013 | F0Z-707143 | AFD | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | IFA | 2021-11-21 | 2021-11-24 | 2021-11-27 | 3 | 3 | 6 | IFA | 2021-12-21 | 2021-12-22 | 2021-12-26 | 1 | 4 | 5 | IFA | 2022-01-18 | 2022-01-16 | 2022-01-16 | -2 | 0 | -2 | AFD | 2022-03-09 | 2022-03-06 | 2022-03-08 | -3 | 2 | -1 | [7 empty] | Modify | 2021-07-24 | 2022-02-23 |  | D05 | AFD | T-0638 | 44615 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03396 | 44628 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-436238 | 44626 | 1400/12/15 | 44628 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 44415 | 1400/05/16 | CM-C2 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0124 | 44468 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 44482 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013_D00 | [5 empty] | 1400-2294-236255 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013_D00 | [9 empty] | D02 | IFA | T-0214 | 44507 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01985 | 44514 | 1400/08/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013-D01 | [5 empty] | 1400-2294-290052 | 44524 | 1400/09/03 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013-D01 | [9 empty] | D03 | IFA | T-0310 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02442 | 44556 | 1400/10/05 | AP | [6 empty] | 1400-2294-331639 | 44552 | 1400/10/01 | 44556 | 1400/10/05 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013-D02 | [9 empty] | D04 | IFA | T-0424 | 44565 | 1400/10/14 |  |  |  | BK-SUR-ENG-PIP-00-02583 | 44566 | 1400/10/15 | AP | [6 empty] | 1400-2294-365876 | 44577 | 1400/10/26 | 44577 | 1400/10/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013-D03 | [9 empty] | D05 | AFD | T-0638 | 44615 | 1400/12/04 |  |  |  | BK-SUR-ENG-PIP-00-03396 | 44628 | 1400/12/17 | AP | [6 empty] | 1400-2294-436238 | 44626 | 1400/12/15 | 44628 | 1400/12/17 | AP
1 | 2 | 0 | 5 | 0 | 2 | 14 | 1.2.5.2.14 | BK-GNRAL-PEDCO-000-PI-SP-0014 | Specification For Pipe Support |  | BK-GNRAL-PEDCO-000-PI-SP-0014 | BK-GNRAL-PEDCO-000-PI-SP-0014 | BK | GNRAL | PEDCO | 000 | PI | SP | 0014 | F0Z-707144 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 15 | 1.2.5.2.15 | BK-GNRAL-PEDCO-000-PI-SP-0015 | Specification For Piping Construction, Fabrication & Erection |  | BK-GNRAL-PEDCO-000-PI-SP-0015 | BK-GNRAL-PEDCO-000-PI-SP-0015 | BK | GNRAL | PEDCO | 000 | PI | SP | 0015 | F0Z-707145 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C2 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 16 | 1.2.5.2.16 | BK-GNRAL-PEDCO-000-PI-SP-0016 | Specification For Piping Design & Plant Layout |  | BK-GNRAL-PEDCO-000-PI-SP-0016 | BK-GNRAL-PEDCO-000-PI-SP-0016 | BK | GNRAL | PEDCO | 000 | PI | SP | 0016 | F0Z-707146 | AFD | IFC | 2021-08-23 | 2022-07-27 | 2022-07-31 | 338 | 4 | 342 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 |  |  | D00 | IFC | T-0039 | 44417 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156748 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 44444 | 1400/06/14 | CM-C3 | [6 empty] | 1401-2294-156748 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
1 | 2 | 0 | 5 | 0 | 2 | 17 | 1.2.5.2.17 | BK-GNRAL-PEDCO-000-PI-SP-0017 | Specification For Piping Cleaning and Flushing | Specification For Cleaning and Flushing | BK-GNRAL-PEDCO-000-PI-SP-0017 | BK-GNRAL-PEDCO-000-PI-SP-0017 | BK | GNRAL | PEDCO | 000 | PI | SP | 0017 | F0Z-707147 | AFD | IFC | 2021-09-07 | 2021-09-12 | 2021-09-14 | 5 | 2 | 7 | IFA | 2021-10-18 | 2021-12-04 | 2021-11-08 | 47 | -26 | 21 | AFD | 2021-12-29 | 0 | 0 | -44559 | 0 | -44559 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-24 | 2021-12-15 |  | D02 | AFD | T-0350 | 44545 | 1400/09/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02374 | 44549 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0017-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0065 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PIP-00-01517 | 44453 | 1400/06/23 | CM-C3 | [6 empty] | 1400-2294-194218 | 2021-09-12 | 1400-06-21 | 44453 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0137 | 44473 | 1400/07/12 |  |  |  | BK-SUR-ENG-PIP-00-01729 | 44482 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0017-D00 | [5 empty] | 1400-2294-261499 | 44534 | 1400/08/13 | 44508 | 1400/08/17 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0017-D00 | [9 empty] | D02 | AFD | T-0350 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-PIP-00-02374 | 44549 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0017-D01
1 | 2 | 0 | 5 | 0 | 2 | 18 | 1.2.5.2.18 | BK-GNRAL-PEDCO-000-PI-SP-0018 | Specification For HDPE Pipes |  | BK-GNRAL-PEDCO-000-PI-SP-0018 | BK-GNRAL-PEDCO-000-PI-SP-0018 | BK | GNRAL | PEDCO | 000 | PI | SP | 0018 | F0Z-707148 | AFD | IFC | 2021-09-07 | 2021-09-12 | 2021-09-14 | 5 | 2 | 7 | AFD | 2021-11-02 | 2021-10-23 | 2021-10-25 | -10 | 2 | -8 | AFD | 2021-12-26 | 2021-12-20 | 2021-12-25 | -6 | 5 | -1 | AFD | 2022-02-05 | 2022-01-23 | 2022-01-30 | -13 | 7 | -6 | AFD | 2022-03-19 | 0 | 0 | -44639 | 0 | -44639 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-24 | 2022-03-05 |  | D04 | AFD | T-0674 | 44625 | 1400/12/14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0065 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PIP-00-01517 | 44453 | 1400/06/23 | CM-C3 | [6 empty] | 1400-2294-194218 | 2021-09-12 | 1400-06-21 | 44453 | 1400/06/23 | AP | [10 empty] | D01 | AFD | T-0173 | 44488 | 1400/07/27 |  |  |  | BK-SUR-ENG-PIP-00-01790 | 44488 | 1400/07/27 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018-D00 | [5 empty] | 1400-2294-243783 | 44492 | 1400/08/01 | 44494 | 1400/08/03 | AP | [10 empty] | D02 | AFD | T-0328 | 44542 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02382 | 44550 | 1400/09/29 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018-D01 | [5 empty] | 1400-2294-327374 | 44550 | 1400/09/29 | 44555 | 1400/10/04 | AP | [10 empty] | D03 | AFD | T-0483 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-PIP-00-02756 | 44582 | 1400/11/01 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018-D02 | [5 empty] | 1400-2294-377397 | 44584 | 1400/11/03 | 44591 | 1400/11/10 | RJ | [10 empty] | D04 | AFD | T-0674 | 44625 | 1400/12/14 | [19 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018_D03
1 | 2 | 0 | 5 | 0 | 2 | 19 | 1.2.5.2.19 | BK-GNRAL-PEDCO-000-PI-SP-0019 | Specification For Insulation |  | BK-GNRAL-PEDCO-000-PI-SP-0019 | BK-GNRAL-PEDCO-000-PI-SP-0019 | BK | GNRAL | PEDCO | 000 | PI | SP | 0019 | F0Z-707149 | AFD | IFC | 2021-09-07 | 2021-09-12 | 2021-09-14 | 5 | 2 | 7 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | AFD | 2021-11-21 | 2021-11-09 | 2021-11-14 | -12 | 5 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-24 | 2021-11-07 |  | D02 | AFD | T-0216 | 44507 | 1400/08/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01983 | 44513 | 1400/08/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0019-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-269292 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0065 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PIP-00-01517 | 44453 | 1400/06/23 | CM-C3 | [6 empty] | 1400-2294-194218 | 2021-09-12 | 1400-06-21 | 44453 | 1400/06/23 | AP | [10 empty] | D01 | IFA | T-0124 | 44468 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 44482 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0019_D00 | [5 empty] | 1400-2294-236255 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | AP | [10 empty] | D02 | AFD | T-0216 | 44507 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01983 | 44513 | 1400/08/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0019-D01 | [5 empty] | 1400-2294-269292 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP
1 | 2 | 0 | 5 | 0 | 3 | 0 | 1.2.5.3 |  | Procedure/Plan
1 | 2 | 0 | 5 | 0 | 3 | 1 | 1.2.5.3.1 | BK-GNRAL-PEDCO-000-PI-PR-0001 | 3D-Model (PDMS) Review Procedure |  | BK-GNRAL-PEDCO-000-PI-PR-0001 | BK-GNRAL-PEDCO-000-PI-PR-0001 | BK | GNRAL | PEDCO | 000 | PI | PR | 0001 | F0Z-707150 | AFC | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-12-11 | 2021-12-05 | 2021-12-07 | -6 | 2 | -4 | AFC | 2022-01-30 | 2022-01-23 | 2022-01-25 | -7 | 2 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-01-16 |  | D02 | AFC | T-0466 | 44577 | 1400/10/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-377387 | 44584 | 1400/11/03 | 44586 | 1400/11/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0273 | 44527 | 1400/09/06 |  |  |  | BK-SUR-ENG-PIP-00-02385 | 44551 | 1400/09/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-PR-0001-D00 | [5 empty] | 1400-2294-303942 | 44535 | 1400/09/14 | 44537 | 1400/09/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-PR-0001_D00 | [9 empty] | D02 | AFC | T-0466 | 44577 | 1400/10/26 | [13 empty] | 1400-2294-377387 | 44584 | 1400/11/03 | 44586 | 1400/11/05 | AP
1 | 2 | 0 | 5 | 0 | 3 | 2 | 1.2.5.3.2 | BK-GNRAL-PEDCO-000-PI-PR-0002 | Piping Hydrostatic Test Diagram - Sub Surface |  | BK-GNRAL-PEDCO-000-PI-PR-0002 | [8 empty] | 0 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 6 | 0 | 0 | 0 | 1.2.6 |  | Pipeline
1 | 2 | 0 | 6 | 0 | 1 | 0 | 1.2.6.1 |  | Basis/Criteria
1 | 2 | 0 | 6 | 0 | 1 | 1 | 1.2.6.1.1 | BK-GNRAL-PEDCO-000-PL-DC-0001 | Pipeline Design Criteria |  | BK-GNRAL-PEDCO-000-PL-DC-0001 | BK-GNRAL-PEDCO-000-PL-DC-0001 | BK | GNRAL | PEDCO | 000 | PL | DC | 0001 | F0Z-707151 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-01-30 | 2022-01-29 | 2022-01-30 | -1 | 1 | 0 | AFD | 2022-02-16 | 2022-02-26 | 2022-02-28 | 10 | 2 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-28 | 2022-02-02 |  | D02 | AFD | T-0537 | 44594 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-426685 | 44618 | 1400/12/07 | 44620 | 1400/12/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 44551 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 44551 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0467 | 44577 | 1400/10/26 |  |  |  | BK-SUR-ENG-PPL-00-02747 | 44580 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DC-0001_D00 | [5 empty] | 1400-2294-386710 | 44590 | 1400/11/09 | 44591 | 1400/11/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DC-0001_D00 | [9 empty] | D02 | AFD | T-0537 | 44594 | 1400/11/13 | [13 empty] | 1400-2294-426685 | 44618 | 1400/12/07 | 44620 | 1400/12/09 | AP
1 | 2 | 0 | 6 | 0 | 2 | 0 | 1.2.6.2 |  | Specification
1 | 2 | 0 | 6 | 0 | 2 | 1 | 1.2.6.2.1 | BK-GNRAL-PEDCO-000-PL-SP-0002 | Specification For Line Pipes |  | BK-GNRAL-PEDCO-000-PL-SP-0002 | BK-GNRAL-PEDCO-000-PL-SP-0002 | BK | GNRAL | PEDCO | 000 | PL | SP | 0002 | F0Z-707152 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-10-04 | 2021-09-25 | 2021-09-29 | -9 | 4 | -5 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 44537 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01311 | 44418 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 44418 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0108 | 44459 | 1400/06/29 |  |  |  | BK-SUR-ENG-PPL-00-01581 | 44461 | 1400/06/31 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0002_D00 | [5 empty] | 1400-2294-210823 | 44464 | 1400/07/03 | 44468 | 1400/07/07 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0002_D00 | [9 empty] | D02 | IFA | T-0174 | 44488 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 44500 | 1400/08/09 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0002-D01 | [5 empty] | 1400-2294-269298 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0002-D01 | [9 empty] | D03 | AFD | T-0312 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | AP | [6 empty] | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 2 | 1.2.6.2.2 | BK-GNRAL-PEDCO-000-PL-SP-0003 | Specification For Pipeline Cold Bending |  | BK-GNRAL-PEDCO-000-PL-SP-0003 | BK-GNRAL-PEDCO-000-PL-SP-0003 | BK | GNRAL | PEDCO | 000 | PL | SP | 0003 | F0Z-707153 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | IFA | 2022-03-09 | 2022-03-14 | 2022-04-01 | 5 | 18 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-28 |  |  | D02 | IFA | T-0639 | 44615 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03403 | 44628 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448473 | 44634 | 1400/12/23 | 44652 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 44551 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 44551 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0474 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 44580 | 1400/10/29 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D00 | [5 empty] | 1400-2294-395120 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D00 | [9 empty] | D02 | IFA | T-0639 | 44615 | 1400/12/04 |  |  |  | BK-SUR-ENG-PPL-00-03403 | 44628 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D01 | [5 empty] | 1400-2294-448473 | 44634 | 1400/12/23 | 44652 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D01
1 | 2 | 0 | 6 | 0 | 2 | 3 | 1.2.6.2.3 | BK-GNRAL-PEDCO-000-PL-SP-0004 | Specification For Barred Tee |  | BK-GNRAL-PEDCO-000-PL-SP-0004 | BK-GNRAL-PEDCO-000-PL-SP-0004 | BK | GNRAL | PEDCO | 000 | PL | SP | 0004 | F0Z-707154 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-01-18 | 2022-01-08 | 2022-01-11 | -10 | 3 | -7 | IFA | 2022-02-05 | 2022-02-16 | 2022-02-21 | 11 | 5 | 16 | AFD | 2022-04-09 | 2022-04-05 | 2022-04-16 | -4 | 11 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-28 | 2022-03-26 |  | D03 | AFD | T-0743 | 44646 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-03741 | 44657 | 1401/01/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-9899 | 44656 | 1401/01/16 | 44667 | 1401/01/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 44551 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 44551 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0426 | 44565 | 1400/10/14 |  |  |  | BK-SUR-ENG-PPL-00-02637 | 44572 | 1400/10/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0004_D00 | [5 empty] | 1400-2294-354640 | 44569 | 1400/10/18 | 44572 | 1400/10/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0004_D00 | [9 empty] | D02 | IFA | T-0490 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-PPL-00-02779 | 44583 | 1400/10/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D01 | [5 empty] | 1400-2294-412890 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D01 | [9 empty] | D03 | AFD | T-0743 | 44646 | 1401/01/06 |  |  |  | BK-SUR-ENG-PPL-01-03741 | 44657 | 1401/01/17 | AP | [6 empty] | 1401-2294-9899 | 44656 | 1401/01/16 | 44667 | 1401/01/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 4 | 1.2.6.2.4 | BK-GNRAL-PEDCO-000-PL-SP-0005 | Specification For Fittings, Flanges, Gaskets and Bolts |  | BK-GNRAL-PEDCO-000-PL-SP-0005 | BK-GNRAL-PEDCO-000-PL-SP-0005 | BK | GNRAL | PEDCO | 000 | PL | SP | 0005 | F0Z-707155 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-09-27 | 2021-09-23 | 2021-09-26 | -4 | 3 | -1 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 44537 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005-D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 44418 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0091 | 44452 | 1400/06/22 |  |  |  | BK-SUR-ENG-PPL-00-01585 | 44464 | 1400/07/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005_D00 | [5 empty] | 1400-2294-210024 | 44462 | 1400/07/01 | 44465 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005_D00 | [9 empty] | D02 | IFA | T-0174 | 44488 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-269298 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005-D01 | [9 empty] | D03 | AFD | T-0312 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | CM-C2 | [6 empty] | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005-D02
1 | 2 | 0 | 6 | 0 | 2 | 5 | 1.2.6.2.5 | BK-GNRAL-PEDCO-000-PL-SP-0006 | Specification For Pipeline Valves |  | BK-GNRAL-PEDCO-000-PL-SP-0006 | BK-GNRAL-PEDCO-000-PL-SP-0006 | BK | GNRAL | PEDCO | 000 | PL | SP | 0006 | F0Z-707156 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-28 |  |  | D01 | IFA | T-0474 | 44579 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02753 | 44580 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-395120 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 44551 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 44551 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0474 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 44580 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0006_D00 | [5 empty] | 1400-2294-395120 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0006_D00
1 | 2 | 0 | 6 | 0 | 2 | 6 | 1.2.6.2.6 | BK-GNRAL-PEDCO-000-PL-SP-0007 | Specification For Pipeline Coating |  | BK-GNRAL-PEDCO-000-PL-SP-0007 | BK-GNRAL-PEDCO-000-PL-SP-0007 | BK | GNRAL | PEDCO | 000 | PL | SP | 0007 | F0Z-707157 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-09-27 | 2021-09-23 | 2021-09-26 | -4 | 3 | -1 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 44537 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 44418 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0091 | 44452 | 1400/06/22 |  |  |  | BK-SUR-ENG-PPL-00-01602 | 44465 | 1400/07/04 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0007_D00 | [5 empty] | 1400-2294-210024 | 44462 | 1400/07/01 | 44465 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0007_D00 | [9 empty] | D02 | IFA | T-0174 | 44488 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 44500 | 1400/08/09 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0007-D01 | [5 empty] | 1400-2294-269298 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0007-D01 | [9 empty] | D03 | AFD | T-0312 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | AP | [6 empty] | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 7 | 1.2.6.2.7 | BK-GNRAL-PEDCO-000-PL-SP-0008 | Specification For Pipeline Flushing, Cleaning And Hydrostatic Testing |  | BK-GNRAL-PEDCO-000-PL-SP-0008 | BK-GNRAL-PEDCO-000-PL-SP-0008 | BK | GNRAL | PEDCO | 000 | PL | SP | 0008 | F0Z-707158 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-10-04 | 2021-09-25 | 2021-09-29 | -9 | 4 | -5 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 44537 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008-D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 44418 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0108 | 44459 | 1400/06/29 |  |  |  | BK-SUR-ENG-PPL-00-01581 | 44461 | 1400/06/31 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008_D00 | [5 empty] | 1400-2294-210823 | 44464 | 1400/07/03 | 44468 | 1400/07/07 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008_D00 | [9 empty] | D02 | IFA | T-0174 | 44488 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 44500 | 1400/08/09 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008-D01 | [5 empty] | 1400-2294-269298 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008-D01 | [9 empty] | D03 | AFD | T-0312 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008-D02 | [5 empty] | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 8 | 1.2.6.2.8 | BK-GNRAL-PEDCO-000-PL-SP-0009 | Specification For Welding of Transportation Pipeline |  | BK-GNRAL-PEDCO-000-PL-SP-0009 | BK-GNRAL-PEDCO-000-PL-SP-0009 | BK | GNRAL | PEDCO | 000 | PL | SP | 0009 | F0Z-707159 | AFD | IFC | 2021-12-26 | 2021-12-30 | 2022-01-02 | 4 | 3 | 7 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | IFA | 2022-03-12 | 2022-03-03 | 2022-03-08 | -9 | 5 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-12 |  |  | D02 | IFA | T-0644 | 44618 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03397 | 44628 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-432767 | 44623 | 1400/12/12 | 44628 | 1400/12/17 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0332 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PPL-00-02484 | 44559 | 1400/10/08 | CM-C2 | [6 empty] | 1400-2294-342111 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0474 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 44580 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0009_D00 | [5 empty] | 1400-2294-395120 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0009_D00 | [9 empty] | D02 | IFA | T-0644 | 44618 | 1400/12/07 |  |  |  | BK-SUR-ENG-PPL-00-03397 | 44628 | 1400/12/17 | AP | [6 empty] | 1400-2294-432767 | 44623 | 1400/12/12 | 44628 | 1400/12/17 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0009_D01
1 | 2 | 0 | 6 | 0 | 2 | 9 | 1.2.6.2.9 | BK-GNRAL-PEDCO-000-PL-SP-0010 | Specification For Pipeline Stress Analysis |  | BK-GNRAL-PEDCO-000-PL-SP-0010 | BK-GNRAL-PEDCO-000-PL-SP-0010 | BK | GNRAL | PEDCO | 000 | PL | SP | 0010 | F0Z-707160 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-11-03 | 2021-11-04 | 2021-11-08 | 1 | 4 | 5 | IFA | 2021-11-29 | 2021-11-23 | 2021-11-27 | -6 | 4 | -2 | IFA | 2021-12-21 | 2022-12-14 | 2022-04-19 | 358 | -239 | 119 | AFD | 2022-08-10 | 2022-08-14 | 2022-08-16 | 4 | 2 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-07-27 |  | D04 | AFD | T-1207 | 44769 | 1401/05/05 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05327 | 44774 | 1401/05/10 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177026 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 44418 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0179 | 44489 | 1400/07/28 |  |  |  | BK-SUR-ENG-PPL-00-01842 | 44495 | 1400/08/04 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D00 | [5 empty] | 1400-2294-261476 | 44504 | 1400/08/13 | 44508 | 1400/08/17 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010-D00 | [9 empty] | D02 | IFA | T-0246 | 44515 | 1400/08/24 |  |  |  | BK-SUR-ENG-PPL-00-02079 | 44522 | 1400/09/01 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02 | [5 empty] | 1400-2294-288567 | 44523 | 1400/09/02 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02 | [9 empty] | D03 | IFA | T-0313 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PPL-00-02271 | 44542 | 1400/09/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02 | [5 empty] | 1400-2294-317186 | 44909 | 1401/09/23 | 44670 | 1401/01/30 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02 | [9 empty] | D04 | AFD | T-1207 | 44769 | 1401/05/05 |  |  |  | BK-SUR-ENG-PPL-01-05327 | 44774 | 1401/05/10 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D03 | [5 empty] | 1401-2294-177026 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | AP
1 | 2 | 0 | 6 | 0 | 2 | 10 | 1.2.6.2.10 | BK-GNRAL-PEDCO-000-PL-SP-0011 | Specification For Pipeline Insulation Joint |  | BK-GNRAL-PEDCO-000-PL-SP-0011 | BK-GNRAL-PEDCO-000-PL-SP-0011 | BK | GNRAL | PEDCO | 000 | PL | SP | 0011 | F0Z-707161 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-09-27 | 2021-09-23 | 2021-09-26 | -4 | 3 | -1 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 44537 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 44418 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0091 | 44452 | 1400/06/22 |  |  |  | BK-SUR-ENG-PPL-00-01585 | 44464 | 1400/07/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0011_D00 | [5 empty] | 1400-2294-210024 | 44462 | 1400/07/01 | 44465 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0011_D00 | [9 empty] | D02 | IFA | T-0174 | 44488 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-269298 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0011-D01 | [9 empty] | D03 | AFD | T-0312 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 44548 | 1400/09/18 | AP | [6 empty] | 1400-2294-318810 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 11 | 1.2.6.2.11 | BK-GNRAL-PEDCO-000-PL-SP-0012 | Specification For Pipeline Construction |  | BK-GNRAL-PEDCO-000-PL-SP-0012 | BK-GNRAL-PEDCO-000-PL-SP-0012 | BK | GNRAL | PEDCO | 000 | PL | SP | 0012 | F0Z-707162 | AFD | IFC | 2022-02-08 | 2022-02-16 | 2022-02-16 | 8 | 0 | 8 | IFA | 2022-03-20 | 2022-03-10 | 2022-03-12 | -10 | 2 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-25 |  |  | D01 | IFA | T-0683 | 44626 | 1400/12/15 |  |  |  | BK-SUR-ENG-PPL-00-03488 | 44632 | 1400/12/21 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0012_D00 | [5 empty] | 1400-2294-443197 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0012_D00 | 1400-2294-412883 | 44608 | 1400/11/27 | 44608 | 1400/11/27 | CM |  |  |  | D00 | IFC | T-0507 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-PPL-00-02938 | 44597 | 1400/11/16 | CM-C2 | [6 empty] | 1400-2294-395163 | 2022-02-15 | 1400/11/15 | 44600 | 1400/11/19 | CM |  | 1400-2294-412883 | 44608 | 1400/11/27 | 44608 | 1400/11/27 | CM |  |  |  | D01 | IFA | T-0683 | 44626 | 1400/12/15 |  |  |  | BK-SUR-ENG-PPL-00-03488 | 44632 | 1400/12/21 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0012_D00 | [5 empty] | 1400-2294-443197 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0012_D00
1 | 2 | 0 | 6 | 0 | 2 | 12 | 1.2.6.2.12 | BK-GNRAL-PEDCO-000-PL-SP-0013 | Specification For Pipeline Cleaning and Flushing |  | BK-GNRAL-PEDCO-000-PL-SP-0013 | [8 empty] | F0Z-707163 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D00 | IFC | T-0007 | 44401 | 1400/05/02 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01274 | 44415 | 1400/05/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-157439 | 44416 | 1400/05/17 | 44418 | 1400/05/19 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400-2294-157439 | 2021-08-08 | 1400/05/17 | 44418 | 1400/05/19 | CM
1 | 2 | 0 | 6 | 0 | 2 | 13 | 1.2.6.2.13 | BK-GNRAL-PEDCO-000-PL-SP-0014 | Specification For Anchor Flanges |  | BK-GNRAL-PEDCO-000-PL-SP-0014 | BK-GNRAL-PEDCO-000-PL-SP-0014 | BK | GNRAL | PEDCO | 000 | PL | SP | 0014 | F0Z-707164 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-28 |  |  | D01 | IFA | T-0474 | 44579 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02753 | 44580 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0014-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-395120 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0014-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 44551 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 44551 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0474 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 44580 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0014-D00 | [5 empty] | 1400-2294-395120 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0014-D00
1 | 2 | 0 | 6 | 0 | 2 | 14 | 1.2.6.2.14 | BK-GNRAL-PEDCO-000-PL-SP-0015 | Specification For Pigs |  | BK-GNRAL-PEDCO-000-PL-SP-0015 | BK-GNRAL-PEDCO-000-PL-SP-0015 | BK | GNRAL | PEDCO | 000 | PL | SP | 0015 | F0Z-707165 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-28 |  |  | D01 | IFA | T-0474 | 44579 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02753 | 44580 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0015_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-395120 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0015_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 44551 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 44551 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0474 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 44580 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0015_D00 | [5 empty] | 1400-2294-395120 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0015_D00
1 | 2 | 0 | 6 | 0 | 2 | 15 | 1.2.6.2.15 | BK-GNRAL-PEDCO-000-PL-SP-0016 | Specification For LBV |  | BK-GNRAL-PEDCO-000-PL-SP-0016 | [8 empty] | - | [50 empty] | Moved to IN | 2021-10-06 |  |  | D00 | IFC | T-0139 | 44475 | 1400/07/14 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01800 | 44489 | 1400/07/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0016_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-245969 | 44493 | 1400/08/02 | 44522 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0139 | 2021-10-06 | 1400/07/14 |  |  |  | BK-SUR-ENG-PPL-00-01800 | 44489 | 1400/07/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0016_D00 | [5 empty] | 1400-2294-245969 | 2021-10-24 | 1400/08/02 | 44522 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0016_D00
1 | 2 | 0 | 6 | 0 | 3 | 0 | 1.2.6.3 |  | Drawing/Diagram
1 | 2 | 0 | 6 | 0 | 3 | 1 | 1.2.6.3.1 | BK-GNRAL-PEDCO-000-PL-DW-0001 | Pipeline Standard Drawing For Line Marker | Pipeline Standard Drawing For Line Marker Post and Cathodic Protection System | BK-GNRAL-PEDCO-000-PL-DW-0001 | BK-GNRAL-PEDCO-000-PL-DW-0001 | BK | GNRAL | PEDCO | 000 | PL | DW | 0001 | F4L-707166 | AFC | IFC | 2021-10-02 | 2021-10-02 | 2021-10-10 | 0 | 8 | 8 | IFA | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | IFA | 2022-08-17 | 2022-09-06 | 2022-09-12 | 20 | 6 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-18 |  |  | D02 | IFA | T-1241 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05433 | 44787 | 1401/05/23 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-212663 | 44810 | 1401/06/15 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0101 | 2021-09-18 | 1400/06/27 |  |  |  | BK-SUR-ENG-PPL-00-01618 | 44467 | 1400/07/06 | CM-C3 | [6 empty] | 1400-2294-222587 | 2021-10-02 | 1400/07/12 | 44479 | 1400/07/18 | CM | [10 empty] | D01 | IFA | T-0303 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PPL-00-02291 | 44544 | 1400/09/23 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001-D00 | [5 empty] | 1400-2294-318687 | 44544 | 1400/09/23 | 44548 | 1400/09/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001-D00 | [9 empty] | D02 | IFA | T-1241 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-PPL-01-05433 | 44787 | 1401/05/23 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001_D01 | [5 empty] | 1401-2294-212663 | 44810 | 1401/06/15 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001_D01
1 | 2 | 0 | 6 | 0 | 3 | 2 | 1.2.6.3.2 | BK-GNRAL-PEDCO-000-PL-DW-0002 | Standard Drawing For Above Ground Pipeline Construction R.O.W |  | BK-GNRAL-PEDCO-000-PL-DW-0002 | BK-GNRAL-PEDCO-000-PL-DW-0002 | BK | GNRAL | PEDCO | 000 | PL | DW | 0002 | F4L-707167 | AFC | IFC | 2021-12-11 | 2021-12-08 | 2021-12-12 | -3 | 4 | 1 | IFA | 2022-02-16 | 2022-02-26 | 2022-02-28 | 10 | 2 | 12 | AFC | 2022-04-11 | 2022-07-09 | 2022-07-12 | 89 | 3 | 92 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 | 2022-03-28 |  | D02 | AFC | T-0760 | 44648 | 1401/01/08 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-03878 | 44663 | 1401/01/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-134703 | 44751 | 1401/04/18 | 44754 | 1401/04/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0272 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PPL-00-02258 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-3394-310752 | 2021-12-08 | 1400/09/17 | 44542 | 1400/09/21 | CM | [10 empty] | D01 | IFA | T-0546 | 44594 | 1400/11/13 |  |  |  | BK-SUR-ENG-PPL-00-03086 | 44608 | 1400/11/27 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0002_D00 | [5 empty] | 1400-2294-426611 | 44618 | 1400/12/07 | 44620 | 1400/12/09 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0002_D00 | [9 empty] | D02 | AFC | T-0760 | 44648 | 1401/01/08 |  |  |  | BK-SUR-ENG-PPL-01-03878 | 44663 | 1401/01/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0002_D01 | [5 empty] | 1401-2294-134703 | 44751 | 1401/04/18 | 44754 | 1401/04/21 | AP
1 | 2 | 0 | 6 | 0 | 3 | 3 | 1.2.6.3.3 | BK-GNRAL-PEDCO-000-PL-DW-0003 | Standard Drawing For Under Ground Pipeline Construction R.O.W |  | BK-GNRAL-PEDCO-000-PL-DW-0003 | BK-GNRAL-PEDCO-000-PL-DW-0003 | BK | GNRAL | PEDCO | 000 | PL | DW | 0003 | F4L-707168 | AFC | IFC | 2021-12-18 | 2021-12-12 | 2021-12-15 | -6 | 3 | -3 | AFC | 2022-02-16 | 2022-02-26 | 2022-02-28 | 10 | 2 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-04 | 2022-02-02 |  | D01 | AFC | T-0537 | 44594 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02951 | 44598 | 1400/11/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0003-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-426685 | 44618 | 1400/12/07 | 44620 | 1400/12/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0289 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02228 | 44537 | 1400/09/16 | CM-C3 | [6 empty] | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 44545 | 1400/09/24 | AP | [10 empty] | D01 | AFC | T-0537 | 44594 | 1400/11/13 |  |  |  | BK-SUR-ENG-PPL-00-02951 | 44598 | 1400/11/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0003-D00 | [5 empty] | 1400-2294-426685 | 44618 | 1400/12/07 | 44620 | 1400/12/09 | AP
1 | 2 | 0 | 6 | 0 | 3 | 4 | 1.2.6.3.4 | BK-GNRAL-PEDCO-000-PL-DW-0004 | Pipeline Standard Drawing For Anchor Support |  | BK-GNRAL-PEDCO-000-PL-DW-0004 | BK-GNRAL-PEDCO-000-PL-DW-0004 | BK | GNRAL | PEDCO | 000 | PL | DW | 0004 | F2L-707169 | AFC | IFC | 2022-01-05 | 2021-12-30 | 2022-01-02 | -6 | 3 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-22 |  |  | D00 | IFC | T-0375 | 44552 | 1400/10/01 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02228 | 44563 | 1400/10/12 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-342150 | 44560 | 1400/10/09 | 44563 | 1400/10/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0375 | 2021-12-22 | 1400/10/01 |  |  |  | BK-SUR-ENG-PPL-00-02228 | 44563 | 1400/10/12 | CM-C3 | [6 empty] | 1400-2294-342150 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM
1 | 2 | 0 | 6 | 0 | 3 | 5 | 1.2.6.3.5 | BK-GNRAL-PEDCO-000-PL-DW-0005 | Standard Drawing For A/G Pipeline Road Crossing |  | BK-GNRAL-PEDCO-000-PL-DW-0005 | BK-GNRAL-PEDCO-000-PL-DW-0005 | BK | GNRAL | PEDCO | 000 | PL | DW | 0005 | F5L-707170 | AFC | IFC | 2021-12-19 | 2021-12-12 | 2021-12-14 | -7 | 2 | -5 | IFA | 2022-04-13 | 2020-04-28 | 2022-04-02 | -715 | 704 | -11 | AFC | 2022-05-30 | 0 | 0 | -44711 | 0 | -44711 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-05 | 2022-05-16 |  | D02 | AFC | T-0959 | 44697 | 1401/02/26 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-04336 | 44702 | 1401/02/31 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0005_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0293 | 2021-12-05 | 1400/09/14 |  |  |  | BK-SUR-ENG-PPL-00-02268 | 44542 | 1400/09/21 | CM-C3 | [6 empty] | 1400-2294-315114 | 2021-12-12 | 1400/09/21 | 44544 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0764 | 44650 | 1401/01/10 |  |  |  | BK-SUR-ENG-PPL-01-03906 | 44667 | 1400/01/27 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0005_D00 | [5 empty] | 1401-2294-43099 | 43949 | 1401/02/08 | 44653 | 1401/02/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0005_D00 | [9 empty] | D02 | AFC | T-0959 | 44697 | 1401/02/26 |  |  |  | BK-SUR-ENG-PPL-01-04336 | 44702 | 1401/02/31 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0005_D02
1 | 2 | 0 | 6 | 0 | 3 | 6 | 1.2.6.3.6 | BK-GNRAL-PEDCO-000-PL-DW-0006 | Standard Drawing For Existing Pipeline Crossing |  | BK-GNRAL-PEDCO-000-PL-DW-0006 | BK-GNRAL-PEDCO-000-PL-DW-0006 | BK | GNRAL | PEDCO | 000 | PL | DW | 0006 | F2L-707171 | AFC | IFC | 2022-01-01 | 2021-12-22 | 2021-12-26 | -10 | 4 | -6 | IFA | 2022-04-12 | 2022-04-13 | 2022-04-16 | 1 | 3 | 4 | IFA | 2022-06-07 | 2022-06-11 | 2022-06-14 | 4 | 3 | 7 | AFC | 2022-07-20 | 2022-08-10 | 2022-08-14 | 21 | 4 | 25 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-18 | 2022-07-06 |  | D03 | AFC | T-1145 | 44748 | 1401/04/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05439 | 44787 | 1401/05/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-172745 | 44783 | 1401/05/19 | 44787 | 1401/05/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0356 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-PPL-00-02431 | 44556 | 1400/10/05 | CM-C3 | [6 empty] | 1400-2294-331426 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0762 | 44649 | 1401/01/09 |  |  |  | BK-SUR-ENG-PPL-01-03905 | 44664 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D00 | [5 empty] | 1401-2294-22793 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D00 | [9 empty] | D02 | IFA | T-0999 | 44705 | 1401/03/03 | T-0999 | 44709 | 1401/03/07 | BK-SUR-ENG-PPL-01-04552 | 44718 | 1401/03/16 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D01 | [5 empty] | 1401-2294-95252 | 44723 | 1401/03/21 | 44726 | 1401/03/24 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D01 | [9 empty] | D03 | AFC | T-1145 | 44748 | 1401/04/15 |  |  |  | BK-SUR-ENG-PPL-01-05439 | 44787 | 1401/05/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D03 | [5 empty] | 1401-2294-172745 | 44783 | 1401/05/19 | 44787 | 1401/05/23 | AP
1 | 2 | 0 | 6 | 0 | 3 | 7 | 1.2.6.3.7 | BK-GNRAL-PEDCO-000-PL-DW-0007 | Pipeline Standard Drawing For Irish Crossing |  | BK-GNRAL-PEDCO-000-PL-DW-0007 | BK-GNRAL-PEDCO-000-PL-DW-0007 | BK | GNRAL | PEDCO | 000 | PL | DW | 0007 | F5L-707172 | AFC | IFC | 2021-12-18 | 2021-12-12 | 2021-12-15 | -6 | 3 | -3 | AFC | 2022-06-01 | 2022-06-02 | 2022-06-08 | 1 | 6 | 7 | AFC | 2022-08-03 | 2022-07-28 | 2022-07-31 | -6 | 3 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-04 | 2022-07-20 |  | D02 | AFC | T-1176 | 44762 | 1401/04/29 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05262 | 44772 | 1401/05/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156922 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0289 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02228 | 44537 | 1400/09/16 | RJ-C4 | [6 empty] | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 44545 | 1400/09/24 | AP | [10 empty] | D01 | AFC | T-0972 | 44699 | 1401/02/28 | T-0972 | 44702 | 1401/02/31 | BK-SUR-ENG-PPL-01-04327 | 44702 | 1401/02/31 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0007_D00 | [5 empty] | 1401-2294-87517 | 44714 | 1401/03/12 | 44720 | 1401/03/18 | AP | [10 empty] | D02 | AFC | T-1176 | 44762 | 1401/04/29 |  |  |  | BK-SUR-ENG-PPL-01-05262 | 44772 | 1401/05/08 | AP | [6 empty] | 1401-2294-156922 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP
1 | 2 | 0 | 6 | 0 | 3 | 8 | 1.2.6.3.8 | BK-GNRAL-PEDCO-000-PL-DW-0008 | Pipeline Standard Drawing For Water - Way Crossing |  | BK-GNRAL-PEDCO-000-PL-DW-0008 | BK-GNRAL-PEDCO-000-PL-DW-0008 | BK | GNRAL | PEDCO | 000 | PL | DW | 0008 | F5L-707173 | AFC | IFC | 2021-12-06 | 2021-12-06 | 2022-04-19 | 0 | 134 | 134 | AFC | 2022-05-29 | 2022-06-06 | 2022-06-08 | 8 | 2 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-22 | 2022-05-15 |  | D01 | AFC | T-0951 | 44696 | 1401/02/25 | T-0951 | 44696 | 1401/02/25 | BK-SUR-ENG-PPL-01-04434 | 44705 | 1401/03/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0008_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-88539 | 44718 | 1401/03/16 | 44720 | 1401/03/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0264 | 2021-11-22 | 1400/09/01 |  |  |  | BK-SUR-ENG-PPL-00-02094 | 44524 | 1400/09/03 | CM-C2 |  | BK-SUR-ENG-PPL-00-02261 | 44542 | 1400/09/21 | CM-C3 |  | 1400-2294-305732 | 2021-12-06 | 1400/09/15 | 44670 | 1401/01/30 | AP | [10 empty] | D01 | AFC | T-0951 | 44696 | 1401/02/25 | T-0951 | 44696 | 1401/02/25 | BK-SUR-ENG-PPL-01-04434 | 44705 | 1401/03/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0008_D00 | [5 empty] | 1401-2294-88539 | 44718 | 1401/03/16 | 44720 | 1401/03/18 | AP
1 | 2 | 0 | 6 | 0 | 3 | 9 | 1.2.6.3.9 | BK-GNRAL-PEDCO-000-PL-DW-0009 | Pipeline Standard Drawing For Pig Signaller Concrete Pit |  | BK-GNRAL-PEDCO-000-PL-DW-0009 | BK-GNRAL-PEDCO-000-PL-DW-0009 | BK | GNRAL | PEDCO | 000 | PL | DW | 0009 | F2L-707174 | AFC | IFC | 2021-12-11 | 2021-12-08 | 2021-12-12 | -3 | 4 | 1 | IFA | 2022-04-17 | 2022-04-09 | 2022-04-12 | -8 | 3 | -5 | AFC | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 | 2022-05-21 |  | D02 | AFC | T-0977 | 44702 | 1401/02/31 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-04438 | 44709 | 1401/03/07 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0272 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PPL-00-02258 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-310752 | 2021-12-08 | 1400/09/17 | 44542 | 1400/09/21 | CM | [10 empty] | D01 | IFA | T-0770 | 44654 | 1401/01/14 |  |  |  | BK-SUR-ENG-PPL-01-03937 | 44667 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0009_D01 | [5 empty] | 1401-2294-14511 | 44660 | 1401/01/20 | 44663 | 1401/01/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0009_D01 | [9 empty] | D02 | AFC | T-0977 | 44702 | 1401/02/31 |  |  |  | BK-SUR-ENG-PPL-01-04438 | 44709 | 1401/03/07 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0009_D01
1 | 2 | 0 | 6 | 0 | 3 | 10 | 1.2.6.3.10 | BK-GNRAL-PEDCO-000-PL-DW-0010 | Pipeline Standard Drawing For H-Pipe Support |  | BK-GNRAL-PEDCO-000-PL-DW-0010 | BK-GNRAL-PEDCO-000-PL-DW-0010 | BK | GNRAL | PEDCO | 000 | PL | DW | 0010 | F5L-707175 | AFC | IFC | 2021-12-11 | 2021-12-08 | 2021-12-12 | -3 | 4 | 1 | AFC | 2022-02-14 | 2022-02-05 | 2022-02-08 | -9 | 3 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 | 2022-01-31 |  | D01 | AFC | T-0524 | 44592 | 1400/11/11 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02891 | 44592 | 1400/11/11 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0010_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-397300 | 44597 | 1400/11/16 | 44600 | 1400/11/19 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0272 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PPL-00-02258 | 44541 | 1400/09/20 | CM-C2 | [6 empty] | 1400-3394-310752 | 2021-12-08 | 1400/09/17 | 44542 | 1400/09/21 | CM | [10 empty] | D01 | AFC | T-0524 | 44592 | 1400/11/11 |  |  |  | BK-SUR-ENG-PPL-00-02891 | 44592 | 1400/11/11 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0010_D00 | [5 empty] | 1400-2294-397300 | 44597 | 1400/11/16 | 44600 | 1400/11/19 | AP
1 | 2 | 0 | 6 | 0 | 3 | 11 | 1.2.6.3.11 | BK-GNRAL-PEDCO-000-PL-DW-0011 | Pipeline Standard Drawing For Vent Valve Pre-cast Concrete Box |  | BK-GNRAL-PEDCO-000-PL-DW-0011 | BK-GNRAL-PEDCO-000-PL-DW-0011 | BK | GNRAL | PEDCO | 000 | PL | DW | 0011 | F2L-707176 | AFC | IFC | 2021-12-11 | 2021-12-08 | 2021-12-12 | -3 | 4 | 1 | IFA | 2022-05-01 | 2022-04-28 | 2022-05-02 | -3 | 4 | 1 | AFC | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 | 2022-05-25 |  | D02 | AFC | T-1005 | 44706 | 1401/03/04 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-04553 | 44718 | 1401/03/16 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0272 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PPL-00-02258 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-3394-310752 | 2021-12-08 | 1400/09/17 | 44542 | 1400/09/21 | CM | [10 empty] | D01 | IFA | T-0830 | 44668 | 1401/01/28 |  |  |  | BK-SUR-ENG-PPL-01-04070 | 44677 | 1401/02/06 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0011_D00 | [5 empty] | 1401-2294-73173 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0011_D00 | [9 empty] | D02 | AFC | T-1005 | 44706 | 1401/03/04 |  |  |  | BK-SUR-ENG-PPL-01-04553 | 44718 | 1401/03/16 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0011_D01
1 | 2 | 0 | 6 | 0 | 3 | 12 | 1.2.6.3.12 | BK-GNRAL-PEDCO-000-PL-DW-0013 | Pipeline Standard Drawing For Cover Slabs And Set-On-Weight |  | BK-GNRAL-PEDCO-000-PL-DW-0013 | BK-GNRAL-PEDCO-000-PL-DW-0013 | BK | GNRAL | PEDCO | 000 | PL | DW | 0013 | F5L-707177 | AFC | IFC | 2022-01-04 | 2021-12-29 | 2022-01-01 | -6 | 3 | -3 | IFA | 2022-08-06 | 2022-08-13 | 2022-08-22 | 7 | 9 | 16 | IFA | 2022-10-03 | 2022-10-05 | 2022-10-08 | 2 | 3 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-21 |  |  | D02 | IFA | T-1420 | 44823 | 1401/06/28 | T-1420 | 44823 | 1401/06/28 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0013_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249361 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0013_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0373 | 2021-12-21 | 1400/09/30 |  |  |  | BK-SUR-ENG-PPL-00-02492 | 44562 | 1400/10/11 | CM-C3 | [6 empty] | 1400-2294-341839 | 2021-12-29 | 1400/10/08 | 44562 | 1400/10/11 | CM | [10 empty] | D01 | IFA | T-1184 | 44765 | 1401/05/01 |  |  |  | BK-SUR-ENG-PPL-01-05317 | 44774 | 1401/05/11 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0013_D00 | [5 empty] | 1401-2294-175032 | 44786 | 1401/05/22 | 44795 | 1401/05/29 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0013_D00 | [9 empty] | D02 | IFA | T-1420 | 44823 | 1401/06/28 | T-1420 | 44823 | 1401/06/28 |  |  |  |  | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0013_D01 | [5 empty] | 1401-2294-249361 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0013_D01
1 | 2 | 0 | 6 | 0 | 3 | 13 | 1.2.6.3.13 | BK-GNRAL-PEDCO-000-PL-DW-0014 | Pipeline Standard Drawing For River Crossing |  | BK-GNRAL-PEDCO-000-PL-DW-0014 | BK-GNRAL-PEDCO-000-PL-DW-0014 | BK | GNRAL | PEDCO | 000 | PL | DW | 0014 | F5L-707178 | AFC | IFC | 2021-12-29 | 2021-12-22 | 2021-12-26 | -7 | 4 | -3 | IFA | 2022-05-14 | 2022-05-12 | 2022-05-18 | -2 | 6 | 4 | AFC | 2022-07-27 | 0 | 0 | -44769 | 0 | -44769 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-15 | 2022-07-13 |  | D02 | AFC | T-1160 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05213 | 44762 | 1401/04/29 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0014_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0347 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-PPL-00-02435 | 44556 | 1400/10/26 | CM-C3 | [6 empty] | 1400-2294-331441 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0875 | 44681 | 1401/02/10 | T-0875 | 44681 | 1401/02/10 | BK-SUR-ENG-PPL-01-04302 | 44699 | 1401/02/28 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0014_D00 | [5 empty] | 1401-2294-59524 | 44693 | 1401/02/22 | 44699 | 1401/02/28 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0014_D00 | [9 empty] | D02 | AFC | T-1160 | 44755 | 1401/04/22 |  |  |  | BK-SUR-ENG-PPL-01-05213 | 44762 | 1401/04/29 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0014_D01
1 | 2 | 0 | 6 | 0 | 4 | 0 | 1.2.6.4 |  | Procedure/Plan
1 | 2 | 0 | 7 | 0 | 0 | 0 | 1.2.7 |  | Control & Instrumentation
1 | 2 | 0 | 7 | 0 | 1 | 0 | 1.2.7.1 |  | Specification
1 | 2 | 0 | 7 | 0 | 1 | 1 | 1.2.7.1.1 | BK-GNRAL-PEDCO-000-IN-SP-0001 | Specification For Instrumentation |  | BK-GNRAL-PEDCO-000-IN-SP-0001 | BK-GNRAL-PEDCO-000-IN-SP-0001 | BK | GNRAL | PEDCO | 000 | IN | SP | 0001 | F9J-707179 | AFD | IFC | 2021-08-09 | 2021-08-29 | 2021-09-12 | 20 | 14 | 34 | IFA | 2021-10-02 | 2021-10-07 | 2021-10-13 | 5 | 6 | 11 | IFA | 2021-11-28 | 2021-11-21 | 2021-12-01 | -7 | 10 | 3 | AFD | 2022-02-16 | 0 | 0 | -44608 | 0 | -44608 | AFD | 2022-08-13 | 0 | 0 | -44786 | 0 | -44786 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-26 | 2022-07-30 |  | D04 | AFD | T-1221 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05438 | 44787 | 1401/05/23 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0011 | 2021-07-26 | 1400/05/04 |  |  |  | BK-SUR-ENG-INS-00-01354 | 44423 | 1400/05/24 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 44451 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0095 | 44457 | 1400/06/27 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D00 | [5 empty] | 1400-2290-225563 | 44476 | 1400/07/15 | 44482 | 1400/07/21 | CM | NISOC-CRS- BK-GNRAL-PEDCO-000-IN-SP-0001_D00 | [9 empty] | D02 | IFA | T-0234 | 44514 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02169 | 44531 | 1400/09/10 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D01 | [5 empty] | 1400-2294-283469 | 44521 | 1400/08/30 | 44531 | 1400/09/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D01 | [9 empty] | D03 | AFD | T-0534 | 44594 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-02952 | 44598 | 1400/11/17 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D02 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D02 | [9 empty] | D04 | AFD | T-1221 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05438 | 44787 | 1401/05/23 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D03
1 | 2 | 0 | 7 | 0 | 1 | 2 | 1.2.7.1.2 | BK-GNRAL-PEDCO-000-IN-SP-0002 | Specification For Control System |  | BK-GNRAL-PEDCO-000-IN-SP-0002 | BK-GNRAL-PEDCO-000-IN-SP-0002 | BK | GNRAL | PEDCO | 000 | IN | SP | 0002 | F9J-707180 | AFD | IFC | 2021-08-11 | 2021-09-22 | 2021-09-12 | 42 | -10 | 32 | IFA | 2021-10-13 | 2021-10-17 | 2021-10-20 | 4 | 3 | 7 | IFA | 2021-12-12 | 2021-12-14 | 2021-12-15 | 2 | 1 | 3 | IFA | 2022-02-06 | 2022-03-08 | 2022-03-11 | 30 | 3 | 33 | AFD | 2022-08-23 | 0 | 0 | -44796 | 0 | -44796 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2022-08-09 |  | D04 | AFD | T-1261 | 44782 | 1401/05/18 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05391 | 44782 | 1401/05/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISCO-CRS-BK-GNRAL-NISCO-000-IN-SP-0002_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0016 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-INS-00-01336 | 44430 | 1400/05/31 | CM-C3 | [6 empty] | 1400-2294-208200 | 2021-09-22 | 1400/06/31 | 44451 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0125 | 44468 | 1400/07/07 |  |  |  | BK-SUR-ENG-INS-00-01744 | 44485 | 1400/07/24 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D00 | [5 empty] | 1400-2294-238033 | 44486 | 1400/07/25 | 44489 | 1400/07/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D00 | [9 empty] | D02 | IFA | T-0281 | 44528 | 1400/09/07 |  |  |  | BK-SUR-ENG-INS-00-02277 | 44543 | 1400/09/22 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D01 | [5 empty] | 1400-2294-317175 | 44544 | 1400/09/23 | 44545 | 1400/09/24 | CM | NICOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D01 | [9 empty] | D03 | IFA | T-0495 | 44584 | 1400/11/03 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D02 | [5 empty] | 1400-2294-441071 | 44628 | 1400/12/17 | 44631 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D02 | [9 empty] | D04 | AFD | T-1261 | 44782 | 1401/05/18 |  |  |  | BK-SUR-ENG-INS-01-05391 | 44782 | 1401/05/18 | CM-C2 | [12 empty] | NISCO-CRS-BK-GNRAL-NISCO-000-IN-SP-0002_D03
1 | 2 | 0 | 7 | 0 | 1 | 3 | 1.2.7.1.3 | BK-GNRAL-PEDCO-000-IN-SP-0003 | Specification For ESD System |  | BK-GNRAL-PEDCO-000-IN-SP-0003 | BK-GNRAL-PEDCO-000-IN-SP-0003 | BK | GNRAL | PEDCO | 000 | IN | SP | 0003 | F9J-707181 | AFD | IFC | 2021-08-11 | 2021-08-29 | 2021-09-12 | 18 | 14 | 32 | IFA | 2021-10-04 | 2021-10-07 | 2021-10-13 | 3 | 6 | 9 | IFA | 2022-01-15 | 2022-01-26 | 2022-01-29 | 11 | 3 | 14 | IFA | 2022-05-11 | 2022-05-18 | 2022-05-23 | 7 | 5 | 12 | IFA | 2022-08-20 | 2022-09-28 | 2022-10-02 | 39 | 4 | 43 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 |  |  | D04 | IFA | T-1255 | 44779 | 1401/05/15 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05491 | 44793 | 1401/05/29 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240310 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-GNRAL-NISCO-000-IN-SP-0003_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0016 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-INS-00-01336 | 44430 | 1400/05/31 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 44451 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0104 | 44459 | 1400/06/29 |  |  |  | BK-SUR-ENG-INS-00-01675 | 44473 | 1400/07/12 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D00 | [5 empty] | 1400-2290-225567 | 44476 | 1400/07/15 | 44482 | 1400/07/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D00 | [9 empty] | D02 | IFA | T-0414 | 44562 | 1400/10/11 |  |  |  | BK-SUR-ENG-INS-00-02675 | 44576 | 1400/10/25 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D01 | [5 empty] | 1400-2294-382426 | 44587 | 1400/11/06 | 44590 | 1400/11/09 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003-D01 | [9 empty] | D03 | IFA | T-0868 | 44678 | 1401/02/07 | T-0868 | 44678 | 1401/02/07 |  |  |  |  | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D02 | [5 empty] | 1401-2294-66361 | 44699 | 1401/02/28 | 44704 | 1401/03/03 | CM | NISCO-CRS-BK-GNRAL-NISCO-000-IN-SP-0003_D02 | [9 empty] | D04 | IFA | T-1255 | 44779 | 1401/05/15 |  |  |  | BK-SUR-ENG-INS-01-05491 | 44793 | 1401/05/29 | CM-C2 | [6 empty] | 1401-2294-240310 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-GNRAL-NISCO-000-IN-SP-0003_D03
1 | 2 | 0 | 7 | 0 | 1 | 4 | 1.2.7.1.4 | BK-GNRAL-PEDCO-000-IN-SP-0004 | Specification For Instrument and Control of Package Unit System (PU) |  | BK-GNRAL-PEDCO-000-IN-SP-0004 | BK-GNRAL-PEDCO-000-IN-SP-0004 | BK | GNRAL | PEDCO | 000 | IN | SP | 0004 | F9J-707182 | AFD | IFC | 2021-08-18 | 2021-12-17 | 2022-04-19 | 121 | 123 | 244 | IFA | 2022-06-12 | 2022-08-04 | 2022-08-06 | 53 | 2 | 55 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-04 |  |  | D01 | IFA | T-1017 | 44710 | 1401/03/08 | T-1017 | 44710 | 1401/03/08 | BK-SUR-ENG-INS-01-04728 | 44727 | 1401/03/25 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-167234 | 44777 | 1401/05/13 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0029 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-INS-00-01341 | 44423 | 1400/5/24 | CM-C3 | [6 empty] | 1400-2294-320793 | 2021-12-17 | 1400/09/26 | 44670 | 1401/01/30 | CM | [10 empty] | D01 | IFA | T-1017 | 44710 | 1401/03/08 | T-1017 | 44710 | 1401/03/08 | BK-SUR-ENG-INS-01-04728 | 44727 | 1401/03/25 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0004_D00 | [5 empty] | 1401-2294-167234 | 44777 | 1401/05/13 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0004_D00
1 | 2 | 0 | 7 | 0 | 1 | 5 | 1.2.7.1.5 | BK-GNRAL-PEDCO-000-IN-SP-0005 | Specification For Control Valves |  | BK-GNRAL-PEDCO-000-IN-SP-0005 | BK-GNRAL-PEDCO-000-IN-SP-0005 | BK | GNRAL | PEDCO | 000 | IN | SP | 0005 | F9J-707183 | AFD | IFC | 2021-08-07 | 2021-08-29 | 2021-09-12 | 22 | 14 | 36 | IFA | 2021-10-16 | 2021-10-17 | 2022-03-14 | 1 | 148 | 149 | IFA | 2022-05-11 | 2022-05-17 | 2022-05-23 | 6 | 6 | 12 | AFD | 2022-08-23 | 0 | 0 | -44796 | 0 | -44796 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-08-09 |  | D03 | AFD | T-1257 | 44782 | 1401/05/17 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05378 | 44782 | 1401/05/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0002 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-INS-00-01299 | 44417 | 1400/05/18 | CM | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 44451 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0126 | 44471 | 1400/07/10 |  |  |  | BK-SUR-ENG-INS-00-01768 | 44490 | 1400/07/28 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D00 | [5 empty] | 1400-2294-238042 | 44486 | 1400/07/25 | 44634 | 1400/12/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D00 | [9 empty] | D02 | IFA | T-0871 | 44678 | 1401/02/07 | T-0871 | 44678 | 1401/02/07 |  |  |  |  | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D01 | [5 empty] | 1401-2294-65621 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D01 | [9 empty] | D03 | AFD | T-1257 | 44782 | 1401/05/17 |  |  |  | BK-SUR-ENG-INS-01-05378 | 44782 | 1401/05/18 | CM-C2
1 | 2 | 0 | 7 | 0 | 1 | 6 | 1.2.7.1.6 | BK-GNRAL-PEDCO-000-IN-SP-0006 | Specification For On-off /Shut Down Valves(ESDV/MOV) |  | BK-GNRAL-PEDCO-000-IN-SP-0006 | BK-GNRAL-PEDCO-000-IN-SP-0006 | BK | GNRAL | PEDCO | 000 | IN | SP | 0006 | F9J-707184 | AFD | IFC | 2021-08-07 | 2021-08-29 | 2021-09-12 | 22 | 14 | 36 | IFA | 2021-10-17 | 2021-10-18 | 2021-10-20 | 1 | 2 | 3 | IFA | 2022-02-06 | 2022-03-08 | 2022-03-11 | 30 | 3 | 33 | AFD | 2022-08-20 | 2022-09-28 | 2022-10-02 | 39 | 4 | 43 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-08-06 |  | D03 | AFD | T-1250 | 44779 | 1401/05/15 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05490 | 44793 | 1401/05/29 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240286 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0002 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-INS-00-01299 | 44417 | 1400/05/18 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 44451 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0130 | 44472 | 1400/07/11 |  |  |  | BK-SUR-ENG-INS-00-01773 | 44487 | 1400/07/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D00 | [5 empty] | 1400-2294-239930 | 44487 | 1400/07/26 | 44489 | 1400/07/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D00 | [9 empty] | D02 | IFA | T-0495 | 44584 | 1400/11/03 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D01 | [5 empty] | 1400-2294-441071 | 44628 | 1400/12/17 | 44631 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D01 | [9 empty] | D03 | AFD | T-1250 | 44779 | 1401/05/15 |  |  |  | BK-SUR-ENG-INS-01-05490 | 44793 | 1401/05/29 | CM-C2 | [6 empty] | 1401-2294-240286 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D02
1 | 2 | 0 | 7 | 0 | 1 | 7 | 1.2.7.1.7 | BK-GNRAL-PEDCO-000-IN-SP-0007 | Specification For Pressure Safety Valves(PSV) |  | BK-GNRAL-PEDCO-000-IN-SP-0007 | BK-GNRAL-PEDCO-000-IN-SP-0007 | BK | GNRAL | PEDCO | 000 | IN | SP | 0007 | F9J-707185 | AFD | IFC | 2021-08-07 | 2021-08-29 | 2021-09-12 | 22 | 14 | 36 | IFA | 2021-10-20 | 2021-10-19 | 2021-10-26 | -1 | 7 | 6 | IFA | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 | AFD | 2022-03-12 | 2022-03-14 | 2022-03-25 | 2 | 11 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-02-26 |  | D03 | AFD | T-0647 | 44618 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03457 | 44632 | 1400/12/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449046 | 44634 | 1400/12/23 | 44645 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0002 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-INS-00-01299 | 44417 | 1400/05/18 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 44451 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0140 | 44475 | 1400/07/14 |  |  |  | BK-SUR-ENG-INS-00-01834 | 44494 | 1400/08/03 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D00 | [5 empty] | 1400-2294-241761 | 44488 | 1400/07/27 | 44495 | 1400/08/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D00 | [9 empty] | D02 | IFA | T-0469 | 44577 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02863 | 44591 | 1400/11/10 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D01 | [5 empty] | 1400-2294-390759 | 44592 | 1400/11/11 | 44593 | 1400/11/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D01 | [9 empty] | D03 | AFD | T-0647 | 44618 | 1400/12/07 |  |  |  | BK-SUR-ENG-INS-00-03457 | 44632 | 1400/12/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D02 | [5 empty] | 1400-2294-449046 | 44634 | 1400/12/23 | 44645 | 1401/01/08 | AP
1 | 2 | 0 | 7 | 0 | 1 | 8 | 1.2.7.1.8 | BK-GNRAL-PEDCO-000-IN-SP-0009 | Specification For Fire & Gas Sensor and Devices |  | BK-GNRAL-PEDCO-000-IN-SP-0009 | BK-GNRAL-PEDCO-000-IN-SP-0009 | BK | GNRAL | PEDCO | 000 | IN | SP | 0009 | F9J-707186 | AFD | IFC | 2021-08-09 | 2021-09-22 | 2021-09-12 | 44 | -10 | 34 | IFA | 2021-10-10 | 2021-10-17 | 2021-10-20 | 7 | 3 | 10 | IFA | 2022-01-15 | 2022-01-26 | 2022-01-29 | 11 | 3 | 14 | IFA | 2022-03-20 | 2022-03-14 | 2022-03-25 | -6 | 11 | 5 | AFD | 2022-09-04 | 0 | 0 | -44808 | 0 | -44808 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-26 | 2022-08-21 |  | D04 | AFD | T-1295 | 44794 | 1401/05/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05586 | 44808 | 1401/06/13 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0011 | 2021-07-26 | 1400/05/04 |  |  |  | BK-SUR-ENG-INS-00-01354 | 44430 | 1400/05/31 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 44451 | 1400/06/21 | CM |  | 1400-2294-208200 | 44461 | 1400/06/31 |  |  | CM |  |  |  | D01 | IFA | T-0123 | 44465 | 1400/07/04 |  |  |  | BK-SUR-ENG-INS-00-01683 | 44478 | 1400/07/17 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009-D00 | [5 empty] | 1400-2294-238037 | 44486 | 1400/07/25 | 44489 | 1400/07/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009-D00 | [9 empty] | D02 | IFA | T-0414 | 44562 | 1400/10/11 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009-D01 | [5 empty] | 1400-2294-382426 | 44587 | 1400/11/06 | 44590 | 1400/11/09 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009-D01 | [9 empty] | D03 | IFA | T-0682 | 44626 | 1400/12/15 |  |  |  | BK-SUR-ENG-INS-00-03655 | 44636 | 1400/12/25 | CM-C3 | [6 empty] | 1400-2294-449020 | 44634 | 1400/12/23 | 44645 | 1401/01/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009_D02 | [9 empty] | D04 | AFD | T-1295 | 44794 | 1401/05/30 |  |  |  | BK-SUR-ENG-INS-01-05586 | 44808 | 1401/06/13 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009_D03
1 | 2 | 0 | 7 | 0 | 1 | 9 | 1.2.7.1.9 | BK-GNRAL-PEDCO-000-IN-SP-0010 | Specification For Instrument/F&G Cables |  | BK-GNRAL-PEDCO-000-IN-SP-0010 | BK-GNRAL-PEDCO-000-IN-SP-0010 | BK | GNRAL | PEDCO | 000 | IN | SP | 0010 | F9J-707187 | AFD | IFC | 2021-08-18 | 2021-12-17 | 2022-04-19 | 121 | 123 | 244 | IFA | 2022-06-14 | 2022-08-09 | 2022-08-14 | 56 | 5 | 61 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-04 |  |  | D01 | IFA | T-1029 | 44712 | 1401/03/10 | T-1029 | 44712 | 1401/03/10 | BK-SUR-ENG-INS-01-04741 | 44731 | 1401/03/29 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171148 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0029 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-INS-00-01341 | 44423 | 1400/5/24 | CM-C3 | [6 empty] | 1400-2294-320793 | 2021-12-17 | 1400/09/26 | 44670 | 1401/01/30 | CM | [10 empty] | D01 | IFA | T-1029 | 44712 | 1401/03/10 | T-1029 | 44712 | 1401/03/10 | BK-SUR-ENG-INS-01-04741 | 44731 | 1401/03/29 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010_D00 | [5 empty] | 1401-2294-171148 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010_D00
1 | 2 | 0 | 7 | 0 | 1 | 10 | 1.2.7.1.10 | BK-GNRAL-PEDCO-000-IN-SP-0011 | Specification For Control Panels and System Cabinets |  | BK-GNRAL-PEDCO-000-IN-SP-0011 | BK-GNRAL-PEDCO-000-IN-SP-0011 | BK | GNRAL | PEDCO | 000 | IN | SP | 0011 | F9J-707188 | AFD | IFC | 2021-08-07 | 2021-08-29 | 2021-09-12 | 22 | 14 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D00 | IFC | T-0002 | 44401 | 1400/05/02 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01299 | 44417 | 1400/05/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-177758 | 44437 | 1400/06/07 | 44451 | 1400/06/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0002 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-INS-00-01299 | 44417 | 1400/05/18 | CM-C3 | [6 empty] | 1400-2294-177758 | 2021-08-29 | 1400/06/07 | 44451 | 1400/06/21 | CM
1 | 2 | 0 | 7 | 0 | 1 | 11 | 1.2.7.1.11 | BK-GNRAL-PEDCO-000-IN-SP-0012 | Specification For Fire & Gas System |  | BK-GNRAL-PEDCO-000-IN-SP-0012 | BK-GNRAL-PEDCO-000-IN-SP-0012 | BK | GNRAL | PEDCO | 000 | IN | SP | 0012 | F9J-707189 | AFD | IFC | 2021-08-11 | 2021-08-29 | 2021-09-12 | 18 | 14 | 32 | IFA | 2021-10-05 | 2021-10-11 | 2021-10-18 | 6 | 7 | 13 | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 | AFD | 2022-03-20 | 2022-03-15 | 2022-03-25 | -5 | 10 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2022-03-06 |  | D03 | AFD | T-0686 | 44626 | 1400/14/15 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03653 | 44636 | 1400/12/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449047 | 44635 | 1400/12/23 | 44645 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0016 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-INS-00-01336 | 44430 | 1400/05/31 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 44451 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0113 | 44460 | 1400/06/30 |  |  |  | BK-SUR-ENG-INS-00-01676 | 44473 | 1400/07/12 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D00 | [5 empty] | 1400-2290-230716 | 44480 | 1400/07/19 | 44487 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D00 | [9 empty] | D02 | IFA | T-0444 | 44571 | 1400/10/20 |  |  |  | BK-SUR-ENG-INS-00-02815 | 44586 | 1400/11/05 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D01 | [5 empty] | 1400-2294-385430 | 44590 | 1400/11/09 | 44591 | 1400/11/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D01 | [9 empty] | D03 | AFD | T-0686 | 44626 | 1400/14/15 |  |  |  | BK-SUR-ENG-INS-00-03653 | 44636 | 1400/12/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D02 | [5 empty] | 1400-2294-449047 | 44635 | 1400/12/23 | 44645 | 1401/01/08 | AP
1 | 2 | 0 | 7 | 0 | 1 | 12 | 1.2.7.1.12 | BK-GNRAL-PEDCO-000-IN-SP-0013 | Specification For LBV |  | BK-GNRAL-PEDCO-000-IN-SP-0013 | BK-GNRAL-PEDCO-000-IN-SP-0013 | BK | GNRAL | PEDCO | 000 | IN | SP | 0013 | F9J-707191 | AFD | IFC | 2021-08-24 | 2021-08-29 | 2021-09-12 | 5 | 14 | 19 | IFA | 2022-02-05 | 2022-03-10 | 2022-03-14 | 33 | 4 | 37 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-10 |  |  | D01 | IFA | T-0485 | 44583 | 1400/11/02 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02926 | 44594 | 1400/11/13 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0013_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443274 | 44630 | 1400/12/19 | 44634 | 1400/12/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0013_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0041 | 2021-08-10 | 1400/05/19 |  |  |  | BK-SUR-ENG-PPL-00-01500 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-177780 | 2021-08-29 | 1400/06/07 | 44451 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0485 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-INS-00-02926 | 44594 | 1400/11/13 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0013_D00 | [5 empty] | 1400-2294-443274 | 44630 | 1400/12/19 | 44634 | 1400/12/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0013_D00
1 | 2 | 0 | 7 | 0 | 1 | 13 | 1.2.7.1.13 | BK-GNRAL-PEDCO-000-IN-SP-0014 | Specification For CCTV |  | BK-GNRAL-PEDCO-000-IN-SP-0014 | BK-GNRAL-PEDCO-000-IN-SP-0014 | BK | GNRAL | PEDCO | 000 | IN | SP | 0014 | F9J-707190 | AFD | IFC | 2021-10-09 | 2021-10-11 | 2021-10-18 | 2 | 7 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-25 |  |  | D00 | IFC | T-0114 | 44464 | 1400/07/03 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01711 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0014_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2290-230714 | 44480 | 1400/07/19 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0014_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0114 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-INS-00-01711 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0014_D00 | [5 empty] | 1400-2290-230714 | 2021-10-11 | 1400/07/19 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0014_D00
1 | 2 | 0 | 7 | 0 | 2 | 0 | 1.2.7.2 |  | Drawing/Diagram
1 | 2 | 0 | 7 | 0 | 2 | 1 | 1.2.7.2.1 | BK-GNRAL-PEDCO-000-IN-DW-0001 | CCTV Typical Installation Details & Notes |  | BK-GNRAL-PEDCO-000-IN-DW-0001 | BK-GNRAL-PEDCO-000-IN-DW-0001 | BK | GNRAL | PEDCO | 000 | IN | DW | 0001 | F2J-707192 | IFI | IFI | 2021-10-09 | 2021-10-11 | 2021-10-18 | 2 | 7 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-25 |  |  | D00 | IFI | T-0114 | 44464 | 1400/07/03 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01711 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2290-230714 | 44480 | 1400/07/19 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0114 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-INS-00-01711 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-DW-0001_D00 | [5 empty] | 1400-2290-230714 | 2021-10-11 | 1400/07/19 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-DW-0001_D00
1 | 2 | 0 | 8 | 0 | 0 | 0 | 1.2.8 |  | Safety & Fire Fighting
1 | 2 | 0 | 8 | 0 | 1 | 0 | 1.2.8.1 |  | Specification
1 | 2 | 0 | 8 | 0 | 1 | 1 | 1.2.8.1.1 | BK-GNRAL-PEDCO-000-SA-SP-0001 | Specification For Fire Fighting Equipment |  | BK-GNRAL-PEDCO-000-SA-SP-0001 | BK-GNRAL-PEDCO-000-SA-SP-0001 | BK | GNRAL | PEDCO | 000 | SA | SP | 0001 | F0Z-707193 | AFD | IFC | 2021-09-12 | 2021-09-13 | 2021-09-18 | 1 | 5 | 6 | IFA | 2021-11-08 | 2021-11-22 | 2021-11-27 | 14 | 5 | 19 | IFA | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | AFD | 2022-01-12 | 2021-12-30 | 2022-01-02 | -13 | 3 | -10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-29 | 2021-12-29 |  | D03 | AFD | T-0399 | 44559 | 1400/10/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-342159 | 44560 | 1400/10/09 | 44563 | 1400/10/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0070 | 2021-08-29 | 1400/06/07 | [13 empty] | 1400-2294-197171 | 2021-09-13 | 1400/06/22 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0184 | 44494 | 1400/08/03 | [13 empty] | 1400-2294-286876 | 44522 | 1400/09/01 | 44527 | 1400/09/06 | CM | NISOC-CRS- BK-GNRAL-PEDCO- 000-SA-SP-0001-D00 | [9 empty] | D02 | IFA | T-0314 | 44538 | 1400/09/17 | [13 empty] | 1400-2294-327298 | 44550 | 1400/09/29 | 44552 | 1400/10/01 | AP | NISOC-CRS- BK-GNRAL-PEDCO- 000-SA-SP-0001-D01 | [9 empty] | D03 | AFD | T-0399 | 44559 | 1400/10/08 | [13 empty] | 1400-2294-342159 | 44560 | 1400/10/09 | 44563 | 1400/10/12 | AP
1 | 2 | 0 | 8 | 0 | 1 | 2 | 1.2.8.1.2 | BK-GNRAL-PEDCO-000-SA-SP-0002 | Specification For Hazardous Area Classification |  | BK-GNRAL-PEDCO-000-SA-SP-0002 | BK-GNRAL-PEDCO-000-SA-SP-0002 | BK | GNRAL | PEDCO | 000 | SA | SP | 0002 | F0Z-707194 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | IFA | 2021-09-21 | 2021-09-29 | 2021-10-11 | 8 | 12 | 20 | IFA | 2021-11-10 | 2021-11-21 | 2021-11-06 | 11 | -15 | -4 | AFD | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-01-09 |  | D03 | AFD | T-0440 | 44570 | 1400/10/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-360413 | 44572 | 1400/10/21 | 44591 | 1400/11/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 44447 | 1400/06/17 | CM | [10 empty] | D01 | IFA | T-0081 | 44446 | 1400/06/16 | [13 empty] | 1400-2294-217844 | 44468 | 1400/07/07 | 44480 | 1400/07/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0002_D00 | [9 empty] | D02 | IFA | T-0188 | 44496 | 1400/08/05 | [13 empty] | 1400-2294-285007 | 44521 | 1400/08/30 | 44506 | 1400/08/15 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0002_D01 | [9 empty] | D03 | AFD | T-0440 | 44570 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 44572 | 1400/10/21 | 44591 | 1400/11/10 | AP
1 | 2 | 0 | 8 | 0 | 1 | 3 | 1.2.8.1.3 | BK-GNRAL-PEDCO-000-SA-SP-0003 | Specification For Fire Water System |  | BK-GNRAL-PEDCO-000-SA-SP-0003 | BK-GNRAL-PEDCO-000-SA-SP-0003 | BK | GNRAL | PEDCO | 000 | SA | SP | 0003 | F0Z-707195 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | IFA | 2021-09-21 | 2021-09-29 | 2021-10-11 | 8 | 12 | 20 | IFA | 2021-11-15 | 2021-11-29 | 2021-12-06 | 14 | 7 | 21 | IFA | 2022-10-22 | 2022-11-03 | 2022-11-05 | 12 | 2 | 14 | IFA | 2022-11-26 | 0 | 0 | -44891 | 0 | -44891 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D04 | IFA | T-1583 | 44877 | 1401/08/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0003-D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 44447 | 1400/06/17 | CM | [10 empty] | D01 | IFA | T-0081 | 44446 | 1400/06/16 | [13 empty] | 1400-2294-217844 | 44468 | 1400/07/07 | 44480 | 1400/07/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0003_D00 | [9 empty] | D02 | IFA | T-0199 | 44501 | 1400/08/10 | [13 empty] | 1400-2290-295054 | 44529 | 1400/09/08 | 44536 | 1400/09/15 | CM | NISO-CCRS-BK-GNRAL-PEDCO-000-SA-SP-0003_D01 | [9 empty] | D03 | IFA | T-1462 | 44842 | 1401/07/16 | T-1462 | 44842 | 1401/07/16 |  |  |  |  | PEDCO-CRS-BK-GNRAL-PEDCO-000-SA-SP-0003_D02 | [5 empty] | 1401-2294-294116 | 44868 | 1401/08/12 | 44870 | 1401/08/15 | CM | [10 empty] | D04 | IFA | T-1583 | 44877 | 1401/08/21 | [19 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0003-D03
1 | 2 | 0 | 8 | 0 | 1 | 4 | 1.2.8.1.4 | BK-GNRAL-PEDCO-000-SA-SP-0004 | Specification For Environmental Job |  | BK-GNRAL-PEDCO-000-SA-SP-0004 | BK-GNRAL-PEDCO-000-SA-SP-0004 | BK | GNRAL | PEDCO | 000 | SA | SP | 0004 | F0Z-707196 | AFD | IFC | 2021-08-25 | 2022-08-31 | 2022-06-09 | 371 | -83 | 288 | AFD | 2022-08-06 | 2022-08-10 | 2022-08-14 | 4 | 4 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-11 | 2022-07-23 |  | D01 | AFD | T-1180 | 44765 | 1401/05/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-172728 | 44783 | 1401/05/19 | 44787 | 1401/05/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0047 | 2021-08-11 | 1400/05/20 | [13 empty] | 1400-2294-168856 | 2022-08-31 | 1400/05/31 | 44721 | 1401/03/19 | AP | [10 empty] | D01 | AFD | T-1180 | 44765 | 1401/05/01 | [13 empty] | 1401-2294-172728 | 44783 | 1401/05/19 | 44787 | 1401/05/23 | AP
1 | 2 | 0 | 8 | 0 | 1 | 5 | 1.2.8.1.5 | BK-GNRAL-PEDCO-000-SA-SP-0005 | Specification For Total Flooding System |  | BK-GNRAL-PEDCO-000-SA-SP-0005 | BK-GNRAL-PEDCO-000-SA-SP-0005 | BK | GNRAL | PEDCO | 000 | SA | SP | 0005 | F0Z-707197 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | IFA | 2021-11-15 | 2021-11-29 | 2021-12-06 | 14 | 7 | 21 | AFD | 2022-03-12 | 2022-03-09 | 2022-03-12 | -3 | 3 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-02-26 |  | D02 | AFD | T-0646 | 44618 | 1400/12/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443038 | 44629 | 1400/12/18 | 44632 | 1400/12/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 44447 | 1400/06/17 | CM | [10 empty] | D01 | IFA | T-0199 | 44501 | 1400/08/10 | [13 empty] | 1400-2290-295054 | 44529 | 1400/09/08 | 44536 | 1400/09/15 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0005_D00 | [9 empty] | D02 | AFD | T-0646 | 44618 | 1400/12/07 | [13 empty] | 1400-2294-443038 | 44629 | 1400/12/18 | 44632 | 1400/12/21 | AP
1 | 2 | 0 | 8 | 0 | 1 | 6 | 1.2.8.1.6 | BK-GNRAL-PEDCO-000-SA-SP-0006 | Specification For Safety Equipment |  | BK-GNRAL-PEDCO-000-SA-SP-0006 | BK-GNRAL-PEDCO-000-SA-SP-0006 | BK | GNRAL | PEDCO | 000 | SA | SP | 0006 | F0Z-707198 | AFD | IFC | 2021-09-12 | 2021-09-13 | 2021-09-18 | 1 | 5 | 6 | IFA | 2021-11-08 | 2021-11-22 | 2021-11-27 | 14 | 5 | 19 | AFD | 2021-12-20 | 2021-12-09 | 2021-12-14 | -11 | 5 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-29 | 2021-12-06 |  | D02 | AFD | T-0297 | 44536 | 1400/09/15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-310955 | 44539 | 1400/09/18 | 44544 | 1400/09/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0070 | 2021-08-29 | 1400/06/07 | [13 empty] | 1400-2294-197171 | 2021-09-13 | 1400/06/22 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0184 | 44494 | 1400/08/03 | [13 empty] | 1400-2294-286876 | 44522 | 1400/09/01 | 44527 | 1400/09/06 | AP | NISOC-CRS- BK-GNRAL-PEDCO- 000-SA-SP-0006-D00 | [9 empty] | D02 | AFD | T-0297 | 44536 | 1400/09/15 | [13 empty] | 1400-2294-310955 | 44539 | 1400/09/18 | 44544 | 1400/09/23 | AP
1 | 2 | 0 | 8 | 0 | 1 | 7 | 1.2.8.1.7 | BK-GNRAL-PEDCO-000-SA-SP-0007 | Specification For passive Fire protection |  | BK-GNRAL-PEDCO-000-SA-SP-0007 | BK-GNRAL-PEDCO-000-SA-SP-0007 | BK | GNRAL | PEDCO | 000 | SA | SP | 0007 | F0Z-707199 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | AFD | 2021-09-21 | 2021-09-30 | 2021-09-18 | 9 | -12 | -3 | AFD | 2022-03-19 | 2022-03-30 | 2022-04-03 | 11 | 4 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-03-05 |  | D02 | AFD | T-0667 | 44625 | 1400/12/14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-6037 | 44650 | 1401/01/10 | 44654 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 44447 | 1400/06/17 | AP | [10 empty] | D01 | AFD | T-0079 | 44446 | 1400/06/16 | [13 empty] | 1400-2294-195927 | 44452 | 1400/06/22 | 44457 | 1400/06/27 | CM | BK-HD-PEDCO-L-0100 | 1400-2294-217946 | 44469 | 1400/07/08 |  |  | CM |  |  |  | D02 | AFD | T-0667 | 44625 | 1400/12/14 | [13 empty] | 1401-2294-6037 | 44650 | 1401/01/10 | 44654 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0007_D01
1 | 2 | 0 | 8 | 0 | 1 | 8 | 1.2.8.1.8 | BK-GNRAL-PEDCO-000-SA-SP-0008 | Specification For Safety Signs |  | BK-GNRAL-PEDCO-000-SA-SP-0008 | BK-GNRAL-PEDCO-000-SA-SP-0008 | BK | GNRAL | PEDCO | 000 | SA | SP | 0008 | F0Z-707200 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | IFA | 2021-09-21 | 2021-09-29 | 2021-10-11 | 8 | 12 | 20 | IFA | 2021-11-10 | 2021-11-01 | 2021-11-06 | -9 | 5 | -4 | AFD | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-01-09 |  | D03 | AFD | T-0440 | 44570 | 1400/10/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-360413 | 44572 | 1400/10/21 | 44591 | 1400/11/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 44447 | 1400/06/17 | CM | [10 empty] | D01 | IFA | T-0081 | 44446 | 1400/06/16 | [13 empty] | 1400-2294-217844 | 44468 | 1400/07/07 | 44480 | 1400/07/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0008_D00 | [9 empty] | D02 | IFA | T-0191 | 44496 | 1400/08/05 | [13 empty] | 1400-2294-256924 | 44501 | 1400/08/10 | 44506 | 1400/08/15 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0008_D01 | [9 empty] | D03 | AFD | T-0440 | 44570 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 44572 | 1400/10/21 | 44591 | 1400/11/10 | AP
1 | 2 | 0 | 8 | 0 | 2 | 0 | 1.2.8.2 |  | Drawing/Diagram
1 | 2 | 0 | 8 | 0 | 2 | 1 | 1.2.8.2.1 | BK-GNRAL-PEDCO-000-SA-DW-0002 | Typical Installation Detail for Safety & Fire Fighting Equipment |  | BK-GNRAL-PEDCO-000-SA-DW-0002 | BK-GNRAL-PEDCO-000-SA-DW-0002 | BK | GNRAL | PEDCO | 000 | SA | DW | 0002 | F2L-707201 | IFI | IFI | 2022-01-12 | 2022-01-20 | 2022-01-22 | 8 | 2 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-29 |  |  | D00 | IFI | T-0405 | 44559 | 1400/10/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-372872 | 44581 | 1400/10/30 | 44583 | 1400/11/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0405 | 2021-12-29 | 1400/10/08 | [13 empty] | 1400-2294-372872 | 2022-01-20 | 1400/10/30 | 44583 | 1400/11/02 | AP
1 | 2 | 0 | 8 | 0 | 2 | 2 | 1.2.8.2.2 | BK-GNRAL-PEDCO-000-SA-DW-0003 | Symbol & Legend For Safety & Firefighting Systems |  | BK-GNRAL-PEDCO-000-SA-DW-0003 | BK-GNRAL-PEDCO-000-SA-DW-0003 | BK | GNRAL | PEDCO | 000 | SA | DW | 0003 | F2L-707202 | AFC | IFC | 2021-09-12 | 2021-09-13 | 2021-09-18 | 1 | 5 | 6 | IFA | 2021-11-08 | 2021-11-22 | 2021-11-27 | 14 | 5 | 19 | AFC | 2021-12-22 | 2021-12-13 | 2021-12-15 | -9 | 2 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-29 | 2021-12-08 |  | D02 | AFC | T-0315 | 44538 | 1400/09/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-316975 | 44543 | 1400/09/22 | 44545 | 1400/09/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0070 | 2021-08-29 | 1400/06/07 | [13 empty] | 1400-2294-197171 | 2021-09-13 | 1400/06/22 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0184 | 44494 | 1400/08/03 | [13 empty] | 1400-2294-286876 | 44522 | 1400/09/01 | 44527 | 1400/09/06 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-SA-DW-0003 D00 | [9 empty] | D02 | AFC | T-0315 | 44538 | 1400/09/18 | [13 empty] | 1400-2294-316975 | 44543 | 1400/09/22 | 44545 | 1400/09/24 | AP
1 | 2 | 0 | 8 | 0 | 3 | 0 | 1.2.8.3 |  | Data Sheets
1 | 2 | 0 | 8 | 0 | 3 | 1 | 1.2.8.3.1 | BK-GNRAL-PEDCO-000-SA-DT-0001 | Material Safety Data Sheets |  | BK-GNRAL-PEDCO-000-SA-DT-0001 | BK-GNRAL-PEDCO-000-SA-DT-0001 | BK | GNRAL | PEDCO | 000 | SA | DT | 0001 | F0Z-707203 | AFC | IFC | 2021-10-05 | 2022-01-29 | 2022-01-31 | 116 | 2 | 118 | IFA | 2022-10-23 | 0 | 0 | -44857 | 0 | -44857 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-21 |  |  | D01 | IFA | T-1467 | 44843 | 1401/07/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-SA-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS- BK-GNRAL-PEDCO-000-SA-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0111 | 2021-09-21 | 1400/06/30 |  |  |  | BK-SUR-HSE-HSE-00-01662 | 44472 | 1400/07/11 | CM-C2 | [6 empty] | 1400-2294-386703 | 2022-01-29 | 1400/11/09 | 44592 | 1400/11/11 | CM | [10 empty] | D01 | IFA | T-1467 | 44843 | 1401/07/17 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-SA-DT-0001_D00 | [11 empty] | NISOC-CRS- BK-GNRAL-PEDCO-000-SA-DT-0001_D00
1 | 2 | 0 | 9 | 0 | 0 | 0 | 1.2.9 |  | Electrical
1 | 2 | 0 | 9 | 0 | 1 | 0 | 1.2.9.1 |  | Basis/Criteria
1 | 2 | 0 | 9 | 0 | 1 | 1 | 1.2.9.1.1 | BK-GNRAL-PEDCO-000-EL-DC-0001 | Electrical System Design Criteria |  | BK-GNRAL-PEDCO-000-EL-DC-0001 | BK-GNRAL-PEDCO-000-EL-DC-0001 | BK | GNRAL | PEDCO | 000 | EL | DC | 0001 | F0Z-707204 | AFD | IFC | 2021-08-17 | 2021-09-02 | 2021-09-04 | 16 | 2 | 18 | IFA | 2021-09-21 | 2021-09-22 | 2021-09-26 | 1 | 4 | 5 | AFD | 2022-03-07 | 2022-03-05 | 2022-03-01 | -2 | -4 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-03 | 2022-02-21 |  | D02 | AFD | T-0619 | 44613 | 1400/12/02 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03251 | 44619 | 1400/12/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430788 | 44625 | 1400/12/05 | 44621 | 1400/12/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DC-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0026 | 2021-08-03 | 1400/05/12 |  |  |  | BK-SUR-ENG-ELE-00-01318 | 44422 | 1400/05/23 | CM-C3 | [6 empty] | 1400/2294/182812 | 2021-09-02 | 1400/06/11 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0083 | 44446 | 1400/06/16 |  |  |  | BK-SUR-ENG-ELE-00-01545 | 44457 | 1400/06/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DC-0001_D00 | [5 empty] | 1400-2294-209506 | 44461 | 1400/06/31 | 44465 | 1400/07/04 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DC-0001_D00 | [9 empty] | D02 | AFD | T-0619 | 44613 | 1400/12/02 |  |  |  | BK-SUR-ENG-ELE-00-03251 | 44619 | 1400/12/08 | AP | [6 empty] | 1400-2294-430788 | 44625 | 1400/12/05 | 44621 | 1400/12/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DC-0001_D01
1 | 2 | 0 | 9 | 0 | 2 | 0 | 1.2.9.2 |  | Specification
1 | 2 | 0 | 9 | 0 | 2 | 1 | 1.2.9.2.1 | BK-GNRAL-PEDCO-000-EL-SP-0001 | Specification For LV Switchgear & Motor Control Centers |  | BK-GNRAL-PEDCO-000-EL-SP-0001 | BK-GNRAL-PEDCO-000-EL-SP-0001 | BK | GNRAL | PEDCO | 000 | EL | SP | 0001 | F0Z-707205 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-10-31 | 2022-01-02 | 2021-11-07 | 63 | -56 | 7 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D03 | AFD | T-0586 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 44412 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 44445 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 44470 | 1400/07/09 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0001_D00 | [9 empty] | D02 | IFA | T-0163 | 44486 | 1400/07/25 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-261165 | 44563 | 1400/08/12 | 44507 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0001-D01 | [9 empty] | D03 | AFD | T-0586 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM
1 | 2 | 0 | 9 | 0 | 2 | 2 | 1.2.9.2.2 | BK-GNRAL-PEDCO-000-EL-SP-0002 | Specification For MV Switchgear |  | BK-GNRAL-PEDCO-000-EL-SP-0002 | BK-GNRAL-PEDCO-000-EL-SP-0002 | BK | GNRAL | PEDCO | 000 | EL | SP | 0002 | F0Z-707206 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-10-31 | 2022-01-02 | 2021-11-07 | 63 | -56 | 7 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D03 | AFD | T-0586 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 44412 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 44445 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 44470 | 1400/07/09 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0002_D00 | [9 empty] | D02 | IFA | T-0163 | 44486 | 1400/07/25 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-261165 | 44563 | 1400/08/12 | 44507 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0002_D01 | [9 empty] | D03 | AFD | T-0586 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM
1 | 2 | 0 | 9 | 0 | 2 | 3 | 1.2.9.2.3 | BK-GNRAL-PEDCO-000-EL-SP-0003 | Specification For UPS System |  | BK-GNRAL-PEDCO-000-EL-SP-0003 | BK-GNRAL-PEDCO-000-EL-SP-0003 | BK | GNRAL | PEDCO | 000 | EL | SP | 0003 | F0Z-707207 | AFD | IFC | 2021-08-18 | 2021-09-02 | 2021-09-04 | 15 | 2 | 17 | IFA | 2021-09-21 | 2021-09-22 | 2021-09-26 | 1 | 4 | 5 | IFA | 2021-12-29 | 2022-01-06 | 2022-01-08 | 8 | 2 | 10 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-04 |  |  | D03 | AFD | T-0594 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0028 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-ELE-00-01337 | 44423 | 1400/05/24 | CM-C2 | [6 empty] | 1400/2294/182811 | 2021-09-02 | 1400/06/13 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0083 | 44446 | 1400/06/16 |  |  |  | BK-SUR-ENG-ELE-00-01545 | 44457 | 1400/06/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0003_D00 | [5 empty] | 1400-2294-209506 | 44461 | 1400/06/31 | 44465 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0003_D00 | [9 empty] | D02 | IFA | T-0348 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-ELE-00-02411 | 44555 | 1400/10/04 | AP | [6 empty] | 1400-2294-352441 | 44567 | 1400/10/16 | 44569 | 1400/10/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0003_D01 | [9 empty] | D03 | AFD | T-0594 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 4 | 1.2.9.2.4 | BK-GNRAL-PEDCO-000-EL-SP-0004 | Specification For Transformers |  | BK-GNRAL-PEDCO-000-EL-SP-0004 | BK-GNRAL-PEDCO-000-EL-SP-0004 | BK | GNRAL | PEDCO | 000 | EL | SP | 0004 | F0Z-707208 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2022-01-02 | 2021-11-07 | 62 | -56 | 6 | AFD | 2022-03-22 | 2022-03-14 | 2022-03-26 | -8 | 12 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-03-08 |  | D03 | AFD | T-0696 | 44628 | 1400/12/17 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03532 | 44633 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448998 | 44634 | 1400/12/23 | 44646 | 1401/01/06 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 44412 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 44445 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 44470 | 1400/07/09 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0004_D00 | [9 empty] | D02 | IFA | T-0166 | 44487 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-261157 | 44563 | 1400/10/12 | 44507 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0004_D01 | [9 empty] | D03 | AFD | T-0696 | 44628 | 1400/12/17 |  |  |  | BK-SUR-ENG-ELE-00-03532 | 44633 | 1400/12/22 | AP | [6 empty] | 1400-2294-448998 | 44634 | 1400/12/23 | 44646 | 1401/01/06 | AP
1 | 2 | 0 | 9 | 0 | 2 | 5 | 1.2.9.2.5 | BK-GNRAL-PEDCO-000-EL-SP-0005 | Specification For DC Charger |  | BK-GNRAL-PEDCO-000-EL-SP-0005 | BK-GNRAL-PEDCO-000-EL-SP-0005 | BK | GNRAL | PEDCO | 000 | EL | SP | 0005 | F0Z-707209 | AFD | IFC | 2021-08-18 | 2021-09-02 | 2021-09-04 | 15 | 2 | 17 | IFA | 2021-09-21 | 2021-09-22 | 2021-09-26 | 1 | 4 | 5 | IFA | 2021-11-03 | 2021-11-09 | 2021-11-14 | 6 | 5 | 11 | AFD | 2021-12-21 | 2022-01-03 | 2022-01-05 | 13 | 2 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-04 | 2021-12-07 |  | D03 | AFD | T-0307 | 44537 | 1400/09/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-348119 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0028 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-ELE-00-01337 | 44423 | 1400/05/24 | CM-C2 | [6 empty] | 1400/2294/182811 | 2021-09-02 | 1400/06/13 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0083 | 44446 | 1400/06/16 |  |  |  | BK-SUR-ENG-ELE-00-01545 | 44457 | 1400/06/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0005_D00 | [5 empty] | 1400-2294-209506 | 44461 | 1400/06/31 | 44465 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0005_D00 | [9 empty] | D02 | IFA | T-0177 | 44489 | 1400/07/28 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-268781 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDEC-000-EL-SP-0005-D01 | [9 empty] | D03 | AFD | T-0307 | 44537 | 1400/09/16 | [13 empty] | 1400-2294-348119 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | AP
1 | 2 | 0 | 9 | 0 | 2 | 6 | 1.2.9.2.6 | BK-GNRAL-PEDCO-000-EL-SP-0006 | Specification For Earthing & Lightning System |  | BK-GNRAL-PEDCO-000-EL-SP-0006 | BK-GNRAL-PEDCO-000-EL-SP-0006 | BK | GNRAL | PEDCO | 000 | EL | SP | 0006 | F0Z-707210 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 44502 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 44418 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 44440 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 44443 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 44452 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 44453 | 1400/06/23 | 44457 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0006_D00 | [9 empty] | D02 | IFA | T-0116 | 44464 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 44472 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0006_D01 | [9 empty] | D03 | AFD | T-0206 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 7 | 1.2.9.2.7 | BK-GNRAL-PEDCO-000-EL-SP-0007 | Specification For Lighting & Small Power System |  | BK-GNRAL-PEDCO-000-EL-SP-0007 | BK-GNRAL-PEDCO-000-EL-SP-0007 | BK | GNRAL | PEDCO | 000 | EL | SP | 0007 | F0Z-707211 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 44502 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 44418 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 44440 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 44443 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 44452 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 44453 | 1400/06/23 | 44457 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0007_D00 | [9 empty] | D02 | IFA | T-0116 | 44464 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 44472 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0007_D01 | [9 empty] | D03 | AFD | T-0206 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 8 | 1.2.9.2.8 | BK-GNRAL-PEDCO-000-EL-SP-0008 | Specification For Bulk Materials |  | BK-GNRAL-PEDCO-000-EL-SP-0008 | BK-GNRAL-PEDCO-000-EL-SP-0008 | BK | GNRAL | PEDCO | 000 | EL | SP | 0008 | F0Z-707212 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2022-01-02 | 2021-11-07 | 62 | -56 | 6 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | AFD | 2022-03-21 | 2022-03-14 | 2022-03-26 | -7 | 12 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 | 2022-03-07 |  | D04 | AFD | T-0693 | 44627 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03530 | 44633 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448996 | 44634 | 1400/12/23 | 44646 | 1401/01/06 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0008_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 44412 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 44445 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 44470 | 1400/07/09 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0008_D00 | [9 empty] | D02 | IFA | T-0166 | 44487 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-261157 | 44563 | 1400/10/12 | 44507 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0008_D01 | [9 empty] | D03 | AFD | T-0586 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM | [10 empty] | D04 | AFD | T-0693 | 44627 | 1400/12/16 |  |  |  | BK-SUR-ENG-ELE-00-03530 | 44633 | 1400/12/22 | AP | [6 empty] | 1400-2294-448996 | 44634 | 1400/12/23 | 44646 | 1401/01/06 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0008_D03
1 | 2 | 0 | 9 | 0 | 2 | 9 | 1.2.9.2.9 | BK-GNRAL-PEDCO-000-EL-SP-0009 | Specification For Diesel Generator |  | BK-GNRAL-PEDCO-000-EL-SP-0009 | BK-GNRAL-PEDCO-000-EL-SP-0009 | BK | GNRAL | PEDCO | 000 | EL | SP | 0009 | F0Z-707213 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 44502 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 44418 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 44440 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 44443 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 44452 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 44453 | 1400/06/23 | 44457 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0009_D00 | [9 empty] | D02 | IFA | T-0116 | 44464 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 44472 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0009_D01 | [9 empty] | D03 | AFD | T-0206 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 10 | 1.2.9.2.10 | BK-GNRAL-PEDCO-000-EL-SP-0010 | Specification For LV Induction Motors |  | BK-GNRAL-PEDCO-000-EL-SP-0010 | BK-GNRAL-PEDCO-000-EL-SP-0010 | BK | GNRAL | PEDCO | 000 | EL | SP | 0010 | F0Z-707214 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFC | 2021-11-01 | 2022-01-02 | 2021-11-07 | 62 | -56 | 6 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D03 | AFD | T-0586 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 44412 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 44445 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 44470 | 1400/07/09 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0010_D00 | [9 empty] | D02 | IFC | T-0170 | 44487 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-261334 | 44563 | 1400/10/12 | 44507 | 1400/08/16 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-EL-SP-0010_D01 | [9 empty] | D03 | AFD | T-0586 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM
1 | 2 | 0 | 9 | 0 | 2 | 11 | 1.2.9.2.11 | BK-GNRAL-PEDCO-000-EL-SP-0011 | Specification For Electrical Requirements of Packaged Units |  | BK-GNRAL-PEDCO-000-EL-SP-0011 | BK-GNRAL-PEDCO-000-EL-SP-0011 | BK | GNRAL | PEDCO | 000 | EL | SP | 0011 | F0Z-707215 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 44502 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 44418 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 44440 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 44443 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 44452 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 44453 | 1400/06/23 | 44457 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0011_D00 | [9 empty] | D02 | IFA | T-0116 | 44464 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 44472 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0011_D01 | [9 empty] | D03 | AFD | T-0206 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 12 | 1.2.9.2.12 | BK-GNRAL-PEDCO-000-EL-SP-0012 | Specification For Capacitor Bank |  | BK-GNRAL-PEDCO-000-EL-SP-0012 | BK-GNRAL-PEDCO-000-EL-SP-0012 | BK | GNRAL | PEDCO | 000 | EL | SP | 0012 | F0Z-707216 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2021-11-07 | 2021-11-07 | 6 | 0 | 6 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D03 | AFD | T-0594 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 44412 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 44445 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 44470 | 1400/07/09 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0012_D00 | [9 empty] | D02 | IFA | T-0171 | 44487 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-263867 | 44507 | 1400/08/16 | 44507 | 1400/08/16 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-EL-SP-0012_D01 | [9 empty] | D03 | AFD | T-0594 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 13 | 1.2.9.2.13 | BK-GNRAL-PEDCO-000-EL-SP-0013 | Specification For Distribution & Lighting Panels |  | BK-GNRAL-PEDCO-000-EL-SP-0013 | BK-GNRAL-PEDCO-000-EL-SP-0013 | BK | GNRAL | PEDCO | 000 | EL | SP | 0013 | F0Z-707217 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 44502 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 44418 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 44440 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 44443 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 44452 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 44453 | 1400/06/23 | 44457 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0013_D00 | [9 empty] | D02 | IFA | T-0116 | 44464 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 44472 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0013_D01 | [9 empty] | D03 | AFD | T-0206 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 14 | 1.2.9.2.14 | BK-GNRAL-PEDCO-000-EL-SP-0014 | Specification For Power & Control Cables |  | BK-GNRAL-PEDCO-000-EL-SP-0014 | BK-GNRAL-PEDCO-000-EL-SP-0014 | BK | GNRAL | PEDCO | 000 | EL | SP | 0014 | F0Z-707218 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2021-11-07 | 2021-11-07 | 6 | 0 | 6 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D03 | AFD | T-0594 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 44412 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 44445 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 44470 | 1400/07/09 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0014_D00 | [9 empty] | D02 | IFA | T-0171 | 44487 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-263867 | 44507 | 1400/08/16 | 44507 | 1400/08/16 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-EL-SP-0014_D01 | [9 empty] | D03 | AFD | T-0594 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 15 | 1.2.9.2.15 | BK-GNRAL-PEDCO-000-EL-SP-0016 | Specification For Cathodic Protection System |  | BK-GNRAL-PEDCO-000-EL-SP-0016 | BK-GNRAL-PEDCO-000-EL-SP-0016 | BK | GNRAL | PEDCO | 000 | EL | SP | 0016 | F0Z-707219 | AFD | IFC | 2021-08-14 | 2021-09-02 | 2021-09-04 | 19 | 2 | 21 | IFA | 2021-09-28 | 2021-09-28 | 2021-10-02 | 0 | 4 | 4 | IFA | 2021-10-25 | 2021-10-30 | 2021-11-01 | 5 | 2 | 7 | AFD | 2021-12-21 | 2022-01-03 | 2022-01-05 | 13 | 2 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-31 | 2021-12-07 |  | D03 | AFD | T-0307 | 44537 | 1400/09/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-348119 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0024 | 2021-07-31 | 1400/05/09 |  |  |  | BK-SUR-ENG-ELE-00-01306 | 44418 | 1400/05/19 | CM-C2 |  | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016_D01 | 44464 | 1400/07/03 | CM-C2 |  | 1400/2294/182822 | 2021-09-02 | 1400/06/11 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0092 | 44453 | 1400/06/23 |  |  |  | BK-SUR-ENG-ELE-00-01592 | 44464 | 1400/07/03 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016_D00 | [5 empty] | 1400-2294-215960 | 44467 | 1400/07/06 | 44471 | 1400/07/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016_D00 | [9 empty] | D02 | IFA | T-0146 | 44480 | 1400/07/19 |  |  |  | BK-SUR-ENG-ELE-00-01783 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016-D01 | [5 empty] | 1400-2294-253895 | 44499 | 1400/08/08 | 44501 | 1400/08/10 | AP | NISOC-CRS-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016-D01 | [9 empty] | D03 | AFD | T-0307 | 44537 | 1400/09/16 | [13 empty] | 1400-2294-348119 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | AP
1 | 2 | 0 | 9 | 0 | 2 | 16 | 1.2.9.2.16 | BK-GNRAL-PEDCO-000-EL-SP-0017 | Specification For MV Induction Motors |  | BK-GNRAL-PEDCO-000-EL-SP-0017 | BK-GNRAL-PEDCO-000-EL-SP-0017 | BK | GNRAL | PEDCO | 000 | EL | SP | 0017 | F0Z-707220 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-12-29 | 2022-01-06 | 2022-01-08 | 8 | 2 | 10 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D03 | AFD | T-0594 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 44412 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 44445 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 44470 | 1400/07/09 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0017_D00 | [9 empty] | D02 | IFA | T-0348 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-ELE-00-02411 | 44555 | 1400/10/04 | AP | [6 empty] | 1400-2294-352441 | 44567 | 1400/10/16 | 44569 | 1400/10/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0017_D01 | [9 empty] | D03 | AFD | T-0594 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 17 | 1.2.9.2.17 | BK-GNRAL-PEDCO-000-EL-SP-0018 | Specification For NGR |  | BK-GNRAL-PEDCO-000-EL-SP-0018 | BK-GNRAL-PEDCO-000-EL-SP-0018 | BK | GNRAL | PEDCO | 000 | EL | SP | 0018 | F0Z-707221 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2021-11-07 | 2021-11-07 | 6 | 0 | 6 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-24 |  |  | D03 | AFD | T-0594 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 44412 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 44445 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 44470 | 1400/07/09 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0018_D00 | [9 empty] | D02 | IFA | T-0171 | 44487 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 44500 | 1400/08/09 | AP | [6 empty] | 1400-2294-263867 | 44507 | 1400/08/16 | 44507 | 1400/08/16 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-EL-SP-0018_D01 | [9 empty] | D03 | AFD | T-0594 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 44614 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 44621 | 1400/12/10 | 44628 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 18 | 1.2.9.2.18 | BK-GNRAL-PEDCO-000-EL-SP-0019 | Specification For Overhead Transmission Lines |  | BK-GNRAL-PEDCO-000-EL-SP-0019 | BK-GNRAL-PEDCO-000-EL-SP-0019 | BK | GNRAL | PEDCO | 000 | EL | SP | 0019 | F0Z-707222 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-10-04 | 2021-09-30 | 2021-10-10 | -4 | 10 | 6 | IFA | 2021-10-26 | 2022-01-01 | 2021-11-07 | 67 | -55 | 12 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 |  |  | D03 | AFD | T-0586 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 44418 | 1400/05/19 | RJ-C4 | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 44440 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0109 | 44459 | 1400/06/29 |  |  |  | BK-SSR-ENG-ELE-00-01652 | 44471 | 1400/07/10 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0019-D00 | [5 empty] | 1400-2294-217976 | 44469 | 1400/07/08 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0019-D00 | [9 empty] | D02 | IFA | T-0154 | 44481 | 1400/07/20 |  |  |  | BK-SUR-ENG-ELE-00-01783 | 44488 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0019-D01 | [5 empty] | 1400-2294-259366 | 44562 | 1400/08/11 | 44507 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0019-D01 | [9 empty] | D03 | AFD | T-0586 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM
1 | 2 | 0 | 9 | 0 | 3 | 0 | 1.2.9.3 |  | Drawing/Diagram
1 | 2 | 0 | 9 | 0 | 3 | 1 | 1.2.9.3.1 | BK-GNRAL-PEDCO-000-EL-DW-0001 | Electrical Legend and Symbols |  | BK-GNRAL-PEDCO-000-EL-DW-0001 | BK-GNRAL-PEDCO-000-EL-DW-0001 | BK | GNRAL | PEDCO | 000 | EL | DW | 0001 | F2P-707223 | AFC | IFC | 2021-08-23 | 2021-08-31 | 2021-09-04 | 8 | 4 | 12 | IFA | 2021-09-19 | 2021-09-19 | 2021-09-20 | 0 | 1 | 1 | AFC | 2021-12-22 | 2021-12-17 | 2021-12-18 | -5 | 1 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 | 2021-12-08 |  | D02 | AFC | T-0318 | 44538 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320829 | 44547 | 1400/09/26 | 44548 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0038 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-ELE-00-01386 | 44431 | 1400/06/01 | CM-C2 | [6 empty] | 1400/2294/180348 | 2021-08-31 | 1400/06/09 | 44443 | 1400/06/13 | AP | [10 empty] | D01 | IFA | T-0077 | 44444 | 1400/06/14 |  |  |  | BK-SUR-ENG-ELE-00-01508 | 44452 | 1400/06/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0001_D00 | [5 empty] | 1400-2294-204414 | 44458 | 1400/06/28 | 44459 | 1400/06/29 | AP | [10 empty] | D02 | AFC | T-0318 | 44538 | 1400/09/17 | [13 empty] | 1400-2294-320829 | 44547 | 1400/09/26 | 44548 | 1400/09/27 | AP
1 | 2 | 0 | 9 | 0 | 3 | 2 | 1.2.9.3.2 | BK-GNRAL-PEDCO-000-EL-DW-0002 | Typical Installation Details & Notes For Earthing and Lightning Protection System |  | BK-GNRAL-PEDCO-000-EL-DW-0002 | BK-GNRAL-PEDCO-000-EL-DW-0002 | BK | GNRAL | PEDCO | 000 | EL | DW | 0002 | F2P-707224 | IFI | IFI | 2021-09-08 | 2021-09-13 | 2021-09-18 | 5 | 5 | 10 | IFI | 2021-10-16 | 2021-10-14 | 2021-10-18 | -2 | 4 | 2 | IFI | 2021-11-13 | 2021-11-14 | 2021-11-21 | 1 | 7 | 8 | IFI | 2021-12-12 | 2021-12-09 | 2021-12-11 | -3 | 2 | -1 | FI | 2022-11-08 | 2022-11-15 | 2022-11-19 | 7 | 4 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-25 | 2022-10-25 |  | D04 | FI | T-1551 | 44859 | 1401/08/03 | T-1551 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06116 | 44872 | 1401/08/16 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-312906 | 44880 | 1401/08/24 | 44884 | 1401/08/28 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0066 | 2021-08-25 | 1400/06/03 |  |  |  | BK-SUR-ENG-ELE-00-01447 | 44440 | 1400/06/10 | CM-C2 | [6 empty] | 1400-2294-197234 | 2021-09-13 | 1400/06/22 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFI | T-0129 | 44471 | 1400/07/10 |  |  |  | BK-SUR-ENG-ELE-00-01713 | 44481 | 1400/07/20 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0002-D00 | [5 empty] | 1400-2294-234294 | 44483 | 1400/07/22 | 44487 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0002-D00 | [9 empty] | D02 | IFI | T-0192 | 44499 | 1400/08/08 |  |  |  | BK-SUR-ENG-ELE-00-01899 | 44503 | 1400/08/12 | AP | [6 empty] | 1400-2294-275278 | 44514 | 1400/08/23 | 44521 | 1400/08/30 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D01 | [9 empty] | D03 | IFI | T-0280 | 44528 | 1400/09/07 |  |  |  | BK-SUR-ENG-ELE-01-06116 | 44872 | 1401/08/16 | AP | [6 empty] | 1400-2294-310950 | 44539 | 1400/09/18 | 44541 | 1400/09/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0002-D03 | [9 empty] | D04 | FI | T-1551 | 44859 | 1401/08/03 | T-1551 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06116 | 44872 | 1401/08/16 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004_D02 | [5 empty] | 1401-2294-312906 | 44880 | 1401/08/24 | 44884 | 1401/08/28 | AP
1 | 2 | 0 | 9 | 0 | 3 | 3 | 1.2.9.3.3 | BK-GNRAL-PEDCO-000-EL-DW-0003 | Typical Installation Details & Notes For Lighting System |  | BK-GNRAL-PEDCO-000-EL-DW-0003 | BK-GNRAL-PEDCO-000-EL-DW-0003 | BK | GNRAL | PEDCO | 000 | EL | DW | 0003 | F2P-707225 | IFI | IFI | 2021-09-08 | 2021-09-13 | 2021-09-18 | 5 | 5 | 10 | IFI | 2021-11-08 | 2021-11-07 | 2021-11-07 | -1 | 0 | -1 | FI | 2022-11-09 | 2022-11-19 | 2022-11-21 | 10 | 2 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-25 | 2022-10-26 |  | D02 | FI | T-1557 | 44860 | 1401/08/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-06137 | 44873 | 1401/08/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318131 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0066 | 2021-08-25 | 1400/06/03 |  |  |  | BK-SUR-ENG-ELE-00-01447 | 44440 | 1400/06/10 | CM-C2 | [6 empty] | 1400-2294-197234 | 2021-09-13 | 1400/06/22 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFI | T-0182 | 44494 | 1400/08/03 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0003-D00 | [5 empty] | 1400-2294-263872 | 44507 | 1400/08/16 | 44507 | 1400/08/16 | AP | NISOC- CRS-BK-GNRAL-PEDCO-000-EL-DW-0003-D00 | [9 empty] | D02 | FI | T-1557 | 44860 | 1401/08/04 |  |  |  | BK-SUR-ENG-ELE-01-06137 | 44873 | 1401/08/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0003_D01 | [5 empty] | 1401-2294-318131 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | AP
1 | 2 | 0 | 9 | 0 | 3 | 4 | 1.2.9.3.4 | BK-GNRAL-PEDCO-000-EL-DW-0004 | Typical Installation Details & Notes For Power System |  | BK-GNRAL-PEDCO-000-EL-DW-0004 | BK-GNRAL-PEDCO-000-EL-DW-0004 | BK | GNRAL | PEDCO | 000 | EL | DW | 0004 | F2P-707226 | IFI | IFI | 2021-09-08 | 2021-09-13 | 2021-09-18 | 5 | 5 | 10 | IFI | 2021-11-09 | 2021-11-09 | 2021-11-14 | 0 | 5 | 5 | IFI | 2021-12-12 | 2021-12-09 | 2021-12-11 | -3 | 2 | -1 | FI | 2022-11-08 | 2022-11-15 | 2022-11-19 | 7 | 4 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-25 | 2022-10-25 |  | D03 | FI | T-1551 | 44859 | 1401/08/03 | T-1551 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-312906 | 44880 | 1401/08/24 | 44884 | 1401/08/28 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0066 | 2021-08-25 | 1400/06/03 |  |  |  | BK-SUR-ENG-ELE-00-01447 | 44440 | 1400/06/10 | CM-C2 | [6 empty] | 1400-2294-197234 | 2021-09-13 | 1400/06/22 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFI | T-0187 | 44495 | 1400/08/04 |  |  |  | BK-SUR-ENG-ELE-00-01899 | 44514 | 1400/08/23 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D00 | [5 empty] | 1400-2294-269297 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D00 | [9 empty] | D02 | IFI | T-0280 | 44528 | 1400/09/07 |  |  |  | BK-SUR-ENG-ELE-00-02138 | 44529 | 1400/09/08 | CM- | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D01 | [5 empty] | 1400-2294-310950 | 44539 | 1400/09/18 | 44541 | 1400/09/20 | AP | NISCO_CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D01 | [9 empty] | D03 | FI | T-1551 | 44859 | 1401/08/03 | T-1551 | 44859 | 1401/08/03 | [10 empty] | 1401-2294-312906 | 44880 | 1401/08/24 | 44884 | 1401/08/28 | AP
1 | 2 | 0 | 9 | 0 | 3 | 5 | 1.2.9.3.5 | BK-GNRAL-PEDCO-000-EL-DW-0005 | Installation Details & Notes For Cathodic Protection Systems |  | BK-GNRAL-PEDCO-000-EL-DW-0005 | BK-GNRAL-PEDCO-000-EL-DW-0005 | BK | GNRAL | PEDCO | 000 | EL | DW | 0005 | F2P-707227 | AFC | IFC | 2021-09-08 | 2021-09-13 | 2021-09-18 | 5 | 5 | 10 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFC | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-25 |  |  | D02 | AFC | T-0586 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0066 | 2021-08-25 | 1400/06/03 |  |  |  | BK-SUR-ENG-ELE-00-01447 | 44440 | 1400/06/10 | CM-C2 | [6 empty] | 1400-2294-197234 | 2021-09-13 | 1400/06/22 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0116 | 44464 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 44472 | 1400/07/11 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0005_D00 | [5 empty] | 1400-2294-232456 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0005_D00 | [9 empty] | D02 | AFC | T-0586 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 44614 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 44625 | 1400/12/14 | 44621 | 1400/12/10 | CM
1 | 2 | 0 | 10 | 0 | 0 | 0 | 1.2.10 |  | Intercom. & Telecomm.
1 | 2 | 0 | 10 | 0 | 1 | 0 | 1.2.10.1 |  | Basis/Criteria
1 | 2 | 0 | 10 | 0 | 1 | 1 | 1.2.10.1.1 | BK-GNRAL-PEDCO-000-TE-DC-0001 | Telecom. Design Criteria |  | BK-GNRAL-PEDCO-000-TE-DC-0001 | BK-GNRAL-PEDCO-000-TE-DC-0001 | BK | GNRAL | PEDCO | 000 | TE | DC | 0001 | F0Z-707228 | AFD | IFC | 2021-08-11 | 2021-09-12 | 2021-09-14 | 32 | 2 | 34 | IFA | 2021-10-09 | 2021-10-09 | 2021-10-12 | 0 | 3 | 3 | IFA | 2021-11-13 | 2021-11-19 | 2021-11-28 | 6 | 9 | 15 | AFD | 2021-12-21 | 2021-12-17 | 2021-12-18 | -4 | 1 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2021-12-07 |  | D03 | AFD | T-0305 | 44537 | 1400/09/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320827 | 44547 | 1400/09/26 | 44548 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0019 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-TEL-00-01305 | 44418 | 1400/05/19 | CM-C3 | [6 empty] | 1400/2294/194238 | 2021-09-12 | 1400/06/21 | 44453 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0117 | 44464 | 1400/07/03 |  |  |  | BK-SUR-ENG-INS-00-01711 | 44480 | 1400/07/19 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-DC-0001_D00 | [5 empty] | 1400-2290-227453 | 44478 | 1400/07/17 | 44481 | 1400/07/20 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-DC-0001_D00 | [9 empty] | D02 | IFA | T-0193 | 44499 | 1400/08/08 | [13 empty] | 1400-2294-281433 | 44519 | 1400/08/27 | 44528 | 1400/09/07 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-DC-0001_D01 | [9 empty] | D03 | AFD | T-0305 | 44537 | 1400/09/16 | [13 empty] | 1400-2294-320827 | 44547 | 1400/09/26 | 44548 | 1400/09/27 | AP
1 | 2 | 0 | 10 | 0 | 2 | 0 | 1.2.10.2 |  | Specification
1 | 2 | 0 | 10 | 0 | 2 | 1 | 1.2.10.2.1 | BK-GNRAL-PEDCO-000-TE-SP-0001 | Specification For CCTV |  | BK-GNRAL-PEDCO-000-TE-SP-0001 | [8 empty] | - | [50 empty] | Moved to IN | 2021-08-10 |  |  | D00 | IFC | T-0042 | 44418 | 1400/05/19 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-01364 | 44430 | 1400/05/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-191906 | 44448 | 1400/06/18 | 44453 | 1400/06/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0042 | 2021-08-10 | 1400/05/19 |  |  |  | BK-SUR-ENG-TEL-00-01364 | 44430 | 1400/05/31 | AP | [6 empty] | 1400-2294-191906 | 2021-09-09 | 1400/06/18 | 44453 | 1400/06/23 | CM
1 | 2 | 0 | 10 | 0 | 2 | 2 | 1.2.10.2.2 | BK-GNRAL-PEDCO-000-TE-SP-0002 | Specification For PABX |  | BK-GNRAL-PEDCO-000-TE-SP-0002 | BK-GNRAL-PEDCO-000-TE-SP-0002 | BK | GNRAL | PEDCO | 000 | TE | SP | 0002 | F0Z-707229 | AFD | IFC | 2021-08-18 | 2021-09-12 | 2021-09-14 | 25 | 2 | 27 | IFA | 2021-10-09 | 2021-10-09 | 2021-10-12 | 0 | 3 | 3 | AFD | 2021-12-21 | 2021-12-17 | 2021-12-18 | -4 | 1 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-04 | 2021-12-07 |  | D02 | AFD | T-0305 | 44537 | 1400/09/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320827 | 44547 | 1400/09/26 | 44548 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0027 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-TEL-00-01301 | 44418 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/194252 | 2021-09-12 | 1400/06/21 | 44453 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0117 | 44464 | 1400/07/03 |  |  |  | BK-SUR-ENG-INS-00-01711 | 44480 | 1400/07/19 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0002_D00 | [5 empty] | 1400-2290-227453 | 44478 | 1400/07/17 | 44481 | 1400/07/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0002_D00 | [9 empty] | D02 | AFD | T-0305 | 44537 | 1400/09/16 | [13 empty] | 1400-2294-320827 | 44547 | 1400/09/26 | 44548 | 1400/09/27 | AP
1 | 2 | 0 | 10 | 0 | 2 | 3 | 1.2.10.2.3 | BK-GNRAL-PEDCO-000-TE-SP-0003 | Specification For PAGA |  | BK-GNRAL-PEDCO-000-TE-SP-0003 | BK-GNRAL-PEDCO-000-TE-SP-0003 | BK | GNRAL | PEDCO | 000 | TE | SP | 0003 | F0Z-707230 | AFD | IFC | 2021-08-18 | 2021-09-12 | 2021-09-14 | 25 | 2 | 27 | IFA | 2021-10-05 | 2021-10-06 | 2021-10-10 | 1 | 4 | 5 | IFA | 2021-11-15 | 2021-12-28 | 2021-12-05 | 43 | -23 | 20 | IFA | 2022-01-30 | 2022-01-26 | 2022-01-31 | -4 | 5 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-04 |  |  | D03 | IFA | T-0468 | 44577 | 1400/10/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-383927 | 44587 | 1400/11/06 | 44592 | 1400/11/11 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0027 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-TEL-00-01301 | 44418 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/194252 | 2021-09-12 | 1400/06/21 | 44453 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0112 | 44460 | 1400/06/30 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D00 | [5 empty] | 1400-2290-223856 | 44475 | 1400/07/14 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D00 | [9 empty] | D02 | IFA | T-0200 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-TEL-00-02390 | 44551 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2290-294875 | 44558 | 1400/09/07 | 44535 | 1400/09/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D01 | [9 empty] | D03 | IFA | T-0468 | 44577 | 1400/10/26 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D02 | [5 empty] | 1400-2294-383927 | 44587 | 1400/11/06 | 44592 | 1400/11/11 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D02
1 | 2 | 0 | 10 | 0 | 2 | 4 | 1.2.10.2.4 | BK-GNRAL-PEDCO-000-TE-SP-0004 | Specification For Radio |  | BK-GNRAL-PEDCO-000-TE-SP-0004 | BK-GNRAL-PEDCO-000-TE-SP-0004 | BK | GNRAL | PEDCO | 000 | TE | SP | 0004 | F0Z-707231 | AFD | IFC | 2021-08-18 | 2021-09-14 | 2021-09-19 | 27 | 5 | 32 | IFA | 2021-10-16 | 2021-10-10 | 2021-12-29 | -6 | 80 | 74 | AFD | 2022-03-08 | 2022-03-06 | 2022-03-01 | -2 | -5 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-04 | 2022-02-22 |  | D02 | AFD | T-0626 | 44614 | 1400/12/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430786 | 44626 | 1400/12/15 | 44621 | 1400/12/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0031 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-TEL-00-01302 | 44418 | 1400/05/19 | CM-C2 | [6 empty] | 1400-2294-198551 | 2021-09-14 | 1400/06/23 | 44458 | 1400/06/28 | CM | [10 empty] | D01 | IFA | T-0128 | 44471 | 1400/07/10 |  |  |  | BK-SUR-ENG-TEL-00-02388 | 44551 | 1400/09/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0004_D00 | [5 empty] | 1400-2290-227505 | 44479 | 1400/07/18 | 44559 | 1400/10/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0004_D00 | [9 empty] | D02 | AFD | T-0626 | 44614 | 1400/12/03 | [13 empty] | 1400-2294-430786 | 44626 | 1400/12/15 | 44621 | 1400/12/10 | AP
1 | 2 | 0 | 10 | 0 | 2 | 5 | 1.2.10.2.5 | BK-GNRAL-PEDCO-000-TE-SP-0005 | Specification For Telecommunication Tower |  | BK-GNRAL-PEDCO-000-TE-SP-0005 | BK-GNRAL-PEDCO-000-TE-SP-0005 | BK | GNRAL | PEDCO | 000 | TE | SP | 0005 | F0Z-707232 | AFD | IFC | 2021-08-18 | 2021-09-14 | 2021-09-19 | 27 | 5 | 32 | IFA | 2021-10-24 | 2021-11-13 | 2021-11-15 | 20 | 2 | 22 | IFA | 2022-03-09 | 2022-03-06 | 2022-03-01 | -3 | -5 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-04 |  |  | D02 | IFA | T-0635 | 44615 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-03219 | 44618 | 1400/12/07 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430784 | 44626 | 1400/11/15 | 44621 | 1400/11/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0031 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-TEL-00-01302 | 44418 | 1400/05/19 | CM-C2 | [6 empty] | 1400-2294-198551 | 2021-09-14 | 1400/06/23 | 44458 | 1400/06/28 | CM | [10 empty] | D01 | IFA | T-0142 | 44479 | 1400/07/18 |  |  |  | BK-SUR-ENG-TEL-00-02389 | 44551 | 1400/09/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0005-D00 | [5 empty] | 1400-2294-273260 | 44513 | 1400/08/22 | 44515 | 1400/08/24 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0005-D00 | [9 empty] | D02 | IFA | T-0635 | 44615 | 1400/12/04 |  |  |  | BK-SUR-ENG-TEL-00-03219 | 44618 | 1400/12/07 | AP | [6 empty] | 1400-2294-430784 | 44626 | 1400/11/15 | 44621 | 1400/11/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0005_D01
1 | 2 | 0 | 10 | 0 | 2 | 6 | 1.2.10.2.6 | BK-GNRAL-PEDCO-000-TE-SP-0006 | Specification For Telecom. Cable |  | BK-GNRAL-PEDCO-000-TE-SP-0006 | BK-GNRAL-PEDCO-000-TE-SP-0006 | BK | GNRAL | PEDCO | 000 | TE | SP | 0006 | F0Z-707233 | AFD | IFC | 2021-08-23 | 2021-09-12 | 2021-09-14 | 20 | 2 | 22 | IFA | 2021-10-04 | 2021-10-06 | 2021-10-10 | 2 | 4 | 6 | IFA | 2021-11-13 | 2021-11-19 | 2021-11-28 | 6 | 9 | 15 | AFD | 2021-12-22 | 2021-12-17 | 2021-12-18 | -5 | 1 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 | 2021-12-08 |  | D03 | AFD | T-0323 | 44538 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320823 | 44547 | 1400/09/26 | 44548 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0037 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-TEL-00-01363 | 44430 | 1400/05/31 | CM-C2 | [6 empty] | 1400/2294/194247 | 2021-09-12 | 1400/06/21 | 44453 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0107 | 44459 | 1400/06/29 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0006_D00 |  |  |  |  | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0006_D00 | 1400-2290-223858 | 44475 | 1400/07/14 | 44479 | 1400/07/18 | CM | [10 empty] | D02 | IFA | T-0193 | 44499 | 1400/08/08 | [13 empty] | 1400-2294-281433 | 44519 | 1400/08/27 | 44528 | 1400/09/07 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0006_D01 | [9 empty] | D03 | AFD | T-0323 | 44538 | 1400/09/17 | [13 empty] | 1400-2294-320823 | 44547 | 1400/09/26 | 44548 | 1400/09/27 | AP
1 | 2 | 0 | 10 | 0 | 3 | 0 | 1.2.10.3 |  | Drawing/Diagram
1 | 2 | 0 | 10 | 0 | 3 | 1 | 1.2.10.3.1 | BK-GNRAL-PEDCO-000-TE-DW-0001 | Telecom Systems Legend and Symbols |  | BK-GNRAL-PEDCO-000-TE-DW-0001 | BK-GNRAL-PEDCO-000-TE-DW-0001 | BK | GNRAL | PEDCO | 000 | TE | DW | 0001 | F2T-707234 | AFC | IFC | 2021-08-15 | 2021-09-12 | 2022-04-19 | 28 | 219 | 247 | IFA | 2022-10-04 | 0 | 0 | -44838 | 0 | -44838 | 0 | 1900-01-13 | 2022-10-11 | 2022-10-12 | 44831 | 1 | 44832 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-01 |  |  | D01 | IFA | T-1422 | 44824 | 1401/06/29 | 0 | 0 | 0 | BK-SUR-ENG-TEL-01-05734 | 44825 | 1401/06/30 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0025 | 2021-08-01 | 1400/05/10 |  |  |  | BK-SUR-ENG-TEL-00-01300 | 44418 | 1400/05/19 | AP | [6 empty] | 1400-2294-194346 | 2021-09-12 | 1400/06/21 | 44670 | 1401/01/30 | CM | [10 empty] | D01 | IFA | T-1422 | 44824 | 1401/06/29 |  |  |  | BK-SUR-ENG-TEL-01-05734 | 44825 | 1401/06/30 | CM-C3 | [12 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-DW-0001_D00 | [27 empty] | 1401-2294-257251 | 44845 | 1401/07/19 | 44846 | 1401/07/20 | AP
1 | 2 | 0 | 10 | 0 | 3 | 2 | 1.2.10.3.2 | BK-GNRAL-PEDCO-000-TE-DW-0002 | Telecom Typical Installation Details & Notes |  | BK-GNRAL-PEDCO-000-TE-DW-0002 | BK-GNRAL-PEDCO-000-TE-DW-0002 | BK | GNRAL | PEDCO | 000 | TE | DW | 0002 | F2T-707235 | IFI | IFI | 2021-08-15 | 2021-09-12 | 2022-04-19 | 28 | 219 | 247 | IFI | 2022-10-05 | 2022-10-11 | 2022-10-18 | 6 | 7 | 13 | FI | 2022-11-08 | 2022-11-19 | 2022-11-20 | 11 | 1 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-01 | 2022-10-25 |  | D02 | FI | T-1554 | 44859 | 1401/08/03 | T-1554 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-312907 | 44884 | 1401/08/28 | 44885 | 1401/08/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0025 | 2021-08-01 | 1400/05/10 |  |  |  | BK-SUR-ENG-TEL-00-01300 | 44418 | 1400/05/19 | CM-C2 | [6 empty] | 1400-2294-194346 | 2021-09-12 | 1400/06/21 | 44670 | 1401/01/30 | CM | [10 empty] | D01 | IFI | T-1430 | 44825 | 1401/06/30 |  |  |  | BK-SUR-ENG-TEL-01-05745 | 44828 | 1401/07/02 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-DW-0002_D00 | [5 empty] | 1401-2294-258367 | 44845 | 1401/07/19 | 44852 | 1401/07/25 | AP | NISOC-CRS-BK-GNRAL-NISOC-000-TE-DW-0002_D00 | [9 empty] | D02 | FI | T-1554 | 44859 | 1401/08/03 | T-1554 | 44859 | 1401/08/03 | [10 empty] | 1401-2294-312907 | 44884 | 1401/08/28 | 44885 | 1401/08/29
1 | 2 | 0 | 10 | 0 | 3 | 3 | 1.2.10.3.3 | BK-GNRAL-PEDCO-000-TE-DW-0003 | CCTV Typical Installation Details & Notes |  | BK-GNRAL-PEDCO-000-TE-DW-0003 | [8 empty] | - | [50 empty] | Moved to IN | 0 |  |  | D00 | IFI | T-0052 | 44430 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-01360 | 44430 | 1400/05/31 | AP | 0 | BK-SUR-ENG-TEL-00-01488 | 44450 | 1400/06/20 | AP | 0 | 1400-2294-170637 | 44431 | 1400/06/01 | 44450 | 1400/06/20 | RJ | 0 | 1400-2294-191906 | 44448 | 1400/06/18 | 0 | 0 | CM | 0 | 0 |  | D00 | IFI | T-0052 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-TEL-00-01360 | 44430 | 1400/05/31 | AP |  | BK-SUR-ENG-TEL-00-01488 | 44450 | 1400/06/20 | AP |  | 1400-2294-170637 | 2021-08-23 | 1400/06/01 | 44450 | 1400/06/20 | RJ |  | 1400-2294-191906 | 44448 | 1400/06/18 |  |  | CM
1 | 2 | 0 | 11 | 0 | 0 | 0 | 1.2.11 |  | Architecture
1 | 2 | 0 | 11 | 0 | 1 | 0 | 1.2.11.1 |  | Basis/Criteria
1 | 2 | 0 | 11 | 0 | 1 | 1 | 1.2.11.1.1 | BK-GNRAL-PEDCO-000-AR-DC-0001 | Architectural Design Criteria |  | BK-GNRAL-PEDCO-000-AR-DC-0001 | BK-GNRAL-PEDCO-000-AR-DC-0001 | BK | GNRAL | PEDCO | 000 | AR | DC | 0001 | F0Z-707236 | AFD | IFC | 2022-02-22 | 2022-02-13 | 2022-02-13 | -9 | 0 | -9 | IFA | 2022-06-12 | 2022-06-06 | 2022-06-08 | -6 | 2 | -4 | AFD | 2022-08-13 | 2022-08-15 | 2022-08-21 | 2 | 6 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-08 | 2022-07-30 |  | D02 | AFD | T-1212 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-05334 | 44775 | 1401/05/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-178874 | 44788 | 1401/05/24 | 44794 | 1401/05/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0566 | 2022-02-08 | 1400/11/19 |  |  |  | BK-SUR-ENG-ARC-00-03120 | 44611 | 1400/11/30 | CM-C2 | [6 empty] | 1400-2294-407460 | 2022-02-13 | 1400/11/24 | 44605 | 1400/11/24 | CM | [10 empty] | D01 | IFA | T-1020 | 44710 | 1401/03/08 | T-1020 | 44710 | 1401/03/08 | BK-SUR-ENG-ARC-01-04582 | 44719 | 1401/03/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-AR-DC-0001_D00 | [5 empty] | 1401-2294-88552 | 44718 | 1401/03/16 | 44720 | 1401/03/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-AR-DC-0001_D00 | [9 empty] | D02 | AFD | T-1212 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-ARC-01-05334 | 44775 | 1401/05/11 | AP | [6 empty] | 1401-2294-178874 | 44788 | 1401/05/24 | 44794 | 1401/05/30 | AP
1 | 2 | 0 | 11 | 0 | 2 | 0 | 1.2.11.2 |  | Specification
1 | 2 | 0 | 11 | 0 | 2 | 1 | 1.2.11.2.1 | BK-GNRAL-PEDCO-000-AR-SP-0001 | Buildings General Specification |  | BK-GNRAL-PEDCO-000-AR-SP-0001 | BK-GNRAL-PEDCO-000-AR-SP-0001 | BK | GNRAL | PEDCO | 000 | AR | SP | 0001 | F0Z-707237 | AFD | IFC | 2022-04-20 | 2022-04-11 | 2022-04-12 | -9 | 1 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-06 |  |  | D00 | IFC | T-0781 | 44657 | 1401/01/17 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-03874 | 44664 | 1401/01/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16799 | 44662 | 1401/01/21 | 44663 | 1401/01/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0781 | 2022-04-06 | 1401/01/17 |  |  |  | BK-SUR-ENG-ARC-01-03874 | 44664 | 1401/01/24 | CM-C2 | [6 empty] | 1401-2294-16799 | 2022-04-11 | 1401/01/21 | 44663 | 1401/01/23 | CM
1 | 2 | 0 | 11 | 0 | 3 | 0 | 1.2.11.3 |  | Drawing/Diagram
1 | 2 | 0 | 11 | 0 | 3 | 1 | 1.2.11.3.1 | BK-GNRAL-PEDCO-000-AR-DW-0001 | Standard Drawing for Architectural Details |  | BK-GNRAL-PEDCO-000-AR-DW-0001 | BK-GNRAL-PEDCO-000-AR-DW-0001 | BK | GNRAL | PEDCO | 000 | AR | DW | 0001 | F4B-707238 | AFC | IFC | 2022-01-01 | 2021-12-23 | 2022-01-01 | -9 | 9 | 0 | AFC | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-18 | 2022-10-22 |  | D01 | AFC | T-1525 | 44856 | 1401/07/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-AR-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0360 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-ARC-00-02489 | 44562 | 1400/10/01 | CM-C2 | [6 empty] | 1400-2294-331872 | 2021-12-23 | 1400/10/02 | 44562 | 1400/10/11 | AP | [10 empty] | D01 | AFC | T-1525 | 44856 | 1401/07/30 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-AR-DW-0001_D00
1 | 2 | 0 | 12 | 0 | 0 | 0 | 1.2.12 |  | Civil
1 | 2 | 0 | 12 | 0 | 1 | 0 | 1.2.12.1 |  | Basis/Criteria
1 | 2 | 0 | 12 | 0 | 1 | 1 | 1.2.12.1.1 | BK-GNRAL-PEDCO-000-CV-DC-0001 | Civil Design Criteria |  | BK-GNRAL-PEDCO-000-CV-DC-0001 | BK-GNRAL-PEDCO-000-CV-DC-0001 | BK | GNRAL | PEDCO | 000 | CV | DC | 0001 | F0Z-707239 | AFD | IFC | 2022-02-27 | 2022-02-16 | 2022-02-16 | -11 | 0 | -11 | IFA | 2022-09-10 | 2022-09-07 | 2022-09-12 | -3 | 5 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D01 | IFA | T-1316 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05566 | 44804 | 1401/06/09 | CM-C2 | PEDCO-BK-GNRAL-PEDCO-000-CV-DC-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-210124 | 44811 | 1401/06/12 | 44816 | 1401/06/21 | RJ | NISOC-BK-GNRAL-PEDCO-000-CV-DC-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0589 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-CIV-00-0320 | 44615 | 1400/11/24 | RJ-C4 | [6 empty] | 1400-2294-4130901 | 2022-02-16 | 1400/11/27 | 44608 | 1400/11/27 | RJ | [10 empty] | D01 | IFA | T-1316 | 44800 | 1401/06/05 |  |  |  | BK-SUR-ENG-CIV-01-05566 | 44804 | 1401/06/09 | CM-C2 | PEDCO-BK-GNRAL-PEDCO-000-CV-DC-0001_D00 | [5 empty] | 1401-2294-210124 | 44811 | 1401/06/12 | 44816 | 1401/06/21 | RJ | NISOC-BK-GNRAL-PEDCO-000-CV-DC-0001_D00
1 | 2 | 0 | 12 | 0 | 1 | 2 | 1.2.12.1.2 | BK-GNRAL-PEDCO-000-CV-DC-0002 | Design Criteria for Sewerage & Drainage |  | BK-GNRAL-PEDCO-000-CV-DC-0002 | BK-GNRAL-PEDCO-000-CV-DC-0002 | BK | GNRAL | PEDCO | 000 | CV | DC | 0002 | F0Z-707240 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 12 | 0 | 2 | 0 | 1.2.12.2 |  | Specification
1 | 2 | 0 | 12 | 0 | 2 | 1 | 1.2.12.2.1 | BK-GNRAL-PEDCO-000-CV-SP-0001 | Specification For Civil Works |  | BK-GNRAL-PEDCO-000-CV-SP-0001 | [8 empty] | F0Z-707241 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 12 | 0 | 2 | 2 | 1.2.12.2.2 | BK-GNRAL-PEDCO-000-CV-SP-0002 | Specification For Road & Paving |  | BK-GNRAL-PEDCO-000-CV-SP-0002 | BK-GNRAL-PEDCO-000-CV-SP-0002 | BK | GNRAL | PEDCO | 000 | CV | SP | 0002 | F0Z-707242 | AFD | IFC | 2021-08-23 | 2021-08-22 | 2021-09-04 | -1 | 13 | 12 | IFA | 2022-03-19 | 2022-03-12 | 2022-03-14 | -7 | 2 | -5 | IFA | 2022-04-17 | 2022-04-07 | 2022-04-10 | -10 | 3 | -7 | AFD | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 | 2022-05-22 |  | D03 | AFD | T-0981 | 44703 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0040 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-CIV-00-01343 | 44425 | 1400/05/26 | CM-C3 | [6 empty] | 1400-2294-167232 | 2021-08-22 | 1400/05/31 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0671 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-CIV-00-03480 | 44633 | 1400/12/22 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0002_D01 | [5 empty] | 1400-2294-445103 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0002_D01 | [9 empty] | D02 | IFA | T-0769 | 44654 | 1401/01/14 |  |  |  | BK-SUR-ENG-CIV-01-05948 | 44856 | 1401/07/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0002_D01 | [5 empty] | 1401-2294-13815 | 44658 | 1401/01/18 | 44661 | 1401/01/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0002_D01 | [9 empty] | D03 | AFD | T-0981 | 44703 | 1401/03/01
1 | 2 | 0 | 12 | 0 | 2 | 3 | 1.2.12.2.3 | BK-GNRAL-PEDCO-000-CV-SP-0003 | Specification For Fence & Gate |  | BK-GNRAL-PEDCO-000-CV-SP-0003 | BK-GNRAL-PEDCO-000-CV-SP-0003 | BK | GNRAL | PEDCO | 000 | CV | SP | 0003 | F0Z-707243 | AFD | IFC | 2021-10-02 | 2021-09-20 | 2021-09-25 | -12 | 5 | -7 | IFA | 2021-11-02 | 2021-10-25 | 2021-11-22 | -8 | 28 | 20 | AFD | 2022-01-09 | 2021-12-29 | 2022-01-02 | -11 | 4 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-18 | 2021-12-26 |  | D02 | AFD | T-0382 | 44556 | 1400/10/05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-341743 | 44559 | 1400/10/08 | 44563 | 1400/10/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0098 | 2021-09-18 | 1400/06/27 |  |  |  | BK-SUR-ENG-CIV-00-01597 | 44464 | 1400/07/03 | CM-C2 | [6 empty] | 1400-2294-209491 | 2021-09-20 | 1400/06/31 | 44464 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0172 | 44488 | 1400/07/27 |  |  |  | BK-SUR-ENG-CIV-00-01875 | 44500 | 1400/08/08 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0003-D00 | [5 empty] | 1400-2294-247798 | 44494 | 1400/08/03 | 44522 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0003-D00 | [9 empty] | D02 | AFD | T-0382 | 44556 | 1400/10/05 | [13 empty] | 1400-2294-341743 | 44559 | 1400/10/08 | 44563 | 1400/10/12 | AP
1 | 2 | 0 | 12 | 0 | 2 | 4 | 1.2.12.2.4 | BK-GNRAL-PEDCO-000-CV-SP-0004 | Specification For Earth Work |  | BK-GNRAL-PEDCO-000-CV-SP-0004 | BK-GNRAL-PEDCO-000-CV-SP-0004 | BK | GNRAL | PEDCO | 000 | CV | SP | 0004 | F0Z-707244 | AFD | IFC | 2021-08-23 | 2021-08-22 | 2021-09-04 | -1 | 13 | 12 | IFA | 2022-03-19 | 2022-03-12 | 2022-03-14 | -7 | 2 | -5 | IFA | 2022-04-26 | 2022-04-16 | 2022-04-18 | -10 | 2 | -8 | AFD | 2022-05-09 | 2022-04-30 | 2022-05-02 | -9 | 2 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 | 2022-04-25 |  | D03 | AFD | T-0860 | 44676 | 1401/02/06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45391 | 44681 | 1401/02/`10 | 44683 | 1401/02/`12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0040 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-CIV-00-01343 | 44425 | 1400/05/26 | CM-C3 | [6 empty] | 1400-2294-167232 | 2021-08-22 | 1400/05/31 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0671 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-CIV-00-03480 | 44633 | 1400/12/22 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0004_D01 | [5 empty] | 1400-2294-445103 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0005_D01 | [9 empty] | D02 | IFA | T-0810 | 44663 | 1401/01/23 |  |  |  | BK-SUR-ENG-CIV-01-03977 | 44669 | 1401/01/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0004_D01 | [5 empty] | 1401-2294-23983 | 44667 | 1401/01/27 | 44669 | 1401/01/29 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0004_D01 | [9 empty] | D03 | AFD | T-0860 | 44676 | 1401/02/06 | [13 empty] | 1401-2294-45391 | 44681 | 1401/02/`10 | 44683 | 1401/02/`12 | AP
1 | 2 | 0 | 12 | 0 | 2 | 5 | 1.2.12.2.5 | BK-GNRAL-PEDCO-000-CV-SP-0005 | Specification For Sewerage & Drainage |  | BK-GNRAL-PEDCO-000-CV-SP-0005 | BK-GNRAL-PEDCO-000-CV-SP-0005 | BK | GNRAL | PEDCO | 000 | CV | SP | 0005 | F0Z-707245 | AFD | IFC | 2021-08-23 | 2021-08-22 | 2021-09-04 | -1 | 13 | 12 | IFA | 2022-03-12 | 2022-03-02 | 2022-03-05 | -10 | 3 | -7 | AFD | 2022-03-26 | 2022-03-15 | 2022-03-25 | -11 | 10 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-09 | 2022-03-12 |  | D02 | AFD | T-0717 | 44632 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03512 | 44633 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449833 | 44635 | 1400/12/24 | 44645 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0040 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-CIV-00-01343 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400-2294-167232 | 2021-08-22 | 1400/05/31 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0643 | 44618 | 1400/12/07 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0005_D00 | [5 empty] | 1400-2294-431005 | 44622 | 1400/12/11 | 44625 | 1400/12/15 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0005_D00 | [9 empty] | D02 | AFD | T-0717 | 44632 | 1400/12/21 |  |  |  | BK-SUR-ENG-CIV-00-03512 | 44633 | 1400/12/22 | AP | [6 empty] | 1400-2294-449833 | 44635 | 1400/12/24 | 44645 | 1401/01/08 | AP
1 | 2 | 0 | 12 | 0 | 2 | 6 | 1.2.12.2.6 | BK-GNRAL-PEDCO-000-CV-SP-0006 | Specification For Geological & Geotechnical Survey |  | BK-GNRAL-PEDCO-000-CV-SP-0006 | BK-GNRAL-PEDCO-000-CV-SP-0006 | BK | GNRAL | PEDCO | 000 | CV | SP | 0006 | F0Z-707246 | AFD | IFC | 2022-04-09 | 2022-04-01 | 2022-04-06 | -8 | 5 | -3 | IFA | 2022-05-22 | 2022-05-11 | 2022-05-16 | -11 | 5 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-26 |  |  | D01 | IFA | T-0910 | 44689 | 1401/02/18 | T-0910 | 44689 | 1401/02/18 | BK-SUR-ENG-CIV-01-04381 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59411 | 44692 | 1401/02/21 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0735 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-CIV-01-03740 | 44656 | 1401/01/16 | CM-C2 | [6 empty] | 1401-2294-7284 | 2022-04-01 | 1401/01/14 | 44657 | 1401/01/17 | CM | [10 empty] | D01 | IFA | T-0910 | 44689 | 1401/02/18 | T-0910 | 44689 | 1401/02/18 | BK-SUR-ENG-CIV-01-04381 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0006_D00 | [5 empty] | 1401-2294-59411 | 44692 | 1401/02/21 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0006_D00
1 | 2 | 0 | 12 | 0 | 3 | 0 | 1.2.12.3 |  | Drawing/Diagram
1 | 2 | 0 | 12 | 0 | 3 | 1 | 1.2.12.3.1 | BK-GNRAL-PEDCO-000-CV-DW-0001 | Standard Drawing For Civil Works |  | BK-GNRAL-PEDCO-000-CV-DW-0001 | [8 empty] | F4S-707247 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 12 | 0 | 3 | 2 | 1.2.12.3.2 | BK-GNRAL-PEDCO-000-CV-DW-0002 | Standard Drawing For Slope Protection Details |  | BK-GNRAL-PEDCO-000-CV-DW-0002 | BK-GNRAL-PEDCO-000-CV-DW-0002 | BK | GNRAL | PEDCO | 000 | CV | DW | 0002 | F4S-707248 | AFC | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | IFA | 2022-08-16 | 0 | 0 | -44789 | 0 | -44789 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFA | T-1186 | 44775 | 1401/05/11 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05345 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 44443 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-1186 | 44775 | 1401/05/11 |  |  |  | BK-SUR-ENG-CIV-01-05345 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0002_D00 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0002_D00
1 | 2 | 0 | 12 | 0 | 3 | 3 | 1.2.12.3.3 | BK-GNRAL-PEDCO-000-CV-DW-0003 | Standard Drawing For Roads |  | BK-GNRAL-PEDCO-000-CV-DW-0003 | BK-GNRAL-PEDCO-000-CV-DW-0003 | BK | GNRAL | PEDCO | 000 | CV | DW | 0003 | F4S-707249 | AFC | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | IFA | 2022-01-23 | 2022-01-11 | 2022-01-15 | -12 | 4 | -8 | IFA | 2022-04-27 | 2022-04-19 | 2022-04-26 | -8 | 7 | -1 | AFC | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 | 2022-05-21 |  | D03 | AFC | T-0976 | 44702 | 1401/02/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 44443 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0441 | 44570 | 1400/10/19 |  |  |  | BK-SUR-ENG-CIV-00-02684 | 44576 | 1400/10/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003-D00 | [5 empty] | 1400-2294-360424 | 44572 | 1400/10/21 | 44576 | 1400/10/25 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003-D00 | [9 empty] | D02 | IFA | T-0814 | 44664 | 1401/01/24 |  |  |  | BK-SUR-ENG-CIV-01-04064 | 44677 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003_D01 | [5 empty] | 1401-2294-31389 | 44670 | 1401/01/30 | 44677 | 1401/02/06 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003_D01 | [9 empty] | D03 | AFC | T-0976 | 44702 | 1401/02/31 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003_D02
1 | 2 | 0 | 12 | 0 | 3 | 4 | 1.2.12.3.4 | BK-GNRAL-PEDCO-000-CV-DW-0004 | Standard Drawing For Electrical Cable Trench |  | BK-GNRAL-PEDCO-000-CV-DW-0004 | BK-GNRAL-PEDCO-000-CV-DW-0004 | BK | GNRAL | PEDCO | 000 | CV | DW | 0004 | F4S-707250 | IFI | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | IFA | 2022-10-25 | 2022-10-30 | 2022-10-31 | 5 | 1 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFA | T-1485 | 44845 | 1401/07/19 | T-1485 | 44845 | 1401/07/19 | BK-SUR-ENG-CIV-01-05940 | 44856 | 1401/07/30 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285894 | 44864 | 1401/08/08 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 44443 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-1485 | 44845 | 1401/07/19 | T-1485 | 44845 | 1401/07/19 | BK-SUR-ENG-CIV-01-05940 | 44856 | 1401/07/30 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0004_D00 | [5 empty] | 1401-2294-285894 | 44864 | 1401/08/08 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0004_D00
1 | 2 | 0 | 12 | 0 | 3 | 5 | 1.2.12.3.5 | BK-GNRAL-PEDCO-000-CV-DW-0005 | Standard Drawing For Manholes |  | BK-GNRAL-PEDCO-000-CV-DW-0005 | BK-GNRAL-PEDCO-000-CV-DW-0005 | BK | GNRAL | PEDCO | 000 | CV | DW | 0005 | F4S-707251 | AFC | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | IFA | 2022-01-25 | 2021-01-15 | 2022-01-16 | -375 | 366 | -9 | IFA | 2022-09-07 | 2022-09-07 | 2022-09-13 | 0 | 6 | 6 | IFA | 2022-11-02 | 2022-11-05 | 2022-11-06 | 3 | 1 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D03 | IFA | T-1515 | 44853 | 1401/07/27 | T-1516 | 44853 | 1401/07/27 | BK-SUR-ENG-CIV-01-06038 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296586 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 44443 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0448 | 44572 | 1400/10/20 |  |  |  | BK-SUR-ENG-CIV-00-02699 | 44577 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005-D00 | [5 empty] | 1400-2294-364648 | 44211 | 1400/10/25 | 44577 | 1400/10/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005-D00 | [9 empty] | D02 | IFA | T-1312 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-CIV-01-05564 | 44804 | 1401/06/09 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005_D01 | [5 empty] | 1401-2294-210047 | 44811 | 1401/06/13 | 44817 | 1401/06/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005_D01 | [9 empty] | D03 | IFA | T-1515 | 44853 | 1401/07/27 | T-1516 | 44853 | 1401/07/27 | BK-SUR-ENG-CIV-01-06038 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005_D02 | [5 empty] | 1401-2294-296586 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005_D02
1 | 2 | 0 | 12 | 0 | 3 | 6 | 1.2.12.3.6 | BK-GNRAL-PEDCO-000-CV-DW-0006 | Standard Drawing For Catch Basins |  | BK-GNRAL-PEDCO-000-CV-DW-0006 | BK-GNRAL-PEDCO-000-CV-DW-0006 | BK | GNRAL | PEDCO | 000 | CV | DW | 0006 | F4S-707252 | AFC | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | IFA | 2022-01-25 | 2021-01-15 | 2022-01-16 | -375 | 366 | -9 | IFA | 2022-09-07 | 2022-09-07 | 2022-09-13 | 0 | 6 | 6 | IFA | 2022-11-07 | 2022-11-05 | 2022-11-06 | -2 | 1 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D03 | IFA | T-1540 | 44858 | 1401/08/02 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05996 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296557 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 44443 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0448 | 44572 | 1400/10/20 |  |  |  | BK-SUR-ENG-CIV-00-02699 | 44577 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006-D00 | [5 empty] | 1400-2294-364648 | 44211 | 1400/10/25 | 44577 | 1400/10/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006-D00 | [9 empty] | D02 | IFA | T-1312 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-CIV-01-05564 | 44804 | 1401/06/09 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006_D01 | [5 empty] | 1401-2294-210047 | 44811 | 1401/06/13 | 44817 | 1401/06/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006_D01 | [9 empty] | D03 | IFA | T-1540 | 44858 | 1401/08/02 |  |  |  | BK-SUR-ENG-CIV-01-05996 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006_D03 | [5 empty] | 1401-2294-296557 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006_D03
1 | 2 | 0 | 12 | 0 | 3 | 7 | 1.2.12.3.7 | BK-GNRAL-PEDCO-000-CV-DW-0007 | Standard Drawing For Sewerage & Drainage Details |  | BK-GNRAL-PEDCO-000-CV-DW-0007 | BK-GNRAL-PEDCO-000-CV-DW-0007 | BK | GNRAL | PEDCO | 000 | CV | DW | 0007 | F4S-707253 | AFC | IFC | 2022-02-16 | 2022-02-08 | 2022-02-13 | -8 | 5 | -3 | IFA | 2022-05-29 | 2022-05-21 | 2022-05-29 | -8 | 8 | 0 | AFC | 2022-07-31 | 0 | 0 | -44773 | 0 | -44773 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-02 | 2022-07-17 |  | D02 | AFC | T-1167 | 44759 | 1401/04/26 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05223 | 44766 | 1401/05/02 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0547 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-CIV-00-02953 | 44598 | 1400/11/17 | CM-C2 | [6 empty] | 1400-2294-402785 | 2022-02-08 | 1400/11/19 | 44605 | 1400/11/24 | CM | [10 empty] | D01 | IFA | T-0948 | 44696 | 1401/02/25 | T-0948 | 44696 | 1401/02/25 | BK-SUR-ENG-CIV-01-04469 | 44710 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0007_D00 | [5 empty] | 1401-2294-69915 | 44702 | 1401/02/31 | 44710 | 1401/03/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0007_D00 | [9 empty] | D02 | AFC | T-1167 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-CIV-01-05223 | 44766 | 1401/05/02 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0007_D01
1 | 2 | 0 | 12 | 0 | 3 | 8 | 1.2.12.3.8 | BK-GNRAL-PEDCO-000-CV-DW-0008 | Standard Drawing For Civil Underground Crossings |  | BK-GNRAL-PEDCO-000-CV-DW-0008 | BK-GNRAL-PEDCO-000-CV-DW-0008 | BK | GNRAL | PEDCO | 000 | CV | DW | 0008 | F4S-707254 | AFC | IFC | 2022-02-21 | 2022-02-13 | 2022-02-13 | -8 | 0 | -8 | IFA | 2022-08-02 | 2022-07-28 | 2022-08-01 | -5 | 4 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-07 |  |  | D01 | IFA | T-1170 | 44761 | 1401/04/28 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05238 | 44768 | 1401/05/04 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0008_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156948 | 44770 | 1401/05/06 | 44774 | 1401/05/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0560 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-CIV-00-03076 | 44608 | 1400/11/27 | CM-C2 | [6 empty] | 1400-2294-407467 | 2022-02-13 | 1400/11/24 | 44605 | 1400/11/24 | CM | [10 empty] | D01 | IFA | T-1170 | 44761 | 1401/04/28 |  |  |  | BK-SUR-ENG-CIV-01-05238 | 44768 | 1401/05/04 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0008_D00 | [5 empty] | 1401-2294-156948 | 44770 | 1401/05/06 | 44774 | 1401/05/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0008_D00
1 | 2 | 0 | 12 | 0 | 3 | 9 | 1.2.12.3.9 | BK-GNRAL-PEDCO-000-CV-DW-0009 | Standard Drawing For Fence & Gate Details |  | BK-GNRAL-PEDCO-000-CV-DW-0009 | BK-GNRAL-PEDCO-000-CV-DW-0009 | BK | GNRAL | PEDCO | 000 | CV | DW | 0009 | F4S-707255 | AFC | IFC | 2021-10-02 | 2021-09-22 | 2021-09-25 | -10 | 3 | -7 | IFA | 2021-11-02 | 2021-10-25 | 2021-11-22 | -8 | 28 | 20 | IFA | 2022-02-06 | 2022-01-26 | 2022-01-29 | -11 | 3 | -8 | AFC | 2022-03-14 | 2022-03-19 | 2022-03-27 | 5 | 8 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-18 | 2022-02-28 |  | D03 | AFC | T-0655 | 44620 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03560 | 44634 | 1400/12/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-454970 | 44639 | 1400/12/28 | 44647 | 1401/01/07 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0099 | 2021-09-18 | 1400/06/27 |  |  |  | BK-SUR-ENG-CIV-00-01599 | 44464 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-209547 | 2021-09-22 | 1400/06/31 | 44464 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0172 | 44488 | 1400/07/27 |  |  |  | BK-SUR-ENG-CIV-00-01875 | 44500 | 1400/08/08 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009-D00 | [5 empty] | 1400-2294-247798 | 44494 | 1400/08/03 | 44522 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009-D00 | [9 empty] | D02 | IFA | T-0492 | 44584 | 1400/11/03 |  |  |  | BK-SUR-ENG-CIV-00-02844 | 44590 | 1400/11/09 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009_D01 | [5 empty] | 1400-2294-383930 | 44587 | 1400/11/06 | 44590 | 1400/11/09 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009_D01 | [9 empty] | D03 | AFC | T-0655 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-ARC-00-03560 | 44634 | 1400/12/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009_D02 | [5 empty] | 1400-2294-454970 | 44639 | 1400/12/28 | 44647 | 1401/01/07 | AP
1 | 2 | 0 | 12 | 0 | 3 | 10 | 1.2.12.3.10 | BK-GNRAL-PEDCO-000-CV-DW-0010 | Standard Drawing For Concrete Continues Weight |  | BK-GNRAL-PEDCO-000-CV-DW-0010 | [8 empty] | F4S-707256 | IFI | IFI | 2021-08-22 | 2021-08-14 | 0 | -8 | -44422 | -44430 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | T-0035 | 44416 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 44422 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 11 | 1.2.12.3.11 | BK-GNRAL-PEDCO-000-CV-DW-0012 | Standard Drawing For Major Floodway Crossing |  | BK-GNRAL-PEDCO-000-CV-DW-0012 | [8 empty] | F4S-707257 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 12 | 0 | 3 | 12 | 1.2.12.3.12 | BK-GNRAL-PEDCO-000-CV-DW-0014 | Standard Drawing For Culvert & Details |  | BK-GNRAL-PEDCO-000-CV-DW-0014 | BK-GNRAL-PEDCO-000-CV-DW-0014 | BK | GNRAL | PEDCO | 000 | CV | DW | 0014 | F4S-707261 | AFC | IFC | 2021-10-09 | 2021-10-02 | 2021-10-09 | -7 | 7 | 0 | IFA | 2021-11-20 | 2021-11-08 | 0 | -12 | -44508 | -44520 | AFC | 2021-11-29 | 2021-11-18 | 2021-11-21 | -11 | 3 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-25 | 2021-11-15 |  | D02 | AFC | T-0244 | 44515 | 1400/08/24 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-02054 | 44521 | 1400/08/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-281432 | 44518 | 1400/08/27 | 44521 | 1400/08/30 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0119 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-CIV-00-01677 | 44473 | 1400/07/12 | CM-C2 | [6 empty] | 1400-2294-219939 | 2021-10-02 | 1400/07/10 | 44478 | 1400/07/17 | CM | [10 empty] | D01 | IFA | T-0204 | 44506 | 1400/08/015 |  |  |  | BK-SUR-ENG-CIV-00-01920 | 44506 | 1400/08/15 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D00 | [5 empty] | 1400-2294-267473 | 44508 | 1400/08/17 |  |  | AP | NISOCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D00 | [9 empty] | D02 | AFC | T-0244 | 44515 | 1400/08/24 |  |  |  | BK-SUR-ENG-CIV-00-02054 | 44521 | 1400/08/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D01 | [5 empty] | 1400-2294-281432 | 44518 | 1400/08/27 | 44521 | 1400/08/30 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D01
1 | 2 | 0 | 12 | 0 | 3 | 13 | 1.2.12.3.13 | BK-GNRAL-PEDCO-000-CV-DW-0016 | Standard Drawing For Valve Box |  | BK-GNRAL-PEDCO-000-CV-DW-0016 | BK-GNRAL-PEDCO-000-CV-DW-0016 | BK | GNRAL | PEDCO | 000 | CV | DW | 0016 | F4S-707258 | IFI | IFI | 2022-01-26 | 2022-01-17 | 2022-01-19 | -9 | 2 | -7 | IFI | 2022-09-12 | 2022-09-11 | 2022-09-13 | -1 | 2 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-12 |  |  | D01 | IFI | T-1339 | 44802 | 1401/06/07 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05626 | 44814 | 1401/06/19 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0016_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-220426 | 44815 | 1401/06/20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0455 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-CIV-00-02714 | 44578 | 1400/10/26 | CM-C2 | [6 empty] | 1400-2294-368537 | 2022-01-17 | 1400/10/27 | 44580 | 1400/10/29 | CM | [10 empty] | D01 | IFI | T-1339 | 44802 | 1401/06/07 |  |  |  | BK-SUR-ENG-CIV-01-05626 | 44814 | 1401/06/19 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0016_D00 | [5 empty] | 1401-2294-220426 | 44815 | 1401/06/20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0016_D00
1 | 2 | 0 | 12 | 0 | 3 | 14 | 1.2.12.3.14 | BK-GNRAL-PEDCO-000-CV-DW-0018 | Standard Drawing For Fire Hydrant PAD |  | BK-GNRAL-PEDCO-000-CV-DW-0018 | BK-GNRAL-PEDCO-000-CV-DW-0018 | BK | GNRAL | PEDCO | 000 | CV | DW | 0018 | F4S-707259 | AFC | IFC | 2022-03-27 | 2022-03-16 | 2022-03-25 | -11 | 9 | -2 | IFA | 2022-05-14 | 2022-05-08 | 2022-05-11 | -6 | 3 | -3 | IFA | 2022-09-05 | 2022-09-04 | 2022-09-12 | -1 | 8 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-13 |  |  | D02 | IFA | T-1298 | 44795 | 1401/05/31 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05551 | 44802 | 1401/06/07 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018-D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-210052 | 44808 | 1401/06/13 | 44816 | 1401/06/21 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0725 | 2022-03-13 | 1400/12/22 |  |  |  | BK-SUR-ENG-CIV-00-03623 | 44636 | 1400/12/25 | CM-C2 | [6 empty] | 1400-2294-452344 | 2022-03-16 | 1400/12/25 | 44645 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0874 | 44681 | 1401/02/10 | T-0874 | 44681 | 1401/02/10 | BK-SUR-ENG-CIV-01-04277 | 44696 | 1401/02/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018-D00 | [5 empty] | 1401-2294-52735 | 44689 | 1401/02/18 | 44692 | 1401/02/21 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018_D00 | [9 empty] | D02 | IFA | T-1298 | 44795 | 1401/05/31 |  |  |  | BK-SUR-ENG-CIV-01-05551 | 44802 | 1401/06/07 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018-D01 | [5 empty] | 1401-2294-210052 | 44808 | 1401/06/13 | 44816 | 1401/06/21 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018_D01
1 | 2 | 0 | 12 | 0 | 3 | 15 | 1.2.12.3.15 | BK-GNRAL-PEDCO-000-CV-DW-0020 | Standard Drawing For Cable Pull Pit |  | BK-GNRAL-PEDCO-000-CV-DW-0020 | BK-GNRAL-PEDCO-000-CV-DW-0020 | BK | GNRAL | PEDCO | 000 | CV | DW | 0020 | F4S-707260 | AFC | IFC | 2022-04-25 | 2022-04-13 | 2022-04-17 | -12 | 4 | -8 | AFC | 2022-06-25 | 0 | 0 | -44737 | 0 | -44737 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-11 | 2022-06-11 |  | D01 | AFC | T-1052 | 44723 | 1401/03/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0020_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0803 | 2022-04-11 | 1401/01/22 |  |  |  | BK-SUR-ENG-CIV-01-03944 | 44668 | 1401/01/28 | CM-C2 | [6 empty] | 1401-2294-22847 | 2022-04-13 | 1401/01/24 | 44668 | 1401/01/28 | AP | [10 empty] | D01 | AFC | T-1052 | 44723 | 1401/03/21 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0020_D00
1 | 2 | 0 | 12 | 0 | 3 | 16 | 1.2.12.3.16 | BK-GNRAL-PEDCO-000-CV-DW-0035 | Standard Drawing For Pavings |  | BK-GNRAL-PEDCO-000-CV-DW-0035 | BK-GNRAL-PEDCO-000-CV-DW-0035 | BK | GNRAL | PEDCO | 000 | CV | DW | 0035 | F4S-707262 | AFC | IFC | 2022-01-22 | 2022-01-11 | 2022-01-15 | -11 | 4 | -7 | IFA | 2022-05-03 | 2022-09-28 | 2022-10-17 | 148 | 19 | 167 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-08 |  |  | D01 | IFA | T-0845 | 44670 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04051 | 44676 | 1401/02/05 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0035_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-38346 | 44832 | 1401/07/06 | 44851 | 1401/07/25 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0035_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0439 | 2022-01-08 | 1400/10/18 |  |  |  | BK-SUR-ENG-CIV-00-02716 | 44578 | 1400/10/27 | CM-C3 | [6 empty] | 1400-2294-359208 | 2022-01-11 | 1400/10/21 | 44576 | 1400/10/25 | CM | [10 empty] | D01 | IFA | T-0845 | 44670 | 1401/01/30 |  |  |  | BK-SUR-ENG-CIV-01-04051 | 44676 | 1401/02/05 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0035_D00 | [5 empty] | 1401-2294-38346 | 44832 | 1401/07/06 | 44851 | 1401/07/25 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0035_D00
1 | 2 | 0 | 12 | 0 | 3 | 17 | 1.2.12.3.17 | BK-GNRAL-PEDCO-000-CV-DW-0037 | Standard Drawing For Earth Pit |  | BK-GNRAL-PEDCO-000-CV-DW-0037 | BK-GNRAL-PEDCO-000-CV-DW-0037 | BK | GNRAL | PEDCO | 000 | CV | DW | 0037 | F4S-707263 | AFC | IFC | 2022-02-27 | 2022-02-19 | 2022-02-20 | -8 | 1 | -7 | IFA | 2022-08-07 | 2022-08-02 | 2022-08-09 | -5 | 7 | 2 | AFC | 2022-08-27 | 2022-08-31 | 2022-08-28 | 4 | -3 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 | 2022-08-13 |  | D02 | AFC | T-1270 | 44786 | 1401/05/22 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05460 | 44789 | 1401/05/25 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0037_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-197260 | 44804 | 1401/06/09 | 44801 | 1401/06/06 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0592 | 2022-02-13 | 1400/11/23 |  |  |  | BK-SUR-ENG-CIV-00-03115 | 44611 | 1400/11/30 | CM-C2 | [6 empty] | 1400-2294-413792 | 2022-02-19 | 1400/11/30 | 44612 | 1400/12/01 | CM | [10 empty] | D01 | IFA | T-1185 | 44766 | 1401/05/02 |  |  |  | BK-SUR-ENG-CIV-01-05343 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0037_D00 | [5 empty] | 1401-2294-164809 | 44775 | 1401/05/11 | 44782 | 1401/05/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0037_D00 | [9 empty] | D02 | AFC | T-1270 | 44786 | 1401/05/22 |  |  |  | BK-SUR-ENG-CIV-01-05460 | 44789 | 1401/05/25 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0037_D01 | [5 empty] | 1401-2294-197260 | 44804 | 1401/06/09 | 44801 | 1401/06/06 | AP
1 | 2 | 0 | 12 | 0 | 3 | 18 | 1.2.12.3.18 | BK-GNRAL-PEDCO-000-CV-DW-0039 | Standard Drawing For Pipe Bedding |  | BK-GNRAL-PEDCO-000-CV-DW-0039 | BK-GNRAL-PEDCO-000-CV-DW-0039 | BK | GNRAL | PEDCO | 000 | CV | DW | 0039 | F4S-707264 | AFC | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | IFA | 2022-08-16 | 0 | 0 | -44789 | 0 | -44789 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFA | T-1186 | 44775 | 1401/05/11 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05345 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0039_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0039_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 44443 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-1186 | 44775 | 1401/05/11 |  |  |  | BK-SUR-ENG-CIV-01-05345 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0039_D00 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0039_D00
1 | 2 | 0 | 12 | 0 | 3 | 19 | 1.2.12.3.19 | BK-GNRAL-PEDCO-000-CV-DW-0040 | Standard Details of Miscellaneous Items |  | BK-GNRAL-PEDCO-000-CV-DW-0040 | BK-GNRAL-PEDCO-000-CV-DW-0040 | BK | GNRAL | PEDCO | 000 | CV | DW | 0040 | F4S-707265 | AFC | IFC | 2022-03-20 | 2022-03-10 | 2022-03-12 | -10 | 2 | -8 | AFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-06 | 2022-05-22 |  | D01 | AFC | T-0981 | 44703 | 1401/03/01 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05948 | 44856 | 1401/07/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0040_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0679 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-CIV-00-03448 | 44632 | 1400/12/21 | CM-C2 | [6 empty] | 1400-2294-443244 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | AP | [10 empty] | D01 | AFC | T-0981 | 44703 | 1401/03/01 |  |  |  | BK-SUR-ENG-CIV-01-05948 | 44856 | 1401/07/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0040_D00
1 | 2 | 0 | 12 | 0 | 3 | 20 | 1.2.12.3.20 | BK-GNRAL-PEDCO-000-CV-DW-0025 | Typical Drawing For A/G Pipeline Road Crossing |  | BK-GNRAL-PEDCO-000-CV-DW-0025 | [8 empty] | - | [50 empty] | Deleted | 0 |  |  | D00 | IFI | T-0035 | 44416 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 44422 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 21 | 1.2.12.3.21 | BK-GNRAL-PEDCO-000-CV-DW-0027 | Pipeline Typical Drawing For Irish Crossing |  | BK-GNRAL-PEDCO-000-CV-DW-0027 | [8 empty] | - | [50 empty] | Deleted | 0 |  |  | D00 | IFI | T-0035 | 44416 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 44422 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 22 | 1.2.12.3.22 | BK-GNRAL-PEDCO-000-CV-DW-0028 | Pipeline Typical Drawing For Water - Way Crossing |  | BK-GNRAL-PEDCO-000-CV-DW-0028 | [8 empty] | - | [50 empty] | Deleted | 0 |  |  | D00 | IFI | T-0035 | 44416 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 44422 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 23 | 1.2.12.3.23 | BK-GNRAL-PEDCO-000-CV-DW-0029 | Pipeline Typical Drawing For Pig Signaller Concrete Pit |  | BK-GNRAL-PEDCO-000-CV-DW-0029 | [8 empty] | - | [50 empty] | Deleted | 0 |  |  | D00 | IFI | T-0035 | 44416 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 44422 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 24 | 1.2.12.3.24 | BK-GNRAL-PEDCO-000-CV-DW-0030 | Pipeline Typical Drawing For H-Pipe Support |  | BK-GNRAL-PEDCO-000-CV-DW-0030 | [8 empty] | - | [50 empty] | Deleted | 0 |  |  | D00 | IFI | T-0035 | 44416 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 44422 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 25 | 1.2.12.3.25 | BK-GNRAL-PEDCO-000-CV-DW-0031 | Pipeline Typical Drawing For Vent Valve Pre-cast Concrete Box |  | BK-GNRAL-PEDCO-000-CV-DW-0031 | [8 empty] | - | [50 empty] | Deleted | 0 |  |  | D00 | IFI | T-0035 | 44416 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 44422 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 44427 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 26 | 1.2.12.3.26 | BK-GNRAL-PEDCO-000-CV-DW-0038 | Standard Detail curbed Stone Bounded Area |  | BK-GNRAL-PEDCO-000-CV-DW-0038 | [8 empty] | - | [50 empty] | Deleted | 0 |  |  | D00 | IFI | T-0061 | 44430 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01408 | 44433 | 1400/06/03 | RJ-C4 | PEDCO-CRS- BK-SUR-ENG-CIV-00-01408 | 0 | 0 | 0 | 0 | 0 | 1400-2294-170684 | 44432 | 1400/06/02 | 44443 | 1400/06/13 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0061 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01408 | 44433 | 1400/06/03 | RJ-C4 | PEDCO-CRS- BK-SUR-ENG-CIV-00-01408 | [5 empty] | 1400-2294-170684 | 2021-08-24 | 1400/06/02 | 44443 | 1400/06/13 | RJ
[8 empty] | BK-GNRAL-PEDCO-220-CV-PY-0002 | Sanitary System & Potable Water Layout For Camp Area |  | BK-GNRAL-PEDCO-220-CV-PY-0002 | BK-GNRAL-PEDCO-220-CV-PY-0002 | BK | GNRAL | PEDCO | 220 | CV | PY | 0002 | F4S-709382 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
1 | 2 | 0 | 13 | 0 | 0 | 0 | 1.2.13 |  | Structure
1 | 2 | 0 | 13 | 0 | 1 | 0 | 1.2.13.1 |  | Basis/Criteria | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 13 | 0 | 1 | 1 | 1.2.13.1.1 | BK-GNRAL-PEDCO-000-ST-DC-0001 | Structural Design Criteria | Design Criteria For Concrete Works | BK-GNRAL-PEDCO-000-ST-DC-0001 | BK-GNRAL-PEDCO-000-ST-DC-0001 | BK | GNRAL | PEDCO | 000 | ST | DC | 0001 | F0Z-707266 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
1 | 2 | 0 | 13 | 0 | 2 | 0 | 1.2.13.2 |  | Specification | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 13 | 0 | 2 | 1 | 1.2.13.2.1 | BK-GNRAL-PEDCO-000-ST-SP-0001 | Specification For Concrete Work |  | BK-GNRAL-PEDCO-000-ST-SP-0001 | BK-GNRAL-PEDCO-000-ST-SP-0001 | BK | GNRAL | PEDCO | 000 | ST | SP | 0001 | F0Z-707267 | AFD | IFC | 2021-08-28 | 2021-08-22 | 2021-09-04 | -6 | 13 | 7 | IFA | 2021-11-17 | 2021-11-09 | 2021-11-14 | -8 | 5 | -3 | IFA | 2022-05-11 | 2022-05-08 | 2022-05-11 | -3 | 3 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-14 |  |  | D02 | IFA | T-0870 | 44678 | 1401/02/07 | T-0870 | 44678 | 1401/02/07 | BK-SUR-ENG-STR-01-04139 | 44688 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52736 | 44689 | 1401/02/18 | 44692 | 1401/02/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0044 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-CIV-00-01346 | 44428 | 1400/05/29 | RJ-C4 | [6 empty] | 1400/2294/167414 | 2021-08-22 | 1400/05/31 | 44443 | 1400/06/13 | CM | [8 empty] | Binak Codes and standards proposal |  | D01 | IFA | T-0209 | 44503 | 1400/08/12 |  |  |  | BK-SUR-ENG-STR-00-01965 | 44510 | 1400/08/19 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001-D00 | [5 empty] | 1400-2294-269294 | 44509 | 1400/08/18 | 44514 | 1400/08/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001-D00 | [9 empty] | D02 | IFA | T-0870 | 44678 | 1401/02/07 | T-0870 | 44678 | 1401/02/07 | BK-SUR-ENG-STR-01-04139 | 44688 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001_D01 | [5 empty] | 1401-2294-52736 | 44689 | 1401/02/18 | 44692 | 1401/02/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001_D01
1 | 2 | 0 | 13 | 0 | 2 | 2 | 1.2.13.2.2 | BK-GNRAL-PEDCO-000-ST-SP-0002 | Specification For Storage Tank Foundation |  | BK-GNRAL-PEDCO-000-ST-SP-0002 | BK-GNRAL-PEDCO-000-ST-SP-0002 | BK | GNRAL | PEDCO | 000 | ST | SP | 0002 | F0Z-707268 | AFD | IFC | 2021-12-07 | 2021-12-05 | 2021-12-06 | -2 | 1 | -1 | IFA | 2022-02-21 | 2022-02-19 | 2022-02-12 | -2 | -7 | -9 | AFD | 2022-03-23 | 2022-03-16 | 2022-03-25 | -7 | 9 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-23 | 2022-03-09 |  | D02 | AFD | T-0711 | 44629 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03590 | 44635 | 1400/12/24 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-452371 | 44636 | 1400/12/25 | 44645 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0268 | 2021-11-23 | 1400/09/02 |  |  |  | BK-SUR-ENG-STR-00-02214 | 44536 | 1400/09/15 | CM-C3 | [6 empty] | 1400-2294-304921 | 2021-12-05 | 1400/09/14 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0557 | 44599 | 1400/11/18 |  |  |  | BK-SUR-ENG-STR-00-03111 | 44611 | 1400/11/30 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0002_D00 | [5 empty] | 1400-2294-406574 | 44611 | 1400/11/30 | 44604 | 1400/11/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0002_D00 | [9 empty] | D02 | AFD | T-0711 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-STR-00-03590 | 44635 | 1400/12/24 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0002_D01 | [5 empty] | 1400-2294-452371 | 44636 | 1400/12/25 | 44645 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 2 | 3 | 1.2.13.2.3 | BK-GNRAL-PEDCO-000-ST-SP-0003 | Specification for Fabrication of Steel Structures |  | BK-GNRAL-PEDCO-000-ST-SP-0003 | BK-GNRAL-PEDCO-000-ST-SP-0003 | BK | GNRAL | PEDCO | 000 | ST | SP | 0003 | F0Z-707269 | AFD | IFC | 2022-02-07 | 2022-01-27 | 2022-01-30 | -11 | 3 | -8 | IFA | 2022-02-27 | 2022-02-09 | 2022-02-09 | -18 | 0 | -18 | AFD | 2022-03-14 | 2022-03-12 | 2022-03-14 | -2 | 2 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-24 | 2022-02-28 |  | D02 | AFD | T-0656 | 44620 | 1400/12/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445229 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0500 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-STR-00-02867 | 44591 | 1400/11/10 | CM-C2 | [6 empty] | 1400-2294-384196 | 2022-01-27 | 1400/11/07 | 44591 | 1400/11/10 | CM | [10 empty] | D01 | IFA | T-0593 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-STR-00-03206 | 44615 | 1400/12/04 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0003_D00 | [5 empty] | 1400-2294-413120 | 44601 | 1400/11/20 | 44601 | 1400/11/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0003_D00 | [9 empty] | D02 | AFD | T-0656 | 44620 | 1400/12/09 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0003_D01 | [5 empty] | 1400-2294-445229 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP
1 | 2 | 0 | 13 | 0 | 2 | 4 | 1.2.13.2.4 | BK-GNRAL-PEDCO-000-ST-SP-0004 | Specification For Grouting |  | BK-GNRAL-PEDCO-000-ST-SP-0004 | BK-GNRAL-PEDCO-000-ST-SP-0004 | BK | GNRAL | PEDCO | 000 | ST | SP | 0004 | F0Z-707270 | AFD | IFC | 2021-08-28 | 2021-08-22 | 2021-09-04 | -6 | 13 | 7 | IFA | 2022-01-08 | 2021-12-27 | 2022-01-02 | -12 | 6 | -6 | AFD | 2022-02-01 | 2022-01-26 | 2022-01-29 | -6 | 3 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-14 | 2022-01-18 |  | D02 | AFD | T-0475 | 44579 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-02762 | 44583 | 1400/11/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-383290 | 44587 | 1400/11/06 | 44590 | 1400/11/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0050 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-CIV-00-01373 | 44430 | 1400/05/31 | CM-C2 | [6 empty] | 1400/2294/168853 | 2021-08-22 | 1400/05/31 | 44443 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0376 | 44555 | 1400/10/04 |  |  |  | BK-SUR-ENG-STR-00-02516 | 44563 | 1400/10/12 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D00 | [5 empty] | 1400-2294-336451 | 44557 | 1400/10/06 | 44563 | 1400/10/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D00 | [9 empty] | D02 | AFD | T-0475 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-STR-00-02762 | 44583 | 1400/11/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D01 | [5 empty] | 1400-2294-383290 | 44587 | 1400/11/06 | 44590 | 1400/11/09 | AP
1 | 2 | 0 | 13 | 0 | 2 | 5 | 1.2.13.2.5 | BK-GNRAL-PEDCO-000-ST-SP-0005 | Specification for Erection of Steel Structures |  | BK-GNRAL-PEDCO-000-ST-SP-0005 | BK-GNRAL-PEDCO-000-ST-SP-0005 | BK | GNRAL | PEDCO | 000 | ST | SP | 0005 | F0Z-707271 | AFD | IFC | 2022-02-07 | 2022-01-27 | 2022-02-06 | -11 | 10 | -1 | IFA | 2022-02-28 | 2022-02-16 | 2022-02-16 | -12 | 0 | -12 | AFD | 2022-03-14 | 2022-03-13 | 2022-03-26 | -1 | 13 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-24 | 2022-02-28 |  | D02 | AFD | T-0657 | 44620 | 1400/12/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-446504 | 44633 | 1400/12/22 | 44646 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0504 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-STR-00-02947 | 44598 | 1400/11/17 | CM-C2 | [6 empty] | 1400-2294-384198 | 2022-01-27 | 1400/11/07 | 44598 | 1400/11/17 | CM | [10 empty] | D01 | IFA | T-0595 | 44606 | 1400/11/25 |  |  |  | BK-SUR-ENG-STR-00-03207 | 44615 | 1400/12/04 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0005_D00 | [5 empty] | 1400-2294-413132 | 44608 | 1400/11/27 | 44608 | 1400/11/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0005_D00 | [9 empty] | D02 | AFD | T-0657 | 44620 | 1400/12/09 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0005_D01 | [5 empty] | 1400-2294-446504 | 44633 | 1400/12/22 | 44646 | 1401/01/09 | AP
1 | 2 | 0 | 13 | 0 | 2 | 6 | 1.2.13.2.6 | BK-GNRAL-PEDCO-000-ST-SP-0006 | Specification for Fireproofing |  | BK-GNRAL-PEDCO-000-ST-SP-0006 | BK-GNRAL-PEDCO-000-ST-SP-0006 | BK | GNRAL | PEDCO | 000 | ST | SP | 0006 | F0Z-707272 | AFD | IFC | 2021-10-02 | 2021-09-22 | 2021-09-25 | -10 | 3 | -7 | IFA | 2021-10-25 | 2021-10-16 | 2021-10-18 | -9 | 2 | -7 | IFA | 2021-12-29 | 2021-12-20 | 2021-12-22 | -9 | 2 | -7 | AFD | 2022-01-09 | 2021-12-29 | 2022-01-02 | -11 | 4 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-18 | 2021-12-26 |  | D03 | AFD | T-0383 | 44556 | 1400/10/05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-341664 | 44559 | 1400/10/08 | 44563 | 1400/10/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0096 | 2021-09-18 | 1400/06/27 |  |  |  | BK-SUR-ENG-STR-00-01590 | 44464 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-209486 | 2021-09-22 | 1400/06/31 | 44464 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0152 | 44480 | 1400/07/15 |  |  |  | BK-SUR-ENG-STR-00-01767 | 44487 | 1400/07/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0006_D00 | [5 empty] | 1400-2294-236248 | 44485 | 1400/07/24 | 44487 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0006_D00 | [9 empty] | D02 | IFA | T-0353 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-STR-00-02407 | 44552 | 1400/10/01 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0006_D01 | [5 empty] | 1400-2294-327398 | 44550 | 1400/09/29 | 44552 | 1400/10/01 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0006_D01 | [9 empty] | D03 | AFD | T-0383 | 44556 | 1400/10/05 | [13 empty] | 1400-2294-341664 | 44559 | 1400/10/08 | 44563 | 1400/10/12 | AP
1 | 2 | 0 | 13 | 0 | 2 | 7 | 1.2.13.2.7 | BK-GNRAL-PEDCO-000-ST-SP-0007 | Specification for Design of Blast Resistant Buildings |  | BK-GNRAL-PEDCO-000-ST-SP-0007 | BK-GNRAL-PEDCO-000-ST-SP-0007 | BK | GNRAL | PEDCO | 000 | ST | SP | 0007 | F0Z-707273 | AFD | IFC | 2021-12-26 | 2021-12-16 | 2021-12-18 | -10 | 2 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-12 |  |  | D00 | IFC | T-0327 | 44542 | 1400/09/21 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-02288 | 44545 | 1400/09/24 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320801 | 44546 | 1400/09/26 | 44548 | 1400/09/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0327 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-STR-00-02288 | 44545 | 1400/09/24 | RJ-C4 | [6 empty] | 1400-2294-320801 | 2021-12-16 | 1400/09/26 | 44548 | 1400/09/27 | CM
1 | 2 | 0 | 13 | 0 | 2 | 8 | 1.2.13.2.8 | BK-GNRAL-PEDCO-000-ST-SP-0008 | Specification For Steel Structural Works |  | BK-GNRAL-PEDCO-000-ST-SP-0008 | [8 empty] | F0Z-707274 | AFD | [50 empty] | 0
1 | 2 | 0 | 13 | 0 | 3 | 0 | 1.2.13.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 13 | 0 | 3 | 1 | 1.2.13.3.1 | BK-GNRAL-PEDCO-000-ST-DW-0001 | Standard Drawing For Fire Proofing |  | BK-GNRAL-PEDCO-000-ST-DW-0001 | BK-GNRAL-PEDCO-000-ST-DW-0001 | BK | GNRAL | PEDCO | 000 | ST | DW | 0001 | F4M-707275 | AFC | IFI | 2021-08-22 | 2021-08-15 | 2021-08-23 | -7 | 8 | 1 | IFA | 2021-10-02 | 2021-09-23 | 2021-09-28 | -9 | 5 | -4 | IFA | 2021-10-25 | 2021-10-16 | 2021-10-18 | -9 | 2 | -7 | IFA | 2022-01-08 | 2021-12-27 | 2022-01-08 | -12 | 12 | 0 | AFC | 2022-02-01 | 2022-01-20 | 2022-01-22 | -12 | 2 | -10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-08 | 2022-01-18 |  | D04 | AFC | T-0478 | 44579 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-02763 | 44583 | 1400/11/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-372847 | 44581 | 1400/10/30 | 44583 | 1400/11/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0033 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-STR-00-01317 | 44422 | 1400/05/23 | CM-C3 | [6 empty] | 1400/2294/166216 | 2021-08-15 | 1400/05/24 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0100 | 44457 | 1400/06/27 |  |  |  | BK-SUR-ENG-STR-00-01606 | 44465 | 1400/07/04 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001-D00 | [5 empty] | 1400-2294-210029 | 44462 | 1400/07/01 | 44467 | 1400/07/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001-D00 | [9 empty] | D02 | IFA | T-0148 | 44480 | 1400/07/19 |  |  |  | BK-SUR-ENG-STR-00-01764 | 44487 | 1400/07/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001-D01 | [5 empty] | 1400-2294-236278 | 44485 | 1400/07/24 | 44487 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001-D01 | [9 empty] | D03 | IFA | T-0378 | 44555 | 1400/10/04 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001_D02 | [5 empty] | 1400-2294-338026 | 44557 | 1400/10/06 | 44569 | 1400/10/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001_D02 | 1400-2294-338026 | 44557 | 1400/10/06 | 44563 | 1400/10/12 | AP |  |  |  | D04 | AFC | T-0478 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-STR-00-02763 | 44583 | 1400/11/02 | AP | [6 empty] | 1400-2294-372847 | 44581 | 1400/10/30 | 44583 | 1400/11/03 | AP
1 | 2 | 0 | 13 | 0 | 3 | 2 | 1.2.13.3.2 | BK-GNRAL-PEDCO-000-ST-DW-0002 | Standard Drawing For Anchor Bolts |  | BK-GNRAL-PEDCO-000-ST-DW-0002 | BK-GNRAL-PEDCO-000-ST-DW-0002 | BK | GNRAL | PEDCO | 000 | ST | DW | 0002 | F4Q-707276 | AFC | IFC | 2021-12-29 | 2021-12-22 | 2021-12-26 | -7 | 4 | -3 | IFA | 2022-02-16 | 2021-02-07 | 2022-02-09 | -374 | 367 | -7 | AFC | 2022-02-26 | 2022-03-12 | 2022-03-14 | 14 | 2 | 16 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-15 | 2022-02-12 |  | D02 | AFC | T-0579 | 44604 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03190 | 44614 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445199 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0352 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-STR-00-02366 | 44549 | 1400/09/28 | RJ-C4 | [6 empty] | 1400-2294-331499 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0545 | 44594 | 1400/11/13 |  |  |  | BK-SUR-ENG-STR-00-03009 | 44601 | 1400/11/20 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0002_D00 | [5 empty] | 1400-2294-400988 | 44234 | 1400/11/18 | 44601 | 1400/11/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0002_D00 | [9 empty] | D02 | AFC | T-0579 | 44604 | 1400/11/23 |  |  |  | BK-SUR-ENG-STR-00-03190 | 44614 | 1400/12/03 | AP | [6 empty] | 1400-2294-445199 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP
1 | 2 | 0 | 13 | 0 | 3 | 3 | 1.2.13.3.3 | BK-GNRAL-PEDCO-000-ST-DW-0003 | Standard Drawing For Steel Stairs |  | BK-GNRAL-PEDCO-000-ST-DW-0003 | BK-GNRAL-PEDCO-000-ST-DW-0003 | BK | GNRAL | PEDCO | 000 | ST | DW | 0003 | F4M-707277 | AFC | IFC | 2022-01-01 | 2021-12-22 | 2021-12-27 | -10 | 5 | -5 | IFA | 2022-02-16 | 2021-02-07 | 2022-02-09 | -374 | 367 | -7 | AFC | 2022-02-27 | 2022-03-14 | 2022-03-26 | 15 | 12 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-18 | 2022-02-13 |  | D02 | AFC | T-0583 | 44605 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03192 | 44614 | 1400/12/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448458 | 44634 | 1400/12/23 | 44646 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0355 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-STR-00-02409 | 44552 | 1400/10/01 | RJ-C4 | [6 empty] | 1400-2294-331510 | 2021-12-22 | 1400/10/01 | 44557 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0545 | 44594 | 1400/11/13 |  |  |  | BK-SUR-ENG-STR-00-03009 | 44601 | 1400/11/20 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0003_D00 | [5 empty] | 1400-2294-400988 | 44234 | 1400/11/18 | 44601 | 1400/11/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0003_D00 | [9 empty] | D02 | AFC | T-0583 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-STR-00-03192 | 44614 | 1400/12/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0003_D01 | [5 empty] | 1400-2294-448458 | 44634 | 1400/12/23 | 44646 | 1401/01/09 | AP
1 | 2 | 0 | 13 | 0 | 3 | 4 | 1.2.13.3.4 | BK-GNRAL-PEDCO-000-ST-DW-0005 | Standard Drawing For Operating Platform |  | BK-GNRAL-PEDCO-000-ST-DW-0005 | BK-GNRAL-PEDCO-000-ST-DW-0005 | BK | GNRAL | PEDCO | 000 | ST | DW | 0005 | F4M-707278 | AFC | IFC | 2022-01-10 | 2021-12-30 | 2022-01-02 | -11 | 3 | -8 | IFA | 2022-02-09 | 2022-01-31 | 2022-02-02 | -9 | 2 | -7 | IFA | 2022-03-09 | 2022-03-07 | 2022-02-28 | -2 | -7 | -9 | AFC | 2022-03-26 | 2022-03-16 | 2022-03-25 | -10 | 9 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-27 | 2022-03-12 |  | D03 | AFC | T-0719 | 44632 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03509 | 44632 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-452397 | 44636 | 1400/12/25 | 44645 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0387 | 2021-12-27 | 1400/10/06 |  |  |  | BK-SUR-ENG-STR-00-02603 | 44569 | 1400/10/18 | CM-C2 | [6 empty] | 1400-2294-342106 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0514 | 44587 | 1400/11/06 |  |  |  | BK-SUR-ENG-STR-00-02917 | 44594 | 1400/11/13 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D00 | [5 empty] | 1400-2294-390694 | 44592 | 1400/11/11 | 44594 | 1400/11/13 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D00 | [9 empty] | D02 | IFA | T-0630 | 44615 | 1400/12/04 |  |  |  | BK-SUR-ENG-STR-00-03384 | 44627 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D01 | [5 empty] | 1400-2294-430111 | 44627 | 1400/12/17 | 44620 | 1400/12/09 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D01 | [9 empty] | D03 | AFC | T-0719 | 44632 | 1400/12/21 |  |  |  | BK-SUR-ENG-STR-00-03509 | 44632 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D02 | [5 empty] | 1400-2294-452397 | 44636 | 1400/12/25 | 44645 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 3 | 5 | 1.2.13.3.5 | BK-GNRAL-PEDCO-000-ST-DW-0006 | Standard Drawing For Handrail |  | BK-GNRAL-PEDCO-000-ST-DW-0006 | BK-GNRAL-PEDCO-000-ST-DW-0006 | BK | GNRAL | PEDCO | 000 | ST | DW | 0006 | F4M-707279 | AFC | IFC | 2022-01-01 | 2021-12-22 | 2021-12-26 | -10 | 4 | -6 | IFA | 2022-02-07 | 2022-01-27 | 2022-01-30 | -11 | 3 | -8 | AFC | 2022-02-23 | 2022-03-12 | 2022-03-14 | 17 | 2 | 19 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-18 | 2022-02-09 |  | D02 | AFC | T-0569 | 44601 | 1400/11/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445210 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0354 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-STR-00-02408 | 44552 | 1400/10/01 | CM-C2 | [6 empty] | 1400-2294-331513 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0501 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-STR-00-02870 | 44591 | 1400/11/10 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0006_D00 | [5 empty] | 1400-2294-384202 | 44588 | 1400/11/07 | 44591 | 1400/11/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0006_D00 | [9 empty] | D02 | AFC | T-0569 | 44601 | 1400/11/20 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0006_D01 | [5 empty] | 1400-2294-445210 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP
1 | 2 | 0 | 13 | 0 | 3 | 6 | 1.2.13.3.6 | BK-GNRAL-PEDCO-000-ST-DW-0007 | Standard Drawing For Insert Plates in Concrete |  | BK-GNRAL-PEDCO-000-ST-DW-0007 | BK-GNRAL-PEDCO-000-ST-DW-0007 | BK | GNRAL | PEDCO | 000 | ST | DW | 0007 | F4M-707280 | AFC | IFI | 2021-08-22 | 2021-08-15 | 2021-08-23 | -7 | 8 | 1 | IFA | 2022-01-12 | 2022-01-02 | 2022-01-12 | -10 | 10 | 0 | AFC | 2022-02-07 | 0 | 0 | -44599 | 0 | -44599 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-08 | 2022-01-24 |  | D02 | AFC | T-0502 | 44585 | 1400/11/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0033 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-STR-00-01317 | 44422 | 1400/05/23 | CM-C3 | [6 empty] | 1400/2294/166216 | 2021-08-15 | 1400/05/24 | 44431 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0407 | 44559 | 1400/10/08 |  |  |  | MB-SUR-ENG-STR-00-02655 | 44572 | 1400/10/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0007_D00 | [5 empty] | 1400-2294-346161 | 44563 | 1400/10/12 | 44573 | 1400/10/22 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0007_D00 | [9 empty] | D02 | AFC | T-0502 | 44585 | 1400/11/04 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0007_D01
1 | 2 | 0 | 13 | 0 | 3 | 7 | 1.2.13.3.7 | BK-GNRAL-PEDCO-000-ST-DW-0009 | Standard Details For Ladder & Safety Cage |  | BK-GNRAL-PEDCO-000-ST-DW-0009 | BK-GNRAL-PEDCO-000-ST-DW-0009 | BK | GNRAL | PEDCO | 000 | ST | DW | 0009 | F4M-707281 | AFC | IFC | 2021-12-29 | 2021-12-22 | 2021-12-26 | -7 | 4 | -3 | IFA | 2022-02-13 | 2022-02-03 | 2022-02-02 | -10 | -1 | -11 | AFC | 2022-03-02 | 2022-03-14 | 2022-03-25 | 12 | 11 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-15 | 2022-02-16 |  | D02 | AFC | T-0596 | 44608 | 1400/11/27 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03442 | 44629 | 1400/12/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0009_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448461 | 44634 | 1400/12/23 | 44645 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0352 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-STR-00-02366 | 44549 | 1400/09/28 | RJ-C4 | [6 empty] | 1400-2294-331499 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0523 | 44591 | 1400/11/10 |  |  |  | BK-SUR-ENG-STR-00-02955 | 44598 | 1400/11/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0009_D00 | [5 empty] | 1400-2294-395079 | 44595 | 1400/11/14 | 44594 | 1400/11/24 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0009_D00 | [9 empty] | D02 | AFC | T-0596 | 44608 | 1400/11/27 |  |  |  | BK-SUR-ENG-STR-00-03442 | 44629 | 1400/12/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0009_D01 | [5 empty] | 1400-2294-448461 | 44634 | 1400/12/23 | 44645 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 3 | 8 | 1.2.13.3.8 | BK-GNRAL-PEDCO-000-ST-DW-0010 | Standard Drawing For Lighting pole foundation Plan & Details |  | BK-GNRAL-PEDCO-000-ST-DW-0010 | BK-GNRAL-PEDCO-000-ST-DW-0010 | BK | GNRAL | PEDCO | 000 | ST | DW | 0010 | F4Q-707282 | AFC | IFC | 2022-02-12 | 2022-02-02 | 2022-02-13 | -10 | 11 | 1 | IFA | 2022-04-12 | 2022-04-06 | 2022-04-09 | -6 | 3 | -3 | IFA | 2022-05-22 | 2022-05-16 | 2022-05-23 | -6 | 7 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-29 |  |  | D02 | IFA | T-0911 | 44689 | 1401/02/18 | T-0911 | 44689 | 1401/02/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-63887 | 44697 | 1401/02/26 | 44704 | 1401/03/03 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0519 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-STR-00-02944 | 44598 | 1400/11/17 | CM-C2 | [6 empty] | 1400-2294-393696 | 2022-02-02 | 1400/11/13 | 44605 | 1400/11/24 | CM | [10 empty] | D01 | IFA | T-0763 | 44649 | 1401/01/09 |  |  |  | BK-SUR-ENG-STR-01-03775 | 44660 | 1401/01/20 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D00 | [5 empty] | 1401-2294-13795 | 44657 | 1401/01/17 | 44660 | 1401/01/25 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D00 | [9 empty] | D02 | IFA | T-0911 | 44689 | 1401/02/18 | T-0911 | 44689 | 1401/02/18 | [10 empty] | 1401-2294-63887 | 44697 | 1401/02/26 | 44704 | 1401/03/03 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D01
1 | 2 | 0 | 13 | 0 | 3 | 9 | 1.2.13.3.9 | BK-GNRAL-PEDCO-000-ST-DW-0011 | General Notes - Steel Structures |  | BK-GNRAL-PEDCO-000-ST-DW-0011 | BK-GNRAL-PEDCO-000-ST-DW-0011 | BK | GNRAL | PEDCO | 000 | ST | DW | 0011 | F4M-707283 | AFC | IFC | 2022-02-08 | 2022-01-27 | 2022-01-30 | -12 | 3 | -9 | IFA | 2022-02-22 | 2022-02-19 | 2022-02-12 | -3 | -7 | -10 | AFC | 2022-03-26 | 2022-03-16 | 2022-03-25 | -10 | 9 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-25 | 2022-03-12 |  | D02 | AFC | T-0719 | 44632 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03509 | 44632 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0011_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-452397 | 44636 | 1400/12/25 | 44645 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0506 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-STR-00-02871 | 44591 | 1400/11/10 | CM-C2 | [6 empty] | 1400-2294-384203 | 2022-01-27 | 1400/11/07 | 44591 | 1400/11/10 | CM | [10 empty] | D01 | IFA | T-0565 | 44600 | 1400/11/19 |  |  |  | BK-SUR-ENG-STR-00-03041 | 44605 | 1400/11/24 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0011_D00 | [5 empty] | 1400-2294-406885 | 44611 | 1400/11/30 | 44604 | 1400/11/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0011_D00 | [9 empty] | D02 | AFC | T-0719 | 44632 | 1400/12/21 |  |  |  | BK-SUR-ENG-STR-00-03509 | 44632 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0011_D01 | [5 empty] | 1400-2294-452397 | 44636 | 1400/12/25 | 44645 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 3 | 10 | 1.2.13.3.10 | BK-GNRAL-PEDCO-000-ST-DW-0012 | General Notes - Reinforced Concrete Structures |  | BK-GNRAL-PEDCO-000-ST-DW-0012 | BK-GNRAL-PEDCO-000-ST-DW-0012 | BK | GNRAL | PEDCO | 000 | ST | DW | 0012 | F4M-707284 | AFC | IFC | 2022-01-03 | 2021-12-23 | 2021-12-26 | -11 | 3 | -8 | IFA | 2022-02-14 | 2022-02-03 | 2022-02-13 | -11 | 10 | -1 | AFC | 2022-03-02 | 2022-03-14 | 2022-03-25 | 12 | 11 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-20 | 2022-02-16 |  | D02 | AFC | T-0596 | 44608 | 1400/11/27 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03442 | 44629 | 1400/12/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0012_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448461 | 44634 | 1400/12/23 | 44645 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0372 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-STR-00-02428 | 44556 | 1400/10/05 | CM-C3 | [6 empty] | 1400-2294-331871 | 2021-12-23 | 1400/10/02 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0530 | 44592 | 1400/11/11 |  |  |  | BK-SUR-ENG-STR-00-02956 | 44598 | 1400/11/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0012_D00 | [5 empty] | 1400-2294-395082 | 44595 | 1400/11/14 | 44605 | 1400/11/24 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0012_D00 | [9 empty] | D02 | AFC | T-0596 | 44608 | 1400/11/27 |  |  |  | BK-SUR-ENG-STR-00-03442 | 44629 | 1400/12/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0012_D01 | [5 empty] | 1400-2294-448461 | 44634 | 1400/12/23 | 44645 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 3 | 11 | 1.2.13.3.11 | BK-GNRAL-PEDCO-000-ST-DW-0014 | Standard Drawing For Structural Built-up Sections |  | BK-GNRAL-PEDCO-000-ST-DW-0014 | BK-GNRAL-PEDCO-000-ST-DW-0014 | BK | GNRAL | PEDCO | 000 | ST | DW | 0014 | F4M-707285 | AFC | IFC | 2021-12-18 | 2021-12-09 | 2021-12-12 | -9 | 3 | -6 | IFA | 2022-02-14 | 2022-02-07 | 2022-02-19 | -7 | 12 | 5 | IFA | 2022-05-11 | 2022-05-08 | 2022-05-08 | -3 | 0 | -3 | AFC | 2022-06-06 | 2022-05-31 | 2022-06-07 | -6 | 7 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-04 | 2022-05-23 |  | D03 | AFC | T-0994 | 44704 | 1401/03/02 | T-0994 | 44704 | 1401/03/02 | BK-SUR-ENG-STR-01-04501 | 44712 | 1401/03/10 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-85266 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0288 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-STR-00-02269 | 44542 | 1400/09/21 | CM-C2 | [6 empty] | 1400-2294-310899 | 2021-12-09 | 1400/09/18 | 44542 | 1400/09/21 | CM | [10 empty] | D01 | IFA | T-0525 | 44592 | 1400/11/11 |  |  |  | BK-SUR-ENG-STR-00-02950 | 44598 | 1400/11/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D00 | [5 empty] | 1400-2294-400912 | 44599 | 1400/11/18 | 44611 | 1400/11/30 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D00 | [9 empty] | D02 | IFA | T-0870 | 44678 | 1401/02/07 | T-0870 | 44678 | 1401/02/07 | BK-SUR-ENG-STR-01-04139 | 44688 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D01 | [5 empty] | 1401-2294-52736 | 44689 | 1401/02/18 | 44689 | 1401/02/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D01 | [9 empty] | D03 | AFC | T-0994 | 44704 | 1401/03/02 | T-0994 | 44704 | 1401/03/02 | BK-SUR-ENG-STR-01-04501 | 44712 | 1401/03/10 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D02 | [5 empty] | 1401-2294-85266 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | AP
1 | 2 | 0 | 13 | 0 | 3 | 12 | 1.2.13.3.12 | BK-GNRAL-PEDCO-000-ST-DW-0015 | Standard Drawing For Steel Flooring, Grating and Chequered Plate |  | BK-GNRAL-PEDCO-000-ST-DW-0015 | BK-GNRAL-PEDCO-000-ST-DW-0015 | BK | GNRAL | PEDCO | 000 | ST | DW | 0015 | F4M-707286 | AFC | IFC | 2022-01-19 | 2022-01-10 | 2022-01-15 | -9 | 5 | -4 | AFC | 2022-02-26 | 2022-03-12 | 2022-03-14 | 14 | 2 | 16 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-05 | 2022-02-12 |  | D01 | AFC | T-0574 | 44604 | 1400/11/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0015-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445213 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0430 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-STR-00-02683 | 44576 | 1400/10/15 | CM-C2 | [6 empty] | 1400-2294-358439 | 2022-01-10 | 1400/10/20 | 44576 | 1400/10/25 | AP | [10 empty] | D01 | AFC | T-0574 | 44604 | 1400/11/23 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0015-D00 | [5 empty] | 1400-2294-445213 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP
1 | 2 | 0 | 13 | 0 | 3 | 13 | 1.2.13.3.13 | BK-GNRAL-PEDCO-000-ST-DW-0016 | Concrete Reinforcement Shape Code |  | BK-GNRAL-PEDCO-000-ST-DW-0016 | [8 empty] | F4M-707287 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 13 | 0 | 3 | 14 | 1.2.13.3.14 | BK-GNRAL-PEDCO-000-ST-DW-0017 | Standard Drawing For Septic Tank |  | BK-GNRAL-PEDCO-000-ST-DW-0017 | BK-GNRAL-PEDCO-000-ST-DW-0017 | BK | GNRAL | PEDCO | 000 | ST | DW | 0017 | F4M-707288 | AFC | IFC | 2022-02-05 | 2022-01-27 | 2022-01-29 | -9 | 2 | -7 | IFA | 2022-03-08 | 2022-02-26 | 2022-03-08 | -10 | 10 | 0 | IFA | 2022-06-08 | 2022-06-07 | 2022-06-11 | -1 | 4 | 3 | IFA | 2022-06-28 | 2022-06-21 | 2022-06-25 | -7 | 4 | -3 | AFC | 2022-07-11 | 0 | 0 | -44753 | 0 | -44753 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-22 | 2022-06-27 |  | D04 | AFC | T-1121 | 44739 | 1401/04/06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0489 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-STR-00-02822 | 44587 | 1400/11/09 | CM-C2 | [6 empty] | 1400-2294-384171 | 2022-01-27 | 1400/11/07 | 44590 | 1400/11/09 | CM | [10 empty] | D01 | IFA | T-0625 | 44614 | 1400/12/03 |  |  |  | MB-SUR-ENG-STR-00-03355 | 44705 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D00 | [5 empty] | 1400-2294-425598 | 44618 | 1400/12/07 | 44628 | 1400/12/17 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D00 | [9 empty] | D02 | IFA | T-1006 | 44706 | 1401/03/04 | T-1006 | 44709 | 1401/03/07 | BK-SUR-ENG-STR-01-04536 | 44718 | 1401/03/16 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D01 | [5 empty] | 1401-2294-92296 | 44719 | 1401/03/17 | 44723 | 1401//03/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D01 | [9 empty] | D03 | IFA | T-1075 | 44726 | 1401/03/24 |  |  |  | BK-SUR-ENG-STR-01-04734 | 44730 | 1401/03/28 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D02 | [5 empty] | 1401-2294-111518 | 44733 | 1401/03/31 | 44737 | 1401/04/04 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D02 | [9 empty] | D04 | AFC | T-1121 | 44739 | 1401/04/06 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D03
1 | 2 | 0 | 14 | 0 | 0 | 0 | 1.2.14 |  | Risk & Environmental Assessment
1 | 2 | 0 | 14 | 1 | 0 | 0 | 1.2.14.1 |  | Environmental Assessment
1 | 2 | 0 | 14 | 1 | 1 | 0 | 1.2.14.1.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 14 | 1 | 1 | 1 | 1.2.14.1.1.1 | BK-GNRAL-HD-000-SA-HP-0001 | EPC Waste Management Plan |  | BK-GNRAL-HD-000-SA-HP-0001 | BK-GNRAL-HD-000-SA-HP-0001 | BK | GNRAL | HD | 000 | SA | HP | 0001 | F0Z-707050 | AFC | IFC | 2022-06-20 | 0 | 0 | -44732 | 0 | -44732 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-06 |  |  | D00 | IFC | T-1040 | 44718 | 1401/03/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1040 | 2022-06-06 | 1401/03/16
1 | 2 | 0 | 14 | 2 | 0 | 0 | 1.2.14.2 |  | Risk Assessment
1 | 2 | 0 | 14 | 2 | 1 | 0 | 1.2.14.2.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 14 | 2 | 1 | 1 | 1.2.14.2.1.1 | BK-GNRAL-PEDCO-000-GE-PR-0001 | HAZOP Study Procedure |  | BK-GNRAL-PEDCO-000-GE-PR-0001 | BK-GNRAL-PEDCO-000-GE-PR-0001 | BK | GNRAL | PEDCO | 000 | GE | PR | 0001 | F0Z-707289 | AFC | IFC | 2021-11-08 | 2021-12-22 | 2021-11-27 | 44 | -25 | 19 | IFA | 2021-12-20 | 2021-12-17 | 2021-12-18 | -3 | 1 | -2 | AFC | 2022-03-16 | 2022-03-12 | 2022-03-15 | -4 | 3 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-25 | 2022-03-02 |  | D02 | AFC | T-0664 | 44622 | 1400/12/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445251 | 44632 | 1400/12/21 | 44635 | 1400/12/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0183 | 2021-10-25 | 1400/08/03 | [13 empty] | 1400-2294-285014 | 2021-11-21 | 1400/08/30 | 44527 | 1400/09/06 | CM |  | 1400-2294-330830 | 44552 | 1400/10/01 |  |  | AP |  |  |  | D01 | IFA | T-0296 | 44536 | 1400/09/15 | [13 empty] | 1400-2294-320830 | 44547 | 1400/09/26 | 44548 | 1400/09/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-PR-0001_D00 | [9 empty] | D02 | AFC | T-0664 | 44622 | 1400/12/11 | [13 empty] | 1400-2294-445251 | 44632 | 1400/12/21 | 44635 | 1400/12/24 | AP
1 | 2 | 0 | 14 | 2 | 1 | 2 | 1.2.14.2.1.2 | BK-GNRAL-PEDCO-000-GE-PR-0002 | HAZID Study Procedure |  | BK-GNRAL-PEDCO-000-GE-PR-0002 | BK-GNRAL-PEDCO-000-GE-PR-0002 | BK | GNRAL | PEDCO | 000 | GE | PR | 0002 | F0Z-707290 | AFC | IFC | 2021-09-19 | 2021-09-22 | 2021-09-25 | 3 | 3 | 6 | IFA | 2021-10-17 | 2021-10-19 | 2021-10-26 | 2 | 7 | 9 | AFC | 2021-11-10 | 2021-11-01 | 2021-11-06 | -9 | 5 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-05 | 2021-10-27 |  | D02 | AFC | T-0189 | 44496 | 1400/08/05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-257495 | 44501 | 1400/08/10 | 44506 | 1400/08/15 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0078 | 2021-09-05 | 1400/06/14 | [13 empty] | 1400-2294-208400 | 2021-09-22 | 1400/06/31 | 44464 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0132 | 44472 | 1400/07/11 | [13 empty] | 1400-2294-241736 | 44488 | 1400/07/27 | 44495 | 1400/08/04 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-PR-0002_D01 | [9 empty] | D02 | AFC | T-0189 | 44496 | 1400/08/05 | [13 empty] | 1400-2294-257495 | 44501 | 1400/08/10 | 44506 | 1400/08/15 | AP
1 | 2 | 0 | 14 | 2 | 1 | 3 | 1.2.14.2.1.3 | BK-GNRAL-PEDCO-000-GE-PR-0003 | SIL Study Procedure |  | BK-GNRAL-PEDCO-000-GE-PR-0003 | BK-GNRAL-PEDCO-000-GE-PR-0003 | BK | GNRAL | PEDCO | 000 | GE | PR | 0003 | F0Z-707291 | AFC | IFC | 2021-11-08 | 2021-12-22 | 2021-11-27 | 44 | -25 | 19 | AFC | 2022-03-21 | 2022-03-12 | 2022-03-15 | -9 | 3 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-25 | 2022-03-07 |  | D01 | AFC | T-0688 | 44627 | 1400/12/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445304 | 44632 | 1400/12/21 | 44635 | 1400/12/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0183 | 2021-10-25 | 1400/08/03 | [13 empty] | 1400-2294-285014 | 2021-11-21 | 1400/08/30 | 44527 | 1400/09/06 | CM |  | 1400-2294-330830 | 44552 | 1400/10/01 |  |  | AP |  |  |  | D01 | AFC | T-0688 | 44627 | 1400/12/16 | [13 empty] | 1400-2294-445304 | 44632 | 1400/12/21 | 44635 | 1400/12/24 | AP
1 | 2 | 0 | 14 | 2 | 1 | 4 | 1.2.14.2.1.4 | BK-GNRAL-HD-000-GE-PR-0004 | Crisis Management Plan |  | BK-GNRAL-HD-000-GE-PR-0004 | BK-GNRAL-HD-000-GE-PR-0004 | BK | GNRAL | HD | 000 | GE | PR | 0004 | F0Z-707051 | AFC | IFC | 2022-06-20 | 0 | 0 | -44732 | 0 | -44732 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-06 |  |  | D00 | IFC | T-1036 | 44718 | 1401/03/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1036 | 2022-06-06 | 1401/03/16
1 | 2 | 0 | 14 | 2 | 1 | 5 | 1.2.14.2.1.5 | BK-GNRAL-HD-000-GE-PR-0005 | EPC FMEA report |  | BK-GNRAL-HD-000-GE-PR-0005 | BK-GNRAL-HD-000-GE-PR-0005 | BK | GNRAL | HD | 000 | GE | PR | 0005 | F0Z-707052 | AFC | IFC | 2022-01-11 | 0 | 0 | -44572 | 0 | -44572 | AFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-28 | 2022-05-22 |  | G01 | AFC | T-0982 | 44703 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0393 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-HSE-HSE-00-02476 | 44558 | 1400/10/06 | AP | [22 empty] | G01 | AFC | T-0982 | 44703 | 1401/03/01
1 | 2 | 0 | 14 | 2 | 1 | 6 | 1.2.14.2.1.6 | BK-GNRAL-HD-000-GE-PR-0006 | PSSR Procedure |  | BK-GNRAL-HD-000-GE-PR-0006 | BK-GNRAL-HD-000-GE-PR-0006 | BK | GNRAL | HD | 000 | GE | PR | 0006 | F0Z-707053 | AFC | IFC | 2022-06-20 | 0 | 0 | -44732 | 0 | -44732 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-06 |  |  | D00 | IFC | T-1036 | 44718 | 1401/03/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1036 | 2022-06-06 | 1401/03/16
1 | 2 | 0 | 14 | 2 | 1 | 7 | 1.2.14.2.1.7 | BK-GNRAL-PEDCO-000-GE-PR-0007 | Pigging Safety Requirement |  | BK-GNRAL-PEDCO-000-GE-PR-0007 | BK-GNRAL-PEDCO-000-GE-PR-0007 | BK | GNRAL | PEDCO | 000 | GE | PR | 0007 | F0Z-707054 | AFC | IFC | 2022-04-23 | 2022-05-10 | 2022-05-16 | 17 | 6 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-09 |  |  | D00 | IFC | T-0787 | 44660 | 1401/01/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-56285 | 44691 | 1401/02/20 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0787 | 2022-04-09 | 1401/01/20 | [13 empty] | 1401-2294-56285 | 2022-05-10 | 1401/02/20 | 44697 | 1401/02/26 | CM
1 | 2 | 0 | 15 | 0 | 0 | 0 | 1.2.15 |  | QC/QA
1 | 2 | 0 | 15 | 1 | 0 | 0 | 1.2.15.1 |  | QC Management | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 15 | 1 | 0 | 1 | 1.2.15.1.1 | BK-GNRAL-PEDCO-000-QC-PR-0001 | Project Quality Plan |  | BK-GNRAL-PEDCO-000-QC-PR-0001 | BK-GNRAL-PEDCO-000-QC-PR-0001 | BK | GNRAL | PEDCO | 000 | QC | PR | 0001 | F0Z-707299 | AFD | IFC | 2021-12-22 | 2022-03-30 | 2022-04-13 | 98 | 14 | 112 | IFA | 2022-05-28 | 2022-06-03 | 2022-06-11 | 6 | 8 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-08 |  |  | D01 | IFA | T-0446 | 44695 | 1401/02/24 | 0 | 0 | 0 | BK-SUR-ENG-QAC-00-02667 | 44576 | 1400/10/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-87498 | 44715 | 1401/03/12 | 44723 | 1401/03//21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0322 | 2021-12-08 | 1400/09/17 |  |  |  | BK-SUR-ENG-QAC-00-02295 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1401-2294-6237 | 2022-03-30 | 1401/01/10 | 44664 | 1401/01/24 | AP | [10 empty] | D01 | IFA | T-0446 | 44695 | 1401/02/24 |  |  |  | BK-SUR-ENG-QAC-00-02667 | 44576 | 1400/10/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0001_D00 | [5 empty] | 1401-2294-87498 | 44715 | 1401/03/12 | 44723 | 1401/03//21 | CM | [22 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0001_D01
1 | 2 | 0 | 15 | 1 | 0 | 2 | 1.2.15.1.2 | BK-GNRAL-PEDCO-000-QC-PR-0003 | Project Audit Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0003 | BK-GNRAL-PEDCO-000-QC-PR-0003 | BK | GNRAL | PEDCO | 000 | QC | PR | 0003 | F0Z-707292 | AFD | IFC | 2022-08-23 | 2022-09-11 | 2022-09-14 | 19 | 3 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-09 |  |  | D00 | IFC | T-1263 | 44782 | 1401/05/18 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-05497 | 44795 | 1401/05/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-220417 | 44815 | 1401/06/20 | 44818 | 1401/06/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1263 | 2022-08-09 | 1401/05/18 |  |  |  | BK-SUR-ENG-QAC-01-05497 | 44795 | 1401/05/31 | AP | [6 empty] | 1401-2294-220417 | 2022-09-11 | 1401/06/20 | 44818 | 1401/06/23 | AP
1 | 2 | 0 | 15 | 1 | 0 | 3 | 1.2.15.1.3 | BK-GNRAL-PEDCO-000-QC-PR-0042 | Non Conformance Control Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0042 | BK-GNRAL-PEDCO-000-QC-PR-0042 | BK | GNRAL | PEDCO | 000 | QC | PR | 0042 | F0Z-707294 | AFC | IFC | 2022-04-24 | 2022-05-16 | 2022-05-23 | 22 | 7 | 29 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-10 |  |  | D00 | IFC | T-0793 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03981 | 44680 | 1401/01/29 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65519 | 44697 | 1401/02/26 | 44704 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0793 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-QAC-01-03981 | 44680 | 1401/01/29 | CM-C3 | [6 empty] | 1401-2294-65519 | 2022-05-16 | 1401/02/26 | 44704 | 1401/03/03 | AP
1 | 2 | 0 | 15 | 1 | 0 | 4 | 1.2.15.1.4 | BK-GNRAL-PEDCO-000-QC-PR-0043 | Corrective Action Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0043 | BK-GNRAL-PEDCO-000-QC-PR-0043 | BK | GNRAL | PEDCO | 000 | QC | PR | 0043 | F0Z-707295 | AFC | IFC | 2022-08-23 | 2022-09-11 | 2022-09-14 | 19 | 3 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-09 |  |  | D00 | IFC | T-1263 | 44782 | 1401/05/18 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-05497 | 44795 | 1401/05/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-220417 | 44815 | 1401/06/20 | 44818 | 1401/06/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1263 | 2022-08-09 | 1401/05/18 |  |  |  | BK-SUR-ENG-QAC-01-05497 | 44795 | 1401/05/31 | AP | [6 empty] | 1401-2294-220417 | 2022-09-11 | 1401/06/20 | 44818 | 1401/06/23 | AP
1 | 2 | 0 | 15 | 1 | 0 | 5 | 1.2.15.1.5 | BK-GNRAL-PEDCO-000-QC-PR-0044 | Material Reciving, Storage, Handling Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0044 | BK-GNRAL-PEDCO-000-QC-PR-0044 | BK | GNRAL | PEDCO | 000 | QC | PR | 0044 | F0Z-707296 | AFC | IFC | 2022-03-06 | 2022-05-12 | 2022-05-21 | 67 | 9 | 76 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-20 |  |  | D00 | IFC | T-0610 | 44612 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-QAC-00-03238 | 44619 | 1400/12/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59522 | 44693 | 1401/02/22 | 44702 | 1401/02/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0610 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-QAC-00-03238 | 44619 | 1400/12/08 | CM-C2 | [6 empty] | 1401-2294-59522 | 2022-05-12 | 1401/02/22 | 44702 | 1401/02/31 | AP
1 | 2 | 0 | 15 | 1 | 0 | 6 | 1.2.15.1.6 | BK-GNRAL-PEDCO-000-QC-PR-0045 | Packing, Marking, Transportation Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0045 | BK-GNRAL-PEDCO-000-QC-PR-0045 | BK | GNRAL | PEDCO | 000 | QC | PR | 0045 | F0Z-707297 | AFC | IFC | 2022-05-08 | 2022-05-12 | 2022-05-21 | 4 | 9 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-24 |  |  | D00 | IFC | T-0855 | 44675 | 1401/02/04 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-04118 | 44682 | 1401/02/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59527 | 44693 | 1401/02/22 | 44702 | 1401/02/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0855 | 2022-04-24 | 1401/02/04 |  |  |  | BK-SUR-ENG-QAC-01-04118 | 44682 | 1401/02/11 | AP | [6 empty] | 1401-2294-59527 | 2022-05-12 | 1401/02/22 | 44702 | 1401/02/31 | AP
1 | 2 | 0 | 15 | 1 | 0 | 7 | 1.2.15.1.7 | BK-GNRAL-PEDCO-000-PM-PR-0013 | Criticality Assessment Procedure |  | BK-GNRAL-PEDCO-000-PM-PR-0013 | BK-GNRAL-PEDCO-000-PM-PR-0013 | BK | GNRAL | PEDCO | 000 | PM | PR | 0013 | F0Z-707298 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 1 | 0 | 8 | 1.2.15.1.8 | BK-GNRAL-PEDCO-000-QC-PR-0022 | Specification For Final Data Book (FDB) Requirements |  | BK-GNRAL-PEDCO-000-QC-PR-0022 | BK-GNRAL-PEDCO-000-QC-PR-0022 | BK | GNRAL | PEDCO | 000 | QC | PR | 0022 | F0Z-707293 | AFC | IFC | 2022-04-17 | 2022-04-19 | 2022-04-24 | 2 | 5 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-03 |  |  | D00 | IFC | T-0771 | 44654 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03936 | 44667 | 1401/01/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31420 | 44670 | 1401/01/30 | 44675 | 1401/02/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0771 | 2022-04-03 | 1401/01/14 |  |  |  | BK-SUR-ENG-QAC-01-03936 | 44667 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-31420 | 2022-04-19 | 1401/01/30 | 44675 | 1401/02/04 | CM
1 | 2 | 0 | 15 | 1 | 0 | 9 | 1.2.15.1.9 | BK-GNRAL-PEDCO-000-QC-PR-0014 | Technical Query Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0014 | BK-GNRAL-PEDCO-000-QC-PR-0014 | BK | GNRAL | PEDCO | 000 | QC | PR | 0014 | F0Z-707300 | AFC | IFC | 2022-04-17 | 2022-04-19 | 2022-04-24 | 2 | 5 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-03 |  |  | D00 | IFC | T-0771 | 44654 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03936 | 44667 | 1401/01/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31420 | 44670 | 1401/01/30 | 44675 | 1401/02/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0771 | 2022-04-03 | 1401/01/14 |  |  |  | BK-SUR-ENG-QAC-01-03936 | 44667 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-31420 | 2022-04-19 | 1401/01/30 | 44675 | 1401/02/04 | CM
1 | 2 | 0 | 15 | 2 | 0 | 0 | 1.2.15.2 |  | QC General Document | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 15 | 2 | 0 | 1 | 1.2.15.2.1 | BK-GNRAL-PEDCO-000-QC-PR-0002 | Quality Control Plan (QCP) |  | BK-GNRAL-PEDCO-000-QC-PR-0002 | BK-GNRAL-PEDCO-000-QC-PR-0002 | BK | GNRAL | PEDCO | 000 | QC | PR | 0002 | F0Z-707301 | AFC | IFC | 2021-12-12 | 2022-02-16 | 2022-02-16 | 66 | 0 | 66 | IFC | 2022-02-05 | 0 | 0 | -44597 | 0 | -44597 | IFC | 2022-03-27 | 0 | 0 | -44647 | 0 | -44647 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-28 |  |  | D01 | IFC | T-0724 | 44633 | 1400/12/22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0282 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-QAC-00-02163 | 44531 | 1400/09/10 | RJ-C4 | [6 empty] | 1400-2294-412900 | 2022-02-16 | 1400/11/27 | 44608 | 1400/11/27 | AP | [10 empty] | D00 | IFC | T-0487 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-QAC-00-02925 | 44594 | 1400/11/13 | C4-RJ | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0002_D00 | [21 empty] | D01 | IFC | T-0724 | 44633 | 1400/12/22 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0002_D00
1 | 2 | 0 | 15 | 2 | 0 | 2 | 1.2.15.2.2 | BK-GNRAL-PEDCO-000-QC-PR-0015 | Specification for Welding Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0015 | BK-GNRAL-PEDCO-000-QC-PR-0015 | BK | GNRAL | PEDCO | 000 | QC | PR | 0015 | F0Z-707302 | AFC | IFC | 2022-04-30 | 2022-05-30 | 2022-06-08 | 30 | 9 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-16 |  |  | D00 | IFC | T-0819 | 44667 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03943 | 44668 | 1401/01/28 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-82859 | 44711 | 1401/03/09 | 44720 | 1401/03/18 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0819 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-QAC-01-03943 | 44668 | 1401/01/28 | RJ-C4 | [6 empty] | 1401-2294-82859 | 2022-05-30 | 1401/03/09 | 44720 | 1401/03/18 | CM
1 | 2 | 0 | 15 | 2 | 0 | 3 | 1.2.15.2.3 | BK-GNRAL-PEDCO-000-QC-PR-0016 | Heat Treatment Procedure (Pre Heating , PWHT) |  | BK-GNRAL-PEDCO-000-QC-PR-0016 | BK-GNRAL-PEDCO-000-QC-PR-0016 | BK | GNRAL | PEDCO | 000 | QC | PR | 0016 | F0Z-707303 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 2 | 0 | 4 | 1.2.15.2.4 | BK-GNRAL-PEDCO-000-QC-PR-0017 | Welder Performance Qualification Test (WQT) Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0017 | BK-GNRAL-PEDCO-000-QC-PR-0017 | BK | GNRAL | PEDCO | 000 | QC | PR | 0017 | F0Z-707304 | AFC | IFC | 2022-04-18 | 2022-05-08 | 2022-05-18 | 20 | 10 | 30 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-04 |  |  | D00 | IFC | T-0772 | 44655 | 1400/01/15 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03946 | 44668 | 1401/01/28 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52746 | 44689 | 1401/02/18 | 44699 | 1401/02/28 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0772 | 2022-04-04 | 1400/01/15 |  |  |  | BK-SUR-ENG-QAC-01-03946 | 44668 | 1401/01/28 | CM-C2 | [6 empty] | 1401-2294-52746 | 2022-05-08 | 1401/02/18 | 44699 | 1401/02/28 | CM
1 | 2 | 0 | 15 | 2 | 0 | 5 | 1.2.15.2.5 | BK-GNRAL-PEDCO-000-QC-PR-0018 | NDT Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0018 | BK-GNRAL-PEDCO-000-QC-PR-0018 | BK | GNRAL | PEDCO | 000 | QC | PR | 0018 | F0Z-707305 | AFC | IFC | 2022-08-13 | 2022-09-06 | 2022-09-11 | 24 | 5 | 29 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-30 |  |  | D00 | IFC | T-1213 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-05350 | 44779 | 1401/05/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213793 | 44810 | 1401/06/15 | 44815 | 1401/06/20 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1213 | 2022-07-30 | 1401/05/08 |  |  |  | BK-SUR-ENG-QAC-01-05350 | 44779 | 1401/05/15 | CM-C3 | [6 empty] | 1401-2294-213793 | 2022-09-06 | 1401/06/15 | 44815 | 1401/06/20 | CM
1 | 2 | 0 | 15 | 2 | 0 | 6 | 1.2.15.2.6 | BK-GNRAL-PEDCO-000-QC-PR-0019 | Surface Preparation and Coating/Painting Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0019 | BK-GNRAL-PEDCO-000-QC-PR-0019 | BK | GNRAL | PEDCO | 000 | QC | PR | 0019 | F0Z-707306 | AFC | IFC | 2022-08-23 | 2022-09-11 | 2022-09-14 | 19 | 3 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-09 |  |  | D00 | IFC | T-1263 | 44782 | 1401/05/18 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-05497 | 44795 | 1401/05/31 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-220417 | 44815 | 1401/06/20 | 44818 | 1401/06/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1263 | 2022-08-09 | 1401/05/18 |  |  |  | BK-SUR-ENG-QAC-01-05497 | 44795 | 1401/05/31 | CM-C3 | [6 empty] | 1401-2294-220417 | 2022-09-11 | 1401/06/20 | 44818 | 1401/06/23 | CM
1 | 2 | 0 | 15 | 2 | 0 | 7 | 1.2.15.2.7 | BK-GNRAL-PEDCO-000-QC-PR-0021 | Control of Inspection Measuring and Test Equipment Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0021 | BK-GNRAL-PEDCO-000-QC-PR-0021 | BK | GNRAL | PEDCO | 000 | QC | PR | 0021 | F0Z-707307 | AFC | IFC | 2022-04-24 | 2022-05-16 | 2022-05-23 | 22 | 7 | 29 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-10 |  |  | D00 | IFC | T-0793 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03981 | 44680 | 1401/01/29 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65519 | 44697 | 1401/02/26 | 44704 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0793 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-QAC-01-03981 | 44680 | 1401/01/29 | CM-C3 | [6 empty] | 1401-2294-65519 | 2022-05-16 | 1401/02/26 | 44704 | 1401/03/03 | AP
1 | 2 | 0 | 15 | 2 | 0 | 8 | 1.2.15.2.8 | BK-GNRAL-PEDCO-000-QC-PR-0035 | Field Joint Coating Procedure For Pipeline |  | BK-GNRAL-PEDCO-000-QC-PR-0035 | BK-GNRAL-PEDCO-000-QC-PR-0035 | BK | GNRAL | PEDCO | 000 | QC | PR | 0035 | F0Z-707315 | AFC | IFC | 2022-10-10 | 0 | 0 | -44844 | 0 | -44844 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-26 |  |  | D00 | IFC | T-1442 | 44830 | 1401/07/04 | T-1442 | 44830 | 1401/07/04 | BK-SUR-ENG-QAC-01-05835 | 44838 | 1401/07/12 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1442 | 2022-09-26 | 1401/07/04 | T-1442 | 44830 | 1401/07/04 | BK-SUR-ENG-QAC-01-05835 | 44838 | 1401/07/12 | RJ-C4
1 | 2 | 0 | 15 | 3 | 0 | 0 | 1.2.15.3 |  | QC Discipline Document
1 | 2 | 0 | 15 | 3 | 1 | 0 | 1.2.15.3.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 15 | 3 | 1 | 1 | 1.2.15.3.1.1 | BK-GNRAL-PEDCO-000-QC-PR-0004 | ITP For Piping Works |  | BK-GNRAL-PEDCO-000-QC-PR-0004 | BK-GNRAL-PEDCO-000-QC-PR-0004 | BK | GNRAL | PEDCO | 000 | QC | PR | 0004 | F0Z-707308 | AFC | IFC | 2022-04-24 | 2022-05-16 | 2022-05-23 | 22 | 7 | 29 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-10 |  |  | D00 | IFC | T-0793 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03981 | 44680 | 1401/01/29 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65519 | 44697 | 1401/02/26 | 44704 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0793 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-QAC-01-03981 | 44680 | 1401/01/29 | CM-C3 | [6 empty] | 1401-2294-65519 | 2022-05-16 | 1401/02/26 | 44704 | 1401/03/03 | AP
1 | 2 | 0 | 15 | 3 | 1 | 2 | 1.2.15.3.1.2 | BK-GNRAL-PEDCO-000-QC-PR-0023 | PIPING PWPS (Preliminary Welding Procedure Specification) |  | BK-GNRAL-PEDCO-000-QC-PR-0023 | BK-GNRAL-PEDCO-000-QC-PR-0023 | BK | GNRAL | PEDCO | 000 | QC | PR | 0023 | F0Z-707309 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 1 | 3 | 1.2.15.3.1.3 | BK-GNRAL-PEDCO-000-QC-PR-0024 | PIPING WPS (Welding Procedure Specification) |  | BK-GNRAL-PEDCO-000-QC-PR-0024 | BK-GNRAL-PEDCO-000-QC-PR-0024 | BK | GNRAL | PEDCO | 000 | QC | PR | 0024 | F0Z-707310 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 1 | 4 | 1.2.15.3.1.4 | BK-GNRAL-PEDCO-000-QC-PR-0025 | PIPING PQR (Procedure Qualification Record) |  | BK-GNRAL-PEDCO-000-QC-PR-0025 | BK-GNRAL-PEDCO-000-QC-PR-0025 | BK | GNRAL | PEDCO | 000 | QC | PR | 0025 | F0Z-707311 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 1 | 5 | 1.2.15.3.1.5 | BK-GNRAL-PEDCO-000-QC-PR-0026 | PIPING PWPS (Preliminary Welding Procedure Specification) for Repair Welding |  | BK-GNRAL-PEDCO-000-QC-PR-0026 | BK-GNRAL-PEDCO-000-QC-PR-0026 | BK | GNRAL | PEDCO | 000 | QC | PR | 0026 | F0Z-707312 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 1 | 6 | 1.2.15.3.1.6 | BK-GNRAL-PEDCO-000-QC-PR-0027 | PIPING WPS (Preliminary Welding Procedure Specification) for Repair Welding |  | BK-GNRAL-PEDCO-000-QC-PR-0027 | BK-GNRAL-PEDCO-000-QC-PR-0027 | BK | GNRAL | PEDCO | 000 | QC | PR | 0027 | F0Z-707313 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 1 | 7 | 1.2.15.3.1.7 | BK-GNRAL-PEDCO-000-QC-PR-0028 | PIPING PQR (Procedure Qualification Record) for Repair Welding |  | BK-GNRAL-PEDCO-000-QC-PR-0028 | BK-GNRAL-PEDCO-000-QC-PR-0028 | BK | GNRAL | PEDCO | 000 | QC | PR | 0028 | F0Z-707314 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
[8 empty] | BK-GNRAL-PEDCO-000-QC-PR-0046 | Pressure Test Procedure |  | BK-GNRAL-PEDCO-000-QC-PR-0046 | BK-GNRAL-PEDCO-000-QC-PR-0046 | BK | GNRAL | PEDCO | 000 | QC | PR | 0046 | F0Z-707316 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 2 | 0 | 1.2.15.3.2 |  | Telecomm.
1 | 2 | 0 | 15 | 3 | 2 | 1 | 1.2.15.3.2.1 | BK-GNRAL-PEDCO-000-QC-PR-0012 | ITP For Telecommunication Installation |  | BK-GNRAL-PEDCO-000-QC-PR-0012 | BK-GNRAL-PEDCO-000-QC-PR-0012 | BK | GNRAL | PEDCO | 000 | QC | PR | 0012 | F0Z-707317 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 3 | 0 | 1.2.15.3.3 |  | Safety
1 | 2 | 0 | 15 | 3 | 3 | 1 | 1.2.15.3.3.1 | BK-GNRAL-PEDCO-000-QC-PR-0013 | ITP For Safety Installation |  | BK-GNRAL-PEDCO-000-QC-PR-0013 | BK-GNRAL-PEDCO-000-QC-PR-0013 | BK | GNRAL | PEDCO | 000 | QC | PR | 0013 | F0Z-707318 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 4 | 0 | 1.2.15.3.4 |  | Architectural
1 | 2 | 0 | 15 | 3 | 4 | 1 | 1.2.15.3.4.1 | BK-GNRAL-PEDCO-000-QC-PR-0008 | ITP For Architectural Works |  | BK-GNRAL-PEDCO-000-QC-PR-0008 | BK-GNRAL-PEDCO-000-QC-PR-0008 | BK | GNRAL | PEDCO | 000 | QC | PR | 0008 | F0Z-707319 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 5 | 0 | 1.2.15.3.5 |  | Mechanical
1 | 2 | 0 | 15 | 3 | 5 | 1 | 1.2.15.3.5.1 | BK-GNRAL-PEDCO-000-QC-PR-0009 | ITP For Mechanical Installation |  | BK-GNRAL-PEDCO-000-QC-PR-0009 | BK-GNRAL-PEDCO-000-QC-PR-0009 | BK | GNRAL | PEDCO | 000 | QC | PR | 0009 | F0Z-707320 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 6 | 0 | 1.2.15.3.6 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 15 | 3 | 6 | 1 | 1.2.15.3.6.1 | BK-GNRAL-PEDCO-000-QC-PR-0007 | ITP For Steel Structural Works |  | BK-GNRAL-PEDCO-000-QC-PR-0007 | BK-GNRAL-PEDCO-000-QC-PR-0007 | BK | GNRAL | PEDCO | 000 | QC | PR | 0007 | F0Z-707321 | AFC | IFC | 2022-06-04 | 2022-05-30 | 2022-06-08 | -5 | 9 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-21 |  |  | D00 | IFC | T-0980 | 44702 | 1401/02/31 | T-0980 | 44703 | 1401/03/01 | BK-SUR-ENG-QAC-01-04484 | 44710 | 1401/03/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-82858 | 44711 | 1401/03/09 | 44720 | 1401/03/18 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0980 | 2022-05-21 | 1401/02/31 | T-0980 | 44703 | 1401/03/01 | BK-SUR-ENG-QAC-01-04484 | 44710 | 1401/03/09 | CM-C3 | [6 empty] | 1401-2294-82858 | 2022-05-30 | 1401/03/09 | 44720 | 1401/03/18 | CM
1 | 2 | 0 | 15 | 3 | 6 | 2 | 1.2.15.3.6.2 | BK-GNRAL-PEDCO-000-QC-PR-0036 | Steel Structure WPS (Welding Procedure Specification) |  | BK-GNRAL-PEDCO-000-QC-PR-0036 | BK-GNRAL-PEDCO-000-QC-PR-0036 | BK | GNRAL | PEDCO | 000 | QC | PR | 0036 | F0Z-707322 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 6 | 3 | 1.2.15.3.6.3 | BK-GNRAL-PEDCO-000-QC-PR-0037 | Steel Structure PQR (Procedure Qualification Record) |  | BK-GNRAL-PEDCO-000-QC-PR-0037 | BK-GNRAL-PEDCO-000-QC-PR-0037 | BK | GNRAL | PEDCO | 000 | QC | PR | 0037 | F0Z-707323 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 6 | 4 | 1.2.15.3.6.4 | BK-GNRAL-PEDCO-000-QC-PR-0038 | Steel Structure WPS (Welding Procedure Specification) For Repair Welding |  | BK-GNRAL-PEDCO-000-QC-PR-0038 | BK-GNRAL-PEDCO-000-QC-PR-0038 | BK | GNRAL | PEDCO | 000 | QC | PR | 0038 | F0Z-707324 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 6 | 5 | 1.2.15.3.6.5 | BK-GNRAL-PEDCO-000-QC-PR-0039 | Steel Structure PQR (Procedure Qualification Record) For Repair Welding |  | BK-GNRAL-PEDCO-000-QC-PR-0039 | BK-GNRAL-PEDCO-000-QC-PR-0039 | BK | GNRAL | PEDCO | 000 | QC | PR | 0039 | F0Z-707325 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 6 | 6 | 1.2.15.3.6.6 | BK-GNRAL-PEDCO-000-QC-PR-0040 | Weld Map For Steel Structures |  | BK-GNRAL-PEDCO-000-QC-PR-0040 | BK-GNRAL-PEDCO-000-QC-PR-0040 | BK | GNRAL | PEDCO | 000 | QC | PR | 0040 | F0Z-707326 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
1 | 2 | 0 | 15 | 3 | 6 | 7 | 1.2.15.3.6.7 | BK-GNRAL-PEDCO-000-QC-PR-0041 | NDT Plan For steel Structures |  | BK-GNRAL-PEDCO-000-QC-PR-0041 | BK-GNRAL-PEDCO-000-QC-PR-0041 | BK | GNRAL | PEDCO | 000 | QC | PR | 0041 | F0Z-707327 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 7 | 0 | 1.2.15.3.7 |  | Instrumentation
1 | 2 | 0 | 15 | 3 | 7 | 1 | 1.2.15.3.7.1 | BK-GNRAL-PEDCO-000-QC-PR-0011 | ITP For I&C Installation |  | BK-GNRAL-PEDCO-000-QC-PR-0011 | BK-GNRAL-PEDCO-000-QC-PR-0011 | BK | GNRAL | PEDCO | 000 | QC | PR | 0011 | F0Z-707328 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 8 | 0 | 1.2.15.3.8 |  | Pipeline | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
1 | 2 | 0 | 15 | 3 | 8 | 1 | 1.2.15.3.8.1 | BK-GNRAL-PEDCO-000-QC-PR-0005 | ITP For Pipeline |  | BK-GNRAL-PEDCO-000-QC-PR-0005 | BK-GNRAL-PEDCO-000-QC-PR-0005 | BK | GNRAL | PEDCO | 000 | QC | PR | 0005 | F0Z-707329 | AFC | IFC | 2022-01-30 | 2022-03-23 | 2022-03-25 | 52 | 2 | 54 | IFA | 2022-05-04 | 2022-06-11 | 2022-06-12 | 38 | 1 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-16 |  |  | D01 | IFA | T-0853 | 44671 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-04120 | 44682 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-95932 | 44723 | 1401/03/21 | 44724 | 1401/03/22 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-QC-PR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0462 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-QAC-00-02928 | 44597 | 1400/11/16 | CM-C2 | [6 empty] | 1400-2294-397208 | 2022-02-05 | 1400/11/16 | 44597 | 1400/11/16 | CM |  | 1401-2294-1325 | 44643 | 1401/01/06 | 44645 | 1401/01/08 | CM |  |  |  | D01 | IFA | T-0853 | 44671 | 1401/01/31 |  |  |  | BK-SUR-ENG-QAC-01-04120 | 44682 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0005_D00 | [5 empty] | 1401-2294-95932 | 44723 | 1401/03/21 | 44724 | 1401/03/22 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-QC-PR-0005_D00
1 | 2 | 0 | 15 | 3 | 8 | 2 | 1.2.15.3.8.2 | BK-GNRAL-PEDCO-000-QC-PR-0029 | PIPELINE PWPS (Preliminary Welding Procedure Specification) |  | BK-GNRAL-PEDCO-000-QC-PR-0029 | BK-GNRAL-PEDCO-000-QC-PR-0029 | BK | GNRAL | PEDCO | 000 | QC | PR | 0029 | F0Z-707330 | AFC | IFC | 2022-03-09 | 2022-03-23 | 2022-03-25 | 14 | 2 | 16 | IFA | 2022-09-11 | 2022-09-13 | 2022-09-19 | 2 | 6 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-23 |  |  | D01 | IFA | T-1330 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-05612 | 44813 | 1401/06/15 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0029_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-222917 | 44817 | 1401/06/22 | 44823 | 1401/06/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-QC-PR-0029_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0629 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-QAC-00-03286 | 44622 | 1400/12/11 | RJ-C4 | [6 empty] | 1401-2294-1320 | 2022-03-23 | 1401/01/06 | 44645 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-1330 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-QAC-01-05612 | 44813 | 1401/06/15 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0029_D00 | [5 empty] | 1401-2294-222917 | 44817 | 1401/06/22 | 44823 | 1401/06/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-QC-PR-0029_D00
1 | 2 | 0 | 15 | 3 | 8 | 3 | 1.2.15.3.8.3 | BK-GNRAL-PEDCO-000-QC-PR-0030 | PIPELINE WPS (Welding Procedure Specification) |  | BK-GNRAL-PEDCO-000-QC-PR-0030 | BK-GNRAL-PEDCO-000-QC-PR-0030 | BK | GNRAL | PEDCO | 000 | QC | PR | 0030 | F0Z-707331 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 8 | 4 | 1.2.15.3.8.4 | BK-GNRAL-PEDCO-000-QC-PR-0031 | PIPELINE PQR (Procedure Qualification Record) |  | BK-GNRAL-PEDCO-000-QC-PR-0031 | BK-GNRAL-PEDCO-000-QC-PR-0031 | BK | GNRAL | PEDCO | 000 | QC | PR | 0031 | F0Z-707332 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 8 | 5 | 1.2.15.3.8.5 | BK-GNRAL-PEDCO-000-QC-PR-0032 | PIPELINE PWPS (Preliminary Welding Procedure Specification) for Repair Welding |  | BK-GNRAL-PEDCO-000-QC-PR-0032 | BK-GNRAL-PEDCO-000-QC-PR-0032 | BK | GNRAL | PEDCO | 000 | QC | PR | 0032 | F0Z-707333 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 8 | 6 | 1.2.15.3.8.6 | BK-GNRAL-PEDCO-000-QC-PR-0033 | PIPELINE WPS (Preliminary Welding Procedure Specification) for Repair Welding |  | BK-GNRAL-PEDCO-000-QC-PR-0033 | BK-GNRAL-PEDCO-000-QC-PR-0033 | BK | GNRAL | PEDCO | 000 | QC | PR | 0033 | F0Z-707334 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
1 | 2 | 0 | 15 | 3 | 8 | 7 | 1.2.15.3.8.7 | BK-GNRAL-PEDCO-000-QC-PR-0034 | PIPELINE PQR (Procedure Qualification Record) for Repair Welding |  | BK-GNRAL-PEDCO-000-QC-PR-0034 | BK-GNRAL-PEDCO-000-QC-PR-0034 | BK | GNRAL | PEDCO | 000 | QC | PR | 0034 | F0Z-707335 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
1 | 2 | 0 | 15 | 3 | 9 | 0 | 1.2.15.3.9 |  | Civil
1 | 2 | 0 | 15 | 3 | 9 | 1 | 1.2.15.3.9.1 | BK-GNRAL-PEDCO-000-QC-PR-0006 | ITP For Civil Works |  | BK-GNRAL-PEDCO-000-QC-PR-0006 | BK-GNRAL-PEDCO-000-QC-PR-0006 | BK | GNRAL | PEDCO | 000 | PM | CG | 0001 | F0Z-707336 | AFD | IFC | 2021-10-04 | 2021-09-23 | 2021-09-26 | -11 | 3 | -8 | AFD | 2021-12-06 | 2021-11-28 | 2021-12-15 | -8 | 17 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-20 | 2021-11-22 |  | D01 | AFD | T-0267 | 44522 | 1400/09/01 | 0 | 0 | 0 | BK-SUR-ENG-QAC-00-02266 | 44542 | 1400/09/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDEC-000-QC-PR-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2290-294991 | 44528 | 1400/09/07 | 44545 | 1400/09/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0103 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SUR-ENG-QAC-00-01584 | 44461 | 1400/06/31 | CM-C2 | [6 empty] | 1400-2294-210031 | 2021-09-23 | 1400/07/01 | 44465 | 1400/07/04 | AP | [10 empty] | D01 | AFD | T-0267 | 44522 | 1400/09/01 |  |  |  | BK-SUR-ENG-QAC-00-02266 | 44542 | 1400/09/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDEC-000-QC-PR-0006_D00 | [5 empty] | 1400-2290-294991 | 44528 | 1400/09/07 | 44545 | 1400/09/24 | AP
1 | 2 | 0 | 15 | 3 | 10 | 0 | 1.2.15.3.10 |  | Electrical
1 | 2 | 0 | 15 | 3 | 10 | 1 | 1.2.15.3.10.1 | BK-GNRAL-PEDCO-000-QC-PR-0010 | ITP For Electrical Installation |  | BK-GNRAL-PEDCO-000-QC-PR-0010 | BK-GNRAL-PEDCO-000-QC-PR-0010 | BK | GNRAL | PEDCO | 000 | QC | PR | 0010 | F0Z-707337 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | SUB-Surface DEVELOPMENT
2 | 1 | 0 | 0 | 0 | 0 | 0 | 2.1 |  | Sub-Surface Common Docs | [61 empty] | Deleted
2 | 1 | 0 | 1 | 0 | 0 | 0 | 2.1.1 |  | Basic Design Endorsement
2 | 1 | 0 | 1 | 0 | 0 | 1 | 2.1.1.1 | BK-SSGRL-PEDCO-110-GE-RT-0001 | Endorsement Report For Basic Design & Scope of Work |  | BK-SSGRL-PEDCO-110-GE-RT-0001 | [8 empty] | - |  | IFC | 2021-08-14 | 2021-08-28 | 2021-09-07 | 14 | 10 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-31 |  |  | B00 | IFC | T-0023 | 44408 | 1400/05/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-176098 | 44436 | 1400/06/06 | 44446 | 1400/06/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B00-Reject |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | [13 empty] | 1400-2294-176098 | 2021-08-28 | 1400/06/06 | 44446 | 1400/06/16 | CM | [8 empty] | B00-Reject
2 | 1 | 0 | 2 | 0 | 0 | 0 | 2.1.2 |  | Value Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 2 | 0 | 0 | 1 | 2.1.2.1 | BK-SSGRL-PEDCO-110-GE-RT-0002 | Value Engineering Study Report |  | BK-SSGRL-PEDCO-110-GE-RT-0002 | BK-SSGRL-PEDCO-110-GE-RT-0002 | BK | SSGRL | PEDCO | 110 | GE | RT | 0002 | F0Z-707338 | IFI | IFC | 2022-02-15 | 2022-03-10 | 2022-03-15 | 23 | 5 | 28 | IFA | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | IFA | 2022-07-27 | 2022-08-17 | 2022-08-21 | 21 | 4 | 25 | AFD | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-01 | 2022-10-25 |  | D03 | AFD | T-1552 | 44859 | 1401/08/03 | T-1552 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0531 | 2022-02-01 | 1400/11/12 |  |  |  | BK-SUR-ENG-PCS-00-03282 | 44622 | 1400/12/11 | CM-C2 | [6 empty] | 1400-2294-443284 | 2022-03-10 | 1400/12/19 | 44635 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0785 | 44661 | 1400/01/21 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-GE-RT-0002-D00 | [5 empty] | 1401-2294-68426 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-GE-RT-0002-D00 | [9 empty] | D02 | IFA | T-1151 | 44755 | 1401/04/22 | [13 empty] | 1401-2294-183534 | 44790 | 1401/05/27 | 44794 | 1401/05/30 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-GE-RT-0002_D01 | [9 empty] | D03 | AFD | T-1552 | 44859 | 1401/08/03 | T-1552 | 44859 | 1401/08/03
2 | 1 | 0 | 2 | 0 | 0 | 2 | 2.1.2.2 | BK-SSGRL-PEDCO-110-GE-RT-0003 | HAZID Report For WHF & Flow lines |  | BK-SSGRL-PEDCO-110-GE-RT-0003 | BK-SSGRL-PEDCO-110-GE-RT-0003 | BK | SSGRL | PEDCO | 110 | GE | RT | 0003 | F0Z-707339 | IFI | IFI | 2022-08-15 | 2022-09-19 | 2022-09-26 | 35 | 7 | 42 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-01 | 2022-11-19 |  | D01 | FI | T-1591 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1233 | 2022-08-01 | 1401/05/10 | [13 empty] | 1401-2294-228737 | 2022-09-19 | 1401/06/28 | 44830 | 1401/07/04 | AP | [10 empty] | D01 | FI | T-1591 | 44884 | 1401/08/28
2 | 1 | 0 | 2 | 0 | 0 | 3 | 2.1.2.3 | BK-SSGRL-PEDCO-110-GE-RT-0004 | HAZOP Report For Binak B/C Manifold Extension |  | BK-SSGRL-PEDCO-110-GE-RT-0004 | BK-SSGRL-PEDCO-110-GE-RT-0004 | BK | SSGRL | PEDCO | 110 | GE | RT | 0004 | F0Z-707340 | IFI | IFI | 2022-08-15 | 2022-09-19 | 2022-09-26 | 35 | 7 | 42 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-01 | 2022-11-19 |  | D01 | FI | T-1591 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1233 | 2022-08-01 | 1401/05/10 | [13 empty] | 1401-2294-228737 | 2022-09-19 | 1401/06/28 | 44830 | 1401/07/04 | AP | [10 empty] | D01 | FI | T-1591 | 44884 | 1401/08/28
2 | 1 | 0 | 2 | 0 | 0 | 4 | 2.1.2.4 | BK-SSGRL-PEDCO-110-GE-RT-0005 | SIL Report For Binak B/C Manifold Extension |  | BK-SSGRL-PEDCO-110-GE-RT-0005 | BK-SSGRL-PEDCO-110-GE-RT-0005 | BK | SSGRL | PEDCO | 110 | GE | RT | 0005 | F0Z-707341 | IFI | IFI | 2022-08-15 | 2022-09-19 | 2022-09-26 | 35 | 7 | 42 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-01 | 2022-11-19 |  | D01 | FI | T-1591 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1233 | 2022-08-01 | 1401/05/10 | [13 empty] | 1401-2294-228737 | 2022-09-19 | 1401/06/28 | 44830 | 1401/07/04 | AP | [10 empty] | D01 | FI | T-1591 | 44884 | 1401/08/28
2 | 1 | 0 | 3 | 0 | 0 | 0 | 2.1.3 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
[9 empty] | DATA SHEETS | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
[8 empty] | BK-SSGRL-PEDCO-110-PR-DT-0001 | Process Data Sheets For Fuel Oil Storage Drum of Well Pads |  | BK-SSGRL-PEDCO-110-PR-DT-0001 | BK-SSGRL-PEDCO-110-PR-DT-0001 | BK | SSGRL | PEDCO | 110 | PR | DT | 0001 | F0Z-707347 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[8 empty] | BK-SSGRL-PEDCO-110-PR-DT-0002 | Process Data Sheets For Potable Water Tank of Well Pads |  | BK-SSGRL-PEDCO-110-PR-DT-0002 | BK-SSGRL-PEDCO-110-PR-DT-0002 | BK | SSGRL | PEDCO | 110 | PR | DT | 0002 | F0Z-707348 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 1 | 0 | 3 | 0 | 1 | 0 | 2.1.3.1 |  | Philosophy | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 3 | 0 | 1 | 1 | 2.1.3.1.1 | BK-SSGRL-PEDCO-110-PR-PH-0001 | Drainage Philosophy |  | BK-SSGRL-PEDCO-110-PR-PH-0001 | BK-SSGRL-PEDCO-110-PR-PH-0001 | BK | SSGRL | PEDCO | 110 | PR | PH | 0001 | F0Z-707342 | AFD | IFC | 2022-04-09 | 2022-05-07 | 2022-05-09 | 28 | 2 | 30 | AFD | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-26 | 2022-05-10 |  | D01 | AFD | T-0927 | 44691 | 1401/02/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0746 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-PCS-01-03956 | 44668 | 1401/01/28 | CM-C2 | [6 empty] | 1401-2294-49820 | 2022-05-07 | 1401/02/17 | 44690 | 1401/02/19 | AP | [10 empty] | D01 | AFD | T-0927 | 44691 | 1401/02/20 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0001_D00
2 | 1 | 0 | 3 | 0 | 1 | 2 | 2.1.3.1.2 | BK-SSGRL-PEDCO-110-PR-PH-0002 | Control Philosophy |  | BK-SSGRL-PEDCO-110-PR-PH-0002 | BK-SSGRL-PEDCO-110-PR-PH-0002 | BK | SSGRL | PEDCO | 110 | PR | PH | 0002 | F0Z-707343 | AFD | IFC | 2022-05-23 | 2022-06-13 | 2022-06-15 | 21 | 2 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-09 |  |  | D00 | IFC | T-0921 | 44690 | 1401/02/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-100891 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 |  |  |  | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C3 | [6 empty] | 1401-2294-100891 | 2022-06-13 | 1401/03/23 | 44727 | 1401/03/25 | CM
2 | 1 | 0 | 3 | 0 | 1 | 3 | 2.1.3.1.3 | BK-SSGRL-PEDCO-110-PR-PH-0003 | Flare,Blow Down And Relief Philosophy |  | BK-SSGRL-PEDCO-110-PR-PH-0003 | BK-SSGRL-PEDCO-110-PR-PH-0003 | BK | SSGRL | PEDCO | 110 | PR | PH | 0003 | F0Z-707344 | AFD | IFC | 2022-04-09 | 2022-05-07 | 2022-05-09 | 28 | 2 | 30 | AFD | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-26 | 2022-05-10 |  | D01 | AFD | T-0927 | 44691 | 1401/02/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0746 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-PCS-01-03956 | 44668 | 1401/01/28 | CM-C2 | [6 empty] | 1401-2294-49820 | 2022-05-07 | 1401/02/17 | 44690 | 1401/02/19 | AP | [10 empty] | D01 | AFD | T-0927 | 44691 | 1401/02/20 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0003_D00
2 | 1 | 0 | 3 | 0 | 1 | 4 | 2.1.3.1.4 | BK-SSGRL-PEDCO-110-PR-PH-0004 | Isolation Philosophy |  | BK-SSGRL-PEDCO-110-PR-PH-0004 | BK-SSGRL-PEDCO-110-PR-PH-0004 | BK | SSGRL | PEDCO | 110 | PR | PH | 0004 | F0Z-707345 | AFD | IFC | 2021-12-05 | 2021-12-11 | 2021-12-14 | 6 | 3 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-21 |  |  | D00 | IFC | T-0262 | 44521 | 1400/08/30 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02227 | 44537 | 1400/09/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-312238 | 44541 | 1400/09/20 | 44544 | 1400/09/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 44537 | 1400/09/16 | CM-C3 | [6 empty] | 1400-2294-312238 | 2021-12-11 | 1400/09/20 | 44544 | 1400/09/23 | CM
2 | 1 | 0 | 3 | 0 | 1 | 5 | 2.1.3.1.5 | BK-SSGRL-PEDCO-110-PR-PH-0005 | ESD Philosophy |  | BK-SSGRL-PEDCO-110-PR-PH-0005 | BK-SSGRL-PEDCO-110-PR-PH-0005 | BK | SSGRL | PEDCO | 110 | PR | PH | 0005 | F0Z-707346 | AFD | IFC | 2022-05-23 | 2022-06-13 | 2022-06-15 | 21 | 2 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-09 |  |  | D00 | IFC | T-0921 | 44690 | 1401/02/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-100891 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 |  |  |  | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C3 | [6 empty] | 1401-2294-100891 | 2022-06-13 | 1401/03/23 | 44727 | 1401/03/25 | CM
2 | 1 | 0 | 3 | 0 | 2 | 0 | 2.1.3.2 |  | Drawing/Diagram
2 | 1 | 0 | 3 | 0 | 2 | 1 | 2.1.3.2.1 | BK-SSGRL-PEDCO-110-PR-PI-0001 | Symbol & Legend For PFD and P&ID |  | BK-SSGRL-PEDCO-110-PR-PI-0001 | BK-SSGRL-PEDCO-110-PR-PI-0001 | BK | SSGRL | PEDCO | 110 | PR | PI | 0001 | F2A-707349 | AFC | IFC | 2021-11-13 | 2021-11-09 | 2021-11-16 | -4 | 7 | 3 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | IFA | 2022-09-20 | 2022-11-19 | 2022-11-21 | 60 | 2 | 62 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-30 |  |  | D02 | IFA | T-1368 | 44810 | 1401/06/15 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0194 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-02022 | 44517 | 1400/08/26 | CM-C3 | [6 empty] | 1400-2294-269245 | 2021-11-09 | 1400/08/18 | 44516 | 1400/08/25 | CM | [10 empty] | D01 | IFA | T-0653 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1401-2294-43153 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-1368 | 44810 | 1401/06/15 |  |  |  | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D01
2 | 1 | 0 | 3 | 0 | 3 | 0 | 2.1.3.3 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 3 | 0 | 3 | 1 | 2.1.3.3.1 | BK-SSGRL-PEDCO-110-PR-LI-0001 | Consumption List |  | BK-SSGRL-PEDCO-110-PR-LI-0001 | BK-SSGRL-PEDCO-110-PR-LI-0001 | BK | SSGRL | PEDCO | 110 | PR | LI | 0001 | F0Z-707350 | AFC | IFC | 2022-03-09 | 2022-03-12 | 2022-03-14 | 3 | 2 | 5 | IFA | 2022-10-03 | 2022-10-17 | 2022-10-19 | 14 | 2 | 16 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-23 |  |  | D01 | IFA | T-1415 | 44823 | 1401/06/28 | T-1415 | 44823 | 1401/06/28 | BK-SUR-ENG-PCS-01-05873 | 44844 | 1401/07/18 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-267492 | 44851 | 1401/07/25 | 44853 | 1401/07/27 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0628 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-PCS-00-03421 | 44629 | 1400/12/18 | CM-C2 | [6 empty] | 1400-2294-445285 | 2022-03-12 | 1400/12/21 | 44634 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-1415 | 44823 | 1401/06/28 | T-1415 | 44823 | 1401/06/28 | BK-SUR-ENG-PCS-01-05873 | 44844 | 1401/07/18 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1401-2294-267492 | 44851 | 1401/07/25 | 44853 | 1401/07/27 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-PR-LI-0001_D00
2 | 1 | 0 | 4 | 0 | 0 | 0 | 2.1.4 |  | Mechanical
2 | 1 | 0 | 4 | 0 | 1 | 0 | 2.1.4.1 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 4 | 0 | 1 | 1 | 2.1.4.1.1 | BK-SSGRL-PEDCO-110-ME-DT-0001 | Data Sheets For Diesel Oil Storage Drum of Well Pads | Data Sheets For FUEL Oil Storage Drum of Well Pads | BK-SSGRL-PEDCO-110-ME-DT-0001 | BK-SSGRL-PEDCO-110-ME-DT-0001 | BK | SSGRL | PEDCO | 110 | ME | DT | 0001 | F0Z-707351 | AFC | IFC | 2022-01-30 | 2022-02-03 | 2022-02-13 | 4 | 10 | 14 | IFA | 2022-04-23 | 2022-04-29 | 2022-05-01 | 6 | 2 | 8 | IFA | 2022-06-21 | 2022-07-10 | 2022-07-30 | 19 | 20 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-16 |  |  | D02 | IFA | T-1048 | 44719 | 1401/03/17 | T-1048 | 44720 | 1401/03/18 | BK-SUR-ENG-MEC-01-05339 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-ME-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-135307 | 44752 | 1401/04/19 | 44772 | 1401/05/08 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0464 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-395075 | 2022-02-03 | 1400/11/14 | 44605 | 1400/11/24 | CM | [10 empty] | D01 | IFA | T-0790 | 44660 | 1401/01/20 |  |  |  | BK-SUR-ENG-MEC-01-03894 | 44664 | 1401/01/24 | CM-C3 | [6 empty] | 1401-2294-43245 | 44680 | 1401/02/09 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0001_D00 | [9 empty] | D02 | IFA | T-1048 | 44719 | 1401/03/17 | T-1048 | 44720 | 1401/03/18 | BK-SUR-ENG-MEC-01-05339 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-ME-DT-0001_D01 | [5 empty] | 1401-2294-135307 | 44752 | 1401/04/19 | 44772 | 1401/05/08 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0001_D01
2 | 1 | 0 | 4 | 0 | 1 | 2 | 2.1.4.1.2 | BK-SSGRL-PEDCO-110-ME-DT-0002 | Data Sheets For Potable Water Tank of Well Pads |  | BK-SSGRL-PEDCO-110-ME-DT-0002 | BK-SSGRL-PEDCO-110-ME-DT-0002 | BK | SSGRL | PEDCO | 110 | ME | DT | 0002 | F0Z-707352 | AFC | IFC | 2022-02-23 | 2022-03-01 | 2022-03-05 | 6 | 4 | 10 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-22 | 5 | 13 | 18 | IFA | 2022-07-05 | 2022-08-02 | 2022-08-09 | 28 | 7 | 35 | IFA | 2022-08-30 | 2022-10-05 | 2022-10-11 | 36 | 6 | 42 | AFC | 2022-11-16 | 0 | 0 | -44881 | 0 | -44881 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-09 | 2022-11-02 |  | D04 | AFC | T-1571 | 44867 | 1401/08/10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0568 | 2022-02-09 | 1400/11/20 |  |  |  | BK-SUR-ENG-MEC-00-03304 | 44622 | 1400/12/11 | CM-C3 | [6 empty] | 1400-2294-430775 | 2022-03-01 | 1400/12/10 | 44625 | 1400/12/14 | CM | [10 empty] | D01 | IFA | T-0851 | 44671 | 1401/01/31 |  |  |  | BK-SUR-ENG-MEC-01-04152 | 44688 | 1401/02/17 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002-D00 | [5 empty] | 1401-2294-54998 | 44690 | 1401/02/19 | 44703 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002_D00 | [9 empty] | D02 | IFA | T-1100 | 44733 | 1401/03/31 | T-1100 | 44733 | 1401/03/31 | BK-SUR-ENG-MEC-01-05340 | 44776 | 1401/05/12 | CM-C3 | [6 empty] | 1401-2294-165013 | 44775 | 1401/05/11 | 44782 | 1401/05/18 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002_D01 | [9 empty] | D03 | IFA | T-1280 | 44789 | 1401/05/25 |  |  |  | BK-SUR-ENG-MEC-01-05793 | 44836 | 1401/07/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002-D02 | [5 empty] | 1401-2294-251971 | 44839 | 1401/07/13 | 44845 | 1401/07/19 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002_D02 | [9 empty] | D04 | AFC | T-1571 | 44867 | 1401/08/10 | [19 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002_D03
2 | 1 | 0 | 5 | 0 | 0 | 0 | 2.1.5 |  | Piping
2 | 1 | 0 | 5 | 0 | 1 | 0 | 2.1.5.1 |  | Specification | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 5 | 0 | 1 | 1 | 2.1.5.1.1 | BK-SSGRL-PEDCO-110-PI-SP-0001 | Piping Material Specification |  | BK-SSGRL-PEDCO-110-PI-SP-0001 | BK-SSGRL-PEDCO-110-PI-SP-0001 | BK | SSGRL | PEDCO | 110 | PI | SP | 0001 | F0Z-707353 | AFD | IFC | 2021-12-12 | 2021-12-22 | 2021-12-26 | 10 | 4 | 14 | IFA | 2022-04-13 | 2022-05-29 | 2022-05-30 | 46 | 1 | 47 | AFD | 2022-09-18 | 2022-09-20 | 2022-09-24 | 2 | 4 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-28 |  |  | D02 | AFD | T-1344 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05699 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-231558 | 44824 | 1401/06/29 | 44828 | 1401/07/02 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0278 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PIP-00-02246 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-331524 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0766 | 44650 | 1401/01/10 |  |  |  | BK-SUR-ENG-PIP-01-03917 | 44667 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D00 | [5 empty] | 1401-2294-78818 | 44710 | 1401/03/08 | 44711 | 1401/03/09 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D00 | [9 empty] | D02 | AFD | T-1344 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05699 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D01 | [5 empty] | 1401-2294-231558 | 44824 | 1401/06/29 | 44828 | 1401/07/02 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D01
2 | 1 | 0 | 5 | 0 | 2 | 0 | 2.1.5.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 5 | 0 | 2 | 1 | 2.1.5.2.1 | BK-SSGRL-PEDCO-110-PI-DT-0001 | Data Sheets For Stone Trap |  | BK-SSGRL-PEDCO-110-PI-DT-0001 | BK-SSGRL-PEDCO-110-PI-DT-0001 | BK | SSGRL | PEDCO | 110 | PI | DT | 0001 | F0Z-707354 | AFC | IFC | 2022-01-10 | 2022-01-03 | 2022-01-08 | -7 | 5 | -2 | IFA | 2022-04-19 | 2022-04-29 | 2022-05-14 | 10 | 15 | 25 | IFA | 2022-09-28 | 2022-09-29 | 2022-10-02 | 1 | 3 | 4 | AFC | 2022-10-23 | 2022-10-25 | 2022-10-29 | 2 | 4 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-27 | 2022-10-09 |  | D03 | AFC | T-1471 | 44843 | 1401/07/17 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05871 | 44844 | 1401/07/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-2810692 | 44859 | 1401/08/03 | 44863 | 1401/08/03 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0388 | 2021-12-27 | 1400/10/06 |  |  |  | BK-SUR-ENG-PIP-00-02554 | 44564 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-348122 | 2022-01-03 | 1400/10/13 | 44569 | 1400/10/18 | CM | [10 empty] | D01 | IFA | T-0777 | 44656 | 1401/01/16 |  |  |  | BK-SUR-ENG-PIP-01-03984 | 44669 | 1401/01/29 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D00 | [5 empty] | 1400-2294-43242 | 44680 | 1401/02/09 | 44695 | 1401/02/24 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D00 | [9 empty] | D02 | IFA | T-1402 | 44818 | 1401/06/23 | T-1402 | 44818 | 1401/06/23 | BK-SUR-ENG-PIP-01-05752 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D01 | [5 empty] | 1401-2294-240489 | 44833 | 1401/07/07 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D01 | [9 empty] | D03 | AFC | T-1471 | 44843 | 1401/07/17 |  |  |  | BK-SUR-ENG-PIP-01-05871 | 44844 | 1401/07/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D02 | [5 empty] | 1401-2294-2810692 | 44859 | 1401/08/03 | 44863 | 1401/08/03 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D02
2 | 1 | 0 | 5 | 0 | 3 | 0 | 2.1.5.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 5 | 0 | 3 | 1 | 2.1.5.3.1 | BK-SSGRL-PEDCO-110-PI-DW-0001 | Standard Pipe Support Drawings |  | BK-SSGRL-PEDCO-110-PI-DW-0001 | BK-SSGRL-PEDCO-110-PI-DW-0001 | BK | SSGRL | PEDCO | 110 | PI | DW | 0001 | F1L-707355 | IFI | IFI | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D00 | IFI | T-0605 | 44611 | 1400/11/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443258 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0605 | 2022-02-19 | 1400/11/30 | [13 empty] | 1400-2294-443258 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | CM
2 | 1 | 0 | 5 | 0 | 3 | 2 | 2.1.5.3.2 | BK-SSGRL-PEDCO-110-PI-DW-0002 | Piping Assembly Drawing |  | BK-SSGRL-PEDCO-110-PI-DW-0002 | BK-SSGRL-PEDCO-110-PI-DW-0002 | BK | SSGRL | PEDCO | 110 | PI | DW | 0002 | F1L-707356 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 1 | 0 | 5 | 0 | 3 | 3 | 2.1.5.3.3 | BK-SSGRL-PEDCO-110-PI-DW-0003 | Piping Hydrostatic Test Diagram - Sub Surface |  | BK-SSGRL-PEDCO-110-PI-DW-0003 | BK-SSGRL-PEDCO-110-PI-DW-0003 | BK | SSGRL | PEDCO | 110 | PI | DW | 0003 | F2L-707357 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 1 | 0 | 5 | 0 | 4 | 0 | 2.1.5.4 |  | Calculation
2 | 1 | 0 | 5 | 0 | 4 | 1 | 2.1.5.4.1 | BK-SSGRL-PEDCO-110-PI-CN-0001 | Piping Wall Thickness Calculation |  | BK-SSGRL-PEDCO-110-PI-CN-0001 | BK-SSGRL-PEDCO-110-PI-CN-0001 | BK | SSGRL | PEDCO | 110 | PI | CN | 0001 | F0Z-707358 | AFD | IFC | 2021-12-12 | 2021-12-22 | 2021-12-26 | 10 | 4 | 14 | IFA | 2022-04-13 | 2022-05-29 | 2022-05-29 | 46 | 0 | 46 | AFD | 2022-09-18 | 2022-09-20 | 2022-09-24 | 2 | 4 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-28 |  |  | D02 | AFD | T-1344 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05699 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-231558 | 44824 | 1401/06/29 | 44828 | 1401/07/02 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0278 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PIP-00-02246 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-331524 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0766 | 44650 | 1401/01/10 |  |  |  | BK-SUR-ENG-PIP-01-03917 | 44667 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D00 | [5 empty] | 1401-2294-78818 | 44710 | 1401/03/08 | 44710 | 1401/03/08 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D00 | [9 empty] | D02 | AFD | T-1344 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05699 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D01 | [5 empty] | 1401-2294-231558 | 44824 | 1401/06/29 | 44828 | 1401/07/02 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D01
2 | 1 | 0 | 5 | 0 | 5 | 0 | 2.1.5.5 |  | Report
2 | 1 | 0 | 5 | 0 | 5 | 1 | 2.1.5.5.1 | BK-SSGRL-PEDCO-110-PI-RT-0001 | Piping Corrosion Study & Material Selection Report |  | BK-SSGRL-PEDCO-110-PI-RT-0001 | BK-SSGRL-PEDCO-110-PI-RT-0001 | BK | SSGRL | PEDCO | 110 | PI | RT | 0001 | F0Z-707359 | IFI | IFC | 2021-12-12 | 2021-12-22 | 2021-12-26 | 10 | 4 | 14 | IFA | 2022-04-13 | 2022-05-29 | 0 | 46 | -44710 | -44664 | AFC | 2022-09-11 | 2022-09-29 | 2022-10-03 | 18 | 4 | 22 | AFD | 2022-11-02 | 0 | 0 | -44867 | 0 | -44867 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-28 | 2022-10-19 |  | D03 | AFD | T-1521 | 44853 | 1401/07/27 | T-1521 | 44853 | 1401/07/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0278 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PIP-00-02322 | 44548 | 1400/09/27 | CM-C2 | [6 empty] | 1400-2294-331524 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0766 | 44650 | 1401/01/10 |  |  |  | BK-SUR-ENG-PIP-01-03917 | 44667 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D00 | [5 empty] | 1401-2294-78818 | 44710 | 1401/03/08 |  |  |  | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D00 | [9 empty] | D02 | AFC | T-1327 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-PIP-01-05697 | 44818 | 1401/06/23 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D01 | [5 empty] | 1401-2294-240496 | 44833 | 1401/07/07 | 44837 | 1401/07/11 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D01 | [9 empty] | D03 | AFD | T-1521 | 44853 | 1401/07/27 | T-1521 | 44853 | 1401/07/27 | [16 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D02
2 | 1 | 0 | 6 | 0 | 0 | 0 | 2.1.6 |  | Pipeline & Flow line | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 6 | 0 | 1 | 0 | 2.1.6.1
2 | 1 | 0 | 6 | 0 | 1 | 1 | 2.1.6.1.1 | BK-SSGRL-PEDCO-110-PL-SP-0001 | Pipeline Material Specification |  | BK-SSGRL-PEDCO-110-PL-SP-0001 | BK-SSGRL-PEDCO-110-PL-SP-0001 | BK | SSGRL | PEDCO | 110 | PL | SP | 0001 | F0Z-707360 | AFD | IFC | 2021-11-10 | 2021-11-16 | 2021-11-21 | 6 | 5 | 11 | IFA | 2021-12-18 | 0 | 0 | -44548 | 0 | -44548 | IFA | 2022-06-07 | 2022-07-10 | 2022-07-30 | 33 | 20 | 53 | AFD | 2022-09-11 | 2022-09-29 | 2022-10-02 | 18 | 3 | 21 | AFD | 2022-11-02 | 0 | 0 | -44867 | 0 | -44867 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-27 | 2022-10-19 |  | D04 | AFD | T-1517 | 44853 | 1401/07/27 | T-1517 | 44853 | 1401/07/27 | BK-SUR-ENG-PPL-01-05978 | 44860 | 1401/08/04 | CM | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0190 | 2021-10-27 | 1400/08/05 |  |  |  | BK-SUR-ENG-PPL-00-01931 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-279110 | 2021-11-16 | 1400/08/25 | 44521 | 1400/08/30 | CM | [10 empty] | D01 | IFA | T-0291 | 44534 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02462 | 44557 | 1400/10/06 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D00 | [9 empty] | D02 | IFA | T-0997 | 44705 | 1401/03/03 | T-0997 | 44709 | 1401/03/07 | BK-SUR-ENG-PPL-01-04589 | 44719 | 1401/03/17 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D01 | [5 empty] | 1401-2294-135308 | 44752 | 1401/04/19 | 44772 | 1401/05/08 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D01 | [9 empty] | D03 | AFD | T-1326 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-PPL-01-05696 | 44818 | 1401/06/23 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D02 | [5 empty] | 1401-2294-240491 | 44833 | 1401/07/07 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D02 | [9 empty] | D04 | AFD | T-1517 | 44853 | 1401/07/27 | T-1517 | 44853 | 1401/07/27 | BK-SUR-ENG-PPL-01-05978 | 44860 | 1401/08/04 | CM | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D03 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D03
2 | 1 | 0 | 6 | 0 | 2 | 0 | 2.1.6.2 |  | Drawing/Diagram
2 | 1 | 0 | 6 | 0 | 2 | 1 | 2.1.6.2.1 | BK-SSGRL-PEDCO-110-PL-DW-0001 | Pipeline Standard Support Drawings |  | BK-SSGRL-PEDCO-110-PL-DW-0001 | BK-SSGRL-PEDCO-110-PL-DW-0001 | BK | SSGRL | PEDCO | 110 | PL | DW | 0001 | F2L-707361 | IFI | IFI | 2021-08-10 | 2021-08-04 | 0 | -6 | -44412 | -44418 | IFI | 2021-11-29 | 2021-11-24 | 2021-11-27 | -5 | 3 | -2 | IFI | 2022-01-19 | 2022-01-12 | 2022-01-15 | -7 | 3 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-27 |  |  | D02 | IFI | T-0432 | 44566 | 1400/10/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02648 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-DW-0001-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-362222 | 44573 | 1400/10/22 | 44576 | 1400/10/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-DW-0001-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0013 | 2021-07-27 | 1400/05/05 |  |  |  | BK-SUR-ENG-PPL-00-01270 | 44415 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/153763 | 2021-08-04 | 1400/05/13 |  |  | CM | [10 empty] | D01 | IFI | T-0247 | 44515 | 1400/08/24 |  |  |  | BK-SUR-ENG-PPL-00-02073 | 44522 | 1400/09/01 | CM-C2 | PEDCO-CRS-D00-BK-SSGRL-PEDCO-110-PL-DW-0001-D00 | [5 empty] | 1400-2294-290695 | 44524 | 1400/09/03 | 44527 | 1400/09/06 | CM | NISOC-CRS-D00-BK-SSGRL-PEDCO-110-PL-DW-0001-D00 | [9 empty] | D02 | IFI | T-0432 | 44566 | 1400/10/15 |  |  |  | BK-SUR-ENG-PPL-00-02648 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-DW-0001-D01 | [5 empty] | 1400-2294-362222 | 44573 | 1400/10/22 | 44576 | 1400/10/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-DW-0001-D01
2 | 1 | 0 | 6 | 0 | 2 | 2 | 2.1.6.2.2 | BK-SSGRL-PEDCO-110-PL-DG-0001 | Pipeline Hydrostatic Test Diagram - Sub Surface |  | BK-SSGRL-PEDCO-110-PL-DG-0001 | BK-SSGRL-PEDCO-110-PL-DG-0001 | BK | SSGRL | PEDCO | 110 | PL | DG | 0001 | F2L-707362 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 1 | 0 | 6 | 0 | 3 | 0 | 2.1.6.3 |  | Calculation
2 | 1 | 0 | 6 | 0 | 3 | 1 | 2.1.6.3.1 | BK-SSGRL-PEDCO-110-PL-CN-0001 | Pipeline Wall Thickness Calculation |  | BK-SSGRL-PEDCO-110-PL-CN-0001 | BK-SSGRL-PEDCO-110-PL-CN-0001 | BK | SSGRL | PEDCO | 110 | PL | CN | 0001 | F0Z-707363 | AFD | IFC | 2021-11-10 | 2021-11-16 | 2021-11-21 | 6 | 5 | 11 | IFA | 2021-12-18 | 2022-08-03 | 2022-08-03 | 228 | 0 | 228 | AFD | 2022-09-11 | 2022-09-29 | 2022-10-02 | 18 | 3 | 21 | AFD | 2022-11-02 | 0 | 0 | -44867 | 0 | -44867 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-27 | 2022-10-19 |  | D03 | AFD | T-1517 | 44853 | 1401/07/27 | T-1517 | 44853 | 1401/07/27 | BK-SUR-ENG-PPL-01-05978 | 44860 | 1401/08/04 | CM | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0190 | 2021-10-27 | 1400/08/05 |  |  |  | BK-SUR-ENG-PPL-00-01931 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-279110 | 2021-11-16 | 1400/08/25 | 44521 | 1400/08/30 | CM | [10 empty] | D01 | IFA | T-0291 | 44534 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02462 | 44557 | 1400/10/06 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D00 | [5 empty] | Comment Sheets\NISOC\صورتجلسه 14010512 - مطالعات خوردگی فلولاین (4).pdf | 44776 | 1401/05/12 | 44776 | 1401/05/12 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D00 | [9 empty] | D02 | AFD | T-1326 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-PPL-01-05696 | 44818 | 1401/06/23 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D01 | [5 empty] | 1401-2294-240491 | 44833 | 1401/07/07 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D01 | [9 empty] | D03 | AFD | T-1517 | 44853 | 1401/07/27 | T-1517 | 44853 | 1401/07/27 | BK-SUR-ENG-PPL-01-05978 | 44860 | 1401/08/04 | CM | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D02 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D02
2 | 1 | 0 | 6 | 0 | 4 | 0 | 2.1.6.4 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 6 | 0 | 4 | 1 | 2.1.6.4.1 | BK-SSGRL-PEDCO-110-PL-RT-0001 | Pipeline Corrosion Study & Material Selection Report |  | BK-SSGRL-PEDCO-110-PL-RT-0001 | BK-SSGRL-PEDCO-110-PL-RT-0001 | BK | SSGRL | PEDCO | 110 | PL | RT | 0001 | F0Z-707364 | IFI | IFC | 2021-11-10 | 2021-11-16 | 2021-11-21 | 6 | 5 | 11 | IFA | 2021-12-18 | 0 | 0 | -44548 | 0 | -44548 | IFA | 2022-03-14 | 2022-03-16 | 2022-04-01 | 2 | 16 | 18 | AFD | 2022-09-11 | 2022-09-29 | 2022-10-02 | 18 | 3 | 21 | AFD | 2022-11-02 | 0 | 0 | -44867 | 0 | -44867 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Deleted | 2021-10-27 | 2022-10-19 |  | D04 | AFD | T-1517 | 44853 | 1401/07/27 | T-1517 | 44853 | 1401/07/27 | BK-SUR-ENG-PPL-01-05978 | 44860 | 1401/08/04 | CM | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0190 | 2021-10-27 | 1400/08/05 |  |  |  | BK-SUR-ENG-PPL-00-02059 | 44521 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-279110 | 2021-11-16 | 1400/08/25 | 44521 | 1400/08/30 | CM | [10 empty] | D01 | IFA | T-0291 | 44534 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02462 | 44557 | 1400/10/06 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001-D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001-D00 | [9 empty] | D02 | IFA | T-0658 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-PPL-00-03447 | 44632 | 1400/12/21 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D01 | [5 empty] | 1400-2294-453303 | 44636 | 1400/12/25 | 44652 | 1401/01/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D01 | [9 empty] | D03 | AFD | T-1326 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-PPL-01-05696 | 44818 | 1401/06/23 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D02 | [5 empty] | 1401-2294-240491 | 44833 | 1401/07/07 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D02 | [9 empty] | D04 | AFD | T-1517 | 44853 | 1401/07/27 | T-1517 | 44853 | 1401/07/27 | BK-SUR-ENG-PPL-01-05978 | 44860 | 1401/08/04 | CM | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D03 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D03
2 | 1 | 0 | 7 | 0 | 0 | 0 | 2.1.7 |  | Control & Instrumentation
2 | 1 | 0 | 7 | 0 | 1 | 0 | 2.1.7.1 |  | Basis/Criteria | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 7 | 0 | 1 | 1 | 2.1.7.1.1 | BK-SSGRL-PEDCO-110-IN-DC-0002 | Instrument & Control System Design Criteria |  | BK-SSGRL-PEDCO-110-IN-DC-0002 | BK-SSGRL-PEDCO-110-IN-DC-0002 | BK | SSGRL | PEDCO | 110 | IN | DC | 0002 | F0Z-707366 | AFD | IFC | 2022-01-17 | 2022-02-16 | 2022-02-21 | 30 | 5 | 35 | IFA | 2022-05-31 | 2022-08-02 | 2022-08-06 | 63 | 4 | 67 | IFA | 2022-11-07 | 0 | 0 | -44872 | 0 | -44872 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-03 |  |  | D02 | IFA | T-1541 | 44858 | 1401/08/02 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-06119 | 44872 | 1401/08/16 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0420 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-INS-00-02625 | 44571 | 1400/10/20 | CM-C3 | [6 empty] | 1400-2294-412682 | 2022-02-16 | 1400/11/27 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0968 | 44698 | 1401/02/27 | T-0968 | 44698 | 1401/02/27 | BK-SUR-ENG-INS-01-04496 | 44713 | 1401/03/11 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D00 | [5 empty] | 1401-2294-164856 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D00 | [9 empty] | D02 | IFA | T-1541 | 44858 | 1401/08/02 |  |  |  | BK-SUR-ENG-INS-01-06119 | 44872 | 1401/08/16 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D01 | [11 empty] | NISCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D01
2 | 1 | 0 | 7 | 0 | 1 | 2 | 2.1.7.1.2 | BK-SSGRL-PEDCO-110-IN-DC-0001 | Fire & Gas Detection Design Criteria |  | BK-SSGRL-PEDCO-110-IN-DC-0001 | BK-SSGRL-PEDCO-110-IN-DC-0001 | BK | SSGRL | PEDCO | 110 | IN | DC | 0001 | F0Z-707365 | AFD | IFC | 2021-08-28 | 2021-09-15 | 2021-09-14 | 18 | -1 | 17 | IFA | 2021-11-03 | 2021-10-29 | 2021-11-03 | -5 | 5 | 0 | AFD | 2022-01-15 | 2022-01-26 | 2022-01-29 | 11 | 3 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-14 | 2022-01-01 |  | D02 | AFD | T-0414 | 44562 | 1400/10/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0001-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-382426 | 44587 | 1400/11/06 | 44590 | 1400/11/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0045 | 2021-08-14 | 1400/05/23 | [13 empty] | 1400-2294-193915 | 2021-09-15 | 1400/06/20 | 44453 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0178 | 44489 | 1400/07/28 |  |  |  | BK-SUR-ENG-INS-00-01906 | 44503 | 1400/08/12 | CM-C3 | [6 empty] | 1400-2294-251691 | 44498 | 1400/08/07 | 44503 | 1400/08/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-DS-0001-D00 | [9 empty] | D02 | AFD | T-0414 | 44562 | 1400/10/11 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0001-D01 | [5 empty] | 1400-2294-382426 | 44587 | 1400/11/06 | 44590 | 1400/11/09 | AP
2 | 1 | 0 | 7 | 0 | 1 | 3 | 2.1.7.1.3 | BK-SSGRL-PEDCO-110-IN-DB-0001 | Instrument & Control System Basis of Design |  | BK-SSGRL-PEDCO-110-IN-DB-0001 | [8 empty] | - |  | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 5 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D00 | IFC | T-0054 | 44430 | 1400/05/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-200192 | 44454 | 1400/06/24 | 44459 | 1400/06/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0054 | 2021-08-22 | 1400/05/31 | [13 empty] | 1400-2294-200192 | 2021-09-15 | 1400/06/24 | 44459 | 1400/06/29 | CM
2 | 1 | 0 | 7 | 0 | 2 | 0 | 2.1.7.2 |  | Specification | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 7 | 0 | 2 | 1 | 2.1.7.2.1 | BK-SSGRL-PEDCO-110-IN-SP-0001 | Specification For WHCP/HPU |  | BK-SSGRL-PEDCO-110-IN-SP-0001 | BK-SSGRL-PEDCO-110-IN-SP-0001 | BK | SSGRL | PEDCO | 110 | IN | SP | 0001 | F9J-707367 | AFD | IFC | 2021-08-22 | 2021-09-18 | 2021-09-14 | 27 | -4 | 23 | IFA | 2021-10-24 | 2021-12-30 | 2022-01-02 | 67 | 3 | 70 | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 | AFD | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-08-08 | 2022-03-27 |  | D03 | AFD | T-0748 | 44647 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03940 | 44667 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-25743 | 44668 | 1401/01/28 | 44676 | 1401/02/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0034 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-INS-00-01375 | 44430 | 1400/06/31 | CM-C3 | [6 empty] | 1400-2294-193985 | 2021-09-18 | 1400/06/20 | 44453 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0143 | 44479 | 1400/07/18 |  |  |  | BK-SUR-ENG-INS-00-01846 | 44495 | 1400/08/04 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D00 | [5 empty] | 1400-2294-320796 | 44547 | 1400/09/26 | 44563 | 1400/10/12 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D00 | 1400-2294-342129 | 44560 | 1400/10/09 |  |  | CM |  |  |  | D02 | IFA | T-0444 | 44571 | 1400/10/20 |  |  |  | BK-SUR-ENG-INS-00-02815 | 44586 | 1400/11/05 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D01 | [5 empty] | 1400-2294-385430 | 44590 | 1400/11/09 | 44591 | 1400/11/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D01 | [9 empty] | D03 | AFD | T-0748 | 44647 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03940 | 44667 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D02 | [5 empty] | 1401-2294-25743 | 44668 | 1401/01/28 | 44676 | 1401/02/05 | AP
2 | 1 | 0 | 7 | 0 | 3 | 0 | 2.1.7.3 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 7 | 0 | 3 | 1 | 2.1.7.3.1 | BK-SSGRL-PEDCO-110-IN-DT-0001 | Data Sheets For WHCP/HPU - Wellheads |  | BK-SSGRL-PEDCO-110-IN-DT-0001 | BK-SSGRL-PEDCO-110-IN-DT-0001 | BK | SSGRL | PEDCO | 110 | IN | DT | 0001 | F9Z-707368 | AFC | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 5 | 15 | IFA | 2021-11-23 | 2021-11-21 | 2021-11-27 | -2 | 6 | 4 | IFA | 2022-01-04 | 2022-01-06 | 2022-01-08 | 2 | 2 | 4 | IFA | 2022-07-02 | 2022-08-28 | 2022-08-25 | 57 | -3 | 54 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D03 | IFA | T-1084 | 44730 | 1401/03/28 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05236 | 44767 | 1401/05/03 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-194443 | 44801 | 1401/06/06 | 44798 | 1401/06/03 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0054 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-INS-00-01426 | 44437 | 1400/06/07 | CM-C3 | [6 empty] | 1400-2294-200192 | 2021-09-15 | 1400/06/24 | 44459 | 1400/06/29 | CM | [10 empty] | D01 | IFA | T-0218 | 44509 | 1400/08/18 |  |  |  | BK-SUR-ENG-INS-00-02067 | 44521 | 1400/08/30 | C4-RJ | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D00 | [5 empty] | 1400-2294-283482 | 44521 | 1400/08/30 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D00 | [9 empty] | D02 | IFA | T-0374 | 44551 | 1400/09/30 |  |  |  | BK-SUR-ENG-INS-00-02519 | 44563 | 1400/10/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D01 | [5 empty] | 1400-2294-352435 | 44567 | 1400/10/16 | 44569 | 1400/10/18 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D01 | [9 empty] | D03 | IFA | T-1084 | 44730 | 1401/03/28 |  |  |  | BK-SUR-ENG-INS-01-05236 | 44767 | 1401/05/03 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D02 | [5 empty] | 1401-2294-194443 | 44801 | 1401/06/06 | 44798 | 1401/06/03 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D02
2 | 1 | 0 | 7 | 0 | 3 | 2 | 2.1.7.3.2 | BK-SSGRL-PEDCO-110-IN-DT-0002 | Data Sheets For Pressure Gauge - Wellheads |  | BK-SSGRL-PEDCO-110-IN-DT-0002 | BK-SSGRL-PEDCO-110-IN-DT-0002 | BK | SSGRL | PEDCO | 110 | IN | DT | 0002 | F9Z-707369 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-16 | 2022-03-15 | 2022-03-25 | -1 | 10 | 9 | IFA | 2022-08-13 | 2022-09-24 | 2022-10-02 | 42 | 8 | 50 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-07 |  |  | D02 | IFA | T-1220 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05462 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-235789 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0308 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02404 | 44552 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342119 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0660 | 44622 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03646 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D00 | [5 empty] | 1400-2294-449418 | 44635 | 1400/12/24 | 44645 | 1401/01/08 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D00 | [9 empty] | D02 | IFA | T-1220 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05462 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D01 | [5 empty] | 1401-2294-235789 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D01
2 | 1 | 0 | 7 | 0 | 3 | 3 | 2.1.7.3.3 | BK-SSGRL-PEDCO-110-IN-DT-0003 | Data Sheets For Temperature Gauge - Wellheads |  | BK-SSGRL-PEDCO-110-IN-DT-0003 | BK-SSGRL-PEDCO-110-IN-DT-0003 | BK | SSGRL | PEDCO | 110 | IN | DT | 0003 | F9Z-707370 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-16 | 2022-03-15 | 2022-03-25 | -1 | 10 | 9 | AFC | 2022-08-10 | 0 | 0 | -44783 | 0 | -44783 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 | 2022-07-27 |  | D02 | AFC | T-1210 | 44769 | 1401/05/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05407 | 44783 | 1401/05/19 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0308 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02404 | 44552 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342119 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0660 | 44622 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03646 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0003_D00 | [5 empty] | 1400-2294-449418 | 44635 | 1400/12/24 | 44645 | 1401/01/08 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0003_D00 | [9 empty] | D02 | AFC | T-1210 | 44769 | 1401/05/05 |  |  |  | BK-SUR-ENG-INS-01-05407 | 44783 | 1401/05/19 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0003_D01
[8 empty] | BK-SSGRL-PEDCO-110-IN-DT-0004 | Data sheets for level Gauge |  | BK-SSGRL-PEDCO-110-IN-DT-0004 | BK-SSGRL-PEDCO-110-IN-DT-0004 | BK | SSGRL | PEDCO | 110 | IN | DT | 0004 | F9Z-709408 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 1 | 0 | 7 | 0 | 4 | 0 | 2.1.7.4 |  | Drawing/Diagram
2 | 1 | 0 | 7 | 0 | 4 | 1 | 2.1.7.4.1 | BK-SSGRL-PEDCO-110-IN-DG-0001 | Instrument Hook-up Diagram - Wellheads |  | BK-SSGRL-PEDCO-110-IN-DG-0001 | BK-SSGRL-PEDCO-110-IN-DG-0001 | BK | SSGRL | PEDCO | 110 | IN | DG | 0001 | F2J-707371 | AFC | IFC | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFA | 2022-01-02 | 2022-03-09 | 2022-03-13 | 66 | 4 | 70 | IFA | 2022-05-23 | 2022-05-29 | 2022-05-31 | 6 | 2 | 8 | IFA | 2022-08-09 | 2022-09-18 | 2022-09-21 | 40 | 3 | 43 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-14 |  |  | D03 | IFA | T-1198 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05392 | 44782 | 1401/05/18 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-227955 | 44822 | 1401/06/27 | 44825 | 1401/06/30 | AP | NISCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0235 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02137 | 44529 | 1400/09/08 | RJ-C4 | [6 empty] | 1400-2294-283471 | 2021-11-21 | 1400/08/30 | 44529 | 1400/09/08 | CM | [10 empty] | D01 | IFA | T-0364 | 44549 | 1400/09/28 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D00 | [5 empty] | 1400-2294-347498 | 44199 | 1400/10/13 | 44565 | 1400/10/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D00 | 1400-2294-442076 | 44629 | 1400/12/18 | 44633 | 1400/12/22 | AP |  |  |  | D02 | IFA | T-0922 | 44690 | 1401/02/19 |  |  |  | BK-SUR-ENG-INS-01-04475 | 44710 | 1401/03/08 | CM-C2 | [6 empty] | 1401-2294-78805 | 44710 | 1401/03/08 | 44712 | 1401/03/10 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D01 | [9 empty] | D03 | IFA | T-1198 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-INS-01-05392 | 44782 | 1401/05/18 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D02 | [5 empty] | 1401-2294-227955 | 44822 | 1401/06/27 | 44825 | 1401/06/30 | AP | NISCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D02
2 | 1 | 0 | 7 | 0 | 4 | 2 | 2.1.7.4.2 | BK-SSGRL-PEDCO-110-IN-DG-0002 | WHCP Hydraulic \Peneumatic Diagrams - Wellheads |  | BK-SSGRL-PEDCO-110-IN-DG-0002 | BK-SSGRL-PEDCO-110-IN-DG-0002 | BK | SSGRL | PEDCO | 110 | IN | DG | 0002 | F2J-707372 | AFC | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 5 | 15 | IFA | 2021-11-24 | 2021-11-21 | 2021-11-27 | -3 | 6 | 3 | AFC | 2022-01-03 | 2022-01-06 | 2022-01-08 | 3 | 2 | 5 | AFC | 2022-06-29 | 2022-08-17 | 2022-08-21 | 49 | 4 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-08-22 | 2022-06-15 |  | D03 | AFC | T-1078 | 44727 | 1401/03/25 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05103 | 44754 | 1401/04/21 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183421 | 44790 | 1401/05/26 | 44794 | 1401/05/30 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0054 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-INS-00-01426 | 44437 | 1400/06/07 | CM-C3 | [6 empty] | 1400-2294-200192 | 2021-09-15 | 1400/06/24 | 44459 | 1400/06/29 | CM | [10 empty] | D01 | IFA | T-0230 | 44510 | 1400/08/19 |  |  |  | BK-SUR-ENG-INS-00-02064 | 44521 | 1400/08/30 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D00 | [5 empty] | 1400-2294-283484 | 44521 | 1400/08/30 | 44527 | 1400/09/06 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002-D00 | [9 empty] | D02 | AFC | T-0369 | 44550 | 1400/09/29 |  |  |  | BK-SUR-ENG-INS-00-02502 | 44562 | 1400/10/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D01 | [5 empty] | 1400-2294-352438 | 44567 | 1400/10/16 | 44569 | 1400/10/18 | CM | [10 empty] | D03 | AFC | T-1078 | 44727 | 1401/03/25 |  |  |  | BK-SUR-ENG-INS-01-05103 | 44754 | 1401/04/21 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D02 | [5 empty] | 1401-2294-183421 | 44790 | 1401/05/26 | 44794 | 1401/05/30 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D02
2 | 1 | 0 | 7 | 0 | 5 | 0 | 2.1.7.5 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 7 | 0 | 5 | 1 | 2.1.7.5.1 | BK-SSGRL-PEDCO-110-IN-LI-0001 | Instrument Index For New Wells & Manifold Extension |  | BK-SSGRL-PEDCO-110-IN-LI-0001 | BK-SSGRL-PEDCO-110-IN-LI-0001 | BK | SSGRL | PEDCO | 110 | IN | LI | 0001 | F0Z-707373 | AFC | IFI | 2021-11-24 | 2021-11-21 | 2021-11-27 | -3 | 6 | 3 | IFA | 2022-03-16 | 2022-03-12 | 2022-03-12 | -4 | 0 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 |  |  | D01 | IFA | T-0666 | 44622 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03648 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445246 | 44632 | 1400/12/21 | 44632 | 1400/12/21 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0229 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-INS-00-02062 | 44521 | 1400/08/30 | CM | [6 empty] | 1400-2294-283479 | 2021-11-21 | 1400/08/30 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0666 | 44622 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03648 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-LI-0001_D00 | [5 empty] | 1400-2294-445246 | 44632 | 1400/12/21 | 44632 | 1400/12/21 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-LI-0001_D00
[8 empty] | BK-SSGRL-PEDCO-110-IN-LI-0002 | Set Point & Alarm List- Wellheads |  | BK-SSGRL-PEDCO-110-IN-LI-0002 | [63 empty] | D00 | IFC | T-1395 | 44816 | 1401/06/21 | T-1395 | 44816 | 1401/06/21 | BK-SUR-ENG-INS-01-05767 | 44830 | 1401/07/04 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-278657 | 44857 | 1401/08/02 | 44859 | 1401/08/04 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1395 | 2022-09-12 | 1401/06/21 | T-1395 | 44816 | 1401/06/21 | BK-SUR-ENG-INS-01-05767 | 44830 | 1401/07/04 | CM-C2 | [6 empty] | 1401-2294-278657 | 2022-10-23 | 1401/08/02 | 44859 | 1401/08/04 | AP
2 | 1 | 0 | 8 | 0 | 0 | 0 | 2.1.8 |  | Safety | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 8 | 0 | 1 | 0 | 2.1.8.1 |  | Basis/Criteria
2 | 1 | 0 | 8 | 0 | 1 | 1 | 2.1.8.1.1 | BK-SSGRL-PEDCO-110-SA-DC-0001 | Active Fire Protection and Safety Concept |  | BK-SSGRL-PEDCO-110-SA-DC-0001 | BK-SSGRL-PEDCO-110-SA-DC-0001 | BK | SSGRL | PEDCO | 110 | SA | DC | 0001 | F0Z-707374 | AFD | IFC | 2021-09-12 | 2021-09-13 | 2021-09-18 | 1 | 5 | 6 | IFA | 2021-11-08 | 2021-11-22 | 2021-11-27 | 14 | 5 | 19 | AFD | 2021-12-20 | 2021-12-09 | 2021-12-14 | -11 | 5 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-08-29 | 2021-12-06 |  | D02 | AFD | T-0297 | 44536 | 1400/09/15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-310955 | 44539 | 1400/09/18 | 44544 | 1400/09/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0070 | 2021-08-29 | 1400/06/07 | [13 empty] | 1400-2294-197171 | 2021-09-13 | 1400/06/22 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0184 | 44494 | 1400/08/03 | [13 empty] | 1400-2294-286876 | 44522 | 1400/09/01 | 44527 | 1400/09/06 | AP | NISOC-CRS- BK-SSGRL-PEDCO- 110-SA-DC-0001-D00 | [9 empty] | D02 | AFD | T-0297 | 44536 | 1400/09/15 | [13 empty] | 1400-2294-310955 | 44539 | 1400/09/18 | 44544 | 1400/09/23 | AP
2 | 1 | 0 | 8 | 0 | 2 | 0 | 2.1.8.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 8 | 0 | 2 | 1 | 2.1.8.2.1 | BK-SSGRL-PEDCO-110-SA-DT-0001 | Data Sheets For Fire Fighting Equipment |  | BK-SSGRL-PEDCO-110-SA-DT-0001 | BK-SSGRL-PEDCO-110-SA-DT-0001 | BK | SSGRL | PEDCO | 110 | SA | DT | 0001 | F0Z-707375 | AFC | IFC | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | AFC | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | AFC | 2022-04-20 | 2022-04-19 | 2022-04-30 | -1 | 11 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-08 | 2022-04-06 |  | D02 | AFC | T-0782 | 44657 | 1401/01/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31231 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0320 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327319 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | AP | [10 empty] | D01 | AFC | T-0440 | 44570 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 44572 | 1400/10/21 | 44591 | 1400/11/10 | CM | [10 empty] | D02 | AFC | T-0782 | 44657 | 1401/01/17 | [13 empty] | 1401-2294-31231 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | AP
2 | 1 | 0 | 8 | 0 | 2 | 2 | 2.1.8.2.2 | BK-SSGRL-PEDCO-110-SA-DT-0002 | Data Sheets For Safety Equipment |  | BK-SSGRL-PEDCO-110-SA-DT-0002 | BK-SSGRL-PEDCO-110-SA-DT-0002 | BK | SSGRL | PEDCO | 110 | SA | DT | 0002 | F0Z-707376 | AFC | IFC | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | AFC | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-08 | 2022-01-09 |  | D01 | AFC | T-0440 | 44570 | 1400/10/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-360413 | 44572 | 1400/10/21 | 44591 | 1400/11/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0320 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327319 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | AP | [10 empty] | D01 | AFC | T-0440 | 44570 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 44572 | 1400/10/21 | 44591 | 1400/11/10 | AP
2 | 1 | 0 | 8 | 0 | 2 | 3 | 2.1.8.2.3 | BK-SSGRL-PEDCO-110-SA-DT-0003 | Data Sheets For Safety Sign |  | BK-SSGRL-PEDCO-110-SA-DT-0003 | BK-SSGRL-PEDCO-110-SA-DT-0003 | BK | SSGRL | PEDCO | 110 | SA | DT | 0003 | F0Z-707377 | AFC | IFC | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | AFC | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-08 | 2022-01-09 |  | D01 | AFC | T-0440 | 44570 | 1400/10/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-360413 | 44572 | 1400/10/21 | 44591 | 1400/11/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0320 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327319 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | AP | [10 empty] | D01 | AFC | T-0440 | 44570 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 44572 | 1400/10/21 | 44591 | 1400/11/10 | AP
2 | 1 | 0 | 9 | 0 | 0 | 0 | 2.1.9 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 9 | 0 | 1 | 0 | 2.1.9.1 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 9 | 0 | 1 | 1 | 2.1.9.1.1 | BK-SSGRL-PEDCO-110-EL-CN-0002 | Calculation Note For Lighting System of Well Pads Switchgear Building |  | BK-SSGRL-PEDCO-110-EL-CN-0002 | BK-SSGRL-PEDCO-110-EL-CN-0002 | BK | SSGRL | PEDCO | 110 | EL | CN | 0002 | F0Z-707378 | AFD | IFC | 2022-05-25 | 2022-06-01 | 2022-06-06 | 7 | 5 | 12 | IFA | 2022-10-26 | 2022-10-25 | 2022-10-29 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-11 |  |  | D01 | IFA | T-1490 | 44846 | 1401/07/20 | T-1490 | 44846 | 1401/07/20 | BK-SUR-ENG-ELE-01-05982 | 44860 | 1401/08/04 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-280865 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0930 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-ELE-01-04347 | 44703 | 1401/03/01 | CM-C2 | [6 empty] | 1401-2294-87162 | 2022-06-01 | 1401/03/11 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1490 | 44846 | 1401/07/20 | T-1490 | 44846 | 1401/07/20 | BK-SUR-ENG-ELE-01-05982 | 44860 | 1401/08/04 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0002_D00 | [5 empty] | 1401-2294-280865 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0002_D00
2 | 1 | 0 | 9 | 0 | 1 | 2 | 2.1.9.1.2 | BK-SSGRL-PEDCO-110-EL-CN-0003 | Calculation Note For Lighting System of Well Pads Security Building |  | BK-SSGRL-PEDCO-110-EL-CN-0003 | BK-SSGRL-PEDCO-110-EL-CN-0003 | BK | SSGRL | PEDCO | 110 | EL | CN | 0003 | F0Z-707379 | AFD | IFC | 2022-05-14 | 2022-05-30 | 2022-10-02 | 16 | 125 | 141 | IFA | 2022-10-18 | 2022-10-25 | 2022-10-29 | 7 | 4 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-30 |  |  | D01 | IFA | T-1456 | 44838 | 1401/07/12 | T-1456 | 44838 | 1401/07/12 | BK-SUR-ENG-ELE-01-05917 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-280883 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0879 | 2022-04-30 | 1401/02/10 | T-0879 | 44681 | 1401/02/10 | BK-SUR-ENG-ELE-01-04215 | 44691 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-82854 | 2022-05-30 | 1401/03/09 | 44836 | 1401/07/10 | CM | [10 empty] | D01 | IFA | T-1456 | 44838 | 1401/07/12 | T-1456 | 44838 | 1401/07/12 | BK-SUR-ENG-ELE-01-05917 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0003_D00 | [5 empty] | 1401-2294-280883 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0003_D00
2 | 1 | 0 | 9 | 0 | 1 | 3 | 2.1.9.1.3 | BK-SSGRL-PEDCO-110-EL-CN-0004 | Calculation Note For Lighting System of Well Pads Area |  | BK-SSGRL-PEDCO-110-EL-CN-0004 | BK-SSGRL-PEDCO-110-EL-CN-0004 | BK | SSGRL | PEDCO | 110 | EL | CN | 0004 | F0Z-707380 | AFD | IFC | 2022-05-28 | 2022-05-31 | 2022-06-16 | 3 | 16 | 19 | IFA | 2022-08-13 | 2022-09-06 | 2022-09-11 | 24 | 5 | 29 | IFA | 2022-10-29 | 2022-10-29 | 2022-10-30 | 0 | 1 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-14 |  |  | D02 | IFA | T-1496 | 44849 | 1401/07/23 | T-1496 | 44849 | 1401/07/23 | BK-SUR-ENG-ELE-01-06004 | 44863 | 1401/08/07 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284217 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0939 | 2022-05-14 | 1401/02/24 | T-0939 | 44695 | 1401/02/24 | BK-SUR-ENG-ELE-01-04389 | 44704 | 1401/03/02 | CM-C2 | [6 empty] | 1401-2294-85204 | 2022-05-31 | 1401/03/10 | 44728 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1219 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-ELE-01-05417 | 44786 | 1401/05/22 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0004_D00 | [5 empty] | 1401-2294-213820 | 44810 | 1401/06/15 | 44815 | 1401/06/20 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0004_D00 | [9 empty] | D02 | IFA | T-1496 | 44849 | 1401/07/23 | T-1496 | 44849 | 1401/07/23 | BK-SUR-ENG-ELE-01-06004 | 44863 | 1401/08/07 | AP | [6 empty] | 1401-2294-284217 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0004_D01
2 | 1 | 0 | 9 | 0 | 1 | 4 | 2.1.9.1.4 | BK-SSGRL-PEDCO-110-EL-CN-0005 | Calculation Note For Cable Sizing of Well Pads |  | BK-SSGRL-PEDCO-110-EL-CN-0005 | BK-SSGRL-PEDCO-110-EL-CN-0005 | BK | SSGRL | PEDCO | 110 | EL | CN | 0005 | F0Z-707381 | AFD | IFC | 2021-11-16 | 2021-11-30 | 2021-11-24 | 14 | -6 | 8 | IFA | 2021-12-22 | 2022-01-06 | 2022-01-08 | 15 | 2 | 17 | IFA | 2022-04-23 | 2022-04-19 | 2022-04-25 | -4 | 6 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-02 |  |  | D02 | IFA | T-0788 | 44660 | 1401/01/20 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-03999 | 44671 | 1400/01/31 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31358 | 44670 | 1401/01/30 | 44676 | 1401/02/05 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0207 | 2021-11-02 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 44509 | 1400/08/18 | RJ-C4 | [6 empty] | 1400-2294-286864 | 2021-11-30 | 1400/09/01 | 44524 | 1400/09/03 | CM | [10 empty] | D01 | IFA | T-0317 | 44538 | 1400/09/17 |  |  |  | BK-SUR-ENG-ELE-00-02323 | 44548 | 1400/09/27 | C4-RJ | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005-D00 | [5 empty] | 1400-2294-352392 | 44567 | 1400/10/16 | 44569 | 1400/10/18 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005-D00 | [9 empty] | D02 | IFA | T-0788 | 44660 | 1401/01/20 |  |  |  | BK-SUR-ENG-ELE-01-03999 | 44671 | 1400/01/31 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005_D01 | [5 empty] | 1401-2294-31358 | 44670 | 1401/01/30 | 44676 | 1401/02/05 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005_D01
2 | 1 | 0 | 9 | 0 | 1 | 5 | 2.1.9.1.5 | BK-SSGRL-PEDCO-110-EL-CN-0006 | Calculation Note For UPS System of Well Pads |  | BK-SSGRL-PEDCO-110-EL-CN-0006 | BK-SSGRL-PEDCO-110-EL-CN-0006 | BK | SSGRL | PEDCO | 110 | EL | CN | 0006 | F0Z-707382 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 1 | 0 | 9 | 0 | 1 | 6 | 2.1.9.1.6 | BK-SSGRL-PEDCO-110-EL-CN-0007 | Calculation Note For Earthing & Lightning System of Well Pads |  | BK-SSGRL-PEDCO-110-EL-CN-0007 | BK-SSGRL-PEDCO-110-EL-CN-0007 | BK | SSGRL | PEDCO | 110 | EL | CN | 0007 | F0Z-707383 | AFD | IFC | 2022-05-15 | 2022-05-30 | 2022-06-06 | 15 | 7 | 22 | IFA | 2022-10-22 | 2022-11-07 | 2022-11-12 | 16 | 5 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-01 |  |  | D01 | IFA | T-1464 | 44842 | 1401/07/16 | T-1464 | 44842 | 1401/07/16 | BK-SUR-ENG-ELE-01-05932 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-298756 | 44872 | 1401/08/16 | 44877 | 1401/08/21 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0890 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ELE-01-04252 | 44705 | 1401/02/24 | CM-C3 | [6 empty] | 1401-2294-82856 | 2022-05-30 | 1401/03/09 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1464 | 44842 | 1401/07/16 | T-1464 | 44842 | 1401/07/16 | BK-SUR-ENG-ELE-01-05932 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0007_D00 | [5 empty] | 1401-2294-298756 | 44872 | 1401/08/16 | 44877 | 1401/08/21 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0007_D00
2 | 1 | 0 | 9 | 0 | 1 | 7 | 2.1.9.1.7 | BK-SSGRL-PEDCO-110-EL-CN-0008 | Calculation Note For Diesel Generator Sizing of Well Pads |  | BK-SSGRL-PEDCO-110-EL-CN-0008 | BK-SSGRL-PEDCO-110-EL-CN-0008 | BK | SSGRL | PEDCO | 110 | EL | CN | 0008 | F0Z-707384 | AFD | IFC | 2022-02-09 | 2022-02-12 | 2022-02-21 | 3 | 9 | 12 | IFA | 2022-05-03 | 2022-05-18 | 2022-05-22 | 15 | 4 | 19 | IFA | 2022-08-30 | 2022-08-31 | 2022-09-04 | 1 | 4 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-26 |  |  | D02 | IFA | T-1279 | 44789 | 1401/05/25 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05528 | 44797 | 1401/06/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205604 | 44804 | 1401/06/09 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0515 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-ELE-00-03005 | 44601 | 1400/11/20 | CM-C3 | [6 empty] | 1400-2294-407130 | 2022-02-12 | 1400/11/23 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0844 | 44670 | 1401/01/30 |  |  |  | BK-SUR-ENG-ELE-01-04079 | 44681 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0008_D00 | [5 empty] | 1401-2294-66366 | 44699 | 1401/02/28 | 44703 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0008_D00 | [9 empty] | D02 | IFA | T-1279 | 44789 | 1401/05/25 |  |  |  | BK-SUR-ENG-ELE-01-05528 | 44797 | 1401/06/02 | AP | [6 empty] | 1401-2294-205604 | 44804 | 1401/06/09 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0008_D01
2 | 1 | 0 | 9 | 0 | 1 | 8 | 2.1.9.1.8 | BK-SSGRL-PEDCO-110-EL-CN-0009 | Calculation Note For DC Charger of Well Pads |  | BK-SSGRL-PEDCO-110-EL-CN-0009 | BK-SSGRL-PEDCO-110-EL-CN-0009 | BK | SSGRL | PEDCO | 110 | EL | CN | 0009 | F0Z-707385 | AFD | IFC | 2022-02-09 | 2022-02-12 | 2022-02-21 | 3 | 9 | 12 | IFA | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-16 | 5 | 7 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-26 |  |  | D02 | IFA | T-0850 | 44671 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04092 | 44681 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54908 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0511 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-ELE-00-02998 | 44600 | 1400/11/19 | CM-C2 | [6 empty] | 1400-2294-407153 | 2022-02-12 | 1400/11/23 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0712 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03642 | 44636 | 1400/12/25 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D00 | [5 empty] | 1400-2294-455098 | 44639 | 1400/12/28 | 44647 | 1401/01/07 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D00 | [9 empty] | D02 | IFA | T-0850 | 44671 | 1401/01/14 |  |  |  | BK-SUR-ENG-ELE-01-04092 | 44681 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D01 | [5 empty] | 1401-2294-54908 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D01
2 | 1 | 0 | 9 | 0 | 1 | 9 | 2.1.9.1.9 | BK-SSGRL-PEDCO-110-EL-CN-0010 | Calculation Note For LV Capacitor Bank of Well Pads |  | BK-SSGRL-PEDCO-110-EL-CN-0010 | BK-SSGRL-PEDCO-110-EL-CN-0010 | BK | SSGRL | PEDCO | 110 | EL | CN | 0010 | F0Z-707386 | AFD | IFC | 2022-02-12 | 2022-02-20 | 2022-03-07 | 8 | 15 | 23 | IFA | 2022-08-09 | 2022-09-10 | 2022-09-11 | 32 | 1 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-29 |  |  | D01 | IFA | T-1199 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0010_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0517 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-ELE-00-03024 | 44604 | 1400/11/23 | CM-C2 | [6 empty] | 1400-2294-415826 | 2022-02-20 | 1400/12/01 | 44627 | 1400/12/17 | CM | [10 empty] | D01 | IFA | T-1199 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0010_D00 | [5 empty] | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0010_D00
2 | 1 | 0 | 9 | 0 | 1 | 10 | 2.1.9.1.10 | BK-SSGRL-PEDCO-110-EL-CN-0011 | Calculation Note For 11 KV Over Head Line Sag and Tension |  | BK-SSGRL-PEDCO-110-EL-CN-0011 | BK-SSGRL-PEDCO-110-EL-CN-0011 | BK | SSGRL | PEDCO | 110 | EL | CN | 0011 | F0Z-707387 | AFD | IFC | 2021-10-27 | 2022-01-01 | 2021-11-07 | 66 | -55 | 11 | IFA | 2022-03-21 | 2022-03-14 | 2022-03-26 | -7 | 12 | 5 | IFA | 2022-06-13 | 2022-08-28 | 2022-09-04 | 76 | 7 | 83 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Deleted | 2021-10-13 |  |  | D02 | IFA | T-1023 | 44711 | 1401/03/09 | T-1023 | 44711 | 1401/03/09 | BK-SUR-ENG-ELE-01-04682 | 44724 | 1401/03/22 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-199009 | 44801 | 1401/06/06 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0155 | 2021-10-13 | 1400/07/21 |  |  |  | BK-SUR-ENG-ELE-00-01828 | 44494 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-259348 | 2022-01-01 | 1400/08/11 | 44507 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0687 | 44627 | 1400/12/16 |  |  |  | BK-SUR-ENG-ELE-00-03586 | 44635 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D00 | [5 empty] | 1400-2294-449000 | 44634 | 1400/12/23 | 44646 | 1401/01/06 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D00 | [9 empty] | D02 | IFA | T-1023 | 44711 | 1401/03/09 | T-1023 | 44711 | 1401/03/09 | BK-SUR-ENG-ELE-01-04682 | 44724 | 1401/03/22 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D01 | [5 empty] | 1401-2294-199009 | 44801 | 1401/06/06 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D01
2 | 1 | 0 | 9 | 0 | 1 | 11 | 2.1.9.1.11 | BK-SSGRL-PEDCO-110-EL-CN-0012 | Calculation Note For 33 KV Over Head Line Sag and Tension |  | BK-SSGRL-PEDCO-110-EL-CN-0012 | BK-SSGRL-PEDCO-110-EL-CN-0012 | BK | SSGRL | PEDCO | 110 | EL | CN | 0012 | F0Z-707388 | AFD | IFC | 2021-10-25 | 2022-01-01 | 2021-11-07 | 68 | -55 | 13 | IFA | 2022-03-21 | 2022-03-14 | 2022-03-26 | -7 | 12 | 5 | IFA | 2022-06-13 | 2022-08-28 | 2022-09-04 | 76 | 7 | 83 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-11 |  |  | D02 | IFA | T-1023 | 44711 | 1401/03/09 | T-1023 | 44711 | 1401/03/09 | BK-SUR-ENG-ELE-01-04682 | 44724 | 1401/03/22 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-199009 | 44801 | 1401/06/06 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0147 | 2021-10-11 | 1400/07/19 |  |  |  | BK-SUR-ENG-ELE-00-01828 | 44494 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-259367 | 2022-01-01 | 1400/08/11 | 44507 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0687 | 44627 | 1400/12/16 |  |  |  | BK-SUR-ENG-ELE-00-03586 | 44635 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D00 | [5 empty] | 1400-2294-449000 | 44634 | 1400/12/23 | 44646 | 1401/01/06 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D00 | [9 empty] | D02 | IFA | T-1023 | 44711 | 1401/03/09 | T-1023 | 44711 | 1401/03/09 | BK-SUR-ENG-ELE-01-04682 | 44724 | 1401/03/22 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D01 | [5 empty] | 1401-2294-199009 | 44801 | 1401/06/06 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D01
2 | 1 | 0 | 9 | 0 | 2 | 0 | 2.1.9.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 9 | 0 | 2 | 1 | 2.1.9.2.1 | BK-SSGRL-PEDCO-110-EL-DT-0002 | Data Sheets For UPS of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DT-0002 | BK-SSGRL-PEDCO-110-EL-DT-0002 | BK | SSGRL | PEDCO | 110 | EL | DT | 0002 | F0Z-707389 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 1 | 0 | 9 | 0 | 2 | 2 | 2.1.9.2.2 | BK-SSGRL-PEDCO-110-EL-DT-0003 | Data Sheets For DC Charger of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DT-0003 | BK-SSGRL-PEDCO-110-EL-DT-0003 | BK | SSGRL | PEDCO | 110 | EL | DT | 0003 | F0Z-707390 | AFC | IFC | 2022-02-12 | 2022-02-20 | 2022-03-07 | 8 | 15 | 23 | IFA | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-16 | 5 | 7 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-29 |  |  | D02 | IFA | T-0850 | 44671 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04092 | 44681 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54908 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0517 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-ELE-00-03024 | 44604 | 1400/11/23 | CM-C3 | [6 empty] | 1400-2294-415826 | 2022-02-20 | 1400/12/01 | 44627 | 1400/12/17 | CM | [10 empty] | D01 | IFA | T-0712 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03642 | 44636 | 1400/12/25 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D00 | [5 empty] | 1400-2294-455098 | 44639 | 1400/12/28 | 44647 | 1401/01/07 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D00 | [9 empty] | D02 | IFA | T-0850 | 44671 | 1401/01/14 |  |  |  | BK-SUR-ENG-ELE-01-04092 | 44681 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D01 | [5 empty] | 1401-2294-54908 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D01
2 | 1 | 0 | 9 | 0 | 2 | 3 | 2.1.9.2.3 | BK-SSGRL-PEDCO-110-EL-DT-0004 | Data Sheets For Diesel Generator of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DT-0004 | BK-SSGRL-PEDCO-110-EL-DT-0004 | BK | SSGRL | PEDCO | 110 | EL | DT | 0004 | F0Z-707391 | AFC | IFC | 2021-10-04 | 2021-09-27 | 2021-10-02 | -7 | 5 | -2 | IFA | 2022-05-03 | 2022-05-18 | 2022-05-22 | 15 | 4 | 19 | IFA | 2022-08-31 | 2022-09-04 | 2022-09-07 | 4 | 3 | 7 | IFA | 2022-11-12 | 2022-11-19 | 2022-11-20 | 7 | 1 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-20 |  |  | D03 | IFA | T-1564 | 44863 | 1401/08/07 | T-1564 | 44863 | 1401/08/07 | BK-SUR-ENG-ELE-01-06159 | 44877 | 1401/08/21 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-316942 | 44884 | 1401/08/28 | 44885 | 1401/08/29 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0105 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SUR-ENG-ELE-00-01651 | 44471 | 1400/07/10 | CM-C2 | [6 empty] | 1400-2294-213965 | 2021-09-27 | 1400/07/05 | 44471 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0844 | 44670 | 1401/01/30 |  |  |  | BK-SUR-ENG-ELE-01-04079 | 44681 | 1401/02/10 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D00 | [5 empty] | 1401-2294-66366 | 44699 | 1401/02/28 | 44703 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D00 | [9 empty] | D02 | IFA | T-1284 | 44790 | 1401/05/26 |  |  |  | BK-SUR-ENG-ELE-01-05532 | 44800 | 1401/06/05 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D01 | [5 empty] | 1401-2294-210113 | 44808 | 1401/06/13 | 44811 | 1401/06/16 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D01 | [9 empty] | D03 | IFA | T-1564 | 44863 | 1401/08/07 | T-1564 | 44863 | 1401/08/07 | BK-SUR-ENG-ELE-01-06159 | 44877 | 1401/08/21 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D02 | [5 empty] | 1401-2294-316942 | 44884 | 1401/08/28 | 44885 | 1401/08/29 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D02
2 | 1 | 0 | 9 | 0 | 2 | 4 | 2.1.9.2.4 | BK-SSGRL-PEDCO-110-EL-DT-0005 | Data Sheets For Local Control Stations (LCS) of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DT-0005 | [8 empty] | - |  | IFC | 2021-09-13 | 2021-09-14 | 2021-09-18 | 1 | 4 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-30 |  |  | D00 | IFC | T-0072 | 44438 | 1400/06/08 | 0 | 0 | 0 | BK-SSR-ENG-ELE-00-01506 | 44452 | 1400/06/22 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-198862 | 44453 | 1400/06/23 | 44457 | 1400/06/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0072 | 2021-08-30 | 1400/06/08 |  |  |  | BK-SSR-ENG-ELE-00-01506 | 44452 | 1400/06/22 | RJ-C4 | [6 empty] | 1400-2294-198862 | 2021-09-14 | 1400/06/23 | 44457 | 1400/06/27 | CM
2 | 1 | 0 | 9 | 0 | 2 | 5 | 2.1.9.2.5 | BK-SSGRL-PEDCO-110-EL-DT-0006 | Data Sheets For LV Capacitor Bank of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DT-0006 | BK-SSGRL-PEDCO-110-EL-DT-0006 | BK | SSGRL | PEDCO | 110 | EL | DT | 0006 | F0Z-707392 | AFC | IFC | 2021-09-26 | 2021-09-28 | 2021-10-02 | 2 | 4 | 6 | IFA | 2022-03-13 | 2022-03-13 | 2022-03-26 | 0 | 13 | 13 | IFA | 2022-08-09 | 2022-09-10 | 2022-09-11 | 32 | 1 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-12 |  |  | D02 | IFA | T-1199 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0087 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ELE-00-01560 | 44464 | 1400/07/03 | RJ-C4 | [6 empty] | 1400-2294-213958 | 2021-09-28 | 1400/07/05 | 44471 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0651 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-ELE-00-03377 | 44627 | 1400/12/17 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D00 | [5 empty] | 1400-2294-447229 | 44633 | 1400/12/22 | 44646 | 1401/01/06 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D00 | [9 empty] | D02 | IFA | T-1199 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D01 | [5 empty] | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D01
2 | 1 | 0 | 9 | 0 | 2 | 6 | 2.1.9.2.6 | BK-SSGRL-PEDCO-110-EL-DT-0008 | Data Sheets For LV Switchgear of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DT-0008 | BK-SSGRL-PEDCO-110-EL-DT-0008 | BK | SSGRL | PEDCO | 110 | EL | DT | 0008 | F0Z-707393 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-06-07 | 2022-06-11 | 2022-06-13 | 4 | 2 | 6 | IFA | 2022-08-09 | 2022-09-10 | 2022-09-11 | 32 | 1 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D02 | IFA | T-1199 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0601 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-ELE-00-03320 | 44625 | 1400/12/14 | CM-C2 | [6 empty] | 1400-2294-443157 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0998 | 44705 | 1401/03/03 | T-0998 | 44709 | 1401/03/07 | BK-SUR-ENG-ELE-01-04499 | 44713 | 1401/03/11 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0008_D00 | [5 empty] | 1401-2294-96604 | 44723 | 1401/03/21 | 44725 | 1401/03/23 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0008_D00 | [9 empty] | D02 | IFA | T-1199 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | [6 empty] | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0008_D01
2 | 1 | 0 | 9 | 0 | 2 | 7 | 2.1.9.2.7 | BK-SSGRL-PEDCO-110-EL-DT-0009 | Data Sheets For Power & Control Cables of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DT-0009 | BK-SSGRL-PEDCO-110-EL-DT-0009 | BK | SSGRL | PEDCO | 110 | EL | DT | 0009 | F0Z-707394 | AFC | IFC | 2021-09-27 | 2021-09-19 | 2021-09-25 | -8 | 6 | -2 | IFA | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-04-10 | 2022-04-13 | 2022-04-16 | 3 | 3 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-13 |  |  | D02 | IFA | T-0751 | 44647 | 1401/01/07 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-03699 | 44650 | 1401/01/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-22895 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0090 | 2021-09-13 | 1400/06/22 |  |  |  | BK-SUR-ENG-ELE-00-01559 | 44464 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-204476 | 2021-09-19 | 1400/06/28 | 44464 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0606 | 44611 | 1400/11/30 |  |  |  | BK-SUR-ENG-ELE-00-03321 | 44625 | 1400/12/14 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D00 | [5 empty] | 1400-2294-443207 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D00 | [9 empty] | D02 | IFA | T-0751 | 44647 | 1401/01/07 |  |  |  | BK-SUR-ENG-ELE-01-03699 | 44650 | 1401/01/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D01 | [5 empty] | 1401-2294-22895 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D01
2 | 1 | 0 | 9 | 0 | 2 | 8 | 2.1.9.2.8 | BK-SSGRL-PEDCO-110-EL-DT-0010 | Data Sheets For Power Transformers of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DT-0010 | BK-SSGRL-PEDCO-110-EL-DT-0010 | BK | SSGRL | PEDCO | 110 | EL | DT | 0010 | F0Z-707395 | AFC | IFC | 2021-09-29 | 2021-09-28 | 2021-10-02 | -1 | 4 | 3 | IFA | 2022-02-22 | 2022-02-24 | 2022-02-28 | 2 | 4 | 6 | IFA | 2022-08-09 | 2022-09-10 | 2022-09-11 | 32 | 1 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-15 |  |  | D02 | IFA | T-1199 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0010_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0094 | 2021-09-15 | 1400/06/24 |  |  |  | BK-SSR-ENG-ELE-00-01608 | 44465 | 1400/07/04 | CM-C2 | [6 empty] | 1400-2294-213964 | 2021-09-28 | 1400/07/05 | 44471 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0563 | 44600 | 1400/11/19 |  |  |  | BK-SUR-ENG-ELE-00-03126 | 44612 | 1400/12/01 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0010_D00 | [5 empty] | 1400-2294-424217 | 44616 | 1400/12/05 | 44620 | 1400/12/09 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0010_D00 | [9 empty] | D02 | IFA | T-1199 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | [6 empty] | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0010_D01
2 | 1 | 0 | 9 | 0 | 2 | 9 | 2.1.9.2.9 | BK-SSGRL-PEDCO-110-EL-DT-0011 | Data Sheets For Distribution & Lighting Panels of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DT-0011 | BK-SSGRL-PEDCO-110-EL-DT-0011 | BK | SSGRL | PEDCO | 110 | EL | DT | 0011 | F0Z-707396 | AFC | IFC | 2021-09-26 | 2021-09-28 | 2021-10-02 | 2 | 4 | 6 | IFA | 2022-05-31 | 2022-06-08 | 2022-06-11 | 8 | 3 | 11 | IFA | 2022-08-06 | 2022-08-02 | 2022-08-09 | -4 | 7 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-12 |  |  | D02 | IFA | T-1183 | 44765 | 1401/05/01 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05321 | 44774 | 1401/05/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-165038 | 44775 | 1401/05/11 | 44782 | 1401/05/18 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0087 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ELE-00-01560 | 44464 | 1400/07/03 | RJ-C4 | [6 empty] | 1400-2294-213958 | 2021-09-28 | 1400/07/05 | 44471 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0966 | 44698 | 1401/02/27 | T-0966 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04478 | 44710 | 1401/03/08 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D00 | [5 empty] | 1401-2294-94378 | 44720 | 1401/03/18 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D00 | [9 empty] | D02 | IFA | T-1183 | 44765 | 1401/05/01 |  |  |  | BK-SUR-ENG-ELE-01-05321 | 44774 | 1401/05/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D01 | [5 empty] | 1401-2294-165038 | 44775 | 1401/05/11 | 44782 | 1401/05/18 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D01
2 | 1 | 0 | 9 | 0 | 2 | 10 | 2.1.9.2.10 | BK-SSGRL-PEDCO-110-EL-DT-0012 | Data Sheets For 11 KV Over Head Line Equipment |  | BK-SSGRL-PEDCO-110-EL-DT-0012 | BK-SSGRL-PEDCO-110-EL-DT-0012 | BK | SSGRL | PEDCO | 110 | EL | DT | 0012 | F0Z-707397 | AFC | IFC | 2021-11-24 | 2021-11-27 | 2021-11-28 | 3 | 1 | 4 | IFA | 2022-01-09 | 2022-01-12 | 2022-01-15 | 3 | 3 | 6 | IFA | 2022-02-09 | 2022-02-08 | 2022-02-13 | -1 | 5 | 4 | IFA | 2022-03-07 | 2022-02-28 | 2022-03-05 | -7 | 5 | -2 | AFC | 2022-08-13 | 2022-08-18 | 2022-08-20 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-07-30 |  | D04 | AFC | T-1214 | 44772 | 1401/0508 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05371 | 44782 | 1401/05/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183472 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0226 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-ELE-00-02011 | 44515 | 1400/08/24 | CM-C2 | [6 empty] | 1400-2294-293077 | 2021-11-27 | 1400/09/06 | 44528 | 1400/09/07 | CM | [10 empty] | D01 | IFA | T-0380 | 44556 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02561 | 44565 | 1400/10/14 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D00 | [5 empty] | 1400-2294-362424 | 44573 | 1400/10/22 | 44576 | 1400/10/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D00 | [9 empty] | D02 | IFA | T-0510 | 44587 | 1400/11/06 |  |  |  | BK-SUR-ENG-ELE-00-02999 | 44600 | 1400/11/19 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D01 | [5 empty] | 1400-2294-402924 | 44600 | 1400/11/19 | 44605 | 1400/11/13 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D01 | [9 empty] | D03 | IFA | T-0615 | 44613 | 1400/12/02 |  |  |  | BK-SUR-ENG-ELE-00-03305 | 44622 | 1400/12/11 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D02 | [5 empty] | 1400-2294-430270 | 44620 | 1400/12/09 | 44625 | 1400/12/14 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D02 | [9 empty] | D04 | AFC | T-1214 | 44772 | 1401/0508 |  |  |  | BK-SUR-ENG-ELE-01-05371 | 44782 | 1401/05/18 | AP | [6 empty] | 1401-2294-183472 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP
2 | 1 | 0 | 9 | 0 | 2 | 11 | 2.1.9.2.11 | BK-SSGRL-PEDCO-110-EL-DT-0013 | Data Sheets For 33 KV Over Head Line Equipment |  | BK-SSGRL-PEDCO-110-EL-DT-0013 | BK-SSGRL-PEDCO-110-EL-DT-0013 | BK | SSGRL | PEDCO | 110 | EL | DT | 0013 | F0Z-707398 | AFC | IFC | 2021-11-24 | 2021-11-27 | 2021-11-28 | 3 | 1 | 4 | IFA | 2022-01-09 | 2022-01-12 | 2022-01-15 | 3 | 3 | 6 | IFA | 2022-02-09 | 2022-02-08 | 2022-02-13 | -1 | 5 | 4 | IFA | 2022-03-07 | 2022-02-28 | 2022-03-05 | -7 | 5 | -2 | AFC | 2022-08-13 | 2022-08-18 | 2022-08-20 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-07-30 |  | D04 | AFC | T-1214 | 44772 | 1401/0508 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05371 | 44782 | 1401/05/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183472 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0226 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-ELE-00-02011 | 44515 | 1400/08/24 | CM-C2 | [6 empty] | 1400-2294-293077 | 2021-11-27 | 1400/09/06 | 44528 | 1400/09/07 | CM | [10 empty] | D01 | IFA | T-0380 | 44556 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02561 | 44565 | 1400/10/14 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D00 | [5 empty] | 1400-2294-362424 | 44573 | 1400/10/22 | 44576 | 1400/10/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D00 | [9 empty] | D02 | IFA | T-0510 | 44587 | 1400/11/06 |  |  |  | BK-SUR-ENG-ELE-00-03000 | 44600 | 1400/11/19 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D01 | [5 empty] | 1400-2294-402924 | 44600 | 1400/11/19 | 44605 | 1400/11/13 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D01 | [9 empty] | D03 | IFA | T-0615 | 44613 | 1400/12/02 |  |  |  | BK-SUR-ENG-ELE-00-03305 | 44622 | 1400/12/11 | AP | [6 empty] | 1400-2294-430270 | 44620 | 1400/12/09 | 44625 | 1400/12/14 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D02 | [9 empty] | D04 | AFC | T-1214 | 44772 | 1401/0508 |  |  |  | BK-SUR-ENG-ELE-01-05371 | 44782 | 1401/05/18 | AP | [6 empty] | 1401-2294-183472 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP
2 | 1 | 0 | 9 | 0 | 3 | 0 | 2.1.9.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 9 | 0 | 3 | 1 | 2.1.9.3.1 | BK-SSGRL-PEDCO-110-EL-DW-0001 | Typical Installation Details For Over Head Line Equipment |  | BK-SSGRL-PEDCO-110-EL-DW-0001 | BK-SSGRL-PEDCO-110-EL-DW-0001 | BK | SSGRL | PEDCO | 110 | EL | DW | 0001 | F2P-707399 | IFI | IFI | 2021-09-05 | 2021-09-06 | 2021-09-11 | 1 | 5 | 6 | IFI | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | IFI | 2021-11-21 | 2021-11-16 | 2021-11-21 | -5 | 5 | 0 | FI | 2022-11-09 | 2022-11-19 | 2022-11-21 | 10 | 2 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 | 2022-10-26 |  | D03 | FI | T-1557 | 44860 | 1401/08/04 | T-1557 | 44860 | 1401/08/04 | BK-SUR-ENG-ELE-01-06137 | 44873 | 1401/08/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318131 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0051 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-ELE-00-01439 | 44438 | 1400/06/08 | CM-C2 | [6 empty] | 1400/2294/188317 | 2021-09-06 | 1400/06/15 | 44450 | 1400/06/20 | CM | [10 empty] | D01 | IFI | T-0115 | 44464 | 1400/07/03 |  |  |  | BK-SSR-ENG-ELE-00-01665 | 44472 | 1400/07/11 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DW-0001_D00 | [5 empty] | 1400-2294-234035 | 44482 | 1400/07/21 | 44487 | 1400/07/26 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DW-0001_D00 | [9 empty] | D02 | IFI | T-0212 | 44507 | 1400/08/16 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 44537 | 1400/09/16 | AP | [6 empty] | 1400-2294-279099 | 44516 | 1400/08/25 | 44521 | 1400/08/30 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DW-0001-D01 | [9 empty] | D03 | FI | T-1557 | 44860 | 1401/08/04 | T-1557 | 44860 | 1401/08/04 | BK-SUR-ENG-ELE-01-06137 | 44873 | 1401/08/17 | AP | [6 empty] | 1401-2294-318131 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | AP
2 | 1 | 0 | 9 | 0 | 3 | 2 | 2.1.9.3.2 | BK-SSGRL-PEDCO-110-EL-DW-0002 | Installation Detail & Notes for Connection OHL to Gantries for Wells |  | BK-SSGRL-PEDCO-110-EL-DW-0002 | BK-SSGRL-PEDCO-110-EL-DW-0002 | BK | SSGRL | PEDCO | 110 | EL | DW | 0002 | F2P-707400 | AFC | IFC | 2022-03-20 | 2022-03-15 | 2022-03-24 | -5 | 9 | 4 | IFA | 2022-08-09 | 2022-09-10 | 2022-09-11 | 32 | 1 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-06 |  |  | D01 | IFA | T-1199 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0684 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-ELE-00-03585 | 44635 | 1400/12/24 | CM-C2 | [6 empty] | 1400-2294-451069 | 2022-03-15 | 1400/12/24 | 44644 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-1199 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DW-0002_D00 | [5 empty] | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DW-0002_D00
2 | 1 | 0 | 9 | 0 | 3 | 3 | 2.1.9.3.3 | BK-SSGRL-PEDCO-110-EL-DG-0001 | Electrical Typical Schematic Diagrams For LV Panels of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DG-0001 | BK-SSGRL-PEDCO-110-EL-DG-0001 | BK | SSGRL | PEDCO | 110 | EL | DG | 0001 | F2P-707401 | IFI | IFI | 2021-09-13 | 2021-09-14 | 2021-09-18 | 1 | 4 | 5 | IFI | 2022-05-02 | 2022-05-08 | 2022-05-11 | 6 | 3 | 9 | IFI | 2022-06-04 | 2022-06-15 | 2022-06-19 | 11 | 4 | 15 | IFI | 2022-07-19 | 2022-08-18 | 2022-08-20 | 30 | 2 | 32 | IFI | 2022-09-21 | 2022-10-05 | 2022-10-08 | 14 | 3 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-30 |  |  | D04 | IFI | T-1378 | 44811 | 1401/06/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249451 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0072 | 2021-08-30 | 1400/06/08 |  |  |  | BK-SSR-ENG-ELE-00-01506 | 44452 | 1400/06/22 | RJ-C4 | [6 empty] | 1400-2294-198862 | 2021-09-14 | 1400/06/23 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFI | T-0835 | 44669 | 1400/01/29 |  |  |  | BK-SUR-ENG-ELE-01-04072 | 44677 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D00 | [5 empty] | 1401-2294-52754 | 44689 | 1401/02/18 | 44692 | 1401/02/21 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D00 | [9 empty] | D02 | IFI | T-0979 | 44702 | 1401/02/31 | T-0979 | 44702 | 1401/02/31 | BK-SUR-ENG-ELE-01-04487 | 44710 | 1401/03/09 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D01 | [5 empty] | 1401-2294-103789 | 44727 | 1401/03/25 | 44731 | 1401/03/29 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D01 | [9 empty] | D03 | IFI | T-1141 | 44747 | 1401/04/14 |  |  |  | BK-SUR-ENG-ELE-01-05158 | 44759 | 1401/04/26 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D02 | [5 empty] | 1401-2294-183489 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D02 | [9 empty] | D04 | IFI | T-1378 | 44811 | 1401/06/16 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D03 | [5 empty] | 1401-2294-249451 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D03
2 | 1 | 0 | 9 | 0 | 3 | 4 | 2.1.9.3.4 | BK-SSGRL-PEDCO-110-EL-LD-0001 | Control Logic Diagram For LV Incomers of Well Pads |  | BK-SSGRL-PEDCO-110-EL-LD-0001 | BK-SSGRL-PEDCO-110-EL-LD-0001 | BK | SSGRL | PEDCO | 110 | EL | LD | 0001 | F2P-707402 | AFC | IFC | 2021-09-13 | 2021-09-14 | 2021-09-18 | 1 | 4 | 5 | IFA | 2022-03-09 | 2022-03-10 | 2022-03-12 | 1 | 2 | 3 | IFA | 2022-06-04 | 2022-06-14 | 2022-06-19 | 10 | 5 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-30 |  |  | D02 | IFA | T-0975 | 44702 | 1401/02/31 | T-0975 | 44702 | 1401/02/31 | BK-SUR-ENG-ELE-01-04489 | 44710 | 1401/03/09 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-102597 | 44726 | 1401/03/24 | 44731 | 1401/03/29 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0072 | 2021-08-30 | 1400/06/08 |  |  |  | BK-SSR-ENG-ELE-00-01506 | 44452 | 1400/06/22 | RJ-C4 | [6 empty] | 1400-2294-198862 | 2021-09-14 | 1400/06/23 | 44457 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0632 | 44615 | 1400/12/04 |  |  |  | BK-SUR-ENG-ELE-00-03376 | 44627 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D00 | [5 empty] | 1400-2294-443146 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D00 | [9 empty] | D02 | IFA | T-0975 | 44702 | 1401/02/31 | T-0975 | 44702 | 1401/02/31 | BK-SUR-ENG-ELE-01-04489 | 44710 | 1401/03/09 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D01 | [5 empty] | 1401-2294-102597 | 44726 | 1401/03/24 | 44731 | 1401/03/29 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D01
2 | 1 | 0 | 9 | 0 | 3 | 5 | 2.1.9.3.5 | BK-SSGRL-PEDCO-110-EL-PY-0001 | Earthing Layout For Electrical Tower (Gantry) of Well Pads |  | BK-SSGRL-PEDCO-110-EL-PY-0001 | BK-SSGRL-PEDCO-110-EL-PY-0001 | BK | SSGRL | PEDCO | 110 | EL | PY | 0001 | F2P-707403 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 1 | 0 | 9 | 0 | 3 | 6 | 2.1.9.3.6 | BK-SSGRL-PEDCO-110-EL-PY-0002 | Cable Route Layout For Electrical Tower (Gantry) of Well Pads |  | BK-SSGRL-PEDCO-110-EL-PY-0002 | BK-SSGRL-PEDCO-110-EL-PY-0002 | BK | SSGRL | PEDCO | 110 | EL | PY | 0002 | F2P-707404 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 1 | 0 | 9 | 0 | 3 | 7 | 2.1.9.3.7 | BK-SSGRL-PEDCO-110-EL-SL-0001 | Overall Single Line Diagram of Well Pads |  | BK-SSGRL-PEDCO-110-EL-SL-0001 | BK-SSGRL-PEDCO-110-EL-SL-0001 | BK | SSGRL | PEDCO | 110 | EL | SL | 0001 | F2P-707405 | AFC | IFC | 2022-03-16 | 2022-04-09 | 2022-04-13 | 24 | 4 | 28 | IFA | 2022-08-09 | 2022-09-10 | 2022-09-11 | 32 | 1 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-02 |  |  | D01 | IFA | T-1199 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0662 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-ELE-00-03469 | 44632 | 1400/12/21 | CM-C2 | [6 empty] | 1401-2294-16106 | 2022-04-09 | 1401/01/20 | 44664 | 1401/01/24 | CM | [10 empty] | D01 | IFA | T-1199 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0001_D00 | [5 empty] | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0001_D00
2 | 1 | 0 | 9 | 0 | 3 | 8 | 2.1.9.3.8 | BK-SSGRL-PEDCO-110-EL-SL-0002 | Single Line Diagram For LV Switchgear of Well Pads |  | BK-SSGRL-PEDCO-110-EL-SL-0002 | BK-SSGRL-PEDCO-110-EL-SL-0002 | BK | SSGRL | PEDCO | 110 | EL | SL | 0002 | F2P-707406 | AFC | IFC | 2022-02-22 | 2022-03-10 | 2022-03-12 | 16 | 2 | 18 | IFA | 2022-05-03 | 2022-05-18 | 2022-05-22 | 15 | 4 | 19 | IFA | 2022-07-19 | 2022-08-09 | 2022-08-13 | 21 | 4 | 25 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-08 |  |  | D02 | IFA | T-1142 | 44747 | 1401/04/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05159 | 44759 | 1401/04/26 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171114 | 44782 | 1401/05/18 | 44786 | 1401/05/22 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0564 | 2022-02-08 | 1400/11/19 |  |  |  | BK-SUR-ENG-ELE-00-03159 | 44613 | 1400/12/02 | CM-C3 | [6 empty] | 1400-2294-443103 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0844 | 44670 | 1401/01/30 |  |  |  | BK-SUR-ENG-ELE-01-04079 | 44681 | 1401/02/10 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D00 | [5 empty] | 1401-2294-66366 | 44699 | 1401/02/28 | 44703 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D00 | [9 empty] | D02 | IFA | T-1142 | 44747 | 1401/04/14 |  |  |  | BK-SUR-ENG-ELE-01-05159 | 44759 | 1401/04/26 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D01 | [5 empty] | 1401-2294-171114 | 44782 | 1401/05/18 | 44786 | 1401/05/22 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D01
2 | 1 | 0 | 9 | 0 | 3 | 9 | 2.1.9.3.9 | BK-SSGRL-PEDCO-110-EL-SL-0003 | Single Line Diagram For LV Power Distribution Panel of Well Pads |  | BK-SSGRL-PEDCO-110-EL-SL-0003 | BK-SSGRL-PEDCO-110-EL-SL-0003 | BK | SSGRL | PEDCO | 110 | EL | SL | 0003 | F2P-707407 | AFC | IFC | 2022-05-28 | 2022-06-26 | 2022-06-29 | 29 | 3 | 32 | IFA | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-14 |  |  | D01 | IFA | T-1509 | 44852 | 1401/07/26 | T-1509 | 44852 | 1401/07/26 | BK-SUR-ENG-ELE-01-06039 | 44865 | 1401/08/09 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0947 | 2022-05-14 | 1401/02/24 | T-0947 | 44695 | 1401/02/24 | BK-SUR-ENG-ELE-01-04393 | 44704 | 1401/03/02 | CM-C3 | [6 empty] | 1401-2294-92409 | 2022-06-07 | 1401/03/17 | 44723 | 1401/03/21 | CM |  | 1401-2294-118097 | 44738 | 1401/04/05 | 44741 | 1401/04/08 | CM |  |  |  | D01 | IFA | T-1509 | 44852 | 1401/07/26 | T-1509 | 44852 | 1401/07/26 | BK-SUR-ENG-ELE-01-06039 | 44865 | 1401/08/09 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0003_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0003_D00
2 | 1 | 0 | 9 | 0 | 3 | 10 | 2.1.9.3.10 | BK-SSGRL-PEDCO-110-EL-SL-0004 | Single Line Diagram For DC Charger of Well Pads |  | BK-SSGRL-PEDCO-110-EL-SL-0004 | BK-SSGRL-PEDCO-110-EL-SL-0004 | BK | SSGRL | PEDCO | 110 | EL | SL | 0004 | F2P-707408 | AFC | IFC | 2022-02-20 | 2022-02-24 | 2022-02-28 | 4 | 4 | 8 | IFA | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-16 | 5 | 7 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-06 |  |  | D02 | IFA | T-0850 | 44671 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04092 | 44681 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54908 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0554 | 2022-02-06 | 1400/11/17 |  |  |  | BK-SUR-ENG-ELE-00-03087 | 44611 | 1400/11/30 | CM-C2 | [6 empty] | 1400-2294-424218 | 2022-02-24 | 1400/12/05 | 44620 | 1400/12/09 | CM | [10 empty] | D01 | IFA | T-0712 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03642 | 44636 | 1400/12/25 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D00 | [5 empty] | 1400-2294-455098 | 44639 | 1400/12/28 | 44647 | 1401/01/07 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D00 | [9 empty] | D02 | IFA | T-0850 | 44671 | 1401/01/14 |  |  |  | BK-SUR-ENG-ELE-01-04092 | 44681 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D01 | [5 empty] | 1401-2294-54908 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D01
2 | 1 | 0 | 9 | 0 | 3 | 11 | 2.1.9.3.11 | BK-SSGRL-PEDCO-110-EL-SL-0005 | Single Line Diagram For Capacitor Banks of Well Pads |  | BK-SSGRL-PEDCO-110-EL-SL-0005 | BK-SSGRL-PEDCO-110-EL-SL-0005 | BK | SSGRL | PEDCO | 110 | EL | SL | 0005 | F2P-707409 | AFC | IFC | 2022-02-16 | 2022-03-09 | 2022-03-12 | 21 | 3 | 24 | IFA | 2022-08-09 | 2022-09-10 | 2022-09-11 | 32 | 1 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-02 |  |  | D01 | IFA | T-1199 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0541 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-ELE-00-03060 | 44606 | 1400/11/25 | CM-C3 | [6 empty] | 1400-2294-442066 | 2022-03-09 | 1400/12/18 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-1199 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-ELE-01-05376 | 44782 | 1401/05/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0005_D00 | [5 empty] | 1401-2294-217200 | 44814 | 1401/06/19 | 44815 | 1401/06/20 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0005_D00
2 | 1 | 0 | 9 | 0 | 3 | 12 | 2.1.9.3.12 | BK-SSGRL-PEDCO-110-EL-DG-0002 | Interconnection Wiring Diagram of Well Pads |  | BK-SSGRL-PEDCO-110-EL-DG-0002 | BK-SSGRL-PEDCO-110-EL-DG-0002 | BK | SSGRL | PEDCO | 110 | EL | DG | 0002 | F2P-707410 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 1 | 0 | 9 | 0 | 3 | 13 | 2.1.9.3.13 | BK-SSGRL-PEDCO-110-EL-PY-0003 | Area Lighting & Small Power Layout of Well Pads |  | BK-SSGRL-PEDCO-110-EL-PY-0003 | BK-SSGRL-PEDCO-110-EL-PY-0003 | BK | SSGRL | PEDCO | 110 | EL | PY | 0003 | F2P-707411 | AFC | IFC | 2022-05-28 | 2022-06-26 | 2022-06-29 | 29 | 3 | 32 | IFA | 2022-10-15 | 2022-11-03 | 2022-11-05 | 19 | 2 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-14 |  |  | D01 | IFA | T-1505 | 44835 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-06037 | 44865 | 1401/08/09 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-PY-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294097 | 44868 | 1401/08/12 | 44870 | 1401/08/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0947 | 2022-05-14 | 1401/02/24 | T-0947 | 44695 | 1401/02/24 | BK-SUR-ENG-ELE-01-04393 | 44704 | 1401/03/02 | CM-C3 | [6 empty] | 1401-2294-92409 | 2022-06-07 | 1401/03/17 | 44723 | 1401/03/21 | CM |  | 1401-2294-118097 | 44738 | 1401/04/05 | 44741 | 1401/04/08 | CM |  |  |  | D01 | IFA | T-1505 | 44835 | 1401/07/25 |  |  |  | BK-SUR-ENG-ELE-01-06037 | 44865 | 1401/08/09 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-PY-0003_D00 | [5 empty] | 1401-2294-294097 | 44868 | 1401/08/12 | 44870 | 1401/08/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0003_D00
2 | 1 | 0 | 9 | 0 | 3 | 14 | 2.1.9.3.14 | BK-SSGRL-PEDCO-110-EL-PY-0004 | Lighting & Small Power Layout For Switchgear Building of Well Pads |  | BK-SSGRL-PEDCO-110-EL-PY-0004 | BK-SSGRL-PEDCO-110-EL-PY-0004 | BK | SSGRL | PEDCO | 110 | EL | PY | 0004 | F2P-707412 | AFC | IFC | 2022-05-25 | 2022-06-01 | 2022-06-06 | 7 | 5 | 12 | IFA | 2022-10-15 | 2022-11-03 | 2022-11-05 | 19 | 2 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-11 |  |  | D01 | IFA | T-1505 | 44835 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-06037 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-PY-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294097 | 44868 | 1401/08/12 | 44870 | 1401/08/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0930 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-ELE-01-04347 | 44703 | 1401/03/01 | CM-C2 | [6 empty] | 1401-2294-87162 | 2022-06-01 | 1401/03/11 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1505 | 44835 | 1401/07/25 |  |  |  | BK-SUR-ENG-ELE-01-06037 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-PY-0004_D00 | [5 empty] | 1401-2294-294097 | 44868 | 1401/08/12 | 44870 | 1401/08/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0004_D00
2 | 1 | 0 | 9 | 0 | 3 | 15 | 2.1.9.3.15 | BK-SSGRL-PEDCO-110-EL-PY-0005 | Lighting & Small Power Layout For Security Building of Well Pads |  | BK-SSGRL-PEDCO-110-EL-PY-0005 | BK-SSGRL-PEDCO-110-EL-PY-0005 | BK | SSGRL | PEDCO | 110 | EL | PY | 0005 | F2P-707413 | AFC | IFC | 2022-05-21 | 2022-05-31 | 2022-06-06 | 10 | 6 | 16 | IFA | 2022-10-23 | 2022-11-14 | 2022-11-19 | 22 | 5 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-07 |  |  | D01 | IFA | T-1470 | 44843 | 1401/07/17 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05952 | 44857 | 1401/08/01 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-PY-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-311090 | 44879 | 1401/08/23 | 44884 | 1401/08/28 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0903 | 2022-05-07 | 1401/02/17 | T-0903 | 44688 | 1401/02/17 | BK-SUR-ENG-ELE-01-04301 | 44689 | 1401/02/28 | CM-C3 | [6 empty] | 1401-2294-85150 | 2022-05-31 | 1400/03/10 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1470 | 44843 | 1401/07/17 |  |  |  | BK-SUR-ENG-ELE-01-05952 | 44857 | 1401/08/01 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-PY-0005_D00 | [5 empty] | 1401-2294-311090 | 44879 | 1401/08/23 | 44884 | 1401/08/28 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0005_D00
2 | 1 | 0 | 9 | 0 | 3 | 16 | 2.1.9.3.16 | BK-SSGRL-PEDCO-110-EL-PY-0006 | Area Electrical Cable Route & Section Layout of Well Pads |  | BK-SSGRL-PEDCO-110-EL-PY-0006 | BK-SSGRL-PEDCO-110-EL-PY-0006 | BK | SSGRL | PEDCO | 110 | EL | PY | 0006 | F2P-707414 | AFC | IFC | 2022-06-11 | 2022-06-26 | 2022-07-02 | 15 | 6 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-28 |  |  | D00 | IFC | T-1008 | 44709 | 1401/03/07 | T-1008 | 44709 | 1401/03/07 | BK-SSR-ENG-ELE-01-04609 | 44720 | 1401/03/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-118236 | 44738 | 1401/04/05 | 44744 | 1401/04/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1008 | 2022-05-28 | 1401/03/07 | T-1008 | 44709 | 1401/03/07 | BK-SSR-ENG-ELE-01-04609 | 44720 | 1401/03/18 | CM-C3 | [6 empty] | 1401-2294-118236 | 2022-06-26 | 1401/04/05 | 44744 | 1401/04/11 | CM
2 | 1 | 0 | 9 | 0 | 3 | 17 | 2.1.9.3.17 | BK-SSGRL-PEDCO-110-EL-PY-0007 | Electrical Cable Route & Section Layout For Switchgear Building of Well Pads |  | BK-SSGRL-PEDCO-110-EL-PY-0007 | BK-SSGRL-PEDCO-110-EL-PY-0007 | BK | SSGRL | PEDCO | 110 | EL | PY | 0007 | F2P-707415 | AFC | IFC | 2022-06-08 | 2022-06-24 | 2022-07-02 | 16 | 8 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-25 |  |  | D00 | IFC | T-1001 | 44706 | 1401/03/04 | T-1001 | 44709 | 1401/03/07 | BK-SUR-ENG-ELE-01-04608 | 44720 | 1401/03/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-114025 | 44736 | 1401/04/03 | 44744 | 1401/04/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1001 | 2022-05-25 | 1401/03/04 | T-1001 | 44709 | 1401/03/07 | BK-SUR-ENG-ELE-01-04608 | 44720 | 1401/03/18 | CM-C3 | [6 empty] | 1401-2294-114025 | 2022-06-24 | 1401/04/03 | 44744 | 1401/04/11 | CM
2 | 1 | 0 | 9 | 0 | 3 | 18 | 2.1.9.3.18 | BK-SSGRL-PEDCO-110-EL-PY-0008 | Electrical Equipment Arrangement Layout For Switchgear Building of Well Pads |  | BK-SSGRL-PEDCO-110-EL-PY-0008 | BK-SSGRL-PEDCO-110-EL-PY-0008 | BK | SSGRL | PEDCO | 110 | EL | PY | 0008 | F2P-707416 | AFC | IFC | 2022-06-06 | 2022-06-01 | 2022-06-07 | -5 | 6 | 1 | IFA | 2022-09-25 | 2022-09-27 | 2022-10-02 | 2 | 5 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-23 |  |  | D01 | IFA | T-1391 | 44815 | 1401/06/20 | T-1391 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05748 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-PY-0008_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238251 | 44831 | 1401/07/05 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0992 | 2022-05-23 | 1401/03/02 | T-0992 | 44704 | 1401/03/02 | BK-SUR-ENG-ELE-01-04494 | 44712 | 1401/03/10 | CM-C2 | [6 empty] | 1401-2294-85732 | 2022-06-01 | 1401/03/11 | 44719 | 1401/03/17 | CM | [10 empty] | D01 | IFA | T-1391 | 44815 | 1401/06/20 | T-1391 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05748 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-PY-0008_D00 | [5 empty] | 1401-2294-238251 | 44831 | 1401/07/05 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0008_D00
2 | 1 | 0 | 9 | 0 | 3 | 20 | 2.1.9.3.20 | BK-SSGRL-PEDCO-110-EL-PY-0010 | Earthing & Lightning Layout for well pads |  | BK-SSGRL-PEDCO-110-EL-PY-0010 | BK-SSGRL-PEDCO-110-EL-PY-0010 | BK | SSGRL | PEDCO | 110 | EL | PY | 0010 | F2P-707417 | AFC | IFC | 2022-10-25 | 2022-11-07 | 2022-11-12 | 13 | 5 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-11 |  |  | D00 | IFC | T-1482 | 44845 | 1401/07/19 | T-1482 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05971 | 44859 | 1401/05/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-298753 | 44872 | 1401/08/16 | 44877 | 1401/08/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1482 | 2022-10-11 | 1401/07/19 | T-1482 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05971 | 44859 | 1401/05/03 | CM-C3 | [6 empty] | 1401-2294-298753 | 2022-11-07 | 1401/08/16 | 44877 | 1401/08/21 | CM
2 | 1 | 0 | 9 | 0 | 4 | 0 | 2.1.9.4 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 9 | 0 | 4 | 1 | 2.1.9.4.1 | BK-SSGRL-PEDCO-110-EL-LI-0001 | Electrical Load List of Well Pads |  | BK-SSGRL-PEDCO-110-EL-LI-0001 | BK-SSGRL-PEDCO-110-EL-LI-0001 | BK | SSGRL | PEDCO | 110 | EL | LI | 0001 | F0Z-707418 | AFC | IFC | 2022-02-08 | 2022-02-12 | 2022-02-21 | 4 | 9 | 13 | IFA | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-08 | 2022-05-09 | 2022-05-16 | 1 | 7 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-25 |  |  | D02 | IFA | T-0856 | 44675 | 1401/02/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04161 | 44689 | 1401/02/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54909 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0505 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-ELE-00-02909 | 44593 | 1400/11/13 | CM-C2 | [6 empty] | 1400-2294-407156 | 2022-02-12 | 1400/11/23 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0712 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03642 | 44636 | 1400/12/25 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D00 | [5 empty] | 1400-2294-455098 | 44639 | 1400/12/28 | 44647 | 1401/01/07 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D00 | [9 empty] | D02 | IFA | T-0856 | 44675 | 1401/02/04 |  |  |  | BK-SUR-ENG-ELE-01-04161 | 44689 | 1401/02/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D01 | [5 empty] | 1401-2294-54909 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D01
2 | 1 | 0 | 9 | 0 | 4 | 2 | 2.1.9.4.2 | BK-SSGRL-PEDCO-110-EL-LI-0002 | Electrical Power & Control Cable List of Well Pads |  | BK-SSGRL-PEDCO-110-EL-LI-0002 | BK-SSGRL-PEDCO-110-EL-LI-0002 | BK | SSGRL | PEDCO | 110 | EL | LI | 0002 | F0Z-707419 | AFC | IFC | 2022-06-08 | 2022-06-24 | 2022-07-02 | 16 | 8 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-25 |  |  | D00 | IFC | T-1001 | 44706 | 1401/03/04 | T-1001 | 44709 | 1401/03/07 | BK-SUR-ENG-ELE-01-04608 | 44720 | 1401/03/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-114025 | 44736 | 1401/04/03 | 44744 | 1401/04/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1001 | 2022-05-25 | 1401/03/04 | T-1001 | 44709 | 1401/03/07 | BK-SUR-ENG-ELE-01-04608 | 44720 | 1401/03/18 | CM-C3 | [6 empty] | 1401-2294-114025 | 2022-06-24 | 1401/04/03 | 44744 | 1401/04/11 | CM
2 | 1 | 0 | 9 | 0 | 4 | 3 | 2.1.9.4.3 | BK-SSGRL-PEDCO-110-EL-LI-0003 | Cable Drum Schedule and Cutting List of Well Pads |  | BK-SSGRL-PEDCO-110-EL-LI-0003 | BK-SSGRL-PEDCO-110-EL-LI-0003 | BK | SSGRL | PEDCO | 110 | EL | LI | 0003 | F0Z-707420 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 1 | 0 | 9 | 0 | 5 | 0 | 2.1.9.5 |  | Report
2 | 1 | 0 | 9 | 0 | 5 | 1 | 2.1.9.5.1 | BK-SSGRL-PEDCO-110-EL-RT-0002 | Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report of Well Pads |  | BK-SSGRL-PEDCO-110-EL-RT-0002 | BK-SSGRL-PEDCO-110-EL-RT-0002 | BK | SSGRL | PEDCO | 110 | EL | RT | 0002 | F0Z-707421 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 1 | 0 | 9 | 0 | 5 | 2 | 2.1.9.5.2 | BK-SSGRL-PEDCO-110-EL-RT-0003 | Relay Coordination & Setting Study Report of Well Pads |  | BK-SSGRL-PEDCO-110-EL-RT-0003 | BK-SSGRL-PEDCO-110-EL-RT-0003 | BK | SSGRL | PEDCO | 110 | EL | RT | 0003 | F0Z-707422 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 1 | 0 | 9 | 0 | 5 | 3 | 2.1.9.5.3 | BK-SSGRL-PEDCO-110-EL-RT-0004 | 11KV Over Head Line Study Report |  | BK-SSGRL-PEDCO-110-EL-RT-0004 | BK-SSGRL-PEDCO-110-EL-RT-0004 | BK | SSGRL | PEDCO | 110 | EL | RT | 0004 | F0Z-707423 | IFI | IFC | 2022-04-12 | 2022-05-01 | 2022-05-02 | 19 | 1 | 20 | IFA | 2022-07-31 | 2022-08-18 | 2022-08-20 | 18 | 2 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-29 |  |  | D01 | IFA | T-1166 | 44759 | 1401/04/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-RT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-RT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0761 | 2022-03-29 | 1401/01/09 |  |  |  | BK-SUR-ENG-ELE-01-03742 | 44657 | 1401/01/17 | CM-C3 | [6 empty] | 1401-2294-47897 | 2022-05-01 | 1401/02/11 | 44683 | 1401/02/12 | CM | [10 empty] | D01 | IFA | T-1166 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-RT-0004_D00 | [5 empty] | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-RT-0004_D00
2 | 1 | 0 | 9 | 0 | 5 | 4 | 2.1.9.5.4 | BK-SSGRL-PEDCO-110-EL-RT-0005 | 33KV Over Head Line Study Report |  | BK-SSGRL-PEDCO-110-EL-RT-0005 | BK-SSGRL-PEDCO-110-EL-RT-0005 | BK | SSGRL | PEDCO | 110 | EL | RT | 0005 | F0Z-707424 | IFI | IFC | 2022-04-12 | 2022-05-01 | 2022-05-02 | 19 | 1 | 20 | IFA | 2022-07-31 | 2022-08-18 | 2022-08-20 | 18 | 2 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-29 |  |  | D01 | IFA | T-1166 | 44759 | 1401/04/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-RT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-RT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0761 | 2022-03-29 | 1401/01/09 |  |  |  | BK-SUR-ENG-ELE-01-03742 | 44657 | 1401/01/17 | CM-C3 | [6 empty] | 1401-2294-47897 | 2022-05-01 | 1401/02/11 | 44683 | 1401/02/12 | CM | [10 empty] | D01 | IFA | T-1166 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-RT-0005_D00 | [5 empty] | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-RT-0005_D00
2 | 1 | 0 | 10 | 0 | 0 | 0 | 2.1.10 |  | Architectural
2 | 1 | 0 | 10 | 0 | 1 | 0 | 2.1.10.1 |  | Drawing/Diagram | [61 empty] | Deleted
2 | 1 | 0 | 10 | 0 | 1 | 1 | 2.1.10.1.1 | BK-SSGRL-PEDCO-110-AR-DW-0001 | Architectural Drawing For Fire Shed |  | BK-SSGRL-PEDCO-110-AR-DW-0001 | BK-SSGRL-PEDCO-110-AR-DW-0001 | BK | SSGRL | PEDCO | 110 | AR | DW | 0001 | F4A-709388 | AFD | IFC | 2022-09-17 | 2022-09-12 | 2022-09-13 | -5 | 1 | -4 | IFA | 2022-10-03 | 2022-10-05 | 2022-10-08 | 2 | 3 | 5 | AFC | 2022-10-29 | 2022-11-03 | 2022-11-05 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-03 |  |  | D02 | AFC | T-1499 | 44849 | 1401/07/23 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-05966 | 44858 | 1401/08/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294220 | 44868 | 1401/08/12 | 44870 | 1401/08/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-AR-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1345 | 2022-09-03 | 1401/06/12 |  |  |  | BK-SUR-ENG-ARC-01-05630 | 44815 | 1401/06/20 | CM-C2 | [6 empty] | 1401-2294-221169 | 2022-09-12 | 1401/06/21 | 44817 | 1401/06/22 | CM | [10 empty] | D01 | IFA | T-1421 | 44823 | 1401/06/28 | T-1421 | 44823 | 1401/06/28 | BK-SUR-ENG-ARC-01-05773 | 44832 | 1401/07/06 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-AR-DW-0001_D00 | [5 empty] | 1401-2294-249423 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-AR-DW-0001_D00 | [9 empty] | D02 | AFC | T-1499 | 44849 | 1401/07/23 |  |  |  | BK-SUR-ENG-ARC-01-05966 | 44858 | 1401/08/02 | AP | [6 empty] | 1401-2294-294220 | 44868 | 1401/08/12 | 44870 | 1401/08/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-AR-DW-0001_D01
2 | 1 | 0 | 10 | 0 | 0 | 0 | 2.1.10 |  | Civil
2 | 1 | 0 | 10 | 0 | 1 | 0 | 2.1.10.1 |  | Drawing/Diagram
2 | 1 | 0 | 10 | 0 | 1 | 1 | 2.1.10.1.1 | BK-SSGRL-PEDCO-110-CV-PY-0001 | BINAK Oil Field Project Overall Well Location/Facilities Layout |  | BK-SSGRL-PEDCO-110-CV-PY-0001 | BK-SSGRL-PEDCO-110-CV-PY-0001 | BK | SSGRL | PEDCO | 110 | CV | PY | 0001 | F4A-707425 | AFC | IFC | 2022-04-20 | 2022-04-12 | 2022-04-17 | -8 | 5 | -3 | IFA | 2022-07-31 | 2022-07-28 | 2022-08-01 | -3 | 4 | 1 | AFC | 2022-09-11 | 0 | 0 | -44815 | 0 | -44815 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-06 | 2022-08-28 |  | D02 | AFC | T-1322 | 44801 | 1401/06/06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0783 | 2022-04-06 | 1401/01/17 |  |  |  | BK-SUR-ENG-CIV-01-03799 | 44660 | 1401/01/20 | CM-C2 | [6 empty] | 1401-2294-19624 | 2022-04-12 | 1401/01/23 | 44668 | 1401/01/28 | CM | [10 empty] | D01 | IFA | T-1165 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-CIV-01-05221 | 44766 | 1401/05/02 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-PY-0001_D00 | [5 empty] | 1401-2294-156950 | 44770 | 1401/05/06 | 44774 | 1401/05/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-CV-PY-0001_D00 | [9 empty] | D02 | AFC | T-1322 | 44801 | 1401/06/06 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-PY-0001_D01
2 | 1 | 0 | 10 | 0 | 2 | 0 | 2.1.10.2 |  | Calculation
2 | 1 | 0 | 10 | 0 | 2 | 1 | 2.1.10.2.1 | BK-SSGRL-PEDCO-110-CV-CN-0001 | Calculation Note For Flood Control |  | BK-SSGRL-PEDCO-110-CV-CN-0001 | BK-SSGRL-PEDCO-110-CV-CN-0001 | BK | SSGRL | PEDCO | 110 | CV | CN | 0001 | F0Z-707426 | AFC | IFC | 2021-12-19 | 2021-12-09 | 2021-12-11 | -10 | 2 | -8 | IFA | 2022-01-29 | 2022-01-19 | 2022-01-26 | -10 | 7 | -3 | IFA | 2022-08-07 | 2022-08-02 | 2022-08-09 | -5 | 7 | 2 | IFA | 2022-09-11 | 2022-09-08 | 2022-09-13 | -3 | 5 | 2 | IFA | 2022-10-08 | 2022-10-12 | 2022-10-17 | 4 | 5 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-05 |  |  | D04 | IFA | T-1435 | 44828 | 1401/07/02 | T-1435 | 44830 | 1401/07/04 | BK-SUR-ENG-CIV-01-05834 | 44838 | 1401/07/12 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-260525 | 44846 | 1401/07/20 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0294 | 2021-12-05 | 1400/09/14 |  |  |  | BK-SUR-ENG-CIV-00-02204 | 44535 | 1400/09/14 | CM-C2 | [6 empty] | 1400-2294-310923 | 2021-12-09 | 1400/09/18 | 44541 | 1400/09/20 | CM | [10 empty] | D01 | IFA | T-0460 | 44576 | 1400/10/25 |  |  |  | BK-SUR-ENG-CIV-00-02816 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D00 | [5 empty] | 1400-2294-372879 | 44580 | 1400/10/30 | 44587 | 1400/11/06 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D00 | [9 empty] | D02 | IFA | T-1185 | 44766 | 1401/05/02 |  |  |  | BK-SUR-ENG-CIV-01-05343 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D01 | [5 empty] | 1401-2294-164809 | 44775 | 1401/05/11 | 44782 | 1401/05/18 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D01 | [9 empty] | D03 | IFA | T-1324 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-CIV-01-05571 | 44804 | 1401/06/09 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D02 | [5 empty] | 1401-2294-216183 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D02 | [9 empty] | D04 | IFA | T-1435 | 44828 | 1401/07/02 | T-1435 | 44830 | 1401/07/04 | BK-SUR-ENG-CIV-01-05834 | 44838 | 1401/07/12 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D03 | [5 empty] | 1401-2294-260525 | 44846 | 1401/07/20 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D03
2 | 1 | 0 | 11 | 0 | 0 | 0 | 2.1.11 |  | Structure
2 | 1 | 0 | 11 | 0 | 1 | 0 | 2.1.11.1 |  | Drawing/Diagram
2 | 1 | 0 | 11 | 0 | 1 | 1 | 2.1.11.1.1 | BK-SSGRL-PEDCO-110-ST-DW-0001 | Foundation Drawing For Fire Shed |  | BK-SSGRL-PEDCO-110-ST-DW-0001 | BK-SSGRL-PEDCO-110-ST-DW-0003 | BK | SSGRL | PEDCO | 110 | ST | DW | 0001 | F4A-709389 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[8 empty] | BK-SSGRL-PEDCO-110-ST-DW-0002 | Structural Drawing For Fire Shed |  | BK-SSGRL-PEDCO-110-ST-DW-0002 | BK-SSGRL-PEDCO-110-ST-DW-0003 | BK | SSGRL | PEDCO | 110 | ST | DW | 0002 | F4A-709389 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 1 | 0 | 11 | 0 | 1 | 1 | 2.1.11.1.1 | BK-SSGRL-PEDCO-110-ST-DW-0003 | Typical Drawing For Rig Foundation Plan & Details |  | BK-SSGRL-PEDCO-110-ST-DW-0003 | [8 empty] | - | [51 empty] | 0
2 | 1 | 0 | 12 | 0 | 0 | 0 | 2.1.12 |  | Geotechnical/Geoelectric | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 12 | 1 | 0 | 0 | 2.1.12.1 |  | Geotechnical/Geoelectrical
2 | 1 | 0 | 12 | 1 | 1 | 0 | 2.1.12.1.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 1 | 0 | 12 | 1 | 1 | 1 | 2.1.12.1.1.1 | BK-SSGRL-PEDCO-110-GT-PR-0001 | Geotechnical Investigation Plan for Well Pads |  | BK-SSGRL-PEDCO-110-GT-PR-0001 | BK-SSGRL-PEDCO-110-GT-PR-0001 | BK | SSGRL | PEDCO | 110 | GT | PR | 0001 | F0Z-707427 | AFC | IFC | 2021-08-25 | 2021-08-15 | 2021-08-23 | -10 | 8 | -2 | IFA | 2021-09-21 | 2021-09-13 | 0 | -8 | -44452 | -44460 | IFA | 2021-10-16 | 2021-10-07 | 2021-10-11 | -9 | 4 | -5 | AFC | 2021-11-08 | 2021-10-29 | 2021-11-02 | -10 | 4 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-08-11 | 2021-10-25 |  | D03 | AFC | T-0181 | 44494 | 1400/08/03 | 0 | 0 | 0 | BK-SUR-ENG-GEN-00-01893 | 44502 | 1400/08/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-251689 | 44498 | 1400/08/07 | 44502 | 1400/08/11 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0043 | 2021-08-11 | 1400/05/20 |  |  |  | BK-SUR-ENG-CIV-00-01344 | 44425 | 1400/05/26 | CM-C3 | [6 empty] | 1400/2294/166479 | 2021-08-15 | 1400/05/24 | 44431 | 1400/06/01 | CM | [8 empty] | L-7572 |  | D01 | IFA | T-0082 | 44446 | 1400/06/16 |  |  |  | BK-SUR-ENG-GEN-00-01491 | 44450 | 1400/06/20 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D00 | [5 empty] | 1400-2294-197155 | 44452 | 1400/06/22 |  |  | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D00 | [9 empty] | D02 | IFA | T-0127 | 44471 | 1400/07/10 |  |  |  | BK-SUR-ENG-GEN-00-01679 | 44475 | 1400/07/14 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D01 | [5 empty] | 1400-2290-225564 | 44476 | 1400/07/15 | 44480 | 1400/07/19 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D01 | [9 empty] | D03 | AFC | T-0181 | 44494 | 1400/08/03 |  |  |  | BK-SUR-ENG-GEN-00-01893 | 44502 | 1400/08/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D02 | [5 empty] | 1400-2294-251689 | 44498 | 1400/08/07 | 44502 | 1400/08/11 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D02
2 | 2 | 2 | 0 | 0 | 0 | 0 | 2.2.2 |  | Procurement Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 0 | 0 | 0 | 2.2.2.1 |  | Mechanical
2 | 2 | 2 | 1 | 1 | 0 | 0 | 2.2.2.1.1 |  | Oil Storage Drum of Well Pads
2 | 2 | 2 | 1 | 1 | 1 | 0 | 2.2.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 1 | 1 | 1 | 2.2.2.1.1.1.1 | BK-SSGRL-PEDCO-110-ME-MR-0001 | PMR For Fuel Oil Storage Drum of Well Pads |  | BK-SSGRL-PEDCO-110-ME-MR-0001 | BK-SSGRL-PEDCO-110-ST-DW-0003 | BK | SSGRL | PEDCO | 110 | ME | MR | 0001 | F0Z-709384 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 2 | 1 | 1 | 2 | 0 | 2.2.1.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 1 | 2 | 1 | 2.2.2.1.1.2.1 | BK-SSGRL-PEDCO-110-ME-TB-0001 | TBE For Fuel Oil Storage Drum of Well Pads |  | BK-SSGRL-PEDCO-110-ME-TB-0001 | BK-SSGRL-PEDCO-110-ST-DW-0003 | BK | SSGRL | PEDCO | 110 | ME | TB | 0001 | F0Z-709385 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 2 | 1 | 1 | 0 | 0 | 2.2.2.1.1 |  | Water Tank of Well Pads
2 | 2 | 2 | 1 | 1 | 1 | 0 | 2.2.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 1 | 1 | 1 | 2.2.2.1.1.1.1 | BK-SSGRL-PEDCO-110-ME-MR-0002 | PMR For Potable Water Tank of Well Pads |  | BK-SSGRL-PEDCO-110-ME-MR-0002 | BK-SSGRL-PEDCO-110-ST-DW-0003 | BK | SSGRL | PEDCO | 110 | ME | MR | 0002 | F0Z-709386 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 2 | 1 | 1 | 2 | 0 | 2.2.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 1 | 2 | 1 | 2.2.2.1.1.2.1 | BK-SSGRL-PEDCO-110-ME-TB-0002 | TBE For Potable Water Tank of Well Pads |  | BK-SSGRL-PEDCO-110-ME-TB-0002 | BK-SSGRL-PEDCO-110-ST-DW-0003 | BK | SSGRL | PEDCO | 110 | ME | TB | 0002 | F0Z-709387 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 0 | 0 | 0 | 0 | 0 | 2.2 |  | Package 01-New Well # W018S | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 0 | 0 | 0 | 0 | 2.2.1 |  | Detail Design Engineering
2 | 2 | 1 | 1 | 0 | 0 | 0 | 2.2.1.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 1 | 1 | 0 | 0 | 2.2.1.1.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 1 | 1 | 0 | 1 | 2.2.1.1.1 | BK-W018S-PEDCO-110-PR-PF-0001 | Process Flow Diagram - W018S |  | BK-W018S-PEDCO-110-PR-PF-0001 | BK-W018S-PEDCO-110-PR-PF-0001 | BK | W018S | PEDCO | 110 | PR | PF | 0001 | F2A-707428 | AFC | IFC | 2021-08-18 | 2021-08-30 | 2021-09-07 | 12 | 8 | 20 | IFC | 2021-11-16 | 2022-06-02 | 2022-06-06 | 198 | 4 | 202 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-02 |  |  | D02 | IFA | T-1266 | 44783 | 1401/05/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0030 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-PCS-00-01391 | 44432 | 1400/06/02 | CM-C3 | [6 empty] | 1400/2294/179417 | 2021-08-30 | 1400/06/08 | 44446 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0205 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-PCS-00-02020 | 44516 | 1400/08/25 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D00 | [5 empty] | 1401-2294-87488 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D00 | [9 empty] | D02 | IFA | T-1266 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D01 | [5 empty] | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D01
2 | 2 | 1 | 1 | 1 | 0 | 2 | 2.2.1.1.1 | BK-W018S-PEDCO-110-PR-PI-0001 | P&ID - W018S |  | BK-W018S-PEDCO-110-PR-PI-0001 | BK-W018S-PEDCO-110-PR-PI-0001 | BK | W018S | PEDCO | 110 | PR | PI | 0001 | F2A-707429 | AFC | IFC | 2021-08-23 | 2021-08-30 | 2021-09-06 | 7 | 7 | 14 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | IFA | 2022-09-20 | 2022-11-19 | 2022-11-21 | 60 | 2 | 62 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-01 |  |  | D04 | IFA | T-1368 | 44810 | 1401/06/15 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0036 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PCS-00-01410 | 44433 | 1400/06/03 | CM-C3 | [6 empty] | 1400/2294/179419 | 2021-08-30 | 1400/06/08 | 44445 | 1400/06/15 | RJ | [10 empty] | D01 | IFC | T-0201 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 44516 | 1400/08/25 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 44564 | 1400/10/13 | CM-C3 | PEDCO-BK-W018S-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 44560 | 1400/10/09 | 44564 | 1400/10/13 | RJ | NISOC-BK-W018S-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D02 | [9 empty] | D04 | IFA | T-1368 | 44810 | 1401/06/15 |  |  |  | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D03 | [5 empty] | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D03
2 | 2 | 1 | 1 | 2 | 0 | 0 | 2.2.1.1.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 1 | 2 | 0 | 1 | 2.2.1.1.2 | BK-W018S-PEDCO-110-PR-LI-0001 | Line List - W018S |  | BK-W018S-PEDCO-110-PR-LI-0001 | BK-W018S-PEDCO-110-PR-LI-0001 | BK | W018S | PEDCO | 110 | PR | LI | 0001 | F0Z-707430 | AFC | IFC | 2021-08-23 | 2021-08-30 | 2021-09-06 | 7 | 7 | 14 | IFC | 2021-11-22 | 2021-11-27 | 2021-11-29 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-06-27 | 0 | 166 | -44739 | -44573 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-08 |  |  | D02 | IFA | T-0403 | 44559 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0036 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PCS-00-01410 | 44433 | 1400/06/03 | CM-C3 | [6 empty] | 1400/2294/179419 | 2021-08-30 | 1400/06/08 | 44445 | 1400/06/15 | RJ | [10 empty] | D01 | IFC | T-0217 | 44508 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 44520 | 1400/08/29 | CM-C2 | PEDCO-CRS-D01-BK-W018S-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 44527 | 1400/09/06 | 44529 | 1400/09/08 | CM | NISOC-CRS-D01-BK-W018S-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-LI-0001_D01 | [5 empty] | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-LI-0001_D01
2 | 2 | 1 | 1 | 3 | 0 | 0 | 2.2.1.1.3 |  | Report
2 | 2 | 1 | 1 | 3 | 0 | 1 | 2.2.1.1.3 | BK-W018S-PEDCO-110-PR-RT-0001 | Flow line Hydraulic Calculation Report |  | BK-W018S-PEDCO-110-PR-RT-0001 | BK-W018S-PEDCO-110-PR-RT-0001 | BK | W018S | PEDCO | 110 | PR | RT | 0001 | F0Z-707431 | IFA | IFC | 2021-11-13 | 2021-11-14 | 2021-11-17 | 1 | 3 | 4 | IFA | 2022-01-15 | 2021-02-01 | 2022-02-05 | -348 | 369 | 21 | IFA | 2022-03-08 | 2022-03-10 | 2022-03-13 | 2 | 3 | 5 | IFA | 2022-05-14 | 2022-06-02 | 2022-06-06 | 19 | 4 | 23 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | AFC | 2022-10-22 | 2022-11-19 | 2022-11-20 | 28 | 1 | 29 | [8 empty] | 2021-10-30 | 2022-10-08 |  | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 44514 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 44517 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 44562 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 44228 | 1400/11/12 | 44597 | 1400/11/16 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 44614 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 44627 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 44630 | 1400/12/19 | 44633 | 1400/12/22 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 44681 | 1401/02/10 | T-0878 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 44709 | 1401/03/07 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D02 | [5 empty] | 1401-2294-87489 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D02 | [9 empty] | D04 | IFA | T-1267 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05524 | 44797 | 1401/06/02 | AP | [6 empty] | 1401-2294-235783 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D03 | [9 empty] | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | [10 empty] | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP
2 | 2 | 1 | 1 | 4 | 0 | 0 | 2.2.1.1.4 |  | Data Sheet | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 1 | 4 | 0 | 1 | 2.2.1.1 | BK-W018S-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - W018S |  | BK-W018S-PEDCO-110-PR-DT-0001 | BK-W018S-PEDCO-110-PR-DT-0001 | BK | W018S | PEDCO | 110 | PR | DT | 0001 | F0Z-707432 | AFC | IFC | 2022-04-26 | 2022-05-08 | 2022-05-14 | 12 | 6 | 18 | IFA | 2022-10-26 | 0 | 0 | -44860 | 0 | -44860 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-12 |  |  | D01 | IFA | T-1490 | 44846 | 1401/07/20 | T-1490 | 44846 | 1401/07/20 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 44695 | 1401/02/24 | CM | [10 empty] | D01 | IFA | T-1490 | 44846 | 1401/07/20 | T-1490 | 44846 | 1401/07/20 |  |  |  |  | PEDCO-CRS-BK-W018S-PEDCO-110-PR-DT-0001_D00 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PR-DT-0001_D00
2 | 2 | 1 | 2 | 0 | 0 | 0 | 2.2.1.2 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 2 | 1 | 0 | 0 | 2.2.1.2.1 |  | Drawing/Diagram
2 | 2 | 1 | 2 | 1 | 0 | 1 | 2.2.1.2.1 | BK-W018S-PEDCO-110-PI-PY-0001 | Plot Plan Drawing - W018S |  | BK-W018S-PEDCO-110-PI-PY-0001 | BK-W018S-PEDCO-110-PI-PY-0001 | BK | W018S | PEDCO | 110 | PI | PY | 0001 | F5A-707433 | AFC | IFC | 2021-09-05 | 2021-09-26 | 2021-09-29 | 21 | 3 | 24 | IFA | 2021-11-29 | 2021-12-08 | 2021-12-12 | 9 | 4 | 13 | IFA | 2022-02-14 | 2022-02-26 | 2022-03-05 | 12 | 7 | 19 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D02 | IFA | T-0526 | 44592 | 1400/11/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-424550 | 44618 | 1400/12/07 | 44625 | 1400/12/17 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0057 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PIP-00-01440 | 44439 | 1400/06/09 | CM-C3 | [6 empty] | 1400-2294-213932 | 2021-09-26 | 1400/07/04 | 44468 | 1400/07/07 | CM | [10 empty] | D01 | IFA | T-0240 | 44515 | 1400/08/24 |  |  |  | BK-SUR-ENG-PIP-00-02069 | 44521 | 1400/08/30 | CM-C3 | PEDCO-BK-W018S-PEDCO-110-PI-PY-0001-D00 | [5 empty] | 1400-2294-310810 | 44538 | 1400/09/17 | 44542 | 1400/09/21 | CM | NISOC-BK-W018S-PEDCO-110-PI-PY-0001-D00 | [9 empty] | D02 | IFA | T-0526 | 44592 | 1400/11/11 | [7 empty] | PEDCO-CRS-BK-W018S-PEDCO-110-PI-PY-0001_D01 | [5 empty] | 1400-2294-424550 | 44618 | 1400/12/07 | 44625 | 1400/12/17 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-PY-0001_D01
2 | 2 | 1 | 2 | 1 | 0 | 2 | 2.2.1.2.1 | BK-W018S-PEDCO-110-PI-DW-0001 | Piping Plan - W018S |  | BK-W018S-PEDCO-110-PI-DW-0001 | BK-W018S-PEDCO-110-PI-DW-0001 | BK | W018S | PEDCO | 110 | PI | DW | 0001 | F4L-707434 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 1 | 2 | 1 | 0 | 3 | 2.2.1.2.1 | BK-W018S-PEDCO-110-PI-DW-0002 | Isometric Drawings - W018S |  | BK-W018S-PEDCO-110-PI-DW-0002 | BK-W018S-PEDCO-110-PI-DW-0002 | BK | W018S | PEDCO | 110 | PI | DW | 0002 | F2L-707435 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 1 | 2 | 1 | 0 | 4 | 2.2.1.2.1 | BK-W018S-PEDCO-110-PI-DG-0001 | Material Flow Diagram - W018S |  | BK-W018S-PEDCO-110-PI-DG-0001 | BK-W018S-PEDCO-110-PI-DG-0001 | BK | W018S | PEDCO | 110 | PI | DG | 0001 | F2A-707436 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 2022-06-28 | 2022-07-05 | 34 | 7 | 41 | IFA | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-08 |  |  | D02 | IFA | T-1522 | 44856 | 1401/07/30 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 44521 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D00 | [5 empty] | 1401-2294-122170 | 44740 | 1401/04/07 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D00 | [9 empty] | D02 | IFA | T-1522 | 44856 | 1401/07/30 |  |  |  | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D01 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D01
2 | 2 | 1 | 2 | 2 | 0 | 0 | 2.2.1.2.2 |  | List
2 | 2 | 1 | 2 | 2 | 0 | 1 | 2.2.1.2.2 | BK-W018S-PEDCO-110-PI-LI-0001 | Piping Support List - W018S |  | BK-W018S-PEDCO-110-PI-LI-0001 | BK-W018S-PEDCO-110-PI-LI-0001 | BK | W018S | PEDCO | 110 | PI | LI | 0001 | F0Z-707437 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 1 | 2 | 2 | 0 | 2 | 2.2.1.2.2 | BK-W018S-PEDCO-110-PI-LI-0002 | Critical Line List - W018S |  | BK-W018S-PEDCO-110-PI-LI-0002 | BK-W018S-PEDCO-110-PI-LI-0002 | BK | W018S | PEDCO | 110 | PI | LI | 0002 | F0Z-707438 | AFC | IFC | 2022-05-11 | 2022-05-31 | 2022-06-06 | 20 | 6 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-27 |  |  | D00 | IFC | T-0872 | 44678 | 1401/02/07 | T-0872 | 44678 | 1401/02/07 | BK-SUR-ENG-PIP-01-04121 | 44683 | 1401/02/12 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-85205 | 44712 | 1401/03/10 | 44718 | 1401/03/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0872 | 2022-04-27 | 1401/02/07 | T-0872 | 44678 | 1401/02/07 | BK-SUR-ENG-PIP-01-04121 | 44683 | 1401/02/12 | RJ-C4 | [6 empty] | 1401-2294-85205 | 2022-05-31 | 1401/03/10 | 44718 | 1401/03/16 | CM
2 | 2 | 1 | 2 | 3 | 0 | 0 | 2.2.1.2.3 |  | Report
2 | 2 | 1 | 2 | 3 | 0 | 1 | 2.2.1.2.3 | BK-W018S-PEDCO-110-PI-RT-0001 | PDMS Model Review Report (60%) - W018S |  | BK-W018S-PEDCO-110-PI-RT-0001 | BK-W018S-PEDCO-110-PI-RT-0001 | BK | W018S | PEDCO | 110 | PI | RT | 0001 | F0Z-707439 | IFI | IFC | 2022-04-18 | 2022-04-07 | 2022-04-11 | -11 | 4 | -7 | IFA | 2022-05-25 | 2022-07-01 | 2022-07-05 | 37 | 4 | 41 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-04 |  |  | D01 | IFA | T-0932 | 44692 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04376 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-124359 | 44743 | 1401/04/10 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0774 | 2022-04-04 | 1401/01/15 |  |  |  | BK-SUR-ENG-PIP-01-03849 | 44662 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-13831 | 2022-04-07 | 1401/01/18 | 44662 | 1401/01/22 | CM | [10 empty] | D01 | IFA | T-0932 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-RT-0001_D00 | [5 empty] | 1401-2294-124359 | 44743 | 1401/04/10 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-RT-0001_D00
2 | 2 | 1 | 2 | 3 | 0 | 2 | 2.2.1.2.3 | BK-W018S-PEDCO-110-PI-RT-0002 | PDMS Model Review Report (90%) - W018S |  | BK-W018S-PEDCO-110-PI-RT-0002 | BK-W018S-PEDCO-110-PI-RT-0002 | BK | W018S | PEDCO | 110 | PI | RT | 0002 | F0Z-707440 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 1 | 2 | 4 | 0 | 0 | 2.2.1.2.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 2 | 4 | 0 | 1 | 2.2.1.2 | BK-W018S-PEDCO-110-PI-MT-0001 | MTO For Pipes - W018S |  | BK-W018S-PEDCO-110-PI-MT-0001 | BK-W018S-PEDCO-110-PI-MT-0001 | BK | W018S | PEDCO | 110 | PI | MT | 0001 | F8Z-707441 | IFI | IFI | 2021-12-18 | 2021-12-13 | 2021-12-15 | -5 | 2 | -3 | IFI | 2022-05-01 | 2022-04-28 | 2022-05-02 | -3 | 4 | 1 | IFI | 2022-09-19 | 2022-09-19 | 2022-09-21 | 0 | 2 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-04 |  |  | D02 | IFI | T-1360 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05705 | 44818 | 1401/06/23 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-229868 | 44823 | 1401/06/28 | 44825 | 1401/06/30 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0290 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PIP-00-02319 | 44545 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-316961 | 2021-12-13 | 1400/09/22 | 44545 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0829 | 44668 | 1401/01/28 |  |  |  | BK-SUR-ENG-PIP-01-04062 | 44677 | 1401/02/07 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D00 | [5 empty] | 1401-2294-42948 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D00 | [9 empty] | D02 | IFI | T-1360 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-PIP-01-05705 | 44818 | 1401/06/23 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D01 | [5 empty] | 1401-2294-229868 | 44823 | 1401/06/28 | 44825 | 1401/06/30 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D01
2 | 2 | 1 | 2 | 4 | 0 | 2 | 2.2.1.2 | BK-W018S-PEDCO-110-PI-MT-0002 | MTO For Fittings - W018S |  | BK-W018S-PEDCO-110-PI-MT-0002 | BK-W018S-PEDCO-110-PI-MT-0002 | BK | W018S | PEDCO | 110 | PI | MT | 0002 | F8Z-707442 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-05 | 2022-10-08 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-20 |  |  | D02 | IFI | T-1349 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 44677 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D00 | [5 empty] | 1401-2294-42943 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D00 | [9 empty] | D02 | IFI | T-1349 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D01 | [5 empty] | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D01
2 | 2 | 1 | 2 | 4 | 0 | 3 | 2.2.1.2 | BK-W018S-PEDCO-110-PI-MT-0003 | MTO For Flanges - W018S |  | BK-W018S-PEDCO-110-PI-MT-0003 | BK-W018S-PEDCO-110-PI-MT-0003 | BK | W018S | PEDCO | 110 | PI | MT | 0003 | F8Z-707443 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-05 | 2022-10-08 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-20 |  |  | D02 | IFI | T-1349 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 44677 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D00 | [5 empty] | 1401-2294-42943 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D00 | [9 empty] | D02 | IFI | T-1349 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D01 | [5 empty] | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D01
2 | 2 | 1 | 2 | 4 | 0 | 4 | 2.2.1.2 | BK-W018S-PEDCO-110-PI-MT-0004 | MTO For Manual Valves - W018S |  | BK-W018S-PEDCO-110-PI-MT-0004 | BK-W018S-PEDCO-110-PI-MT-0004 | BK | W018S | PEDCO | 110 | PI | MT | 0004 | F8Z-707444 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-05 | 2022-10-08 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-20 |  |  | D02 | IFI | T-1349 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 44677 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D00 | [5 empty] | 1401-2294-42943 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D00 | [9 empty] | D02 | IFI | T-1349 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D01 | [5 empty] | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D01
2 | 2 | 1 | 2 | 4 | 0 | 5 | 2.2.1.2 | BK-W018S-PEDCO-110-PI-MT-0005 | MTO For Gaskets - W018S |  | BK-W018S-PEDCO-110-PI-MT-0005 | BK-W018S-PEDCO-110-PI-MT-0005 | BK | W018S | PEDCO | 110 | PI | MT | 0005 | F8Z-707445 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-05 | 2022-10-08 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-20 |  |  | D02 | IFI | T-1349 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 44677 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D00 | [5 empty] | 1401-2294-42943 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D00 | [9 empty] | D02 | IFI | T-1349 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D01 | [5 empty] | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D01
2 | 2 | 1 | 2 | 4 | 0 | 6 | 2.2.1.2 | BK-W018S-PEDCO-110-PI-MT-0006 | MTO For Bolt & Nuts - W018S |  | BK-W018S-PEDCO-110-PI-MT-0006 | BK-W018S-PEDCO-110-PI-MT-0006 | BK | W018S | PEDCO | 110 | PI | MT | 0006 | F8Z-707446 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-05 | 2022-10-08 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-20 |  |  | D02 | IFI | T-1349 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 44677 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D00 | [5 empty] | 1401-2294-42943 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D00 | [9 empty] | D02 | IFI | T-1349 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D01 | [5 empty] | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D01
2 | 2 | 1 | 3 | 0 | 0 | 0 | 2.2.1.3 |  | Pipeline & Flow line
2 | 2 | 1 | 3 | 1 | 0 | 0 | 2.2.1.3.1 |  | Drawing/Diagram
2 | 2 | 1 | 3 | 1 | 0 | 1 | 2.2.1.3.1 | BK-W018S-PEDCO-110-PL-DW-0002 | Flow line Transversal Drawings - W018S |  | BK-W018S-PEDCO-110-PL-DW-0002 | BK-W018S-PEDCO-110-PL-DW-0002 | BK | W018S | PEDCO | 110 | PL | DW | 0002 | F4A-707447 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 1 | 3 | 2 | 0 | 0 | 2.2.1.3.2 |  | List
2 | 2 | 1 | 3 | 2 | 0 | 1 | 2.2.1.3.2 | BK-W018S-PEDCO-110-PL-LI-0001 | Road Crossing Location List |  | BK-W018S-PEDCO-110-PL-LI-0001 | BK-W018S-PEDCO-110-PL-LI-0001 | BK | W018S | PEDCO | 110 | PL | LI | 0001 | F0Z-707448 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 1 | 3 | 3 | 0 | 0 | 2.2.1.3.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 3 | 3 | 0 | 1 | 2.2.1.3 | BK-W018S-PEDCO-110-PL-MT-0001 | MTO For Line Pipes (Flow lines) - W018S |  | BK-W018S-PEDCO-110-PL-MT-0001 | BK-W018S-PEDCO-110-PL-MT-0001 | BK | W018S | PEDCO | 110 | PL | MT | 0001 | F8Z-707449 | IFI | IFI | 2021-09-05 | 2021-08-30 | 2021-09-05 | -6 | 6 | 0 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PL-MT-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 44430 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 |  |  |  |  | PEDCO-CRS-BK-W008N-PEDCO-110-PL-MT-0001_D00 | [5 empty] | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PL-MT-0001-D00
2 | 2 | 1 | 4 | 0 | 0 | 0 | 2.2.1.4 |  | Control & Instrumentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 4 | 1 | 0 | 0 | 2.2.1.4.1 |  | Drawing/Diagram
2 | 2 | 1 | 4 | 1 | 0 | 1 | 2.2.1.4.1 | BK-W018S-PEDCO-110-IN-PY-0001 | Instrument Location Layout Drawing - W018S |  | BK-W018S-PEDCO-110-IN-PY-0001 | BK-W018S-PEDCO-110-IN-PY-0001 | BK | W018S | PEDCO | 110 | IN | PY | 0001 | F2J-707450 | AFC | IFC | 2022-03-09 | 2022-03-16 | 2022-03-27 | 7 | 11 | 18 | IFA | 2022-05-08 | 2022-05-21 | 2022-05-23 | 13 | 2 | 15 | IFA | 2022-08-10 | 2022-09-26 | 2022-10-02 | 47 | 6 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-23 |  |  | D02 | IFA | T-1209 | 44769 | 1401/05/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05406 | 44783 | 1401/05/19 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238087 | 44830 | 1401/07/04 | 44836 | 1401/07/10 | CM | NISCO-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0633 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-INS-00-03437 | 44629 | 1400/12/18 | CM-C3 | [6 empty] | 1400-2294-453220 | 2022-03-16 | 1400/12/25 | 44647 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-0858 | 44675 | 1401/02/04 |  |  |  | BK-SUR-ENG-INS-01-04171 | 44689 | 1401/02/18 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D00 | [5 empty] | 1401-2294-68583 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D00 | [9 empty] | D02 | IFA | T-1209 | 44769 | 1401/05/05 |  |  |  | BK-SUR-ENG-INS-01-05406 | 44783 | 1401/05/19 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D01 | [5 empty] | 1401-2294-238087 | 44830 | 1401/07/04 | 44836 | 1401/07/10 | CM | NISCO-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D01
2 | 2 | 1 | 4 | 2 | 0 | 0 | 2.2.1.4.2 |  | MTO
2 | 2 | 1 | 4 | 2 | 0 | 1 | 2.2.1.4 | BK-W018S-PEDCO-110-IN-MT-0001 | MTO For Instrument Tube and Fitting - W018S |  | BK-W018S-PEDCO-110-IN-MT-0001 | BK-W018S-PEDCO-110-IN-MT-0001 | BK | W018S | PEDCO | 110 | IN | MT | 0001 | F8Z-707451 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-14 |  |  | D02 | IFI | T-0451 | 44573 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W018N-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0237 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02141 | 44528 | 1400/09/08 | RJ-C4 | [6 empty] | 1400-2294-283475 | 2021-11-21 | 1400/08/30 | 44529 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 44548 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 44562 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MT-0001_D00 | [5 empty] | 1400-2294-347953 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0001_D00 | [9 empty] | D02 | IFI | T-0451 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W018N-PEDCO-110-IN-MT-0001_D01 | [5 empty] | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0001_D01
2 | 2 | 1 | 4 | 2 | 0 | 2 | 2.2.1.4 | BK-W018S-PEDCO-110-IN-MT-0002 | MTO For Instrument Cable Tray - W018S |  | BK-W018S-PEDCO-110-IN-MT-0002 | BK-W018S-PEDCO-110-IN-MT-0002 | BK | W018S | PEDCO | 110 | IN | MT | 0002 | F8Z-707452 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-14 |  |  | D02 | IFI | T-0451 | 44573 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W018N-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0237 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02141 | 44528 | 1400/09/08 | RJ-C4 | [6 empty] | 1400-2294-283475 | 2021-11-21 | 1400/08/30 | 44529 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 44548 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 44562 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MT-0002_D00 | [5 empty] | 1400-2294-347953 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0002_D00 | [9 empty] | D02 | IFI | T-0451 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W018N-PEDCO-110-IN-MT-0002_D01 | [5 empty] | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0002_D01
2 | 2 | 1 | 5 | 0 | 0 | 0 | 2.2.1.5 |  | Safety
2 | 2 | 1 | 5 | 1 | 0 | 0 | 2.2.1.5.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 5 | 1 | 0 | 1 | 2.2.1.5.1 | BK-W018S-PEDCO-110-SA-PY-0001 | Hazardous Area Classification Layout - W018S |  | BK-W018S-PEDCO-110-SA-PY-0001 | BK-W018S-PEDCO-110-SA-PY-0001 | BK | W018S | PEDCO | 110 | SA | PY | 0001 | F2L-707453 | AFC | IFC | 2021-11-29 | 2021-12-06 | 2022-04-19 | 7 | 134 | 141 | AFC | 2022-05-15 | 2022-05-09 | 2022-05-21 | -6 | 12 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-15 | 2022-05-01 |  | D01 | AFC | T-0887 | 44682 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54966 | 44690 | 1401/02/19 | 44702 | 1401/02/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0248 | 2021-11-15 | 1400/08/24 | [13 empty] | 1400-2294-305726 | 2021-12-06 | 1400/09/15 | 44670 | 1401/01/30 | AP | [10 empty] | D01 | AFC | T-0887 | 44682 | 1401/02/11 | [13 empty] | 1401-2294-54966 | 44690 | 1401/02/19 | 44702 | 1401/02/31 | AP
2 | 2 | 1 | 5 | 1 | 0 | 2 | 2.2.1.5.1 | BK-W018S-PEDCO-110-SA-PY-0002 | Safety & Fire Fighting Equipment Location Layout - W018S |  | BK-W018S-PEDCO-110-SA-PY-0002 | BK-W018S-PEDCO-110-SA-PY-0002 | BK | W018S | PEDCO | 110 | SA | PY | 0002 | F2L-707454 | AFC | IFC | 2021-09-21 | 2021-09-21 | 2021-09-25 | 0 | 4 | 4 | IFA | 2021-10-17 | 2021-10-19 | 2021-10-23 | 2 | 4 | 6 | AFC | 2022-05-03 | 2022-04-30 | 2022-05-07 | -3 | 7 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-07 | 2022-04-19 |  | D02 | AFC | T-0843 | 44670 | 1401/01/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45395 | 44681 | 1401/02/10 | 44688 | 1401/02/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0080 | 2021-09-07 | 1400/06/16 | [13 empty] | 1400-2294-207960 | 2021-09-21 | 1400/06/31 | 44464 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0131 | 44472 | 1400/07/10 | [13 empty] | 1400-2294-240499 | 44488 | 1400/07/27 | 44492 | 1400/08/01 | AP | NISOC-CRS-BK-W018S-PEDCO-110-SA-PY-0002_D00 | 1400-2294-241737 | 44488 | 1400/07/27 |  |  | AP |  |  |  | D02 | AFC | T-0843 | 44670 | 1401/01/30 | [13 empty] | 1401-2294-45395 | 44681 | 1401/02/10 | 44688 | 1401/02/17 | AP
2 | 2 | 1 | 5 | 1 | 0 | 3 | 2.2.1.5.1 | BK-W018S-PEDCO-110-SA-PY-0003 | Escape Route & Safety Sign Layout - W018S |  | BK-W018S-PEDCO-110-SA-PY-0003 | BK-W018S-PEDCO-110-SA-PY-0003 | BK | W018S | PEDCO | 110 | SA | PY | 0003 | F2L-707455 | AFC | IFC | 2021-11-29 | 2021-12-06 | 2022-04-19 | 7 | 134 | 141 | AFC | 2022-05-30 | 2022-05-21 | 2022-05-23 | -9 | 2 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-15 | 2022-05-16 |  | D01 | AFC | T-0956 | 44697 | 1401/02/26 | T-0956 | 44697 | 1401/02/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70735 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0248 | 2021-11-15 | 1400/08/24 | [13 empty] | 1400-2294-305726 | 2021-12-06 | 1400/09/15 | 44670 | 1401/01/30 | AP | [10 empty] | D01 | AFC | T-0956 | 44697 | 1401/02/26 | T-0956 | 44697 | 1401/02/26 | [10 empty] | 1401-2294-70735 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP
2 | 2 | 1 | 5 | 2 | 0 | 0 | 2.2.1.5.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 5 | 2 | 0 | 1 | 2.2.1.5.2 | BK-W018S-PEDCO-110-SA-LI-0001 | Hazard Source List - W018S |  | BK-W018S-PEDCO-110-SA-LI-0001 | BK-W018S-PEDCO-110-SA-LI-0001 | BK | W018S | PEDCO | 110 | SA | LI | 0001 | F0Z-707456 | AFC | IFC | 2021-11-23 | 2021-11-30 | 2021-12-06 | 7 | 6 | 13 | IFA | 2022-02-16 | 2022-03-08 | 2022-03-06 | 20 | -2 | 18 | IFA | 2022-04-26 | 2022-06-07 | 2022-06-11 | 42 | 4 | 46 | AFC | 2022-08-09 | 2022-09-01 | 2022-09-04 | 23 | 3 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-09 | 2022-07-26 |  | D03 | AFC | T-1197 | 44768 | 1401/05/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205788 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-W018S-PEDCO-110-SA-LI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0544 | 44594 | 1400/11/13 | [13 empty] | 1400-2294-435413 | 44628 | 1400/12/15 | 44626 | 1400/12/15 | CM | NISOC-CRS-BK-W018S-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0806 | 44663 | 1401/01/23 | [13 empty] | 1401-2294-92282 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-W018S-PEDCO-110-SA-LI-0001_D01 | [9 empty] | D03 | AFC | T-1197 | 44768 | 1401/05/04 | [13 empty] | 1401-2294-205788 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-W018S-PEDCO-110-SA-LI-0001_D02
2 | 2 | 1 | 5 | 3 | 0 | 0 | 2.2.1.5.3 |  | MTO
2 | 2 | 1 | 5 | 3 | 0 | 1 | 2.2.1.5 | BK-W018S-PEDCO-110-SA-MT-0001 | MTO For Fire Fighting & Safety Equipment - W018S |  | BK-W018S-PEDCO-110-SA-MT-0001 | BK-W018S-PEDCO-110-SA-MT-0001 | BK | W018S | PEDCO | 110 | SA | MT | 0001 | F8Z-707457 | IFI | IFI | 2021-11-29 | 2021-12-06 | 2022-02-22 | 7 | 78 | 85 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-15 |  |  | D00 | IFI | T-0245 | 44515 | 1400/08/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-305188 | 44536 | 1400/09/15 | 44614 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0245 | 2021-11-15 | 1400/08/24 | [13 empty] | 1400-2294-305188 | 2021-12-06 | 1400/09/15 | 44614 | 1400/12/03 | AP
2 | 2 | 1 | 5 | 3 | 0 | 2 | 2.2.1.5 | BK-W018S-PEDCO-110-SA-MT-0002 | MTO For Safety Sign - W018S |  | BK-W018S-PEDCO-110-SA-MT-0002 | BK-W018S-PEDCO-110-SA-MT-0002 | BK | W018S | PEDCO | 110 | SA | MT | 0002 | F8Z-707458 | IFI | IFI | 2021-11-29 | 2021-12-06 | 2022-02-22 | 7 | 78 | 85 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-15 |  |  | D00 | IFI | T-0245 | 44515 | 1400/08/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-305188 | 44536 | 1400/09/15 | 44614 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0245 | 2021-11-15 | 1400/08/24 | [13 empty] | 1400-2294-305188 | 2021-12-06 | 1400/09/15 | 44614 | 1400/12/03 | AP
2 | 2 | 1 | 6 | 0 | 0 | 0 | 2.2.1.6 |  | Architecture
2 | 2 | 1 | 6 | 1 | 0 | 0 | 2.2.1.6.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 6 | 1 | 0 | 1 | 2.2.1.6 | BK-W018S-PEDCO-110-AR-DW-0001 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W018 |  | BK-W018S-PEDCO-110-AR-DW-0001 | BK-W018S-PEDCO-110-AR-DW-0001 | BK | W018S | PEDCO | 110 | AR | DW | 0001 | F4A-707459 | AFC | IFC | 2022-03-07 | 2022-02-27 | 2022-03-08 | -8 | 9 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-21 |  |  | D00 | IFC | T-0617 | 44613 | 1400/12/02 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03203 | 44615 | 1400/12/04 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-427462 | 44619 | 1400/12/08 | 44628 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0617 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-ENG-ARC-00-03203 | 44615 | 1400/12/04 | CM-C2 | [6 empty] | 1400-2294-427462 | 2022-02-27 | 1400/12/08 | 44628 | 1400/12/17 | AP
2 | 2 | 1 | 7 | 0 | 0 | 0 | 2.2.1.7 |  | Civil
2 | 2 | 1 | 7 | 1 | 0 | 0 | 2.2.1.7.1 |  | Drawing/Diagram
2 | 2 | 1 | 7 | 1 | 0 | 1 | 2.2.1.7.1 | BK-W018S-PEDCO-110-CV-PY-0001 | General Civil Layout - W018S |  | BK-W018S-PEDCO-110-CV-PY-0001 | BK-W018S-PEDCO-110-CV-PY-0001 | BK | W018S | PEDCO | 110 | CV | PY | 0001 | F4A-707460 | AFC | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | 4 | -4 | IFA | 2021-09-11 | 2021-08-29 | 2021-09-04 | -13 | 6 | -7 | IFA | 2021-09-27 | 2021-09-18 | 2021-09-18 | -9 | 0 | -9 | IFA | 2021-11-06 | 2021-10-29 | 2021-11-02 | -8 | 4 | -4 | AFC | 2021-12-04 | 2021-11-23 | 2021-11-27 | -11 | 4 | -7 | AFC | 2022-01-10 | 2021-12-30 | 2022-01-02 | -11 | 3 | -8 | [8 empty] | 2021-07-28 | 2021-12-27 |  | D05 | AFC | T-0384 | 44557 | 1400/10/06 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-02525 | 44563 | 1400/10/12 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D04 | 0 | 0 | 0 | 0 | 0 | 1400-2294-342104 | 44560 | 1400/10/09 | 44563 | 1400/10/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0018 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-CIV-00-01260 | 44412 | 1400/05/13 | CM-C3 |  | نقشه شماتيك Waste management موقعيت W018 | 44419 | 1400/05/20 | CM |  | 1400/2294/152141 | 2021-08-03 | 1400/05/12 | 44415 | 1400/05/16 | CM | [10 empty] | D01 | IFA | T-0067 | 44436 | 1400/06/06 |  |  |  | BK-SUR-ENG-CIV-00-01432 | 44438 | 1400/06/08 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D00 | [5 empty] | 1400-2294-177757 | 44437 | 1400/06/07 | 44443 | 1400/06/13 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D00 | [9 empty] | D02 | IFA | T-0089 | 44452 | 1400/06/22 |  |  |  | BK-SUR-ENG-CIV-00-01544 | 44457 | 1400/06/27 | RJ-C4 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D01 | [5 empty] | 1400-2294-200540 | 44457 | 1400/06/27 | 44457 | 1400/06/27 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D01 | [9 empty] | D03 | IFA | T-0180 | 44492 | 1400/08/01 |  |  |  | BK-SUR-ENG-CIV-00-01871 | 44500 | 1400/08/09 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D02 | [5 empty] | 1400-2294-251688 | 44498 | 1400/08/07 | 44502 | 1400/08/11 | AP | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D02 | [9 empty] | D04 | AFC | T-0257 | 44520 | 1400/08/29 |  |  |  | BK-SUR-ENG-CIV-00-02056 | 44521 | 1400/08/30 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D03 | [5 empty] | 1400-2294-287963 | 44523 | 1400/09/02 | 44527 | 1400/09/06 | AP | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D03 | [9 empty] | D05 | AFC | T-0384 | 44557 | 1400/10/06 |  |  |  | BK-SUR-ENG-CIV-00-02525 | 44563 | 1400/10/12 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D04 | [5 empty] | 1400-2294-342104 | 44560 | 1400/10/09 | 44563 | 1400/10/12 | AP
2 | 2 | 1 | 7 | 1 | 0 | 2 | 2.2.1.7.1 | BK-W018S-PEDCO-110-CV-PY-0002 | Civil and Structural drawings - W018S |  | BK-W018S-PEDCO-110-CV-PY-0002 | BK-W018S-PEDCO-110-CV-PY-0002 | BK | W018S | PEDCO | 110 | CV | PY | 0002 | F4S-707461 | AFC | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | 4 | -4 | IFA | 2022-01-18 | 2022-01-08 | 2022-01-11 | -10 | 3 | -7 | AFC | 2022-11-22 | 0 | 0 | -44887 | 0 | -44887 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2022-11-08 |  | D02 | AFC | T-0673 | 44873 | 1401/08/17 | T-0673 | 44873 | 1401/08/17 | BK-SUR-ENG-CIV-01-06131 | 44873 | 1401/08/17 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0021 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-CIV-00-01261 | 44412 | 1400/05/13 | CM-C3 | [6 empty] | 1400/2294/152142 | 2021-08-03 | 1400/05/12 | 44415 | 1400/05/16 | CM | [10 empty] | D01 | IFA | T-0425 | 44565 | 1400/10/14 |  |  |  | BK-SUR-ENG-CIV-00-02642 | 44572 | 1400/10/21 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0002-D01 | [5 empty] | 1400-2294-354625 | 44569 | 1400/10/18 | 44572 | 1400/10/21 | AP | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0002-D01 | [9 empty] | D02 | AFC | T-0673 | 44873 | 1401/08/17 | T-0673 | 44873 | 1401/08/17 | BK-SUR-ENG-CIV-01-06131 | 44873 | 1401/08/17 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0002_D01 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0002_D01
2 | 2 | 1 | 7 | 1 | 0 | 3 | 2.2.1.7.1 | BK-W018S-PEDCO-110-CV-DW-0001 | Rough Grading Plans -W018S |  | BK-W018S-PEDCO-110-CV-DW-0001 | BK-W018S-PEDCO-110-CV-DW-0001 | BK | W018S | PEDCO | 110 | CV | DW | 0001 | F4S-707462 | AFC | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | 4 | -4 | IFC | 2021-11-13 | 2021-11-02 | 2021-11-06 | -11 | 4 | -7 | IFA | 2022-01-29 | 2022-01-20 | 2022-01-22 | -9 | 2 | -7 | IFA | 2022-03-12 | 2022-03-02 | 2022-03-05 | -10 | 3 | -7 | AFC | 2022-03-27 | 2022-03-16 | 2022-03-27 | -11 | 11 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-10-30 | 2022-03-13 |  | D03 | AFC | T-0727 | 44633 | 1400/12/22 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03505 | 44633 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-453185 | 44636 | 1400/12/25 | 44647 | 1401/01/07 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0017 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-CIV-00-01259 | 44412 | 1400/05/13 | CM | [6 empty] | 1400/2294/152130 | 2021-08-03 | 1400/05/12 | 44415 | 1400/05/16 | RJ | [10 empty] | D00 | IFC | T-0195 | 44499 | 1400/08/08 |  |  |  | BK-SUR-ENG-CIV-00-01905 | 44503 | 1400/08/12 | CM-C2 | [6 empty] | 1400-2294-259112 | 44502 | 1400/08/11 | 44506 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0461 | 44576 | 1400/10/25 |  |  |  | BK-SUR-ENG-CIV-00-02702 | 44577 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-DW-0001_D00 | [5 empty] | 1400-2294-372851 | 44581 | 1400/10/30 | 44583 | 1400/11/02 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-DW-0001_D00 | [9 empty] | D03 | IFA | T-0643 | 44618 | 1400/12/07 | [7 empty] | PEDCO-CRS-BK-W018S-PEDCO-110-CV-DW-0001_D01 | [5 empty] | 1400-2294-431005 | 44622 | 1400/12/11 | 44625 | 1400/12/15 | AP | NISOC-CRS-BK-W018S-PEDCO-110-CV-DW-0001_D01 | [9 empty] | D03 | AFC | T-0727 | 44633 | 1400/12/22 |  |  |  | BK-SUR-ENG-CIV-00-03505 | 44633 | 1400/12/22 | AP | [6 empty] | 1400-2294-453185 | 44636 | 1400/12/25 | 44647 | 1401/01/07 | AP
2 | 2 | 1 | 7 | 2 | 0 | 0 | 2.2.1.7.2 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 7 | 2 | 0 | 1 | 2.2.1.7.2 | BK-W018S-PEDCO-110-CV-CN-0001 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W018S |  | BK-W018S-PEDCO-110-CV-CN-0001 | BK-W018S-PEDCO-110-CV-CN-0001 | BK | W018S | PEDCO | 110 | CV | CN | 0001 | F0Z-707463 | AFC | IFC | 2022-03-05 | 2022-02-27 | 2022-02-22 | -6 | -5 | -11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D00 | IFC | T-0600 | 44611 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03411 | 44628 | 1400/12/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421741 | 44619 | 1400/12/08 | 44614 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0600 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-CIV-00-03411 | 44628 | 1400/12/17 | CM-C3 | [6 empty] | 1400-2294-421741 | 2022-02-27 | 1400/12/08 | 44614 | 1400/12/03 | AP
2 | 2 | 1 | 7 | 3 | 0 | 0 | 2.2.1.7.3 |  | MTO
2 | 2 | 1 | 7 | 3 | 0 | 1 | 2.2.1.7 | BK-W018S-PEDCO-110-CV-MT-0001 | MTO For Civil Works - W018S |  | BK-W018S-PEDCO-110-CV-MT-0001 | BK-W018S-PEDCO-110-CV-MT-0001 | BK | W018S | PEDCO | 110 | CV | MT | 0001 | F8Z-707464 | IFI | IFI | 2022-05-29 | 2022-05-21 | 2022-05-23 | -8 | 2 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-15 |  |  | D00 | IFI | T-0955 | 44696 | 1401/02/25 | T-0955 | 44696 | 1401/02/25 | BK-SUR-ENG-CIV-01-04413 | 44704 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-69670 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0955 | 2022-05-15 | 1401/02/25 | T-0955 | 44696 | 1401/02/25 | BK-SUR-ENG-CIV-01-04413 | 44704 | 1401/03/02 | AP | [6 empty] | 1401-2294-69670 | 2022-05-21 | 1401/02/31 | 44704 | 1401/03/02 | AP
2 | 2 | 1 | 8 | 0 | 0 | 0 | 2.2.1.8 |  | Structure
2 | 2 | 1 | 8 | 1 | 0 | 0 | 2.2.1.8.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 8 | 1 | 0 | 1 | 2.2.1.8.1 | BK-W018S-PEDCO-110-ST-DW-0001 | Structure Drawing For WHCP/HPU Shelter - W018S |  | BK-W018S-PEDCO-110-ST-DW-0001 | BK-W018S-PEDCO-110-ST-DW-0001 | BK | W018S | PEDCO | 110 | ST | DW | 0001 | F4M-707465 | AFC | IFC | 2022-04-10 | 2022-04-03 | 2022-04-09 | -7 | 6 | -1 | IFA | 2022-05-15 | 2022-05-08 | 2022-05-11 | -7 | 3 | -4 | AFC | 2022-05-30 | 0 | 0 | -44711 | 0 | -44711 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-27 | 2022-05-16 |  | D02 | AFC | T-0961 | 44697 | 1401/02/26 | T-0961 | 44697 | 1401/02/26 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W018S-PEDCO-110-ST-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0755 | 2022-03-27 | 1401/01/07 |  |  |  | BK-SUR-ENG-STR-01-03764 | 44660 | 1401/01/20 | CM | [6 empty] | 1401-2294-7521 | 2022-04-03 | 1401/01/14 | 44660 | 1401/01/20 | CM | [10 empty] | D01 | IFA | T-0893 | 44682 | 1401/02/11 |  |  |  | BK-SUR-ENG-STR-01-04140 | 44688 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-ST-DW-0001_D00 | [5 empty] | 1401-2294-52742 | 44689 | 1401/02/18 | 44692 | 1401/02/21 | AP | NISOC-CRS-BK-W018S-PEDCO-110-ST-DW-0001_D00 | [9 empty] | D02 | AFC | T-0961 | 44697 | 1401/02/26 | T-0961 | 44697 | 1401/02/26 |  |  |  |  | PEDCO-CRS-BK-W018S-PEDCO-110-ST-DW-0001_D01
2 | 2 | 1 | 8 | 1 | 0 | 2 | 2.2.1.8.1 | BK-W018S-PEDCO-110-ST-DW-0002 | Platform Structure Drawing - W018S |  | BK-W018S-PEDCO-110-ST-DW-0002 | BK-W018S-PEDCO-110-ST-DW-0002 | BK | W018S | PEDCO | 110 | ST | DW | 0002 | F4M-707466 | AFC | IFC | 2022-02-16 | 2022-02-08 | 2022-02-13 | -8 | 5 | -3 | IFC | 2022-05-01 | 2022-05-08 | 2022-05-11 | 7 | 3 | 10 | IFA | 2022-07-04 | 2022-06-26 | 2022-06-29 | -8 | 3 | -5 | AFC | 2022-10-10 | 0 | 0 | -44844 | 0 | -44844 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-17 | 2022-09-26 |  | D03 | AFC | T-1332 | 44830 | 1401/07/04 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-05625 | 44814 | 1401/06/19 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-ST-DW-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0535 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-STR-00-03007 | 44601 | 1400/11/20 | RJ-C4 | [6 empty] | 1400-2294-402774 | 2022-02-08 | 1400/11/19 | 44605 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0832 | 44668 | 1401/01/28 |  |  |  | BK-SUR-ENG-STR-01-04053 | 44677 | 1401/02/06 | CM-C3 | PEDCO-CRS-BK-W18S-PEDCO-000-ST-DW-0002_D00 | [5 empty] | 1401-2294-52739 | 44689 | 1401/02/18 | 44692 | 1401/02/21 | CM | NISOC-CRS-BK-W18S-PEDCO-000-ST-DW-0002_D00 | [9 empty] | D02 | IFA | T-1097 | 44732 | 1401/03/30 |  |  |  | BK-SUR-ENG-STR-01-04907 | 44740 | 1401/04/07 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-000-ST-DW-0002_D01 | [5 empty] | 1401-2294-118040 | 44738 | 1401/04/05 | 44741 | 1401/04/08 | AP | NISOC-CRS-BK-W018S-PEDCO-000-ST-DW-0002_D01 | [9 empty] | D03 | AFC | T-1332 | 44830 | 1401/07/04 |  |  |  | BK-SUR-ENG-STR-01-05625 | 44814 | 1401/06/19 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-ST-DW-0002_D02
[8 empty] | BK-W018S-PEDCO-110-ST-CN-0003 | CALCULATION NOTE WHCP/ HPU SHELTER |  | BK-W018S-PEDCO-110-ST-CN-0003 | BK-W018S-PEDCO-110-ST-CN-0003 | BK | W018S | PEDCO | 110 | ST | CN | 3 | F4M-707467 | AFC | IFC | 2022-05-15 | 2022-05-08 | 2022-05-11 | -7 | 3 | -4 | AFC | 2022-06-05 | 2022-05-31 | 2022-06-06 | -5 | 6 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-01 | 2022-05-22 |  | D01 | AFC | T-0961 | 44703 | 1401/02/02 | T-0961 | 44728 | 1401/02/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-85213 | 44712 | 1401/03/10 | 44718 | 1401/03/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0894 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-52752 | 2022-05-08 | 1401/02/18 | 44692 | 1401/02/21 | AP | [10 empty] | D01 | AFC | T-0961 | 44703 | 1401/02/02 | T-0961 | 44728 | 1401/02/26 | [10 empty] | 1401-2294-85213 | 44712 | 1401/03/10 | 44718 | 1401/03/16 | AP
2 | 2 | 1 | 8 | 2 | 0 | 0 | 2.2.1.8.2 |  | MTO
2 | 2 | 1 | 8 | 2 | 0 | 1 | 2.2.1.8 | BK-W018S-PEDCO-110-ST-MT-0001 | MTO For Structural Works - W018S |  | BK-W018S-PEDCO-110-ST-MT-0001 | BK-W018S-PEDCO-110-ST-MT-0001 | BK | W018S | PEDCO | 110 | ST | MT | 0001 | F8Z-707467 | IFI | IFI | 2022-05-16 | 2022-05-09 | 2022-05-21 | -7 | 12 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-02 |  |  | D00 | IFI | T-0896 | 44683 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-04427 | 44705 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54881 | 44690 | 1401/02/19 | 44702 | 1401/02/31 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0896 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-STR-01-04427 | 44705 | 1401/03/03 | AP | [6 empty] | 1401-2294-54881 | 2022-05-09 | 1401/02/19 | 44702 | 1401/02/31 | CM
2 | 2 | 1 | 9 | 0 | 0 | 0 | 2.2.1.9 |  | Geotechnic/Geoelectric
2 | 2 | 1 | 9 | 1 | 0 | 0 | 2.2.1.9.1 |  | Geotechnic
2 | 2 | 1 | 9 | 1 | 1 | 0 | 2.2.9.1.1 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 9 | 1 | 1 | 1 | 2.2.1.9.1.1.1 | BK-W018S-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - W018S |  | BK-W018S-PEDCO-110-GT-RT-0001 | BK-W018S-PEDCO-110-GT-RT-0001 | BK | W018S | PEDCO | 110 | GT | RT | 0001 | F0Z-707468 | IFI | IFC | 2022-03-12 | 2022-03-05 | 2022-03-08 | -7 | 3 | -4 | IFA | 2022-10-29 | 2022-11-05 | 2022-11-06 | 7 | 1 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-26 |  |  | D01 | IFA | T-1495 | 44849 | 1401/07/23 | T-1495 | 44849 | 1401/07/23 | BK-SUR-ENG-CIV-01-05963 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-295374 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-W018S-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0641 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-CIV-00-03408 | 44628 | 1400/12/17 | CM-C3 | [6 empty] | 1400-2294-435012 | 2022-03-05 | 1400/12/14 | 44628 | 1400/12/17 | CM | [10 empty] | D01 | IFA | T-1495 | 44849 | 1401/07/23 | T-1495 | 44849 | 1401/07/23 | BK-SUR-ENG-CIV-01-05963 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-GT-RT-0001_D00 | [5 empty] | 1401-2294-295374 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-W018S-PEDCO-110-GT-RT-0001_D00
2 | 2 | 1 | 9 | 2 | 0 | 0 | 2.2.1.9.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 1 | 9 | 2 | 0 | 1 | 2.2.1.9 | BK-W018S-PEDCO-110-SU-DW-0001 | Flow line Plan & Profile Drawings - W018S |  | BK-W018S-PEDCO-110-SU-DW-0001 | BK-W018S-PEDCO-110-SU-DW-0001 | BK | W018S | PEDCO | 110 | SU | DW | 0001 | F4A-707469 | AFC | IFC | 2022-03-12 | 0 | 0 | -44632 | 0 | -44632 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-26 |  |  | D00 | IFC | T-0636 | 44618 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03419 | 44628 | 1400/12/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0636 | 2022-02-26 | 1400/12/04 |  |  |  | BK-SUR-ENG-PPL-00-03419 | 44628 | 1400/12/17 | CM-C3
2 | 2 | 2 | 0 | 0 | 0 | 0 | 2.2.2 |  | Procurement Engineering
2 | 2 | 2 | 1 | 0 | 0 | 0 | 2.2.2.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 1 | 0 | 0 | 2.2.2.1.1 |  | Pipes
2 | 2 | 2 | 1 | 1 | 1 | 0 | 2.2.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 1 | 1 | 1 | 2.2.2.1.1.1.1 | BK-W018S-PEDCO-110-PI-MR-0001 | PMR For Pipes - W018S |  | BK-W018S-PEDCO-110-PI-MR-0001 | BK-W018S-PEDCO-110-PI-MR-0001 | BK | W018S | PEDCO | 110 | PI | MR | 0001 | F0Z-707470 | IFI | IFI | 2021-12-20 | 2021-12-15 | 2021-12-15 | -5 | 0 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-06 |  |  | D00 | IFI | T-0298 | 44536 | 1400/09/15 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02320 | 44545 | 1400/09/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-315076 | 44542 | 1400/09/21 | 44545 | 1400/09/24 | AP | 0 | 1400-2294-316959 | 44545 | 1400/09/22 | 0 | 0 | CM | 0 | 0 |  | D00 | IFI | T-0298 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02320 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 44545 | 1400/09/24 | AP |  | 1400-2294-316959 | 44545 | 1400/09/22 |  |  | CM
2 | 2 | 2 | 1 | 1 | 2 | 0 | 2.2.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 1 | 2 | 1 | 2.2.2.1.1.2.1 | BK-W018S-PEDCO-110-PI-TB-0001 | TBE For Pipes - W018S |  | BK-W018S-PEDCO-110-PI-TB-0001 | BK-W018S-PEDCO-110-PI-TB-0001 | BK | W018S | PEDCO | 110 | PI | TB | 0001 | F0Z-707471 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 2 | 1 | 2 | 0 | 0 | 2.2.2.1.2 |  | Fittings
2 | 2 | 2 | 1 | 2 | 1 | 0 | 2.2.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 2 | 1 | 1 | 2.2.2.1.2.1.1 | BK-W018S-PEDCO-110-PI-MR-0002 | PMR For Fittings - W018S |  | BK-W018S-PEDCO-110-PI-MR-0002 | BK-W018S-PEDCO-110-PI-MR-0002 | BK | W018S | PEDCO | 110 | PI | MR | 0002 | F0Z-707472 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-05 | 2022-10-08 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-04 |  |  | D01 | IFI | T-1349 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1349 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0002_D00 | [5 empty] | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0002_D00
2 | 2 | 2 | 1 | 2 | 2 | 0 | 2.2.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 2 | 2 | 1 | 2.2.2.1.2.2.1 | BK-W018S-PEDCO-110-PI-TB-0002 | TBE For Fitting - W018S |  | BK-W018S-PEDCO-110-PI-TB-0002 | BK-W018S-PEDCO-110-PI-TB-0002 | BK | W018S | PEDCO | 110 | PI | TB | 0002 | F0Z-707473 | IFI | IFI | 2022-09-03 | 2022-09-10 | 2022-09-13 | 7 | 3 | 10 | IFI | 2022-11-21 | 0 | 0 | -44886 | 0 | -44886 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-20 |  |  | D01 | IFI | T-1579 | 44872 | 1401/08/16 | T-1579 | 44872 | 1401/08/16 | BK-SUR-ENG-PIP-01-06210 | 44884 | 1401/08/28 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1287 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-PIP-01-05496 | 44795 | 1401/05/31 | RJ-C4 | [6 empty] | 1401-2294-218268 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/23 | CM | [10 empty] | D01 | IFI | T-1579 | 44872 | 1401/08/16 | T-1579 | 44872 | 1401/08/16 | BK-SUR-ENG-PIP-01-06210 | 44884 | 1401/08/28 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0002_D00 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0002_D00
2 | 2 | 2 | 1 | 3 | 0 | 0 | 2.2.2.1.3 |  | Flanges
2 | 2 | 2 | 1 | 3 | 1 | 0 | 2.2.1.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 3 | 1 | 1 | 2.2.2.1.3.1.1 | BK-W018S-PEDCO-110-PI-MR-0003 | PMR For Flanges - W018S |  | BK-W018S-PEDCO-110-PI-MR-0003 | BK-W018S-PEDCO-110-PI-MR-0003 | BK | W018S | PEDCO | 110 | PI | MR | 0003 | F0Z-707474 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-05 | 2022-10-08 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-04 |  |  | D01 | IFI | T-1349 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1349 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0003_D00 | [5 empty] | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0003_D00
2 | 2 | 2 | 1 | 3 | 2 | 0 | 2.2.1.3.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 3 | 2 | 1 | 2.2.2.1.3.2.1 | BK-W018S-PEDCO-110-PI-TB-0003 | TBE For Flanges - W018S |  | BK-W018S-PEDCO-110-PI-TB-0003 | BK-W018S-PEDCO-110-PI-TB-0003 | BK | W018S | PEDCO | 110 | PI | TB | 0003 | F0Z-707475 | IFI | IFI | 2022-02-27 | 2022-04-01 | 2022-03-05 | 33 | -27 | 6 | IFI | 2022-07-27 | 2022-08-02 | 2022-08-06 | 6 | 4 | 10 | IFI | 2022-10-17 | 0 | 0 | -44851 | 0 | -44851 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 |  |  | D02 | IFI | T-1454 | 44837 | 1401/07/11 | T-1454 | 44837 | 1401/07/11 | BK-SUR-ENG-PIP-01-05829 | 44838 | 1401/07/12 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0003-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0003-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 44625 | 1400/12/14 | RJ-C4 | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 44625 | 1400/12/14 | CM | [10 empty] | D01 | IFI | T-1155 | 44755 | 1401/04/22 |  |  |  | BK-SUR-ENG-PIP-01-05203 | 44762 | 1401/04/29 | C4-RJ | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0003-D00 | [5 empty] | 1401-2294-165008 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0003-D00 | [9 empty] | D02 | IFI | T-1454 | 44837 | 1401/07/11 | T-1454 | 44837 | 1401/07/11 | BK-SUR-ENG-PIP-01-05829 | 44838 | 1401/07/12 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0003-D01 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0003-D01
2 | 2 | 2 | 1 | 4 | 0 | 0 | 2.2.2.1.4 |  | Manual Valves
2 | 2 | 2 | 1 | 4 | 1 | 0 | 2.2.1.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 4 | 1 | 1 | 2.2.2.1.4.1.1 | BK-W018S-PEDCO-110-PI-MR-0004 | PMR For Manual Valves - W018S |  | BK-W018S-PEDCO-110-PI-MR-0004 | BK-W018S-PEDCO-110-PI-MR-0004 | BK | W018S | PEDCO | 110 | PI | MR | 0004 | F0Z-707476 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-05 | 2022-10-08 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-04 |  |  | D01 | IFI | T-1349 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1349 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0004_D00 | [5 empty] | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0004_D00
2 | 2 | 2 | 1 | 4 | 2 | 0 | 2.2.1.4.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 4 | 2 | 1 | 2.2.2.1.4.2.1 | BK-W018S-PEDCO-110-PI-TB-0004 | TBE For Manual Valves - W018S |  | BK-W018S-PEDCO-110-PI-TB-0004 | BK-W018S-PEDCO-110-PI-TB-0004 | BK | W018S | PEDCO | 110 | PI | TB | 0004 | F0Z-707477 | IFI | IFI | 2022-02-27 | 2022-04-01 | 2022-03-05 | 33 | -27 | 6 | IFI | 2022-11-02 | 2022-11-03 | 2022-11-06 | 1 | 3 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 |  |  | D01 | IFI | T-1516 | 44853 | 1401/07/27 | T-1516 | 44853 | 1401/07/27 | BK-SUR-ENG-PIP-01-05976 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294098 | 44868 | 1401/08/12 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 44625 | 1400/12/14 | RJ-C4 | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 44625 | 1400/12/14 | CM | [10 empty] | D01 | IFI | T-1516 | 44853 | 1401/07/27 | T-1516 | 44853 | 1401/07/27 | BK-SUR-ENG-PIP-01-05976 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0004_D00 | [5 empty] | 1401-2294-294098 | 44868 | 1401/08/12 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0004_D00
2 | 2 | 2 | 1 | 5 | 0 | 0 | 2.2.2.1.5 |  | Gaskets
2 | 2 | 2 | 1 | 5 | 1 | 0 | 2.2.1.5.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 5 | 1 | 1 | 2.2.2.1.5.1.1 | BK-W018S-PEDCO-110-PI-MR-0005 | PMR For Gaskets - W018S |  | BK-W018S-PEDCO-110-PI-MR-0005 | BK-W018S-PEDCO-110-PI-MR-0005 | BK | W018S | PEDCO | 110 | PI | MR | 0005 | F0Z-707478 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-05 | 2022-10-08 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-04 |  |  | D01 | IFI | T-1349 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1349 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05614 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0005_D00 | [5 empty] | 1401-2294-249366 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0005_D00
2 | 2 | 2 | 1 | 5 | 2 | 0 | 2.2.1.5.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 5 | 2 | 1 | 2.2.2.1.5.2.1 | BK-W018S-PEDCO-110-PI-TB-0005 | TBE For Gaskets - W018S |  | BK-W018S-PEDCO-110-PI-TB-0005 | BK-W018S-PEDCO-110-PI-TB-0005 | BK | W018S | PEDCO | 110 | PI | TB | 0005 | F0Z-707479 | IFI | IFI | 2022-02-27 | 2022-04-01 | 2022-03-05 | 33 | -27 | 6 | IFI | 2022-10-22 | 2022-10-29 | 2022-10-31 | 7 | 2 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-13 |  |  | D01 | IFI | T-1463 | 44842 | 1401/07/16 | T-1463 | 44842 | 1401/07/16 | BK-SUR-ENG-PIP-01-05897 | 44846 | 1401/07/20 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284130 | 44863 | 1401/08/07 | 44865 | 1401/08/09 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 44625 | 1400/12/14 | RJ-C4 | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 44625 | 1400/12/14 | CM | [10 empty] | D01 | IFI | T-1463 | 44842 | 1401/07/16 | T-1463 | 44842 | 1401/07/16 | BK-SUR-ENG-PIP-01-05897 | 44846 | 1401/07/20 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0005_D00 | [5 empty] | 1401-2294-284130 | 44863 | 1401/08/07 | 44865 | 1401/08/09 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0005_D00
2 | 2 | 2 | 1 | 6 | 0 | 0 | 2.2.2.1.6 |  | Bolt & Nuts | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 6 | 1 | 0 | 2.2.1.6.1 |  | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 6 | 1 | 1 | 2.2.2.1.6.1.1 | BK-W018S-PEDCO-110-PI-MR-0006 | PMR For Bolt/Nuts - W018S |  | BK-W018S-PEDCO-110-PI-MR-0006 | BK-W018S-PEDCO-110-PI-MR-0006 | BK | W018S | PEDCO | 110 | PI | MR | 0006 | F0Z-707480 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-09-20 | 2022-09-24 | 2 | 4 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-04 |  |  | D01 | IFI | T-1353 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05617 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-231048 | 44824 | 1401/06/29 | 44828 | 1401/07/02 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1353 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05617 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0006_D01 | [5 empty] | 1401-2294-231048 | 44824 | 1401/06/29 | 44828 | 1401/07/02 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0006_D01
2 | 2 | 2 | 1 | 6 | 2 | 0 | 2.2.1.6.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 6 | 2 | 1 | 2.2.2.1.6.2.1 | BK-W018S-PEDCO-110-PI-TB-0006 | TBE For Bolt/Nuts - W018S |  | BK-W018S-PEDCO-110-PI-TB-0006 | BK-W018S-PEDCO-110-PI-TB-0006 | BK | W018S | PEDCO | 110 | PI | TB | 0006 | F0Z-707481 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 1 | 7 | 0 | 0 | 2.2.2.1.7 |  | Sampling Connection | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 7 | 1 | 0 | 2.2.1.7.1 |  | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 7 | 1 | 1 | 2.2.2.1.7.1.1 | BK-W018S-PEDCO-110-PI-MR-0007 | PMR For Sampling Connection Set - W018S |  | BK-W018S-PEDCO-110-PI-MR-0007 | BK-W018S-PEDCO-110-PI-MR-0007 | BK | W018S | PEDCO | 110 | PI | MR | 0007 | F0Z-707482 | IFI | IFI | 2022-03-06 | 2022-03-09 | 2022-03-07 | 3 | -2 | 1 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-23 |  |  | D01 | IFI | T-1532 | 44857 | 1401/08/01 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-06147 | 44874 | 1401/08/18 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296596 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0613 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PIP-00-03420 | 44628 | 1400/12/17 | CM-C2 | [6 empty] | 1400-2294-438859 | 2022-03-09 | 1400/12/18 | 44627 | 1400/12/16 | RJ | [10 empty] | D01 | IFI | T-1532 | 44857 | 1401/08/01 |  |  |  | BK-SUR-ENG-PIP-01-06147 | 44874 | 1401/08/18 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0007_D00 | [5 empty] | 1401-2294-296596 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0007_D00
2 | 2 | 2 | 1 | 7 | 2 | 0 | 2.2.1.7.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 7 | 2 | 1 | 2.2.2.1.7.2.1 | BK-W018S-PEDCO-110-PI-TB-0007 | TBE For Sampling Connection |  | BK-W018S-PEDCO-110-PI-TB-0007 | BK-W018S-PEDCO-110-PI-TB-0007 | BK | W018S | PEDCO | 110 | PI | TB | 0007 | F0Z-707483 | IFI | IFI | 2022-11-06 | 0 | 0 | -44871 | 0 | -44871 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-23 |  |  | D00 | IFI | T-1537 | 44857 | 1401/08/01 | T-1537 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1537 | 2022-10-23 | 1401/08/01 | T-1537 | 44857 | 1401/08/01
2 | 2 | 2 | 1 | 8 | 0 | 0 | 2.2.2.1.8 |  | Stone Trap
2 | 2 | 2 | 1 | 8 | 1 | 0 | 2.2.1.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 8 | 1 | 1 | 2.2.2.1.8.1.1 | BK-W018S-PEDCO-110-PI-MR-0008 | PMR For Stone Trap - W018S |  | BK-W018S-PEDCO-110-PI-MR-0008 | BK-W018S-PEDCO-110-PI-MR-0008 | BK | W018S | PEDCO | 110 | PI | MR | 0008 | F0Z-707484 | IFI | IFI | 2022-05-11 | 2022-04-30 | 2022-05-14 | -11 | 14 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-27 |  |  | D00 | IFI | T-0869 | 44678 | 1401/02/07 | T-0869 | 44678 | 1401/02/07 | BK-SUR-ENG-PIP-01-04122 | 44683 | 1401/02/12 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45413 | 44681 | 1401/02/10 | 44695 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0869 | 2022-04-27 | 1401/02/07 | T-0869 | 44678 | 1401/02/07 | BK-SUR-ENG-PIP-01-04122 | 44683 | 1401/02/12 | CM-C2 | [6 empty] | 1401-2294-45413 | 2022-04-30 | 1401/02/10 | 44695 | 1401/02/24 | CM
2 | 2 | 2 | 1 | 8 | 2 | 0 | 2.2.1.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 8 | 2 | 1 | 2.2.2.1.8.2.1 | BK-W018S-PEDCO-110-PI-TB-0008 | TBE For Stone Trap - W018S |  | BK-W018S-PEDCO-110-PI-TB-0008 | BK-W018S-PEDCO-110-PI-TB-0008 | BK | W018S | PEDCO | 110 | PI | TB | 0008 | F0Z-707485 | IFI | IFI | 2022-06-07 | 2022-06-14 | 2022-06-15 | 7 | 1 | 8 | IFI | 2022-11-15 | 0 | 0 | -44880 | 0 | -44880 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-24 |  |  | D01 | IFI | T-1569 | 44866 | 1401/08/10 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-06100 | 44871 | 1401/08/15 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03 | T-0996 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04515 | 44713 | 1401/03/11 | CM-C3 | [6 empty] | 1401-2294-102043 | 2022-06-14 | 1401/03/24 | 44727 | 1401/03/25 | CM | [10 empty] | D01 | IFI | T-1569 | 44866 | 1401/08/10 |  |  |  | BK-SUR-ENG-PIP-01-06100 | 44871 | 1401/08/15 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0008_D01 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0008_D01
2 | 2 | 2 | 1 | 9 | 0 | 0 | 2.2.2.1.9 |  | Pipe Support
2 | 2 | 2 | 1 | 9 | 1 | 0 | 2.2.1.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 9 | 1 | 1 | 2.2.2.1.9.1.1 | BK-W018S-PEDCO-110-PI-MR-0010 | PMR For Pipe Support - W018S |  | BK-W018S-PEDCO-110-PI-MR-0010 | BK-W018S-PEDCO-110-PI-MR-0010 | BK | W018S | PEDCO | 110 | PI | MR | 0010 | F0Z-707486 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 1 | 9 | 2 | 0 | 2.2.1.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 9 | 2 | 1 | 2.2.2.1.9.2.1 | BK-W018S-PEDCO-110-PI-TB-0010 | TBE For Pipe Support - W018S |  | BK-W018S-PEDCO-110-PI-TB-0010 | BK-W018S-PEDCO-110-PI-TB-0010 | BK | W018S | PEDCO | 110 | PI | TB | 0010 | F0Z-707487 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 1 | 9 | 0 | 0 | 2.2.2.1.9 |  | BURN PIT PIPES
2 | 2 | 2 | 1 | 9 | 1 | 0 | 2.2.1.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 9 | 1 | 1 | 2.2.2.1.9.1.1 | BK-W018S-PEDCO-110-PI-MR-0010 | PMR FOR BURN PIT PIPES– W018S |  | BK-W018S-PEDCO-110-PI-MR-0011 | BK-W018S-PEDCO-110-PI-MR-0010 | BK | W018S | PEDCO | 110 | PI | MR | 0010 | F0Z-707486 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [11 empty] | D00 | IFI | T-1550 | 44859 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1550 | 2022-10-25 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2
2 | 2 | 2 | 1 | 9 | 2 | 0 | 2.2.1.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 1 | 9 | 2 | 1 | 2.2.2.1.9.2.1 | BK-W018S-PEDCO-110-PI-TB-0010 |  |  | BK-W018S-PEDCO-110-PI-TB-0011 | BK-W018S-PEDCO-110-PI-TB-0010 | BK | W018S | PEDCO | 110 | PI | TB | 0010 | F0Z-707487 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14
2 | 2 | 2 | 2 | 0 | 0 | 0 | 2.2.2.2 |  | Pipeline
2 | 2 | 2 | 2 | 1 | 0 | 0 | 2.2.2.2.1 |  | Line Pipe | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 2 | 1 | 1 | 0 | 2.2.2.1.1 |  | Purchase Material Requisition (PMR)
2 | 2 | 2 | 2 | 1 | 1 | 1 | 2.2.2.2.1.1.1 | BK-W018S-PEDCO-110-PL-MR-0001 | PMR For Line Pipes - W018S |  | BK-W018S-PEDCO-110-PL-MR-0001 | BK-W018S-PEDCO-110-PL-MR-0001 | BK | W018S | PEDCO | 110 | PL | MR | 0001 | F0Z-707488 | IFI | IFI | 2021-12-20 | 2021-12-13 | 2021-12-15 | -7 | 2 | -5 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-06 |  |  | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W018S-PEDCO-110-PL-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PL-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0299 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PPL-00-02321 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-316957 | 2021-12-13 | 1400/09/22 | 44545 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 |  |  |  |  | PEDCO-CRS-BK-W018S-PEDCO-110-PL-MR-0001_D00 | [5 empty] | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PL-MR-0001_D00
2 | 2 | 2 | 2 | 1 | 2 | 0 | 2.2.2.1.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 2 | 1 | 2 | 1 | 2.2.2.2.1.2.1 | BK-W018S-PEDCO-110-PL-TB-0001 | TBE For Line Pipes - W018S |  | BK-W018S-PEDCO-110-PL-TB-0001 | BK-W018S-PEDCO-110-PL-TB-0001 | BK | W018S | PEDCO | 110 | PL | TB | 0001 | F0Z-707489 | IFI | IFI | 2022-03-05 | 2022-03-10 | 2022-03-14 | 5 | 4 | 9 | IFI | 2022-05-28 | 2022-05-31 | 2022-06-07 | 3 | 7 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 44628 | 1400/12/17 | RJ-C4 | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 44634 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | [5 empty] | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PL-TB-0001-D00
2 | 2 | 2 | 2 | 2 | 0 | 0 | 2.2.2.2.2 |  | Line Support
2 | 2 | 2 | 2 | 2 | 1 | 0 | 2.2.2.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 2 | 2 | 1 | 1 | 2.2.2.2.2.1.1 | BK-W018S-PEDCO-110-PL-MR-0002 | PMR For Flow Line Support - W018S |  | BK-W018S-PEDCO-110-PL-MR-0002 | BK-W018S-PEDCO-110-PL-MR-0002 | BK | W018S | PEDCO | 110 | PL | MR | 0002 | F0Z-707490 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 2 | 2 | 2 | 0 | 2.2.2.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 2 | 2 | 2 | 1 | 2.2.2.2.2.2.1 | BK-W018S-PEDCO-110-PL-TB-0002 | TBE For Flow Line Support - W018S |  | BK-W018S-PEDCO-110-PL-TB-0002 | BK-W018S-PEDCO-110-PL-TB-0002 | BK | W018S | PEDCO | 110 | PL | TB | 0002 | F0Z-707491 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 3 | 0 | 0 | 0 | 2.2.2.3 |  | Control & Instrumentation
2 | 2 | 2 | 3 | 1 | 0 | 0 | 2.2.2.3.1 |  | WHCP/HPU | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 3 | 1 | 1 | 0 | 2.2.3.1.1 |  | Purchase Material Requisition (PMR)
2 | 2 | 2 | 3 | 1 | 1 | 1 | 2.2.2.3.1.1.1 | BK-W018S-PEDCO-110-IN-MR-0001 | PMR For WHCP/HPU - W018S |  | BK-W018S-PEDCO-110-IN-MR-0001 | BK-W018S-PEDCO-110-IN-MR-0001 | BK | W018S | PEDCO | 110 | IN | MR | 0001 | F0Z-707492 | IFI | IFI | 2021-11-29 | 2021-12-17 | 2021-12-07 | 18 | -10 | 8 | IFI | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 | IFI | 2022-07-04 | 2022-08-14 | 2022-08-16 | 41 | 2 | 43 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-15 |  |  | D02 | IFI | T-1096 | 44732 | 1401/03/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05244 | 44768 | 1401/05/04 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177113 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0243 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-INS-00-02170 | 44531 | 1400/09/10 | RJ-C4 |  | BK-SUR-ENG-INS-00-02224 | 44537 | 1400/09/16 | CM-C3 |  | 1400-2294-320808 | 2021-12-17 | 1400/09/26 | 44537 | 1400/09/16 | CM | [10 empty] | D01 | IFI | T-0470 | 44577 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02865 | 44591 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D00 | [5 empty] | 1400-2294-390765 | 44592 | 1400/11/11 | 44593 | 1400/11/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D00 | [9 empty] | D02 | IFI | T-1096 | 44732 | 1401/03/30 |  |  |  | BK-SUR-ENG-INS-01-05244 | 44768 | 1401/05/04 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D01 | [5 empty] | 1401-2294-177113 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D01
2 | 2 | 2 | 3 | 1 | 2 | 0 | 2.2.3.1.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 3 | 1 | 2 | 1 | 2.2.2.3.1.2.1 | BK-W018S-PEDCO-110-IN-TB-0001 | TBE/TBA For WHCP/HPU - W018S |  | BK-W018S-PEDCO-110-IN-TB-0001 | BK-W018S-PEDCO-110-IN-TB-0001 | BK | W018S | PEDCO | 110 | IN | TB | 0001 | F0Z-707493 | IFI | IFI | 2021-12-14 | 2021-12-14 | 2021-12-15 | 0 | 1 | 1 | IFI | 2022-03-05 | 2022-04-04 | 2022-04-09 | 30 | 5 | 35 | IFI | 2022-07-18 | 2022-07-06 | 2022-07-12 | -12 | 6 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-30 |  |  | D02 | IFI | T-1136 | 44746 | 1401/04/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05364 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-132654 | 44748 | 1401/04/15 | 44754 | 1401/04/21 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0284 | 2021-11-30 | 1400/09/09 |  |  |  | BK-SUR-ENG-INS-00-02296 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318638 | 2021-12-14 | 1400/09/23 | 44545 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0602 | 44611 | 1400/11/30 |  |  |  | BK-SUR-ENG-INS-00-03345 | 44625 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D00 | [5 empty] | 1401-2294-9652 | 44655 | 1401/01/15 | 44660 | 1401/01/20 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D00 | [9 empty] | D02 | IFI | T-1136 | 44746 | 1401/04/13 |  |  |  | BK-SUR-ENG-INS-01-05364 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D01 | [5 empty] | 1401-2294-132654 | 44748 | 1401/04/15 | 44754 | 1401/04/21 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D01
2 | 2 | 2 | 3 | 2 | 0 | 0 | 2.2.2.3.2 |  | Field Instrumentations
2 | 2 | 2 | 3 | 2 | 1 | 0 | 2.2.3.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 3 | 2 | 1 | 1 | 2.2.2.3.2.1.1 | BK-W018S-PEDCO-110-IN-MR-0002 | PMR For Field Instrumentations - W018S |  | BK-W018S-PEDCO-110-IN-MR-0002 | BK-W018S-PEDCO-110-IN-MR-0002 | BK | W018S | PEDCO | 110 | IN | MR | 0002 | F0Z-707494 | IFI | IFI | 2021-12-27 | 2022-01-21 | 2021-01-25 | 25 | -361 | -336 | IFI | 2022-08-13 | 2022-09-08 | 2022-09-13 | 26 | 5 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-13 |  |  | D01 | IFI | T-1218 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 44557 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/10/01 | 44221 | 1400/11/05 | CM | [10 empty] | D01 | IFI | T-1218 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0002_D00 | [5 empty] | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MR-0002_D00
2 | 2 | 2 | 3 | 2 | 2 | 0 | 2.2.3.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 3 | 2 | 2 | 1 | 2.2.2.3.2.2.1 | BK-W018S-PEDCO-110-IN-TB-0002 | TBE/TBA For Field Instrumentations - W018S |  | BK-W018S-PEDCO-110-IN-TB-0002 | BK-W018S-PEDCO-110-IN-TB-0002 | BK | W018S | PEDCO | 110 | IN | TB | 0002 | F0Z-707495 | IFI | IFI | 2022-06-11 | 2022-06-21 | 2022-07-05 | 10 | 14 | 24 | IFI | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-26 |  |  | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | T-1012 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-05635 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-111541 | 2022-06-21 | 1401/03/31 | 44747 | 1401/04/14 | RJ | [10 empty] | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0002_D00 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-IN-TB-0002_D00
2 | 2 | 2 | 3 | 3 | 0 | 0 | 2.2.2.3.3 |  | Instrument Bulk Items
2 | 2 | 2 | 3 | 3 | 1 | 0 | 2.2.3.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 3 | 3 | 1 | 1 | 2.2.2.3.3.1.1 | BK-W018S-PEDCO-110-IN-MR-0003 | PMR For Instrument Bulk Items - W018S |  | BK-W018S-PEDCO-110-IN-MR-0003 | BK-W018S-PEDCO-110-IN-MR-0003 | BK | W018S | PEDCO | 110 | IN | MR | 0003 | F0Z-707496 | IFI | IFI | 2022-02-01 | 2022-03-06 | 2022-03-08 | 33 | 2 | 35 | IFI | 2022-09-18 | 2022-09-21 | 2022-10-02 | 3 | 11 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-18 |  |  | D01 | IFI | T-1351 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W018S-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0472 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-INS-00-02832 | 44587 | 1400/11/09 | CM-C2 | [6 empty] | 1400-2294-436921 | 2022-03-06 | 1400/12/15 | 44628 | 1400/12/17 | CM | [10 empty] | D01 | IFI | T-1351 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0003_D00 | [5 empty] | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W018S-PEDCO-110-IN-MR-0003_D00
2 | 2 | 2 | 3 | 3 | 2 | 0 | 2.2.3.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 3 | 3 | 2 | 1 | 2.2.2.3.3.2.1 | BK-W018S-PEDCO-110-IN-TB-0003 | TBE/TBA For Instrument Bulk Items - W018S |  | BK-W018S-PEDCO-110-IN-TB-0003 | BK-W018S-PEDCO-110-IN-TB-0003 | BK | W018S | PEDCO | 110 | IN | TB | 0003 | F0Z-707497 | IFI | IFI | 2022-02-16 | 2022-03-19 | 2022-03-14 | 31 | -5 | 26 | IFI | 2022-11-08 | 2022-11-17 | 2022-11-19 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-02 |  |  | D01 | IFI | T-1555 | 44859 | 1401/08/03 | T-1555 | 44859 | 1401/08/03 | BK-SUR-ENG-INS-01-06134 | 44873 | 1401/08/17 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-315870 | 44882 | 1401/08/26 | 44884 | 1401/08/28 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-TB-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | [6 empty] | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 44634 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-1555 | 44859 | 1401/08/03 | T-1555 | 44859 | 1401/08/03 | BK-SUR-ENG-INS-01-06134 | 44873 | 1401/08/17 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0003_D00 | [5 empty] | 1401-2294-315870 | 44882 | 1401/08/26 | 44884 | 1401/08/28 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-TB-0003_D00
2 | 2 | 2 | 4 | 0 | 0 | 0 | 2.2.2.4 |  | Safety & Fire Fighting
2 | 2 | 2 | 4 | 1 | 0 | 0 | 2.2.2.4.1 |  | Fire Fighting and Safety Equipment
2 | 2 | 2 | 4 | 1 | 1 | 0 | 2.2.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 4 | 1 | 1 | 1 | 2.2.2.4.1.1.1 | BK-W018S-PEDCO-110-SA-MR-0001 | PMR For Fire Fighting and Safety Equipment - W018S |  | BK-W018S-PEDCO-110-SA-MR-0001 | BK-W018S-PEDCO-110-SA-MR-0001 | BK | W018S | PEDCO | 110 | SA | MR | 0001 | F0Z-707498 | IFI | IFI | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | IFI | 2022-05-25 | 2022-07-05 | 2022-07-17 | 41 | 12 | 53 | FI | 2022-11-07 | 2022-10-29 | 2022-10-01 | -9 | -28 | -37 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-08 | 2022-10-24 |  | D02 | FI | T-1542 | 44858 | 1401/08/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285739 | 44863 | 1401/08/08 | 44835 | 1401/08/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | CM | [10 empty] | D01 | IFI | T-0933 | 44692 | 1401/02/21 | [13 empty] | 1401-2294-130088 | 44747 | 1401/04/14 | 44759 | 1401/04/26 | AP | NISOC-CRS-BK-W018S-PEDCO-110-SA-MR-0001_D00 | [9 empty] | D02 | FI | T-1542 | 44858 | 1401/08/02 | [13 empty] | 1401-2294-285739 | 44863 | 1401/08/08 | 44835 | 1401/08/10 | AP
2 | 2 | 2 | 4 | 1 | 2 | 0 | 2.2.4.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 4 | 1 | 2 | 1 | 2.2.2.4.1.2.1 | BK-W018S-PEDCO-110-SA-TB-0001 | TBE For Fire Fighting and Safety Equipment - W018S |  | BK-W018S-PEDCO-110-SA-TB-0001 | BK-W018S-PEDCO-110-SA-TB-0001 | BK | W018S | PEDCO | 110 | SA | TB | 0001 | F0Z-707499 | IFI | IFI | 2022-03-26 | 2022-04-13 | 2022-04-16 | 18 | 3 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-12 |  |  | D00 | IFI | T-0721 | 44632 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-22713 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0721 | 2022-03-12 | 1400/12/21 | [13 empty] | 1401-2294-22713 | 2022-04-13 | 1401/01/24 | 44667 | 1401/01/27 | CM
2 | 2 | 2 | 4 | 2 | 0 | 0 | 2.2.2.4.2 |  | Safety Sign
2 | 2 | 2 | 4 | 2 | 1 | 0 | 2.2.4.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 4 | 2 | 1 | 1 | 2.2.2.4.2.1.1 | BK-W018S-PEDCO-110-SA-MR-0002 | PMR For Fire Safety Sign - W018S |  | BK-W018S-PEDCO-110-SA-MR-0002 | BK-W018S-PEDCO-110-SA-MR-0002 | BK | W018S | PEDCO | 110 | SA | MR | 0002 | F0Z-707500 | IFI | IFI | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-08 |  |  | D00 | IFI | T-0316 | 44538 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 44550 | 1400/09/29 | 44552 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | AP
2 | 2 | 2 | 4 | 2 | 2 | 0 | 2.2.4.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 4 | 2 | 2 | 1 | 2.2.2.4.2.2.1 | BK-W018S-PEDCO-110-SA-TB-0002 | TBE For Fire Safety Sign - W018S |  | BK-W018S-PEDCO-110-SA-TB-0002 | BK-W018S-PEDCO-110-SA-TB-0002 | BK | W018S | PEDCO | 110 | SA | TB | 0002 | F0Z-707501 | IFI | IFI | 2022-03-26 | 2022-04-13 | 2022-04-16 | 18 | 3 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-12 |  |  | D00 | IFI | T-0721 | 44632 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-22713 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0721 | 2022-03-12 | 1400/12/21 | [13 empty] | 1401-2294-22713 | 2022-04-13 | 1401/01/24 | 44667 | 1401/01/27 | CM
2 | 2 | 2 | 5 | 0 | 0 | 0 | 2.2.2.5 |  | Structure
2 | 2 | 2 | 5 | 1 | 0 | 0 | 2.2.2.5.1 |  | Steel Structure Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 5 | 1 | 1 | 0 | 2.2.5.1.1 |  | Purchase Material Requisition (PMR)
2 | 2 | 2 | 5 | 1 | 1 | 1 | 2.2.2.5.1.1.1 | BK-W018S-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - W018S |  | BK-W018S-PEDCO-110-ST-MR-0001 | BK-W018S-PEDCO-110-ST-MR-0001 | BK | W018S | PEDCO | 110 | ST | MR | 0001 | F0Z-707502 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 5 | 1 | 2 | 0 | 2.2.5.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 5 | 1 | 2 | 1 | 2.2.2.5.1.2.1 | BK-W018S-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - W018S |  | BK-W018S-PEDCO-110-ST-TB-0001 | BK-W018S-PEDCO-110-ST-TB-0001 | BK | W018S | PEDCO | 110 | ST | TB | 0001 | F0Z-707503 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 5 | 2 | 0 | 0 | 2.2.2.5.2 |  | Anchor Bolts | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 5 | 2 | 1 | 0 | 2.2.5.2.1 |  | Purchase Material Requisition (PMR)
2 | 2 | 2 | 5 | 2 | 1 | 1 | 2.2.2.5.2.1.1 | BK-W018S-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - W018S |  | BK-W018S-PEDCO-110-ST-MR-0002 | BK-W018S-PEDCO-110-ST-MR-0002 | BK | W018S | PEDCO | 110 | ST | MR | 0002 | F0Z-707504 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 5 | 2 | 2 | 0 | 2.2.5.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 5 | 2 | 2 | 1 | 2.2.2.5.2.2.1 | BK-W018S-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - W018S |  | BK-W018S-PEDCO-110-ST-TB-0002 | BK-W018S-PEDCO-110-ST-TB-0002 | BK | W018S | PEDCO | 110 | ST | TB | 0002 | F0Z-707505 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 6 | 0 | 0 | 0 | 2.2.2.6 |  | Civil | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 6 | 1 | 0 | 0 | 2.2.2.6.1 |  | Geomembrane | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 6 | 1 | 1 | 0 | 2.2.6.1.1 |  | Purchase Material Requisition (PMR)
2 | 2 | 2 | 6 | 1 | 1 | 1 | 2.2.2.6.1.1.1 | BK-W018S-PEDCO-110-CV-MR-0001 | PMR For Geomembrane - W018S |  | BK-W018S-PEDCO-110-CV-MR-0001 | BK-W018S-PEDCO-110-CV-MR-0001 | BK | W018S | PEDCO | 110 | CV | MR | 0001 | F0Z-707506 | IFI | IFI | 2022-04-17 | 2022-04-07 | 2022-04-10 | -10 | 3 | -7 | IFI | 2022-06-21 | 2022-06-12 | 2022-06-22 | -9 | 10 | 1 | IFI | 2022-07-06 | 2022-06-29 | 2022-07-05 | -7 | 6 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-03 |  |  | D02 | IFI | T-1106 | 44734 | 1401/04/01 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04916 | 44741 | 1401/04/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-123172 | 44741 | 1401/04/08 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0768 | 2022-04-03 | 1401/01/14 |  |  |  | BK-SUR-ENG-CIV-01-03846 | 44662 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-13822 | 2022-04-07 | 1401/01/18 | 44661 | 1401/01/21 | CM | [10 empty] | D01 | IFI | T-1044 | 44719 | 1401/03/17 | [7 empty] | PEDCO-CRS-BK-W018S-PEDCO-110-CV-MR-0001_D00 | [5 empty] | 1401-2294-98951 | 44724 | 1401/03/22 | 44734 | 1401/04/01 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-MR-0001_D00 | [9 empty] | D02 | IFI | T-1106 | 44734 | 1401/04/01 |  |  |  | BK-SUR-ENG-CIV-01-04916 | 44741 | 1401/04/08 | AP | [6 empty] | 1401-2294-123172 | 44741 | 1401/04/08 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-MR-0001_D01
2 | 2 | 2 | 6 | 1 | 2 | 0 | 2.2.6.1.2 |  | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 6 | 1 | 2 | 1 | 2.2.2.6.1.2.1 | BK-W018S-PEDCO-110-CV-TB-0001 | TBE For Geomembrane - W018S |  | BK-W018S-PEDCO-110-CV-TB-0001 | BK-W018S-PEDCO-110-CV-TB-0001 | BK | W018S | PEDCO | 110 | CV | TB | 0001 | F0Z-707507 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 2 | 6 | 2 | 0 | 0 | 2.2.2.6.2 |  | Geotextile | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 6 | 2 | 1 | 0 | 2.2.6.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 6 | 2 | 1 | 1 | 2.2.2.6.2.1.1 | BK-W018S-PEDCO-110-CV-MR-0002 | PMR For Geotextile - W018S |  | BK-W018S-PEDCO-110-CV-MR-0002 | BK-W018S-PEDCO-110-CV-MR-0002 | BK | W018S | PEDCO | 110 | CV | MR | 0002 | F0Z-707508 | IFI | IFI | 2022-04-17 | 2022-04-07 | 2022-04-10 | -10 | 3 | -7 | IFI | 2022-06-21 | 2022-06-12 | 2022-06-14 | -9 | 2 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-03 |  |  | D01 | IFI | T-1044 | 44719 | 1401/03/17 | T-1044 | 44719 | 1401/03/17 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-98951 | 44724 | 1401/03/22 | 44726 | 1401/03/24 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0768 | 2022-04-03 | 1401/01/14 |  |  |  | BK-SUR-ENG-CIV-01-03846 | 44662 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-13822 | 2022-04-07 | 1401/01/18 | 44661 | 1401/01/21 | CM | [10 empty] | D01 | IFI | T-1044 | 44719 | 1401/03/17 | T-1044 | 44719 | 1401/03/17 |  |  |  |  | PEDCO-CRS-BK-W018S-PEDCO-110-CV-MR-0002_D00 | [5 empty] | 1401-2294-98951 | 44724 | 1401/03/22 | 44726 | 1401/03/24 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-MR-0002_D00
2 | 2 | 2 | 6 | 2 | 2 | 0 | 2.2.6.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 2 | 6 | 2 | 2 | 1 | 2.2.2.6.2.2.1 | BK-W018S-PEDCO-110-CV-TB-0002 | TBE For Geotextile - W018S |  | BK-W018S-PEDCO-110-CV-TB-0002 | BK-W018S-PEDCO-110-CV-TB-0002 | BK | W018S | PEDCO | 110 | CV | TB | 0002 | F0Z-707509 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 2 | 3 | 0 | 0 | 0 | 0 | 2.2.3 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 3 | 0 | 0 | 1 | 0 | 2.2.3.1 |  | Procedure/Plan
2 | 2 | 3 | 0 | 0 | 1 | 1 | 2.2.3.1.1 | BK-W018S-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - W018S |  | BK-W018S-PEDCO-110-CO-PR-0001 | BK-W018S-PEDCO-110-CO-PR-0001 | BK | W018S | PEDCO | 110 | CO | PR | 0001 | F0Z-707510 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 4 | 0 | 0 | 0 | 0 | 2.2.4 |  | Field Engineering
2 | 2 | 4 | 0 | 0 | 1 | 0 | 2.2.4.1 |  | Query
2 | 2 | 4 | 0 | 0 | 1 | 1 | 2.2.4.1.1 | BK-W018S-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-W018S-PEDCO-110-GE-TQ-0001 | BK-W018S-PEDCO-110-GE-TQ-0001 | BK | W018S | PEDCO | 110 | GE | TQ | 0001 | F7Z-707511 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 4 | 0 | 0 | 2 | 0 | 2.2.4.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 4 | 0 | 0 | 2 | 1 | 2.2.4.2.1 | BK-W018S-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W018S |  | BK-W018S-PEDCO-110-GE-DO-0001 | BK-W018S-PEDCO-110-GE-DO-0001 | BK | W018S | PEDCO | 110 | GE | DO | 0001 | F0Z-707512 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 5 | 0 | 0 | 0 | 0 | 2.2.5 |  | Engineering Final Documentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 5 | 0 | 0 | 1 | 0 | 2.2.5.1 |  | Manual
2 | 2 | 5 | 0 | 0 | 1 | 1 | 2.2.5.1.1 | BK-W018S-PEDCO-110-GE-ML-0001 | Operating Manual - W018S |  | BK-W018S-PEDCO-110-GE-ML-0001 | BK-W018S-PEDCO-110-GE-ML-0001 | BK | W018S | PEDCO | 110 | GE | ML | 0001 | F7Z-707513 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 2 | 5 | 0 | 0 | 2 | 0 | 2.2.5.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 2 | 5 | 0 | 0 | 2 | 1 | 2.2.5.2.1 | BK-W018S-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W018S |  | BK-W018S-PEDCO-110-GE-DO-0001 | [8 empty] | F0Z-707512 | AB-A | [50 empty] | 0
2 | 2 | 5 | 0 | 0 | 2 | 2 | 2.2.5.2.2 | BK-W018S-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - W018S |  | BK-W018S-PEDCO-110-GE-DO-0002 | BK-W018S-PEDCO-110-GE-DO-0002 | BK | W018S | PEDCO | 110 | GE | DO | 0002 | F0Z-707514 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 3 | 0 | 0 | 0 | 0 | 0 | 2.3 |  | Package 02-New Well # W028 (Bangestan) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 0 | 0 | 0 | 0 | 2.3.1 |  | Detail Design
2 | 3 | 1 | 1 | 0 | 0 | 0 | 2.3.1.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 1 | 1 | 0 | 0 | 2.3.1.1.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 1 | 1 | 0 | 1 | 2.3.1.1.1 | BK-W028-PEDCO-110-PR-PF-0001 | Process Flow Diagram - W028 |  | BK-W028-PEDCO-110-PR-PF-0001 | BK-W028-PEDCO-110-PR-PF-0001 | BK | W028 | PEDCO | 110 | PR | PF | 0001 | F2A-707515 | AFC | IFC | 2021-08-28 | 2021-08-30 | 2021-09-06 | 2 | 7 | 9 | IFC | 2021-11-16 | 2022-06-02 | 2022-06-06 | 198 | 4 | 202 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-02 |  |  | D02 | IFA | T-1266 | 44783 | 1401/05/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W028-PEDCO-110-PR-PF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0046 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-PCS-00-01394 | 44432 | 1400/06/02 | CM-C3 | [6 empty] | 1400/2294/179413 | 2021-08-30 | 1400/06/08 | 44445 | 1400/06/15 | RJ | [10 empty] | D01 | IFC | T-0205 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-PCS-00-02020 | 44516 | 1400/08/25 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PF-0001_D00 | [5 empty] | 1401-2294-87488 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-PF-0001_D00 | [9 empty] | D02 | IFA | T-1266 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PF-0001_D01 | [5 empty] | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W028-PEDCO-110-PR-PF-0001_D01
2 | 3 | 1 | 1 | 1 | 0 | 2 | 2.3.1.1.1 | BK-W028-PEDCO-110-PR-PI-0001 | P&ID - W028 |  | BK-W028-PEDCO-110-PR-PI-0001 | BK-W028-PEDCO-110-PR-PI-0001 | BK | W028 | PEDCO | 110 | PR | PI | 0001 | F2A-707516 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | IFA | 2022-09-20 | 2022-11-19 | 2022-11-21 | 60 | 2 | 62 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-01 |  |  | D04 | IFA | T-1368 | 44810 | 1401/06/15 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 44447 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0201 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 44516 | 1400/08/25 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 44564 | 1400/10/13 | CM-C3 | PEDCO-BK-W028-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 44560 | 1400/10/09 | 44564 | 1400/10/13 | RJ | NISOC-BK-W028-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-PI-0001_D02 | [9 empty] | D04 | IFA | T-1368 | 44810 | 1401/06/15 |  |  |  | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PI-0001_D03 | [5 empty] | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-PI-0001_D03
2 | 3 | 1 | 1 | 2 | 0 | 0 | 2.3.1.1.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 1 | 2 | 0 | 1 | 2.3.1.1.2 | BK-W028-PEDCO-110-PR-LI-0001 | Line List - W028 |  | BK-W028-PEDCO-110-PR-LI-0001 | BK-W028-PEDCO-110-PR-LI-0001 | BK | W028 | PEDCO | 110 | PR | LI | 0001 | F0Z-707517 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-22 | 2021-11-27 | 2021-11-29 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-06-27 | 0 | 166 | -44739 | -44573 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-08 |  |  | D02 | IFA | T-0403 | 44559 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 44447 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0217 | 44508 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 44520 | 1400/08/29 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 44527 | 1400/09/06 | 44529 | 1400/09/08 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-LI-0001_D01 | [5 empty] | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-LI-0001_D01
2 | 3 | 1 | 1 | 3 | 0 | 0 | 2.3.1.1.3 |  | Report | [142 empty] | 44520 | 1400/08/29
2 | 3 | 1 | 1 | 3 | 0 | 1 | 2.3.1.1.3 | BK-W028-PEDCO-110-PR-RT-0001 | Flow line Hydraulic Calculation Report |  | BK-W028-PEDCO-110-PR-RT-0001 | BK-W028-PEDCO-110-PR-RT-0001 | BK | W028 | PEDCO | 110 | PR | RT | 0001 | F0Z-707518 | IFA | IFC | 2021-11-13 | 2021-11-14 | 2021-11-17 | 1 | 3 | 4 | IFA | 2022-01-15 | 2021-02-01 | 2022-02-05 | -348 | 369 | 21 | IFA | 2022-03-08 | 2022-03-10 | 2022-03-13 | 2 | 3 | 5 | IFA | 2022-05-14 | 2022-06-02 | 2022-06-06 | 19 | 4 | 23 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | AFC | 2022-10-22 | 2022-11-19 | 2022-11-20 | 28 | 1 | 29 | [8 empty] | 2021-10-30 | 2022-10-08 |  | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 44514 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 44517 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 44562 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 44228 | 1400/11/12 | 44597 | 1400/11/16 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 44614 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 44627 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 44630 | 1400/12/19 | 44633 | 1400/12/22 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 44681 | 1401/02/10 | T-0878 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 44709 | 1401/03/07 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PR-RT-0001_D02 | [5 empty] | 1401-2294-87489 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-RT-0001_D02 | [9 empty] | D04 | IFA | T-1267 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05524 | 44797 | 1401/06/02 | AP | [6 empty] | 1401-2294-235783 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W028-PEDCO-110-PR-RT-0001_D03 | [9 empty] | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | [10 empty] | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP
2 | 3 | 1 | 1 | 4 | 0 | 0 | 2.3.1.1.4 |  | Data Sheet | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 1 | 4 | 0 | 1 | 2.3.1.1 | BK-W028-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - W028 |  | BK-W028-PEDCO-110-PR-DT-0001 | BK-W028-PEDCO-110-PR-DT-0001 | BK | W028 | PEDCO | 110 | PR | DT | 0001 | F0Z-707519 | AFC | IFC | 2022-04-26 | 2022-05-08 | 2022-05-14 | 12 | 6 | 18 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-12 |  |  | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 44695 | 1401/02/24 | CM | [10 empty] | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-DT-0001_D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PR-DT-0001_D00
2 | 3 | 1 | 2 | 0 | 0 | 0 | 2.3.1.2 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 2 | 1 | 0 | 0 | 2.3.1.2.1 |  | Drawing/Diagram
2 | 3 | 1 | 2 | 1 | 0 | 1 | 2.3.1.2.1 | BK-W028-PEDCO-110-PI-DW-0001 | Plot Plan Drawing - W028 |  | BK-W028-PEDCO-110-PI-DW-0001 | BK-W028-PEDCO-110-PI-DW-0001 | BK | W028 | PEDCO | 110 | PI | DW | 0001 | F5A-707520 | AFC | IFC | 2022-02-16 | 2022-04-16 | 2022-04-25 | 59 | 9 | 68 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-02 |  |  | D00 | IFC | T-0533 | 44594 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03123 | 44611 | 1400/11/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-25043 | 44667 | 1401/01/27 | 44676 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0533 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-PIP-00-03123 | 44611 | 1400/11/30 | CM-C2 | [6 empty] | 1401-2294-25043 | 2022-04-16 | 1401/01/27 | 44676 | 1401/02/05 | CM
2 | 3 | 1 | 2 | 1 | 0 | 2 | 2.3.1.2.1 | BK-W028-PEDCO-110-PI-DW-0002 | Piping Plan - W028 |  | BK-W028-PEDCO-110-PI-DW-0002 | BK-W028-PEDCO-110-PI-DW-0002 | BK | W028 | PEDCO | 110 | PI | DW | 0002 | F4L-707521 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 1 | 2 | 1 | 0 | 3 | 2.3.1.2.1 | BK-W028-PEDCO-110-PI-DW-0003 | Isometric Drawings - W028 |  | BK-W028-PEDCO-110-PI-DW-0003 | BK-W028-PEDCO-110-PI-DW-0003 | BK | W028 | PEDCO | 110 | PI | DW | 0003 | F2L-707522 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 1 | 2 | 1 | 0 | 4 | 2.3.1.2.1 | BK-W028-PEDCO-110-PI-DG-0001 | Material Flow Diagram - W028 |  | BK-W028-PEDCO-110-PI-DG-0001 | BK-W028-PEDCO-110-PI-DG-0001 | BK | W028 | PEDCO | 110 | PI | DG | 0001 | F2A-707523 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 2022-06-28 | 2022-07-05 | 34 | 7 | 41 | IFA | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-08 |  |  | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 44521 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PI-DG-0001_D00 | [5 empty] | 1401-2294-122170 | 44740 | 1401/04/07 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W028-PEDCO-110-PI-DG-0001_D00 | [9 empty] | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-DG-0001_D01 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PI-DG-0001_D01
2 | 3 | 1 | 2 | 2 | 0 | 0 | 2.3.1.2.2 |  | List
2 | 3 | 1 | 2 | 2 | 0 | 1 | 2.3.1.2.2 | BK-W028-PEDCO-110-PI-LI-0001 | Piping Support List - W028 |  | BK-W028-PEDCO-110-PI-LI-0001 | BK-W028-PEDCO-110-PI-LI-0001 | BK | W028 | PEDCO | 110 | PI | LI | 0001 | F0Z-707524 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 3 | 1 | 2 | 2 | 0 | 2 | 2.3.1.2.2 | BK-W028-PEDCO-110-PI-LI-0002 | Critical Line List - W028 |  | BK-W028-PEDCO-110-PI-LI-0002 | BK-W028-PEDCO-110-PI-LI-0002 | BK | W028 | PEDCO | 110 | PI | LI | 0002 | F0Z-707525 | AFC | IFC | 2022-05-16 | 2022-06-08 | 2022-06-08 | 23 | 0 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-02 |  |  | D00 | IFC | T-0899 | 44683 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04153 | 44627 | 1401/02/17 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94251 | 44720 | 1401/03/18 | 44720 | 1401/03/18 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0899 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-PIP-01-04153 | 44627 | 1401/02/17 | RJ-C4 | [6 empty] | 1401-2294-94251 | 2022-06-08 | 1401/03/18 | 44720 | 1401/03/18 | CM
2 | 3 | 1 | 2 | 3 | 0 | 0 | 2.3.1.2.3 |  | Report
2 | 3 | 1 | 2 | 3 | 0 | 1 | 2.3.1.2.3 | BK-W028-PEDCO-110-PI-RT-0001 | PDMS Model Review Report (60%) - W028 |  | BK-W028-PEDCO-110-PI-RT-0001 | BK-W028-PEDCO-110-PI-RT-0001 | BK | W028 | PEDCO | 110 | PI | RT | 0001 | F0Z-707526 | IFI | IFC | 2022-07-17 | 2022-07-27 | 2022-07-31 | 10 | 4 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-07-03 |  |  | D00 | IFC | T-1134 | 44745 | 1401/04/12 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05140 | 44758 | 1401/04/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156849 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1134 | 2022-07-03 | 1401/04/12 |  |  |  | BK-SUR-ENG-PIP-01-05140 | 44758 | 1401/04/25 | CM-C2 | [6 empty] | 1401-2294-156849 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | AP
2 | 3 | 1 | 2 | 3 | 0 | 2 | 2.3.1.2.3 | BK-W028-PEDCO-110-PI-RT-0002 | PDMS Model Review Report (90%) - W028 |  | BK-W028-PEDCO-110-PI-RT-0002 | BK-W028-PEDCO-110-PI-RT-0002 | BK | W028 | PEDCO | 110 | PI | RT | 0002 | F0Z-707527 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 3 | 1 | 2 | 4 | 0 | 0 | 2.3.1.2.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 2 | 4 | 0 | 1 | 2.3.1.2 | BK-W028-PEDCO-110-PI-MT-0001 | MTO For Pipes - W028 |  | BK-W028-PEDCO-110-PI-MT-0001 | BK-W028-PEDCO-110-PI-MT-0001 | BK | W028 | PEDCO | 110 | PI | MT | 0001 | F8Z-707528 | IFI | IFI | 2021-12-18 | 2021-12-13 | 2021-12-15 | -5 | 2 | -3 | IFI | 2022-05-01 | 2022-04-28 | 2022-05-02 | -3 | 4 | 1 | IFI | 2022-09-19 | 2022-09-19 | 2022-09-21 | 0 | 2 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-04 |  |  | D02 | IFI | T-1360 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05705 | 44818 | 1401/06/23 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-229868 | 44823 | 1401/06/28 | 44825 | 1401/06/30 | CM | NISOC-CRS-BK-W028-PEDCO-110-PI-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0290 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PIP-00-02319 | 44545 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-316961 | 2021-12-13 | 1400/09/22 | 44545 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0829 | 44668 | 1401/01/28 |  |  |  | BK-SUR-ENG-PIP-01-04062 | 44677 | 1401/02/07 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-MT-0001_D00 | [5 empty] | 1401-2294-42948 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-W028-PEDCO-110-PI-MT-0001_D00 | [9 empty] | D02 | IFI | T-1360 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-PIP-01-05705 | 44818 | 1401/06/23 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MT-0001_D01 | [5 empty] | 1401-2294-229868 | 44823 | 1401/06/28 | 44825 | 1401/06/30 | CM | NISOC-CRS-BK-W028-PEDCO-110-PI-MT-0001_D01
2 | 3 | 1 | 2 | 4 | 0 | 2 | 2.3.1.2 | BK-W028-PEDCO-110-PI-MT-0002 | MTO For Fittings - W028 |  | BK-W028-PEDCO-110-PI-MT-0002 | BK-W028-PEDCO-110-PI-MT-0002 | BK | W028 | PEDCO | 110 | PI | MT | 0002 | F8Z-707529 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-10 | 2022-10-12 | 22 | 2 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-20 |  |  | D02 | IFI | T-1352 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 44657 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D00 | [5 empty] | 1401-2294-42946 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D00 | [9 empty] | D02 | IFI | T-1352 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D01 | [5 empty] | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D01
2 | 3 | 1 | 2 | 4 | 0 | 3 | 2.3.1.2 | BK-W028-PEDCO-110-PI-MT-0003 | MTO For Flanges - W028 |  | BK-W028-PEDCO-110-PI-MT-0003 | BK-W028-PEDCO-110-PI-MT-0003 | BK | W028 | PEDCO | 110 | PI | MT | 0003 | F8Z-707530 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-10 | 2022-10-12 | 22 | 2 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-20 |  |  | D02 | IFI | T-1352 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 44657 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D00 | [5 empty] | 1401-2294-42946 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D00 | [9 empty] | D02 | IFI | T-1352 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D01 | [5 empty] | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D01
2 | 3 | 1 | 2 | 4 | 0 | 4 | 2.3.1.2 | BK-W028-PEDCO-110-PI-MT-0004 | MTO For Manual Valves - W028 |  | BK-W028-PEDCO-110-PI-MT-0004 | BK-W028-PEDCO-110-PI-MT-0004 | BK | W028 | PEDCO | 110 | PI | MT | 0004 | F8Z-707531 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-10 | 2022-10-12 | 22 | 2 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-20 |  |  | D02 | IFI | T-1352 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 44657 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D00 | [5 empty] | 1401-2294-42946 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D00 | [9 empty] | D02 | IFI | T-1352 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D01 | [5 empty] | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D01
2 | 3 | 1 | 2 | 4 | 0 | 5 | 2.3.1.2 | BK-W028-PEDCO-110-PI-MT-0005 | MTO For Gaskets - W028 |  | BK-W028-PEDCO-110-PI-MT-0005 | BK-W028-PEDCO-110-PI-MT-0005 | BK | W028 | PEDCO | 110 | PI | MT | 0005 | F8Z-707532 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-10 | 2022-10-12 | 22 | 2 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-20 |  |  | D02 | IFI | T-1352 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 44657 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D00 | [5 empty] | 1401-2294-42946 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D00 | [9 empty] | D02 | IFI | T-1352 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D01 | [5 empty] | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D01
2 | 3 | 1 | 2 | 4 | 0 | 6 | 2.3.1.2 | BK-W028-PEDCO-110-PI-MT-0006 | MTO For Bolt & Nuts - W028 |  | BK-W028-PEDCO-110-PI-MT-0006 | BK-W028-PEDCO-110-PI-MT-0006 | BK | W028 | PEDCO | 110 | PI | MT | 0006 | F8Z-707533 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-10 | 2022-10-12 | 22 | 2 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-20 |  |  | D02 | IFI | T-1352 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 44559 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 44657 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D00 | [5 empty] | 1401-2294-42946 | 44679 | 1401/02/08 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D00 | [9 empty] | D02 | IFI | T-1352 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D01 | [5 empty] | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D01
2 | 3 | 1 | 3 | 0 | 0 | 0 | 2.3.1.3 |  | Pipeline & Flow line
2 | 3 | 1 | 3 | 1 | 0 | 0 | 2.3.1.3.1 |  | Drawings
2 | 3 | 1 | 3 | 1 | 0 | 1 | 2.3.1.3.1 | BK-W028-PEDCO-110-PL-DW-0002 | Flow line Transversal Drawings - W028 |  | BK-W028-PEDCO-110-PL-DW-0002 | BK-W028-PEDCO-110-PL-DW-0002 | BK | W028 | PEDCO | 110 | PL | DW | 0002 | F4A-707534 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 3 | 1 | 3 | 2 | 0 | 0 | 2.3.1.3.2 |  | List
2 | 3 | 1 | 3 | 2 | 0 | 1 | 2.3.1.3.2 | BK-W028-PEDCO-110-PL-LI-0001 | Road Crossing Location List |  | BK-W028-PEDCO-110-PL-LI-0001 | BK-W028-PEDCO-110-PL-LI-0001 | BK | W028 | PEDCO | 110 | PL | LI | 0001 | F0Z-707535 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 1 | 3 | 3 | 0 | 0 | 2.3.1.3.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 3 | 3 | 0 | 1 | 2.3.1.3 | BK-W028-PEDCO-110-PL-MT-0001 | MTO For Line Pipes (Flow lines) - W028 |  | BK-W028-PEDCO-110-PL-MT-0001 | BK-W028-PEDCO-110-PL-MT-0001 | BK | W028 | PEDCO | 110 | PL | MT | 0001 | F8Z-707536 | IFI | IFI | 2021-09-05 | 2021-08-30 | 2021-09-05 | -6 | 6 | 0 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W028-PEDCO-110-PL-MT-0001-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-PL-MT-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 44430 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 |  |  |  |  | PEDCO-CRS-BK-W028-PEDCO-110-PL-MT-0001-D00 | [5 empty] | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-PL-MT-0001-D00
2 | 3 | 1 | 4 | 0 | 0 | 0 | 2.3.1.4 |  | Control & Instrumentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 4 | 1 | 0 | 0 | 2.3.1.4.1 |  | Drawing/Diagram
2 | 3 | 1 | 4 | 1 | 0 | 1 | 2.3.1.4.1 | BK-W028-PEDCO-110-IN-PY-0001 | Instrument Location Layout Drawing - W028 |  | BK-W028-PEDCO-110-IN-PY-0001 | BK-W028-PEDCO-110-IN-PY-0001 | BK | W028 | PEDCO | 110 | IN | PY | 0001 | F2J-707537 | AFC | IFC | 2022-05-30 | 2022-08-03 | 2022-08-06 | 65 | 3 | 68 | IFA | 2022-10-04 | 2022-10-30 | 2022-11-01 | 26 | 2 | 28 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-16 |  |  | D01 | IFA | T-1425 | 44824 | 1401/06/29 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05864 | 44843 | 1401/07/17 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-286156 | 44864 | 1401/08/08 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0958 | 2022-05-16 | 1401/02/26 | T-0958 | 44697 | 1401/02/26 | BK-SUR-ENG-INS-01-04488 | 44710 | 1401/03/09 | CM-C2 | [6 empty] | 1401-2294-165334 | 2022-08-03 | 1401/05/12 | 44779 | 1401/05/15 | CM | [10 empty] | D01 | IFA | T-1425 | 44824 | 1401/06/29 |  |  |  | BK-SUR-ENG-INS-01-05864 | 44843 | 1401/07/17 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-PY-0001_D00 | [5 empty] | 1401-2294-286156 | 44864 | 1401/08/08 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-PY-0001_D00
2 | 3 | 1 | 4 | 2 | 0 | 0 | 2.3.1.4.2 |  | MTO
2 | 3 | 1 | 4 | 2 | 0 | 1 | 2.3.1.4 | BK-W028-PEDCO-110-IN-MT-0001 | MTO For Instrument Tube and Fitting - W028 |  | BK-W028-PEDCO-110-IN-MT-0001 | BK-W028-PEDCO-110-IN-MT-0001 | BK | W028 | PEDCO | 110 | IN | MT | 0001 | F8Z-707538 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-14 |  |  | D02 | IFI | T-0451 | 44573 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0238 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02142 | 44528 | 1400/09/08 | RJ-C4 | [6 empty] | 1400-2294-283472 | 2021-11-21 | 1400/08/30 | 44529 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 44548 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 44562 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0001_D00 | [5 empty] | 1400-2294-347953 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0001_D00 | [9 empty] | D02 | IFI | T-0451 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0001_D01 | [5 empty] | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0001_D01
2 | 3 | 1 | 4 | 2 | 0 | 2 | 2.3.1.4 | BK-W028-PEDCO-110-IN-MT-0002 | MTO For Instrument Cable Tray - W028 |  | BK-W028-PEDCO-110-IN-MT-0002 | BK-W028-PEDCO-110-IN-MT-0002 | BK | W028 | PEDCO | 110 | IN | MT | 0002 | F8Z-707539 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-14 |  |  | D02 | IFI | T-0451 | 44573 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0238 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02142 | 44528 | 1400/09/08 | RJ-C4 | [6 empty] | 1400-2294-283472 | 2021-11-21 | 1400/08/30 | 44529 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 44548 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 44562 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0002_D00 | [5 empty] | 1400-2294-347953 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0002_D00 | [9 empty] | D02 | IFI | T-0451 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0002_D01 | [5 empty] | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0002_D01
2 | 3 | 1 | 5 | 0 | 0 | 0 | 2.3.1.5 |  | Safety
2 | 3 | 1 | 5 | 1 | 0 | 0 | 2.3.1.5.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 5 | 1 | 0 | 1 | 2.3.1.5.1 | BK-W028-PEDCO-110-SA-PY-0001 | Hazardous Area Classification Layout - W028 |  | BK-W028-PEDCO-110-SA-PY-0001 | BK-W028-PEDCO-110-SA-PY-0001 | BK | W028 | PEDCO | 110 | SA | PY | 0001 | F2L-707540 | AFC | IFC | 2022-05-21 | 2022-06-10 | 2022-06-20 | 20 | 10 | 30 | IFA | 2022-10-30 | 2022-11-03 | 2022-11-06 | 4 | 3 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-07 |  |  | D01 | IFA | T-1502 | 44850 | 1401/07/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294119 | 44868 | 1401/08/12 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-W028-PEDCO-110-SA-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0905 | 2022-05-07 | 1401/02/17 | T-0905 | 44688 | 1401/02/17 | [10 empty] | 1401-2294-94656 | 2022-06-10 | 1401/03/20 | 44732 | 1401/03/30 | CM | [10 empty] | D01 | IFA | T-1502 | 44850 | 1401/07/24 | [13 empty] | 1401-2294-294119 | 44868 | 1401/08/12 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-W028-PEDCO-110-SA-PY-0001_D00
2 | 3 | 1 | 5 | 1 | 0 | 2 | 2.3.1.5.1 | BK-W028-PEDCO-110-SA-PY-0002 | Safety & Fire Fighting Equipment Location Layout - W028 |  | BK-W028-PEDCO-110-SA-PY-0002 | BK-W028-PEDCO-110-SA-PY-0002 | BK | W028 | PEDCO | 110 | SA | PY | 0002 | F2L-707541 | AFC | IFC | 2022-04-30 | 2022-06-07 | 2022-06-11 | 38 | 4 | 42 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-16 |  |  | D00 | IFC | T-0820 | 44667 | 1401/01/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-92281 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0820 | 2022-04-16 | 1401/01/27 | [13 empty] | 1401-2294-92281 | 2022-06-07 | 1401/03/17 | 44723 | 1401/03/21 | AP
2 | 3 | 1 | 5 | 1 | 0 | 3 | 2.3.1.5.1 | BK-W028-PEDCO-110-SA-PY-0003 | Escape Route & Safety Sign Layout - W028 |  | BK-W028-PEDCO-110-SA-PY-0003 | BK-W028-PEDCO-110-SA-PY-0003 | BK | W028 | PEDCO | 110 | SA | PY | 0003 | F2L-707542 | AFC | IFC | 2022-05-01 | 2022-06-07 | 2022-06-11 | 37 | 4 | 41 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-17 |  |  | D00 | IFC | T-0826 | 44668 | 1401/01/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-92388 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0826 | 2022-04-17 | 1401/01/28 | [13 empty] | 1401-2294-92388 | 2022-06-07 | 1401/03/17 | 44723 | 1401/03/21 | CM
2 | 3 | 1 | 5 | 2 | 0 | 0 | 2.3.1.5.2 |  | List
2 | 3 | 1 | 5 | 2 | 0 | 1 | 2.3.1.5.2 | BK-W028-PEDCO-110-SA-LI-0001 | Hazard Source List - W028 |  | BK-W028-PEDCO-110-SA-LI-0001 | BK-W028-PEDCO-110-SA-LI-0001 | BK | W028 | PEDCO | 110 | SA | LI | 0001 | F0Z-707543 | AFC | IFC | 2021-11-23 | 2021-11-30 | 2021-12-06 | 7 | 6 | 13 | IFA | 2022-02-19 | 2022-02-26 | 2022-02-21 | 7 | -5 | 2 | IFA | 2022-04-26 | 2022-06-07 | 2022-06-11 | 42 | 4 | 46 | AFC | 2022-08-09 | 2022-09-01 | 2022-09-04 | 23 | 3 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-09 | 2022-07-26 |  | D03 | AFC | T-1197 | 44768 | 1401/05/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205788 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-W028-PEDCO-110-SA-LI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0551 | 44597 | 1400/11/16 | [13 empty] | 1400-2294-419389 | 44618 | 1400/12/02 | 44613 | 1400/12/02 | CM | NISOC-CRS-BK-W028-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0806 | 44663 | 1401/01/23 | [13 empty] | 1401-2294-92282 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-W028-PEDCO-110-SA-LI-0001_D01 | [9 empty] | D03 | AFC | T-1197 | 44768 | 1401/05/04 | [13 empty] | 1401-2294-205788 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-W028-PEDCO-110-SA-LI-0001_D02
2 | 3 | 1 | 5 | 3 | 0 | 0 | 2.3.1.5.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 5 | 3 | 0 | 1 | 2.3.1.5 | BK-W028-PEDCO-110-SA-MT-0001 | MTO For Fire Fighting & Safety Equipment - W028 |  | BK-W028-PEDCO-110-SA-MT-0001 | BK-W028-PEDCO-110-SA-MT-0001 | BK | W028 | PEDCO | 110 | SA | MT | 0001 | F8Z-707544 | IFI | IFI | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-08 |  |  | D00 | IFI | T-0316 | 44538 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 44550 | 1400/09/29 | 44552 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | AP
2 | 3 | 1 | 5 | 3 | 0 | 2 | 2.3.1.5 | BK-W028-PEDCO-110-SA-MT-0002 | MTO For Safety Sign - W028 |  | BK-W028-PEDCO-110-SA-MT-0002 | BK-W028-PEDCO-110-SA-MT-0002 | BK | W028 | PEDCO | 110 | SA | MT | 0002 | F8Z-707545 | IFI | IFI | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-08 |  |  | D00 | IFI | T-0316 | 44538 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 44550 | 1400/09/29 | 44552 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | AP
2 | 3 | 1 | 6 | 0 | 0 | 0 | 2.3.1.6 |  | Architecture
2 | 3 | 1 | 6 | 1 | 0 | 0 | 2.3.1.6.1 |  | Drawing/Diagram
2 | 3 | 1 | 6 | 1 | 0 | 1 | 2.3.1.6 | BK-W028-PEDCO-110-AR-DW-0001 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W028 |  | BK-W028-PEDCO-110-AR-DW-0001 | BK-W028-PEDCO-110-AR-DW-0001 | BK | W028 | PEDCO | 110 | AR | DW | 0001 | F4B-707546 | AFC | IFC | 2022-03-12 | 2022-03-05 | 2022-03-08 | -7 | 3 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-26 |  |  | D00 | IFC | T-0640 | 44618 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03400 | 44628 | 1400/12/17 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-435028 | 44625 | 1400/12/14 | 44628 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0640 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-ARC-00-03400 | 44628 | 1400/12/17 | CM-C2 | [6 empty] | 1400-2294-435028 | 2022-03-05 | 1400/12/14 | 44628 | 1400/12/17 | AP
2 | 3 | 1 | 7 | 0 | 0 | 0 | 2.3.1.7 |  | Civil
2 | 3 | 1 | 7 | 1 | 0 | 0 | 2.3.1.7.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 7 | 1 | 0 | 1 | 2.3.1.7.1 | BK-W028-PEDCO-110-CV-PY-0001 | General Civil Layout -W028 |  | BK-W028-PEDCO-110-CV-PY-0001 | BK-W028-PEDCO-110-CV-PY-0001 | BK | W028 | PEDCO | 110 | CV | PY | 0001 | F4A-707547 | AFC | IFC | 2021-11-02 | 2021-10-25 | 2021-11-22 | -8 | 28 | 20 | IFA | 2022-03-26 | 2022-03-15 | 2022-03-25 | -11 | 10 | -1 | IFA | 2022-06-15 | 2022-06-08 | 2022-06-11 | -7 | 3 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-10-19 |  |  | D02 | IFA | T-1033 | 44713 | 1401/03/11 | T-1033 | 44713 | 1401/03/11 | BK-SUR-ENG-CIV-01-04604 | 44720 | 1401/03/18 | AP | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-93083 | 44720 | 1401/03/18 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0175 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-CIV-00-01825 | 44492 | 1400/08/01 | CM-C2 | [6 empty] | 1400-2294-247863 | 2021-10-25 | 1400/08/03 | 44522 | 1400/09/01 | CM | [10 empty] | D01 | IFA | T-0718 | 44632 | 1400/12/21 |  |  |  | BK-SUR-ENG-CIV-00-03529 | 44633 | 1400/12/22 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0001_D00 | [5 empty] | 1400-2294-449851 | 44635 | 1400/12/24 | 44645 | 1401/01/08 | RJ | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0001_D00 | [9 empty] | D02 | IFA | T-1033 | 44713 | 1401/03/11 | T-1033 | 44713 | 1401/03/11 | BK-SUR-ENG-CIV-01-04604 | 44720 | 1401/03/18 | AP | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0001_D01 | [5 empty] | 1401-2294-93083 | 44720 | 1401/03/18 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0001_D01
2 | 3 | 1 | 7 | 1 | 0 | 2 | 2.3.1.7.1 | BK-W028-PEDCO-110-CV-PY-0002 | Civil and Structural drawings -W028 |  | BK-W028-PEDCO-110-CV-PY-0002 | BK-W028-PEDCO-110-CV-PY-0002 | BK | W028 | PEDCO | 110 | CV | PY | 0002 | F4S-707548 | AFC | IFC | 2021-11-02 | 0 | 0 | -44502 | 0 | -44502 | IFA | 2021-12-04 | 2021-11-29 | 2021-12-01 | -5 | 2 | -3 | IFA | 2022-03-28 | 2022-03-30 | 2022-04-03 | 2 | 4 | 6 | IFA | 2022-06-21 | 2022-06-14 | 2022-06-15 | -7 | 1 | -6 | IFA | 2022-07-02 | 2022-06-25 | 2022-06-29 | -7 | 4 | -3 | IFA | 2022-07-31 | 2022-07-28 | 2022-08-01 | -3 | 4 | 1 | [7 empty] | Modify | 2021-10-19 |  |  | D07 | IFA | T-1576 | 44871 | 1401/08/15 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-06168 | 44879 | 1401/08/23 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002-D06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002_D06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0175 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-CIV-00-01825 | 44492 | 1400/08/01 | CM-C2 | [22 empty] | D01 | IFA | T-0258 | 44520 | 1400/08/29 |  |  |  | BK-SUR-ENG-CIV-00-02096 | 44524 | 1400/09/03 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002-D00 | [5 empty] | 1400-2290-296830 | 44529 | 1400/09/08 | 44531 | 1400/09/10 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002-D01 | [9 empty] | D02 | IFA | T-0732 | 44634 | 1400/12/23 |  |  |  | BK-SUR-ENG-CIV-01-03695 | 44646 | 1401/01/09 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002-D02 | [5 empty] | 1401-2294-6027 | 44650 | 1401/01/10 | 44654 | 1401/01/14 | RJ | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002-D02 | [9 empty] | D03 | IFA | T-1046 | 44719 | 1401/03/17 | T-1046 | 44719 | 1401/03/17 | BK-SUR-ENG-CIV-01-04693 | 44725 | 1401/03/23 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002_D02 | [5 empty] | 1401-2294-101848 | 44726 | 1401/03/24 | 44727 | 1401/03/25 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002_D02 | [9 empty] | D04 | IFA | T-1085 | 44730 | 1401/03/28 |  |  |  | BK-SUR-ENG-CIV-01-04912 | 44740 | 1401/04/07 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002_D03 | [5 empty] | 1401-2294-116094 | 44737 | 1401/04/04 | 44741 | 1401/04/08 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002_D03 | [9 empty] | D05 | IFA | T-1165 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-CIV-01-05221 | 44766 | 1401/05/02 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002_D04 | [5 empty] | 1401-2294-156950 | 44770 | 1401/05/06 | 44774 | 1401/05/10 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002_D04 | [9 empty] | D06 | IFA | T-1331 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-CIV-01-05624 | 44815 | 1401/06/20 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002_D05 | [5 empty] | 1401-2290-258365 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002_D05 | [9 empty] | D07 | IFA | T-1576 | 44871 | 1401/08/15 |  |  |  | BK-SUR-ENG-CIV-01-06168 | 44879 | 1401/08/23 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002-D06 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002_D06
2 | 3 | 1 | 7 | 1 | 0 | 3 | 2.3.1.7.1 | BK-W028-PEDCO-110-CV-DW-0001 | Rough Grading Plans -W028 |  | BK-W028-PEDCO-110-CV-DW-0001 | BK-W028-PEDCO-110-CV-DW-0001 | BK | W028 | PEDCO | 110 | CV | DW | 0001 | F4S-707549 | AFC | IFC | 2021-10-25 | 2021-10-16 | 2021-10-18 | -9 | 2 | -7 | IFA | 2022-02-20 | 2022-02-19 | 2022-02-12 | -1 | -7 | -8 | IFA | 2022-03-28 | 2022-03-30 | 2022-04-03 | 2 | 4 | 6 | AFC | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-10-11 | 2022-04-10 |  | D03 | AFC | T-0796 | 44661 | 1401/01/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0149 | 2021-10-11 | 1400/07/19 |  |  |  | BK-SUR-ENG-CIV-00-01735 | 44482 | 1400/07/21 | CM-C2 | [6 empty] | 1400-2294-236267 | 2021-10-16 | 1400/07/24 | 44487 | 1400/07/26 | CM | [10 empty] | D01 | IFA | T-0556 | 44598 | 1400/11/17 |  |  |  | BK-SUR-ENG-CIV-00-02971 | 44599 | 1400/11/18 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-DW-0001_D00 | [5 empty] | 1400-2294-406550 | 44611 | 1400/11/30 | 44604 | 1400/11/23 | RJ | NISOC-CRS-BK-W028-PEDCO-110-CV-DW-0001_D00 | [9 empty] | D02 | IFA | T-0732 | 44634 | 1400/12/23 |  |  |  | BK-SUR-ENG-CIV-01-03695 | 44646 | 1401/01/09 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | [5 empty] | 1401-2294-6027 | 44650 | 1401/01/10 | 44654 | 1401/01/14 | AP | NISOC-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | [9 empty] | D03 | AFC | T-0796 | 44661 | 1401/01/21 | [7 empty] | PEDCO-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02
2 | 3 | 1 | 7 | 2 | 0 | 0 | 2.3.1.7.2 |  | Calculation
2 | 3 | 1 | 7 | 2 | 0 | 1 | 2.3.1.7.2 | BK-W028-PEDCO-110-CV-CN-0001 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W028 |  | BK-W028-PEDCO-110-CV-CN-0001 | BK-W028-PEDCO-110-CV-CN-0001 | BK | W028 | PEDCO | 110 | CV | CN | 0001 | F0Z-707550 | AFC | IFC | 2021-12-19 | 2021-12-12 | 2021-12-14 | -7 | 2 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-0292 | 44535 | 1400/09/14 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-02212 | 44536 | 1400/09/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-315094 | 44542 | 1400/09/21 | 44544 | 1400/09/23 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0292 | 2021-12-05 | 1400/09/14 |  |  |  | BK-SUR-ENG-STR-00-02212 | 44536 | 1400/09/15 | CM-C3 | [6 empty] | 1400-2294-315094 | 2021-12-12 | 1400/09/21 | 44544 | 1400/09/23 | RJ
2 | 3 | 1 | 7 | 3 | 0 | 0 | 2.3.1.7.3 |  | MTO
2 | 3 | 1 | 7 | 3 | 0 | 1 | 2.3.1.7 | BK-W028-PEDCO-110-CV-MT-0001 | MTO For Civil Works - W028 |  | BK-W028-PEDCO-110-CV-MT-0001 | BK-W028-PEDCO-110-CV-MT-0001 | BK | W028 | PEDCO | 110 | CV | MT | 0001 | F8Z-707551 | IFI | IFI | 2022-05-23 | 2022-05-12 | 2022-05-16 | -11 | 4 | -7 | IFI | 2022-08-09 | 2022-08-02 | 2022-08-09 | -7 | 7 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-09 |  |  | D01 | IFI | T-1205 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05347 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-163803 | 44775 | 1401/05/11 | 44782 | 1401/05/18 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0918 | 2022-05-09 | 1401/02/19 | T-0918 | 44690 | 1401/02/19 | BK-SUR-ENG-CIV-01-04328 | 44702 | 1401/02/31 | CM-C2 | [6 empty] | 1401-2294-59526 | 2022-05-12 | 1401/02/22 | 44697 | 1401/02/26 | CM | [10 empty] | D01 | IFI | T-1205 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-CIV-01-05347 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-MT-0001_D00 | [5 empty] | 1401-2294-163803 | 44775 | 1401/05/11 | 44782 | 1401/05/18 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-MT-0001_D00
2 | 3 | 1 | 8 | 0 | 0 | 0 | 2.3.1.8 |  | Structure
2 | 3 | 1 | 8 | 1 | 0 | 0 | 2.3.1.8.1 |  | Drawing/Diagram
2 | 3 | 1 | 8 | 1 | 0 | 1 | 2.3.1.8.1 | BK-W028-PEDCO-110-ST-DW-0002 | Platform Structure Drawing - W028 |  | BK-W028-PEDCO-110-ST-DW-0002 | BK-W028-PEDCO-110-ST-DW-0002 | BK | W028 | PEDCO | 110 | ST | DW | 0002 | F4M-707552 | AFC | IFC | 2022-07-05 | 2022-07-17 | 2022-07-20 | 12 | 3 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-21 |  |  | D00 | IFC | T-1103 | 44733 | 1401/03/31 | T-1103 | 44733 | 1401/03/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-144022 | 44759 | 1401/04/26 | 44762 | 1401/04/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1103 | 2022-06-21 | 1401/03/31 | T-1103 | 44733 | 1401/03/31 | [10 empty] | 1401-2294-144022 | 2022-07-17 | 1401/04/26 | 44762 | 1401/04/29 | CM
2 | 3 | 1 | 8 | 2 | 0 | 0 | 2.3.1.8.2 |  | MTO
2 | 3 | 1 | 8 | 2 | 0 | 1 | 2.3.1.8 | BK-W028-PEDCO-110-ST-MT-0001 | MTO For Structural Works - W028 |  | BK-W028-PEDCO-110-ST-MT-0001 | BK-W028-PEDCO-110-ST-MT-0001 | BK | W028 | PEDCO | 110 | ST | MT | 0001 | F8Z-707553 | IFI | IFI | 2022-05-16 | 2022-05-09 | 2022-05-21 | -7 | 12 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-02 |  |  | D00 | IFI | T-0896 | 44683 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-04427 | 44705 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54881 | 44690 | 1401/02/19 | 44702 | 1401/02/31 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0896 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-STR-01-04427 | 44705 | 1401/03/03 | AP | [6 empty] | 1401-2294-54881 | 2022-05-09 | 1401/02/19 | 44702 | 1401/02/31 | CM
2 | 3 | 1 | 9 | 0 | 0 | 0 | 2.3.1.9 |  | Survey (Topography) & Geotechnic/Geoelectric
2 | 3 | 1 | 9 | 1 | 0 | 0 | 2.3.1.9.1 |  | Geotechnic
2 | 3 | 1 | 9 | 1 | 1 | 0 | 2.3.9.1.1 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 9 | 1 | 1 | 1 | 2.3.1.9.1.1.1 | BK-W028-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - W028 |  | BK-W028-PEDCO-110-GT-RT-0001 | BK-W028-PEDCO-110-GT-RT-0001 | BK | W028 | PEDCO | 110 | GT | RT | 0001 | F0Z-707554 | IFI | IFC | 2022-05-31 | 2022-05-31 | 2022-06-06 | 0 | 6 | 6 | IFA | 2022-11-19 | 0 | 0 | -44884 | 0 | -44884 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-17 |  |  | D01 | IFA | T-1572 | 44870 | 1401/08/14 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-06081 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0963 | 2022-05-17 | 1401/02/27 | T-0963 | 44699 | 1401/02/28 | BK-SUR-ENG-CIV-01-04492 | 44712 | 1401/03/10 | CM-C3 | [6 empty] | 1401-2294-85269 | 2022-05-31 | 1401/03/10 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1572 | 44870 | 1401/08/14 |  |  |  | BK-SUR-ENG-CIV-01-06081 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-GT-RT-0001_D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-GT-RT-0001_D00
2 | 3 | 1 | 9 | 1 | 2 | 0 | 2.3.9.1.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 1 | 9 | 1 | 2 | 1 | 2.3.1.9.1.2.1 | BK-W028-PEDCO-110-SU-DW-0001 | Flow line Plan & Profile Drawings - W028 |  | BK-W028-PEDCO-110-SU-DW-0001 | BK-W028-PEDCO-110-SU-DW-0001 | BK | W028 | PEDCO | 110 | SU | DW | 0001 | F4A-707555 | AFC | IFC | 2022-09-03 | 2022-09-12 | 2022-09-13 | 9 | 1 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-20 |  |  | D00 | IFC | T-1291 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05577 | 44807 | 1401/06/12 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-220543 | 44816 | 1401/06/21 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1291 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-PPL-01-05577 | 44807 | 1401/06/12 | CM-C3 | [6 empty] | 1401-2294-220543 | 2022-09-12 | 1401/06/21 | 44817 | 1401/06/22 | CM
2 | 3 | 2 | 0 | 0 | 0 | 0 | 2.3.2 |  | Procurement Engineering
2 | 3 | 2 | 1 | 0 | 0 | 0 | 2.3.2.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 1 | 0 | 0 | 2.3.2.1.1 |  | Pipes
2 | 3 | 2 | 1 | 1 | 1 | 0 | 2.3.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 1 | 1 | 1 | 2.3.2.1.1.1.1 | BK-W028-PEDCO-110-PI-MR-0001 | PMR For Pipes - W028 |  | BK-W028-PEDCO-110-PI-MR-0001 | BK-W028-PEDCO-110-PI-MR-0001 | BK | W028 | PEDCO | 110 | PI | MR | 0001 | F0Z-707556 | IFI | IFI | 2021-12-20 | 2021-12-15 | 2021-12-15 | -5 | 0 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-06 |  |  | D00 | IFI | T-0298 | 44536 | 1400/09/15 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02320 | 44545 | 1400/09/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-315076 | 44542 | 1400/09/21 | 44545 | 1400/09/24 | AP | 0 | 1400-2294-316959 | 44545 | 1400/09/22 | 0 | 0 | CM | 0 | 0 |  | D00 | IFI | T-0298 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02320 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 44545 | 1400/09/24 | AP |  | 1400-2294-316959 | 44545 | 1400/09/22 |  |  | CM
2 | 3 | 2 | 1 | 1 | 2 | 0 | 2.3.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 1 | 2 | 1 | 2.3.2.1.1.2.1 | BK-W028-PEDCO-110-PI-TB-0001 | TBE For Pipes - W028 |  | BK-W028-PEDCO-110-PI-TB-0001 | BK-W028-PEDCO-110-PI-TB-0001 | BK | W028 | PEDCO | 110 | PI | TB | 0001 | F0Z-707557 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 3 | 2 | 1 | 2 | 0 | 0 | 2.3.2.1.2 |  | Fittings
2 | 3 | 2 | 1 | 2 | 1 | 0 | 2.3.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 2 | 1 | 1 | 2.3.2.1.2.1.1 | BK-W028-PEDCO-110-PI-MR-0002 | PMR For Fittings - W028 |  | BK-W028-PEDCO-110-PI-MR-0002 | BK-W028-PEDCO-110-PI-MR-0002 | BK | W028 | PEDCO | 110 | PI | MR | 0002 | F0Z-707558 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-10 | 2022-10-12 | 22 | 2 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-04 |  |  | D01 | IFI | T-1352 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1352 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0002_D00 | [5 empty] | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0002_D00
2 | 3 | 2 | 1 | 2 | 2 | 0 | 2.3.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 2 | 2 | 1 | 2.3.2.1.2.2.1 | BK-W028-PEDCO-110-PI-TB-0002 | TBE For Fitting - W028 |  | BK-W028-PEDCO-110-PI-TB-0002 | BK-W028-PEDCO-110-PI-TB-0002 | BK | W028 | PEDCO | 110 | PI | TB | 0002 | F0Z-707559 | IFI | IFI | 2022-09-03 | 2022-09-10 | 2022-09-13 | 7 | 3 | 10 | IFI | 2022-11-21 | 0 | 0 | -44886 | 0 | -44886 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-20 |  |  | D01 | IFI | T-1579 | 44872 | 1401/08/16 | T-1579 | 44872 | 1401/08/16 | BK-SUR-ENG-PIP-01-06210 | 44884 | 1401/08/28 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1287 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-PIP-01-05496 | 44795 | 1401/05/31 | RJ-C4 | [6 empty] | 1401-2294-218268 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/23 | CM | [10 empty] | D01 | IFI | T-1579 | 44872 | 1401/08/16 | T-1579 | 44872 | 1401/08/16 | BK-SUR-ENG-PIP-01-06210 | 44884 | 1401/08/28 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0002_D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0002_D00
2 | 3 | 2 | 1 | 3 | 0 | 0 | 2.3.2.1.3 |  | Flanges
2 | 3 | 2 | 1 | 3 | 1 | 0 | 2.3.1.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 3 | 1 | 1 | 2.3.2.1.3.1.1 | BK-W028-PEDCO-110-PI-MR-0003 | PMR For Flanges - W028 |  | BK-W028-PEDCO-110-PI-MR-0003 | BK-W028-PEDCO-110-PI-MR-0003 | BK | W028 | PEDCO | 110 | PI | MR | 0003 | F0Z-707560 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-10 | 2022-10-12 | 22 | 2 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-04 |  |  | D01 | IFI | T-1352 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1352 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0003_D00 | [5 empty] | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0003_D00
2 | 3 | 2 | 1 | 3 | 2 | 0 | 2.3.1.3.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 3 | 2 | 1 | 2.3.2.1.3.2.1 | BK-W028-PEDCO-110-PI-TB-0003 | TBE For Flanges - W028 |  | BK-W028-PEDCO-110-PI-TB-0003 | BK-W028-PEDCO-110-PI-TB-0003 | BK | W028 | PEDCO | 110 | PI | TB | 0003 | F0Z-707561 | IFI | IFI | 2022-02-27 | 2022-04-01 | 2022-03-05 | 33 | -27 | 6 | IFI | 2022-07-30 | 2022-08-09 | 2022-08-13 | 10 | 4 | 14 | IFI | 2022-10-17 | 0 | 0 | -44851 | 0 | -44851 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 |  |  | D02 | IFI | T-1454 | 44837 | 1401/07/11 | T-1454 | 44837 | 1401/07/11 | BK-SUR-ENG-PIP-01-05829 | 44838 | 1401/07/12 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 44625 | 1400/12/14 | RJ-C4 | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 44625 | 1400/12/14 | CM | [10 empty] | D01 | IFI | T-1164 | 44758 | 1401/04/25 |  |  |  | BK-SUR-ENG-PIP-01-05204 | 44762 | 1401/04/29 | C4-RJ | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0003_D00 | [5 empty] | 1401-2294-169863 | 44782 | 1401/05/18 | 44786 | 1401/05/22 | CM | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0003_D00 | [9 empty] | D02 | IFI | T-1454 | 44837 | 1401/07/11 | T-1454 | 44837 | 1401/07/11 | BK-SUR-ENG-PIP-01-05829 | 44838 | 1401/07/12 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0003_D01 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0003_D01
2 | 3 | 2 | 1 | 4 | 0 | 0 | 2.3.2.1.4 |  | Manual Valves
2 | 3 | 2 | 1 | 4 | 1 | 0 | 2.3.1.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 4 | 1 | 1 | 2.3.2.1.4.1.1 | BK-W028-PEDCO-110-PI-MR-0004 | PMR For Manual Valves - W028 |  | BK-W028-PEDCO-110-PI-MR-0004 | BK-W028-PEDCO-110-PI-MR-0004 | BK | W028 | PEDCO | 110 | PI | MR | 0004 | F0Z-707562 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-10 | 2022-10-12 | 22 | 2 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-04 |  |  | D01 | IFI | T-1352 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1352 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0004_D00 | [5 empty] | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0004_D00
2 | 3 | 2 | 1 | 4 | 2 | 0 | 2.3.1.4.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 4 | 2 | 1 | 2.3.2.1.4.2.1 | BK-W028-PEDCO-110-PI-TB-0004 | TBE For Manual Valves - W028 |  | BK-W028-PEDCO-110-PI-TB-0004 | BK-W028-PEDCO-110-PI-TB-0004 | BK | W028 | PEDCO | 110 | PI | TB | 0004 | F0Z-707563 | IFI | IFI | 2022-02-27 | 2022-04-01 | 2022-03-05 | 33 | -27 | 6 | IFI | 2022-11-02 | 2022-11-03 | 2022-11-06 | 1 | 3 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 |  |  | D01 | IFI | T-1516 | 44853 | 1401/07/27 | T-1516 | 44853 | 1401/07/27 | BK-SUR-ENG-PIP-01-05976 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294098 | 44868 | 1401/08/12 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 44625 | 1400/12/14 | RJ-C4 | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 44625 | 1400/12/14 | CM | [10 empty] | D01 | IFI | T-1516 | 44853 | 1401/07/27 | T-1516 | 44853 | 1401/07/27 | BK-SUR-ENG-PIP-01-05976 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0004_D00 | [5 empty] | 1401-2294-294098 | 44868 | 1401/08/12 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0004_D00
2 | 3 | 2 | 1 | 5 | 0 | 0 | 2.3.2.1.5 |  | Gaskets
2 | 3 | 2 | 1 | 5 | 1 | 0 | 2.3.1.5.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 5 | 1 | 1 | 2.3.2.1.5.1.1 | BK-W028-PEDCO-110-PI-MR-0005 | PMR For Gaskets - W028 |  | BK-W028-PEDCO-110-PI-MR-0005 | BK-W028-PEDCO-110-PI-MR-0005 | BK | W028 | PEDCO | 110 | PI | MR | 0005 | F0Z-707564 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-10-10 | 2022-10-12 | 22 | 2 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-04 |  |  | D01 | IFI | T-1352 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1352 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05622 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0005_D00 | [5 empty] | 1401-2294-256260 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0005_D00
2 | 3 | 2 | 1 | 5 | 2 | 0 | 2.3.1.5.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 5 | 2 | 1 | 2.3.2.1.5.2.1 | BK-W028-PEDCO-110-PI-TB-0005 | TBE For Gaskets - W028 |  | BK-W028-PEDCO-110-PI-TB-0005 | BK-W028-PEDCO-110-PI-TB-0005 | BK | W028 | PEDCO | 110 | PI | TB | 0005 | F0Z-707565 | IFI | IFI | 2022-02-27 | 2022-04-01 | 2022-03-05 | 33 | -27 | 6 | IFI | 2022-10-22 | 2022-10-29 | 2022-10-31 | 7 | 2 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-13 |  |  | D01 | IFI | T-1463 | 44842 | 1401/07/16 | T-1463 | 44842 | 1401/07/16 | BK-SUR-ENG-PIP-01-05897 | 44846 | 1401/07/20 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284130 | 44863 | 1401/08/07 | 44865 | 1401/08/09 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 44625 | 1400/12/14 | RJ-C4 | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 44625 | 1400/12/14 | CM | [10 empty] | D01 | IFI | T-1463 | 44842 | 1401/07/16 | T-1463 | 44842 | 1401/07/16 | BK-SUR-ENG-PIP-01-05897 | 44846 | 1401/07/20 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0005_D00 | [5 empty] | 1401-2294-284130 | 44863 | 1401/08/07 | 44865 | 1401/08/09 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0005_D00
2 | 3 | 2 | 1 | 6 | 0 | 0 | 2.3.2.1.6 |  | Bolt & Nuts | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 6 | 1 | 0 | 2.3.1.6.1 |  | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 6 | 1 | 1 | 2.3.2.1.6.1.1 | BK-W028-PEDCO-110-PI-MR-0006 | PMR For Bolt/Nuts - W028 |  | BK-W028-PEDCO-110-PI-MR-0006 | BK-W028-PEDCO-110-PI-MR-0006 | BK | W028 | PEDCO | 110 | PI | MR | 0006 | F0Z-707566 | IFI | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | IFI | 2022-09-18 | 2022-09-20 | 2022-09-24 | 2 | 4 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-04 |  |  | D01 | IFI | T-1353 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05617 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-231048 | 44824 | 1401/06/29 | 44828 | 1401/07/02 | CM | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 44683 | 1401/02/12 | RJ | [10 empty] | D01 | IFI | T-1353 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-PIP-01-05617 | 44814 | 1401/06/19 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0006_D01 | [5 empty] | 1401-2294-231048 | 44824 | 1401/06/29 | 44828 | 1401/07/02 | CM | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0006_D01
2 | 3 | 2 | 1 | 6 | 2 | 0 | 2.3.1.6.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 6 | 2 | 1 | 2.3.2.1.6.2.1 | BK-W028-PEDCO-110-PI-TB-0006 | TBE For Bolt/Nuts - W028 |  | BK-W028-PEDCO-110-PI-TB-0006 | BK-W028-PEDCO-110-PI-TB-0006 | BK | W028 | PEDCO | 110 | PI | TB | 0006 | F0Z-707567 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 1 | 7 | 0 | 0 | 2.3.2.1.7 |  | Sampling Connection | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 7 | 1 | 0 | 2.3.1.7.1 |  | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 7 | 1 | 1 | 2.3.2.1.7.1.1 | BK-W028-PEDCO-110-PI-MR-0007 | PMR For Sampling Connection Set - W028 |  | BK-W028-PEDCO-110-PI-MR-0007 | BK-W028-PEDCO-110-PI-MR-0007 | BK | W028 | PEDCO | 110 | PI | MR | 0007 | F0Z-707568 | IFI | IFI | 2022-03-06 | 2022-03-09 | 2022-03-07 | 3 | -2 | 1 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-23 |  |  | D01 | IFI | T-1532 | 44857 | 1401/08/01 | T-1532 | 44857 | 1401/08/01 | BK-SUR-ENG-PIP-01-06147 | 44874 | 1401/08/18 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296596 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0613 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PIP-00-03420 | 44628 | 1400/12/17 | CM-C2 | [6 empty] | 1400-2294-438859 | 2022-03-09 | 1400/12/18 | 44627 | 1400/12/16 | RJ | [10 empty] | D01 | IFI | T-1532 | 44857 | 1401/08/01 | T-1532 | 44857 | 1401/08/01 | BK-SUR-ENG-PIP-01-06147 | 44874 | 1401/08/18 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0007_D00 | [5 empty] | 1401-2294-296596 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-PI-MR-0007_D00
2 | 3 | 2 | 1 | 7 | 2 | 0 | 2.3.1.7.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 7 | 2 | 1 | 2.3.2.1.7.2.1 | BK-W028-PEDCO-110-PI-TB-0007 | TBE For Sampling Connection Set - W028 |  | BK-W028-PEDCO-110-PI-TB-0007 | BK-W028-PEDCO-110-PI-TB-0007 | BK | W028 | PEDCO | 110 | PI | TB | 0007 | F0Z-707569 | IFI | IFI | 2022-11-06 | 0 | 0 | -44871 | 0 | -44871 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-23 |  |  | D00 | IFI | T-1537 | 44857 | 1401/08/01 | T-1537 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1537 | 2022-10-23 | 1401/08/01 | T-1537 | 44857 | 1401/08/01
2 | 3 | 2 | 1 | 8 | 0 | 0 | 2.3.2.1.8 |  | Stone Trap
2 | 3 | 2 | 1 | 8 | 1 | 0 | 2.3.1.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 8 | 1 | 1 | 2.3.2.1.8.1.1 | BK-W028-PEDCO-110-PI-MR-0008 | PMR For Stone Trap - W028 |  | BK-W028-PEDCO-110-PI-MR-0008 | BK-W028-PEDCO-110-PI-MR-0008 | BK | W028 | PEDCO | 110 | PI | MR | 0008 | F0Z-707570 | IFI | IFI | 2022-05-11 | 2022-04-30 | 2022-05-14 | -11 | 14 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-27 |  |  | D00 | IFI | T-0869 | 44678 | 1401/02/07 | T-0869 | 44678 | 1401/02/07 | BK-SUR-ENG-PIP-01-04122 | 44683 | 1401/02/12 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45413 | 44681 | 1401/02/10 | 44695 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0869 | 2022-04-27 | 1401/02/07 | T-0869 | 44678 | 1401/02/07 | BK-SUR-ENG-PIP-01-04122 | 44683 | 1401/02/12 | CM-C2 | [6 empty] | 1401-2294-45413 | 2022-04-30 | 1401/02/10 | 44695 | 1401/02/24 | CM
2 | 3 | 2 | 1 | 8 | 2 | 0 | 2.3.1.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 8 | 2 | 1 | 2.3.2.1.8.2.1 | BK-W028-PEDCO-110-PI-TB-0008 | TBE For Stone Trap - W028 |  | BK-W028-PEDCO-110-PI-TB-0008 | BK-W028-PEDCO-110-PI-TB-0008 | BK | W028 | PEDCO | 110 | PI | TB | 0008 | F0Z-707571 | IFI | IFI | 2022-06-07 | 2022-06-14 | 2022-06-15 | 7 | 1 | 8 | IFI | 2022-11-15 | 0 | 0 | -44880 | 0 | -44880 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-24 |  |  | D01 | IFI | T-1569 | 44866 | 1401/08/10 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-06100 | 44871 | 1401/08/15 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03 | T-0996 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04515 | 44713 | 1401/03/11 | CM-C3 | [6 empty] | 1401-2294-102043 | 2022-06-14 | 1401/03/24 | 44727 | 1401/03/25 | CM | [10 empty] | D01 | IFI | T-1569 | 44866 | 1401/08/10 |  |  |  | BK-SUR-ENG-PIP-01-06100 | 44871 | 1401/08/15 | AP | PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0008_D01 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PI-TB-0008_D01
2 | 3 | 2 | 1 | 9 | 0 | 0 | 2.3.2.1.9 |  | Pipe Support
2 | 3 | 2 | 1 | 9 | 1 | 0 | 2.3.1.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 9 | 1 | 1 | 2.3.2.1.9.1.1 | BK-W028-PEDCO-110-PI-MR-0009 | PMR For Pipe Support - W028 |  | BK-W028-PEDCO-110-PI-MR-0009 | BK-W028-PEDCO-110-PI-MR-0009 | BK | W028 | PEDCO | 110 | PI | MR | 0009 | F0Z-707572 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 1 | 9 | 2 | 0 | 2.3.1.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 9 | 2 | 1 | 2.3.2.1.9.2.1 | BK-W028-PEDCO-110-PI-TB-0009 | TBE For Pipe Support - W028 |  | BK-W028-PEDCO-110-PI-TB-0009 | BK-W028-PEDCO-110-PI-TB-0009 | BK | W028 | PEDCO | 110 | PI | TB | 0009 | F0Z-707573 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 1 | 9 | 0 | 0 | 2.3.2.1.9 |  | BURN PIT PIPES
2 | 3 | 2 | 1 | 9 | 1 | 0 | 2.3.1.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 9 | 1 | 1 | 2.3.2.1.9.1.1 | BK-W028-PEDCO-110-PI-MR-0009 | PMR FOR BURN PIT PIPES– W028 |  | BK-W028-PEDCO-110-PI-MR-0011 | BK-W028-PEDCO-110-PI-MR-0009 | BK | W028 | PEDCO | 110 | PI | MR | 0009 | F0Z-707572 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [11 empty] | D00 | IFI | T-1550 | 44859 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1550 | 2022-10-25 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2
2 | 3 | 2 | 1 | 9 | 2 | 0 | 2.3.1.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 1 | 9 | 2 | 1 | 2.3.2.1.9.2.1 | BK-W028-PEDCO-110-PI-TB-0009 | TBE FOR BURN PIT PIPES– W028 |  | BK-W028-PEDCO-110-PI-TB-0011 | BK-W028-PEDCO-110-PI-TB-0009 | BK | W028 | PEDCO | 110 | PI | TB | 0009 | F0Z-707573 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14
2 | 3 | 2 | 2 | 0 | 0 | 0 | 2.3.2.2 |  | Pipeline
2 | 3 | 2 | 2 | 1 | 0 | 0 | 2.3.2.2.1 |  | Line Pipe | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 2 | 1 | 1 | 0 | 2.3.2.1.1 |  | Purchase Material Requisition (PMR)
2 | 3 | 2 | 2 | 1 | 1 | 1 | 2.3.2.2.1.1.1 | BK-W028-PEDCO-110-PL-MR-0001 | PMR For Line Pipes - W028 |  | BK-W028-PEDCO-110-PL-MR-0001 | BK-W028-PEDCO-110-PL-MR-0001 | BK | W028 | PEDCO | 110 | PL | MR | 0001 | F0Z-707574 | IFI | IFI | 2021-12-20 | 2021-12-13 | 2021-12-15 | -7 | 2 | -5 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-06 |  |  | D01 | IFI | T-1533 | 44857 | 1401/08/01 | T-1533 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W028-PEDCO-110-PL-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296597 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-PL-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0299 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PPL-00-02321 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-316957 | 2021-12-13 | 1400/09/22 | 44545 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-1533 | 44857 | 1401/08/01 | T-1533 | 44857 | 1401/08/01 |  |  |  |  | PEDCO-CRS-BK-W028-PEDCO-110-PL-MR-0001_D00 | [5 empty] | 1401-2294-296597 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-PL-MR-0001_D00
2 | 3 | 2 | 2 | 1 | 2 | 0 | 2.3.2.1.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 2 | 1 | 2 | 1 | 2.3.2.2.1.2.1 | BK-W028-PEDCO-110-PL-TB-0001 | TBE For Line Pipes - W028 |  | BK-W028-PEDCO-110-PL-TB-0001 | BK-W028-PEDCO-110-PL-TB-0001 | BK | W028 | PEDCO | 110 | PL | TB | 0001 | F0Z-707575 | IFI | IFI | 2022-03-05 | 2022-03-10 | 2022-03-14 | 5 | 4 | 9 | IFI | 2022-05-28 | 2022-05-31 | 2022-06-07 | 3 | 7 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W028-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 44628 | 1400/12/17 | RJ-C4 | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 44634 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PL-TB-0001-D00 | [5 empty] | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W028-PEDCO-110-PL-TB-0001-D00
2 | 3 | 2 | 2 | 2 | 0 | 0 | 2.3.2.2.2 |  | Flow Line Support
2 | 3 | 2 | 2 | 2 | 1 | 0 | 2.3.2.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 2 | 2 | 1 | 1 | 2.3.2.2.2.1.1 | BK-W028-PEDCO-110-PL-MR-0002 | PMR For Flow Line Support - W028 |  | BK-W028-PEDCO-110-PL-MR-0002 | BK-W028-PEDCO-110-PL-MR-0002 | BK | W028 | PEDCO | 110 | PL | MR | 0002 | F0Z-707576 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 2 | 2 | 2 | 0 | 2.3.2.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 2 | 2 | 2 | 1 | 2.3.2.2.2.2.1 | BK-W028-PEDCO-110-PL-TB-0002 | TBE For Flow Line Support - W028 |  | BK-W028-PEDCO-110-PL-TB-0002 | BK-W028-PEDCO-110-PL-TB-0002 | BK | W028 | PEDCO | 110 | PL | TB | 0002 | F0Z-707577 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 3 | 0 | 0 | 0 | 2.3.2.3 |  | Control & Instrumentation
2 | 3 | 2 | 3 | 1 | 0 | 0 | 2.3.2.3.1 |  | WHCP/HPU | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 3 | 1 | 1 | 0 | 2.3.3.1.1 |  | Purchase Material Requisition (PMR)
2 | 3 | 2 | 3 | 1 | 1 | 1 | 2.3.2.3.1.1.1 | BK-W028-PEDCO-110-IN-MR-0001 | PMR For WHCP/HPU - W028 |  | BK-W028-PEDCO-110-IN-MR-0001 | BK-W028-PEDCO-110-IN-MR-0001 | BK | W028 | PEDCO | 110 | IN | MR | 0001 | F0Z-707578 | IFI | IFI | 2021-11-29 | 2021-12-17 | 2021-12-07 | 18 | -10 | 8 | IFI | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 | IFI | 2022-07-03 | 2022-08-18 | 2022-08-23 | 46 | 5 | 51 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-15 |  |  | D02 | IFI | T-1091 | 44731 | 1401/03/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05243 | 44768 | 1401/05/04 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183563 | 44791 | 1401/05/27 | 44796 | 1401/06/01 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0243 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-INS-00-02170 | 44531 | 1400/09/10 | RJ-C4 |  | BK-SUR-ENG-INS-00-02224 | 44537 | 1400/09/16 | CM-C3 |  | 1400-2294-320808 | 2021-12-17 | 1400/09/26 | 44537 | 1400/09/16 | CM | [10 empty] | D01 | IFI | T-0470 | 44577 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02865 | 44591 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MR-0001_D00 | [5 empty] | 1400-2294-390765 | 44592 | 1400/11/11 | 44593 | 1400/11/12 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-MR-0001_D00 | [9 empty] | D02 | IFI | T-1091 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-INS-01-05243 | 44768 | 1401/05/04 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MR-0001_D01 | [5 empty] | 1401-2294-183563 | 44791 | 1401/05/27 | 44796 | 1401/06/01 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-MR-0001_D01
2 | 3 | 2 | 3 | 1 | 2 | 0 | 2.3.3.1.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 3 | 1 | 2 | 1 | 2.3.2.3.1.2.1 | BK-W028-PEDCO-110-IN-TB-0001 | TBE/TBA For WHCP/HPU - W028 |  | BK-W028-PEDCO-110-IN-TB-0001 | BK-W028-PEDCO-110-IN-TB-0001 | BK | W028 | PEDCO | 110 | IN | TB | 0001 | F0Z-707579 | IFI | IFI | 2021-12-15 | 2021-12-14 | 2021-12-15 | -1 | 1 | 0 | IFI | 2022-03-05 | 2022-04-04 | 2022-04-09 | 30 | 5 | 35 | IFI | 2022-07-18 | 2022-07-06 | 2022-07-12 | -12 | 6 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-01 |  |  | D02 | IFI | T-1136 | 44746 | 1401/04/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05364 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-132654 | 44748 | 1401/04/15 | 44754 | 1401/04/21 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0286 | 2021-12-01 | 1400/09/10 |  |  |  | BK-SUR-ENG-INS-00-02297 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-317340 | 2021-12-14 | 1400/09/23 | 44545 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0602 | 44611 | 1400/11/30 |  |  |  | BK-SUR-ENG-INS-00-03345 | 44625 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0001_D00 | [5 empty] | 1401-2294-9652 | 44655 | 1401/01/15 | 44660 | 1401/01/20 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0001_D00 | [9 empty] | D02 | IFI | T-1136 | 44746 | 1401/04/13 |  |  |  | BK-SUR-ENG-INS-01-05364 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0001_D01 | [5 empty] | 1401-2294-132654 | 44748 | 1401/04/15 | 44754 | 1401/04/21 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0001_D01
2 | 3 | 2 | 3 | 2 | 0 | 0 | 2.3.2.3.2 |  | Field Instrumentations
2 | 3 | 2 | 3 | 2 | 1 | 0 | 2.3.3.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 3 | 2 | 1 | 1 | 2.3.2.3.2.1.1 | BK-W028-PEDCO-110-IN-MR-0002 | PMR For Field Instrumentations - W028 |  | BK-W028-PEDCO-110-IN-MR-0002 | BK-W028-PEDCO-110-IN-MR-0002 | BK | W028 | PEDCO | 110 | IN | MR | 0002 | F0Z-707580 | IFI | IFI | 2021-12-27 | 2022-01-21 | 2021-01-25 | 25 | -361 | -336 | IFI | 2022-08-13 | 2022-09-08 | 2022-09-13 | 26 | 5 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-13 |  |  | D01 | IFI | T-1218 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 44557 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/10/01 | 44221 | 1400/11/05 | CM | [10 empty] | D01 | IFI | T-1218 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MR-0002_D00 | [5 empty] | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MR-0002_D00
2 | 3 | 2 | 3 | 2 | 2 | 0 | 2.3.3.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 3 | 2 | 2 | 1 | 2.3.2.3.2.2.1 | BK-W028-PEDCO-110-IN-TB-0002 | TBE/TBA For Field Instrumentations - W028 |  | BK-W028-PEDCO-110-IN-TB-0002 | BK-W028-PEDCO-110-IN-TB-0002 | BK | W028 | PEDCO | 110 | IN | TB | 0002 | F0Z-707581 | IFI | IFI | 2022-06-11 | 2022-06-21 | 2022-07-05 | 10 | 14 | 24 | IFI | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-26 |  |  | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | T-1012 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-05635 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-111541 | 2022-06-21 | 1401/03/31 | 44747 | 1401/04/14 | RJ | [10 empty] | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0002_D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0002_D00
2 | 3 | 2 | 3 | 3 | 0 | 0 | 2.3.2.3.3 |  | Instrument Bulk Items
2 | 3 | 2 | 3 | 3 | 1 | 0 | 2.3.3.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 3 | 3 | 1 | 1 | 2.3.2.3.3.1.1 | BK-W028-PEDCO-110-IN-MR-0003 | PMR For Instrument Bulk Items - W028 |  | BK-W028-PEDCO-110-IN-MR-0003 | BK-W028-PEDCO-110-IN-MR-0003 | BK | W028 | PEDCO | 110 | IN | MR | 0003 | F0Z-707582 | IFI | IFI | 2022-01-30 | 2021-01-31 | 2022-02-01 | -364 | 366 | 2 | IFI | 2022-09-18 | 2022-09-06 | 2022-09-11 | -12 | 5 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-16 |  |  | D01 | IFI | T-1350 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05710 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213888 | 44810 | 1401/06/15 | 44815 | 1401/06/20 | AP | NISCO-CRS-BK-W028-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C2 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 44593 | 1400/11/12 | CM | [10 empty] | D01 | IFI | T-1350 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-INS-01-05710 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MR-0003_D00 | [5 empty] | 1401-2294-213888 | 44810 | 1401/06/15 | 44815 | 1401/06/20 | AP | NISCO-CRS-BK-W028-PEDCO-110-IN-MR-0003_D00
2 | 3 | 2 | 3 | 3 | 2 | 0 | 2.3.3.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 3 | 3 | 2 | 1 | 2.3.2.3.3.2.1 | BK-W028-PEDCO-110-IN-TB-0003 | TBE/TBA For Instrument Bulk Items - W028 |  | BK-W028-PEDCO-110-IN-TB-0003 | BK-W028-PEDCO-110-IN-TB-0003 | BK | W028 | PEDCO | 110 | IN | TB | 0003 | F0Z-707583 | IFI | IFI | 2022-02-16 | 2022-03-19 | 2022-03-14 | 31 | -5 | 26 | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-02 |  |  | D01 | IFI | T-1553 | 44859 | 1401/08/03 | T-1553 | 44859 | 1401/08/03 | BK-SUR-ENG-INS-01-06134 | 44873 | 1401/08/17 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | [6 empty] | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 44634 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-1553 | 44859 | 1401/08/03 | T-1553 | 44859 | 1401/08/03 | BK-SUR-ENG-INS-01-06134 | 44873 | 1401/08/17 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0003_D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0003_D00
2 | 3 | 2 | 4 | 0 | 0 | 0 | 2.3.2.4 |  | Safety & Fire Fighting
2 | 3 | 2 | 4 | 1 | 0 | 0 | 2.3.2.4.1 |  | Fire Fighting and Safety Equipment
2 | 3 | 2 | 4 | 1 | 1 | 0 | 2.3.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 4 | 1 | 1 | 1 | 2.3.2.4.1.1.1 | BK-W028-PEDCO-110-SA-MR-0001 | PMR For Fire Fighting and Safety Equipment - W028 |  | BK-W028-PEDCO-110-SA-MR-0001 | BK-W028-PEDCO-110-SA-MR-0001 | BK | W028 | PEDCO | 110 | SA | MR | 0001 | F0Z-707584 | IFI | IFI | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-08 |  |  | D00 | IFI | T-0316 | 44538 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 44550 | 1400/09/29 | 44552 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | AP
2 | 3 | 2 | 4 | 1 | 2 | 0 | 2.3.4.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 4 | 1 | 2 | 1 | 2.3.2.4.1.2.1 | BK-W028-PEDCO-110-SA-TB-0001 | TBE For Fire Fighting and Safety Equipment - W028 |  | BK-W028-PEDCO-110-SA-TB-0001 | BK-W028-PEDCO-110-SA-TB-0001 | BK | W028 | PEDCO | 110 | SA | TB | 0001 | F0Z-707585 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 4 | 2 | 0 | 0 | 2.3.2.4.2 |  | Safety Sign
2 | 3 | 2 | 4 | 2 | 1 | 0 | 2.3.4.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 4 | 2 | 1 | 1 | 2.3.2.4.2.1.1 | BK-W028-PEDCO-110-SA-MR-0002 | PMR For Fire Safety Sign - W028 |  | BK-W028-PEDCO-110-SA-MR-0002 | BK-W028-PEDCO-110-SA-MR-0002 | BK | W028 | PEDCO | 110 | SA | MR | 0002 | F0Z-707586 | IFI | IFI | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-08 |  |  | D00 | IFI | T-0316 | 44538 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 44550 | 1400/09/29 | 44552 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | AP
2 | 3 | 2 | 4 | 2 | 2 | 0 | 2.3.4.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 4 | 2 | 2 | 1 | 2.3.2.4.2.2.1 | BK-W028-PEDCO-110-SA-TB-0002 | TBE For Fire Safety Sign - W028 |  | BK-W028-PEDCO-110-SA-TB-0002 | BK-W028-PEDCO-110-SA-TB-0002 | BK | W028 | PEDCO | 110 | SA | TB | 0002 | F0Z-707587 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 5 | 0 | 0 | 0 | 2.3.2.5 |  | Structure
2 | 3 | 2 | 5 | 1 | 0 | 0 | 2.3.2.5.1 |  | Steel Structure Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 5 | 1 | 1 | 0 | 2.3.5.1.1 |  | Purchase Material Requisition (PMR)
2 | 3 | 2 | 5 | 1 | 1 | 1 | 2.3.2.5.1.1.1 | BK-W028-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - W028 |  | BK-W028-PEDCO-110-ST-MR-0001 | BK-W028-PEDCO-110-ST-MR-0001 | BK | W028 | PEDCO | 110 | ST | MR | 0001 | F0Z-707588 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 5 | 1 | 2 | 0 | 2.3.5.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 5 | 1 | 2 | 1 | 2.3.2.5.1.2.1 | BK-W028-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - W028 |  | BK-W028-PEDCO-110-ST-TB-0001 | BK-W028-PEDCO-110-ST-TB-0001 | BK | W028 | PEDCO | 110 | ST | TB | 0001 | F0Z-707589 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 5 | 2 | 0 | 0 | 2.3.2.5.2 |  | Anchor Bolts | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 5 | 2 | 1 | 0 | 2.3.5.2.1 |  | Purchase Material Requisition (PMR)
2 | 3 | 2 | 5 | 2 | 1 | 1 | 2.3.2.5.2.1.1 | BK-W028-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - W028 |  | BK-W028-PEDCO-110-ST-MR-0002 | BK-W028-PEDCO-110-ST-MR-0002 | BK | W028 | PEDCO | 110 | ST | MR | 0002 | F0Z-707590 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 5 | 2 | 2 | 0 | 2.3.5.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 5 | 2 | 2 | 1 | 2.3.2.5.2.2.1 | BK-W028-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - W028 |  | BK-W028-PEDCO-110-ST-TB-0002 | BK-W028-PEDCO-110-ST-TB-0002 | BK | W028 | PEDCO | 110 | ST | TB | 0002 | F0Z-707591 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 6 | 0 | 0 | 0 | 2.3.2.6 |  | Civil | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 6 | 1 | 0 | 0 | 2.3.2.6.1 |  | Geomembrane | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 6 | 1 | 1 | 0 | 2.3.6.1.1 |  | Purchase Material Requisition (PMR)
2 | 3 | 2 | 6 | 1 | 1 | 1 | 2.3.2.6.1.1.1 | BK-W028-PEDCO-110-CV-MR-0001 | PMR For Geomembrane - W028 |  | BK-W028-PEDCO-110-CV-MR-0001 | BK-W028-PEDCO-110-CV-MR-0001 | BK | W028 | PEDCO | 110 | CV | MR | 0001 | F0Z-707592 | IFI | IFI | 2022-04-27 | 2022-04-16 | 2022-04-25 | -11 | 9 | -2 | IFI | 2022-06-05 | 2022-06-01 | 2022-06-07 | -4 | 6 | 2 | IFI | 2022-07-06 | 2022-06-29 | 2022-07-05 | -7 | 6 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-13 |  |  | D02 | IFI | T-1106 | 44734 | 1401/04/01 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04916 | 44741 | 1401/04/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-123172 | 44741 | 1401/04/08 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0813 | 2022-04-13 | 1401/01/24 |  |  |  | BK-SUR-ENG-CIV-01-04058 | 44676 | 1401/02/05 | CM-C2 | [6 empty] | 1401-2294-27299 | 2022-04-16 | 1401/01/28 | 44676 | 1401/02/05 | CM | [10 empty] | D01 | IFI | T-0989 | 44703 | 1401/03/01 | T-0989 | 44704 | 1401/03/02 | BK-SUR-ENG-CIV-01-04468 | 44710 | 1401/03/08 | AP | PEDCO-CRS-BK-W028-PEDCO-110-CV-MR-0001_D00 | [5 empty] | 1401-2294-85267 | 44713 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0001_D00 | [9 empty] | D02 | IFI | T-1106 | 44734 | 1401/04/01 |  |  |  | BK-SUR-ENG-CIV-01-04916 | 44741 | 1401/04/08 | AP | [6 empty] | 1401-2294-123172 | 44741 | 1401/04/08 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0001_D01
2 | 3 | 2 | 6 | 1 | 2 | 0 | 2.3.6.1.2 |  | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 6 | 1 | 2 | 1 | 2.3.2.6.1.2.1 | BK-W028-PEDCO-110-CV-TB-0001 | TBE For Geomembrane - W028 |  | BK-W028-PEDCO-110-CV-TB-0001 | BK-W028-PEDCO-110-CV-TB-0001 | BK | W028 | PEDCO | 110 | CV | TB | 0001 | F0Z-707593 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 2 | 6 | 2 | 0 | 0 | 2.3.2.6.2 |  | Geotextile | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 6 | 2 | 1 | 0 | 2.3.6.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 6 | 2 | 1 | 1 | 2.3.2.6.2.1.1 | BK-W028-PEDCO-110-CV-MR-0002 | PMR For Geotextile - W028 |  | BK-W028-PEDCO-110-CV-MR-0002 | BK-W028-PEDCO-110-CV-MR-0002 | BK | W028 | PEDCO | 110 | CV | MR | 0002 | F0Z-707594 | IFI | IFI | 2022-04-27 | 2022-04-16 | 2022-04-25 | -11 | 9 | -2 | IFI | 2022-06-05 | 2022-06-01 | 2022-06-07 | -4 | 6 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-13 |  |  | D01 | IFI | T-0989 | 44703 | 1401/03/01 | T-0989 | 44704 | 1401/03/02 | BK-SUR-ENG-CIV-01-04468 | 44710 | 1401/03/08 | AP | PEDCO-CRS-BK-W028-PEDCO-110-CV-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-85267 | 44713 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0813 | 2022-04-13 | 1401/01/24 |  |  |  | BK-SUR-ENG-CIV-01-04058 | 44676 | 1401/02/05 | CM-C2 | [6 empty] | 1401-2294-27299 | 2022-04-16 | 1401/01/28 | 44676 | 1401/02/05 | CM | [10 empty] | D01 | IFI | T-0989 | 44703 | 1401/03/01 | T-0989 | 44704 | 1401/03/02 | BK-SUR-ENG-CIV-01-04468 | 44710 | 1401/03/08 | AP | PEDCO-CRS-BK-W028-PEDCO-110-CV-MR-0002_D00 | [5 empty] | 1401-2294-85267 | 44713 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0002_D00
2 | 3 | 2 | 6 | 2 | 2 | 0 | 2.3.6.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 2 | 6 | 2 | 2 | 1 | 2.3.2.6.2.2.1 | BK-W028-PEDCO-110-CV-TB-0002 | TBE For Geotextile - W028 |  | BK-W028-PEDCO-110-CV-TB-0002 | BK-W028-PEDCO-110-CV-TB-0002 | BK | W028 | PEDCO | 110 | CV | TB | 0002 | F0Z-707595 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 3 | 0 | 0 | 0 | 0 | 2.3.3 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 3 | 0 | 0 | 1 | 0 | 2.3.3.1 |  | Procedure/Plan
2 | 3 | 3 | 0 | 0 | 1 | 1 | 2.3.3.1.1 | BK-W028-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - W028 |  | BK-W028-PEDCO-110-CO-PR-0001 | BK-W028-PEDCO-110-CO-PR-0001 | BK | W028 | PEDCO | 110 | CO | PR | 0001 | F0Z-707596 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 3 | 4 | 0 | 0 | 0 | 0 | 2.3.4 |  | Field Engineering
2 | 3 | 4 | 0 | 0 | 1 | 0 | 2.3.4.1 |  | Query | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 4 | 0 | 0 | 1 | 1 | 2.3.4.1.1 | BK-W028-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-W028-PEDCO-110-GE-TQ-0001 | BK-W028-PEDCO-110-GE-TQ-0001 | BK | W028 | PEDCO | 110 | GE | TQ | 0001 | F7Z-707597 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 3 | 4 | 0 | 0 | 2 | 0 | 2.3.4.2 |  | Dossier
2 | 3 | 4 | 0 | 0 | 2 | 1 | 2.3.4.2.1 | BK-W028-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W028 |  | BK-W028-PEDCO-110-GE-DO-0001 | BK-W028-PEDCO-110-GE-DO-0001 | BK | W028 | PEDCO | 110 | GE | DO | 0001 | F0Z-707598 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 3 | 5 | 0 | 0 | 0 | 0 | 2.3.5 |  | Engineering Final Documentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 3 | 5 | 0 | 0 | 1 | 0 | 2.3.5.1 |  | Manual
2 | 3 | 5 | 0 | 0 | 1 | 1 | 2.3.5.1.1 | BK-W028-PEDCO-110-GE-ML-0001 | Operating Manual - W028 |  | BK-W028-PEDCO-110-GE-ML-0001 | BK-W028-PEDCO-110-GE-ML-0001 | BK | W028 | PEDCO | 110 | GE | ML | 0001 | F7Z-707599 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 3 | 5 | 0 | 0 | 2 | 0 | 2.3.5.2 |  | Dossier
2 | 3 | 5 | 0 | 0 | 2 | 1 | 2.3.5.2.1 | BK-W028-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W028 |  | BK-W028-PEDCO-110-GE-DO-0001 | [8 empty] | F0Z-707598 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 3 | 5 | 0 | 0 | 2 | 2 | 2.3.5.2.2 | BK-W028-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - W028 |  | BK-W028-PEDCO-110-GE-DO-0002 | BK-W028-PEDCO-110-GE-DO-0002 | BK | W028 | PEDCO | 110 | GE | DO | 0002 | F0Z-707600 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 0 | 0 | 0 | 0 | 0 | 2.4 |  | Package 03-New Well # W046S (Bangestan) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 0 | 0 | 0 | 0 | 2.4.1 |  | Detail Design | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 1 | 0 | 0 | 0 | 2.4.1.1 |  | Process
2 | 4 | 1 | 1 | 1 | 0 | 0 | 2.4.1.1.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 1 | 1 | 0 | 1 | 2.4.1.1.1 | BK-W046S-PEDCO-110-PR-PF-0001 | Process Flow Diagram - W0046S |  | BK-W046S-PEDCO-110-PR-PF-0001 | BK-W046S-PEDCO-110-PR-PF-0001 | BK | W046S | PEDCO | 110 | PR | PF | 0001 | F2A-707601 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-15 | 2021-11-28 | 2021-11-27 | 13 | -1 | 12 | IFA | 2022-01-12 | 2022-01-17 | 2022-01-19 | 5 | 2 | 7 | AFC | 2022-03-27 | 2022-04-29 | 2022-05-01 | 33 | 2 | 35 | AFC | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-01 |  |  | D04 | AFC | T-1268 | 44783 | 1401/05/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05525 | 44797 | 1401/06/02 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-235819 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 44446 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0203 | 44501 | 1400/08/10 | [7 empty] | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D00 | [5 empty] | 1400-2294-288935 | 44523 | 1400/09/02 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D00 | 1400-2290-294909 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D02 | IFA | T-0409 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02659 | 44573 | 1400/10/22 | CM-C3 | [6 empty] | 1400-2294-368486 | 44578 | 1400/10/27 | 44580 | 1400/10/19 | AP | NISOC-BK-W046S-PEDCO-110-PR-PF-0001_D01 | [9 empty] | D03 | AFC | T-0729 | 44633 | 1400/12/22 |  |  |  | BK-SUR-ENG-PCS-01-03886 | 44664 | 1401/01/23 | AP | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D02 | [5 empty] | 1401-2294-43234 | 44680 | 1401/02/09 | 44682 | 1401/02/11 | CM | [10 empty] | D04 | AFC | T-1268 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05525 | 44797 | 1401/06/02 | CM-C2 | [6 empty] | 1401-2294-235819 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D03
2 | 4 | 1 | 1 | 1 | 0 | 2 | 2.4.1.1.1 | BK-W046S-PEDCO-110-PR-PI-0001 | P&ID - W0046S |  | BK-W046S-PEDCO-110-PR-PI-0001 | BK-W046S-PEDCO-110-PR-PI-0001 | BK | W046S | PEDCO | 110 | PR | PI | 0001 | F2A-707602 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | IFA | 2022-09-20 | 2022-11-19 | 2022-11-21 | 60 | 2 | 62 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-01 |  |  | D04 | IFA | T-1368 | 44810 | 1401/06/15 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 44446 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0201 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 44516 | 1400/08/25 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 44564 | 1400/10/13 | CM-C3 | PEDCO-BK-W046S-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 44560 | 1400/10/09 | 44564 | 1400/10/13 | RJ | NISOC-BK-W046S-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D02 | [9 empty] | D04 | IFA | T-1368 | 44810 | 1401/06/15 |  |  |  | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D03 | [5 empty] | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D03
2 | 4 | 1 | 1 | 1 | 0 | 3 | 2.4.1.1.1 | BK-W046S-PEDCO-110-PR-PI-0002 | P&ID for Diesel Oil Drum- W0046S |  | BK-W046S-PEDCO-110-PR-PI-0002 | BK-W046S-PEDCO-110-PR-PI-0002 | BK | W046S | PEDCO | 110 | PR | PI | 0002 | F2A-707603 | AFC | IFC | 2021-11-30 | 2021-12-01 | 2021-12-06 | 1 | 5 | 6 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-10-18 | 2022-10-12 | 177 | -6 | 171 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-16 |  |  | D03 | IFA | T-0794 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0242 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02160 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300481 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-402841 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | AP | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0649 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 44634 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0794 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D02
2 | 4 | 1 | 1 | 1 | 0 | 4 | 2.4.1.1.1 | BK-W046S-PEDCO-110-PR-PI-0003 | P&ID for Potable Water Tank - W0046S |  | BK-W046S-PEDCO-110-PR-PI-0003 | BK-W046S-PEDCO-110-PR-PI-0003 | BK | W046S | PEDCO | 110 | PR | PI | 0003 | F2A-707604 | AFC | IFC | 2021-11-30 | 2021-12-01 | 2021-12-06 | 1 | 5 | 6 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-10-18 | 2022-10-12 | 177 | -6 | 171 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-16 |  |  | D03 | IFA | T-0794 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0242 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02160 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300481 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D00 | [5 empty] | 1400-2294-402841 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | AP | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D00 | [9 empty] | D02 | IFA | T-0649 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 44634 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D01 | [9 empty] | D03 | IFA | T-0794 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D02 | [5 empty] | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D02
2 | 4 | 1 | 1 | 2 | 0 | 0 | 2.4.1.1.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 1 | 2 | 0 | 1 | 2.4.1.1.2 | BK-W046S-PEDCO-110-PR-LI-0001 | Line List - W0046S |  | BK-W046S-PEDCO-110-PR-LI-0001 | BK-W046S-PEDCO-110-PR-LI-0001 | BK | W046S | PEDCO | 110 | PR | LI | 0001 | F0Z-707605 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-22 | 2021-11-27 | 2021-11-29 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-06-27 | 0 | 166 | -44739 | -44573 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-08 |  |  | D02 | IFA | T-0403 | 44559 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-LI-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 44446 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0217 | 44508 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 44520 | 1400/08/29 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 44527 | 1400/09/06 | 44529 | 1400/09/08 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-LI-0001 _D01 | [5 empty] | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-LI-0001_D01
2 | 4 | 1 | 1 | 3 | 0 | 0 | 2.4.1.1.3 |  | Report | [153 empty] | 1400/09/06
2 | 4 | 1 | 1 | 3 | 0 | 1 | 2.4.1.1.3 | BK-W046S-PEDCO-110-PR-RT-0001 | Flow line Hydraulic Calculation Report |  | BK-W046S-PEDCO-110-PR-RT-0001 | BK-W046S-PEDCO-110-PR-RT-0001 | BK | W046S | PEDCO | 110 | PR | RT | 0001 | F0Z-707606 | IFA | IFC | 2021-11-13 | 2021-11-14 | 2021-11-17 | 1 | 3 | 4 | IFA | 2022-01-15 | 2021-02-01 | 2022-02-05 | -348 | 369 | 21 | IFA | 2022-03-08 | 2022-03-10 | 2022-03-13 | 2 | 3 | 5 | IFA | 2022-05-14 | 2022-06-02 | 2022-06-06 | 19 | 4 | 23 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | AFC | 2022-10-22 | 2022-11-19 | 2022-11-20 | 28 | 1 | 29 | [7 empty] | Modify | 2021-10-30 | 2022-10-08 |  | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 44514 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 44517 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 44562 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 44228 | 1400/11/12 | 44597 | 1400/11/16 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 44614 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 44627 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 44630 | 1400/12/19 | 44633 | 1400/12/22 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 44681 | 1401/02/10 | T-0878 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 44709 | 1401/03/07 | AP | PEDCO-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D02 | [5 empty] | 1401-2294-87489 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D02 | [9 empty] | D04 | IFA | T-1267 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05524 | 44797 | 1401/06/02 | AP | [6 empty] | 1401-2294-235783 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D03 | [9 empty] | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | [10 empty] | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP
2 | 4 | 1 | 1 | 4 | 0 | 0 | 2.4.1.1.4 |  | Data Sheet | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 1 | 4 | 0 | 1 | 2.4.1.1 | BK-W046S-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - W046S |  | BK-W046S-PEDCO-110-PR-DT-0001 | BK-W046S-PEDCO-110-PR-DT-0001 | BK | W046S | PEDCO | 110 | PR | DT | 0001 | F0Z-707607 | AFC | IFC | 2022-04-26 | 2022-05-08 | 2022-05-14 | 12 | 6 | 18 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-12 |  |  | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 44695 | 1401/02/24 | CM | [10 empty] | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-DT-0001_D00 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-PR-DT-0001_D00
2 | 4 | 1 | 2 | 0 | 0 | 0 | 2.4.1.2 |  | HVAC/Plumbing | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 2 | 1 | 0 | 0 | 2.4.1.2.1 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 2 | 1 | 0 | 1 | 2.4.1.2.1 | BK-W046S-PEDCO-110-HV-CN-0001 | HVAC Calculation Note For Switchgear Building - W046S |  | BK-W046S-PEDCO-110-HV-CN-0001 | BK-W046S-PEDCO-110-HV-CN-0001 | BK | W046S | PEDCO | 110 | HV | CN | 0001 | F0Z-707608 | AFD | IFC | 2022-03-28 | 2022-03-23 | 2022-03-26 | -5 | 3 | -2 | IFA | 2022-10-10 | 0 | 0 | -44844 | 0 | -44844 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-14 |  |  | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-HV-CN-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-HV-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0731 | 2022-03-14 | 1400/12/23 |  |  |  | BK-SUR-ENG-HVC-01-03861 | 44662 | 1401/01/22 | CM-C3 | [6 empty] | 1401-2294-1285 | 2022-03-23 | 1401/01/06 | 44646 | 1401/01/09 | CM | [10 empty] | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-HV-CN-0001-D00 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-HV-CN-0001_D00
2 | 4 | 1 | 2 | 1 | 0 | 2 | 2.4.1.2.1 | BK-W046S-PEDCO-110-HV-CN-0002 | HVAC Calculation Note For Security Building - W046S |  | BK-W046S-PEDCO-110-HV-CN-0002 | BK-W046S-PEDCO-110-HV-CN-0002 | BK | W046S | PEDCO | 110 | HV | CN | 0002 | F0Z-707609 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 2 | 2 | 0 | 0 | 2.4.1.2.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 2 | 2 | 0 | 1 | 2.4.1.2.2 | BK-W046S-PEDCO-110-HV-DT-0001 | Data Sheets For Main HVAC Equipment - W046S |  | BK-W046S-PEDCO-110-HV-DT-0001 | BK-W046S-PEDCO-110-HV-DT-0001 | BK | W046S | PEDCO | 110 | HV | DT | 0001 | F0Z-707610 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 2 | 3 | 0 | 0 | 2.4.1.2.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 2 | 3 | 0 | 1 | 2.4.1.2.3 | BK-W046S-PEDCO-110-HV-PY-0001 | HVAC System Layout For Switchgear Building - W046S |  | BK-W046S-PEDCO-110-HV-PY-0001 | BK-W046S-PEDCO-110-HV-PY-0001 | BK | W046S | PEDCO | 110 | HV | PY | 0001 | F4B-707611 | AFC | IFC | 2022-05-03 | 2022-04-30 | 2022-05-01 | -3 | 1 | -2 | IFA | 2022-10-10 | 0 | 0 | -44844 | 0 | -44844 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-19 |  |  | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-HV-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-HV-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0846 | 2022-04-19 | 1401/01/30 |  |  |  | BK-SUR-ENG-HVC-01-04149 | 44688 | 1401/02/17 | CM-C3 | [6 empty] | 1401-2294-43977 | 2022-04-30 | 1401/02/10 | 44682 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-HV-PY-0001_D00 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-HV-PY-0001_D00
2 | 4 | 1 | 2 | 3 | 0 | 2 | 2.4.1.2.3 | BK-W046S-PEDCO-110-HV-PY-0002 | HVAC System Layout For Security Building - W046S |  | BK-W046S-PEDCO-110-HV-PY-0002 | BK-W046S-PEDCO-110-HV-PY-0002 | BK | W046S | PEDCO | 110 | HV | PY | 0002 | F4B-707612 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 2 | 3 | 0 | 3 | 2.4.1.2.3 | BK-W046S-PEDCO-110-HV-PY-0003 | Plumbing & Sewage Piping Layout For Switchgear Building - W046S |  | BK-W046S-PEDCO-110-HV-PY-0003 | BK-W046S-PEDCO-110-HV-PY-0003 | BK | W046S | PEDCO | 110 | HV | PY | 0003 | F4B-707613 | AFC | IFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-18 |  |  | D00 | IFC | T-1512 | 44852 | 1401/07/26 | T-1512 | 44852 | 1401/07/26 | BK-SUR-ENG-HVC-01-05965 | 44858 | 1401/08/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1512 | 2022-10-18 | 1401/07/26 | T-1512 | 44852 | 1401/07/26 | BK-SUR-ENG-HVC-01-05965 | 44858 | 1401/08/02 | CM-C3
2 | 4 | 1 | 2 | 3 | 0 | 4 | 2.4.1.2.3 | BK-W046S-PEDCO-110-HV-PY-0004 | Plumbing & Sewage Piping Layout For Security Building - W046S |  | BK-W046S-PEDCO-110-HV-PY-0004 | BK-W046S-PEDCO-110-HV-PY-0004 | BK | W046S | PEDCO | 110 | HV | PY | 0004 | F4B-707614 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 2 | 4 | 0 | 0 | 2.4.1.2.4 |  | MTO
2 | 4 | 1 | 2 | 4 | 0 | 1 | 2.4.1.2 | BK-W046S-PEDCO-110-HV-MT-0001 | MTO For Building HVAC & Plumbing Systems - W046S |  | BK-W046S-PEDCO-110-HV-MT-0001 | BK-W046S-PEDCO-110-HV-MT-0001 | BK | W046S | PEDCO | 110 | HV | MT | 0001 | F8Z-707615 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 3 | 0 | 0 | 0 | 2.4.1.3 |  | Piping
2 | 4 | 1 | 3 | 1 | 0 | 0 | 2.4.1.3.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 3 | 1 | 0 | 1 | 2.4.1.3.1 | BK-W046S-PEDCO-110-PI-DW-0001 | Plot Plan Drawing - W046S |  | BK-W046S-PEDCO-110-PI-DW-0001 | BK-W046S-PEDCO-110-PI-DW-0001 | BK | W046S | PEDCO | 110 | PI | DW | 0001 | F5A-707616 | AFC | IFC | 2022-05-23 | 2022-05-31 | 2022-06-07 | 8 | 7 | 15 | IFA | 2022-11-26 | 0 | 0 | -44891 | 0 | -44891 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-09 |  |  | D01 | IFA | T-1584 | 44877 | 1401/08/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W046S-PEDCO-110-PI-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-PI-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0919 | 2022-05-09 | 1401/02/19 | T-0919 | 44690 | 1401/02/19 | BK-SUR-ENG-PIP-01-04388 | 44704 | 1401/03/02 | CM-C3 | [6 empty] | 1401-2294-85192 | 2022-05-31 | 1401/03/10 | 44719 | 1401/03/17 | CM | [10 empty] | D01 | IFA | T-1584 | 44877 | 1401/08/21 | [7 empty] | PEDCO-CRS-BK-W046S-PEDCO-110-PI-DW-0001_D00 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-PI-DW-0001_D00
2 | 4 | 1 | 3 | 1 | 0 | 2 | 2.4.1.3.1 | BK-W046S-PEDCO-110-PI-DW-0002 | Piping Plan - W046S |  | BK-W046S-PEDCO-110-PI-DW-0002 | BK-W046S-PEDCO-110-PI-DW-0002 | BK | W046S | PEDCO | 110 | PI | DW | 0002 | F4L-707617 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 3 | 1 | 0 | 3 | 2.4.1.3.1 | BK-W046S-PEDCO-110-PI-DW-0003 | Isometric Drawings - W046S |  | BK-W046S-PEDCO-110-PI-DW-0003 | BK-W046S-PEDCO-110-PI-DW-0003 | BK | W046S | PEDCO | 110 | PI | DW | 0003 | F2L-707618 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 3 | 1 | 0 | 4 | 2.4.1.3.1 | BK-W046S-PEDCO-110-PI-DG-0001 | Material Flow Diagram - W046S |  | BK-W046S-PEDCO-110-PI-DG-0001 | BK-W046S-PEDCO-110-PI-DG-0001 | BK | W046S | PEDCO | 110 | PI | DG | 0001 | F2A-707619 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 2022-06-28 | 2022-07-05 | 34 | 7 | 41 | IFA | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-08 |  |  | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 44521 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D00 | [5 empty] | 1401-2294-122170 | 44740 | 1401/04/07 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D00 | [9 empty] | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D01 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D01
2 | 4 | 1 | 3 | 2 | 0 | 0 | 2.4.1.3.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 3 | 2 | 0 | 1 | 2.4.1.3.2 | BK-W046S-PEDCO-110-PI-LI-0001 | Piping Support List - W046S |  | BK-W046S-PEDCO-110-PI-LI-0001 | BK-W046S-PEDCO-110-PI-LI-0001 | BK | W046S | PEDCO | 110 | PI | LI | 0001 | F0Z-707620 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 3 | 2 | 0 | 2 | 2.4.1.3.2 | BK-W046S-PEDCO-110-PI-LI-0002 | Critical Line List - W046S |  | BK-W046S-PEDCO-110-PI-LI-0002 | BK-W046S-PEDCO-110-PI-LI-0002 | BK | W046S | PEDCO | 110 | PI | LI | 0002 | F0Z-707621 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 3 | 3 | 0 | 0 | 2.4.1.3.3 |  | Report
2 | 4 | 1 | 3 | 3 | 0 | 1 | 2.4.1.3.3 | BK-W046S-PEDCO-110-PI-RT-0001 | PDMS Model Review Report (30%) - W046S |  | BK-W046S-PEDCO-110-PI-RT-0001 | BK-W046S-PEDCO-110-PI-RT-0001 | BK | W046S | PEDCO | 110 | PI | RT | 0001 | F0Z-707622 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 3 | 3 | 0 | 2 | 2.4.1.3.3 | BK-W046S-PEDCO-110-PI-RT-0002 | PDMS Model Review Report (60%) - W046S |  | BK-W046S-PEDCO-110-PI-RT-0002 | BK-W046S-PEDCO-110-PI-RT-0002 | BK | W046S | PEDCO | 110 | PI | RT | 0002 | F0Z-707623 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 3 | 3 | 0 | 3 | 2.4.1.3.3 | BK-W046S-PEDCO-110-PI-RT-0003 | PDMS Model Review Report (90%) - W046S |  | BK-W046S-PEDCO-110-PI-RT-0003 | BK-W046S-PEDCO-110-PI-RT-0003 | BK | W046S | PEDCO | 110 | PI | RT | 0003 | F0Z-707624 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 3 | 4 | 0 | 0 | 2.4.1.3.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 3 | 4 | 0 | 1 | 2.4.1.3 | BK-W046S-PEDCO-110-PI-MT-0001 | MTO For Pipes - W046S |  | BK-W046S-PEDCO-110-PI-MT-0001 | BK-W046S-PEDCO-110-PI-MT-0001 | BK | W046S | PEDCO | 110 | PI | MT | 0001 | F8Z-707625 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFI | T-1545 | 44859 | 1401/08/03 | T-1545 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1545 | 2022-10-25 | 1401/08/03 | T-1545 | 44859 | 1401/08/03
2 | 4 | 1 | 3 | 4 | 0 | 2 | 2.4.1.3 | BK-W046S-PEDCO-110-PI-MT-0002 | MTO For Fittings - W046S |  | BK-W046S-PEDCO-110-PI-MT-0002 | BK-W046S-PEDCO-110-PI-MT-0002 | BK | W046S | PEDCO | 110 | PI | MT | 0002 | F8Z-707626 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 3 | 4 | 0 | 3 | 2.4.1.3 | BK-W046S-PEDCO-110-PI-MT-0003 | MTO For Flanges - W046S |  | BK-W046S-PEDCO-110-PI-MT-0003 | BK-W046S-PEDCO-110-PI-MT-0003 | BK | W046S | PEDCO | 110 | PI | MT | 0003 | F8Z-707627 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 3 | 4 | 0 | 4 | 2.4.1.3 | BK-W046S-PEDCO-110-PI-MT-0004 | MTO For Manual Valves - W046S |  | BK-W046S-PEDCO-110-PI-MT-0004 | BK-W046S-PEDCO-110-PI-MT-0004 | BK | W046S | PEDCO | 110 | PI | MT | 0004 | F8Z-707628 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 3 | 4 | 0 | 5 | 2.4.1.3 | BK-W046S-PEDCO-110-PI-MT-0005 | MTO For Gaskets - W046S |  | BK-W046S-PEDCO-110-PI-MT-0005 | BK-W046S-PEDCO-110-PI-MT-0005 | BK | W046S | PEDCO | 110 | PI | MT | 0005 | F8Z-707629 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 3 | 4 | 0 | 6 | 2.4.1.3 | BK-W046S-PEDCO-110-PI-MT-0006 | MTO For Bolt & Nuts - W046S |  | BK-W046S-PEDCO-110-PI-MT-0006 | BK-W046S-PEDCO-110-PI-MT-0006 | BK | W046S | PEDCO | 110 | PI | MT | 0006 | F8Z-707630 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 4 | 0 | 0 | 0 | 2.4.1.4 |  | Pipeline & Flow line
2 | 4 | 1 | 4 | 1 | 0 | 0 | 2.4.1.4.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 4 | 1 | 0 | 1 | 2.4.1.4.1 | BK-W046S-PEDCO-110-PL-DW-0002 | Flow line Transversal Drawings - W046S |  | BK-W046S-PEDCO-110-PL-DW-0002 | BK-W046S-PEDCO-110-PL-DW-0002 | BK | W046S | PEDCO | 110 | PL | DW | 0002 | F4A-707631 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 4 | 2 | 0 | 0 | 2.4.1.4.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 4 | 2 | 0 | 1 | 2.4.1.4.2 | BK-W046S-PEDCO-110-PL-LI-0001 | Road Crossing Location List |  | BK-W046S-PEDCO-110-PL-LI-0001 | BK-W046S-PEDCO-110-PL-LI-0001 | BK | W046S | PEDCO | 110 | PL | LI | 0001 | F0Z-707632 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 4 | 3 | 0 | 0 | 2.4.1.4.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 4 | 3 | 0 | 1 | 2.4.1.4 | BK-W046S-PEDCO-110-PL-MT-0001 | MTO For Line Pipes (Flow lines) - W046S |  | BK-W046S-PEDCO-110-PL-MT-0001 | BK-W046S-PEDCO-110-PL-MT-0001 | BK | W046S | PEDCO | 110 | PL | MT | 0001 | F8Z-707633 | IFI | IFI | 2021-09-05 | 2021-08-30 | 2021-09-05 | -6 | 6 | 0 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W046S-PEDCO-110-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W046S-PEDCO-110-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 44430 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 |  |  |  |  | PEDCO-CRS-BK-W046S-PEDCO-110-PL-MT-0001_D00 | [5 empty] | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W046S-PEDCO-110-PL-MT-0001_D00
2 | 4 | 1 | 5 | 0 | 0 | 0 | 2.4.1.5 |  | Control & Instrumentation
2 | 4 | 1 | 5 | 1 | 0 | 0 | 2.4.1.5.1 |  | Drawing/Diagram
2 | 4 | 1 | 5 | 1 | 0 | 1 | 2.4.1.5.1 | BK-W046S-PEDCO-110-IN-PY-0001 | Instrument Location Layout Drawing - W046S |  | BK-W046S-PEDCO-110-IN-PY-0001 | BK-W046S-PEDCO-110-IN-PY-0001 | BK | W046S | PEDCO | 110 | IN | PY | 0001 | F2J-707634 | AFC | IFC | 2022-05-30 | 2022-08-03 | 2022-08-06 | 65 | 3 | 68 | IFA | 2022-10-05 | 0 | 0 | -44839 | 0 | -44839 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-16 |  |  | D01 | IFA | T-1427 | 44825 | 1401/06/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05868 | 44844 | 1401/07/18 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0958 | 2022-05-16 | 1401/02/26 | T-0958 | 44697 | 1401/02/26 | BK-SUR-ENG-INS-01-04488 | 44710 | 1401/03/09 | CM-C2 | [6 empty] | 1401-2294-165334 | 2022-08-03 | 1401/05/12 | 44779 | 1401/05/15 | CM | [10 empty] | D01 | IFA | T-1427 | 44825 | 1401/06/21 |  |  |  | BK-SUR-ENG-INS-01-05868 | 44844 | 1401/07/18 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-IN-PY-0001_D00 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-IN-PY-0001_D00
2 | 4 | 1 | 5 | 2 | 0 | 0 | 2.4.1.5.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 5 | 2 | 0 | 1 | 2.4.1.5 | BK-W046S-PEDCO-110-IN-MT-0001 | MTO For Instrument Tube and Fitting - W046S |  | BK-W046S-PEDCO-110-IN-MT-0001 | BK-W046S-PEDCO-110-IN-MT-0001 | BK | W046S | PEDCO | 110 | IN | MT | 0001 | F8Z-707635 | IFI | IFI | 2022-01-01 | 2021-01-03 | 2022-01-04 | -363 | 366 | 3 | IFI | 2022-02-12 | 2022-03-10 | 2022-03-14 | 26 | 4 | 30 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-18 |  |  | D01 | IFI | T-0521 | 44590 | 1400/11/09 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03031 | 44604 | 1400/11/23 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443228 | 44630 | 1400/12/19 | 44634 | 1400/12/23 | AP | NISOC-CRS-BK-W046S-PEDCO-110-IN-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0358 | 2021-12-18 | 1400/09/27 | [13 empty] | 1400-2294-347081 | 2021-01-03 | 1400/10/13 | 44565 | 1400/10/14 | CM | [10 empty] | D01 | IFI | T-0521 | 44590 | 1400/11/09 |  |  |  | BK-SUR-ENG-INS-00-03031 | 44604 | 1400/11/23 | CM-C2 | [6 empty] | 1400-2294-443228 | 44630 | 1400/12/19 | 44634 | 1400/12/23 | AP | NISOC-CRS-BK-W046S-PEDCO-110-IN-MT-0001_D00
2 | 4 | 1 | 6 | 0 | 0 | 0 | 2.4.1.6 |  | Safety | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 6 | 1 | 0 | 0 | 2.4.1.6.1 |  | Drawing/Diagram
2 | 4 | 1 | 6 | 1 | 0 | 1 | 2.4.1.6.1 | BK-W046S-PEDCO-110-SA-PY-0001 | Hazardous Area Classification Layout - W046S |  | BK-W046S-PEDCO-110-SA-PY-0001 | BK-W046S-PEDCO-110-SA-PY-0001 | BK | W046S | PEDCO | 110 | SA | PY | 0001 | F2L-707636 | AFC | IFC | 2022-06-08 | 2022-06-23 | 2022-07-02 | 15 | 9 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-25 |  |  | D00 | IFC | T-1003 | 44706 | 1401/03/03 | T-1003 | 44709 | 1401/03/07 | BK-SUR-ENG-STR-01-04985 | 44747 | 1401/04/14 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-113875 | 44735 | 1401/04/02 | 44744 | 1401/04/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1003 | 2022-05-25 | 1401/03/03 | T-1003 | 44709 | 1401/03/07 | BK-SUR-ENG-STR-01-04985 | 44747 | 1401/04/14 | CM-C2 | [6 empty] | 1401-2294-113875 | 2022-06-23 | 1401/04/02 | 44744 | 1401/04/11 | CM
2 | 4 | 1 | 6 | 1 | 0 | 2 | 2.4.1.6.1 | BK-W046S-PEDCO-110-SA-PY-0002 | Safety & Fire Fighting Equipment Location Layout - W046S |  | BK-W046S-PEDCO-110-SA-PY-0002 | BK-W046S-PEDCO-110-SA-PY-0002 | BK | W046S | PEDCO | 110 | SA | PY | 0002 | F2L-707637 | AFC | IFC | 2022-06-25 | 2022-08-09 | 2022-08-14 | 45 | 5 | 50 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-11 |  |  | D00 | IFC | T-1060 | 44723 | 1401/03/21 | T-1060 | 44723 | 1401/03/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171063 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1060 | 2022-06-11 | 1401/03/21 | T-1060 | 44723 | 1401/03/21 | [10 empty] | 1401-2294-171063 | 2022-08-09 | 1401/05/18 | 44787 | 1401/05/23 | CM
2 | 4 | 1 | 6 | 1 | 0 | 3 | 2.4.1.6.1 | BK-W046S-PEDCO-110-SA-PY-0003 | Escape Route & Safety Sign Layout - W046S |  | BK-W046S-PEDCO-110-SA-PY-0003 | BK-W046S-PEDCO-110-SA-PY-0003 | BK | W046S | PEDCO | 110 | SA | PY | 0003 | F2L-707638 | AFC | IFC | 2022-06-25 | 2022-08-09 | 2022-08-14 | 45 | 5 | 50 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-11 |  |  | D00 | IFC | T-1060 | 44723 | 1401/03/21 | T-1060 | 44723 | 1401/03/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171063 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1060 | 2022-06-11 | 1401/03/21 | T-1060 | 44723 | 1401/03/21 | [10 empty] | 1401-2294-171063 | 2022-08-09 | 1401/05/18 | 44787 | 1401/05/23 | CM
2 | 4 | 1 | 6 | 2 | 0 | 0 | 2.4.1.6.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | [42 empty] | T-1059
2 | 4 | 1 | 6 | 2 | 0 | 1 | 2.4.1.6.2 | BK-W046S-PEDCO-110-SA-LI-0001 | Hazard Source List - W046S |  | BK-W046S-PEDCO-110-SA-LI-0001 | BK-W046S-PEDCO-110-SA-LI-0001 | BK | W046S | PEDCO | 110 | SA | LI | 0001 | F0Z-707639 | AFC | IFC | 2021-11-23 | 2021-11-30 | 2021-12-06 | 7 | 6 | 13 | IFA | 2022-03-12 | 2022-04-05 | 2022-04-09 | 24 | 4 | 28 | IFA | 2022-04-30 | 2022-06-07 | 2022-06-09 | 38 | 2 | 40 | AFC | 2022-08-06 | 2022-07-28 | 2022-08-01 | -9 | 4 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-09 | 2022-07-23 |  | D03 | AFC | T-1182 | 44765 | 1401/05/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156966 | 44770 | 1401/05/06 | 44774 | 1401/05/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | T-1059 | [12 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0645 | 44618 | 1400/12/07 | [13 empty] | 1401-2294-13856 | 44656 | 1401/01/18 | 44660 | 1401/01/20 | CM | NISOC-CRS-BK-W046S-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0821 | 44667 | 1401/01/27 | [13 empty] | 1401-2294-91191 | 44719 | 1401/03/17 | 44721 | 1401/03/19 | AP | NISOC-CRS-BK-W046S-PEDCO-110-SA-LI-0001_D01 | [9 empty] | D03 | AFC | T-1182 | 44765 | 1401/05/01 | [13 empty] | 1401-2294-156966 | 44770 | 1401/05/06 | 44774 | 1401/05/10 | AP
2 | 4 | 1 | 6 | 3 | 0 | 0 | 2.4.1.6.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | [42 empty] | T-1053
2 | 4 | 1 | 6 | 3 | 0 | 1 | 2.4.1.6 | BK-W046S-PEDCO-110-SA-MT-0001 | MTO For Fire Fighting & Safety Equipment - W046S |  | BK-W046S-PEDCO-110-SA-MT-0001 | BK-W046S-PEDCO-110-SA-MT-0001 | BK | W046S | PEDCO | 110 | SA | MT | 0001 | F8Z-707640 | IFI | IFI | 2022-06-28 | 2022-08-09 | 2022-08-14 | 42 | 5 | 47 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-14 |  |  | D00 | IFI | T-1077 | 44726 | 1401/03/24 | T-1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171070 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1077 | 2022-06-14 | 1401/03/24 | T-1050 | [12 empty] | 1401-2294-171070 | 2022-08-09 | 1401/05/18 | 44787 | 1401/05/23 | CM
2 | 4 | 1 | 6 | 3 | 0 | 2 | 2.4.1.6 | BK-W046S-PEDCO-110-SA-MT-0002 | MTO For Safety Sign - W046S |  | BK-W046S-PEDCO-110-SA-MT-0002 | BK-W046S-PEDCO-110-SA-MT-0002 | BK | W046S | PEDCO | 110 | SA | MT | 0002 | F8Z-707641 | IFI | IFI | 2022-06-28 | 2022-08-09 | 2022-08-14 | 42 | 5 | 47 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-14 |  |  | D00 | IFI | T-1077 | 44726 | 1401/03/24 | T-1049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171070 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1077 | 2022-06-14 | 1401/03/24 | T-1049 | [12 empty] | 1401-2294-171070 | 2022-08-09 | 1401/05/18 | 44787 | 1401/05/23 | CM
2 | 4 | 1 | 7 | 0 | 0 | 0 | 2.4.1.7 |  | Electrical | [104 empty] | T-1059
2 | 4 | 1 | 7 | 1 | 0 | 0 | 2.4.1.7.1 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | [42 empty] | T-1053
2 | 4 | 1 | 7 | 1 | 0 | 1 | 2.4.1.7 | BK-W046S-PEDCO-110-EL-MT-0001 | MTO For Transmission Over Head Line - W046S |  | BK-W046S-PEDCO-110-EL-MT-0001 | BK-W046S-PEDCO-110-EL-MT-0001 | BK | W046S | PEDCO | 110 | EL | MT | 0001 | F8Z-707642 | IFI | IFI | 2022-10-03 | 2022-09-29 | 2022-10-08 | -4 | 9 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-19 |  |  | D00 | IFI | T-1417 | 44823 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249371 | 44833 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1417 | 2022-09-19 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | [6 empty] | 1401-2294-249371 | 2022-09-29 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 4 | 1 | 7 | 1 | 0 | 2 | 2.4.1.7 | BK-W046S-PEDCO-110-EL-MT-0002 | MTO For Earthing & Lightning Systems - W046S |  | BK-W046S-PEDCO-110-EL-MT-0002 | BK-W046S-PEDCO-110-EL-MT-0002 | BK | W046S | PEDCO | 110 | EL | MT | 0002 | F8Z-707643 | IFI | IFI | 2022-10-25 | 2022-11-10 | 2022-11-14 | 16 | 4 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-11 |  |  | D00 | IFI | T-1480 | 44845 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-304880 | 44875 | 1401/08/19 | 44879 | 1401/08/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1480 | 2022-10-11 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | [6 empty] | 1401-2294-304880 | 2022-11-10 | 1401/08/19 | 44879 | 1401/08/23 | CM
2 | 4 | 1 | 7 | 1 | 0 | 3 | 2.4.1.7 | BK-W046S-PEDCO-110-EL-MT-0003 | MTO For Lighting & Small Powers - W046S |  | BK-W046S-PEDCO-110-EL-MT-0003 | BK-W046S-PEDCO-110-EL-MT-0003 | BK | W046S | PEDCO | 110 | EL | MT | 0003 | F8Z-707644 | IFI | IFI | 2022-06-01 | 2022-06-10 | 2022-06-12 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-18 |  |  | D00 | IFI | T-0969 | 44699 | 1401/02/28 | T-1063 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94633 | 44722 | 1401/03/20 | 44724 | 1401/03/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | T-1063 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | [6 empty] | 1401-2294-94633 | 2022-06-10 | 1401/03/20 | 44724 | 1401/03/22 | CM
2 | 4 | 1 | 7 | 1 | 0 | 4 | 2.4.1.7 | BK-W046S-PEDCO-110-EL-MT-0004 | MTO For Power & Control Cables - W046S |  | BK-W046S-PEDCO-110-EL-MT-0004 | BK-W046S-PEDCO-110-EL-MT-0004 | BK | W046S | PEDCO | 110 | EL | MT | 0004 | F8Z-707645 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [41 empty] | T-1039
2 | 4 | 1 | 7 | 1 | 0 | 5 | 2.4.1.7 | BK-W046S-PEDCO-110-EL-MT-0005 | MTO For Tray/Ladder and Accessories - W046S |  | BK-W046S-PEDCO-110-EL-MT-0005 | BK-W046S-PEDCO-110-EL-MT-0005 | BK | W046S | PEDCO | 110 | EL | MT | 0005 | F8Z-707646 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [41 empty] | T-1068
2 | 4 | 1 | 7 | 1 | 0 | 6 | 2.4.1.7 | BK-W046S-PEDCO-110-EL-MT-0006 | MTO For Electrical Bulk Items - W046S |  | BK-W046S-PEDCO-110-EL-MT-0006 | BK-W046S-PEDCO-110-EL-MT-0006 | BK | W046S | PEDCO | 110 | EL | MT | 0006 | F8Z-707647 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [41 empty] | T-1053
2 | 4 | 1 | 8 | 0 | 0 | 0 | 2.4.1.8 |  | Architecture | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | [42 empty] | T-1068
2 | 4 | 1 | 8 | 1 | 0 | 0 | 2.4.1.8.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | [42 empty] | T-1038
2 | 4 | 1 | 8 | 1 | 0 | 1 | 2.4.1.8.1 | BK-W046S-PEDCO-110-AR-DW-0001 | Architectural Drawing For Diesel Generator Shelter of Well Pads - W046S |  | BK-W046S-PEDCO-110-AR-DW-0001 | BK-W046S-PEDCO-110-AR-DW-0001 | BK | W046S | PEDCO | 110 | AR | DW | 0001 | F4B-707648 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-01 |  |  | D00 | IFC | T-0885 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04151 | 44688 | 1401/02/17 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04151 | 44688 | 1401/02/17 | CM-C2 | [6 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 44697 | 1401/02/26 | CM
2 | 4 | 1 | 8 | 1 | 0 | 2 | 2.4.1.8.1 | BK-W046S-PEDCO-110-AR-DW-0002 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W046S |  | BK-W046S-PEDCO-110-AR-DW-0002 | BK-W046S-PEDCO-110-AR-DW-0002 | BK | W046S | PEDCO | 110 | AR | DW | 0002 | F4B-707649 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [41 empty] | T-1056
2 | 4 | 1 | 8 | 1 | 0 | 3 | 2.4.1.8.1 | BK-W046S-PEDCO-110-AR-DW-0003 | Architectural Drawing For Switchgear Building of Well Pads - W046S |  | BK-W046S-PEDCO-110-AR-DW-0003 | BK-W046S-PEDCO-110-AR-DW-0003 | BK | W046S | PEDCO | 110 | AR | DW | 0003 | F4B-707650 | AFC | IFC | 2022-03-16 | 2022-03-10 | 2022-03-12 | -6 | 2 | -4 | IFC | 2022-06-01 | 2022-05-31 | 2022-06-07 | -1 | 7 | 6 | IFC | 2022-09-21 | 2022-10-11 | 2022-10-17 | 20 | 6 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D02 | IFC | T-1370 | 44811 | 1401/06/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W046S-PEDCO-110-AR-DW-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-W046S-PEDCO-110-AR-DW-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0661 | 2022-03-02 | 1400/12/11 | T-1051 |  |  | BK-SUR-ENG-ARC-00-03449 | 44632 | 1400/12/21 | CM-C2 | [6 empty] | 1400-2294-443270 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | RJ | [10 empty] | D01 | IFC | T-0974 | 44699 | 1401/02/28 | T-0974 | 44702 | 1401/02/31 | BK-SUR-ENG-ARC-01-04416 | 44705 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-AR-DW-0003-D00 | [5 empty] | 1401-2294-85268 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-AR-DW-0003_D00 | [9 empty] | D02 | IFC | T-1370 | 44811 | 1401/06/16 | [7 empty] | PEDCO-CRS-BK-W046S-PEDCO-110-AR-DW-0003_D01 | [5 empty] | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-W046S-PEDCO-110-AR-DW-0003_D01
2 | 4 | 1 | 8 | 1 | 0 | 4 | 2.4.1.8.1 | BK-W046S-PEDCO-110-AR-DW-0004 | Architectural Drawing For Security Building of Well Pads - W046S |  | BK-W046S-PEDCO-110-AR-DW-0004 | BK-W046S-PEDCO-110-AR-DW-0004 | BK | W046S | PEDCO | 110 | AR | DW | 0004 | F4B-707651 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | IFC | 2022-10-03 | 2022-10-29 | 2022-10-30 | 26 | 1 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-19 |  |  | D01 | IFC | T-1418 | 44823 | 1401/06/28 | T-1418 | 44823 | 1401/06/28 | BK-SUR-ENG-ARC-01-05772 | 44832 | 1401/07/06 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-AR-DW-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284604 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-W046S-PEDCO-110-AR-DW-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 44697 | 1401/02/26 | RJ | [10 empty] | D01 | IFC | T-1418 | 44823 | 1401/06/28 | T-1418 | 44823 | 1401/06/28 | BK-SUR-ENG-ARC-01-05772 | 44832 | 1401/07/06 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-AR-DW-0004_D00 | [5 empty] | 1401-2294-284604 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-W046S-PEDCO-110-AR-DW-0004_D00
2 | 4 | 1 | 8 | 2 | 0 | 0 | 2.4.1.8.2 |  | MTO | [104 empty] | T-1058
2 | 4 | 1 | 8 | 2 | 0 | 1 | 2.4.1.8 | BK-W046S-PEDCO-110-AR-MT-0001 | MTO For Architectural Works - W0046S |  | BK-W046S-PEDCO-110-AR-MT-0001 | BK-W046S-PEDCO-110-AR-MT-0001 | BK | W046S | PEDCO | 110 | AR | MT | 0001 | F8Z-707652 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [41 empty] | T-1043
2 | 4 | 1 | 9 | 0 | 0 | 0 | 2.4.1.9 |  | Civil | [104 empty] | T-1057
2 | 4 | 1 | 9 | 1 | 0 | 0 | 2.4.1.9.1 |  | Drawing/Diagram | [104 empty] | T-1037
2 | 4 | 1 | 9 | 1 | 0 | 1 | 2.4.1.9.1 | BK-W046S-PEDCO-110-CV-PY-0001 | General Civil Layout -W046S |  | BK-W046S-PEDCO-110-CV-PY-0001 | BK-W046S-PEDCO-110-CV-PY-0001 | BK | W046S | PEDCO | 110 | CV | PY | 0001 | F4A-707653 | AFC | IFC | 2022-05-16 | 2022-07-10 | 2022-07-26 | 55 | 16 | 71 | IFA | 2022-09-18 | 2022-09-19 | 2022-09-20 | 1 | 1 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-02 |  |  | D01 | IFA | T-1355 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05698 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-228562 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | CM | NISOC-CRS-BK-W046S-PEDCO-110-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0900 | 2022-05-02 | 1401/02/12 | T-1067 |  |  | BK-SUR-ENG-CIV-01-04158 | 44688 | 1401/02/17 | CM-C2 | [6 empty] | 1401-2294-54858 | 2022-07-10 | 1401/05/19 | 44768 | 1401/05/04 | CM | [10 empty] | D01 | IFA | T-1355 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-CIV-01-05698 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-PY-0001_D01 | [5 empty] | 1401-2294-228562 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | CM | NISOC-CRS-BK-W046S-PEDCO-110-CV-PY-0001_D01
2 | 4 | 1 | 9 | 1 | 0 | 2 | 2.4.1.9.1 | BK-W046S-PEDCO-110-CV-PY-0002 | Civil and Structural drawings -W046S |  | BK-W046S-PEDCO-110-CV-PY-0002 | BK-W046S-PEDCO-110-CV-PY-0002 | BK | W046S | PEDCO | 110 | CV | PY | 0002 | F4S-707654 | AFC | IFC | 2022-06-05 | 2022-06-01 | 2022-06-07 | -4 | 6 | 2 | IFA | 2022-08-07 | 2022-08-02 | 2022-08-09 | -5 | 7 | 2 | IFA | 2022-10-10 | 2022-10-25 | 2022-10-26 | 15 | 1 | 16 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-22 |  |  | D02 | IFA | T-1440 | 44830 | 1401/07/04 | T-1440 | 44830 | 1401/07/04 | BK-SUR-ENG-CIV-01-05863 | 44842 | 1401/07/16 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-PY-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279781 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-CV-PY-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0988 | 2022-05-22 | 1401/03/01 | T-1069 | 44704 | 1401/03/02 | BK-SUR-ENG-CIV-01-04523 | 44718 | 1401/03/16 | CM-C2 | [6 empty] | 1401-2294-85729 | 2022-06-01 | 1401/03/11 | 44719 | 1401/03/17 | CM | [10 empty] | D01 | IFA | T-1185 | 44766 | 1401/05/02 |  |  |  | BK-SUR-ENG-CIV-01-05343 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-PY-0002_D00 | [5 empty] | 1401-2294-164809 | 44775 | 1401/05/11 | 44782 | 1401/05/18 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-CV-PY-0002_D00 | [9 empty] | D02 | IFA | T-1440 | 44830 | 1401/07/04 | T-1440 | 44830 | 1401/07/04 | BK-SUR-ENG-CIV-01-05863 | 44842 | 1401/07/16 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-PY-0002_D01 | [5 empty] | 1401-2294-279781 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-CV-PY-0002_D01
2 | 4 | 1 | 9 | 1 | 0 | 3 | 2.4.1.9.1 | BK-W046S-PEDCO-110-CV-DW-0001 | Rough Grading Plans -W046S |  | BK-W046S-PEDCO-110-CV-DW-0001 | BK-W046S-PEDCO-110-CV-DW-0001 | BK | W046S | PEDCO | 110 | CV | DW | 0001 | F4S-707655 | AFC | IFC | 2021-12-26 | 2021-12-16 | 2021-12-19 | -10 | 3 | -7 | IFA | 2022-02-07 | 2022-01-31 | 2022-02-02 | -7 | 2 | -5 | IFA | 2022-05-22 | 2022-05-11 | 2022-05-16 | -11 | 5 | -6 | IFA | 2022-08-15 | 2022-08-28 | 2022-08-31 | 13 | 3 | 16 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-12 |  |  | D03 | IFA | T-1230 | 44774 | 1401/05/10 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05573 | 44804 | 1401/06/09 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-197967 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | CM | NISOC-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0331 | 2021-12-12 | 1400/09/21 | T-1041 |  |  | BK-SUR-ENG-CIV-00-02371 | 44549 | 1400/09/28 | CM-C3 | [6 empty] | 1400-2294-320697 | 2021-12-16 | 1400/09/25 | 44549 | 1400/09/28 | CM | [10 empty] | D01 | IFA | T-0496 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-CIV-00-02833 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D00 | [5 empty] | 1400-2294-389630 | 44592 | 1400/11/11 | 44594 | 1400/11/13 | CM | NISOC-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D00 | [9 empty] | D02 | IFA | T-0910 | 44689 | 1401/02/18 | T-0910 | 44689 | 1401/02/18 | BK-SUR-ENG-CIV-01-04381 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D01 | [5 empty] | 1401-2294-59411 | 44692 | 1401/02/21 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D01 | [9 empty] | D03 | IFA | T-1230 | 44774 | 1401/05/10 |  |  |  | BK-SUR-ENG-CIV-01-05573 | 44804 | 1401/06/09 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D02 | [5 empty] | 1401-2294-197967 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | CM | NISOC-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D02
2 | 4 | 1 | 9 | 2 | 0 | 0 | 2.4.1.9.2 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | [42 empty] | T-1030
2 | 4 | 1 | 9 | 2 | 0 | 1 | 2.4.1.9.2 | BK-W046S-PEDCO-110-CV-CN-0001 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W046S |  | BK-W046S-PEDCO-110-CV-CN-0001 | BK-W046S-PEDCO-110-CV-CN-0001 | BK | W046S | PEDCO | 110 | CV | CN | 0001 | F0Z-707656 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [41 empty] | T-1054
2 | 4 | 1 | 9 | 3 | 0 | 0 | 2.4.1.9.3 |  | MTO | [104 empty] | T-1045
2 | 4 | 1 | 9 | 3 | 0 | 1 | 2.4.1.9 | BK-W046S-PEDCO-110-CV-MT-0001 | MTO For Civil Works - W046S |  | BK-W046S-PEDCO-110-CV-MT-0001 | BK-W046S-PEDCO-110-CV-MT-0001 | BK | W046S | PEDCO | 110 | CV | MT | 0001 | F8Z-707657 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [41 empty] | T-1045
2 | 4 | 1 | 10 | 0 | 0 | 0 | 2.4.1.10 |  | Structure | [104 empty] | T-1064
2 | 4 | 1 | 10 | 1 | 0 | 0 | 2.4.1.10.1 |  | Drawing/Diagram | [104 empty] | T-1062
2 | 4 | 1 | 10 | 1 | 0 | 1 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0003 | Fuel Oil Storage Drum Detail Drawing For Well Pads - W046S |  | BK-W046S-PEDCO-110-ST-DW-0003 | BK-W046S-PEDCO-110-ST-DW-0003 | BK | W046S | PEDCO | 110 | ST | DW | 0003 | F4G-707658 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 10 | 1 | 0 | 2 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0004 | Foundation Drawing For Security Building For Well Pads - W046S |  | BK-W046S-PEDCO-110-ST-DW-0004 | BK-W046S-PEDCO-110-ST-DW-0004 | BK | W046S | PEDCO | 110 | ST | DW | 0004 | F4Q-707659 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 10 | 1 | 0 | 3 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0005 | Structural Drawing For Security Building For Well Pads - W046S |  | BK-W046S-PEDCO-110-ST-DW-0005 | BK-W046S-PEDCO-110-ST-DW-0005 | BK | W046S | PEDCO | 110 | ST | DW | 0005 | F4M-707660 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 10 | 1 | 0 | 4 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0006 | Foundation Drawing For Switchgear Building For Well Pads - W046S |  | BK-W046S-PEDCO-110-ST-DW-0006 | BK-W046S-PEDCO-110-ST-DW-0006 | BK | W046S | PEDCO | 110 | ST | DW | 0006 | F4Q-707661 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 10 | 1 | 0 | 5 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0007 | Structural Drawing For Switchgear Building For Well Pads - W046S |  | BK-W046S-PEDCO-110-ST-DW-0007 | BK-W046S-PEDCO-110-ST-DW-0007 | BK | W046S | PEDCO | 110 | ST | DW | 0007 | F4M-707662 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 10 | 1 | 0 | 6 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0008 | Foundation Drawing For Potable Water Tank For Well Pads - W046S |  | BK-W046S-PEDCO-110-ST-DW-0008 | BK-W046S-PEDCO-110-ST-DW-0008 | BK | W046S | PEDCO | 110 | ST | DW | 0008 | F4Q-707663 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 10 | 1 | 0 | 7 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0009 | Foundation Drawing For Diesel Generator Shelter For Well Pads - W046S |  | BK-W046S-PEDCO-110-ST-DW-0009 | BK-W046S-PEDCO-110-ST-DW-0009 | BK | W046S | PEDCO | 110 | ST | DW | 0009 | F4Q-707664 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 10 | 1 | 0 | 8 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0010 | Structural Drawing For Diesel Generator Shelter For Well Pads - W046S |  | BK-W046S-PEDCO-110-ST-DW-0010 | BK-W046S-PEDCO-110-ST-DW-0010 | BK | W046S | PEDCO | 110 | ST | DW | 0010 | F4M-707665 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 10 | 1 | 0 | 9 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0012 | Platform Structure Drawing - W046S |  | BK-W046S-PEDCO-110-ST-DW-0012 | BK-W046S-PEDCO-110-ST-DW-0012 | BK | W046S | PEDCO | 110 | ST | DW | 0012 | F4M-707666 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 10 | 1 | 0 | 10 | 2.4.1.10.1 | BK-W046S-PEDCO-110-ST-DW-0013 | Foundation Drawing For Transmission Line Tower - W046S |  | BK-W046S-PEDCO-110-ST-DW-0013 | BK-W046S-PEDCO-110-ST-DW-0013 | BK | W046S | PEDCO | 110 | ST | DW | 0013 | F4Q-707667 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 10 | 2 | 0 | 0 | 2.4.1.10.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 10 | 2 | 0 | 1 | 2.4.1.10 | BK-W046S-PEDCO-110-ST-MT-0001 | MTO For Structural Works - W046S |  | BK-W046S-PEDCO-110-ST-MT-0001 | BK-W046S-PEDCO-110-ST-MT-0001 | BK | W046S | PEDCO | 110 | ST | MT | 0001 | F8Z-707668 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 1 | 11 | 0 | 0 | 0 | 2.4.1.11 |  | Survey (Topography) & Geotechnic/Geoelectric | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 1 | 11 | 1 | 0 | 0 | 2.4.1.11.1 |  | Geotechnic
2 | 4 | 1 | 11 | 1 | 1 | 0 | 2.4.11.1.1 |  | Report
2 | 4 | 1 | 11 | 1 | 1 | 1 | 2.4.1.11.1.1.1 | BK-W046S-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - W046S |  | BK-W046S-PEDCO-110-GT-RT-0001 | BK-W046S-PEDCO-110-GT-RT-0001 | BK | W046S | PEDCO | 110 | GT | RT | 0001 | F0Z-707669 | IFI | IFI | 2022-08-17 | 2022-08-27 | 2022-08-28 | 10 | 1 | 11 | IFA | 2022-11-13 | 0 | 0 | -44878 | 0 | -44878 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-03 |  |  | D01 | IFA | T-1567 | 44864 | 1401/08/08 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-06117 | 44872 | 1401/08/16 | CM | PEDCO-CRS-BK-W046SL-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046SL-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1239 | 2022-08-03 | 1401/05/12 |  |  |  | BK-SUR-ENG-CIV-01-05541 | 44801 | 1401/06/06 | CM-C2 | [6 empty] | 1401-2294-196157 | 2022-08-27 | 1401/06/05 | 44801 | 1401/06/06 | CM | [10 empty] | D01 | IFA | T-1567 | 44864 | 1401/08/08 |  |  |  | BK-SUR-ENG-CIV-01-06117 | 44872 | 1401/08/16 | CM | PEDCO-CRS-BK-W046SL-PEDCO-110-GT-RT-0001_D00 | [11 empty] | NISOC-CRS-BK-W046SL-PEDCO-110-GT-RT-0001_D00
2 | 4 | 1 | 11 | 1 | 2 | 0 | 2.4.11.1.2 |  | Drawing/Diagram
2 | 4 | 1 | 11 | 1 | 2 | 1 | 2.4.1.11.1.2.1 | BK-W046S-PEDCO-110-SU-DW-0001 | Flow line Plan & Profile Drawings - W046S |  | BK-W046S-PEDCO-110-SU-DW-0001 | BK-W046S-PEDCO-110-SU-DW-0001 | BK | W046S | PEDCO | 110 | SU | DW | 0001 | F4A-707670 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 1 | 11 | 1 | 2 | 2 | 2.4.1.11.1.2.2 | BK-W046S-PEDCO-110-SU-DW-0002 | Over Head Line Plan and Profile - W046S |  | BK-W046S-PEDCO-110-SU-DW-0002 | BK-W046S-PEDCO-110-SU-DW-0002 | BK | W046S | PEDCO | 110 | SU | DW | 0002 | F4A-707671 | AFC | IFC | 2022-04-09 | 2022-04-28 | 2022-05-01 | 19 | 3 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-26 |  |  | D00 | IFC | T-0745 | 44646 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-03676 | 44645 | 1401/01/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43154 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0745 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-CIV-01-03676 | 44645 | 1401/01/08 | CM-C2 | [6 empty] | 1401-2294-43154 | 2022-04-28 | 1401/02/08 | 44682 | 1401/02/11 | CM
2 | 4 | 2 | 0 | 0 | 0 | 0 | 2.4.2 |  | Procurement Engineering
2 | 4 | 2 | 1 | 0 | 0 | 0 | 2.4.2.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 1 | 0 | 0 | 2.4.2.1.1 |  | Pipes
2 | 4 | 2 | 1 | 1 | 1 | 0 | 2.4.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 1 | 1 | 1 | 2.4.2.1.1.1.1 | BK-W046S-PEDCO-110-PI-MR-0001 | PMR For Pipes - W046S |  | BK-W046S-PEDCO-110-PI-MR-0001 | BK-W046S-PEDCO-110-PI-MR-0001 | BK | W046S | PEDCO | 110 | PI | MR | 0001 | F0Z-707672 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 1 | 2 | 0 | 2.4.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 1 | 2 | 1 | 2.4.2.1.1.2.1 | BK-W046S-PEDCO-110-PI-TB-0001 | TBE For Pipes - W046S |  | BK-W046S-PEDCO-110-PI-TB-0001 | BK-W046S-PEDCO-110-PI-TB-0001 | BK | W046S | PEDCO | 110 | PI | TB | 0001 | F0Z-707673 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 1 | 2 | 0 | 0 | 2.4.2.1.2 |  | Fittings
2 | 4 | 2 | 1 | 2 | 1 | 0 | 2.4.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 2 | 1 | 1 | 2.4.2.1.2.1.1 | BK-W046S-PEDCO-110-PI-MR-0002 | PMR For Fittings - W046S |  | BK-W046S-PEDCO-110-PI-MR-0002 | BK-W046S-PEDCO-110-PI-MR-0002 | BK | W046S | PEDCO | 110 | PI | MR | 0002 | F0Z-707674 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 2 | 2 | 0 | 2.4.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 2 | 2 | 1 | 2.4.2.1.2.2.1 | BK-W046S-PEDCO-110-PI-TB-0002 | TBE For Fitting - W046S |  | BK-W046S-PEDCO-110-PI-TB-0002 | BK-W046S-PEDCO-110-PI-TB-0002 | BK | W046S | PEDCO | 110 | PI | TB | 0002 | F0Z-707675 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 1 | 3 | 0 | 0 | 2.4.2.1.3 |  | Flanges
2 | 4 | 2 | 1 | 3 | 1 | 0 | 2.4.1.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 3 | 1 | 1 | 2.4.2.1.3.1.1 | BK-W046S-PEDCO-110-PI-MR-0003 | PMR For Flanges - W046S |  | BK-W046S-PEDCO-110-PI-MR-0003 | BK-W046S-PEDCO-110-PI-MR-0003 | BK | W046S | PEDCO | 110 | PI | MR | 0003 | F0Z-707676 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 3 | 2 | 0 | 2.4.1.3.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 3 | 2 | 1 | 2.4.2.1.3.2.1 | BK-W046S-PEDCO-110-PI-TB-0003 | TBE For Flanges - W046S |  | BK-W046S-PEDCO-110-PI-TB-0003 | BK-W046S-PEDCO-110-PI-TB-0003 | BK | W046S | PEDCO | 110 | PI | TB | 0003 | F0Z-707677 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 1 | 4 | 0 | 0 | 2.4.2.1.4 |  | Manual Valves
2 | 4 | 2 | 1 | 4 | 1 | 0 | 2.4.1.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 4 | 1 | 1 | 2.4.2.1.4.1.1 | BK-W046S-PEDCO-110-PI-MR-0004 | PMR For Manual Valves - W046S |  | BK-W046S-PEDCO-110-PI-MR-0004 | BK-W046S-PEDCO-110-PI-MR-0004 | BK | W046S | PEDCO | 110 | PI | MR | 0004 | F0Z-707678 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 4 | 2 | 0 | 2.4.1.4.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 4 | 2 | 1 | 2.4.2.1.4.2.1 | BK-W046S-PEDCO-110-PI-TB-0004 | TBE For Manual Valves - W046S |  | BK-W046S-PEDCO-110-PI-TB-0004 | BK-W046S-PEDCO-110-PI-TB-0004 | BK | W046S | PEDCO | 110 | PI | TB | 0004 | F0Z-707679 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 1 | 5 | 0 | 0 | 2.4.2.1.5 |  | Gaskets
2 | 4 | 2 | 1 | 5 | 1 | 0 | 2.4.1.5.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 5 | 1 | 1 | 2.4.2.1.5.1.1 | BK-W046S-PEDCO-110-PI-MR-0005 | PMR For Gaskets - W046S |  | BK-W046S-PEDCO-110-PI-MR-0005 | BK-W046S-PEDCO-110-PI-MR-0005 | BK | W046S | PEDCO | 110 | PI | MR | 0005 | F0Z-707680 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 5 | 2 | 0 | 2.4.1.5.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 5 | 2 | 1 | 2.4.2.1.5.2.1 | BK-W046S-PEDCO-110-PI-TB-0005 | TBE For Gaskets - W046S |  | BK-W046S-PEDCO-110-PI-TB-0005 | BK-W046S-PEDCO-110-PI-TB-0005 | BK | W046S | PEDCO | 110 | PI | TB | 0005 | F0Z-707681 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 6 | 0 | 0 | 2.4.2.1.6 |  | Bolt & Nuts | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 6 | 1 | 0 | 2.4.1.6.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 6 | 1 | 1 | 2.4.2.1.6.1.1 | BK-W046S-PEDCO-110-PI-MR-0006 | PMR For Bolt/Nuts - W046S |  | BK-W046S-PEDCO-110-PI-MR-0006 | BK-W046S-PEDCO-110-PI-MR-0006 | BK | W046S | PEDCO | 110 | PI | MR | 0006 | F0Z-707682 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 1 | 6 | 2 | 0 | 2.4.1.6.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 6 | 2 | 1 | 2.4.2.1.6.2.1 | BK-W046S-PEDCO-110-PI-TB-0006 | TBE For Bolt/Nuts - W046S |  | BK-W046S-PEDCO-110-PI-TB-0006 | BK-W046S-PEDCO-110-PI-TB-0006 | BK | W046S | PEDCO | 110 | PI | TB | 0006 | F0Z-707683 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 7 | 0 | 0 | 2.4.2.1.7 |  | Sampling Connection
2 | 4 | 2 | 1 | 7 | 1 | 0 | 2.4.1.7.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 7 | 1 | 1 | 2.4.2.1.7.1.1 | BK-W046S-PEDCO-110-PI-MR-0007 | PMR For Sampling Connection Set - W046S |  | BK-W046S-PEDCO-110-PI-MR-0007 | BK-W046S-PEDCO-110-PI-MR-0007 | BK | W046S | PEDCO | 110 | PI | MR | 0007 | F0Z-707684 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 7 | 2 | 0 | 2.4.1.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 7 | 2 | 1 | 2.4.2.1.7.2.1 | BK-W046S-PEDCO-110-PI-TB-0007 | TBE For Sampling Connection - W046S |  | BK-W046S-PEDCO-110-PI-TB-0007 | BK-W046S-PEDCO-110-PI-TB-0007 | BK | W046S | PEDCO | 110 | PI | TB | 0007 | F0Z-707685 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 8 | 0 | 0 | 2.4.2.1.8 |  | Stone Trap
2 | 4 | 2 | 1 | 8 | 1 | 0 | 2.4.1.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 8 | 1 | 1 | 2.4.2.1.8.1.1 | BK-W046S-PEDCO-110-PI-MR-0008 | PMR For Stone Trap - W046S |  | BK-W046S-PEDCO-110-PI-MR-0008 | BK-W046S-PEDCO-110-PI-MR-0008 | BK | W046S | PEDCO | 110 | PI | MR | 0008 | F0Z-707686 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 1 | 8 | 2 | 0 | 2.4.1.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 1 | 8 | 2 | 1 | 2.4.2.1.8.2.1 | BK-W046S-PEDCO-110-PI-TB-0008 | TBE For Stone Trap - W046S |  | BK-W046S-PEDCO-110-PI-TB-0008 | BK-W046S-PEDCO-110-PI-TB-0008 | BK | W046S | PEDCO | 110 | PI | TB | 0008 | F0Z-707687 | IFI | IFI | 2022-06-08 | 2022-06-13 | 2022-06-14 | 5 | 1 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-25 |  |  | D00 | IFI | T-1002 | 44706 | 1401/03/03 | T-1002 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04514 | 44713 | 1401/03/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-100877 | 44725 | 1401/03/23 | 44726 | 1401/03/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1002 | 2022-05-25 | 1401/03/03 | T-1002 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04514 | 44713 | 1401/03/11 | CM-C3 | [6 empty] | 1401-2294-100877 | 2022-06-13 | 1401/03/23 | 44726 | 1401/03/24 | CM
2 | 4 | 2 | 1 | 9 | 0 | 0 | 2.4.2.1.9 |  | Pipe Support
2 | 4 | 2 | 1 | 9 | 1 | 0 | 2.4.1.9.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 9 | 1 | 1 | 2.4.2.1.9.1.1 | BK-W046S-PEDCO-110-PI-MR-0009 | PMR For Pipe Support - W046S |  | BK-W046S-PEDCO-110-PI-MR-0009 | BK-W046S-PEDCO-110-PI-MR-0009 | BK | W046S | PEDCO | 110 | PI | MR | 0009 | F0Z-707688 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 1 | 9 | 2 | 0 | 2.4.1.9.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 9 | 2 | 1 | 2.4.2.1.9.2.1 | BK-W046S-PEDCO-110-PI-TB-0009 | TBE For Pipe Support - W046S |  | BK-W046S-PEDCO-110-PI-TB-0009 | BK-W046S-PEDCO-110-PI-TB-0009 | BK | W046S | PEDCO | 110 | PI | TB | 0009 | F0Z-707689 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 1 | 9 | 0 | 0 | 2.4.2.1.9 |  | BURN PIT PIPES
2 | 4 | 2 | 1 | 9 | 1 | 0 | 2.4.1.9.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 9 | 1 | 1 | 2.4.2.1.9.1.1 | BK-W046S-PEDCO-110-PI-MR-0009 | PMR FOR BURN PIT PIPES– W046S |  | BK-W046S-PEDCO-110-PI-MR-0011 | BK-W046S-PEDCO-110-PI-MR-0009 | BK | W046S | PEDCO | 110 | PI | MR | 0009 | F0Z-707688 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify |  |  |  | D00 | IFI | T-1550 | 44859 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1550 | 2022-10-25 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2
2 | 4 | 2 | 1 | 9 | 2 | 0 | 2.4.1.9.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 9 | 2 | 1 | 2.4.2.1.9.2.1 | BK-W046S-PEDCO-110-PI-TB-0009 | TBE FOR BURN PIT PIPES– W046S |  | BK-W046S-PEDCO-110-PI-TB-0011 | BK-W046S-PEDCO-110-PI-TB-0009 | BK | W046S | PEDCO | 110 | PI | TB | 0009 | F0Z-707689 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 2 | 0 | 0 | 0 | 2.4.2.2 |  | HVAC
2 | 4 | 2 | 2 | 1 | 0 | 0 | 2.4.2.2.1 |  | Main HVAC Equipment
2 | 4 | 2 | 2 | 1 | 1 | 0 | 2.4.2.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 2 | 1 | 1 | 1 | 2.4.2.2.1.1.1 | BK-W046S-PEDCO-110-HV-MR-0001 | PMR For Main HVAC Equipment - W046S |  | BK-W046S-PEDCO-110-HV-MR-0001 | BK-W046S-PEDCO-110-HV-MR-0001 | BK | W046S | PEDCO | 110 | HV | MR | 0001 | F0Z-707690 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 2 | 1 | 2 | 0 | 2.4.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 2 | 1 | 2 | 1 | 2.4.2.2.1.2.1 | BK-W046S-PEDCO-110-HV-TB-0001 | TBE For Main HVAC Equipment - W046S |  | BK-W046S-PEDCO-110-HV-TB-0001 | BK-W046S-PEDCO-110-HV-TB-0001 | BK | W046S | PEDCO | 110 | HV | TB | 0001 | F0Z-707691 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 3 | 0 | 0 | 0 | 2.4.2.3 |  | Pipeline
2 | 4 | 2 | 3 | 1 | 0 | 0 | 2.4.2.3.1 |  | Line Pipe
2 | 4 | 2 | 3 | 1 | 1 | 0 | 2.4.3.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 3 | 1 | 1 | 1 | 2.4.2.3.1.1.1 | BK-W046S-PEDCO-110-PL-MR-0001 | PMR For Line Pipes - W046S |  | BK-W046S-PEDCO-110-PL-MR-0001 | BK-W046S-PEDCO-110-PL-MR-0001 | BK | W046S | PEDCO | 110 | PL | MR | 0001 | F0Z-707692 | IFI | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-23 |  |  | D00 | IFI | T-1529 | 44857 | 1401/08/01 | T-1529 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296595 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1529 | 2022-10-23 | 1401/08/01 | T-1529 | 44857 | 1401/08/01 | [10 empty] | 1401-2294-296595 | 2022-11-05 | 1401/08/14 | 44874 | 1401/08/18 | AP
2 | 4 | 2 | 3 | 1 | 2 | 0 | 2.4.3.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 3 | 1 | 2 | 1 | 2.4.2.3.1.2.1 | BK-W046S-PEDCO-110-PL-TB-0001 | TBE For Line Pipes - W046S |  | BK-W046S-PEDCO-110-PL-TB-0001 | BK-W046S-PEDCO-110-PL-TB-0001 | BK | W046S | PEDCO | 110 | PL | TB | 0001 | F0Z-707693 | IFI | IFI | 2022-03-05 | 2022-03-10 | 2022-03-14 | 5 | 4 | 9 | IFI | 2022-05-28 | 2022-05-31 | 2022-06-07 | 3 | 7 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 44628 | 1400/12/17 | RJ-C4 | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 44634 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PL-TB-0001-D00 | [5 empty] | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PL-TB-0001-D00
2 | 4 | 2 | 3 | 2 | 0 | 0 | 2.4.2.3.2 |  | Line Support
2 | 4 | 2 | 3 | 2 | 1 | 0 | 2.4.3.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 3 | 2 | 1 | 1 | 2.4.2.3.2.1.1 | BK-W046S-PEDCO-110-PL-MR-0002 | PMR For Flow Line Support - W046S |  | BK-W046S-PEDCO-110-PL-MR-0002 | BK-W046S-PEDCO-110-PL-MR-0002 | BK | W046S | PEDCO | 110 | PL | MR | 0002 | F0Z-707694 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 3 | 2 | 2 | 0 | 2.4.3.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 3 | 2 | 2 | 1 | 2.4.2.3.2.2.1 | BK-W046S-PEDCO-110-PL-TB-0002 | TBE For Flow Line Support - W046S |  | BK-W046S-PEDCO-110-PL-TB-0002 | BK-W046S-PEDCO-110-PL-TB-0002 | BK | W046S | PEDCO | 110 | PL | TB | 0002 | F0Z-707695 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 4 | 0 | 0 | 0 | 2.4.2.4 |  | Control & Instrumentation
2 | 4 | 2 | 4 | 1 | 0 | 0 | 2.4.2.4.1 |  | Field Instrumentations
2 | 4 | 2 | 4 | 1 | 1 | 0 | 2.4.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 4 | 1 | 1 | 1 | 2.4.2.4.1.1.1 | BK-W046S-PEDCO-110-IN-MR-0002 | PMR For Field Instrumentations - W046S |  | BK-W046S-PEDCO-110-IN-MR-0002 | BK-W046S-PEDCO-110-IN-MR-0002 | BK | W046S | PEDCO | 110 | IN | MR | 0002 | F0Z-707696 | IFI | IFI | 2021-12-27 | 2022-01-21 | 2021-01-25 | 25 | -361 | -336 | IFI | 2022-08-13 | 2022-09-08 | 2022-09-13 | 26 | 5 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-13 |  |  | D01 | IFI | T-1218 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W046S-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 44557 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/10/01 | 44221 | 1400/11/05 | CM | [10 empty] | D01 | IFI | T-1218 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-IN-MR-0002_D00 | [5 empty] | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W046S-PEDCO-110-IN-MR-0002_D00
2 | 4 | 2 | 4 | 1 | 2 | 0 | 2.4.4.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 4 | 1 | 2 | 1 | 2.4.2.4.1.2.1 | BK-W046S-PEDCO-110-IN-TB-0002 | TBE/TBA For Field Instrumentations - W046S |  | BK-W046S-PEDCO-110-IN-TB-0002 | BK-W046S-PEDCO-110-IN-TB-0002 | BK | W046S | PEDCO | 110 | IN | TB | 0002 | F0Z-707697 | IFI | IFI | 2022-06-11 | 2022-06-21 | 2022-07-05 | 10 | 14 | 24 | IFI | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-26 |  |  | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | T-1012 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-05635 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-111541 | 2022-06-21 | 1401/03/31 | 44747 | 1401/04/14 | RJ | [10 empty] | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-IN-TB-0002_D00 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-IN-TB-0002_D00
2 | 4 | 2 | 4 | 2 | 0 | 0 | 2.4.2.4.2 |  | Instrument Bulk Items
2 | 4 | 2 | 4 | 2 | 1 | 0 | 2.4.4.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 4 | 2 | 1 | 1 | 2.4.2.4.2.1.1 | BK-W046S-PEDCO-110-IN-MR-0003 | PMR For Instrument Bulk Items - W046S |  | BK-W046S-PEDCO-110-IN-MR-0003 | BK-W046S-PEDCO-110-IN-MR-0003 | BK | W046S | PEDCO | 110 | IN | MR | 0003 | F0Z-707698 | IFI | IFI | 2022-01-30 | 2021-01-31 | 2022-02-01 | -364 | 366 | 2 | IFI | 2022-09-18 | 2022-09-21 | 2022-10-02 | 3 | 11 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-16 |  |  | D01 | IFI | T-1351 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W046S-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C2 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 44593 | 1400/11/12 | CM | [10 empty] | D01 | IFI | T-1351 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-IN-MR-0003_D00 | [5 empty] | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W046S-PEDCO-110-IN-MR-0003_D00
2 | 4 | 2 | 4 | 2 | 2 | 0 | 2.4.4.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 4 | 2 | 2 | 1 | 2.4.2.4.2.2.1 | BK-W046S-PEDCO-110-IN-TB-0003 | TBE/TBA For Instrument Bulk Items - W046S |  | BK-W046S-PEDCO-110-IN-TB-0003 | BK-W046S-PEDCO-110-IN-TB-0003 | BK | W046S | PEDCO | 110 | IN | TB | 0003 | F0Z-707699 | IFI | IFI | 2022-02-16 | 2022-03-19 | 2022-03-14 | 31 | -5 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-02 |  |  | D00 | IFI | T-0539 | 44594 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443275 | 44639 | 1400/12/19 | 44634 | 1400/12/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | [6 empty] | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 44634 | 1400/12/23 | CM
2 | 4 | 2 | 4 | 2 | 0 | 0 | 2.4.2.4.2 |  | Level Gauge
2 | 4 | 2 | 4 | 2 | 1 | 0 | 2.4.4.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 4 | 2 | 1 | 1 | 2.4.2.4.2.1.1 | BK-W046S-PEDCO-110-IN-MR-0004 | PMR For Level Gauge- W046S |  | BK-W046S-PEDCO-110-IN-MR-0004 | BK-W046S-PEDCO-110-IN-MR-0004 | BK | W046S | PEDCO | 110 | IN | MR | 0004 | F0Z-709411 | IFI | IFI | 2022-01-30 | 2021-01-31 | 2022-02-01 | -364 | 366 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-16 |  |  | D00 | IFI | T-0471 | 44577 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C2 | 0 | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C2 | 0 | 1400-2294-390714 | 44227 | 1400/11/11 | 44593 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C2 |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C2 |  | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 44593 | 1400/11/12 | CM
2 | 4 | 2 | 4 | 2 | 2 | 0 | 2.4.4.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 4 | 2 | 2 | 1 | 2.4.2.4.2.2.1 | BK-W046S-PEDCO-110-IN-TB-0004 | TBE/TBA For Level Gauge- W046S |  | BK-W046S-PEDCO-110-IN-TB-0004 | BK-W046S-PEDCO-110-IN-TB-0004 | BK | W046S | PEDCO | 110 | IN | TB | 0004 | F0Z-709412 | IFI | IFI | 2022-02-16 | 2022-03-19 | 2022-03-14 | 31 | -5 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-02 |  |  | D00 | IFI | T-0539 | 44594 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443275 | 44639 | 1400/12/19 | 44634 | 1400/12/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | [6 empty] | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 44634 | 1400/12/23 | CM
2 | 4 | 2 | 5 | 0 | 0 | 0 | 2.4.2.5 |  | Safety & Fire Fighting
2 | 4 | 2 | 5 | 1 | 0 | 0 | 2.4.2.5.1 |  | Fire Fighting and Safety Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 5 | 1 | 1 | 0 | 2.4.5.1.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 5 | 1 | 1 | 1 | 2.4.2.5.1.1.1 | BK-W046S-PEDCO-110-SA-MR-0001 | PMR For Fire Fighting and Safety Equipment - W046S |  | BK-W046S-PEDCO-110-SA-MR-0001 | BK-W046S-PEDCO-110-SA-MR-0001 | BK | W046S | PEDCO | 110 | SA | MR | 0001 | F0Z-707700 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 5 | 1 | 2 | 0 | 2.4.5.1.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 5 | 1 | 2 | 1 | 2.4.2.5.1.2.1 | BK-W046S-PEDCO-110-SA-TB-0001 | TBE For Fire Fighting and Safety Equipment - W046S |  | BK-W046S-PEDCO-110-SA-TB-0001 | BK-W046S-PEDCO-110-SA-TB-0001 | BK | W046S | PEDCO | 110 | SA | TB | 0001 | F0Z-707701 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 5 | 2 | 0 | 0 | 2.4.2.5.2 |  | Safety Sign | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 5 | 2 | 1 | 0 | 2.4.5.2.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 5 | 2 | 1 | 1 | 2.4.2.5.2.1.1 | BK-W046S-PEDCO-110-SA-MR-0002 | PMR For Fire Safety Sign - W046S |  | BK-W046S-PEDCO-110-SA-MR-0002 | BK-W046S-PEDCO-110-SA-MR-0002 | BK | W046S | PEDCO | 110 | SA | MR | 0002 | F0Z-707702 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 5 | 2 | 2 | 0 | 2.4.5.2.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 5 | 2 | 2 | 1 | 2.4.2.5.2.2.1 | BK-W046S-PEDCO-110-SA-TB-0002 | TBE For Fire Safety Sign - W046S |  | BK-W046S-PEDCO-110-SA-TB-0002 | BK-W046S-PEDCO-110-SA-TB-0002 | BK | W046S | PEDCO | 110 | SA | TB | 0002 | F0Z-707703 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 0 | 0 | 0 | 2.4.2.6 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 1 | 0 | 0 | 2.4.2.6.1 |  | Transformers
2 | 4 | 2 | 6 | 1 | 1 | 0 | 2.4.6.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 1 | 1 | 1 | 2.4.2.6.1.1.1 | BK-W046S-PEDCO-110-EL-MR-0001 | PMR For Transformers - W046S |  | BK-W046S-PEDCO-110-EL-MR-0001 | BK-W046S-PEDCO-110-EL-MR-0001 | BK | W046S | PEDCO | 110 | EL | MR | 0001 | F0Z-707704 | AFD | IFC | 2022-07-27 | 2022-08-03 | 2022-08-09 | 7 | 6 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-07-13 |  |  | D00 | IFC | T-1156 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05235 | 44767 | 1401/05/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-167067 | 44776 | 1401/05/12 | 44782 | 1401/05/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1156 | 2022-07-13 | 1401/04/22 |  |  |  | BK-SUR-ENG-ELE-01-05235 | 44767 | 1401/05/03 | CM-C3 | [6 empty] | 1401-2294-167067 | 2022-08-03 | 1401/05/12 | 44782 | 1401/05/18 | AP
2 | 4 | 2 | 6 | 1 | 2 | 0 | 2.4.6.1.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 1 | 2 | 1 | 2.4.2.6.1.2.1 | BK-W046S-PEDCO-110-EL-TB-0001 | TBE For Transformers - W046S |  | BK-W046S-PEDCO-110-EL-TB-0001 | BK-W046S-PEDCO-110-EL-TB-0001 | BK | W046S | PEDCO | 110 | EL | TB | 0001 | F0Z-707705 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 2 | 0 | 0 | 2.4.2.6.2 |  | LV Switchgear & MCC
2 | 4 | 2 | 6 | 2 | 1 | 0 | 2.4.6.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 2 | 1 | 1 | 2.4.2.6.2.1.1 | BK-W046S-PEDCO-110-EL-MR-0002 | PMR For LV Switchgear & MCC - W046S |  | BK-W046S-PEDCO-110-EL-MR-0002 | BK-W046S-PEDCO-110-EL-MR-0002 | BK | W046S | PEDCO | 110 | EL | MR | 0002 | F0Z-707706 | IFI | IFI | 2022-09-25 | 2022-10-05 | 2022-10-08 | 10 | 3 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-11 |  |  | D00 | IFI | T-1392 | 44815 | 1401/06/20 | T-1392 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05753 | 44828 | 1401/07/02 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249408 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1392 | 2022-09-11 | 1401/06/20 | T-1392 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05753 | 44828 | 1401/07/02 | CM-C2 | [6 empty] | 1401-2294-249408 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 4 | 2 | 6 | 2 | 2 | 0 | 2.4.6.2.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 2 | 2 | 1 | 2.4.2.6.2.2.1 | BK-W046S-PEDCO-110-EL-TB-0002 | TBE For LV Switchgear & MCC - W046S |  | BK-W046S-PEDCO-110-EL-TB-0002 | BK-W046S-PEDCO-110-EL-TB-0002 | BK | W046S | PEDCO | 110 | EL | TB | 0002 | F0Z-707707 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 3 | 0 | 0 | 2.4.2.6.3 |  | Emergency Diesel Generator
2 | 4 | 2 | 6 | 3 | 1 | 0 | 2.4.6.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 3 | 1 | 1 | 2.4.2.6.3.1.1 | BK-W046S-PEDCO-110-EL-MR-0003 | PMR For Emergency Diesel Generator - W046S |  | BK-W046S-PEDCO-110-EL-MR-0003 | BK-W046S-PEDCO-110-EL-MR-0003 | BK | W046S | PEDCO | 110 | EL | MR | 0003 | F0Z-707708 | IFI | IFI | 2022-09-03 | 2022-09-08 | 2022-09-12 | 5 | 4 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-20 |  |  | D00 | IFI | T-1293 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216140 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1293 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | [6 empty] | 1401-2294-216140 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | AP
2 | 4 | 2 | 6 | 3 | 2 | 0 | 2.4.6.3.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 3 | 2 | 1 | 2.4.2.6.3.2.1 | BK-W046S-PEDCO-110-EL-TB-0003 | TBE For Emergency Diesel Generator - W046S |  | BK-W046S-PEDCO-110-EL-TB-0003 | BK-W046S-PEDCO-110-EL-TB-0003 | BK | W046S | PEDCO | 110 | EL | TB | 0003 | F0Z-707709 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 4 | 0 | 0 | 2.4.2.6.4 |  | UPS System
2 | 4 | 2 | 6 | 4 | 1 | 0 | 2.4.6.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 4 | 1 | 1 | 2.4.2.6.4.1.1 | BK-W046S-PEDCO-110-EL-MR-0004 | PMR For UPS System - W046S |  | BK-W046S-PEDCO-110-EL-MR-0004 | BK-W046S-PEDCO-110-EL-MR-0004 | BK | W046S | PEDCO | 110 | EL | MR | 0004 | F0Z-707710 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 4 | 2 | 0 | 2.4.6.4.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 4 | 2 | 1 | 2.4.2.6.4.2.1 | BK-W046S-PEDCO-110-EL-TB-0004 | TBE For UPS System - W046S |  | BK-W046S-PEDCO-110-EL-TB-0004 | BK-W046S-PEDCO-110-EL-TB-0004 | BK | W046S | PEDCO | 110 | EL | TB | 0004 | F0Z-707711 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 5 | 0 | 0 | 2.4.2.6.5 |  | DC Charger
2 | 4 | 2 | 6 | 5 | 1 | 0 | 2.4.6.5.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 5 | 1 | 1 | 2.4.2.6.5.1.1 | BK-W046S-PEDCO-110-EL-MR-0005 | PMR For DC Charger - W046S |  | BK-W046S-PEDCO-110-EL-MR-0005 | BK-W046S-PEDCO-110-EL-MR-0005 | BK | W046S | PEDCO | 110 | EL | MR | 0005 | F0Z-707712 | IFI | IFI | 2022-05-10 | 2022-05-29 | 2022-05-30 | 19 | 1 | 20 | IFI | 2022-09-07 | 2022-09-08 | 2022-09-12 | 1 | 4 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-26 |  |  | D01 | IFI | T-1311 | 44797 | 1401/06/01 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W046S-PEDCO-110-EL-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-W046S-PEDCO-110-EL-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0864 | 2022-04-26 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04211 | 44691 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78867 | 2022-05-29 | 1401/03/08 | 44711 | 1401/03/09 | CM | [10 empty] | D01 | IFI | T-1311 | 44797 | 1401/06/01 |  |  |  | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W046S-PEDCO-110-EL-MR-0005_D00 | [5 empty] | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-W046S-PEDCO-110-EL-MR-0005_D00
2 | 4 | 2 | 6 | 5 | 2 | 0 | 2.4.6.5.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 5 | 2 | 1 | 2.4.2.6.5.2.1 | BK-W046S-PEDCO-110-EL-TB-0005 | TBE For DC Charger - W046S |  | BK-W046S-PEDCO-110-EL-TB-0005 | BK-W046S-PEDCO-110-EL-TB-0005 | BK | W046S | PEDCO | 110 | EL | TB | 0005 | F0Z-707713 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 6 | 0 | 0 | 2.4.2.6.6 |  | Capacitor Bank
2 | 4 | 2 | 6 | 6 | 1 | 0 | 2.4.6.6.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 6 | 1 | 1 | 2.4.2.6.6.1.1 | BK-W046S-PEDCO-110-EL-MR-0006 | PMR For Capacitor Bank - W046S |  | BK-W046S-PEDCO-110-EL-MR-0006 | BK-W046S-PEDCO-110-EL-MR-0006 | BK | W046S | PEDCO | 110 | EL | MR | 0006 | F0Z-707714 | IFI | IFI | 2022-08-13 | 2022-08-18 | 2022-08-20 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFI | T-1215 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183488 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1215 | 2022-07-30 | 1401/05/08 |  |  |  | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | [6 empty] | 1401-2294-183488 | 2022-08-18 | 1401/05/27 | 44793 | 1401/05/29 | RJ
2 | 4 | 2 | 6 | 6 | 2 | 0 | 2.4.6.6.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 6 | 2 | 1 | 2.4.2.6.6.2.1 | BK-W046S-PEDCO-110-EL-TB-0006 | TBE For Capacitor Bank - W046S |  | BK-W046S-PEDCO-110-EL-TB-0006 | BK-W046S-PEDCO-110-EL-TB-0006 | BK | W046S | PEDCO | 110 | EL | TB | 0006 | F0Z-707715 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 7 | 0 | 0 | 2.4.2.6.7 |  | Lighting & Distribution Main Panels
2 | 4 | 2 | 6 | 7 | 1 | 0 | 2.4.6.7.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 7 | 1 | 1 | 2.4.2.6.7.1.1 | BK-W046S-PEDCO-110-EL-MR-0007 | PMR For Lighting & Distribution Main Panels - W046S |  | BK-W046S-PEDCO-110-EL-MR-0007 | BK-W046S-PEDCO-110-EL-MR-0007 | BK | W046S | PEDCO | 110 | EL | MR | 0007 | F0Z-707716 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 7 | 2 | 0 | 2.4.6.7.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 7 | 2 | 1 | 2.4.2.6.7.2.1 | BK-W046S-PEDCO-110-EL-TB-0007 | TBE For Lighting & Distribution Main Panels - W046S |  | BK-W046S-PEDCO-110-EL-TB-0007 | BK-W046S-PEDCO-110-EL-TB-0007 | BK | W046S | PEDCO | 110 | EL | TB | 0007 | F0Z-707717 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 8 | 0 | 0 | 2.4.2.6.8 |  | Earthing & Lightning System
2 | 4 | 2 | 6 | 8 | 1 | 0 | 2.4.6.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 8 | 1 | 1 | 2.4.2.6.8.1.1 | BK-W046S-PEDCO-110-EL-MR-0008 | PMR For Earthing & Lightning System - W046S |  | BK-W046S-PEDCO-110-EL-MR-0008 | BK-W046S-PEDCO-110-EL-MR-0008 | BK | W046S | PEDCO | 110 | EL | MR | 0008 | F0Z-707718 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 8 | 2 | 0 | 2.4.6.8.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 8 | 2 | 1 | 2.4.2.6.8.2.1 | BK-W046S-PEDCO-110-EL-TB-0008 | TBE For Earthing & Lightning System - W046S |  | BK-W046S-PEDCO-110-EL-TB-0008 | BK-W046S-PEDCO-110-EL-TB-0008 | BK | W046S | PEDCO | 110 | EL | TB | 0008 | F0Z-707719 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 9 | 0 | 0 | 2.4.2.6.9 |  | Lighting and Small Power Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 9 | 1 | 0 | 2.4.6.9.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 9 | 1 | 1 | 2.4.2.6.9.1.1 | BK-W046S-PEDCO-110-EL-MR-0009 | PMR For Lighting and Small Power Equipment - W046S |  | BK-W046S-PEDCO-110-EL-MR-0009 | BK-W046S-PEDCO-110-EL-MR-0009 | BK | W046S | PEDCO | 110 | EL | MR | 0009 | F0Z-707720 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 9 | 2 | 0 | 2.4.6.9.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 9 | 2 | 1 | 2.4.2.6.9.2.1 | BK-W046S-PEDCO-110-EL-TB-0009 | TBE For Lighting and Small Power Equipment - W046S |  | BK-W046S-PEDCO-110-EL-TB-0009 | BK-W046S-PEDCO-110-EL-TB-0009 | BK | W046S | PEDCO | 110 | EL | TB | 0009 | F0Z-707721 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 10 | 0 | 0 | 2.4.2.6.10 |  | Tray/Ladder and Accessories | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 10 | 1 | 0 | 2.4.6.10.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 10 | 1 | 1 | 2.4.2.6.10.1.1 | BK-W046S-PEDCO-110-EL-MR-0010 | PMR For Tray/Ladder and Accessories - W046S |  | BK-W046S-PEDCO-110-EL-MR-0010 | BK-W046S-PEDCO-110-EL-MR-0010 | BK | W046S | PEDCO | 110 | EL | MR | 0010 | F0Z-707722 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 10 | 2 | 0 | 2.4.6.10.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 10 | 2 | 1 | 2.4.2.6.10.2.1 | BK-W046S-PEDCO-110-EL-TB-0010 | TBE For Tray/Ladder and Accessories - W046S |  | BK-W046S-PEDCO-110-EL-TB-0010 | BK-W046S-PEDCO-110-EL-TB-0010 | BK | W046S | PEDCO | 110 | EL | TB | 0010 | F0Z-707723 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 11 | 0 | 0 | 2.4.2.6.11 |  | Power & Control Cables | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 11 | 1 | 0 | 2.4.6.11.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 11 | 1 | 1 | 2.4.2.6.11.1.1 | BK-W046S-PEDCO-110-EL-MR-0011 | PMR For Power & Control Cables - W046S |  | BK-W046S-PEDCO-110-EL-MR-0011 | BK-W046S-PEDCO-110-EL-MR-0011 | BK | W046S | PEDCO | 110 | EL | MR | 0011 | F0Z-707724 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 6 | 11 | 2 | 0 | 2.4.6.11.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 11 | 2 | 1 | 2.4.2.6.11.2.1 | BK-W046S-PEDCO-110-EL-TB-0011 | TBE For Power & Control Cables - W046S |  | BK-W046S-PEDCO-110-EL-TB-0011 | BK-W046S-PEDCO-110-EL-TB-0011 | BK | W046S | PEDCO | 110 | EL | TB | 0011 | F0Z-707725 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 12 | 0 | 0 | 2.4.2.6.12 |  | Electrical Bulk Items
2 | 4 | 2 | 6 | 12 | 1 | 0 | 2.4.6.12.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 12 | 1 | 1 | 2.4.2.6.12.1.1 | BK-W046S-PEDCO-110-EL-MR-0012 | PMR For Electrical Bulk Items - W046S |  | BK-W046S-PEDCO-110-EL-MR-0012 | BK-W046S-PEDCO-110-EL-MR-0012 | BK | W046S | PEDCO | 110 | EL | MR | 0012 | F0Z-707726 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 12 | 2 | 0 | 2.4.6.12.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 12 | 2 | 1 | 2.4.2.6.12.2.1 | BK-W046S-PEDCO-110-EL-TB-0012 | TBE For Electrical Bulk Items - W046S |  | BK-W046S-PEDCO-110-EL-TB-0012 | BK-W046S-PEDCO-110-EL-TB-0012 | BK | W046S | PEDCO | 110 | EL | TB | 0012 | F0Z-707727 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 13 | 0 | 0 | 2.4.2.6.13 |  | Transmission Over head Line
2 | 4 | 2 | 6 | 13 | 1 | 0 | 2.4.6.13.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 13 | 1 | 1 | 2.4.2.6.13.1.1 | BK-W046S-PEDCO-110-EL-MR-0013 | PMR For Transmission Over head Line - W046S |  | BK-W046S-PEDCO-110-EL-MR-0013 | BK-W046S-PEDCO-110-EL-MR-0013 | BK | W046S | PEDCO | 110 | EL | MR | 0013 | F0Z-707728 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 6 | 13 | 2 | 0 | 2.4.6.13.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 6 | 13 | 2 | 1 | 2.4.2.6.13.2.1 | BK-W046S-PEDCO-110-EL-TB-0013 | TBE For Transmission Over head Line - W046S |  | BK-W046S-PEDCO-110-EL-TB-0013 | BK-W046S-PEDCO-110-EL-TB-0013 | BK | W046S | PEDCO | 110 | EL | TB | 0013 | F0Z-707729 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 7 | 0 | 0 | 0 | 2.4.2.7 |  | Structure
2 | 4 | 2 | 7 | 1 | 0 | 0 | 2.4.2.7.1 |  | Steel Structure Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 7 | 1 | 1 | 0 | 2.4.7.1.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 7 | 1 | 1 | 1 | 2.4.2.7.1.1.1 | BK-W046S-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - W046S |  | BK-W046S-PEDCO-110-ST-MR-0001 | BK-W046S-PEDCO-110-ST-MR-0001 | BK | W046S | PEDCO | 110 | ST | MR | 0001 | F0Z-707730 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 7 | 1 | 2 | 0 | 2.4.7.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 7 | 1 | 2 | 1 | 2.4.2.7.1.2.1 | BK-W046S-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - W046S |  | BK-W046S-PEDCO-110-ST-TB-0001 | BK-W046S-PEDCO-110-ST-TB-0001 | BK | W046S | PEDCO | 110 | ST | TB | 0001 | F0Z-707731 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 7 | 2 | 0 | 0 | 2.4.2.7.2 |  | Anchor Bolts | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 7 | 2 | 1 | 0 | 2.4.7.2.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 7 | 2 | 1 | 1 | 2.4.2.7.2.1.1 | BK-W046S-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - W046S |  | BK-W046S-PEDCO-110-ST-MR-0002 | BK-W046S-PEDCO-110-ST-MR-0002 | BK | W046S | PEDCO | 110 | ST | MR | 0002 | F0Z-707732 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 7 | 2 | 2 | 0 | 2.4.7.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 7 | 2 | 2 | 1 | 2.4.2.7.2.2.1 | BK-W046S-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - W046S |  | BK-W046S-PEDCO-110-ST-TB-0002 | BK-W046S-PEDCO-110-ST-TB-0002 | BK | W046S | PEDCO | 110 | ST | TB | 0002 | F0Z-707733 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 7 | 3 | 0 | 0 | 2.4.2.7.3 |  | Blast Proof Doors | [61 empty] | Moved to Field
2 | 4 | 2 | 7 | 3 | 1 | 0 | 2.4.7.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 7 | 3 | 1 | 1 | 2.4.2.7.3.1.1 | BK-W046S-PEDCO-110-ST-MR-0003 | PMR For Blast Proof Doors - W046S |  | BK-W046S-PEDCO-110-ST-MR-0003 | BK-W046S-PEDCO-110-ST-MR-0003 | BK | W046S | PEDCO | 110 | ST | MR | 0003 | F0Z-707734 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 7 | 3 | 2 | 0 | 2.4.7.3.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 7 | 3 | 2 | 1 | 2.4.2.7.3.2.1 | BK-W046S-PEDCO-110-ST-TB-0003 | TBE For Blast Proof Doors - W046S |  | BK-W046S-PEDCO-110-ST-TB-0003 | BK-W046S-PEDCO-110-ST-TB-0003 | BK | W046S | PEDCO | 110 | ST | TB | 0003 | F0Z-707735 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 8 | 0 | 0 | 0 | 2.4.2.8 |  | Civil
2 | 4 | 2 | 8 | 1 | 0 | 0 | 2.4.2.8.1 |  | Geomembrane | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 8 | 1 | 1 | 0 | 2.4.8.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 8 | 1 | 1 | 1 | 2.4.2.8.1.1.1 | BK-W046S-PEDCO-110-CV-MR-0001 | PMR For Geomembrane - W046S |  | BK-W046S-PEDCO-110-CV-MR-0001 | BK-W046S-PEDCO-110-CV-MR-0001 | BK | W046S | PEDCO | 110 | CV | MR | 0001 | F0Z-707736 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 8 | 1 | 2 | 0 | 2.4.8.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 8 | 1 | 2 | 1 | 2.4.2.8.1.2.1 | BK-W046S-PEDCO-110-CV-TB-0001 | TBE For Geomembrane - W046S |  | BK-W046S-PEDCO-110-CV-TB-0001 | BK-W046S-PEDCO-110-CV-TB-0001 | BK | W046S | PEDCO | 110 | CV | TB | 0001 | F0Z-707737 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 2 | 8 | 2 | 0 | 0 | 2.4.2.8.2 |  | Geotextile | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 2 | 8 | 2 | 1 | 0 | 2.4.8.2.1 |  | Purchase Material Requisition (PMR)
2 | 4 | 2 | 8 | 2 | 1 | 1 | 2.4.2.8.2.1.1 | BK-W046S-PEDCO-110-CV-MR-0002 | PMR For Geotextile - W046S |  | BK-W046S-PEDCO-110-CV-MR-0002 | BK-W046S-PEDCO-110-CV-MR-0002 | BK | W046S | PEDCO | 110 | CV | MR | 0002 | F0Z-707738 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 2 | 8 | 2 | 2 | 0 | 2.4.8.2.2 |  | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 8 | 2 | 2 | 1 | 2.4.2.8.2.2.1 | BK-W046S-PEDCO-110-CV-TB-0002 | TBE For Geotextile - W046S |  | BK-W046S-PEDCO-110-CV-TB-0002 | BK-W046S-PEDCO-110-CV-TB-0002 | BK | W046S | PEDCO | 110 | CV | TB | 0002 | F0Z-707739 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 3 | 0 | 0 | 0 | 0 | 2.4.3 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 3 | 0 | 0 | 1 | 0 | 2.4.3.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 3 | 0 | 0 | 1 | 1 | 2.4.3.1.1 | BK-W046S-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - W046S |  | BK-W046S-PEDCO-110-CO-PR-0001 | BK-W046S-PEDCO-110-CO-PR-0001 | BK | W046S | PEDCO | 110 | CO | PR | 0001 | F0Z-707740 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 4 | 0 | 0 | 0 | 0 | 2.4.4 |  | Field Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 4 | 0 | 0 | 1 | 0 | 2.4.4.1 |  | Query
2 | 4 | 4 | 0 | 0 | 1 | 1 | 2.4.4.1.1 | BK-W046S-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-W046S-PEDCO-110-GE-TQ-0001 | BK-W046S-PEDCO-110-GE-TQ-0001 | BK | W046S | PEDCO | 110 | GE | TQ | 0001 | F7Z-707741 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 4 | 0 | 0 | 2 | 0 | 2.4.4.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 4 | 0 | 0 | 2 | 1 | 2.4.4.2.1 | BK-W046S-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W046S |  | BK-W046S-PEDCO-110-GE-DO-0001 | BK-W046S-PEDCO-110-GE-DO-0001 | BK | W046S | PEDCO | 110 | GE | DO | 0001 | F0Z-707742 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 5 | 0 | 0 | 0 | 0 | 2.4.5 |  | Engineering Final Documentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 5 | 0 | 0 | 1 | 0 | 2.4.5.1 |  | Manual | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 5 | 0 | 0 | 1 | 1 | 2.4.5.1.1 | BK-W046S-PEDCO-110-GE-ML-0001 | Operating Manual - W046S |  | BK-W046S-PEDCO-110-GE-ML-0001 | BK-W046S-PEDCO-110-GE-ML-0001 | BK | W046S | PEDCO | 110 | GE | ML | 0001 | F7Z-707743 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 4 | 5 | 0 | 0 | 2 | 0 | 2.4.5.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 4 | 5 | 0 | 0 | 2 | 1 | 2.4.5.2.1 | BK-W046S-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W046S |  | BK-W046S-PEDCO-110-GE-DO-0001 | [8 empty] | F0Z-707742 |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 4 | 5 | 0 | 0 | 2 | 2 | 2.4.5.2.2 | BK-W046S-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - W046S |  | BK-W046S-PEDCO-110-GE-DO-0002 | BK-W046S-PEDCO-110-GE-DO-0002 | BK | W046S | PEDCO | 110 | GE | DO | 0002 | F0Z-707744 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 5 | 0 | 0 | 0 | 0 | 0 | 2.5 |  | Package 04-New Well # W035 (Bangestan) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 0 | 0 | 0 | 0 | 2.5.1 |  | Detail Design | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 1 | 0 | 0 | 0 | 2.5.1.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 1 | 1 | 0 | 0 | 2.5.1.1.1 |  | Drawing/Diagram
2 | 5 | 1 | 1 | 1 | 0 | 1 | 2.5.1.1.1 | BK-W035-PEDCO-110-PR-PF-0001 | Process Flow Diagram - W035 |  | BK-W035-PEDCO-110-PR-PF-0001 | BK-W035-PEDCO-110-PR-PF-0001 | BK | W035 | PEDCO | 110 | PR | PF | 0001 | F2A-707745 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-16 | 2022-06-02 | 2022-06-06 | 198 | 4 | 202 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-02 |  |  | D02 | IFA | T-1266 | 44783 | 1401/05/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PF-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W035-PEDCO-110-PR-PF-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 44447 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0205 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-PCS-00-02020 | 44516 | 1400/08/25 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PF-0001_D00 | [5 empty] | 1401-2294-87488 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-PF-0001_D00 | [9 empty] | D02 | IFA | T-1266 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PF-0001 _D01 | [5 empty] | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W035-PEDCO-110-PR-PF-0001 _D01
2 | 5 | 1 | 1 | 1 | 0 | 2 | 2.5.1.1.1 | BK-W035-PEDCO-110-PR-PI-0001 | P&ID - W035 |  | BK-W035-PEDCO-110-PR-PI-0001 | BK-W035-PEDCO-110-PR-PI-0001 | BK | W035 | PEDCO | 110 | PR | PI | 0001 | F2A-707746 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | IFA | 2022-09-20 | 2022-11-19 | 2022-11-21 | 60 | 2 | 62 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-01 |  |  | D04 | IFA | T-1368 | 44810 | 1401/06/15 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 44447 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0201 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 44516 | 1400/08/25 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 44564 | 1400/10/13 | CM-C3 | PEDCO-BK-W035-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 44560 | 1400/10/09 | 44564 | 1400/10/13 | RJ | NISOC-BK-W035-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-PI-0001_D02 | [9 empty] | D04 | IFA | T-1368 | 44810 | 1401/06/15 |  |  |  | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PI-0001_D03 | [5 empty] | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-PI-0001_D03
2 | 5 | 1 | 1 | 2 | 0 | 0 | 2.5.1.1.2 |  | List
2 | 5 | 1 | 1 | 2 | 0 | 1 | 2.5.1.1.2 | BK-W035-PEDCO-110-PR-LI-0001 | Line List - W035 |  | BK-W035-PEDCO-110-PR-LI-0001 | BK-W035-PEDCO-110-PR-LI-0001 | BK | W035 | PEDCO | 110 | PR | LI | 0001 | F0Z-707747 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-22 | 2021-11-27 | 2021-11-29 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-06-27 | 0 | 166 | -44739 | -44573 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-08 |  |  | D02 | IFA | T-0403 | 44559 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-LI-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 44447 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0217 | 44508 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 44520 | 1400/08/29 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 44527 | 1400/09/06 | 44529 | 1400/09/08 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-LI-0001 _D01 | [5 empty] | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-LI-0001_D01
2 | 5 | 1 | 1 | 3 | 0 | 0 | 2.5.1.1.3 |  | Report | [153 empty] | 1400/09/06
2 | 5 | 1 | 1 | 3 | 0 | 1 | 2.5.1.1.3 | BK-W035-PEDCO-110-PR-RT-0001 | Flow line Hydraulic Calculation Report |  | BK-W035-PEDCO-110-PR-RT-0001 | BK-W035-PEDCO-110-PR-RT-0001 | BK | W035 | PEDCO | 110 | PR | RT | 0001 | F0Z-707748 | IFA | IFC | 2021-11-13 | 2021-11-14 | 2021-11-17 | 1 | 3 | 4 | IFA | 2022-01-15 | 2021-02-01 | 2022-02-05 | -348 | 369 | 21 | IFA | 2022-03-08 | 2022-03-10 | 2022-03-13 | 2 | 3 | 5 | IFA | 2022-05-14 | 2022-06-02 | 2022-06-06 | 19 | 4 | 23 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | AFC | 2022-10-22 | 2022-11-19 | 2022-11-20 | 28 | 1 | 29 | [7 empty] | Modify | 2021-10-30 | 2022-10-08 |  | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 44514 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 44517 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 44562 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 44228 | 1400/11/12 | 44597 | 1400/11/16 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 44614 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 44627 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 44630 | 1400/12/19 | 44633 | 1400/12/22 | CM | NISON-CRS-BK-W035-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 44681 | 1401/02/10 | T-0878 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 44709 | 1401/03/07 | AP | PEDCO-CRS-BK-W035-PEDCO-110-PR-RT-0001_D02 | [5 empty] | 1401-2294-87489 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-RT-0001_D02 | [9 empty] | D04 | IFA | T-1267 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05524 | 44797 | 1401/06/02 | AP | [6 empty] | 1401-2294-235783 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W035-PEDCO-110-PR-RT-0001_D03 | [9 empty] | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | [10 empty] | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP
2 | 5 | 1 | 1 | 4 | 0 | 0 | 2.5.1.1.4 |  | Data Sheet
2 | 5 | 1 | 1 | 4 | 0 | 1 | 2.5.1.1 | BK-W035-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - W035 |  | BK-W035-PEDCO-110-PR-DT-0001 | BK-W035-PEDCO-110-PR-DT-0001 | BK | W035 | PEDCO | 110 | PR | DT | 0001 | F0Z-707749 | AFC | IFC | 2022-04-26 | 2022-05-08 | 2022-05-14 | 12 | 6 | 18 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-12 |  |  | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W035-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 44695 | 1401/02/24 | CM | [10 empty] | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-DT-0001_D00 | [11 empty] | NISOC-CRS-BK-W035-PEDCO-110-PR-DT-0001_D00
2 | 5 | 1 | 2 | 0 | 0 | 0 | 2.5.1.2 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 2 | 1 | 0 | 0 | 2.5.1.2.1 |  | Drawing/Diagram
2 | 5 | 1 | 2 | 1 | 0 | 1 | 2.5.1.2.1 | BK-W035-PEDCO-110-PI-DW-0001 | Plot Plan Drawing - W035 |  | BK-W035-PEDCO-110-PI-DW-0001 | BK-W035-PEDCO-110-PI-DW-0001 | BK | W035 | PEDCO | 110 | PI | DW | 0001 | F5A-707750 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 5 | 1 | 2 | 1 | 0 | 2 | 2.5.1.2.1 | BK-W035-PEDCO-110-PI-DW-0002 | Piping Plan - W035 |  | BK-W035-PEDCO-110-PI-DW-0002 | BK-W035-PEDCO-110-PI-DW-0002 | BK | W035 | PEDCO | 110 | PI | DW | 0002 | F4L-707751 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 5 | 1 | 2 | 1 | 0 | 3 | 2.5.1.2.1 | BK-W035-PEDCO-110-PI-DW-0003 | Isometric Drawings - W035 |  | BK-W035-PEDCO-110-PI-DW-0003 | BK-W035-PEDCO-110-PI-DW-0003 | BK | W035 | PEDCO | 110 | PI | DW | 0003 | F2L-707752 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 5 | 1 | 2 | 1 | 0 | 4 | 2.5.1.2.1 | BK-W035-PEDCO-110-PI-DG-0001 | Material Flow Diagram - W035 |  | BK-W035-PEDCO-110-PI-DG-0001 | BK-W035-PEDCO-110-PI-DG-0001 | BK | W035 | PEDCO | 110 | PI | DG | 0001 | F2A-707753 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 2022-06-28 | 2022-07-05 | 34 | 7 | 41 | IFA | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-08 |  |  | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W035-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 44521 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PI-DG-0001_D00 | [5 empty] | 1401-2294-122170 | 44740 | 1401/04/07 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W035-PEDCO-110-PI-DG-0001_D00 | [9 empty] | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PI-DG-0001_D01 | [11 empty] | NISOC-CRS-BK-W035-PEDCO-110-PI-DG-0001_D01
2 | 5 | 1 | 2 | 2 | 0 | 0 | 2.5.1.2.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 2 | 2 | 0 | 1 | 2.5.1.2.2 | BK-W035-PEDCO-110-PI-LI-0001 | Piping Support List - W035 |  | BK-W035-PEDCO-110-PI-LI-0001 | BK-W035-PEDCO-110-PI-LI-0001 | BK | W035 | PEDCO | 110 | PI | LI | 0001 | F0Z-707754 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 5 | 1 | 2 | 2 | 0 | 2 | 2.5.1.2.2 | BK-W035-PEDCO-110-PI-LI-0002 | Critical Line List - W035 |  | BK-W035-PEDCO-110-PI-LI-0002 | BK-W035-PEDCO-110-PI-LI-0002 | BK | W035 | PEDCO | 110 | PI | LI | 0002 | F0Z-707755 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 5 | 1 | 2 | 3 | 0 | 0 | 2.5.1.2.3 |  | Report
2 | 5 | 1 | 2 | 3 | 0 | 1 | 2.5.1.2.3 | BK-W035-PEDCO-110-PI-RT-0001 | PDMS Model Review Report (60%) - W035 |  | BK-W035-PEDCO-110-PI-RT-0001 | BK-W035-PEDCO-110-PI-RT-0001 | BK | W035 | PEDCO | 110 | PI | RT | 0001 | F0Z-707756 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 5 | 1 | 2 | 3 | 0 | 2 | 2.5.1.2.3 | BK-W035-PEDCO-110-PI-RT-0002 | PDMS Model Review Report (90%) - W035 |  | BK-W035-PEDCO-110-PI-RT-0002 | BK-W035-PEDCO-110-PI-RT-0002 | BK | W035 | PEDCO | 110 | PI | RT | 0002 | F0Z-707757 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 5 | 1 | 2 | 4 | 0 | 0 | 2.5.1.2.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 2 | 4 | 0 | 1 | 2.5.1.2 | BK-W035-PEDCO-110-PI-MT-0001 | MTO For Pipes - W035 |  | BK-W035-PEDCO-110-PI-MT-0001 | BK-W035-PEDCO-110-PI-MT-0001 | BK | W035 | PEDCO | 110 | PI | MT | 0001 | F8Z-707758 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-25 |  |  | D00 | IFI | T-1545 | 44859 | 1401/08/03 | T-1545 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1545 | 2022-10-25 | 1401/08/03 | T-1545 | 44859 | 1401/08/03
2 | 5 | 1 | 2 | 4 | 0 | 2 | 2.5.1.2 | BK-W035-PEDCO-110-PI-MT-0002 | MTO For Fittings - W035 |  | BK-W035-PEDCO-110-PI-MT-0002 | BK-W035-PEDCO-110-PI-MT-0002 | BK | W035 | PEDCO | 110 | PI | MT | 0002 | F8Z-707759 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 5 | 1 | 2 | 4 | 0 | 3 | 2.5.1.2 | BK-W035-PEDCO-110-PI-MT-0003 | MTO For Flanges - W035 |  | BK-W035-PEDCO-110-PI-MT-0003 | BK-W035-PEDCO-110-PI-MT-0003 | BK | W035 | PEDCO | 110 | PI | MT | 0003 | F8Z-707760 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 5 | 1 | 2 | 4 | 0 | 4 | 2.5.1.2 | BK-W035-PEDCO-110-PI-MT-0004 | MTO For Manual Valves - W035 |  | BK-W035-PEDCO-110-PI-MT-0004 | BK-W035-PEDCO-110-PI-MT-0004 | BK | W035 | PEDCO | 110 | PI | MT | 0004 | F8Z-707761 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 5 | 1 | 2 | 4 | 0 | 5 | 2.5.1.2 | BK-W035-PEDCO-110-PI-MT-0005 | MTO For Gaskets - W035 |  | BK-W035-PEDCO-110-PI-MT-0005 | BK-W035-PEDCO-110-PI-MT-0005 | BK | W035 | PEDCO | 110 | PI | MT | 0005 | F8Z-707762 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 5 | 1 | 2 | 4 | 0 | 6 | 2.5.1.2 | BK-W035-PEDCO-110-PI-MT-0006 | MTO For Bolt & Nuts - W035 |  | BK-W035-PEDCO-110-PI-MT-0006 | BK-W035-PEDCO-110-PI-MT-0006 | BK | W035 | PEDCO | 110 | PI | MT | 0006 | F8Z-707763 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 5 | 1 | 3 | 0 | 0 | 0 | 2.5.1.3 |  | Pipeline & Flow line | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 3 | 1 | 0 | 0 | 2.5.1.3.1 |  | Drawings | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 3 | 1 | 0 | 1 | 2.5.1.3.1 | BK-W035-PEDCO-110-PL-DW-0002 | Flow line Transversal Drawings - W035 |  | BK-W035-PEDCO-110-PL-DW-0002 | BK-W035-PEDCO-110-PL-DW-0002 | BK | W035 | PEDCO | 110 | PL | DW | 0002 | F4A-707764 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 5 | 1 | 3 | 2 | 0 | 0 | 2.5.1.3.2 |  | List
2 | 5 | 1 | 3 | 2 | 0 | 1 | 2.5.1.3.2 | BK-W035-PEDCO-110-PL-LI-0001 | Road Crossing Location List |  | BK-W035-PEDCO-110-PL-LI-0001 | BK-W035-PEDCO-110-PL-LI-0001 | BK | W035 | PEDCO | 110 | PL | LI | 0001 | F0Z-707765 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 5 | 1 | 3 | 3 | 0 | 0 | 2.5.1.3.3 |  | MTO
2 | 5 | 1 | 3 | 3 | 0 | 1 | 2.5.1.3 | BK-W035-PEDCO-110-PL-MT-0001 | MTO For Line Pipes (Flow lines) - W035 |  | BK-W035-PEDCO-110-PL-MT-0001 | BK-W035-PEDCO-110-PL-MT-0001 | BK | W035 | PEDCO | 110 | PL | MT | 0001 | F8Z-707766 | IFI | IFI | 2021-09-05 | 2021-08-30 | 2021-09-05 | -6 | 6 | 0 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W035-PEDCO-110-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 44430 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 |  |  |  |  | PEDCO-CRS-BK-W035-PEDCO-110-PL-MT-0001_D00 | [5 empty] | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-PL-MT-0001_D00
2 | 5 | 1 | 4 | 0 | 0 | 0 | 2.5.1.4 |  | Control & Instrumentation
2 | 5 | 1 | 4 | 1 | 0 | 0 | 2.5.1.4.1 |  | Drawing/Diagram
2 | 5 | 1 | 4 | 1 | 0 | 1 | 2.5.1.4.1 | BK-W035-PEDCO-110-IN-PY-0001 | Instrument Location Layout Drawing - W035 |  | BK-W035-PEDCO-110-IN-PY-0001 | BK-W035-PEDCO-110-IN-PY-0001 | BK | W035 | PEDCO | 110 | IN | PY | 0001 | F2J-707767 | AFC | IFC | 2022-08-29 | 2022-09-26 | 2022-10-02 | 28 | 6 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-15 |  |  | D00 | IFC | T-1277 | 44788 | 1401/05/24 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05539 | 44800 | 1401/06/05 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238110 | 44830 | 1401/07/04 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1277 | 2022-08-15 | 1401/05/24 |  |  |  | BK-SUR-ENG-INS-01-05539 | 44800 | 1401/06/05 | CM-C2 | [6 empty] | 1401-2294-238110 | 2022-09-26 | 1401/07/04 | 44836 | 1401/07/10 | CM
2 | 5 | 1 | 4 | 2 | 0 | 0 | 2.5.1.4.2 |  | MTO
2 | 5 | 1 | 4 | 2 | 0 | 1 | 2.5.1.4 | BK-W035-PEDCO-110-IN-MT-0001 | MTO For Instrument Tube and Fitting - W035 |  | BK-W035-PEDCO-110-IN-MT-0001 | BK-W035-PEDCO-110-IN-MT-0001 | BK | W035 | PEDCO | 110 | IN | MT | 0001 | F8Z-707768 | IFI | IFI | 2021-11-28 | 2021-10-21 | 2021-11-29 | -38 | 39 | 1 | IFI | 2022-01-02 | 2021-01-03 | 2022-01-04 | -364 | 366 | 2 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-14 |  |  | D02 | IFI | T-0451 | 44573 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0239 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02143 | 44528 | 1400/09/08 | RJ-C4 | [6 empty] | 1400-2294-283478 | 2021-10-21 | 1400/08/30 | 44529 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0363 | 44549 | 1400/09/28 |  |  |  | BK-SUR-ENG-INS-00-02500 | 44562 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0001_D00 | [5 empty] | 1400-2294-347440 | 44199 | 1400/10/13 | 44565 | 1400/10/14 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0001_D00 | [9 empty] | D02 | IFI | T-0451 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0001_D01 | [5 empty] | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0001_D01
2 | 5 | 1 | 4 | 2 | 0 | 2 | 2.5.1.4 | BK-W035-PEDCO-110-IN-MT-0002 | MTO For Instrument Cable Tray - W035 |  | BK-W035-PEDCO-110-IN-MT-0002 | BK-W035-PEDCO-110-IN-MT-0002 | BK | W035 | PEDCO | 110 | IN | MT | 0002 | F8Z-707769 | IFI | IFI | 2021-11-28 | 2021-10-21 | 2021-11-29 | -38 | 39 | 1 | IFI | 2022-01-02 | 2021-01-03 | 2022-01-04 | -364 | 366 | 2 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-14 |  |  | D02 | IFI | T-0451 | 44573 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0239 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02143 | 44528 | 1400/09/08 | RJ-C4 | [6 empty] | 1400-2294-283478 | 2021-10-21 | 1400/08/30 | 44529 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0363 | 44549 | 1400/09/28 |  |  |  | BK-SUR-ENG-INS-00-02500 | 44562 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0002_D00 | [5 empty] | 1400-2294-347440 | 44199 | 1400/10/13 | 44565 | 1400/10/14 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0002_D00 | [9 empty] | D02 | IFI | T-0451 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0002_D01 | [5 empty] | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0002_D01
2 | 5 | 1 | 5 | 0 | 0 | 0 | 2.5.1.5 |  | Safety
2 | 5 | 1 | 5 | 1 | 0 | 0 | 2.5.1.5.1 |  | Drawing/Diagram
2 | 5 | 1 | 5 | 1 | 0 | 1 | 2.5.1.5.1 | BK-W035-PEDCO-110-SA-PY-0001 | Hazardous Area Classification Layout - W035 |  | BK-W035-PEDCO-110-SA-PY-0001 | BK-W035-PEDCO-110-SA-PY-0001 | BK | W035 | PEDCO | 110 | SA | PY | 0001 | F2L-707770 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 5 | 1 | 0 | 2 | 2.5.1.5.1 | BK-W035-PEDCO-110-SA-PY-0002 | Safety & Fire Fighting Equipment Location Layout - W035 |  | BK-W035-PEDCO-110-SA-PY-0002 | BK-W035-PEDCO-110-SA-PY-0002 | BK | W035 | PEDCO | 110 | SA | PY | 0002 | F2L-707771 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 5 | 1 | 0 | 3 | 2.5.1.5.1 | BK-W035-PEDCO-110-SA-PY-0003 | Escape Route & Safety Sign Layout - W035 |  | BK-W035-PEDCO-110-SA-PY-0003 | BK-W035-PEDCO-110-SA-PY-0003 | BK | W035 | PEDCO | 110 | SA | PY | 0003 | F2L-707772 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 5 | 2 | 0 | 0 | 2.5.1.5.2 |  | List
2 | 5 | 1 | 5 | 2 | 0 | 1 | 2.5.1.5.2 | BK-W035-PEDCO-110-SA-LI-0001 | Hazard Source List - W035 |  | BK-W035-PEDCO-110-SA-LI-0001 | BK-W035-PEDCO-110-SA-LI-0001 | BK | W035 | PEDCO | 110 | SA | LI | 0001 | F0Z-707773 | AFC | IFC | 2021-11-23 | 2021-11-30 | 2021-12-06 | 7 | 6 | 13 | IFA | 2022-02-16 | 2022-03-08 | 2022-03-06 | 20 | -2 | 18 | IFA | 2022-04-26 | 2022-06-07 | 2022-06-11 | 42 | 4 | 46 | AFC | 2022-08-09 | 2022-09-01 | 2022-09-04 | 23 | 3 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-09 | 2022-07-26 |  | D03 | AFC | T-1197 | 44768 | 1401/05/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205788 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-W035-PEDCO-110-SA-LI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0544 | 44594 | 1400/11/13 | [13 empty] | 1400-2294-435413 | 44628 | 1400/12/15 | 44626 | 1400/12/15 | CM | NISOC-CRS-BK-W035-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0806 | 44663 | 1401/01/23 | [13 empty] | 1401-2294-92282 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-W035-PEDCO-110-SA-LI-0001_D01 | [9 empty] | D03 | AFC | T-1197 | 44768 | 1401/05/04 | [13 empty] | 1401-2294-205788 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-W035-PEDCO-110-SA-LI-0001_D02
2 | 5 | 1 | 5 | 3 | 0 | 0 | 2.5.1.5.3 |  | MTO
2 | 5 | 1 | 5 | 3 | 0 | 1 | 2.5.1.5 | BK-W035-PEDCO-110-SA-MT-0001 | MTO For Fire Fighting & Safety Equipment - W035 |  | BK-W035-PEDCO-110-SA-MT-0001 | BK-W035-PEDCO-110-SA-MT-0001 | BK | W035 | PEDCO | 110 | SA | MT | 0001 | F8Z-707774 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 5 | 3 | 0 | 2 | 2.5.1.5 | BK-W035-PEDCO-110-SA-MT-0002 | MTO For Safety Sign - W035 |  | BK-W035-PEDCO-110-SA-MT-0002 | BK-W035-PEDCO-110-SA-MT-0002 | BK | W035 | PEDCO | 110 | SA | MT | 0002 | F8Z-707775 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 6 | 0 | 0 | 0 | 2.5.1.6 |  | Architecture
2 | 5 | 1 | 6 | 1 | 0 | 0 | 2.5.1.6.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 6 | 1 | 0 | 1 | 2.5.1.6 | BK-W035-PEDCO-110-AR-DW-0001 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W035 |  | BK-W035-PEDCO-110-AR-DW-0001 | BK-W035-PEDCO-110-AR-DW-0001 | BK | W035 | PEDCO | 110 | AR | DW | 0001 | F4B-707776 | AFC | IFC | 2022-03-12 | 2022-03-05 | 2022-03-08 | -7 | 3 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-26 |  |  | D00 | IFC | T-0640 | 44618 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03400 | 44628 | 1400/12/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-435028 | 44625 | 1400/12/14 | 44628 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0640 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-ARC-00-03400 | 44628 | 1400/12/18 | CM-C2 | [6 empty] | 1400-2294-435028 | 2022-03-05 | 1400/12/14 | 44628 | 1400/12/17 | AP | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 7 | 0 | 0 | 0 | 2.5.1.7 |  | Civil
2 | 5 | 1 | 7 | 1 | 0 | 0 | 2.5.1.7.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 7 | 1 | 0 | 1 | 2.5.1.7.1 | BK-W035-PEDCO-110-CV-PY-0001 | General Civil Layout -W035 |  | BK-W035-PEDCO-110-CV-PY-0001 | BK-W035-PEDCO-110-CV-PY-0001 | BK | W035 | PEDCO | 110 | CV | PY | 0001 | F4A-707777 | AFC | IFC | 2022-09-07 | 2022-09-12 | 2022-09-13 | 5 | 1 | 6 | IFA | 2022-10-05 | 2022-10-10 | 2022-10-17 | 5 | 7 | 12 | IFA | 2022-11-06 | 2022-11-05 | 2022-11-06 | -1 | 1 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-24 |  |  | D02 | IFA | T-1534 | 44857 | 1401/08/01 | T-1534 | 44857 | 1401/08/01 | BK-SUR-ENG-CIV-01-05999 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-295379 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-W035-PEDCO-110-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1313 | 2022-08-24 | 1401/06/02 |  |  |  | BK-SUR-ENG-CIV-01-05565 | 44804 | 1401/06/09 | CM-C2 | [6 empty] | 1401-2294-222585 | 2022-09-12 | 1401/06/22 | 44817 | 1301/06/22 | CM | [10 empty] | D01 | IFA | T-1428 | 44825 | 1401/06/30 |  |  |  | BK-SUR-ENG-CIV-01-05783 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-CV-PY-0001_D00 | [5 empty] | 1401-2294-260292 | 44844 | 1401/07/20 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-W035-PEDCO-110-CV-PY-0001_D00 | [9 empty] | D02 | IFA | T-1534 | 44857 | 1401/08/01 | T-1534 | 44857 | 1401/08/01 | BK-SUR-ENG-CIV-01-05999 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-CV-PY-0001_D01 | [5 empty] | 1401-2294-295379 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-W035-PEDCO-110-CV-PY-0001_D01
2 | 5 | 1 | 7 | 1 | 0 | 2 | 2.5.1.7.1 | BK-W035-PEDCO-110-CV-PY-0002 | Civil and Structural drawings -W035 |  | BK-W035-PEDCO-110-CV-PY-0002 | BK-W035-PEDCO-110-CV-PY-0002 | BK | W035 | PEDCO | 110 | CV | PY | 0002 | F4S-707778 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 7 | 1 | 0 | 3 | 2.5.1.7.1 | BK-W035-PEDCO-110-CV-DW-0001 | Rough Grading Plans -W035 |  | BK-W035-PEDCO-110-CV-DW-0001 | BK-W035-PEDCO-110-CV-DW-0001 | BK | W035 | PEDCO | 110 | CV | DW | 0001 | F4S-707779 | AFC | IFC | 2021-12-29 | 2021-12-20 | 2021-12-22 | -9 | 2 | -7 | IFA | 2022-02-19 | 2022-02-19 | 2022-02-12 | 0 | -7 | -7 | IFA | 2022-09-25 | 2022-09-21 | 2022-10-02 | -4 | 11 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-15 |  |  | D02 | IFA | T-1381 | 44815 | 1401/06/20 | T-1381 | 44815 | 1401/06/20 | BK-SUR-ENG-CIV-01-05708 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-CV-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-232682 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | RJ | NISOC-CRS-BK-W035-PEDCO-110-CV-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0351 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-CIV-00-02370 | 44549 | 1400/09/28 | CM-C3 |  | BK-SUR-ENG-CIV-00-02945 | 44597 | 1400/11/17 | CM |  | 1400-2294-327399 | 2021-12-20 | 1400/09/29 | 44552 | 1400/10/01 | CM | [10 empty] | D01 | IFA | T-0552 | 44597 | 1400/11/16 |  |  |  | BK-SUR-ENG-CIV-00-02945 | 44598 | 1400/11/27 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-CV-DW-0001_D00 | [5 empty] | 1400-2294-406451 | 44611 | 1400/11/30 | 44604 | 1400/11/23 | CM | NISOC-CRS-BK-W035-PEDCO-110-CV-DW-0001_D00 | [9 empty] | D02 | IFA | T-1381 | 44815 | 1401/06/20 | T-1381 | 44815 | 1401/06/20 | BK-SUR-ENG-CIV-01-05708 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-CV-DW-0001_D01 | [5 empty] | 1401-2294-232682 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | RJ | NISOC-CRS-BK-W035-PEDCO-110-CV-DW-0001_D01
2 | 5 | 1 | 7 | 2 | 0 | 0 | 2.5.1.7.2 |  | Calculation
2 | 5 | 1 | 7 | 2 | 0 | 1 | 2.5.1.7.2 | BK-W035-PEDCO-110-CV-CN-0001 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W035 |  | BK-W035-PEDCO-110-CV-CN-0001 | BK-W035-PEDCO-110-CV-CN-0001 | BK | W035 | PEDCO | 110 | CV | CN | 0001 | F0Z-707780 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 7 | 3 | 0 | 0 | 2.5.1.7.3 |  | MTO
2 | 5 | 1 | 7 | 3 | 0 | 1 | 2.5.1.7 | BK-W035-PEDCO-110-CV-MT-0001 | MTO For Civil Works - W035 |  | BK-W035-PEDCO-110-CV-MT-0001 | BK-W035-PEDCO-110-CV-MT-0001 | BK | W035 | PEDCO | 110 | CV | MT | 0001 | F8Z-707781 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 8 | 0 | 0 | 0 | 2.5.1.8 |  | Structure
2 | 5 | 1 | 8 | 1 | 0 | 0 | 2.5.1.8.1 |  | Drawing/Diagram
2 | 5 | 1 | 8 | 1 | 0 | 1 | 2.5.1.8.1 | BK-W035-PEDCO-110-ST-DW-0002 | Platform Structure Drawing - W035 |  | BK-W035-PEDCO-110-ST-DW-0002 | BK-W035-PEDCO-110-ST-DW-0002 | BK | W035 | PEDCO | 110 | ST | DW | 0002 | F4M-707782 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 8 | 2 | 0 | 0 | 2.5.1.8.2 |  | MTO
2 | 5 | 1 | 8 | 2 | 0 | 1 | 2.5.1.8 | BK-W035-PEDCO-110-ST-MT-0001 | MTO For Structural Works - W035 |  | BK-W035-PEDCO-110-ST-MT-0001 | BK-W035-PEDCO-110-ST-MT-0001 | BK | W035 | PEDCO | 110 | ST | MT | 0001 | F8Z-707783 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 9 | 0 | 0 | 0 | 2.5.1.9 |  | Survey (Topography) & Geotechnic/Geoelectric
2 | 5 | 1 | 9 | 1 | 0 | 0 | 2.5.1.9.1 |  | Geotechnic
2 | 5 | 1 | 9 | 1 | 1 | 0 | 2.5.9.1.1 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 9 | 1 | 1 | 1 | 2.5.1.9.1.1.1 | BK-W035-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - W035 |  | BK-W035-PEDCO-110-GT-RT-0001 | BK-W035-PEDCO-110-GT-RT-0001 | BK | W035 | PEDCO | 110 | GT | RT | 0001 | F0Z-707784 | IFI | IFC | 2022-06-25 | 2022-06-21 | 2022-06-25 | -4 | 4 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-11 |  |  | D00 | IFC | T-1059 | 44723 | 1401/03/21 | T-1059 | 44723 | 1401/03/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-111566 | 44733 | 1401/03/31 | 44737 | 1401/04/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1059 | 2022-06-11 | 1401/03/21 | T-1059 | 44723 | 1401/03/21 | [10 empty] | 1401-2294-111566 | 2022-06-21 | 1401/03/31 | 44737 | 1401/04/04 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 1 | 9 | 1 | 2 | 0 | 2.5.9.1.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 1 | 9 | 1 | 2 | 1 | 2.5.1.9.1.2.1 | BK-W035-PEDCO-110-SU-DW-0001 | Flow line Plan & Profile Drawings - W035 |  | BK-W035-PEDCO-110-SU-DW-0001 | BK-W035-PEDCO-110-SU-DW-0001 | BK | W035 | PEDCO | 110 | SU | DW | 0001 | F4A-707785 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 0 | 0 | 0 | 0 | 2.5.2 |  | Procurement Engineering
2 | 5 | 2 | 1 | 0 | 0 | 0 | 2.5.2.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 1 | 0 | 0 | 2.5.2.1.1 |  | Pipes
2 | 5 | 2 | 1 | 1 | 1 | 0 | 2.5.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 1 | 1 | 1 | 2.5.2.1.1.1.1 | BK-W035-PEDCO-110-PI-MR-0001 | PMR For Pipes - W035 |  | BK-W035-PEDCO-110-PI-MR-0001 | BK-W035-PEDCO-110-PI-MR-0001 | BK | W035 | PEDCO | 110 | PI | MR | 0001 | F0Z-707786 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 1 | 2 | 0 | 2.5.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 1 | 2 | 1 | 2.5.2.1.1.2.1 | BK-W035-PEDCO-110-PI-TB-0001 | TBE For Pipes - W035 |  | BK-W035-PEDCO-110-PI-TB-0001 | BK-W035-PEDCO-110-PI-TB-0001 | BK | W035 | PEDCO | 110 | PI | TB | 0001 | F0Z-707787 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 2 | 0 | 0 | 2.5.2.1.2 |  | Fittings
2 | 5 | 2 | 1 | 2 | 1 | 0 | 2.5.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 2 | 1 | 1 | 2.5.2.1.2.1.1 | BK-W035-PEDCO-110-PI-MR-0002 | PMR For Fittings - W035 |  | BK-W035-PEDCO-110-PI-MR-0002 | BK-W035-PEDCO-110-PI-MR-0002 | BK | W035 | PEDCO | 110 | PI | MR | 0002 | F0Z-707788 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 2 | 2 | 0 | 2.5.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 2 | 2 | 1 | 2.5.2.1.2.2.1 | BK-W035-PEDCO-110-PI-TB-0002 | TBE For Fitting - W035 |  | BK-W035-PEDCO-110-PI-TB-0002 | BK-W035-PEDCO-110-PI-TB-0002 | BK | W035 | PEDCO | 110 | PI | TB | 0002 | F0Z-707789 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 3 | 0 | 0 | 2.5.2.1.3 |  | Flanges
2 | 5 | 2 | 1 | 3 | 1 | 0 | 2.5.1.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 3 | 1 | 1 | 2.5.2.1.3.1.1 | BK-W035-PEDCO-110-PI-MR-0003 | PMR For Flanges - W035 |  | BK-W035-PEDCO-110-PI-MR-0003 | BK-W035-PEDCO-110-PI-MR-0003 | BK | W035 | PEDCO | 110 | PI | MR | 0003 | F0Z-707790 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 3 | 2 | 0 | 2.5.1.3.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 3 | 2 | 1 | 2.5.2.1.3.2.1 | BK-W035-PEDCO-110-PI-TB-0003 | TBE For Flanges - W035 |  | BK-W035-PEDCO-110-PI-TB-0003 | BK-W035-PEDCO-110-PI-TB-0003 | BK | W035 | PEDCO | 110 | PI | TB | 0003 | F0Z-707791 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 4 | 0 | 0 | 2.5.2.1.4 |  | Manual Valves
2 | 5 | 2 | 1 | 4 | 1 | 0 | 2.5.1.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 4 | 1 | 1 | 2.5.2.1.4.1.1 | BK-W035-PEDCO-110-PI-MR-0004 | PMR For Manual Valves - W035 |  | BK-W035-PEDCO-110-PI-MR-0004 | BK-W035-PEDCO-110-PI-MR-0004 | BK | W035 | PEDCO | 110 | PI | MR | 0004 | F0Z-707792 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 4 | 2 | 0 | 2.5.1.4.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 4 | 2 | 1 | 2.5.2.1.4.2.1 | BK-W035-PEDCO-110-PI-TB-0004 | TBE For Manual Valves - W035 |  | BK-W035-PEDCO-110-PI-TB-0004 | BK-W035-PEDCO-110-PI-TB-0004 | BK | W035 | PEDCO | 110 | PI | TB | 0004 | F0Z-707793 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 5 | 0 | 0 | 2.5.2.1.5 |  | Gaskets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 5 | 1 | 0 | 2.5.1.5.1 |  | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 5 | 1 | 1 | 2.5.2.1.5.1.1 | BK-W035-PEDCO-110-PI-MR-0005 | PMR For Gaskets - W035 |  | BK-W035-PEDCO-110-PI-MR-0005 | BK-W035-PEDCO-110-PI-MR-0005 | BK | W035 | PEDCO | 110 | PI | MR | 0005 | F0Z-707794 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 5 | 2 | 0 | 2.5.1.5.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 5 | 2 | 1 | 2.5.2.1.5.2.1 | BK-W035-PEDCO-110-PI-TB-0005 | TBE For Gaskets - W035 |  | BK-W035-PEDCO-110-PI-TB-0005 | BK-W035-PEDCO-110-PI-TB-0005 | BK | W035 | PEDCO | 110 | PI | TB | 0005 | F0Z-707795 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 6 | 0 | 0 | 2.5.2.1.6 |  | Bolt & Nuts | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 6 | 1 | 0 | 2.5.1.6.1 |  | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 6 | 1 | 1 | 2.5.2.1.6.1.1 | BK-W035-PEDCO-110-PI-MR-0006 | PMR For Bolt/Nuts - W035 |  | BK-W035-PEDCO-110-PI-MR-0006 | BK-W035-PEDCO-110-PI-MR-0006 | BK | W035 | PEDCO | 110 | PI | MR | 0006 | F0Z-707796 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 6 | 2 | 0 | 2.5.1.6.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 6 | 2 | 1 | 2.5.2.1.6.2.1 | BK-W035-PEDCO-110-PI-TB-0006 | TBE For Bolt/Nuts - W035 |  | BK-W035-PEDCO-110-PI-TB-0006 | BK-W035-PEDCO-110-PI-TB-0006 | BK | W035 | PEDCO | 110 | PI | TB | 0006 | F0Z-707797 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 7 | 0 | 0 | 2.5.2.1.7 |  | Sampling Connection
2 | 5 | 2 | 1 | 7 | 1 | 0 | 2.5.1.7.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 7 | 1 | 1 | 2.5.2.1.7.1.1 | BK-W035-PEDCO-110-PI-MR-0007 | PMR For Sampling Connection Set - W035 |  | BK-W035-PEDCO-110-PI-MR-0007 | BK-W035-PEDCO-110-PI-MR-0007 | BK | W035 | PEDCO | 110 | PI | MR | 0007 | F0Z-707798 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 7 | 2 | 0 | 2.5.1.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 7 | 2 | 1 | 2.5.2.1.7.2.1 | BK-W035-PEDCO-110-PI-TB-0007 | TBE For Sampling Connection Set - W035 |  | BK-W035-PEDCO-110-PI-TB-0007 | BK-W035-PEDCO-110-PI-TB-0007 | BK | W035 | PEDCO | 110 | PI | TB | 0007 | F0Z-707799 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 8 | 0 | 0 | 2.5.2.1.8 |  | Stone Trap
2 | 5 | 2 | 1 | 8 | 1 | 0 | 2.5.1.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 8 | 1 | 1 | 2.5.2.1.8.1.1 | BK-W035-PEDCO-110-PI-MR-0008 | PMR For Stone Trap - W035 |  | BK-W035-PEDCO-110-PI-MR-0008 | BK-W035-PEDCO-110-PI-MR-0008 | BK | W035 | PEDCO | 110 | PI | MR | 0008 | F0Z-707800 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 8 | 2 | 0 | 2.5.1.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 8 | 2 | 1 | 2.5.2.1.8.2.1 | BK-W035-PEDCO-110-PI-TB-0008 | TBE For Stone Trap - W035 |  | BK-W035-PEDCO-110-PI-TB-0008 | BK-W035-PEDCO-110-PI-TB-0008 | BK | W035 | PEDCO | 110 | PI | TB | 0008 | F0Z-707801 | IFI | IFI | 2022-06-08 | 2022-06-13 | 2022-06-14 | 5 | 1 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-25 |  |  | D00 | IFI | T-1002 | 44706 | 1401/03/03 | T-1002 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04514 | 44713 | 1401/03/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-100877 | 44725 | 1401/03/23 | 44726 | 1401/03/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1002 | 2022-05-25 | 1401/03/03 | T-1002 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04514 | 44713 | 1401/03/11 | CM-C3 | [6 empty] | 1401-2294-100877 | 2022-06-13 | 1401/03/23 | 44726 | 1401/03/24 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 9 | 0 | 0 | 2.5.2.1.9 |  | Pipe Support
2 | 5 | 2 | 1 | 9 | 1 | 0 | 2.5.1.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 9 | 1 | 1 | 2.5.2.1.9.1.1 | BK-W035-PEDCO-110-PI-MR-0009 | PMR For Pipe Support - W035 |  | BK-W035-PEDCO-110-PI-MR-0009 | BK-W035-PEDCO-110-PI-MR-0009 | BK | W035 | PEDCO | 110 | PI | MR | 0009 | F0Z-707802 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 9 | 2 | 0 | 2.5.1.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 9 | 2 | 1 | 2.5.2.1.9.2.1 | BK-W035-PEDCO-110-PI-TB-0009 | TBE For Pipe Support - W035 |  | BK-W035-PEDCO-110-PI-TB-0009 | BK-W035-PEDCO-110-PI-TB-0009 | BK | W035 | PEDCO | 110 | PI | TB | 0009 | F0Z-707803 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 1 | 9 | 0 | 0 | 2.5.2.1.9 |  | BURN PIT PIPES
2 | 5 | 2 | 1 | 9 | 1 | 0 | 2.5.1.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 9 | 1 | 1 | 2.5.2.1.9.1.1 | BK-W035-PEDCO-110-PI-MR-0009 | PMR FOR BURN PIT PIPES– W035 |  | BK-W035-PEDCO-110-PI-MR-0011 | BK-W035-PEDCO-110-PI-MR-0009 | BK | W035 | PEDCO | 110 | PI | MR | 0009 | F0Z-707802 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [11 empty] | D00 | IFI | T-1550 | 44859 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1550 | 2022-10-25 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2
2 | 5 | 2 | 1 | 9 | 2 | 0 | 2.5.1.9.2 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 1 | 9 | 2 | 1 | 2.5.2.1.9.2.1 | BK-W035-PEDCO-110-PI-TB-0009 | TBE FOR BURN PIT PIPES– W035 |  | BK-W035-PEDCO-110-PI-TB-0011 | BK-W035-PEDCO-110-PI-TB-0009 | BK | W035 | PEDCO | 110 | PI | TB | 0009 | F0Z-707803 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14
2 | 5 | 2 | 2 | 0 | 0 | 0 | 2.5.2.2 |  | Pipeline
2 | 5 | 2 | 2 | 1 | 0 | 0 | 2.5.2.2.1 |  | Line Pipe
2 | 5 | 2 | 2 | 1 | 1 | 0 | 2.5.2.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 2 | 1 | 1 | 1 | 2.5.2.2.1.1.1 | BK-W035-PEDCO-110-PL-MR-0001 | PMR For Line Pipes - W035 |  | BK-W035-PEDCO-110-PL-MR-0001 | BK-W035-PEDCO-110-PL-MR-0001 | BK | W035 | PEDCO | 110 | PL | MR | 0001 | F0Z-707804 | IFI | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-23 |  |  | D00 | IFI | T-1529 | 44857 | 1401/08/01 | T-1529 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296595 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1529 | 2022-10-23 | 1401/08/01 | T-1529 | 44857 | 1401/08/01 | [10 empty] | 1401-2294-296595 | 2022-11-05 | 1401/08/14 | 44874 | 1401/08/18 | AP | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 2 | 1 | 2 | 0 | 2.5.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 2 | 1 | 2 | 1 | 2.5.2.2.1.2.1 | BK-W035-PEDCO-110-PL-TB-0001 | TBE For Line Pipes - W035 |  | BK-W035-PEDCO-110-PL-TB-0001 | BK-W035-PEDCO-110-PL-TB-0001 | BK | W035 | PEDCO | 110 | PL | TB | 0001 | F0Z-707805 | IFI | IFI | 2022-03-05 | 2022-03-10 | 2022-03-14 | 5 | 4 | 9 | IFI | 2022-05-28 | 2022-05-31 | 2022-06-07 | 3 | 7 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W035-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 44628 | 1400/12/17 | RJ-C4 | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 44634 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PL-TB-0001-D00 | [5 empty] | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W035-PEDCO-110-PL-TB-0001-D00
2 | 5 | 2 | 2 | 2 | 0 | 0 | 2.5.2.2.2 |  | Line Pipe
2 | 5 | 2 | 2 | 2 | 1 | 0 | 2.5.2.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 2 | 2 | 1 | 1 | 2.5.2.2.2.1.1 | BK-W035-PEDCO-110-PL-MR-0002 | PMR For Flow Line Support - W035 |  | BK-W035-PEDCO-110-PL-MR-0002 | BK-W035-PEDCO-110-PL-MR-0002 | BK | W035 | PEDCO | 110 | PL | MR | 0002 | F0Z-707806 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 2 | 2 | 2 | 0 | 2.5.2.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 2 | 2 | 2 | 1 | 2.5.2.2.2.2.1 | BK-W035-PEDCO-110-PL-TB-0002 | TBE For Flow Line Support - W035 |  | BK-W035-PEDCO-110-PL-TB-0002 | BK-W035-PEDCO-110-PL-TB-0002 | BK | W035 | PEDCO | 110 | PL | TB | 0002 | F0Z-707807 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 3 | 0 | 0 | 0 | 2.5.2.3 |  | Control & Instrumentation
2 | 5 | 2 | 3 | 1 | 0 | 0 | 2.5.2.3.1 |  | WHCP/HPU
2 | 5 | 2 | 3 | 1 | 1 | 0 | 2.5.3.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 3 | 1 | 1 | 1 | 2.5.2.3.1.1.1 | BK-W035-PEDCO-110-IN-MR-0001 | PMR For WHCP/HPU - W035 |  | BK-W035-PEDCO-110-IN-MR-0001 | BK-W035-PEDCO-110-IN-MR-0001 | BK | W035 | PEDCO | 110 | IN | MR | 0001 | F0Z-707808 | IFI | IFI | 2021-11-29 | 2021-12-17 | 2021-12-07 | 18 | -10 | 8 | IFI | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 | IFI | 2022-07-03 | 2022-08-18 | 2022-08-23 | 46 | 5 | 51 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-15 |  |  | D02 | IFI | T-1091 | 44731 | 1401/03/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05243 | 44768 | 1401/05/04 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183563 | 44791 | 1401/05/27 | 44796 | 1401/06/01 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0243 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-INS-00-02170 | 44531 | 1400/09/10 | RJ-C4 |  | BK-SUR-ENG-INS-00-02224 | 44537 | 1400/09/16 | CM-C3 |  | 1400-2294-320808 | 2021-12-17 | 1400/09/26 | 44537 | 1400/09/16 | CM | [10 empty] | D01 | IFI | T-0470 | 44577 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02865 | 44591 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MR-0001_D00 | [5 empty] | 1400-2294-390765 | 44592 | 1400/11/11 | 44593 | 1400/11/12 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-MR-0001_D00 | [9 empty] | D02 | IFI | T-1091 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-INS-01-05243 | 44768 | 1401/05/04 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MR-0001_D01 | [5 empty] | 1401-2294-183563 | 44791 | 1401/05/27 | 44796 | 1401/06/01 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-MR-0001_D01
2 | 5 | 2 | 3 | 1 | 2 | 0 | 2.5.3.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 3 | 1 | 2 | 1 | 2.5.2.3.1.2.1 | BK-W035-PEDCO-110-IN-TB-0001 | TBE/TBA For WHCP/HPU - W035 |  | BK-W035-PEDCO-110-IN-TB-0001 | BK-W035-PEDCO-110-IN-TB-0001 | BK | W035 | PEDCO | 110 | IN | TB | 0001 | F0Z-707809 | IFI | IFI | 2021-12-15 | 2021-12-14 | 2021-12-15 | -1 | 1 | 0 | IFI | 2022-03-05 | 2022-04-04 | 2022-04-09 | 30 | 5 | 35 | IFI | 2022-07-18 | 2022-07-06 | 2022-07-12 | -12 | 6 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-01 |  |  | D02 | IFI | T-1136 | 44746 | 1401/04/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05364 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-132654 | 44748 | 1401/04/15 | 44754 | 1401/04/21 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0286 | 2021-12-01 | 1400/09/10 |  |  |  | BK-SUR-ENG-INS-00-02297 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-317340 | 2021-12-14 | 1400/09/23 | 44545 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0602 | 44611 | 1400/11/30 |  |  |  | BK-SUR-ENG-INS-00-03345 | 44625 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-TB-0001_D00 | [5 empty] | 1401-2294-9652 | 44655 | 1401/01/15 | 44660 | 1401/01/20 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-TB-0001_D00 | [9 empty] | D02 | IFI | T-1136 | 44746 | 1401/04/13 |  |  |  | BK-SUR-ENG-INS-01-05364 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-TB-0001_D01 | [5 empty] | 1401-2294-132654 | 44748 | 1401/04/15 | 44754 | 1401/04/21 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-TB-0001_D01
2 | 5 | 2 | 3 | 2 | 0 | 0 | 2.5.2.3.2 |  | Field Instrumentations
2 | 5 | 2 | 3 | 2 | 1 | 0 | 2.5.3.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 3 | 2 | 1 | 1 | 2.5.2.3.2.1.1 | BK-W035-PEDCO-110-IN-MR-0002 | PMR For Field Instrumentations - W035 |  | BK-W035-PEDCO-110-IN-MR-0002 | BK-W035-PEDCO-110-IN-MR-0002 | BK | W035 | PEDCO | 110 | IN | MR | 0002 | F0Z-707810 | IFI | IFI | 2021-12-27 | 2022-01-21 | 2021-01-25 | 25 | -361 | -336 | IFI | 2022-08-13 | 2022-09-08 | 2022-09-13 | 26 | 5 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-13 |  |  | D01 | IFI | T-1218 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 44557 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/10/01 | 44221 | 1400/11/05 | CM | [10 empty] | D01 | IFI | T-1218 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MR-0002_D00 | [5 empty] | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MR-0002_D00
2 | 5 | 2 | 3 | 2 | 2 | 0 | 2.5.3.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 3 | 2 | 2 | 1 | 2.5.2.3.2.2.1 | BK-W035-PEDCO-110-IN-TB-0002 | TBE/TBA For Field Instrumentations - W035 |  | BK-W035-PEDCO-110-IN-TB-0002 | BK-W035-PEDCO-110-IN-TB-0002 | BK | W035 | PEDCO | 110 | IN | TB | 0002 | F0Z-707811 | IFI | IFI | 2022-06-11 | 2022-06-21 | 2022-07-05 | 10 | 14 | 24 | IFI | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-26 |  |  | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W035-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | T-1012 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-05635 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-111541 | 2022-06-21 | 1401/03/31 | 44747 | 1401/04/14 | RJ | [10 empty] | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-TB-0002_D00 | [11 empty] | NISOC-CRS-BK-W035-PEDCO-110-IN-TB-0002_D00
2 | 5 | 2 | 3 | 3 | 0 | 0 | 2.5.2.3.3 |  | Instrument Bulk Items
2 | 5 | 2 | 3 | 3 | 1 | 0 | 2.5.3.3.1 |  | Purchase Material Requisition (PMR)
2 | 5 | 2 | 3 | 3 | 1 | 1 | 2.5.2.3.3.1.1 | BK-W035-PEDCO-110-IN-MR-0003 | PMR For Instrument Bulk Items - W035 |  | BK-W035-PEDCO-110-IN-MR-0003 | BK-W035-PEDCO-110-IN-MR-0003 | BK | W035 | PEDCO | 110 | IN | MR | 0003 | F0Z-707812 | IFI | IFI | 2022-01-30 | 2021-01-31 | 2022-02-01 | -364 | 366 | 2 | IFI | 2022-09-18 | 2022-09-21 | 2022-10-02 | 3 | 11 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-16 |  |  | D01 | IFI | T-1351 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W035-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C2 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 44593 | 1400/11/12 | CM | [10 empty] | D01 | IFI | T-1351 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MR-0003_D00 | [5 empty] | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W035-PEDCO-110-IN-MR-0003_D00
2 | 5 | 2 | 3 | 3 | 2 | 0 | 2.5.3.3.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 3 | 3 | 2 | 1 | 2.5.2.3.3.2.1 | BK-W035-PEDCO-110-IN-TB-0003 | TBE/TBA For Instrument Bulk Items - W035 |  | BK-W035-PEDCO-110-IN-TB-0003 | BK-W035-PEDCO-110-IN-TB-0003 | BK | W035 | PEDCO | 110 | IN | TB | 0003 | F0Z-707813 | IFI | IFI | 2022-02-16 | 2022-03-19 | 2022-03-14 | 31 | -5 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-02 |  |  | D00 | IFI | T-0539 | 44594 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443275 | 44639 | 1400/12/19 | 44634 | 1400/12/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | [6 empty] | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 44634 | 1400/12/23 | CM
2 | 5 | 2 | 4 | 0 | 0 | 0 | 2.5.2.4 |  | Safety & Fire Fighting
2 | 5 | 2 | 4 | 1 | 0 | 0 | 2.5.2.4.1 |  | Fire Fighting and Safety Equipment
2 | 5 | 2 | 4 | 1 | 1 | 0 | 2.5.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 4 | 1 | 1 | 1 | 2.5.2.4.1.1.1 | BK-W035-PEDCO-110-SA-MR-0001 | PMR For Fire Fighting and Safety Equipment - W035 |  | BK-W035-PEDCO-110-SA-MR-0001 | BK-W035-PEDCO-110-SA-MR-0001 | BK | W035 | PEDCO | 110 | SA | MR | 0001 | F0Z-707814 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 4 | 1 | 2 | 0 | 2.5.4.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 4 | 1 | 2 | 1 | 2.5.2.4.1.2.1 | BK-W035-PEDCO-110-SA-TB-0001 | TBE For Fire Fighting and Safety Equipment - W035 |  | BK-W035-PEDCO-110-SA-TB-0001 | BK-W035-PEDCO-110-SA-TB-0001 | BK | W035 | PEDCO | 110 | SA | TB | 0001 | F0Z-707815 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 4 | 2 | 0 | 0 | 2.5.2.4.2 |  | Safety Sign
2 | 5 | 2 | 4 | 2 | 1 | 0 | 2.5.4.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 4 | 2 | 1 | 1 | 2.5.2.4.2.1.1 | BK-W035-PEDCO-110-SA-MR-0002 | PMR For Fire Safety Sign - W035 |  | BK-W035-PEDCO-110-SA-MR-0002 | BK-W035-PEDCO-110-SA-MR-0002 | BK | W035 | PEDCO | 110 | SA | MR | 0002 | F0Z-707816 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 4 | 2 | 2 | 0 | 2.5.4.2.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 4 | 2 | 2 | 1 | 2.5.2.4.2.2.1 | BK-W035-PEDCO-110-SA-TB-0002 | TBE For Fire Safety Sign - W035 |  | BK-W035-PEDCO-110-SA-TB-0002 | BK-W035-PEDCO-110-SA-TB-0002 | BK | W035 | PEDCO | 110 | SA | TB | 0002 | F0Z-707817 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 5 | 0 | 0 | 0 | 2.5.2.5 |  | Structure
2 | 5 | 2 | 5 | 1 | 0 | 0 | 2.5.2.5.1 |  | Steel Structure Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 5 | 1 | 1 | 0 | 2.5.5.1.1 |  | Purchase Material Requisition (PMR)
2 | 5 | 2 | 5 | 1 | 1 | 1 | 2.5.2.5.1.1.1 | BK-W035-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - W035 |  | BK-W035-PEDCO-110-ST-MR-0001 | BK-W035-PEDCO-110-ST-MR-0001 | BK | W035 | PEDCO | 110 | ST | MR | 0001 | F0Z-707818 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 5 | 1 | 2 | 0 | 2.5.5.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 5 | 1 | 2 | 1 | 2.5.2.5.1.2.1 | BK-W035-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - W035 |  | BK-W035-PEDCO-110-ST-TB-0001 | BK-W035-PEDCO-110-ST-TB-0001 | BK | W035 | PEDCO | 110 | ST | TB | 0001 | F0Z-707819 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 5 | 2 | 0 | 0 | 2.5.2.5.2 |  | Anchor Bolts | [61 empty] | Moved to Field
2 | 5 | 2 | 5 | 2 | 1 | 0 | 2.5.5.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 5 | 2 | 1 | 1 | 2.5.2.5.2.1.1 | BK-W035-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - W035 |  | BK-W035-PEDCO-110-ST-MR-0002 | BK-W035-PEDCO-110-ST-MR-0002 | BK | W035 | PEDCO | 110 | ST | MR | 0002 | F0Z-707820 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 5 | 2 | 2 | 0 | 2.5.5.2.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 5 | 2 | 2 | 1 | 2.5.2.5.2.2.1 | BK-W035-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - W035 |  | BK-W035-PEDCO-110-ST-TB-0002 | BK-W035-PEDCO-110-ST-TB-0002 | BK | W035 | PEDCO | 110 | ST | TB | 0002 | F0Z-707821 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 6 | 0 | 0 | 0 | 2.5.2.6 |  | Civil
2 | 5 | 2 | 6 | 1 | 0 | 0 | 2.5.2.6.1 |  | Geomembrane | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 6 | 1 | 1 | 0 | 2.5.6.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 6 | 1 | 1 | 1 | 2.5.2.6.1.1.1 | BK-W035-PEDCO-110-CV-MR-0001 | PMR For Geomembrane - W035 |  | BK-W035-PEDCO-110-CV-MR-0001 | BK-W035-PEDCO-110-CV-MR-0001 | BK | W035 | PEDCO | 110 | CV | MR | 0001 | F0Z-707822 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 6 | 1 | 2 | 0 | 2.5.6.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 6 | 1 | 2 | 1 | 2.5.2.6.1.2.1 | BK-W035-PEDCO-110-CV-TB-0001 | TBE For Geomembrane - W035 |  | BK-W035-PEDCO-110-CV-TB-0001 | BK-W035-PEDCO-110-CV-TB-0001 | BK | W035 | PEDCO | 110 | CV | TB | 0001 | F0Z-707823 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 6 | 2 | 0 | 0 | 2.5.2.6.2 |  | Geotextile | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 2 | 6 | 2 | 1 | 0 | 2.5.6.2.1 |  | Purchase Material Requisition (PMR)
2 | 5 | 2 | 6 | 2 | 1 | 1 | 2.5.2.6.2.1.1 | BK-W035-PEDCO-110-CV-MR-0002 | PMR For Geotextile - W035 |  | BK-W035-PEDCO-110-CV-MR-0002 | BK-W035-PEDCO-110-CV-MR-0002 | BK | W035 | PEDCO | 110 | CV | MR | 0002 | F0Z-707824 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 2 | 6 | 2 | 2 | 0 | 2.5.6.2.2 |  | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 6 | 2 | 2 | 1 | 2.5.2.6.2.2.1 | BK-W035-PEDCO-110-CV-TB-0002 | TBE For Geotextile - W035 |  | BK-W035-PEDCO-110-CV-TB-0002 | BK-W035-PEDCO-110-CV-TB-0002 | BK | W035 | PEDCO | 110 | CV | TB | 0002 | F0Z-707825 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 3 | 0 | 0 | 0 | 0 | 2.5.3 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 3 | 0 | 0 | 1 | 0 | 2.5.3.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 3 | 0 | 0 | 1 | 1 | 2.5.3.1.1 | BK-W035-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - W035 |  | BK-W035-PEDCO-110-CO-PR-0001 | BK-W035-PEDCO-110-CO-PR-0001 | BK | W035 | PEDCO | 110 | CO | PR | 0001 | F0Z-707826 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 4 | 0 | 0 | 0 | 0 | 2.5.4 |  | Field Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 4 | 0 | 0 | 1 | 0 | 2.5.4.1 |  | Query
2 | 5 | 4 | 0 | 0 | 1 | 1 | 2.5.4.1.1 | BK-W035-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-W035-PEDCO-110-GE-TQ-0001 | BK-W035-PEDCO-110-GE-TQ-0001 | BK | W035 | PEDCO | 110 | GE | TQ | 0001 | F7Z-707827 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 4 | 0 | 0 | 2 | 0 | 2.5.4.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 4 | 0 | 0 | 2 | 1 | 2.5.4.2.1 | BK-W035-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W035 |  | BK-W035-PEDCO-110-GE-DO-0001 | BK-W035-PEDCO-110-GE-DO-0001 | BK | W035 | PEDCO | 110 | GE | DO | 0001 | F0Z-707828 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 5 | 0 | 0 | 0 | 0 | 2.5.5 |  | Engineering Final Documentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 5 | 0 | 0 | 1 | 0 | 2.5.5.1 |  | Manual | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 5 | 0 | 0 | 1 | 1 | 2.5.5.1.1 | BK-W035-PEDCO-110-GE-ML-0001 | Operating Manual - W035 |  | BK-W035-PEDCO-110-GE-ML-0001 | BK-W035-PEDCO-110-GE-ML-0001 | BK | W035 | PEDCO | 110 | GE | ML | 0001 | F0Z-707829 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 5 | 0 | 0 | 2 | 0 | 2.5.5.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 5 | 5 | 0 | 0 | 2 | 1 | 2.5.5.2.1 | BK-W035-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W035 |  | BK-W035-PEDCO-110-GE-DO-0001 | [8 empty] | F0Z-707828 |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 5 | 5 | 0 | 0 | 2 | 2 | 2.5.5.2.2 | BK-W035-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - W035 |  | BK-W035-PEDCO-110-GE-DO-0002 | BK-W035-PEDCO-110-GE-DO-0002 | BK | W035 | PEDCO | 110 | GE | DO | 0002 | F0Z-707830 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 0 | 0 | 0 | 0 | 0 | 2.6 |  | Package 05-New Well # W008N | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 0 | 0 | 0 | 0 | 2.6.1 |  | Detail Design | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 1 | 0 | 0 | 0 | 2.6.1.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 1 | 1 | 0 | 0 | 2.6.1.1.1 |  | Drawing/Diagram
2 | 6 | 1 | 1 | 1 | 0 | 1 | 2.6.1.1.1 | BK-W008N-PEDCO-110-PR-PF-0001 | Process Flow Diagram - W008N |  | BK-W008N-PEDCO-110-PR-PF-0001 | BK-W008N-PEDCO-110-PR-PF-0001 | BK | W008N | PEDCO | 110 | PR | PF | 0001 | F2A-707831 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-16 | 2022-06-02 | 2022-06-06 | 198 | 4 | 202 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-02 |  |  | D02 | IFA | T-1266 | 44783 | 1401/05/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK- W008N-PEDCO-110-PR-PF-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK- W008N-PEDCO-110-PR-PF-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 44447 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0205 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-PCS-00-02020 | 44516 | 1400/08/25 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PF-0001_D00 | [5 empty] | 1401-2294-87488 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-PF-0001_D00 | [9 empty] | D02 | IFA | T-1266 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK- W008N-PEDCO-110-PR-PF-0001 _D01 | [5 empty] | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK- W008N-PEDCO-110-PR-PF-0001 _D01
2 | 6 | 1 | 1 | 1 | 0 | 2 | 2.6.1.1.1 | BK-W008N-PEDCO-110-PR-PI-0001 | P&ID - W008N |  | BK-W008N-PEDCO-110-PR-PI-0001 | BK-W008N-PEDCO-110-PR-PI-0001 | BK | W008N | PEDCO | 110 | PR | PI | 0001 | F2A-707832 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | IFA | 2022-09-20 | 2022-11-19 | 2022-11-21 | 60 | 2 | 62 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-01 |  |  | D04 | IFA | T-1368 | 44810 | 1401/06/15 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 44447 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0201 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 44516 | 1400/08/25 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 44564 | 1400/10/13 | CM-C3 | PEDCO-BK-W008N-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 44560 | 1400/10/09 | 44564 | 1400/10/13 | RJ | NISOC-BK-W008N-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D02 | [9 empty] | D04 | IFA | T-1368 | 44810 | 1401/06/15 |  |  |  | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D03 | [5 empty] | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D03
2 | 6 | 1 | 1 | 2 | 0 | 0 | 2.6.1.1.2 |  | List
2 | 6 | 1 | 1 | 2 | 0 | 1 | 2.6.1.1.2 | BK-W008N-PEDCO-110-PR-LI-0001 | Line List - W008N |  | BK-W008N-PEDCO-110-PR-LI-0001 | BK-W008N-PEDCO-110-PR-LI-0001 | BK | W008N | PEDCO | 110 | PR | LI | 0001 | F0Z-707833 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-22 | 2021-11-27 | 2021-11-29 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-06-27 | 0 | 166 | -44739 | -44573 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-08 |  |  | D02 | IFA | T-0403 | 44559 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 44447 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0217 | 44508 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 44520 | 1400/08/29 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 44527 | 1400/09/06 | 44529 | 1400/09/08 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D01 | [5 empty] | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D01
2 | 6 | 1 | 1 | 3 | 0 | 0 | 2.6.1.1.3 |  | Report | [153 empty] | 1400/09/06
2 | 6 | 1 | 1 | 3 | 0 | 1 | 2.6.1.1.3 | BK-W008N-PEDCO-110-PR-RT-0001 | Flow line Hydraulic Calculation Report |  | BK-W008N-PEDCO-110-PR-RT-0001 | BK-W008N-PEDCO-110-PR-RT-0001 | BK | W008N | PEDCO | 110 | PR | RT | 0001 | F0Z-707834 | IFA | IFC | 2021-11-13 | 2021-11-14 | 2021-11-17 | 1 | 3 | 4 | IFA | 2022-01-15 | 2021-02-01 | 2022-02-05 | -348 | 369 | 21 | IFA | 2022-03-08 | 2022-03-10 | 2022-03-13 | 2 | 3 | 5 | IFA | 2022-05-14 | 2022-06-02 | 2022-06-06 | 19 | 4 | 23 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | AFC | 2022-10-22 | 2022-11-19 | 2022-11-20 | 28 | 1 | 29 | [7 empty] | Modify | 2021-10-30 | 2022-10-08 |  | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 44514 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 44517 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 44562 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 44228 | 1400/11/12 | 44597 | 1400/11/16 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 44614 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 44627 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 44630 | 1400/12/19 | 44633 | 1400/12/22 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 44681 | 1401/02/10 | T-0878 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 44709 | 1401/03/07 | AP | PEDCO-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D02 | [5 empty] | 1401-2294-87489 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D02 | [9 empty] | D04 | IFA | T-1267 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05524 | 44797 | 1401/06/02 | AP | [6 empty] | 1401-2294-235783 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D03 | [9 empty] | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | [10 empty] | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP
2 | 6 | 1 | 1 | 4 | 0 | 0 | 2.6.1.1.4 |  | Data Sheet
2 | 6 | 1 | 1 | 4 | 0 | 1 | 2.6.1.1 | BK-W008N-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - W008N |  | BK-W008N-PEDCO-110-PR-DT-0001 | BK-W008N-PEDCO-110-PR-DT-0001 | BK | W008N | PEDCO | 110 | PR | DT | 0001 | F0Z-707835 | AFC | IFC | 2022-04-26 | 2022-05-08 | 2022-05-14 | 12 | 6 | 18 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-12 |  |  | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W008N-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 44695 | 1401/02/24 | CM | [10 empty] | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-DT-0001_D00 | [11 empty] | NISOC-CRS-BK-W008N-PEDCO-110-PR-DT-0001_D00
2 | 6 | 1 | 2 | 0 | 0 | 0 | 2.6.1.2 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 2 | 1 | 0 | 0 | 2.6.1.2.1 |  | Drawing/Diagram
2 | 6 | 1 | 2 | 1 | 0 | 1 | 2.6.1.2.1 | BK-W008N-PEDCO-110-PI-DW-0001 | Plot Plan Drawing - W008N |  | BK-W008N-PEDCO-110-PI-DW-0001 | BK-W008N-PEDCO-110-PI-DW-0001 | BK | W008N | PEDCO | 110 | PI | DW | 0001 | F5A-707836 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 1 | 0 | 2 | 2.6.1.2.1 | BK-W008N-PEDCO-110-PI-DW-0002 | Piping Plan - W008N |  | BK-W008N-PEDCO-110-PI-DW-0002 | BK-W008N-PEDCO-110-PI-DW-0002 | BK | W008N | PEDCO | 110 | PI | DW | 0002 | F4L-707837 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 1 | 0 | 3 | 2.6.1.2.1 | BK-W008N-PEDCO-110-PI-DW-0003 | Isometric Drawings - W008N |  | BK-W008N-PEDCO-110-PI-DW-0003 | BK-W008N-PEDCO-110-PI-DW-0003 | BK | W008N | PEDCO | 110 | PI | DW | 0003 | F2L-707838 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 1 | 0 | 4 | 2.6.1.2.1 | BK-W008N-PEDCO-110-PI-DG-0001 | Material Flow Diagram - W008N |  | BK-W008N-PEDCO-110-PI-DG-0001 | BK-W008N-PEDCO-110-PI-DG-0001 | BK | W008N | PEDCO | 110 | PI | DG | 0001 | F2A-707839 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 2022-06-28 | 2022-07-05 | 34 | 7 | 41 | IFA | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-08 |  |  | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 44521 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D00 | [5 empty] | 1401-2294-122170 | 44740 | 1401/04/07 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D00 | [9 empty] | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D01 | [11 empty] | NISOC-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D01
2 | 6 | 1 | 2 | 2 | 0 | 0 | 2.6.1.2.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 2 | 2 | 0 | 1 | 2.6.1.2.2 | BK-W008N-PEDCO-110-PI-LI-0001 | Piping Support List - W008N |  | BK-W008N-PEDCO-110-PI-LI-0001 | BK-W008N-PEDCO-110-PI-LI-0001 | BK | W008N | PEDCO | 110 | PI | LI | 0001 | F0Z-707840 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 2 | 0 | 2 | 2.6.1.2.2 | BK-W008N-PEDCO-110-PI-LI-0002 | Critical Line List - W008N |  | BK-W008N-PEDCO-110-PI-LI-0002 | BK-W008N-PEDCO-110-PI-LI-0002 | BK | W008N | PEDCO | 110 | PI | LI | 0002 | F0Z-707841 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 3 | 0 | 0 | 2.6.1.2.3 |  | Report
2 | 6 | 1 | 2 | 3 | 0 | 1 | 2.6.1.2.3 | BK-W008N-PEDCO-110-PI-RT-0001 | PDMS Model Review Report (60%) - W008N |  | BK-W008N-PEDCO-110-PI-RT-0001 | BK-W008N-PEDCO-110-PI-RT-0001 | BK | W008N | PEDCO | 110 | PI | RT | 0001 | F0Z-707842 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 3 | 0 | 2 | 2.6.1.2.3 | BK-W008N-PEDCO-110-PI-RT-0002 | PDMS Model Review Report (90%) - W008N |  | BK-W008N-PEDCO-110-PI-RT-0002 | BK-W008N-PEDCO-110-PI-RT-0002 | BK | W008N | PEDCO | 110 | PI | RT | 0002 | F0Z-707843 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 0 | 2.6.1.2.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 2 | 4 | 0 | 1 | 2.6.1.2 | BK-W008N-PEDCO-110-PI-MT-0001 | MTO For Pipes - W008N |  | BK-W008N-PEDCO-110-PI-MT-0001 | BK-W008N-PEDCO-110-PI-MT-0001 | BK | W008N | PEDCO | 110 | PI | MT | 0001 | F8Z-707844 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-25 |  |  | D00 | IFI | T-1545 | 44859 | 1401/08/03 | T-1545 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1545 | 2022-10-25 | 1401/08/03 | T-1545 | 44859 | 1401/08/03 | [34 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 2 | 2.6.1.2 | BK-W008N-PEDCO-110-PI-MT-0002 | MTO For Fittings - W008N |  | BK-W008N-PEDCO-110-PI-MT-0002 | BK-W008N-PEDCO-110-PI-MT-0002 | BK | W008N | PEDCO | 110 | PI | MT | 0002 | F8Z-707845 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 3 | 2.6.1.2 | BK-W008N-PEDCO-110-PI-MT-0003 | MTO For Flanges - W008N |  | BK-W008N-PEDCO-110-PI-MT-0003 | BK-W008N-PEDCO-110-PI-MT-0003 | BK | W008N | PEDCO | 110 | PI | MT | 0003 | F8Z-707846 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 4 | 2.6.1.2 | BK-W008N-PEDCO-110-PI-MT-0004 | MTO For Manual Valves - W008N |  | BK-W008N-PEDCO-110-PI-MT-0004 | BK-W008N-PEDCO-110-PI-MT-0004 | BK | W008N | PEDCO | 110 | PI | MT | 0004 | F8Z-707847 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 5 | 2.6.1.2 | BK-W008N-PEDCO-110-PI-MT-0005 | MTO For Gaskets - W008N |  | BK-W008N-PEDCO-110-PI-MT-0005 | BK-W008N-PEDCO-110-PI-MT-0005 | BK | W008N | PEDCO | 110 | PI | MT | 0005 | F8Z-707848 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 6 | 2.6.1.2 | BK-W008N-PEDCO-110-PI-MT-0006 | MTO For Bolt & Nuts - W008N |  | BK-W008N-PEDCO-110-PI-MT-0006 | BK-W008N-PEDCO-110-PI-MT-0006 | BK | W008N | PEDCO | 110 | PI | MT | 0006 | F8Z-707849 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 3 | 0 | 0 | 0 | 2.6.1.3 |  | Pipeline & Flow line | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 3 | 1 | 0 | 0 | 2.6.1.3.1 |  | Drawings | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 3 | 1 | 0 | 1 | 2.6.1.3.1 | BK-W008N-PEDCO-110-PL-DW-0002 | Flow line Transversal Drawings - W008N |  | BK-W008N-PEDCO-110-PL-DW-0002 | BK-W008N-PEDCO-110-PL-DW-0002 | BK | W008N | PEDCO | 110 | PL | DW | 0002 | F4A-707850 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 3 | 2 | 0 | 0 | 2.6.1.3.2 |  | List
2 | 6 | 1 | 3 | 2 | 0 | 1 | 2.6.1.3.2 | BK-W008N-PEDCO-110-PL-LI-0001 | Road Crossing Location List |  | BK-W008N-PEDCO-110-PL-LI-0001 | BK-W008N-PEDCO-110-PL-LI-0001 | BK | W008N | PEDCO | 110 | PL | LI | 0001 | F0Z-707851 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 3 | 3 | 0 | 0 | 2.6.1.3.3 |  | MTO
2 | 6 | 1 | 3 | 3 | 0 | 1 | 2.6.1.3 | BK-W008N-PEDCO-110-PL-MT-0001 | MTO For Line Pipes (Flow lines) - W008N |  | BK-W008N-PEDCO-110-PL-MT-0001 | BK-W008N-PEDCO-110-PL-MT-0001 | BK | W008N | PEDCO | 110 | PL | MT | 0001 | F8Z-707852 | IFI | IFI | 2021-09-05 | 2021-08-30 | 2021-09-05 | -6 | 6 | 0 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PL-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 44430 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 |  |  |  |  | PEDCO-CRS-BK-W008N-PEDCO-110-PL-MT-0001_D00 | [5 empty] | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PL-MR-0001_D00
2 | 6 | 1 | 4 | 0 | 0 | 0 | 2.6.1.4 |  | Control & Instrumentation
2 | 6 | 1 | 4 | 1 | 0 | 0 | 2.6.1.4.1 |  | Drawing/Diagram
2 | 6 | 1 | 4 | 1 | 0 | 1 | 2.6.1.4.1 | BK-W008N-PEDCO-110-IN-PY-0001 | Instrument Location Layout Drawing - W008N |  | BK-W008N-PEDCO-110-IN-PY-0001 | BK-W008N-PEDCO-110-IN-PY-0001 | BK | W008N | PEDCO | 110 | IN | PY | 0001 | F2J-707853 | AFC | IFC | 2022-08-29 | 2022-09-26 | 2022-10-02 | 28 | 6 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-15 |  |  | D00 | IFC | T-1277 | 44788 | 1401/05/24 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05539 | 44800 | 1401/06/05 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238110 | 44830 | 1401/07/04 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1277 | 2022-08-15 | 1401/05/24 |  |  |  | BK-SUR-ENG-INS-01-05539 | 44800 | 1401/06/05 | CM-C2 | [6 empty] | 1401-2294-238110 | 2022-09-26 | 1401/07/04 | 44836 | 1401/07/10 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 4 | 2 | 0 | 0 | 2.6.1.4.2 |  | MTO
2 | 6 | 1 | 4 | 2 | 0 | 1 | 2.6.1.4 | BK-W008N-PEDCO-110-IN-MT-0001 | MTO For Instrument Tube and Fitting - W008N |  | BK-W008N-PEDCO-110-IN-MT-0001 | BK-W008N-PEDCO-110-IN-MT-0001 | BK | W008N | PEDCO | 110 | IN | MT | 0001 | F8Z-707854 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-14 |  |  | D02 | IFI | T-0451 | 44573 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0236 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02140 | 44528 | 1400/09/08 | RJ-C4 | [6 empty] | 1400-2294-283474 | 2021-11-21 | 1400/08/30 | 44529 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 44548 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 44562 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D00 | [5 empty] | 1400-2294-347953 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D00 | [9 empty] | D02 | IFI | T-0451 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D01 | [5 empty] | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D01
2 | 6 | 1 | 4 | 2 | 0 | 2 | 2.6.1.4 | BK-W008N-PEDCO-110-IN-MT-0002 | MTO For Instrument Cable Tray - W008N |  | BK-W008N-PEDCO-110-IN-MT-0002 | BK-W008N-PEDCO-110-IN-MT-0002 | BK | W008N | PEDCO | 110 | IN | MT | 0002 | F8Z-707855 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-14 |  |  | D02 | IFI | T-0451 | 44573 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0236 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02140 | 44528 | 1400/09/08 | RJ-C4 | [6 empty] | 1400-2294-283474 | 2021-11-21 | 1400/08/30 | 44529 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 44548 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 44562 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D00 | [5 empty] | 1400-2294-347953 | 44564 | 1400/10/13 | 44566 | 1400/10/15 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D00 | [9 empty] | D02 | IFI | T-0451 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 44587 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D01 | [5 empty] | 1400-2294-394002 | 44594 | 1400/11/13 | 44599 | 1400/11/18 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D01
2 | 6 | 1 | 5 | 0 | 0 | 0 | 2.6.1.5 |  | Safety
2 | 6 | 1 | 5 | 1 | 0 | 0 | 2.6.1.5.1 |  | Drawing/Diagram
2 | 6 | 1 | 5 | 1 | 0 | 1 | 2.6.1.5.1 | BK-W008N-PEDCO-110-SA-PY-0001 | Hazardous Area Classification Layout - W008N |  | BK-W008N-PEDCO-110-SA-PY-0001 | BK-W008N-PEDCO-110-SA-PY-0001 | BK | W008N | PEDCO | 110 | SA | PY | 0001 | F2L-707856 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 5 | 1 | 0 | 2 | 2.6.1.5.1 | BK-W008N-PEDCO-110-SA-PY-0002 | Safety & Fire Fighting Equipment Location Layout - W008N |  | BK-W008N-PEDCO-110-SA-PY-0002 | BK-W008N-PEDCO-110-SA-PY-0002 | BK | W008N | PEDCO | 110 | SA | PY | 0002 | F2L-707857 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 5 | 1 | 0 | 3 | 2.6.1.5.1 | BK-W008N-PEDCO-110-SA-PY-0003 | Escape Route & Safety Sign Layout - W008N |  | BK-W008N-PEDCO-110-SA-PY-0003 | BK-W008N-PEDCO-110-SA-PY-0003 | BK | W008N | PEDCO | 110 | SA | PY | 0003 | F2L-707858 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 5 | 2 | 0 | 0 | 2.6.1.5.2 |  | List
2 | 6 | 1 | 5 | 2 | 0 | 1 | 2.6.1.5.2 | BK-W008N-PEDCO-110-SA-LI-0001 | Hazard Source List - W008N |  | BK-W008N-PEDCO-110-SA-LI-0001 | BK-W008N-PEDCO-110-SA-LI-0001 | BK | W008N | PEDCO | 110 | SA | LI | 0001 | F0Z-707859 | AFC | IFC | 2021-11-23 | 2021-11-30 | 2021-12-06 | 7 | 6 | 13 | IFA | 2022-02-16 | 2022-03-08 | 2022-03-06 | 20 | -2 | 18 | IFA | 2022-04-26 | 2022-06-07 | 2022-06-11 | 42 | 4 | 46 | AFC | 2022-08-09 | 2022-09-01 | 2022-09-04 | 23 | 3 | 26 | AFC | 2022-09-21 | 2022-10-05 | 2022-10-11 | 14 | 6 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-09 | 2022-09-07 |  | D04 | AFC | T-1379 | 44811 | 1401/06/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249440 | 44839 | 1401/07/13 | 44845 | 1401/07/19 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0544 | 44594 | 1400/11/13 | [13 empty] | 1400-2294-435413 | 44628 | 1400/12/15 | 44626 | 1400/12/15 | CM | NISOC-CRS-BK-W008N-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0806 | 44663 | 1401/01/23 | [13 empty] | 1401-2294-92282 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-W008N-PEDCO-110-SA-LI-0001_D01 | [9 empty] | D03 | AFC | T-1197 | 44768 | 1401/05/04 | [13 empty] | 1401-2294-205788 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-W008N-PEDCO-110-SA-LI-0001_D02 | [9 empty] | D04 | AFC | T-1379 | 44811 | 1401/06/16 | [13 empty] | 1401-2294-249440 | 44839 | 1401/07/13 | 44845 | 1401/07/19 | AP
2 | 6 | 1 | 5 | 3 | 0 | 0 | 2.6.1.5.3 |  | MTO
2 | 6 | 1 | 5 | 3 | 0 | 1 | 2.6.1.5 | BK-W008N-PEDCO-110-SA-MT-0001 | MTO For Fire Fighting & Safety Equipment - W008N |  | BK-W008N-PEDCO-110-SA-MT-0001 | BK-W008N-PEDCO-110-SA-MT-0001 | BK | W008N | PEDCO | 110 | SA | MT | 0001 | F8Z-707860 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 5 | 3 | 0 | 2 | 2.6.1.5 | BK-W008N-PEDCO-110-SA-MT-0002 | MTO For Safety Sign - W008N |  | BK-W008N-PEDCO-110-SA-MT-0002 | BK-W008N-PEDCO-110-SA-MT-0002 | BK | W008N | PEDCO | 110 | SA | MT | 0002 | F8Z-707861 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 6 | 0 | 0 | 0 | 2.6.1.6 |  | Architecture
2 | 6 | 1 | 6 | 1 | 0 | 0 | 2.6.1.6.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 6 | 1 | 0 | 1 | 2.6.1.6 | BK-W008N-PEDCO-110-AR-DW-0001 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W008N |  | BK-W008N-PEDCO-110-AR-DW-0001 | BK-W008N-PEDCO-110-AR-DW-0001 | BK | W008N | PEDCO | 110 | AR | DW | 0001 | F4B-707862 | AFC | IFC | 2022-03-12 | 2022-03-05 | 2022-03-08 | -7 | 3 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-26 |  |  | D00 | IFC | T-0640 | 44618 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03400 | 44628 | 1400/12/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-435028 | 44625 | 1400/12/14 | 44628 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0640 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-ARC-00-03400 | 44628 | 1400/12/18 | CM-C2 | [6 empty] | 1400-2294-435028 | 2022-03-05 | 1400/12/14 | 44628 | 1400/12/17 | AP | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 7 | 0 | 0 | 0 | 2.6.1.7 |  | Civil
2 | 6 | 1 | 7 | 1 | 0 | 0 | 2.6.1.7.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 7 | 1 | 0 | 1 | 2.6.1.7.1 | BK-W008N-PEDCO-110-CV-PY-0001 | General Civil Layout -W008N |  | BK-W008N-PEDCO-110-CV-PY-0001 | BK-W008N-PEDCO-110-CV-PY-0001 | BK | W008N | PEDCO | 110 | CV | PY | 0001 | F4A-707863 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 7 | 1 | 0 | 2 | 2.6.1.7.1 | BK-W008N-PEDCO-110-CV-PY-0002 | Civil and Structural drawings -W008N |  | BK-W008N-PEDCO-110-CV-PY-0002 | BK-W008N-PEDCO-110-CV-PY-0002 | BK | W008N | PEDCO | 110 | CV | PY | 0002 | F4S-707864 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 7 | 1 | 0 | 3 | 2.6.1.7.1 | BK-W008N-PEDCO-110-CV-DW-0001 | Rough Grading Plans -W008N |  | BK-W008N-PEDCO-110-CV-DW-0001 | BK-W008N-PEDCO-110-CV-DW-0001 | BK | W008N | PEDCO | 110 | CV | DW | 0001 | F4S-707865 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 7 | 2 | 0 | 0 | 2.6.1.7.2 |  | Calculation
2 | 6 | 1 | 7 | 2 | 0 | 1 | 2.6.1.7.2 | BK-W008N-PEDCO-110-CV-CN-0001 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W008N |  | BK-W008N-PEDCO-110-CV-CN-0001 | BK-W008N-PEDCO-110-CV-CN-0001 | BK | W008N | PEDCO | 110 | CV | CN | 0001 | F0Z-707866 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 7 | 3 | 0 | 0 | 2.6.1.7.3 |  | MTO
2 | 6 | 1 | 7 | 3 | 0 | 1 | 2.6.1.7 | BK-W008N-PEDCO-110-CV-MT-0001 | MTO For Civil Works |  | BK-W008N-PEDCO-110-CV-MT-0001 | BK-W008N-PEDCO-110-CV-MT-0001 | BK | W008N | PEDCO | 110 | CV | MT | 0001 | F8Z-707867 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 8 | 0 | 0 | 0 | 2.6.1.8 |  | Structure
2 | 6 | 1 | 8 | 1 | 0 | 0 | 2.6.1.8.1 |  | Drawing/Diagram
2 | 6 | 1 | 8 | 1 | 0 | 1 | 2.6.1.8.1 | BK-W008N-PEDCO-110-ST-DW-0002 | Platform Structure Drawing - W008N |  | BK-W008N-PEDCO-110-ST-DW-0002 | BK-W008N-PEDCO-110-ST-DW-0002 | BK | W008N | PEDCO | 110 | ST | DW | 0002 | F4M-707868 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 8 | 2 | 0 | 0 | 2.6.1.8.2 |  | MTO
2 | 6 | 1 | 8 | 2 | 0 | 1 | 2.6.1.8 | BK-W008N-PEDCO-110-ST-MT-0001 | MTO For Structural Works - W008N |  | BK-W008N-PEDCO-110-ST-MT-0001 | BK-W008N-PEDCO-110-ST-MT-0001 | BK | W008N | PEDCO | 110 | ST | MT | 0001 | F8Z-707869 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 9 | 0 | 0 | 0 | 2.6.1.9 |  | Survey (Topography) & Geotechnic/Geoelectric
2 | 6 | 1 | 9 | 1 | 0 | 0 | 2.6.1.9.1 |  | Geotechnic
2 | 6 | 1 | 9 | 1 | 1 | 0 | 2.6.9.1.1 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 9 | 1 | 1 | 1 | 2.6.1.9.1.1.1 | BK-W008N-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - W008N |  | BK-W008N-PEDCO-110-GT-RT-0001 | BK-W008N-PEDCO-110-GT-RT-0001 | BK | W008N | PEDCO | 110 | GT | RT | 0001 | F0Z-707870 | IFI | IFC | 2022-06-25 | 2022-06-21 | 2022-06-25 | -4 | 4 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-11 |  |  | D00 | IFC | T-1059 | 44723 | 1401/03/21 | T-1059 | 44723 | 1401/03/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-111566 | 44733 | 1401/03/31 | 44737 | 1401/04/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1059 | 2022-06-11 | 1401/03/21 | T-1059 | 44723 | 1401/03/21 | [10 empty] | 1401-2294-111566 | 2022-06-21 | 1401/03/31 | 44737 | 1401/04/04 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 1 | 9 | 1 | 2 | 0 | 2.6.9.1.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 1 | 9 | 1 | 2 | 1 | 2.6.1.9.1.2.1 | BK-W008N-PEDCO-110-SU-DW-0001 | Flow line Plan & Profile Drawings - W008N |  | BK-W008N-PEDCO-110-SU-DW-0001 | BK-W008N-PEDCO-110-SU-DW-0001 | BK | W008N | PEDCO | 110 | SU | DW | 0001 | F4A-707871 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 0 | 0 | 0 | 0 | 2.6.2 |  | Procurement Engineering
2 | 6 | 2 | 1 | 0 | 0 | 0 | 2.6.2.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 1 | 0 | 0 | 2.6.2.1.1 |  | Pipes
2 | 6 | 2 | 1 | 1 | 1 | 0 | 2.6.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 1 | 1 | 1 | 2.6.2.1.1.1.1 | BK-W008N-PEDCO-110-PI-MR-0001 | PMR For Pipes - W008N |  | BK-W008N-PEDCO-110-PI-MR-0001 | BK-W008N-PEDCO-110-PI-MR-0001 | BK | W008N | PEDCO | 110 | PI | MR | 0001 | F0Z-707872 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 1 | 2 | 0 | 2.6.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 1 | 2 | 1 | 2.6.2.1.1.2.1 | BK-W008N-PEDCO-110-PI-TB-0001 | TBE For Pipes - W008N |  | BK-W008N-PEDCO-110-PI-TB-0001 | BK-W008N-PEDCO-110-PI-TB-0001 | BK | W008N | PEDCO | 110 | PI | TB | 0001 | F0Z-707873 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 2 | 0 | 0 | 2.6.2.1.2 |  | Fittings
2 | 6 | 2 | 1 | 2 | 1 | 0 | 2.6.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 2 | 1 | 1 | 2.6.2.1.2.1.1 | BK-W008N-PEDCO-110-PI-MR-0002 | PMR For Fittings - W008N |  | BK-W008N-PEDCO-110-PI-MR-0002 | BK-W008N-PEDCO-110-PI-MR-0002 | BK | W008N | PEDCO | 110 | PI | MR | 0002 | F0Z-707874 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 2 | 2 | 0 | 2.6.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 2 | 2 | 1 | 2.6.2.1.2.2.1 | BK-W008N-PEDCO-110-PI-TB-0002 | TBE For Fitting - W008N |  | BK-W008N-PEDCO-110-PI-TB-0002 | BK-W008N-PEDCO-110-PI-TB-0002 | BK | W008N | PEDCO | 110 | PI | TB | 0002 | F0Z-707875 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 3 | 0 | 0 | 2.6.2.1.3 |  | Flanges
2 | 6 | 2 | 1 | 3 | 1 | 0 | 2.6.1.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 3 | 1 | 1 | 2.6.2.1.3.1.1 | BK-W008N-PEDCO-110-PI-MR-0003 | PMR For Flanges - W008N |  | BK-W008N-PEDCO-110-PI-MR-0003 | BK-W008N-PEDCO-110-PI-MR-0003 | BK | W008N | PEDCO | 110 | PI | MR | 0003 | F0Z-707876 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 3 | 2 | 0 | 2.6.1.3.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 3 | 2 | 1 | 2.6.2.1.3.2.1 | BK-W008N-PEDCO-110-PI-TB-0003 | TBE For Flanges - W008N |  | BK-W008N-PEDCO-110-PI-TB-0003 | BK-W008N-PEDCO-110-PI-TB-0003 | BK | W008N | PEDCO | 110 | PI | TB | 0003 | F0Z-707877 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 4 | 0 | 0 | 2.6.2.1.4 |  | Manual Valves
2 | 6 | 2 | 1 | 4 | 1 | 0 | 2.6.1.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 4 | 1 | 1 | 2.6.2.1.4.1.1 | BK-W008N-PEDCO-110-PI-MR-0004 | PMR For Manual Valves - W008N |  | BK-W008N-PEDCO-110-PI-MR-0004 | BK-W008N-PEDCO-110-PI-MR-0004 | BK | W008N | PEDCO | 110 | PI | MR | 0004 | F0Z-707878 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 4 | 2 | 0 | 2.6.1.4.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 4 | 2 | 1 | 2.6.2.1.4.2.1 | BK-W008N-PEDCO-110-PI-TB-0004 | TBE For Manual Valves - W008N |  | BK-W008N-PEDCO-110-PI-TB-0004 | BK-W008N-PEDCO-110-PI-TB-0004 | BK | W008N | PEDCO | 110 | PI | TB | 0004 | F0Z-707879 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 5 | 0 | 0 | 2.6.2.1.5 |  | Gaskets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 5 | 1 | 0 | 2.6.1.5.1 |  | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 5 | 1 | 1 | 2.6.2.1.5.1.1 | BK-W008N-PEDCO-110-PI-MR-0005 | PMR For Gaskets - W008N |  | BK-W008N-PEDCO-110-PI-MR-0005 | BK-W008N-PEDCO-110-PI-MR-0005 | BK | W008N | PEDCO | 110 | PI | MR | 0005 | F0Z-707880 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 5 | 2 | 0 | 2.6.1.5.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 5 | 2 | 1 | 2.6.2.1.5.2.1 | BK-W008N-PEDCO-110-PI-TB-0005 | TBE For Gaskets - W008N |  | BK-W008N-PEDCO-110-PI-TB-0005 | BK-W008N-PEDCO-110-PI-TB-0005 | BK | W008N | PEDCO | 110 | PI | TB | 0005 | F0Z-707881 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 6 | 0 | 0 | 2.6.2.1.6 |  | Bolt & Nuts | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 6 | 1 | 0 | 2.6.1.6.1 |  | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 6 | 1 | 1 | 2.6.2.1.6.1.1 | BK-W008N-PEDCO-110-PI-MR-0006 | PMR For Bolt/Nuts - W008N |  | BK-W008N-PEDCO-110-PI-MR-0006 | BK-W008N-PEDCO-110-PI-MR-0006 | BK | W008N | PEDCO | 110 | PI | MR | 0006 | F0Z-707882 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 6 | 2 | 0 | 2.6.1.6.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 6 | 2 | 1 | 2.6.2.1.6.2.1 | BK-W008N-PEDCO-110-PI-TB-0006 | TBE For Bolt/Nuts - W008N |  | BK-W008N-PEDCO-110-PI-TB-0006 | BK-W008N-PEDCO-110-PI-TB-0006 | BK | W008N | PEDCO | 110 | PI | TB | 0006 | F0Z-707883 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 7 | 0 | 0 | 2.6.2.1.7 |  | Sampling Connection
2 | 6 | 2 | 1 | 7 | 1 | 0 | 2.6.1.7.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 7 | 1 | 1 | 2.6.2.1.7.1.1 | BK-W008N-PEDCO-110-PI-MR-0007 | PMR For Sampling Connection Set - W008N |  | BK-W008N-PEDCO-110-PI-MR-0007 | BK-W008N-PEDCO-110-PI-MR-0007 | BK | W008N | PEDCO | 110 | PI | MR | 0007 | F0Z-707884 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 7 | 2 | 0 | 2.6.1.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 7 | 2 | 1 | 2.6.2.1.7.2.1 | BK-W008N-PEDCO-110-PI-TB-0007 | TBE For Sampling Connection Set - W008N |  | BK-W008N-PEDCO-110-PI-TB-0007 | BK-W008N-PEDCO-110-PI-TB-0007 | BK | W008N | PEDCO | 110 | PI | TB | 0007 | F0Z-707885 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 8 | 0 | 0 | 2.6.2.1.8 |  | Stone Trap
2 | 6 | 2 | 1 | 8 | 1 | 0 | 2.6.1.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 8 | 1 | 1 | 2.6.2.1.8.1.1 | BK-W008N-PEDCO-110-PI-MR-0008 | PMR For Stone Trap - W008N |  | BK-W008N-PEDCO-110-PI-MR-0008 | BK-W008N-PEDCO-110-PI-MR-0008 | BK | W008N | PEDCO | 110 | PI | MR | 0008 | F0Z-707886 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 8 | 2 | 0 | 2.6.1.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 8 | 2 | 1 | 2.6.2.1.8.2.1 | BK-W008N-PEDCO-110-PI-TB-0008 | TBE For Stone Trap - W008N |  | BK-W008N-PEDCO-110-PI-TB-0008 | BK-W008N-PEDCO-110-PI-TB-0008 | BK | W008N | PEDCO | 110 | PI | TB | 0008 | F0Z-707887 | IFI | IFI | 2022-06-07 | 2022-06-14 | 2022-06-15 | 7 | 1 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-24 |  |  | D00 | IFI | T-0996 | 44705 | 1401/03/03 | T-0996 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04515 | 44713 | 1401/03/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-102043 | 44726 | 1401/03/24 | 44727 | 1401/03/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03 | T-0996 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04515 | 44713 | 1401/03/11 | CM-C3 | [6 empty] | 1401-2294-102043 | 2022-06-14 | 1401/03/24 | 44727 | 1401/03/25 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 9 | 0 | 0 | 2.6.2.1.9 |  | Pipe Support
2 | 6 | 2 | 1 | 9 | 1 | 0 | 2.6.1.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 9 | 1 | 1 | 2.6.2.1.9.1.1 | BK-W008N-PEDCO-110-PI-MR-0009 | PMR For Pipe Support - W008N |  | BK-W008N-PEDCO-110-PI-MR-0009 | BK-W008N-PEDCO-110-PI-MR-0009 | BK | W008N | PEDCO | 110 | PI | MR | 0009 | F0Z-707888 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 9 | 2 | 0 | 2.6.1.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 9 | 2 | 1 | 2.6.2.1.9.2.1 | BK-W008N-PEDCO-110-PI-TB-0009 | TBE For Pipe Support - W008N |  | BK-W008N-PEDCO-110-PI-TB-0009 | BK-W008N-PEDCO-110-PI-TB-0009 | BK | W008N | PEDCO | 110 | PI | TB | 0009 | F0Z-707889 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 1 | 9 | 0 | 0 | 2.6.2.1.9 |  | BURN PIT PIPES
2 | 6 | 2 | 1 | 9 | 1 | 0 | 2.6.1.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 9 | 1 | 1 | 2.6.2.1.9.1.1 | BK-W008N-PEDCO-110-PI-MR-0009 | PMR FOR BURN PIT PIPES– W008N |  | BK-W008N-PEDCO-110-PI-MR-0011 | BK-W008N-PEDCO-110-PI-MR-0009 | BK | W008N | PEDCO | 110 | PI | MR | 0009 | F0Z-707888 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [11 empty] | D00 | IFI | T-1550 | 44859 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1550 | 2022-10-25 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2
2 | 6 | 2 | 1 | 9 | 2 | 0 | 2.6.1.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 1 | 9 | 2 | 1 | 2.6.2.1.9.2.1 | BK-W008N-PEDCO-110-PI-TB-0009 | TBE FOR BURN PIT PIPES– W008N |  | BK-W008N-PEDCO-110-PI-TB-0011 | BK-W008N-PEDCO-110-PI-TB-0009 | BK | W008N | PEDCO | 110 | PI | TB | 0009 | F0Z-707889 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14
2 | 6 | 2 | 2 | 0 | 0 | 0 | 2.6.2.2 |  | Pipeline
2 | 6 | 2 | 2 | 1 | 0 | 0 | 2.6.2.2.1 |  | Line Pipe
2 | 6 | 2 | 2 | 1 | 1 | 0 | 2.6.2.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 2 | 1 | 1 | 1 | 2.6.2.2.1.1.1 | BK-W008N-PEDCO-110-PL-MR-0001 | PMR For Line Pipes - W008N |  | BK-W008N-PEDCO-110-PL-MR-0001 | BK-W008N-PEDCO-110-PL-MR-0001 | BK | W008N | PEDCO | 110 | PL | MR | 0001 | F0Z-707890 | IFI | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-23 |  |  | D00 | IFI | T-1529 | 44857 | 1401/08/01 | T-1529 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296595 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1529 | 2022-10-23 | 1401/08/01 | T-1529 | 44857 | 1401/08/01 | [10 empty] | 1401-2294-296595 | 2022-11-05 | 1401/08/14 | 44874 | 1401/08/18 | AP | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 2 | 1 | 2 | 0 | 2.6.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 2 | 1 | 2 | 1 | 2.6.2.2.1.2.1 | BK-W008N-PEDCO-110-PL-TB-0001 | TBE For Line Pipes - W008N |  | BK-W008N-PEDCO-110-PL-TB-0001 | BK-W008N-PEDCO-110-PL-TB-0001 | BK | W008N | PEDCO | 110 | PL | TB | 0001 | F0Z-707891 | IFI | IFI | 2022-03-05 | 2022-03-10 | 2022-03-14 | 5 | 4 | 9 | IFI | 2022-05-28 | 2022-05-31 | 2022-06-07 | 3 | 7 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 44628 | 1400/12/17 | RJ-C4 | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 44634 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | [5 empty] | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00
2 | 6 | 2 | 2 | 2 | 0 | 0 | 2.6.2.2.2 |  | Flow Line Support
2 | 6 | 2 | 2 | 2 | 1 | 0 | 2.6.2.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 2 | 2 | 1 | 1 | 2.6.2.2.2.1.1 | BK-W008N-PEDCO-110-PL-MR-0002 | PMR For Flow Line Support - W008N |  | BK-W008N-PEDCO-110-PL-MR-0002 | BK-W008N-PEDCO-110-PL-MR-0002 | BK | W008N | PEDCO | 110 | PL | MR | 0002 | F0Z-707892 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 2 | 2 | 2 | 0 | 2.6.2.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 2 | 2 | 2 | 1 | 2.6.2.2.2.2.1 | BK-W008N-PEDCO-110-PL-TB-0002 | TBE For Flow Line Support - W008N |  | BK-W008N-PEDCO-110-PL-TB-0002 | BK-W008N-PEDCO-110-PL-TB-0002 | BK | W008N | PEDCO | 110 | PL | TB | 0002 | F0Z-707893 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 3 | 0 | 0 | 0 | 2.6.2.3 |  | Control & Instrumentation
2 | 6 | 2 | 3 | 1 | 0 | 0 | 2.6.2.3.1 |  | WHCP/HPU
2 | 6 | 2 | 3 | 1 | 1 | 0 | 2.6.3.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 3 | 1 | 1 | 1 | 2.6.2.3.1.1.1 | BK-W008N-PEDCO-110-IN-MR-0001 | PMR For WHCP/HPU - W008N |  | BK-W008N-PEDCO-110-IN-MR-0001 | BK-W008N-PEDCO-110-IN-MR-0001 | BK | W008N | PEDCO | 110 | IN | MR | 0001 | F0Z-707894 | IFI | IFI | 2021-11-29 | 2021-12-17 | 2021-12-07 | 18 | -10 | 8 | IFI | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 | IFI | 2022-07-03 | 2022-08-18 | 2022-08-23 | 46 | 5 | 51 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-15 |  |  | D02 | IFI | T-1091 | 44731 | 1401/03/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05243 | 44768 | 1401/05/04 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183563 | 44791 | 1401/05/27 | 44796 | 1401/06/01 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0243 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-INS-00-02170 | 44531 | 1400/09/10 | RJ-C4 |  | BK-SUR-ENG-INS-00-02224 | 44537 | 1400/09/16 | CM-C3 |  | 1400-2294-320808 | 2021-12-17 | 1400/09/26 | 44537 | 1400/09/16 | CM | [10 empty] | D01 | IFI | T-0470 | 44577 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02865 | 44591 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D00 | [5 empty] | 1400-2294-390765 | 44592 | 1400/11/11 | 44593 | 1400/11/12 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D00 | [9 empty] | D02 | IFI | T-1091 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-INS-01-05243 | 44768 | 1401/05/04 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D01 | [5 empty] | 1401-2294-183563 | 44791 | 1401/05/27 | 44796 | 1401/06/01 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D01
2 | 6 | 2 | 3 | 1 | 2 | 0 | 2.6.3.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 3 | 1 | 2 | 1 | 2.6.2.3.1.2.1 | BK-W008N-PEDCO-110-IN-TB-0001 | TBE/TBA For WHCP/HPU - W008N |  | BK-W008N-PEDCO-110-IN-TB-0001 | BK-W008N-PEDCO-110-IN-TB-0001 | BK | W008N | PEDCO | 110 | IN | TB | 0001 | F0Z-707895 | IFI | IFI | 2021-12-15 | 2021-12-14 | 2021-12-15 | -1 | 1 | 0 | IFI | 2022-03-05 | 2022-04-04 | 2022-04-09 | 30 | 5 | 35 | IFI | 2022-07-18 | 2022-07-06 | 2022-07-12 | -12 | 6 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-01 |  |  | D02 | IFI | T-1136 | 44746 | 1401/04/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05364 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-132654 | 44748 | 1401/04/15 | 44754 | 1401/04/21 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0286 | 2021-12-01 | 1400/09/10 |  |  |  | BK-SUR-ENG-INS-00-02297 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-317340 | 2021-12-14 | 1400/09/23 | 44545 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0602 | 44611 | 1400/11/30 |  |  |  | BK-SUR-ENG-INS-00-03345 | 44625 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D00 | [5 empty] | 1401-2294-9652 | 44655 | 1401/01/15 | 44660 | 1401/01/20 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D00 | [9 empty] | D02 | IFI | T-1136 | 44746 | 1401/04/13 |  |  |  | BK-SUR-ENG-INS-01-05364 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D01 | [5 empty] | 1401-2294-132654 | 44748 | 1401/04/15 | 44754 | 1401/04/21 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D01
2 | 6 | 2 | 3 | 2 | 0 | 0 | 2.6.2.3.2 |  | Field Instrumentations
2 | 6 | 2 | 3 | 2 | 1 | 0 | 2.6.3.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 3 | 2 | 1 | 1 | 2.6.2.3.2.1.1 | BK-W008N-PEDCO-110-IN-MR-0002 | PMR For Field Instrumentations - W008N |  | BK-W008N-PEDCO-110-IN-MR-0002 | BK-W008N-PEDCO-110-IN-MR-0002 | BK | W008N | PEDCO | 110 | IN | MR | 0002 | F0Z-707896 | IFI | IFI | 2021-12-27 | 2022-01-21 | 2021-01-25 | 25 | -361 | -336 | IFI | 2022-08-13 | 2022-09-08 | 2022-09-13 | 26 | 5 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-13 |  |  | D01 | IFI | T-1218 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 44557 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/10/01 | 44221 | 1400/11/05 | CM | [10 empty] | D01 | IFI | T-1218 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0002_D00 | [5 empty] | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MR-0002_D00
2 | 6 | 2 | 3 | 2 | 2 | 0 | 2.6.3.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 3 | 2 | 2 | 1 | 2.6.2.3.2.2.1 | BK-W008N-PEDCO-110-IN-TB-0002 | TBE/TBA For Field Instrumentations - W008N |  | BK-W008N-PEDCO-110-IN-TB-0002 | BK-W008N-PEDCO-110-IN-TB-0002 | BK | W008N | PEDCO | 110 | IN | TB | 0002 | F0Z-707897 | IFI | IFI | 2022-06-11 | 2022-06-21 | 2022-07-05 | 10 | 14 | 24 | IFI | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-26 |  |  | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W008N-PEDCO-110-IN-TB-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | T-1012 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-05635 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-111541 | 2022-06-21 | 1401/03/31 | 44747 | 1401/04/14 | RJ | [10 empty] | D01 | IFI | T-1556 | 44860 | 1401/08/04 | T-1556 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06149 | 44874 | 1401/08/18 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-TB-0002_D00 | [11 empty] | NISOC-CRS-BK-W008N-PEDCO-110-IN-TB-0002_D00
2 | 6 | 2 | 3 | 3 | 0 | 0 | 2.6.2.3.3 |  | Instrument Bulk Items
2 | 6 | 2 | 3 | 3 | 1 | 0 | 2.6.3.3.1 |  | Purchase Material Requisition (PMR)
2 | 6 | 2 | 3 | 3 | 1 | 1 | 2.6.2.3.3.1.1 | BK-W008N-PEDCO-110-IN-MR-0003 | PMR For Instrument Bulk Items - W008N |  | BK-W008N-PEDCO-110-IN-MR-0003 | BK-W008N-PEDCO-110-IN-MR-0003 | BK | W008N | PEDCO | 110 | IN | MR | 0003 | F0Z-707898 | IFI | IFI | 2022-01-30 | 2021-01-31 | 2022-02-01 | -364 | 366 | 2 | IFI | 2022-09-18 | 2022-09-21 | 2022-10-02 | 3 | 11 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-16 |  |  | D01 | IFI | T-1351 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W008N-PEDCO-110-IN-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C2 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 44593 | 1400/11/12 | CM | [10 empty] | D01 | IFI | T-1351 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0003_D00 | [5 empty] | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W008N-PEDCO-110-IN-MR-0003_D00
2 | 6 | 2 | 3 | 3 | 2 | 0 | 2.6.3.3.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 3 | 3 | 2 | 1 | 2.6.2.3.3.2.1 | BK-W008N-PEDCO-110-IN-TB-0003 | TBE/TBA For Instrument Bulk Items-W008N |  | BK-W008N-PEDCO-110-IN-TB-0003 | BK-W008N-PEDCO-110-IN-TB-0003 | BK | W008N | PEDCO | 110 | IN | TB | 0003 | F0Z-707899 | IFI | IFI | 2022-02-16 | 2022-03-19 | 2022-03-14 | 31 | -5 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-02 |  |  | D00 | IFI | T-0539 | 44594 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443275 | 44639 | 1400/12/19 | 44634 | 1400/12/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 44606 | 1400/11/25 | CM-C2 | [6 empty] | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 44634 | 1400/12/23 | CM
2 | 6 | 2 | 4 | 0 | 0 | 0 | 2.6.2.4 |  | Safety & Fire Fighting
2 | 6 | 2 | 4 | 1 | 0 | 0 | 2.6.2.4.1 |  | Fire Fighting and Safety Equipment
2 | 6 | 2 | 4 | 1 | 1 | 0 | 2.6.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 4 | 1 | 1 | 1 | 2.6.2.4.1.1.1 | BK-W008N-PEDCO-110-SA-MR-0001 | PMR For Fire Fighting and Safety Equipment - W008N |  | BK-W008N-PEDCO-110-SA-MR-0001 | BK-W008N-PEDCO-110-SA-MR-0001 | BK | W008N | PEDCO | 110 | SA | MR | 0001 | F0Z-707900 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 4 | 1 | 2 | 0 | 2.6.4.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 4 | 1 | 2 | 1 | 2.6.2.4.1.2.1 | BK-W008N-PEDCO-110-SA-TB-0001 | TBE For Fire Fighting and Safety Equipment - W008N |  | BK-W008N-PEDCO-110-SA-TB-0001 | BK-W008N-PEDCO-110-SA-TB-0001 | BK | W008N | PEDCO | 110 | SA | TB | 0001 | F0Z-707901 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 4 | 2 | 0 | 0 | 2.6.2.4.2 |  | Safety Sign
2 | 6 | 2 | 4 | 2 | 1 | 0 | 2.6.4.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 4 | 2 | 1 | 1 | 2.6.2.4.2.1.1 | BK-W008N-PEDCO-110-SA-MR-0002 | PMR For Fire Safety Sign - W008N |  | BK-W008N-PEDCO-110-SA-MR-0002 | BK-W008N-PEDCO-110-SA-MR-0002 | BK | W008N | PEDCO | 110 | SA | MR | 0002 | F0Z-707902 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 4 | 2 | 2 | 0 | 2.6.4.2.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 4 | 2 | 2 | 1 | 2.6.2.4.2.2.1 | BK-W008N-PEDCO-110-SA-TB-0002 | TBE For Fire Safety Sign - W008N |  | BK-W008N-PEDCO-110-SA-TB-0002 | BK-W008N-PEDCO-110-SA-TB-0002 | BK | W008N | PEDCO | 110 | SA | TB | 0002 | F0Z-707903 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 5 | 0 | 0 | 0 | 2.6.2.5 |  | Structure
2 | 6 | 2 | 5 | 1 | 0 | 0 | 2.6.2.5.1 |  | Steel Structure Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 5 | 1 | 1 | 0 | 2.6.5.1.1 |  | Purchase Material Requisition (PMR)
2 | 6 | 2 | 5 | 1 | 1 | 1 | 2.6.2.5.1.1.1 | BK-W008N-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - W008N |  | BK-W008N-PEDCO-110-ST-MR-0001 | BK-W008N-PEDCO-110-ST-MR-0001 | BK | W008N | PEDCO | 110 | ST | MR | 0001 | F0Z-707904 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 5 | 1 | 2 | 0 | 2.6.5.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 5 | 1 | 2 | 1 | 2.6.2.5.1.2.1 | BK-W008N-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - W008N |  | BK-W008N-PEDCO-110-ST-TB-0001 | BK-W008N-PEDCO-110-ST-TB-0001 | BK | W008N | PEDCO | 110 | ST | TB | 0001 | F0Z-707905 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 5 | 2 | 0 | 0 | 2.6.2.5.2 |  | Anchor Bolts | [61 empty] | Moved to Field
2 | 6 | 2 | 5 | 2 | 1 | 0 | 2.6.5.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 5 | 2 | 1 | 1 | 2.6.2.5.2.1.1 | BK-W008N-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - W008N |  | BK-W008N-PEDCO-110-ST-MR-0002 | BK-W008N-PEDCO-110-ST-MR-0002 | BK | W008N | PEDCO | 110 | ST | MR | 0002 | F0Z-707906 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 5 | 2 | 2 | 0 | 2.6.5.2.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 5 | 2 | 2 | 1 | 2.6.2.5.2.2.1 | BK-W008N-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - W008N |  | BK-W008N-PEDCO-110-ST-TB-0002 | BK-W008N-PEDCO-110-ST-TB-0002 | BK | W008N | PEDCO | 110 | ST | TB | 0002 | F0Z-707907 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 6 | 0 | 0 | 0 | 2.6.2.6 |  | Civil
2 | 6 | 2 | 6 | 1 | 0 | 0 | 2.6.2.6.1 |  | Geomembrane | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 6 | 1 | 1 | 0 | 2.6.6.1.1 |  | Purchase Material Requisition (PMR)
2 | 6 | 2 | 6 | 1 | 1 | 1 | 2.6.2.6.1.1.1 | BK-W008N-PEDCO-110-CV-MR-0001 | PMR For Geomembrane - W008N |  | BK-W008N-PEDCO-110-CV-MR-0001 | BK-W008N-PEDCO-110-CV-MR-0001 | BK | W008N | PEDCO | 110 | CV | MR | 0001 | F0Z-707908 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 6 | 1 | 2 | 0 | 2.6.6.1.2 |  | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 6 | 1 | 2 | 1 | 2.6.2.6.1.2.1 | BK-W008N-PEDCO-110-CV-TB-0001 | TBE For Geomembrane - W008N |  | BK-W008N-PEDCO-110-CV-TB-0001 | BK-W008N-PEDCO-110-CV-TB-0001 | BK | W008N | PEDCO | 110 | CV | TB | 0001 | F0Z-707909 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 7 | 0 | 0 | 0 | 2.6.2.7 |  | Geotextile | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 7 | 0 | 1 | 0 | 2.6.2.7.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 7 | 0 | 1 | 1 | 2.6.2.7.1.1 | BK-W008N-PEDCO-110-CV-MR-0002 | PMR For Geotextile - W008N |  | BK-W008N-PEDCO-110-CV-MR-0002 | BK-W008N-PEDCO-110-CV-MR-0002 | BK | W008N | PEDCO | 110 | CV | MR | 0002 | F0Z-707910 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 2 | 7 | 0 | 2 | 0 | 2.6.2.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 2 | 7 | 0 | 2 | 1 | 2.6.2.7.2.1 | BK-W008N-PEDCO-110-CV-TB-0002 | TBE For Geotextile - W008N |  | BK-W008N-PEDCO-110-CV-TB-0002 | BK-W008N-PEDCO-110-CV-TB-0002 | BK | W008N | PEDCO | 110 | CV | TB | 0002 | F0Z-707911 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 3 | 0 | 0 | 0 | 0 | 2.6.3 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 3 | 0 | 0 | 1 | 0 | 2.6.3.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 3 | 0 | 0 | 1 | 1 | 2.6.3.1.1 | BK-W008N-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - W008N |  | BK-W008N-PEDCO-110-CO-PR-0001 | BK-W008N-PEDCO-110-CO-PR-0001 | BK | W008N | PEDCO | 110 | CO | PR | 0001 | F0Z-707912 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 4 | 0 | 0 | 0 | 0 | 2.6.4 |  | Field Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 4 | 0 | 0 | 1 | 0 | 2.6.4.1 |  | Query | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 4 | 0 | 0 | 1 | 1 | 2.6.4.1.1 | BK-W008N-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-W008N-PEDCO-110-GE-TQ-0001 | BK-W008N-PEDCO-110-GE-TQ-0001 | BK | W008N | PEDCO | 110 | GE | TQ | 0001 | F7Z-707913 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 4 | 0 | 0 | 2 | 0 | 2.6.4.2 |  | Dossier
2 | 6 | 4 | 0 | 0 | 2 | 1 | 2.6.4.2.1 | BK-W008N-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W008N |  | BK-W008N-PEDCO-110-GE-DO-0001 | BK-W008N-PEDCO-110-GE-DO-0001 | BK | W008N | PEDCO | 110 | GE | DO | 0001 | F0Z-707914 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 5 | 0 | 0 | 0 | 0 | 2.6.5 |  | Engineering Final Documentation
2 | 6 | 5 | 0 | 1 | 0 | 0 | 2.6.5.1 |  | Manual | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 6 | 5 | 0 | 1 | 0 | 1 | 2.6.5.1.1 | BK-W008N-PEDCO-110-GE-ML-0001 | Operating Manual - W008N |  | BK-W008N-PEDCO-110-GE-ML-0001 | BK-W008N-PEDCO-110-GE-ML-0001 | BK | W008N | PEDCO | 110 | GE | ML | 0001 | F0Z-707915 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 5 | 0 | 2 | 0 | 0 | 2.6.5.2 |  | Dossier
2 | 6 | 5 | 0 | 2 | 0 | 1 | 2.6 | BK-W008N-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - W008N |  | BK-W008N-PEDCO-110-GE-DO-0001 | [8 empty] | F0Z-707914 |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 6 | 5 | 0 | 2 | 0 | 2 | 2.6 | BK-W008N-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - W008N |  | BK-W008N-PEDCO-110-GE-DO-0002 | BK-W008N-PEDCO-110-GE-DO-0002 | BK | W008N | PEDCO | 110 | GE | DO | 0002 | F0Z-707916 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 7 | 0 | 0 | 0 | 0 | 0 | 2.7 |  | Package 06-New Well # W007S/Manifold Extension (Bangestan)
2 | 7 | 1 | 0 | 0 | 0 | 0 | 2.7.1 |  | Detail Design | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 1 | 0 | 0 | 0 | 2.7.1.1 |  | Process
2 | 7 | 1 | 1 | 1 | 0 | 0 | 2.7.1.1.1 |  | Description
2 | 7 | 1 | 1 | 1 | 0 | 1 | 2.7.1.1.1 | BK-W007S-PEDCO-110-PR-DP-0001 | Process Description - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PR-DP-0001 | BK-W007S-PEDCO-110-PR-DP-0001 | BK | W007S | PEDCO | 110 | PR | DP | 0001 | F0Z-707917 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 7 | 1 | 1 | 2 | 0 | 0 | 2.7.1.1.2 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 1 | 2 | 0 | 1 | 2.7.1.1.2 | BK-W007S-PEDCO-110-PR-CN-0001 | Calculation book for (CV,PSV,Pump & Line sizing) - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PR-CN-0001 | BK-W007S-PEDCO-110-PR-CN-0001 | BK | W007S | PEDCO | 110 | PR | CN | 0001 | F0Z-707918 | AFD | IFC | 2022-03-09 | 2022-03-12 | 2022-03-14 | 3 | 2 | 5 | IFA | 2022-09-10 | 2022-10-25 | 2022-10-26 | 45 | 1 | 46 | IFA | 2022-11-19 | 0 | 0 | -44884 | 0 | -44884 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-23 |  |  | D02 | IFA | T-1574 | 44870 | 1401/08/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-06217 | 44885 | 1401/08/29 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PR-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0628 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-PCS-00-03421 | 44629 | 1400/12/18 | CM-C3 | [6 empty] | 1400-2294-445285 | 2022-03-12 | 1400/12/21 | 44634 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-1314 | 44800 | 1401/06/05 |  |  |  | BK-SUR-ENG-PCS-01-05731 | 44824 | 1401/06/29 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-CN-0001_D00 | [5 empty] | 1401-2294-280775 | 44859 | 1401/08/03 | 44860 | 1401/08/4 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-CN-0001_D00 | [9 empty] | D02 | IFA | T-1574 | 44870 | 1401/08/14 |  |  |  | BK-SUR-ENG-PCS-01-06217 | 44885 | 1401/08/29 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-CN-0001_D01 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PR-CN-0001_D01
2 | 7 | 1 | 1 | 3 | 0 | 0 | 2.7.1.1.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 1 | 3 | 0 | 1 | 2.7.1.1.3 | BK-W007S-PEDCO-110-PR-DG-0001 | ESD Block Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PR-DG-0001 | BK-W007S-PEDCO-110-PR-DG-0001 | BK | W007S | PEDCO | 110 | PR | DG | 0001 | F2A-707919 | AFC | IFC | 2022-06-25 | 2022-10-10 | 2022-10-12 | 107 | 2 | 109 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-11 |  |  | D00 | IFC | T-1053 | 44723 | 1401/03/21 | T-1053 | 44723 | 1401/03/21 | BK-SUR-ENG-PCS-01-04989 | 44747 | 1401/04/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255985 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1053 | 2022-06-11 | 1401/03/21 | T-1053 | 44723 | 1401/03/21 | BK-SUR-ENG-PCS-01-04989 | 44747 | 1401/04/14 | CM-C3 | [6 empty] | 1401-2294-255985 | 2022-10-10 | 1401/07/18 | 44846 | 1401/07/20 | AP | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 7 | 1 | 1 | 3 | 0 | 2 | 2.7.1.1.3 | BK-W007S-PEDCO-110-PR-PF-0001 | Process Flow Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PR-PF-0001 | BK-W007S-PEDCO-110-PR-PF-0001 | BK | W007S | PEDCO | 110 | PR | PF | 0001 | F2A-707920 | AFC | IFC | 2021-08-23 | 2021-08-30 | 2021-09-06 | 7 | 7 | 14 | IFC | 2021-11-15 | 2021-11-14 | 2021-11-17 | -1 | 3 | 2 | IFA | 2022-05-01 | 2022-05-12 | 2022-05-16 | 11 | 4 | 15 | IFA | 2022-10-16 | 2022-11-15 | 2022-11-16 | 30 | 1 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-01 |  |  | D03 | IFA | T-1448 | 44836 | 1401/07/10 | T-1448 | 44837 | 1401/07/11 | BK-SUR-ENG-PCS-01-05944 | 44856 | 1401/07/30 | CM | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-312894 | 44880 | 1401/08/24 | 44881 | 1401/08/25 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0036 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PCS-00-01410 | 44433 | 1400/06/03 | CM-C3 | [6 empty] | 1400/2294/179419 | 2021-08-30 | 1400/06/08 | 44445 | 1400/06/15 | RJ | [10 empty] | D01 | IFC | T-0198 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02015 | 44515 | 1400/08/24 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D00 | [5 empty] | 1400-2294-275268 | 44514 | 1400/08/23 | 44517 | 1400/08/26 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D00 | [9 empty] | D02 | IFA | T-0831 | 44668 | 1401/01/28 |  |  |  | BK-SUR-ENG-PCS-01-04104 | 44682 | 1401/02/11 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D01 | [5 empty] | 1401-2294-59523 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D01 | [9 empty] | D03 | IFA | T-1448 | 44836 | 1401/07/10 | T-1448 | 44837 | 1401/07/11 | BK-SUR-ENG-PCS-01-05944 | 44856 | 1401/07/30 | CM | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D02 | [5 empty] | 1401-2294-312894 | 44880 | 1401/08/24 | 44881 | 1401/08/25 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D02
2 | 7 | 1 | 1 | 3 | 0 | 3 | 2.7.1.1.3 | BK-W007S-PEDCO-110-PR-PI-0001 | P&ID - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PR-PI-0001 | BK-W007S-PEDCO-110-PR-PI-0001 | BK | W007S | PEDCO | 110 | PR | PI | 0001 | F2A-707921 | AFC | IFC | 2021-11-09 | 2021-11-28 | 2021-11-14 | 19 | -14 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | IFA | 2022-09-07 | 2022-10-19 | 2022-10-23 | 42 | 4 | 46 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-26 |  |  | D02 | IFA | T-1310 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05608 | 44813 | 1401/06/15 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-271653 | 44853 | 1401/07/27 | 44857 | 1401/08/01 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0186 | 2021-10-26 | 1400/08/04 |  |  |  | BK-SUR-ENG-PCS-00-01976 | 44513 | 1400/08/22 | CM-C3 | [6 empty] | 1400-2294-271311 | 2021-11-11 | 1400/08/20 | 44514 | 1400/08/23 | CM |  | 1400-2290-294882 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0653 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1401-2294-43153 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-1310 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05608 | 44813 | 1401/06/15 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1401-2294-271653 | 44853 | 1401/07/27 | 44857 | 1401/08/01 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D01
2 | 7 | 1 | 1 | 3 | 0 | 4 | 2.7.1.1.3 | BK-W007S-PEDCO-110-PR-DG-0002 | Cause & Effect Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PR-DG-0002 | BK-W007S-PEDCO-110-PR-DG-0002 | BK | W007S | PEDCO | 110 | PR | DG | 0002 | F2A-707922 | AFC | IFC | 2022-06-21 | 2022-07-19 | 2022-07-31 | 28 | 12 | 40 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-07 |  |  | D00 | IFC | T-1050 | 44719 | 1401/03/17 | T-1050 | 44719 | 1401/03/18 | BK-SUR-ENG-PCS-01-04795 | 44733 | 1401/03/31 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-144345 | 44761 | 1401/04/28 | 44773 | 1401/05/08 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1050 | 2022-06-07 | 1401/03/17 | T-1050 | 44719 | 1401/03/18 | BK-SUR-ENG-PCS-01-04795 | 44733 | 1401/03/31 | CM-C3 | [6 empty] | 1401-2294-144345 | 2022-07-19 | 1401/04/28 | 44773 | 1401/05/08 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29
2 | 7 | 1 | 1 | 3 | 0 | 5 | 2.7.1.1.3 | BK-W007S-PEDCO-110-PR-PF-0002 | Process Flow Diagram - W007S |  | BK-W007S-PEDCO-110-PR-PF-0002 | BK-W007S-PEDCO-110-PR-PF-0002 | BK | W007S | PEDCO | 110 | PR | PF | 0002 | F2A-707923 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-16 | 2022-06-02 | 2022-06-06 | 198 | 4 | 202 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-02 |  |  | D02 | IFA | T-1266 | 44783 | 1401/05/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 44446 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0205 | 44502 | 1400/08/11 |  |  |  | BK-SUR-ENG-PCS-00-02020 | 44516 | 1400/08/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D00 | [5 empty] | 1401-2294-87488 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D00 | [9 empty] | D02 | IFA | T-1266 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05523 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D01 | [5 empty] | 1401-2294-235818 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D01
2 | 7 | 1 | 1 | 3 | 0 | 6 | 2.7.1.1.3 | BK-W007S-PEDCO-110-PR-PI-0002 | P&ID - W007S |  | BK-W007S-PEDCO-110-PR-PI-0002 | BK-W007S-PEDCO-110-PR-PI-0002 | BK | W007S | PEDCO | 110 | PR | PI | 0002 | F2A-707924 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | IFA | 2022-09-20 | 0 | 0 | -44824 | 0 | -44824 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-01 |  |  | D03 | IFA | T-0653 | 44620 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03656 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43153 | 44679 | 1401/02/08 | 0 | 0 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 44446 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0201 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 44520 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-279084 | 44516 | 1400/08/25 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0345 | 44545 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 44564 | 1400/10/13 | CM-C3 | PEDCO-BK-W007S-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-342085 | 44560 | 1400/10/09 | 44564 | 1400/10/13 | RJ | NISOC-BK-W007S-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0653 | 44620 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-43153 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D02 | [10 empty] | IFA | T-1368 | 44810 | 1401/06/15 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D03 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D03
2 | 7 | 1 | 1 | 3 | 0 | 7 | 2.7.1.1.3 | BK-W007S-PEDCO-110-PR-PI-0003 | P&ID for Diesel Oil Drum- W007S |  | BK-W007S-PEDCO-110-PR-PI-0003 | BK-W007S-PEDCO-110-PR-PI-0003 | BK | W007S | PEDCO | 110 | PR | PI | 0003 | F2A-707925 | AFC | IFC | 2021-11-30 | 2021-12-01 | 2021-12-06 | 1 | 5 | 6 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-10-18 | 2022-10-12 | 177 | -6 | 171 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-16 |  |  | D03 | IFA | T-0794 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0242 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02160 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300481 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D00 | [5 empty] | 1400-2294-402841 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D00 | [9 empty] | D02 | IFA | T-0649 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 44634 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D01 | [9 empty] | D03 | IFA | T-0794 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D02 | [5 empty] | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D02
2 | 7 | 1 | 1 | 3 | 0 | 8 | 2.7.1.1.3 | BK-W007S-PEDCO-110-PR-PI-0004 | P&ID for Potable Water Tank - W007S |  | BK-W007S-PEDCO-110-PR-PI-0004 | BK-W007S-PEDCO-110-PR-PI-0004 | BK | W007S | PEDCO | 110 | PR | PI | 0004 | F2A-707926 | AFC | IFC | 2021-11-30 | 2021-12-01 | 2021-12-06 | 1 | 5 | 6 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-10-18 | 2022-10-12 | 177 | -6 | 171 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-16 |  |  | D03 | IFA | T-0794 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0242 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02160 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300481 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D00 | [5 empty] | 1400-2294-402841 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D00 | [9 empty] | D02 | IFA | T-0649 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 44634 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D01 | [9 empty] | D03 | IFA | T-0794 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D02 | [5 empty] | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D02
2 | 7 | 1 | 1 | 4 | 0 | 0 | 2.7.1.1.4 |  | List | [142 empty] | 44520 | 1400/08/29
2 | 7 | 1 | 1 | 4 | 0 | 1 | 2.7.1.1.4 | BK-W007S-PEDCO-110-PR-LI-0001 | Line List - W007S & Manifold Extension |  | BK-W007S-PEDCO-110-PR-LI-0001 | BK-W007S-PEDCO-110-PR-LI-0001 | BK | W007S | PEDCO | 110 | PR | LI | 0001 | F0Z-707927 | AFC | IFC | 2022-05-04 | 2022-05-21 | 2022-05-23 | 17 | 2 | 19 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-20 |  |  | D00 | IFC | T-0848 | 44671 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04314 | 44702 | 1401/02/31 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70086 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0848 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-PCS-01-04314 | 44702 | 1401/02/31 | CM-C3 | [6 empty] | 1401-2294-70086 | 2022-05-21 | 1401/02/31 | 44704 | 1401/03/02 | CM | [19 empty] | 44520 | 1400/08/29
2 | 7 | 1 | 1 | 4 | 0 | 2 | 2.7.1.1.4 | BK-W007S-PEDCO-110-PR-LI-0002 | Tie-In List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PR-LI-0002 | BK-W007S-PEDCO-110-PR-LI-0002 | BK | W007S | PEDCO | 110 | PR | LI | 0002 | F0Z-707928 | AFC | IFC | 2022-05-04 | 2022-05-21 | 2022-05-23 | 17 | 2 | 19 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-20 |  |  | D00 | IFC | T-0848 | 44671 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04314 | 44702 | 1401/02/31 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70086 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0848 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-PCS-01-04314 | 44702 | 1401/02/31 | CM-C3 | [6 empty] | 1401-2294-70086 | 2022-05-21 | 1401/02/31 | 44704 | 1401/03/02 | CM | [19 empty] | 44520 | 1400/08/29
2 | 7 | 1 | 1 | 4 | 0 | 3 | 2.7.1.1.4 | BK-W007S-PEDCO-110-PR-LI-0003 | Line List - W007S |  | BK-W007S-PEDCO-110-PR-LI-0003 | BK-W007S-PEDCO-110-PR-LI-0003 | BK | W007S | PEDCO | 110 | PR | LI | 0003 | F0Z-707929 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-22 | 2021-11-27 | 2021-11-29 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-06-27 | 0 | 166 | -44739 | -44573 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-08 |  |  | D02 | IFA | T-0403 | 44559 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-LI-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-LI-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 44446 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0217 | 44508 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 44520 | 1400/08/29 | CM-C2 | PEDCO-CRS-D01-BK-W007S-PEDCO-110-PR-LI-0003_D00 | [5 empty] | 1400-2290-293083 | 44527 | 1400/09/06 | 44529 | 1400/09/08 | CM | NISOC-CRS-D01-BK-W007S-PEDCO-110-PR-LI-0003_D00 | [9 empty] | D02 | IFA | T-0403 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-LI-0003_D01 | [5 empty] | 1400-2294-343762 | 44739 | 1401/10/11 | 23-FEB-2022 | 1400/12/04 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-LI-0003_D01
2 | 7 | 1 | 1 | 5 | 0 | 0 | 2.7.1.1.5 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | [91 empty] | 1400/09/06
2 | 7 | 1 | 1 | 5 | 0 | 1 | 2.7.1.1.5 | BK-W007S-PEDCO-110-PR-RT-0001 | Flow line Hydraulic Calculation Report |  | BK-W007S-PEDCO-110-PR-RT-0001 | BK-W007S-PEDCO-110-PR-RT-0001 | BK | W007S | PEDCO | 110 | PR | RT | 0001 | F0Z-707930 | IFA | IFC | 2021-11-13 | 2021-11-14 | 2021-11-17 | 1 | 3 | 4 | IFA | 2022-01-15 | 2021-02-01 | 2022-02-05 | -348 | 369 | 21 | IFA | 2022-03-08 | 2022-03-10 | 2022-03-13 | 2 | 3 | 5 | IFA | 2022-05-14 | 2022-06-02 | 2022-06-06 | 19 | 4 | 23 | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 | AFC | 2022-10-22 | 2022-11-19 | 2022-11-20 | 28 | 1 | 29 | [7 empty] | Modify | 2021-10-30 | 2022-10-08 |  | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 44514 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 44517 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 44562 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 44228 | 1400/11/12 | 44597 | 1400/11/16 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 44614 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 44627 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 44630 | 1400/12/19 | 44633 | 1400/12/22 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 44681 | 1401/02/10 | T-0878 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 44709 | 1401/03/07 | AP | PEDCO-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D02 | [5 empty] | 1401-2294-87489 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D02 | [9 empty] | D04 | IFA | T-1267 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05524 | 44797 | 1401/06/02 | AP | [6 empty] | 1401-2294-235783 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D03 | [9 empty] | D05 | AFC | T-1460 | 44842 | 1401/07/16 | T-1460 | 44842 | 1401/07/16 | [10 empty] | 1401-2294-316910 | 44884 | 1401/08/28 | 44885 | 14014/08/29 | AP
2 | 7 | 1 | 1 | 6 | 0 | 0 | 2.7.1.1.6 |  | Data Sheet | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 1 | 6 | 0 | 1 | 2.7.1.1 | BK-W007S-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - W007S & Extension Manifold |  | BK-W007S-PEDCO-110-PR-DT-0001 | BK-W007S-PEDCO-110-PR-DT-0001 | BK | W007S | PEDCO | 110 | PR | DT | 0001 | F0Z-707931 | AFC | IFC | 2022-04-26 | 2022-05-08 | 2022-05-14 | 12 | 6 | 18 | IFA | 2022-10-23 | 0 | 0 | -44857 | 0 | -44857 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-12 |  |  | D01 | IFA | T-1466 | 44843 | 1401/07/17 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05973 | 44859 | 1401/08/03 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 44681 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 44695 | 1401/02/24 | CM | [10 empty] | D01 | IFA | T-1466 | 44843 | 1401/07/17 |  |  |  | BK-SUR-ENG-PCS-01-05973 | 44859 | 1401/08/03 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-DT-0001_D00 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PR-DT-0001_D00
2 | 7 | 1 | 2 | 0 | 0 | 0 | 2.7.1.2 |  | Mechanical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 2 | 1 | 0 | 0 | 2.7.1.2.1 |  | Specification
2 | 7 | 1 | 2 | 1 | 0 | 1 | 2.7.1.2.1 | BK-W007S-PEDCO-110-ME-SP-0001 | Specification For Positive Displacement Rotary Pumps |  | BK-W007S-PEDCO-110-ME-SP-0001 | BK-W007S-PEDCO-110-ME-SP-0001 | BK | W007S | PEDCO | 110 | ME | SP | 0001 | F0Z-707932 | AFD | IFC | 2022-03-07 | 2022-04-06 | 2022-04-13 | 30 | 7 | 37 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-21 |  |  | D00 | IFC | T-0614 | 44613 | 1400/11/02 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03504 | 44633 | 1400/12/22 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-13623 | 44657 | 1401/01/17 | 44664 | 1401/01/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0614 | 2022-02-21 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03504 | 44633 | 1400/12/22 | CM-C3 | [6 empty] | 1401-2294-13623 | 2022-04-06 | 1401/01/17 | 44664 | 1401/01/24 | AP
2 | 7 | 1 | 2 | 2 | 0 | 0 | 2.7.1.2.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 2 | 2 | 1 | 0 | 2.7.2.2.1 |  | Rotary Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 2 | 2 | 1 | 1 | 2.7.1.2.2.1.1 | BK-W007S-PEDCO-110-ME-DT-0001 | Data Sheets For Oil Sump Pump - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-ME-DT-0001 | BK-W007S-PEDCO-110-ME-DT-0001 | BK | W007S | PEDCO | 110 | ME | DT | 0001 | F0Z-707933 | AFC | IFC | 2022-03-28 | 2022-03-28 | 2022-04-04 | 0 | 7 | 7 | IFA | 2022-04-24 | 2022-04-30 | 2022-05-07 | 6 | 7 | 13 | IFA | 2022-09-12 | 2022-09-18 | 2022-09-21 | 6 | 3 | 9 | IFA | 2022-10-23 | 0 | 0 | -44857 | 0 | -44857 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-14 |  |  | D03 | IFA | T-1469 | 44843 | 1401/07/17 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05922 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D02 | BK-SUR-ENG-MEC-01-05924 | 44852 | 1401/07/26 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0730 | 2022-03-14 | 1400/12/12 |  |  |  | BK-SUR-ENG-MEC-01-03941 | 44667 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-4004 | 2022-03-28 | 1401/01/08 | 44655 | 1401/01/15 | CM | [10 empty] | D01 | IFA | T-0799 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-MEC-01-03921 | 44667 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-45436 | 44681 | 1401/02/10 | 44688 | 1401/02/17 | CM | NISOC-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D00 | [9 empty] | D02 | IFA | T-1336 | 44802 | 1401/06/07 |  |  |  | BK-SUR-ENG-MEC-01-05770 | 44830 | 1401/07/04 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D01 | [5 empty] | 1401-2294-229741 | 44822 | 1401/06/28 | 44825 | 1401/06/30 | CM | NISOC-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D01 | [9 empty] | D03 | IFA | T-1469 | 44843 | 1401/07/17 |  |  |  | BK-SUR-ENG-MEC-01-05922 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D02 | BK-SUR-ENG-MEC-01-05924 | 44852 | 1401/07/26 | CM-C2 | [7 empty] | NISOC-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D02
2 | 7 | 1 | 3 | 0 | 0 | 0 | 2.7.1.3 |  | HVAC/Plumbing | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 3 | 1 | 0 | 0 | 2.7.1.3.1 |  | Calculation
2 | 7 | 1 | 3 | 1 | 0 | 1 | 2.7.1.3.1 | BK-W007S-PEDCO-110-HV-CN-0001 | HVAC Calculation Note For Switchgear Building - W007S |  | BK-W007S-PEDCO-110-HV-CN-0001 | BK-W007S-PEDCO-110-HV-CN-0001 | BK | W007S | PEDCO | 110 | HV | CN | 0001 | F0Z-707934 | AFD | IFC | 2022-04-18 | 2022-04-12 | 2022-04-18 | -6 | 6 | 0 | IFA | 2022-10-10 | 0 | 0 | -44844 | 0 | -44844 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-04 |  |  | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-HV-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-HV-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0773 | 2022-04-04 | 1401/01/15 |  |  |  | BK-SUR-ENG-HVC-01-03863 | 44662 | 1401/01/22 | CM-C3 | [6 empty] | 1401-2294-20740 | 2022-04-12 | 1401/01/23 | 44669 | 1401/01/29 | CM | [10 empty] | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-HV-CN-0001_D00 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-HV-CN-0001_D00
2 | 7 | 1 | 3 | 1 | 0 | 2 | 2.7.1.3.1 | BK-W007S-PEDCO-110-HV-CN-0002 | HVAC Calculation Note For Security Building - W007S |  | BK-W007S-PEDCO-110-HV-CN-0002 | BK-W007S-PEDCO-110-HV-CN-0002 | BK | W007S | PEDCO | 110 | HV | CN | 0002 | F0Z-707935 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 3 | 2 | 0 | 0 | 2.7.1.3.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 3 | 2 | 0 | 1 | 2.7.1.3.2 | BK-W007S-PEDCO-110-HV-DT-0001 | Data Sheets For Main HVAC Equipment - W007S |  | BK-W007S-PEDCO-110-HV-DT-0001 | BK-W007S-PEDCO-110-HV-DT-0001 | BK | W007S | PEDCO | 110 | HV | DT | 0001 | F0Z-707936 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 3 | 3 | 0 | 0 | 2.7.1.3.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 3 | 3 | 0 | 1 | 2.7.1.3.3 | BK-W007S-PEDCO-110-HV-PY-0001 | HVAC System Layout For Switchgear Building - W007S |  | BK-W007S-PEDCO-110-HV-PY-0001 | BK-W007S-PEDCO-110-HV-PY-0001 | BK | W007S | PEDCO | 110 | HV | PY | 0001 | F4B-707937 | AFC | IFC | 2022-05-03 | 2022-04-30 | 2022-05-01 | -3 | 1 | -2 | IFA | 2022-10-10 | 0 | 0 | -44844 | 0 | -44844 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-19 |  |  | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-HV-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-HV-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0846 | 2022-04-19 | 1401/01/30 |  |  |  | BK-SUR-ENG-HVC-01-04149 | 44688 | 1401/02/17 | CM-C3 | [6 empty] | 1401-2294-43977 | 2022-04-30 | 1401/02/10 | 44682 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-HV-PY-0001_D00 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-HV-PY-0001_D00
2 | 7 | 1 | 3 | 3 | 0 | 2 | 2.7.1.3.3 | BK-W007S-PEDCO-110-HV-PY-0002 | HVAC System Layout For Security Building - W007S |  | BK-W007S-PEDCO-110-HV-PY-0002 | BK-W007S-PEDCO-110-HV-PY-0002 | BK | W007S | PEDCO | 110 | HV | PY | 0002 | F4B-707938 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 3 | 3 | 0 | 3 | 2.7.1.3.3 | BK-W007S-PEDCO-110-HV-PY-0003 | Plumbing & Sewage Piping Layout For Switchgear Building - W007S |  | BK-W007S-PEDCO-110-HV-PY-0003 | BK-W007S-PEDCO-110-HV-PY-0003 | BK | W007S | PEDCO | 110 | HV | PY | 0003 | F4B-707939 | AFC | IFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-18 |  |  | D00 | IFC | T-1512 | 44852 | 1401/07/26 | T-1512 | 44852 | 1401/07/26 | BK-SUR-ENG-HVC-01-05965 | 44858 | 1401/08/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1512 | 2022-10-18 | 1401/07/26 | T-1512 | 44852 | 1401/07/26 | BK-SUR-ENG-HVC-01-05965 | 44858 | 1401/08/02 | CM-C3
2 | 7 | 1 | 3 | 3 | 0 | 4 | 2.7.1.3.3 | BK-W007S-PEDCO-110-HV-PY-0004 | Plumbing & Sewage Piping Layout For Security Building - W007S |  | BK-W007S-PEDCO-110-HV-PY-0004 | BK-W007S-PEDCO-110-HV-PY-0004 | BK | W007S | PEDCO | 110 | HV | PY | 0004 | F4B-707940 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 3 | 4 | 0 | 0 | 2.7.1.3.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 3 | 4 | 0 | 1 | 2.7.1.3 | BK-W007S-PEDCO-110-HV-MT-0001 | MTO For Building HVAC & Plumbing Systems - W007S |  | BK-W007S-PEDCO-110-HV-MT-0001 | BK-W007S-PEDCO-110-HV-MT-0001 | BK | W007S | PEDCO | 110 | HV | MT | 0001 | F8Z-707941 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 0 | 0 | 0 | 2.7.1.4 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 4 | 1 | 0 | 0 | 2.7.1.4.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 4 | 1 | 0 | 1 | 2.7.1.4.1 | BK-W007S-PEDCO-110-PI-PY-0001 | Plot Plan Drawing - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-PY-0001 | BK-W007S-PEDCO-110-PI-PY-0001 | BK | W007S | PEDCO | 110 | PI | PY | 0001 | F5A-707942 | AFC | IFC | 2022-01-29 | 2022-02-04 | 2022-02-08 | 6 | 4 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-15 |  |  | D00 | IFC | T-0458 | 44576 | 1400/10/25 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02800 | 44585 | 1400/11/04 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-395124 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0458 | 2022-01-15 | 1400/10/25 |  |  |  | BK-SUR-ENG-PIP-00-02800 | 44585 | 1400/11/04 | RJ-C4 | [6 empty] | 1400-2294-395124 | 2022-02-04 | 1400/11/15 | 44600 | 1400/11/19 | CM
2 | 7 | 1 | 4 | 1 | 0 | 2 | 2.7.1.4.1 | BK-W007S-PEDCO-110-PI-DW-0001 | Piping Plan Drawing - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-DW-0001 | BK-W007S-PEDCO-110-PI-DW-0001 | BK | W007S | PEDCO | 110 | PI | DW | 0001 | F4L-707943 | AFC | IFC | 2022-10-18 | 2022-11-12 | 2022-11-14 | 25 | 2 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-04 |  |  | D00 | IFC | T-1457 | 44838 | 1401/07/12 | T-1457 | 44838 | 1401/07/12 | BK-SUR-ENG-PIP-01-05866 | 44844 | 1401/07/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-307415 | 44877 | 1401/08/21 | 44879 | 1401/08/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1457 | 2022-10-04 | 1401/07/12 | T-1457 | 44838 | 1401/07/12 | BK-SUR-ENG-PIP-01-05866 | 44844 | 1401/07/18 | CM-C3 | [6 empty] | 1401-2294-307415 | 2022-11-12 | 1401/08/21 | 44879 | 1401/08/23 | CM
2 | 7 | 1 | 4 | 1 | 0 | 3 | 2.7.1.4.1 | BK-W007S-PEDCO-110-PI-DW-0002 | Isometric Drawings - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-DW-0002 | BK-W007S-PEDCO-110-PI-DW-0002 | BK | W007S | PEDCO | 110 | PI | DW | 0002 | F2L-707944 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 4 | 1 | 0 | 4 | 2.7.1.4.1 | BK-W007S-PEDCO-110-PI-PY-0002 | Plot Plan Drawing - W007S |  | BK-W007S-PEDCO-110-PI-PY-0002 | BK-W007S-PEDCO-110-PI-PY-0002 | BK | W007S | PEDCO | 110 | PI | PY | 0002 | F5A-707945 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 1 | 0 | 5 | 2.7.1.4.1 | BK-W007S-PEDCO-110-PI-DW-0003 | Piping Plan - W007S |  | BK-W007S-PEDCO-110-PI-DW-0003 | BK-W007S-PEDCO-110-PI-DW-0003 | BK | W007S | PEDCO | 110 | PI | DW | 0003 | F4L-707946 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 4 | 1 | 0 | 6 | 2.7.1.4.1 | BK-W007S-PEDCO-110-PI-DW-0004 | Isometric Drawings - W007S |  | BK-W007S-PEDCO-110-PI-DW-0004 | BK-W007S-PEDCO-110-PI-DW-0004 | BK | W007S | PEDCO | 110 | PI | DW | 0004 | F2L-707947 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 1 | 0 | 7 | 2.7.1.4.1 | BK-W007S-PEDCO-110-PI-DG-0001 | Material Flow Diagram - W007S |  | BK-W007S-PEDCO-110-PI-DG-0001 | BK-W007S-PEDCO-110-PI-DG-0001 | BK | W007S | PEDCO | 110 | PI | DG | 0001 | F2A-707948 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 2022-06-28 | 2022-07-05 | 34 | 7 | 41 | IFA | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-08 |  |  | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 44521 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D00 | [5 empty] | 1401-2294-122170 | 44740 | 1401/04/07 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D00 | [9 empty] | D02 | IFA | T-1522 | 44856 | 1401/07/30 | T-1522 | 44856 | 1401/07/30 | BK-SUR-ENG-PIP-01-06052 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D01 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D01
2 | 7 | 1 | 4 | 1 | 0 | 8 | 2.7.1.4.1 | BK-W007S-PEDCO-110-PI-DG-0002 | Material Flow Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-DG-0002 | BK-W007S-PEDCO-110-PI-DG-0002 | BK | W007S | PEDCO | 110 | PI | DG | 0002 | F2A-707949 | AFC | IFC | 2022-05-25 | 2022-06-30 | 2022-07-05 | 36 | 5 | 41 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-11 |  |  | D00 | IFC | T-0934 | 44692 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04380 | 44704 | 1401/03/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-124157 | 44742 | 1401/04/09 | 44747 | 1401/04/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0934 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04380 | 44704 | 1401/03/02 | CM-C3 | [6 empty] | 1401-2294-124157 | 2022-06-30 | 1401/04/09 | 44747 | 1401/04/14 | CM
2 | 7 | 1 | 4 | 2 | 0 | 0 | 2.7.1.4.2 |  | List
2 | 7 | 1 | 4 | 2 | 0 | 1 | 2.7.1.4.2 | BK-W007S-PEDCO-110-PI-LI-0001 | Critical Line List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-LI-0001 | BK-W007S-PEDCO-110-PI-LI-0001 | BK | W007S | PEDCO | 110 | PI | LI | 0001 | F0Z-707950 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 4 | 2 | 0 | 2 | 2.7.1.4.2 | BK-W007S-PEDCO-110-PI-LI-0002 | Piping Tie-In List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-LI-0002 | BK-W007S-PEDCO-110-PI-LI-0002 | BK | W007S | PEDCO | 110 | PI | LI | 0002 | F0Z-707951 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 2 | 0 | 3 | 2.7.1.4.2 | BK-W007S-PEDCO-110-PI-LI-0003 | Piping Support List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-LI-0003 | BK-W007S-PEDCO-110-PI-LI-0003 | BK | W007S | PEDCO | 110 | PI | LI | 0003 | F0Z-707952 | AFC | IFC | 2022-10-30 | 2022-11-01 | 2022-11-06 | 2 | 5 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-16 |  |  | D00 | IFC | T-1500 | 44850 | 1401/07/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05969 | 44859 | 1401/08/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-290463 | 44866 | 1401/08/10 | 44871 | 1401/08/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1500 | 2022-10-16 | 1401/07/24 |  |  |  | BK-SUR-ENG-PIP-01-05969 | 44859 | 1401/08/03 | CM-C3 | [6 empty] | 1401-2294-290463 | 2022-11-01 | 1401/08/10 | 44871 | 1401/08/15 | CM
2 | 7 | 1 | 4 | 2 | 0 | 4 | 2.7.1.4.2 | BK-W007S-PEDCO-110-PI-LI-0004 | Piping Support List - W007S |  | BK-W007S-PEDCO-110-PI-LI-0004 | BK-W007S-PEDCO-110-PI-LI-0004 | BK | W007S | PEDCO | 110 | PI | LI | 0004 | F0Z-707953 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 2 | 0 | 5 | 2.7.1.4.2 | BK-W007S-PEDCO-110-PI-LI-0005 | Critical Line List - W007S |  | BK-W007S-PEDCO-110-PI-LI-0005 | BK-W007S-PEDCO-110-PI-LI-0005 | BK | W007S | PEDCO | 110 | PI | LI | 0005 | F0Z-707954 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 3 | 0 | 0 | 2.7.1.4.3 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 4 | 3 | 0 | 1 | 2.7.1.4.3 | BK-W007S-PEDCO-110-PI-RT-0001 | PDMS Model Review Report (30%) - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-RT-0001 | BK-W007S-PEDCO-110-PI-RT-0001 | BK | W007S | PEDCO | 110 | PI | RT | 0001 | F0Z-707955 | IFI | IFC | 2022-04-23 | 2022-04-12 | 2022-04-16 | -11 | 4 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-09 |  |  | D00 | IFC | T-0791 | 44660 | 1401/01/20 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-03935 | 44667 | 1401/01/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-20714 | 44663 | 1401/01/23 | 44667 | 1401/01/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0791 | 2022-04-09 | 1401/01/20 |  |  |  | BK-SUR-ENG-PIP-01-03935 | 44667 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-20714 | 2022-04-12 | 1401/01/23 | 44667 | 1401/01/27 | CM
2 | 7 | 1 | 4 | 3 | 0 | 2 | 2.7.1.4.3 | BK-W007S-PEDCO-110-PI-RT-0002 | PDMS Model Review Report (60%) - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-RT-0002 | BK-W007S-PEDCO-110-PI-RT-0002 | BK | W007S | PEDCO | 110 | PI | RT | 0002 | F0Z-707956 | IFI | IFC | 2022-07-19 | 2022-07-27 | 2022-07-31 | 8 | 4 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-05 |  |  | D00 | IFC | T-1138 | 44747 | 1401/04/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05169 | 44759 | 1401/04/26 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156846 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1138 | 2022-07-05 | 1401/04/14 |  |  |  | BK-SUR-ENG-PIP-01-05169 | 44759 | 1401/04/26 | CM-C2 | [6 empty] | 1401-2294-156846 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | AP
2 | 7 | 1 | 4 | 3 | 0 | 3 | 2.7.1.4.3 | BK-W007S-PEDCO-110-PI-RT-0003 | PDMS Model Review Report (90%) - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-PI-RT-0003 | BK-W007S-PEDCO-110-PI-RT-0003 | BK | W007S | PEDCO | 110 | PI | RT | 0003 | F0Z-707957 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 3 | 0 | 4 | 2.7.1.4.3 | BK-W007S-PEDCO-110-PI-RT-0004 | PDMS Model Review Report (30%) - W007S | PDMS Model Review Report | BK-W007S-PEDCO-110-PI-RT-0004 | BK-W007S-PEDCO-110-PI-RT-0004 | BK | W007S | PEDCO | 110 | PI | RT | 0004 | F0Z-707958 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 3 | 0 | 5 | 2.7.1.4.3 | BK-W007S-PEDCO-110-PI-RT-0005 | PDMS Model Review Report (60%) - W007S |  | BK-W007S-PEDCO-110-PI-RT-0005 | BK-W007S-PEDCO-110-PI-RT-0005 | BK | W007S | PEDCO | 110 | PI | RT | 0005 | F0Z-707959 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 3 | 0 | 6 | 2.7.1.4.3 | BK-W007S-PEDCO-110-PI-RT-0006 | PDMS Model Review Report (90%) - W007S |  | BK-W007S-PEDCO-110-PI-RT-0006 | BK-W007S-PEDCO-110-PI-RT-0006 | BK | W007S | PEDCO | 110 | PI | RT | 0006 | F0Z-707960 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 3 | 0 | 7 | 2.7.1.4.3 | BK-W007S-PEDCO-110-PI-RT-0007 | Stress Analysis Calculations Report For Manifold area |  | BK-W007S-PEDCO-110-PI-RT-0007 | BK-W007S-PEDCO-110-PI-RT-0007 | BK | W007S | PEDCO | 110 | PI | RT | 0007 | F0Z-707961 | IFI | IFI | 2022-11-01 | 2022-10-25 | 2022-10-29 | -7 | 4 | -3 | IFI | 2022-11-29 | 0 | 0 | -44894 | 0 | -44894 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-18 |  |  | D01 | IFI | T-1590 | 44880 | 1401/08/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-BK-W007S-PEDCO-110-PI-RT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-BK-W007S-PEDCO-110-PI-RT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1510 | 2022-10-18 | 1401/07/26 | T-1510 | 44852 | 1401/07/26 | BK-SUR-ENG-PIP-01-06008 | 44863 | 1401/08/07 | CM-C3 | [6 empty] | 1401-2294-281069 | 2022-10-25 | 1401/08/03 | 44863 | 1401/08/07 | CM | [10 empty] | D01 | IFI | T-1590 | 44880 | 1401/08/24 | [7 empty] | PEDCO-BK-W007S-PEDCO-110-PI-RT-0007_D00 | [11 empty] | NISOC-BK-W007S-PEDCO-110-PI-RT-0007_D00
2 | 7 | 1 | 4 | 4 | 0 | 0 | 2.7.1.4.4 |  | MTO
2 | 7 | 1 | 4 | 4 | 0 | 1 | 2.7.1.4 | BK-W007S-PEDCO-110-PI-MT-0001 | MTO For Pipes - Manifold & W007S |  | BK-W007S-PEDCO-110-PI-MT-0001 | BK-W007S-PEDCO-110-PI-MT-0001 | BK | W007S | PEDCO | 110 | PI | MT | 0001 | F8Z-707962 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-25 |  |  | D00 | IFI | T-1545 | 44859 | 1401/08/03 | T-1545 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1545 | 2022-10-25 | 1401/08/03 | T-1545 | 44859 | 1401/08/03
2 | 7 | 1 | 4 | 4 | 0 | 2 | 2.7.1.4 | BK-W007S-PEDCO-110-PI-MT-0002 | MTO For Fittings - Manifold & W007S |  | BK-W007S-PEDCO-110-PI-MT-0002 | BK-W007S-PEDCO-110-PI-MT-0002 | BK | W007S | PEDCO | 110 | PI | MT | 0002 | F8Z-707963 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 4 | 0 | 3 | 2.7.1.4 | BK-W007S-PEDCO-110-PI-MT-0003 | MTO For Flanges - Manifold & W007S |  | BK-W007S-PEDCO-110-PI-MT-0003 | BK-W007S-PEDCO-110-PI-MT-0003 | BK | W007S | PEDCO | 110 | PI | MT | 0003 | F8Z-707964 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 4 | 0 | 4 | 2.7.1.4 | BK-W007S-PEDCO-110-PI-MT-0004 | MTO For Manual Valves - Manifold & W007S |  | BK-W007S-PEDCO-110-PI-MT-0004 | BK-W007S-PEDCO-110-PI-MT-0004 | BK | W007S | PEDCO | 110 | PI | MT | 0004 | F8Z-707965 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 4 | 0 | 5 | 2.7.1.4 | BK-W007S-PEDCO-110-PI-MT-0005 | MTO For Gaskets - Manifold & W007S |  | BK-W007S-PEDCO-110-PI-MT-0005 | BK-W007S-PEDCO-110-PI-MT-0005 | BK | W007S | PEDCO | 110 | PI | MT | 0005 | F8Z-707966 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 4 | 4 | 0 | 6 | 2.7.1.4 | BK-W007S-PEDCO-110-PI-MT-0006 | MTO For Bolt & Nuts - Manifold & W007S |  | BK-W007S-PEDCO-110-PI-MT-0006 | BK-W007S-PEDCO-110-PI-MT-0006 | BK | W007S | PEDCO | 110 | PI | MT | 0006 | F8Z-707967 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 5 | 0 | 0 | 0 | 2.7.1.5 |  | Pipeline & Flow line | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 5 | 1 | 0 | 0 | 2.7.1.5.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 5 | 1 | 0 | 1 | 2.7.1.5.1 | BK-W007S-PEDCO-110-PL-DW-0002 | Flow line Transversal Drawings - W007S |  | BK-W007S-PEDCO-110-PL-DW-0002 | BK-W007S-PEDCO-110-PL-DW-0002 | BK | W007S | PEDCO | 110 | PL | DW | 0002 | F4A-707968 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 5 | 2 | 0 | 0 | 2.7.1.5.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 5 | 2 | 0 | 1 | 2.7.1.5.2 | BK-W007S-PEDCO-110-PL-LI-0001 | Road Crossing Location List |  | BK-W007S-PEDCO-110-PL-LI-0001 | BK-W007S-PEDCO-110-PL-LI-0001 | BK | W007S | PEDCO | 110 | PL | LI | 0001 | F0Z-707969 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 5 | 3 | 0 | 0 | 2.7.1.5.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 5 | 3 | 0 | 1 | 2.7.1.5 | BK-W007S-PEDCO-110-PL-MT-0001 | MTO For Line Pipes (Flow lines) - W007S |  | BK-W007S-PEDCO-110-PL-MT-0001 | BK-W007S-PEDCO-110-PL-MT-0001 | BK | W007S | PEDCO | 110 | PL | MT | 0001 | F8Z-707970 | IFI | IFI | 2021-09-05 | 2021-08-30 | 2021-09-05 | -6 | 6 | 0 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W007S-PEDCO-110-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 44430 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFI | T-1528 | 44857 | 1401/08/01 | T-1528 | 44857 | 1401/08/01 |  |  |  |  | PEDCO-CRS-BK-W007S-PEDCO-110-PL-MT-0001_D00 | [5 empty] | 1401-2294-296594 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PL-MT-0001_D00
2 | 7 | 1 | 6 | 0 | 0 | 0 | 2.7.1.6 |  | Control & Instrumentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 6 | 1 | 0 | 0 | 2.7.1.6.1 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 6 | 1 | 0 | 1 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0001 | Data Sheets For Temperature Gauge - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0001 | BK-W007S-PEDCO-110-IN-DT-0001 | BK | W007S | PEDCO | 110 | IN | DT | 0001 | F9Z-707971 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-21 | 2022-03-16 | 2022-03-27 | -5 | 11 | 6 | AFC | 2022-09-19 | 2022-10-19 | 2022-10-22 | 30 | 3 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 | 2022-09-05 |  | D02 | AFC | T-1365 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05720 | 44824 | 1401/06/29 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-271470 | 44853 | 1401/07/27 | 44856 | 1401/07/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0309 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02403 | 44552 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342127 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0691 | 44627 | 1400/12/16 |  |  |  | BK-SUR-ENG-INS-00-03649 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0001_D00 | [5 empty] | 1400-2294-453216 | 44636 | 1400/12/25 | 44647 | 1401/01/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0001_D00 | [9 empty] | D02 | AFC | T-1365 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-INS-01-05720 | 44824 | 1401/06/29 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0001_D01 | [5 empty] | 1401-2294-271470 | 44853 | 1401/07/27 | 44856 | 1401/07/30 | AP
2 | 7 | 1 | 6 | 1 | 0 | 2 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0002 | Data Sheets For Pressure & Diff. Pressure Gauge - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0002 | BK-W007S-PEDCO-110-IN-DT-0002 | BK | W007S | PEDCO | 110 | IN | DT | 0002 | F9Z-707972 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-22 | 2022-03-16 | 2022-03-25 | -6 | 9 | 3 | AFC | 2022-09-19 | 2022-10-19 | 2022-10-22 | 30 | 3 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 | 2022-09-05 |  | D02 | AFC | T-1365 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05720 | 44824 | 1401/06/29 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-271470 | 44853 | 1401/07/27 | 44856 | 1401/07/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0304 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02402 | 44552 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342113 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0698 | 44628 | 1400/12/17 |  |  |  | BK-SUR-ENG-INS-00-03651 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0002_D00 | [5 empty] | 1400-2294-453217 | 44636 | 1400/12/25 | 44645 | 1401/01/08 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0002_D00 | [9 empty] | D02 | AFC | T-1365 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-INS-01-05720 | 44824 | 1401/06/29 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0002_D01 | [5 empty] | 1401-2294-271470 | 44853 | 1401/07/27 | 44856 | 1401/07/30 | AP
2 | 7 | 1 | 6 | 1 | 0 | 3 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0003 | Data Sheets For Pressure Transmitter - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0003 | BK-W007S-PEDCO-110-IN-DT-0003 | BK | W007S | PEDCO | 110 | IN | DT | 0003 | F9Z-707973 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-26 | 2022-03-26 | 2022-03-27 | 0 | 1 | 1 | AFC | 2022-09-19 | 2022-10-19 | 2022-10-22 | 30 | 3 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 | 2022-09-05 |  | D02 | AFC | T-1365 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05720 | 44824 | 1401/06/29 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-271470 | 44853 | 1401/07/27 | 44856 | 1401/07/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0309 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02403 | 44552 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342127 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0720 | 44632 | 1400/12/21 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0003_D00 | [5 empty] | 1400-2294-1301 | 44646 | 1401/01/06 | 44647 | 1401/01/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0003_D00 | [9 empty] | D02 | AFC | T-1365 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-INS-01-05720 | 44824 | 1401/06/29 | CM-C2 | [6 empty] | 1401-2294-271470 | 44853 | 1401/07/27 | 44856 | 1401/07/30 | AP
2 | 7 | 1 | 6 | 1 | 0 | 4 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0004 | Data Sheets For Pressure & Safety Relief Valves - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0004 | BK-W007S-PEDCO-110-IN-DT-0004 | BK | W007S | PEDCO | 110 | IN | DT | 0004 | F9Z-707974 | AFC | IFC | 2022-06-08 | 2022-07-14 | 2022-07-17 | 36 | 3 | 39 | IFA | 2022-10-31 | 2022-11-05 | 2022-11-07 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-25 |  |  | D01 | IFA | T-1503 | 44851 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1007 | 2022-05-25 | 1401/03/04 | T-1007 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-04627 | 44721 | 1401/03/19 | CM-C3 | [6 empty] | 1401-2294-139937 | 2022-07-14 | 1401/04/23 | 44759 | 1401/04/26 | CM | [10 empty] | D01 | IFA | T-1503 | 44851 | 1401/07/25 |  |  |  | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0004_D00 | [5 empty] | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0004_D00
2 | 7 | 1 | 6 | 1 | 0 | 5 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0005 | Data Sheets For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0005 | BK-W007S-PEDCO-110-IN-DT-0005 | BK | W007S | PEDCO | 110 | IN | DT | 0005 | F9Z-707975 | AFC | IFC | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-22 | 2022-05-03 | 2022-06-06 | -19 | 34 | 15 | IFA | 2022-09-11 | 2022-09-28 | 2022-10-02 | 17 | 4 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-09 |  |  | D02 | IFA | T-1335 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05700 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240290 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0708 | 2022-03-09 | 1400/12/18 | [13 empty] | 1400-2294-454928 | 2022-03-19 | 1400/12/28 | 44647 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-0909 | 44689 | 1401/02/17 | T-0909 | 44689 | 1401/02/17 | BK-SUR-ENG-INS-01-04430 | 44706 | 1401/03/03 | CM-C3 | [6 empty] | 1401-2294-82863 | 44684 | 1401/03/09 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0005_D00 | [9 empty] | D02 | IFA | T-1335 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-INS-01-05700 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0005_D01 | [5 empty] | 1401-2294-240290 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0005_D01
2 | 7 | 1 | 6 | 1 | 0 | 6 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0006 | Data Sheets For Control/Regulator valves - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0006 | BK-W007S-PEDCO-110-IN-DT-0006 | BK | W007S | PEDCO | 110 | IN | DT | 0006 | F9Z-707976 | AFC | IFC | 2022-03-21 | 2022-04-17 | 2022-04-19 | 27 | 2 | 29 | IFA | 2022-07-02 | 2022-08-28 | 2022-08-25 | 57 | -3 | 54 | IFA | 2022-09-17 | 2022-10-04 | 0 | 17 | -44838 | -44821 | IFA | 2022-11-02 | 2022-10-28 | 2022-11-02 | -5 | 5 | 0 | IFA | 2022-11-28 | 0 | 0 | -44893 | 0 | -44893 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-07 |  |  | D04 | IFA | T-1587 | 44879 | 1401/08/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-06194 | 44881 | 1401/08/25 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0695 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-INS-00-03650 | 44636 | 1400/12/25 | CM-C3 | [6 empty] | 1400-2294-453218 | 2022-03-16 | 1400/12/25 | 44647 | 1401/01/07 | CM |  | 1401-2294-25145 | 44668 | 1401/01/27 | 44670 | 1401/01/30 | CM |  |  |  | D01 | IFA | T-1084 | 44730 | 1401/03/28 |  |  |  | BK-SUR-ENG-INS-01-05236 | 44767 | 1401/05/03 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D00 | [5 empty] | 1401-2294-194443 | 44801 | 1401/06/06 | 44798 | 1401/06/03 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D00 | [9 empty] | D02 | IFA | T-1348 | 44807 | 1401/06/12 |  |  |  | BK-SUR-ENG-INS-01-05712 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D01 | [5 empty] | 1401-2294-249326 | 44838 | 1401/07/12 | 9-OVT-2022 | 1401/07/17 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D01 | [9 empty] | D03 | IFA | T-1519 | 44853 | 1401/07/27 | T-1519 | 44853 | 1401/07/27 | BK-SUR-ENG-INS-01-06073 | 44867 | 1401/08/11 | CM | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D02 | [5 empty] | 1401-2294-283397 | 44862 | 1401/08/06 | 44867 | 1401/08/11 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D02 | [9 empty] | D04 | IFA | T-1587 | 44879 | 1401/08/23 |  |  |  | BK-SUR-ENG-INS-01-06194 | 44881 | 1401/08/25 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D03 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D03
2 | 7 | 1 | 6 | 1 | 0 | 7 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0007 | Data Sheets For Flow Transmitter/Diff. Pressure Transmitter - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0007 | BK-W007S-PEDCO-110-IN-DT-0007 | BK | W007S | PEDCO | 110 | IN | DT | 0007 | F9Z-707977 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-26 | 2022-03-26 | 2022-03-27 | 0 | 1 | 1 | IFA | 2022-09-11 | 2022-09-28 | 2022-10-02 | 17 | 4 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 |  |  | D02 | IFA | T-1333 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05639 | 44816 | 1401/06/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240312 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0309 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02403 | 44552 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342127 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0720 | 44632 | 1400/12/21 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D00 | [5 empty] | 1400-2294-1301 | 44646 | 1401/01/06 | 44647 | 1401/01/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D00 | [9 empty] | D02 | IFA | T-1333 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-INS-01-05639 | 44816 | 1401/06/21 | CM-C2 | [6 empty] | 1401-2294-240312 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D01
2 | 7 | 1 | 6 | 1 | 0 | 8 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0008 | Data Sheets For Orifice Plate/Restriction Orifice - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0008 | BK-W007S-PEDCO-110-IN-DT-0008 | BK | W007S | PEDCO | 110 | IN | DT | 0008 | F9Z-707978 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 6 | 1 | 0 | 9 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0009 | Data Sheets For Corrosion Coupon/ Probe - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0009 | BK-W007S-PEDCO-110-IN-DT-0009 | BK | W007S | PEDCO | 110 | IN | DT | 0009 | F9Z-707979 | AFC | IFC | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-22 | 2022-08-02 | 2022-08-06 | 72 | 4 | 76 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-09 |  |  | D01 | IFA | T-0914 | 44689 | 1401/02/18 | T-0914 | 44689 | 1401/02/18 | BK-SUR-ENG-INS-01-04431 | 44706 | 1401/03/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-164864 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0708 | 2022-03-09 | 1400/12/18 | [13 empty] | 1400-2294-454928 | 2022-03-19 | 1400/12/28 | 44647 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-0914 | 44689 | 1401/02/18 | T-0914 | 44689 | 1401/02/18 | BK-SUR-ENG-INS-01-04431 | 44706 | 1401/03/03 | CM-C3 | [6 empty] | 1401-2294-164864 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0009_D00
2 | 7 | 1 | 6 | 1 | 0 | 10 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0010 | Data Sheets For F&G Devices - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0010 | BK-W007S-PEDCO-110-IN-DT-0010 | BK | W007S | PEDCO | 110 | IN | DT | 0010 | F9Z-707980 | AFC | IFC | 2022-10-02 | 2022-11-05 | 2022-11-07 | 34 | 2 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-18 |  |  | D00 | IFC | T-1407 | 44822 | 1401/06/27 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05837 | 44838 | 1401/07/12 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296259 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1407 | 2022-09-18 | 1401/06/27 |  |  |  | BK-SUR-ENG-INS-01-05837 | 44838 | 1401/07/12 | CM-C2 | [6 empty] | 1401-2294-296259 | 2022-11-05 | 1401/08/14 | 44872 | 1401/08/16 | CM
2 | 7 | 1 | 6 | 1 | 0 | 11 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0011 | Data Sheets For Pressure Switch and Differential Pressure Switch - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DT-0011 | [8 empty] | F9Z-707981 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 6 | 1 | 0 | 11 | 2.7.1.6.1 | BK-W007S-PEDCO-110-IN-DT-0012 | Data Sheets For Displacer Level Transmitter - Extension Of Binak BC Manifold |  | BK-W007S-PEDCO-110-IN-DT-0012 | BK-W007S-PEDCO-110-IN-DT-0012 | BK | W007S | PEDCO | 110 | IN | DT | 0011 | F9Z-707982 | AFC | IFC | 2022-01-15 | 2022-01-26 | 2022-01-29 | 11 | 3 | 14 | IFA | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | AFC | 2022-09-11 | 0 | 0 | -44815 | 0 | -44815 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-01 | 2022-08-28 |  | D02 | AFC | T-1334 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05568 | 44804 | 1401/06/09 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0012_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0415 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-INS-00-02692 | 44577 | 1400/10/26 | CM-C3 | [6 empty] | 1400-2294-383988 | 2022-01-26 | 1400/11/06 | 44590 | 1400/11/09 | CM | [10 empty] | D01 | IFA | T-0752 | 44647 | 1401/01/07 |  |  |  | BK-SUR-ENG-INS-01-03845 | 44661 | 1401/01/21 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0012_D00 | [5 empty] | 1401-2294-27193 | 44668 | 1401/01/28 | 44676 | 1401/02/05 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0012_D00 | [9 empty] | D02 | AFC | T-1334 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-INS-01-05568 | 44804 | 1401/06/09 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0012_D01
2 | 7 | 1 | 6 | 2 | 0 | 0 | 2.7.1.6.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 6 | 2 | 0 | 1 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DW-0001 | Typical Instrument Installation Drawing - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DW-0001 | BK-W007S-PEDCO-110-IN-DW-0001 | BK | W007S | PEDCO | 110 | IN | DW | 0001 | F2J-707983 | IFI | IFI | 2022-03-23 | 2022-04-04 | 2022-04-09 | 12 | 5 | 17 | IFI | 2022-05-25 | 2022-06-14 | 2022-06-19 | 20 | 5 | 25 | IFI | 2022-08-15 | 2022-09-29 | 2022-10-02 | 45 | 3 | 48 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-09 |  |  | D02 | IFI | T-1231 | 44774 | 1401/05/10 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05495 | 44794 | 1401/05/30 | AP | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240479 | 44833 | 1401/07/07 | 44836 | 1401/07/10 | CM | NISCO-CRS-BK-W007S-PEDCO-110-IN-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0709 | 2022-03-09 | 1400/12/18 | [13 empty] | 1401-2294-9656 | 2022-04-04 | 1401/01/15 | 44660 | 1401/01/20 | CM | [10 empty] | D01 | IFI | T-0936 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-INS-01-04471 | 44710 | 1401/03/08 | CM-C2 | [6 empty] | 1401-2294-102599 | 44726 | 1401/03/24 | 44731 | 1401/03/29 | CM | NISCO-CRS-BK-W007S-PEDCO-110-IN-DW-0001_D01 | [9 empty] | D02 | IFI | T-1231 | 44774 | 1401/05/10 |  |  |  | BK-SUR-ENG-INS-01-05495 | 44794 | 1401/05/30 | AP | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DW-0001_D01 | [5 empty] | 1401-2294-240479 | 44833 | 1401/07/07 | 44836 | 1401/07/10 | CM | NISCO-CRS-BK-W007S-PEDCO-110-IN-DW-0001_D01
2 | 7 | 1 | 6 | 2 | 0 | 2 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0001 | Block Diagram Configuration For Control/ESD/F&G System - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0001 | BK-W007S-PEDCO-110-IN-DG-0001 | BK | W007S | PEDCO | 110 | IN | DG | 0001 | F2J-707984 | AFC | IFC | 2021-09-15 | 2021-09-29 | 2021-10-09 | 14 | 10 | 24 | IFA | 2021-11-15 | 2021-11-21 | 2021-11-27 | 6 | 6 | 12 | IFA | 2022-01-22 | 2022-01-31 | 2022-02-01 | 9 | 1 | 10 | IFA | 2022-04-20 | 2022-05-09 | 2022-05-21 | 19 | 12 | 31 | IFA | 2022-08-13 | 2022-09-28 | 2022-10-02 | 46 | 4 | 50 | IFA | 2022-10-31 | 2022-11-05 | 2022-11-07 | 5 | 2 | 7 | [8 empty] | 2021-09-01 |  |  | D05 | IFA | T-1503 | 44851 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D04 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0073 | 2021-09-01 | 1400/06/10 |  |  |  | BK-SUR-ENG-INS-00-01551 | 44488 | 1400/07/27 | CM-C3 | [6 empty] | 1400-2294-217809 | 2021-09-29 | 1400/07/07 | 44478 | 1400/07/17 | CM | [10 empty] | D01 | IFA | T-0202 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-INS-00-01995 | 44514 | 1400/08/23 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001-D00 | [5 empty] | 1400-2294-283464 | 44521 | 1400/08/30 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001-D00 | [9 empty] | D02 | IFA | T-0438 | 44569 | 1400/10/18 |  |  |  | BK-SUR-ENG-INS-00-02850 | 44590 | 1400/11/09 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001-D01 | [5 empty] | 1400-2294-389640 | 44592 | 1400/11/11 | 44593 | 1400/11/13 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001-D01 | [9 empty] | D03 | IFA | T-0780 | 44657 | 1401/01/17 |  |  |  | BK-SUR-ENG-INS-01-04007 | 44671 | 1401/01/031 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D02 | [5 empty] | 1401-2294-54898 | 44690 | 1401/02/19 | 44702 | 1401/02/31 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D02 | [9 empty] | D04 | IFA | T-1208 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05689 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D03 | [5 empty] | 1401-2294-238950 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D03 | [9 empty] | D05 | IFA | T-1503 | 44851 | 1401/07/25 |  |  |  | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D04 | [5 empty] | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D04
2 | 7 | 1 | 6 | 2 | 0 | 3 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0002 | Instrument Earthing Typical Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0002 | BK-W007S-PEDCO-110-IN-DG-0002 | BK | W007S | PEDCO | 110 | IN | DG | 0002 | F2J-707985 | IFI | IFI | 2022-01-15 | 2022-01-20 | 2022-01-22 | 5 | 2 | 7 | IFI | 2022-05-04 | 2022-05-12 | 2022-05-16 | 8 | 4 | 12 | IFI | 2022-08-15 | 2022-10-04 | 2022-10-08 | 50 | 4 | 54 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-01 |  |  | D02 | IFI | T-1235 | 44774 | 1401/05/10 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05461 | 44789 | 1401/05/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249317 | 44838 | 1401/07/12 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0410 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-INS-00-02616 | 44562 | 1400/10/20 | CM-C2 | [6 empty] | 1400-2294-372857 | 2022-01-20 | 1400/10/30 | 44583 | 1400/11/22 | CM | [10 empty] | D01 | IFI | T-0849 | 44671 | 1401/01/31 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0002_D00 | [5 empty] | 1401-2294-59514 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0002_D00 | [9 empty] | D02 | IFI | T-1235 | 44774 | 1401/05/10 |  |  |  | BK-SUR-ENG-INS-01-05461 | 44789 | 1401/05/25 | CM-C2 | [6 empty] | 1401-2294-249317 | 44838 | 1401/07/12 | 44842 | 1401/07/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D01
2 | 7 | 1 | 6 | 2 | 0 | 4 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0003 | Instrument Hook-up Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0003 | BK-W007S-PEDCO-110-IN-DG-0003 | BK | W007S | PEDCO | 110 | IN | DG | 0003 | F2J-707986 | AFC | IFC | 2022-06-21 | 2022-08-30 | 2022-09-04 | 70 | 5 | 75 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-07 |  |  | D00 | IFC | T-1049 | 44719 | 1401/03/17 | T-1049 | 44719 | 1401/03/18 | BK-SUR-ENG-INS-01-04800 | 44733 | 1401/03/31 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-201845 | 44803 | 1401/0608 | 44808 | 1401/06/13 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1049 | 2022-06-07 | 1401/03/17 | T-1049 | 44719 | 1401/03/18 | BK-SUR-ENG-INS-01-04800 | 44733 | 1401/03/31 | CM-C3 | [6 empty] | 1401-2294-201845 | 2022-08-30 | 1401/0608 | 44808 | 1401/06/13 | CM
2 | 7 | 1 | 6 | 2 | 0 | 5 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0004 | ESD Level Hierarchy - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0004 | BK-W007S-PEDCO-110-IN-DG-0004 | BK | W007S | PEDCO | 110 | IN | DG | 0004 | F2J-707987 | AFC | IFC | 2022-05-08 | 2022-06-01 | 2022-06-06 | 24 | 5 | 29 | IFA | 2022-09-25 | 2022-10-25 | 2022-10-29 | 30 | 4 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-24 |  |  | D01 | IFA | T-1388 | 44815 | 1401/06/20 | T-1388 | 44816 | 1401/06/21 | BK-SUR-ENG-INS-01-05757 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281107 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0857 | 2022-04-24 | 1401/02/04 |  |  |  | BK-SUR-ENG-INS-01-04192 | 44691 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-87474 | 2022-06-01 | 1401/03/12 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1388 | 44815 | 1401/06/20 | T-1388 | 44816 | 1401/06/21 | BK-SUR-ENG-INS-01-05757 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0004_D00 | [5 empty] | 1401-2294-281107 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0004_D00
2 | 7 | 1 | 6 | 2 | 0 | 6 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0005 | ESD System Loop Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0005 | BK-W007S-PEDCO-110-IN-DG-0005 | BK | W007S | PEDCO | 110 | IN | DG | 0005 | F2J-707988 | AFC | IFC | 2022-09-25 | 2022-10-29 | 2022-10-30 | 34 | 1 | 35 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-11 |  |  | D00 | IFC | T-1389 | 44815 | 1401/06/20 | T-1389 | 44816 | 1401/06/21 | BK-SUR-ENG-INS-01-05761 | 44828 | 1401/07/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283455 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1389 | 2022-09-11 | 1401/06/20 | T-1389 | 44816 | 1401/06/21 | BK-SUR-ENG-INS-01-05761 | 44828 | 1401/07/02 | CM-C3 | [6 empty] | 1401-2294-283455 | 2022-10-29 | 1401/08/07 | 44864 | 1401/08/08 | CM
2 | 7 | 1 | 6 | 2 | 0 | 7 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0006 | Control System Loop Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0006 | BK-W007S-PEDCO-110-IN-DG-0006 | BK | W007S | PEDCO | 110 | IN | DG | 0006 | F2J-707989 | AFC | IFC | 2022-09-19 | 2022-10-24 | 2022-10-26 | 35 | 2 | 37 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-05 |  |  | D00 | IFC | T-1362 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05716 | 44823 | 1401/06/28 | cm-c3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-278718 | 44858 | 1401/08/02 | 44860 | 1401/08/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1362 | 2022-09-05 | 1401/06/14 |  |  |  | BK-SUR-ENG-INS-01-05716 | 44823 | 1401/06/28 | cm-c3 | [6 empty] | 1401-2294-278718 | 2022-10-24 | 1401/08/02 | 44860 | 1401/08/04 | CM
2 | 7 | 1 | 6 | 2 | 0 | 8 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0007 | F&G System Loop Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0007 | BK-W007S-PEDCO-110-IN-DG-0007 | BK | W007S | PEDCO | 110 | IN | DG | 0007 | F2J-707990 | AFC | IFC | 2022-10-04 | 2022-11-05 | 2022-11-07 | 32 | 2 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-20 |  |  | D00 | IFC | T-1426 | 44824 | 1401/06/29 | T-1426 | 44825 | 1401/06/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296325 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1426 | 2022-09-20 | 1401/06/29 | T-1426 | 44825 | 1401/06/30 | [10 empty] | 1401-2294-296325 | 2022-11-05 | 1401/08/14 | 44872 | 1401/08/16 | CM
2 | 7 | 1 | 6 | 2 | 0 | 9 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0008 | Instrument Air Piping and Air Header Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0008 | BK-W007S-PEDCO-110-IN-DG-0008 | BK | W007S | PEDCO | 110 | IN | DG | 0008 | F2J-707991 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 6 | 2 | 0 | 10 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0009 | Instrument & F&G Junction Box Termination Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0009 | BK-W007S-PEDCO-110-IN-DG-0009 | BK | W007S | PEDCO | 110 | IN | DG | 0009 | F2J-707992 | AFC | IFC | 2022-05-28 | 2022-07-14 | 2022-07-17 | 47 | 3 | 50 | IFA | 2022-09-05 | 2022-09-28 | 2022-10-02 | 23 | 4 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-14 |  |  | D01 | IFA | T-1302 | 44795 | 1401/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05596 | 44808 | 1401/06/13 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0009_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240318 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0946 | 2022-05-14 | 1401/02/24 | T-0946 | 44695 | 1401/02/24 | BK-SUR-ENG-INS-01-04474 | 44710 | 1401/03/08 | CM-C3 | [6 empty] | 1401-2294-139957 | 2022-07-14 | 1401/04/23 | 44759 | 1401/04/26 | CM |  | 1401-2294-139957 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | CM |  |  |  | D01 | IFA | T-1302 | 44795 | 1401/05/31 |  |  |  | BK-SUR-ENG-INS-01-05596 | 44808 | 1401/06/13 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0009_D00 | [5 empty] | 1401-2294-240318 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0009_D00
2 | 7 | 1 | 6 | 2 | 0 | 11 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0010 | F&G Cause and Effect Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0010 | BK-W007S-PEDCO-110-IN-DG-0010 | BK | W007S | PEDCO | 110 | IN | DG | 0010 | F2J-707993 | AFC | IFC | 2022-10-03 | 2022-11-05 | 2022-11-07 | 33 | 2 | 35 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-19 |  |  | D00 | IFC | T-1412 | 44823 | 1401/06/28 | T-1412 | 44823 | 1401/06/28 | BK-SUR-ENG-INS-01-05839 | 44838 | 1401/07/12 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296399 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1412 | 2022-09-19 | 1401/06/28 | T-1412 | 44823 | 1401/06/28 | BK-SUR-ENG-INS-01-05839 | 44838 | 1401/07/12 | CM-C3 | [6 empty] | 1401-2294-296399 | 2022-11-05 | 1401/08/14 | 44872 | 1401/08/16 | CM
2 | 7 | 1 | 6 | 2 | 0 | 12 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-LD-0001 | Control System Logic Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LD-0001 | BK-W007S-PEDCO-110-IN-LD-0001 | BK | W007S | PEDCO | 110 | IN | LD | 0001 | F1J-707994 | AFC | IFC | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | IFA | 2022-08-31 | 2022-09-28 | 2022-10-02 | 28 | 4 | 32 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-10 |  |  | D01 | IFA | T-1281 | 44790 | 1401/05/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05572 | 44804 | 1401/06/09 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LD-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240283 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-LD-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0797 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-INS-01-04115 | 44682 | 1401/02/11 | CM-C3 | [6 empty] | 1401-2294-70032 | 2022-05-21 | 1401/02/31 | 44704 | 1401/03/02 | CM | [10 empty] | D01 | IFA | T-1281 | 44790 | 1401/05/26 |  |  |  | BK-SUR-ENG-INS-01-05572 | 44804 | 1401/06/09 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LD-0001_D00 | [5 empty] | 1401-2294-240283 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-LD-0001_D00
2 | 7 | 1 | 6 | 2 | 0 | 13 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-LD-0002 | ESD Logic Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LD-0002 | BK-W007S-PEDCO-110-IN-LD-0002 | BK | W007S | PEDCO | 110 | IN | LD | 0002 | F1J-707995 | AFC | IFC | 2022-06-08 | 2022-07-14 | 2022-07-17 | 36 | 3 | 39 | IFA | 2022-10-05 | 0 | 0 | -44839 | 0 | -44839 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-25 |  |  | D01 | IFA | T-1427 | 44825 | 1401/06/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05868 | 44844 | 1401/07/18 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LD-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-NISOC-110-IN-LD-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1007 | 2022-05-25 | 1401/03/04 | T-1007 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-04627 | 44721 | 1401/03/19 | RJ-C4 | [6 empty] | 1401-2294-139937 | 2022-07-14 | 1401/04/23 | 44759 | 1401/04/26 | CM | [10 empty] | D01 | IFA | T-1427 | 44825 | 1401/06/21 |  |  |  | BK-SUR-ENG-INS-01-05868 | 44844 | 1401/07/18 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LD-0002_D00 | [11 empty] | NISOC-CRS-BK-W007S-NISOC-110-IN-LD-0002_D00
2 | 7 | 1 | 6 | 2 | 0 | 14 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-PY-0001 | Control Room Layout & Arrangement Drawing - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-PY-0001 | BK-W007S-PEDCO-110-IN-PY-0001 | BK | W007S | PEDCO | 110 | IN | PY | 0001 | F2J-707996 | AFC | IFC | 2022-05-25 | 2022-06-15 | 2022-06-19 | 21 | 4 | 25 | IFA | 2022-09-25 | 2022-10-10 | 2022-10-12 | 15 | 2 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-11 |  |  | D01 | IFA | T-1390 | 44815 | 1401/06/20 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05760 | 44828 | 1401/07/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256207 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0935 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-INS-01-04459 | 44709 | 1401/03/07 | CM-C3 | [6 empty] | 1401-22294-104511 | 2022-06-15 | 1401/03/25 | 44731 | 1401/03/29 | CM | [10 empty] | D01 | IFA | T-1390 | 44815 | 1401/06/20 |  |  |  | BK-SUR-ENG-INS-01-05760 | 44828 | 1401/07/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-PY-0001_D00 | [5 empty] | 1401-2294-256207 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-PY-0001_D00
2 | 7 | 1 | 6 | 2 | 0 | 15 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-PY-0002 | Control Room Cable Route Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-PY-0002 | BK-W007S-PEDCO-110-IN-PY-0002 | BK | W007S | PEDCO | 110 | IN | PY | 0002 | F2J-707997 | AFC | IFC | 2022-09-27 | 2022-10-25 | 2022-10-26 | 28 | 1 | 29 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-13 |  |  | D00 | IFC | T-1398 | 44817 | 1401/06/22 | T-1398 | 44817 | 1401/06/22 | BK-SUR-ENG-INS-01-05768 | 44830 | 1401/07/04 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279765 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1398 | 2022-09-13 | 1401/06/22 | T-1398 | 44817 | 1401/06/22 | BK-SUR-ENG-INS-01-05768 | 44830 | 1401/07/04 | CM-C2 | [6 empty] | 1401-2294-279765 | 2022-10-25 | 1401/08/03 | 44860 | 1401/08/04 | CM
2 | 7 | 1 | 6 | 2 | 0 | 16 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-PY-0003 | Instrument Location Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-PY-0003 | BK-W007S-PEDCO-110-IN-PY-0003 | BK | W007S | PEDCO | 110 | IN | PY | 0003 | F2J-707998 | AFC | IFC | 2022-05-31 | 2022-07-14 | 2022-07-17 | 44 | 3 | 47 | IFA | 2022-10-08 | 2022-11-07 | 2022-11-13 | 30 | 6 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-17 |  |  | D01 | IFA | T-1434 | 44828 | 1401/07/02 | T-1434 | 44828 | 1401/07/02 | BK-SUR-ENG-INS-01-05885 | 44845 | 1401/07/19 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-PY-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-298680 | 44872 | 1401/08/16 | 44878 | 1401/08/22 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-PY-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0967 | 2022-05-17 | 1401/02/27 | T-0967 | 44699 | 1401/02/28 | BK-SUR-ENG-INS-01-04510 | 44713 | 1401/03/11 | RJ-C4 | [6 empty] | 1401-2294-139962 | 2022-07-14 | 1401/04/23 | 44759 | 1401/04/26 | CM | [10 empty] | D01 | IFA | T-1434 | 44828 | 1401/07/02 | T-1434 | 44828 | 1401/07/02 | BK-SUR-ENG-INS-01-05885 | 44845 | 1401/07/19 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-PY-0003_D00 | [5 empty] | 1401-2294-298680 | 44872 | 1401/08/16 | 44878 | 1401/08/22 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-PY-0003_D00
2 | 7 | 1 | 6 | 2 | 0 | 17 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-PY-0004 | Instrument/F&G Cable Trench/Route Layout Drawing - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-PY-0004 | BK-W007S-PEDCO-110-IN-PY-0004 | BK | W007S | PEDCO | 110 | IN | PY | 0004 | F2J-707999 | AFC | IFC | 2022-10-05 | 0 | 0 | -44839 | 0 | -44839 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-21 |  |  | D00 | IFC | T-1431 | 44825 | 1401/06/30 | T-1431 | 44825 | 1401/06/30 | BK-SUR-ENG-INS-01-05870 | 44844 | 1401/07/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1431 | 2022-09-21 | 1401/06/30 | T-1431 | 44825 | 1401/06/30 | BK-SUR-ENG-INS-01-05870 | 44844 | 1401/07/18 | CM-C3
2 | 7 | 1 | 6 | 2 | 0 | 18 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-PY-0005 | F&G Location Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-PY-0005 | BK-W007S-PEDCO-110-IN-PY-0005 | BK | W007S | PEDCO | 110 | IN | PY | 0005 | F2J-708000 | AFC | IFC | 2022-06-13 | 2022-08-14 | 2022-08-16 | 62 | 2 | 64 | IFA | 2022-10-02 | 2022-10-25 | 2022-10-26 | 23 | 1 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-30 |  |  | D01 | IFA | T-1410 | 44822 | 1401/06/27 | T-1410 | 44822 | 1401/06/27 | BK-SUR-ENG-INS-01-05828 | 44837 | 1401/07/11 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-PY-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279720 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-PY-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1025 | 2022-05-30 | 1401/03/09 | T-1026 | 44712 | 1401/03/10 | BK-SUR-ENG-INS-01-04742 | 44731 | 1401/03/29 | CM-C3 | [6 empty] | 1401-2294-177038 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM | [10 empty] | D01 | IFA | T-1410 | 44822 | 1401/06/27 | T-1410 | 44822 | 1401/06/27 | BK-SUR-ENG-INS-01-05828 | 44837 | 1401/07/11 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-PY-0005_D00 | [5 empty] | 1401-2294-279720 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-PY-0005_D00
2 | 7 | 1 | 6 | 2 | 0 | 19 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-PY-0006 | Instrument Location Layout Drawing - W007S |  | BK-W007S-PEDCO-110-IN-PY-0006 | BK-W007S-PEDCO-110-IN-PY-0006 | BK | W007S | PEDCO | 110 | IN | PY | 0006 | F2J-708001 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 6 | 2 | 0 | 20 | 2.7.1.6.2 | BK-W007S-PEDCO-110-IN-DG-0011 | Wiring Diagram; Interposing Relay Panel (IRP) - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-DG-0011 | BK-W007S-PEDCO-110-IN-DG-0011 | BK | W007S | PEDCO | 110 | IN | DG | 0011 | F2J-708002 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 6 | 3 | 0 | 0 | 2.7.1.6.3 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 6 | 3 | 0 | 1 | 2.7.1.6.3 | BK-W007S-PEDCO-110-IN-LI-0002 | I/O List For Control System - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LI-0002 | BK-W007S-PEDCO-110-IN-LI-0002 | BK | W007S | PEDCO | 110 | IN | LI | 0002 | F0Z-708003 | AFC | IFC | 2021-11-17 | 2021-11-21 | 2021-11-27 | 4 | 6 | 10 | IFA | 2022-03-16 | 2022-03-13 | 2022-03-25 | -3 | 12 | 9 | AFC | 2022-08-28 | 0 | 0 | -44801 | 0 | -44801 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-03 | 2022-08-14 |  | D02 | AFC | T-1271 | 44787 | 1401/05/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05527 | 44797 | 1401/06/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0208 | 2021-11-03 | 1400/08/12 |  |  |  | BK-SUR-ENG-INS-00-02036 | 44517 | 1400/08/26 | RJ-C4 | [6 empty] | 1400-2294-285060 | 2021-11-21 | 1400/08/30 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0665 | 44622 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03647 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0002_D00 | [5 empty] | 1400-2294-447179 | 44633 | 1400/12/22 | 44645 | 1401/01/08 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0002_D00 | [9 empty] | D02 | AFC | T-1271 | 44787 | 1401/05/23 |  |  |  | BK-SUR-ENG-INS-01-05527 | 44797 | 1401/06/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0002_D01
2 | 7 | 1 | 6 | 3 | 0 | 2 | 2.7.1.6.3 | BK-W007S-PEDCO-110-IN-LI-0003 | I/O List For ESD Systems - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LI-0003 | BK-W007S-PEDCO-110-IN-LI-0003 | BK | W007S | PEDCO | 110 | IN | LI | 0003 | F0Z-708004 | AFC | IFC | 2021-11-17 | 2021-11-21 | 2021-11-27 | 4 | 6 | 10 | IFA | 2022-03-16 | 2022-03-13 | 2022-03-25 | -3 | 12 | 9 | AFC | 2022-08-28 | 0 | 0 | -44801 | 0 | -44801 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-03 | 2022-08-14 |  | D02 | AFC | T-1271 | 44787 | 1401/05/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05527 | 44797 | 1401/06/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0208 | 2021-11-03 | 1400/08/12 |  |  |  | BK-SUR-ENG-INS-00-02036 | 44517 | 1400/08/26 | RJ-C4 | [6 empty] | 1400-2294-285060 | 2021-11-21 | 1400/08/30 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0665 | 44622 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03647 | 44636 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0003_D00 | [5 empty] | 1400-2294-447179 | 44633 | 1400/12/22 | 44645 | 1401/01/08 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0003_D00 | [9 empty] | D02 | AFC | T-1271 | 44787 | 1401/05/23 |  |  |  | BK-SUR-ENG-INS-01-05527 | 44797 | 1401/06/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0003_D01
2 | 7 | 1 | 6 | 3 | 0 | 3 | 2.7.1.6.3 | BK-W007S-PEDCO-110-IN-LI-0004 | I/O List For F&G Systems - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LI-0004 | BK-W007S-PEDCO-110-IN-LI-0004 | BK | W007S | PEDCO | 110 | IN | LI | 0004 | F0Z-708005 | AFC | IFC | 2022-08-31 | 2022-08-31 | 2022-08-28 | 0 | -3 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-17 |  |  | D00 | IFC | T-1282 | 44790 | 1401/05/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05549 | 44801 | 1401/06/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-198406 | 44804 | 1401/06/06 | 44801 | 1401/06/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1282 | 2022-08-17 | 1401/05/26 |  |  |  | BK-SUR-ENG-INS-01-05549 | 44801 | 1401/06/06 | CM-C3 | [6 empty] | 1401-2294-198406 | 2022-08-31 | 1401/06/06 | 44801 | 1401/06/09 | CM
2 | 7 | 1 | 6 | 3 | 0 | 4 | 2.7.1.6.3 | BK-W007S-PEDCO-110-IN-LI-0005 | Panels & Junction Box List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LI-0005 | BK-W007S-PEDCO-110-IN-LI-0005 | BK | W007S | PEDCO | 110 | IN | LI | 0005 | F0Z-708006 | AFC | IFC | 2022-10-02 | 2022-11-05 | 2022-11-07 | 34 | 2 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-18 |  |  | D00 | IFC | T-1407 | 44822 | 1401/06/27 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05837 | 44838 | 1401/07/12 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296259 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1407 | 2022-09-18 | 1401/06/27 |  |  |  | BK-SUR-ENG-INS-01-05837 | 44838 | 1401/07/12 | CM-C3 | [6 empty] | 1401-2294-296259 | 2022-11-05 | 1401/08/14 | 44872 | 1401/08/16 | CM
2 | 7 | 1 | 6 | 3 | 0 | 5 | 2.7.1.6.3 | BK-W007S-PEDCO-110-IN-LI-0006 | Set Point & Alarm List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LI-0006 | BK-W007S-PEDCO-110-IN-LI-0006 | BK | W007S | PEDCO | 110 | IN | LI | 0006 | F0Z-708007 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 6 | 3 | 0 | 6 | 2.7.1.6.3 | BK-W007S-PEDCO-110-IN-LI-0007 | I&C Power Consumption Summary - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LI-0007 | BK-W007S-PEDCO-110-IN-LI-0007 | BK | W007S | PEDCO | 110 | IN | LI | 0007 | F0Z-708008 | AFC | IFC | 2022-03-14 | 2022-03-25 | 2022-04-01 | 11 | 7 | 18 | IFA | 2022-05-04 | 2022-05-01 | 2022-05-02 | -3 | 1 | -2 | IFA | 2022-10-10 | 2022-11-05 | 2022-11-07 | 26 | 2 | 28 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-28 |  |  | D02 | IFA | T-1439 | 44830 | 1401/07/04 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05879 | 44845 | 1401/07/119 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296323 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0654 | 2022-02-28 | 1400/12/09 | [13 empty] | 1400-2294-453222 | 2022-03-16 | 1400/12/25 | 44647 | 1401/01/07 | CM |  | 1401-2294-4017 | 44645 | 1401/01/08 | 44652 | 1401/01/14 | CM |  |  |  | D01 | IFA | T-0852 | 44671 | 1401/01/31 | [13 empty] | 1401-2294-47232 | 44682 | 1401/02/11 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0007_D00 | [9 empty] | D02 | IFA | T-1439 | 44830 | 1401/07/04 |  |  |  | BK-SUR-ENG-INS-01-05879 | 44845 | 1401/07/119 | CM-C3 | [6 empty] | 1401-2294-296323 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0007_D01
2 | 7 | 1 | 6 | 3 | 0 | 7 | 2.7.1.6.3 | BK-W007S-PEDCO-110-IN-LI-0008 | F&G Detector List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LI-0008 | BK-W007S-PEDCO-110-IN-LI-0008 | BK | W007S | PEDCO | 110 | IN | LI | 0008 | F0Z-708009 | AFC | IFC | 2022-09-28 | 2022-11-03 | 2022-11-06 | 36 | 3 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-14 |  |  | D00 | IFC | T-1404 | 44818 | 1401/06/23 | T-1404 | 44818 | 1401/06/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294037 | 44868 | 1401/08/12 | 44871 | 1401/08/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1404 | 2022-09-14 | 1401/06/23 | T-1404 | 44818 | 1401/06/23 | [10 empty] | 1401-2294-294037 | 2022-11-03 | 1401/08/12 | 44871 | 1401/08/15 | CM
2 | 7 | 1 | 6 | 3 | 0 | 8 | 2.7.1.6.3 | BK-W007S-PEDCO-110-IN-LI-0009 | Instrument /F&G Cable List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-LI-0009 | BK-W007S-PEDCO-110-IN-LI-0009 | BK | W007S | PEDCO | 110 | IN | LI | 0009 | F0Z-708010 | AFC | IFC | 2022-09-05 | 2022-09-28 | 2022-10-02 | 23 | 4 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-22 |  |  | D00 | IFC | T-1303 | 44795 | 1401/05/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240271 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1303 | 2022-08-22 | 1401/05/31 | [13 empty] | 1401-2294-240271 | 2022-09-28 | 1401/07/06 | 44836 | 1401/07/10 | CM
2 | 7 | 1 | 6 | 4 | 0 | 0 | 2.7.1.6.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 6 | 4 | 0 | 1 | 2.7.1.6 | BK-W007S-PEDCO-110-IN-MT-0001 | MTO for Bulk Item and Installation Accessories - W007S & Manifold |  | BK-W007S-PEDCO-110-IN-MT-0001 | BK-W007S-PEDCO-110-IN-MT-0001 | BK | W007S | PEDCO | 110 | IN | MT | 0001 | F8Z-708011 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 6 | 4 | 0 | 2 | 2.7.1.6 | BK-W007S-PEDCO-110-IN-MT-0002 | MTO For Instrument/F&G Cable - W007S & Manifold |  | BK-W007S-PEDCO-110-IN-MT-0002 | BK-W007S-PEDCO-110-IN-MT-0002 | BK | W007S | PEDCO | 110 | IN | MT | 0002 | F8Z-708012 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 6 | 4 | 0 | 3 | 2.7.1.6 | BK-W007S-PEDCO-110-IN-MT-0003 | MTO For Instrument/F&G Junction box and Gland - W007S & Manifold |  | BK-W007S-PEDCO-110-IN-MT-0003 | BK-W007S-PEDCO-110-IN-MT-0003 | BK | W007S | PEDCO | 110 | IN | MT | 0003 | F8Z-708013 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 6 | 4 | 0 | 4 | 2.7.1.6 | BK-W007S-PEDCO-110-IN-MT-0004 | MTO For Instrument Tube and Fitting - W007S & Manifold |  | BK-W007S-PEDCO-110-IN-MT-0004 | BK-W007S-PEDCO-110-IN-MT-0004 | BK | W007S | PEDCO | 110 | IN | MT | 0004 | F8Z-708014 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 6 | 4 | 0 | 5 | 2.7.1.6 | BK-W007S-PEDCO-110-IN-MT-0005 | MTO For Instrument Cable Tray/Ladder - W007S & Manifold |  | BK-W007S-PEDCO-110-IN-MT-0005 | BK-W007S-PEDCO-110-IN-MT-0005 | BK | W007S | PEDCO | 110 | IN | MT | 0005 | F8Z-708015 | IFI | IFI | 2022-09-06 | 2022-09-10 | 2022-09-13 | 4 | 3 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-23 |  |  | D00 | IFI | T-1306 | 44796 | 1401/06/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05631 | 44816 | 1401/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216521 | 44814 | 1401/06/19 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1306 | 2022-08-23 | 1401/06/01 |  |  |  | BK-SUR-ENG-INS-01-05631 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-216521 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/22 | CM
2 | 7 | 1 | 7 | 0 | 0 | 0 | 2.7.1.7 |  | Safety | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 7 | 1 | 0 | 0 | 2.7.1.7.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 7 | 1 | 0 | 1 | 2.7.1.7.1 | BK-W007S-PEDCO-110-SA-PY-0001 | Hazardous Area Classification Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-SA-PY-0001 | BK-W007S-PEDCO-110-SA-PY-0001 | BK | W007S | PEDCO | 110 | SA | PY | 0001 | F2L-708016 | AFC | IFC | 2022-03-26 | 2022-04-13 | 2022-04-16 | 18 | 3 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-12 |  |  | D00 | IFC | T-0715 | 44632 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16831 | 44661 | 1401/01/21 | 44662 | 1401/01/22 | CM | 0 | 1401-2294-22713 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | CM | 0 | 0 |  | D00 | IFC | T-0715 | 2022-03-12 | 1400/12/21 | [13 empty] | 1401-2294-16831 | 2022-04-10 | 1401/01/21 | 44662 | 1401/01/22 | CM |  | 1401-2294-22713 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | CM
2 | 7 | 1 | 7 | 1 | 0 | 2 | 2.7.1.7.1 | BK-W007S-PEDCO-110-SA-PY-0002 | Safety & Fire Fighting Equipment Location Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-SA-PY-0002 | BK-W007S-PEDCO-110-SA-PY-0002 | BK | W007S | PEDCO | 110 | SA | PY | 0002 | F2L-708017 | AFC | IFC | 2022-05-01 | 2022-05-21 | 2022-05-23 | 20 | 2 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-17 |  |  | D00 | IFC | T-0834 | 44668 | 1401/01/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70732 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0834 | 2022-04-17 | 1401/01/28 | [13 empty] | 1401-2294-70732 | 2022-05-21 | 1401/02/31 | 44704 | 1401/03/02 | CM
2 | 7 | 1 | 7 | 1 | 0 | 3 | 2.7.1.7.1 | BK-W007S-PEDCO-110-SA-PY-0003 | Escape Route & Safety Sign Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-SA-PY-0003 | BK-W007S-PEDCO-110-SA-PY-0003 | BK | W007S | PEDCO | 110 | SA | PY | 0003 | F2L-708018 | AFC | IFC | 2022-05-01 | 2022-05-21 | 2022-05-23 | 20 | 2 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-17 |  |  | D00 | IFC | T-0834 | 44668 | 1401/01/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70732 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0834 | 2022-04-17 | 1401/01/28 | [13 empty] | 1401-2294-70732 | 2022-05-21 | 1401/02/31 | 44704 | 1401/03/02 | CM
2 | 7 | 1 | 7 | 1 | 0 | 4 | 2.7.1.7.1 | BK-W007S-PEDCO-110-SA-PY-0004 | Hazardous Area Classification Layout - W007S |  | BK-W007S-PEDCO-110-SA-PY-0004 | BK-W007S-PEDCO-110-SA-PY-0004 | BK | W007S | PEDCO | 110 | SA | PY | 0004 | F2L-708019 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 7 | 1 | 0 | 5 | 2.7.1.7.1 | BK-W007S-PEDCO-110-SA-PY-0005 | Safety & Fire Fighting Equipment Location Layout - W007S |  | BK-W007S-PEDCO-110-SA-PY-0005 | BK-W007S-PEDCO-110-SA-PY-0005 | BK | W007S | PEDCO | 110 | SA | PY | 0005 | F2L-708020 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 7 | 1 | 0 | 6 | 2.7.1.7.1 | BK-W007S-PEDCO-110-SA-PY-0006 | Escape Route & Safety Sign Layout - W007S |  | BK-W007S-PEDCO-110-SA-PY-0006 | BK-W007S-PEDCO-110-SA-PY-0006 | BK | W007S | PEDCO | 110 | SA | PY | 0006 | F2L-708021 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 7 | 2 | 0 | 0 | 2.7.1.7.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 7 | 2 | 0 | 1 | 2.7.1.7.2 | BK-W007S-PEDCO-110-SA-LI-0001 | Hazard Source List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-SA-LI-0001 | BK-W007S-PEDCO-110-SA-LI-0001 | BK | W007S | PEDCO | 110 | SA | LI | 0001 | F0Z-708022 | AFC | IFC | 2021-11-23 | 2021-11-30 | 2021-12-06 | 7 | 6 | 13 | IFA | 2022-03-16 | 2022-04-05 | 2022-04-09 | 20 | 4 | 24 | IFA | 2022-09-04 | 2022-10-04 | 2022-10-11 | 30 | 7 | 37 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-09 |  |  | D02 | IFA | T-1296 | 44794 | 1401/05/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249299 | 44838 | 1401/07/12 | 44845 | 1401/07/19 | CM | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0663 | 44622 | 1400/12/11 | [13 empty] | 1401-2294-10280 | 44656 | 1401/01/16 | 44660 | 1401/01/20 | CM | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-1296 | 44794 | 1401/05/30 | [13 empty] | 1401-2294-249299 | 44838 | 1401/07/12 | 44845 | 1401/07/19 | CM | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0001_D01
2 | 7 | 1 | 7 | 2 | 0 | 2 | 2.7.1.7.2 | BK-W007S-PEDCO-110-SA-LI-0002 | Hazard Source List - W007S |  | BK-W007S-PEDCO-110-SA-LI-0002 | BK-W007S-PEDCO-110-SA-LI-0002 | BK | W007S | PEDCO | 110 | SA | LI | 0002 | F0Z-708023 | AFC | IFC | 2021-11-23 | 2021-11-30 | 2021-12-06 | 7 | 6 | 13 | IFA | 2022-03-12 | 2022-04-05 | 2022-04-09 | 24 | 4 | 28 | IFA | 2022-05-01 | 0 | 0 | -44682 | 0 | -44682 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-09 |  |  | D02 | IFA | T-0827 | 44668 | 1401/01/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0645 | 44618 | 1400/12/07 | [13 empty] | 1401-2294-13856 | 44656 | 1401/01/18 | 44660 | 1401/01/20 | CM | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0002_D00 | [9 empty] | D02 | IFA | T-0827 | 44668 | 1401/01/28 | [19 empty] | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0002_D01
2 | 7 | 1 | 7 | 3 | 0 | 0 | 2.7.1.7.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 7 | 3 | 0 | 1 | 2.7.1.7 | BK-W007S-PEDCO-110-SA-MT-0002 | MTO For Fire Fighting & Safety Equipment - Manifold & W007S |  | BK-W007S-PEDCO-110-SA-MT-0002 | BK-W007S-PEDCO-110-SA-MT-0002 | BK | W007S | PEDCO | 110 | SA | MT | 0002 | F8Z-708024 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 7 | 3 | 0 | 2 | 2.7.1.7 | BK-W007S-PEDCO-110-SA-MT-0003 | MTO For Safety Sign - W007S |  | BK-W007S-PEDCO-110-SA-MT-0003 | BK-W007S-PEDCO-110-SA-MT-0003 | BK | W007S | PEDCO | 110 | SA | MT | 0003 | F8Z-708025 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 8 | 0 | 0 | 0 | 2.7.1.8 |  | Electrical
2 | 7 | 1 | 8 | 1 | 0 | 0 | 2.7.1.8.1 |  | Calculations
2 | 7 | 1 | 8 | 1 | 0 | 1 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-CN-0001 | Calculation Note for DC Charger System - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-CN-0001 | BK-W007S-PEDCO-110-EL-CN-0001 | BK | W007S | PEDCO | 110 | EL | CN | 0001 | F0Z-709390 | AFD | IFC | 2022-09-21 | 2022-10-05 | 2022-10-08 | 14 | 3 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D00 | IFC | T-1377 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05737 | 44825 | 1401/06/30 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249452 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1377 | 2022-09-07 | 1401/06/16 |  |  |  | BK-SUR-ENG-ELE-01-05737 | 44825 | 1401/06/30 | CM-C3 | [6 empty] | 1401-2294-249452 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 7 | 1 | 8 | 1 | 0 | 2 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-CN-0002 | Calculation Note for UPS System - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-CN-0002 | BK-W007S-PEDCO-110-EL-CN-0002 | BK | W007S | PEDCO | 110 | EL | CN | 0002 | F0Z-709391 | AFD | IFC | 2022-09-21 | 2022-10-05 | 2022-10-08 | 14 | 3 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D00 | IFC | T-1371 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05735 | 44825 | 1401/06/30 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249354 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1371 | 2022-09-07 | 1401/06/16 |  |  |  | BK-SUR-ENG-ELE-01-05735 | 44825 | 1401/06/30 | CM-C3 | [6 empty] | 1401-2294-249354 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 7 | 1 | 8 | 1 | 0 | 0 | 2.7.1.8.1 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 8 | 1 | 0 | 1 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-DT-0001 | Data Sheets for DC Charger - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-DT-0001 | BK-W007S-PEDCO-110-EL-DT-0001 | BK | W007S | PEDCO | 110 | EL | DT | 0001 | F0Z-709392 | AFD | IFC | 2022-09-21 | 2022-10-05 | 2022-10-08 | 14 | 3 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-07 |  |  | D00 | IFC | T-1377 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05737 | 44825 | 1401/06/30 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249452 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1377 | 2022-09-07 | 1401/06/16 |  |  |  | BK-SUR-ENG-ELE-01-05737 | 44825 | 1401/06/30 | CM-C3 | [6 empty] | 1401-2294-249452 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 7 | 1 | 8 | 1 | 0 | 2 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-DT-0002 | Data Sheets for UPS - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-DT-0002 | BK-W007S-PEDCO-110-EL-DT-0002 | BK | W007S | PEDCO | 110 | EL | DT | 0002 | F0Z-709393 | AFD | IFC | 2022-09-21 | 2022-10-05 | 2022-10-08 | 14 | 3 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D00 | IFC | T-1371 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05735 | 44825 | 1401/06/30 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249354 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1371 | 2022-09-07 | 1401/06/16 |  |  |  | BK-SUR-ENG-ELE-01-05735 | 44825 | 1401/06/30 | CM-C3 | [6 empty] | 1401-2294-249354 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 7 | 1 | 8 | 1 | 0 | 0 | 2.7.1.8.1 |  | Drawing/Diagram
2 | 7 | 1 | 8 | 1 | 0 | 1 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-PY-0001 | Earthing Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-PY-0001 | BK-W007S-PEDCO-110-EL-PY-0001 | BK | W007S | PEDCO | 110 | EL | PY | 0001 | F2P-708026 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 8 | 1 | 0 | 2 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-SL-0001 | LV Switchgear/MCC Expansion SLD - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-SL-0001 | BK-W007S-PEDCO-110-EL-SL-0001 | BK | W007S | PEDCO | 110 | EL | SL | 0001 | F2P-708027 | AFC | IFC | 2022-10-04 | 2022-10-05 | 2022-10-08 | 1 | 3 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-20 |  |  | D00 | IFC | T-1424 | 44824 | 1401/06/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05840 | 44838 | 1401/07/12 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-229369 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1424 | 2022-09-20 | 1401/06/29 |  |  |  | BK-SUR-ENG-ELE-01-05840 | 44838 | 1401/07/12 | CM-C2 | [6 empty] | 1401-2294-229369 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | CM
2 | 7 | 1 | 8 | 1 | 0 | 3 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-SL-0002 | UPS Single Line Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-SL-0002 | BK-W007S-PEDCO-110-EL-SL-0002 | BK | W007S | PEDCO | 110 | EL | SL | 0002 | F2P-708028 | AFC | IFC | 2022-04-09 | 2022-04-19 | 2022-04-25 | 10 | 6 | 16 | IFA | 2022-09-21 | 2022-09-19 | 2022-09-20 | -2 | 1 | -1 | IFA | 2022-11-08 | 2022-11-14 | 2022-11-19 | 6 | 5 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-26 |  |  | D02 | IFA | T-1546 | 44859 | 1401/08/03 | T-1546 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06130 | 44873 | 1401/08/17 | RJ-C4 | PEDCO-CRS-BK-W007S-PEDCO-110-EL-SL-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-311278 | 44879 | 1401/08/23 | 44884 | 1401/08/28 | AP | NISOC-CRS-BK-W007S-PEDCO-110-EL-SL-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0737 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-ELE-01-03698 | 44650 | 1401/01/10 | CM-C3 | [6 empty] | 1401-2294-31452 | 2022-04-19 | 1401/01/30 | 44676 | 1401/02/05 | CM | [10 empty] | D01 | IFA | T-1380 | 44811 | 1401/06/16 |  |  |  | BK-SUR-ENG-ELE-01-05739 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-EL-SL-0002_D00 | [5 empty] | 1401-2294-229895 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | CM | NISOC-CRS-BK-W007S-PEDCO-110-EL-SL-0002_D00 | [9 empty] | D02 | IFA | T-1546 | 44859 | 1401/08/03 | T-1546 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06130 | 44873 | 1401/08/17 | RJ-C4 | PEDCO-CRS-BK-W007S-PEDCO-110-EL-SL-0002_D01 | [5 empty] | 1401-2294-311278 | 44879 | 1401/08/23 | 44884 | 1401/08/28 | AP | NISOC-CRS-BK-W007S-PEDCO-110-EL-SL-0002_D01
2 | 7 | 1 | 8 | 1 | 0 | 4 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-SL-0003 | DC Charger Single Line Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-SL-0003 | BK-W007S-PEDCO-110-EL-SL-0003 | BK | W007S | PEDCO | 110 | EL | SL | 0003 | F2P-708029 | AFC | IFC | 2022-04-09 | 2022-04-19 | 2022-04-25 | 10 | 6 | 16 | IFA | 2022-09-21 | 2022-09-27 | 2022-09-27 | 6 | 0 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-26 |  |  | D01 | IFA | T-1374 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05736 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-EL-SL-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238252 | 44831 | 1401/07/05 | 44831 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-EL-SL-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0737 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-ELE-01-03698 | 44650 | 1401/01/10 | CM-C3 | [6 empty] | 1401-2294-31452 | 2022-04-19 | 1401/01/30 | 44676 | 1401/02/05 | CM | [10 empty] | D01 | IFA | T-1374 | 44811 | 1401/06/16 |  |  |  | BK-SUR-ENG-ELE-01-05736 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-EL-SL-0003_D00 | [5 empty] | 1401-2294-238252 | 44831 | 1401/07/05 | 44831 | 1401/07/10 | AP | NISOC-CRS-BK-W007S-PEDCO-110-EL-SL-0003_D00
2 | 7 | 1 | 8 | 1 | 0 | 5 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-DG-0001 | Interconnection Wiring Diagram - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-DG-0001 | BK-W007S-PEDCO-110-EL-DG-0001 | BK | W007S | PEDCO | 110 | EL | DG | 0001 | F2P-708030 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 8 | 1 | 0 | 6 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-PY-0002 | Area Electrical Cable Route & Section Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-PY-0002 | BK-W007S-PEDCO-110-EL-PY-0002 | BK | W007S | PEDCO | 110 | EL | PY | 0002 | F2P-708031 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 8 | 1 | 0 | 7 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-PY-0003 | Electrical Equipment Arrangement Layout In Switchgear Building - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-PY-0003 | BK-W007S-PEDCO-110-EL-PY-0003 | BK | W007S | PEDCO | 110 | EL | PY | 0003 | F2P-708032 | AFC | IFC | 2022-10-03 | 2022-10-29 | 2022-10-30 | 26 | 1 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-19 |  |  | D00 | IFC | T-1419 | 44823 | 1401/06/28 | T-1419 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05831 | 44837 | 1401/07/11 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284229 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1419 | 2022-09-19 | 1401/06/28 | T-1419 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05831 | 44837 | 1401/07/11 | RJ-C4 | [6 empty] | 1401-2294-284229 | 2022-10-29 | 1401/08/07 | 44864 | 1401/08/08 | CM
2 | 7 | 1 | 8 | 1 | 0 | 8 | 2.7.1.8.1 | BK-W007S-PEDCO-110-EL-PY-0004 | Earthing & Lightning Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-PY-0004 | BK-W007S-PEDCO-110-EL-PY-0004 | BK | W007S | PEDCO | 110 | EL | PY | 0004 | F2P-708033 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 8 | 2 | 0 | 0 | 2.7.1.8.2 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 8 | 2 | 0 | 1 | 2.7.1.8.2 | BK-W007S-PEDCO-110-EL-LI-0001 | Electrical Load List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-LI-0001 | BK-W007S-PEDCO-110-EL-LI-0001 | BK | W007S | PEDCO | 110 | EL | LI | 0001 | F0Z-708034 | AFC | IFC | 2022-03-21 | 2022-03-26 | 2022-03-27 | 5 | 1 | 6 | IFA | 2022-09-10 | 2022-09-08 | 2022-09-12 | -2 | 4 | 2 | IFA | 2022-10-05 | 2022-10-25 | 2022-10-29 | 20 | 4 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-07 |  |  | D02 | IFA | T-1429 | 44825 | 1401/06/30 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05860 | 44842 | 1401/07/16 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-EL-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279683 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-EL-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0692 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-ELE-00-03603 | 44635 | 1400/12/24 | CM-C2 | [6 empty] | 1401-2294-1235 | 2022-03-26 | 1401/01/06 | 44647 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-1320 | 44800 | 1401/06/05 |  |  |  | BK-SUR-ENG-ELE-01-05609 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-W007S-PEDCO-110-EL-LI-0001_D00 | [5 empty] | 1401-2294-216050 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | CM | NISOC-CRS-BK-W007S-PEDCO-110-EL-LI-0001_D00 | [9 empty] | D02 | IFA | T-1429 | 44825 | 1401/06/30 |  |  |  | BK-SUR-ENG-ELE-01-05860 | 44842 | 1401/07/16 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-EL-LI-0001_D01 | [5 empty] | 1401-2294-279683 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-EL-LI-0001_D01
2 | 7 | 1 | 8 | 2 | 0 | 2 | 2.7.1.8.2 | BK-W007S-PEDCO-110-EL-LI-0002 | Electrical Power & Control Cable List - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-EL-LI-0002 | BK-W007S-PEDCO-110-EL-LI-0002 | BK | W007S | PEDCO | 110 | EL | LI | 0002 | F0Z-708035 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 8 | 3 | 0 | 0 | 2.7.1.8.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 8 | 3 | 0 | 1 | 2.7.1.8 | BK-W007S-PEDCO-110-EL-MT-0001 | MTO For Earthing & Lightning Systems - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MT-0001 | BK-W007S-PEDCO-110-EL-MT-0001 | BK | W007S | PEDCO | 110 | EL | MT | 0001 | F8Z-708036 | IFI | IFI | 2022-10-25 | 2022-11-10 | 2022-11-14 | 16 | 4 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-11 |  |  | D00 | IFI | T-1480 | 44845 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-304880 | 44875 | 1401/08/19 | 44879 | 1401/08/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1480 | 2022-10-11 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | [6 empty] | 1401-2294-304880 | 2022-11-10 | 1401/08/19 | 44879 | 1401/08/23 | CM
2 | 7 | 1 | 8 | 3 | 0 | 2 | 2.7.1.8 | BK-W007S-PEDCO-110-EL-MT-0002 | MTO For Lighting & Small Powers - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MT-0002 | BK-W007S-PEDCO-110-EL-MT-0002 | BK | W007S | PEDCO | 110 | EL | MT | 0002 | F8Z-708037 | IFI | IFI | 2022-06-01 | 2022-06-10 | 2022-06-12 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-18 |  |  | D00 | IFI | T-0969 | 44699 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94633 | 44722 | 1401/03/20 | 44724 | 1401/03/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | [6 empty] | 1401-2294-94633 | 2022-06-10 | 1401/03/20 | 44724 | 1401/03/22 | CM
2 | 7 | 1 | 8 | 3 | 0 | 3 | 2.7.1.8 | BK-W007S-PEDCO-110-EL-MT-0003 | MTO For Power & Control Cables - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MT-0003 | BK-W007S-PEDCO-110-EL-MT-0003 | BK | W007S | PEDCO | 110 | EL | MT | 0003 | F8Z-708038 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 8 | 3 | 0 | 4 | 2.7.1.8 | BK-W007S-PEDCO-110-EL-MT-0004 | MTO For Tray/Ladder and Accessories - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MT-0004 | BK-W007S-PEDCO-110-EL-MT-0004 | BK | W007S | PEDCO | 110 | EL | MT | 0004 | F8Z-708039 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 8 | 3 | 0 | 5 | 2.7.1.8 | BK-W007S-PEDCO-110-EL-MT-0005 | MTO For Electrical Bulk Items - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MT-0005 | BK-W007S-PEDCO-110-EL-MT-0005 | BK | W007S | PEDCO | 110 | EL | MT | 0005 | F8Z-708040 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 8 | 3 | 0 | 6 | 2.7.1.8 | BK-W007S-PEDCO-110-EL-MT-0006 | MTO For Transmission Over Head Line - W007S |  | BK-W007S-PEDCO-110-EL-MT-0006 | BK-W007S-PEDCO-110-EL-MT-0006 | BK | W007S | PEDCO | 110 | EL | MT | 0006 | F8Z-708041 | IFI | IFI | 2022-10-03 | 2022-09-29 | 2022-10-08 | -4 | 9 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-19 |  |  | D00 | IFI | T-1417 | 44823 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249371 | 44833 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1417 | 2022-09-19 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | [6 empty] | 1401-2294-249371 | 2022-09-29 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 7 | 1 | 9 | 0 | 0 | 0 | 2.7.1.9 |  | Architecture | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 9 | 1 | 0 | 0 | 2.7.1.9.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 9 | 1 | 0 | 1 | 2.7.1.9.1 | BK-W007S-PEDCO-110-AR-DW-0001 | Architectural Drawing For Diesel Generator Shelter of Well Pads - W007S |  | BK-W007S-PEDCO-110-AR-DW-0001 | BK-W007S-PEDCO-110-AR-DW-0001 | BK | W007S | PEDCO | 110 | AR | DW | 0001 | F4B-708042 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-01 |  |  | D00 | IFC | T-0885 | 44682 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 44697 | 1401/02/26 | CM
2 | 7 | 1 | 9 | 1 | 0 | 2 | 2.7.1.9.1 | BK-W007S-PEDCO-110-AR-DW-0002 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W007S |  | BK-W007S-PEDCO-110-AR-DW-0002 | BK-W007S-PEDCO-110-AR-DW-0002 | BK | W007S | PEDCO | 110 | AR | DW | 0002 | F4B-708043 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 9 | 1 | 0 | 3 | 2.7.1.9.1 | BK-W007S-PEDCO-110-AR-DW-0003 | Architectural Drawing For Switchgear Building of Well Pads - W007S |  | BK-W007S-PEDCO-110-AR-DW-0003 | BK-W007S-PEDCO-110-AR-DW-0003 | BK | W007S | PEDCO | 110 | AR | DW | 0003 | F4B-708044 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 2022-05-31 | 2022-06-07 | -1 | 7 | 6 | IFC | 2022-09-21 | 2022-10-11 | 2022-10-17 | 20 | 6 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D02 | IFC | T-1370 | 44811 | 1401/06/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ARC-00-03551 | 44634 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 44645 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 44699 | 1401/02/28 | T-0974 | 44702 | 1401/02/31 | BK-SUR-ENG-ARC-01-04416 | 44705 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D00 | [5 empty] | 1401-2294-85268 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D00 | [9 empty] | D02 | IFC | T-1370 | 44811 | 1401/06/16 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D01 | [5 empty] | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D01
2 | 7 | 1 | 9 | 1 | 0 | 4 | 2.7.1.9.1 | BK-W007S-PEDCO-110-AR-DW-0004 | Architectural Drawing For Security Building of Well Pads - W007S |  | BK-W007S-PEDCO-110-AR-DW-0004 | BK-W007S-PEDCO-110-AR-DW-0004 | BK | W007S | PEDCO | 110 | AR | DW | 0004 | F4B-708045 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-01 |  |  | D00 | IFC | T-0886 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 44695 | 1401/02/21 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 44697 | 1401/02/26 | CM
2 | 7 | 1 | 9 | 2 | 0 | 0 | 2.7.1.9.2 |  | MTO
2 | 7 | 1 | 9 | 2 | 0 | 1 | 2.7.1.9 | BK-W007S-PEDCO-110-AR-MT-0001 | MTO For Architectural Works - W007S |  | BK-W007S-PEDCO-110-AR-MT-0001 | BK-W007S-PEDCO-110-AR-MT-0001 | BK | W007S | PEDCO | 110 | AR | MT | 0001 | F8Z-708046 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 10 | 0 | 0 | 0 | 2.7.1.10 |  | Civil | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 10 | 1 | 0 | 0 | 2.7.1.10.1 |  | Drawing/Diagram
2 | 7 | 1 | 10 | 1 | 0 | 1 | 2.7.1.10.1 | BK-W007S-PEDCO-110-CV-PY-0001 | General Civil Layout - W007S |  | BK-W007S-PEDCO-110-CV-PY-0001 | BK-W007S-PEDCO-110-CV-PY-0001 | BK | W007S | PEDCO | 110 | CV | PY | 0001 | F4A-708047 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 10 | 1 | 0 | 2 | 2.7.1.10.1 | BK-W007S-PEDCO-110-CV-PY-0002 | Civil and Structural drawings - W007S |  | BK-W007S-PEDCO-110-CV-PY-0002 | BK-W007S-PEDCO-110-CV-PY-0002 | BK | W007S | PEDCO | 110 | CV | PY | 0002 | F4S-708048 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[7 empty] | 2.7.1.10.2 | BK-W007S-PEDCO-110-CV-PY-0003 | General Civil Layout - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-CV-PY-0003 | [8 empty] | F4A-709415 | AFC | IFC | 2022-06-29 | 2022-06-24 | 2022-06-27 | -5 | 3 | -2 | IFA | 2022-07-19 | 2022-07-13 | 2022-07-23 | -6 | 10 | 4 | AFC | 2022-08-08 | 2022-08-28 | 2022-08-31 | 20 | 3 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-15 | 2022-07-25 |  | D02 | AFC | T-1191 | 44767 | 1401/05/03 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05459 | 44789 | 1401/05/25 | AP | PEDCO-CRS-BK-W007S-PEDCO-110-CV-PY-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-197935 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1083 | 2022-06-15 | 1401/03/25 |  |  |  | BK-SUR-ENG-CIV-01-04767 | 44732 | 1401/03/30 | CM-C2 | [6 empty] | 1401-2294-113987 | 2022-06-24 | 1401/04/03 | 44739 | 1401/04/06 | CM | [10 empty] | D01 | IFA | T-1144 | 44747 | 1401/04/14 |  |  |  | BK-SUR-ENG-CIV-01-05043 | 44751 | 1401/04/18 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-CV-PY-0003_D00 | [5 empty] | 1401-2294-139724 | 44755 | 1401/04/22 | 44765 | 1401/05/01 | AP | NISOC-CRS-BK-W007S-PEDCO-110-CV-PY-0003_D00 | [9 empty] | D02 | AFC | T-1191 | 44767 | 1401/05/03 |  |  |  | BK-SUR-ENG-CIV-01-05459 | 44789 | 1401/05/25 | AP | PEDCO-CRS-BK-W007S-PEDCO-110-CV-PY-0003_D01 | [5 empty] | 1401-2294-197935 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | AP
2 | 7 | 1 | 10 | 1 | 0 | 3 | 2.7.1.10.3 | BK-W007S-PEDCO-110-CV-DW-0001 | Rough Grading Plans -W007S |  | BK-W007S-PEDCO-110-CV-DW-0001 | BK-W007S-PEDCO-110-CV-DW-0001 | BK | W007S | PEDCO | 110 | CV | DW | 0001 | F4S-708049 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 10 | 2 | 0 | 0 | 2.7.1.10.2 |  | Calculation
2 | 7 | 1 | 10 | 2 | 0 | 1 | 2.7.1.10.2 | BK-W007S-PEDCO-110-CV-CN-0001 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W007S |  | BK-W007S-PEDCO-110-CV-CN-0001 | BK-W007S-PEDCO-110-CV-CN-0001 | BK | W007S | PEDCO | 110 | CV | CN | 0001 | F0Z-708050 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 10 | 3 | 0 | 0 | 2.7.1.10.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 10 | 3 | 0 | 1 | 2.7.1.10.3 | BK-W007S-PEDCO-110-CV-MT-0001 | MTO For Civil Works - W007S |  | BK-W007S-PEDCO-110-CV-MT-0001 | BK-W007S-PEDCO-110-CV-MT-0001 | BK | W007S | PEDCO | 110 | CV | MT | 0001 | F8Z-708051 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 10 | 4 | 0 | 0 | 2.7.1.10.4 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 10 | 4 | 0 | 1 | 2.7.1.10 | BK-W007S-PEDCO-110-SU-RT-0001 | Site Visit Report - Manifold Extension |  | BK-W007S-PEDCO-110-SU-RT-0001 | BK-W007S-PEDCO-110-CV-RT-0001 | BK | W007S | PEDCO | 110 | CV | RT | 0001 | F0Z-708052 | IFI | IFC | 2022-05-02 | 2022-05-17 | 2022-05-29 | 15 | 12 | 27 | IFA | 2022-08-07 | 2022-08-21 | 2022-08-27 | 14 | 6 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-18 |  |  | D01 | IFA | T-1189 | 44766 | 1401/05/02 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05326 | 44743 | 1401/05/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-187916 | 44794 | 1401/05/30 | 44800 | 1401/06/05 | CM | NISOC-CRS-BK-W007S-PEDCO-110-SU-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0840 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-GEN-01-04426 | 44705 | 1401/03/03 | AP | [6 empty] | 1401-2294-65660 | 2022-05-17 | 1401/02/27 | 44710 | 1401/03/08 | CM | [10 empty] | D01 | IFA | T-1189 | 44766 | 1401/05/02 |  |  |  | BK-SUR-ENG-CIV-01-05326 | 44743 | 1401/05/10 | CM-C2 | [6 empty] | 1401-2294-187916 | 44794 | 1401/05/30 | 44800 | 1401/06/05 | CM | NISOC-CRS-BK-W007S-PEDCO-110-SU-RT-0001_D00
2 | 7 | 1 | 11 | 0 | 0 | 0 | 2.7.1.11 |  | Structure
2 | 7 | 1 | 11 | 1 | 0 | 0 | 2.7.1.11.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 11 | 1 | 0 | 1 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0001 | Pipe Supports Foundation Drawing For Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-ST-DW-0001 | BK-W007S-PEDCO-110-ST-DW-0001 | BK | W007S | PEDCO | 110 | ST | DW | 0001 | F4Q-708053 | AFC | IFC | 2022-10-15 | 2022-10-30 | 2022-10-31 | 15 | 1 | 16 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFC | T-1445 | 44835 | 1401/07/09 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-05843 | 44842 | 1401/07/16 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285889 | 44864 | 1401/08/08 | 44865 | 1401/08/09 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1445 | 2022-10-01 | 1401/07/09 |  |  |  | BK-SUR-ENG-STR-01-05843 | 44842 | 1401/07/16 | CM-C2 | [6 empty] | 1401-2294-285889 | 2022-10-30 | 1401/08/08 | 44865 | 1401/08/09 | RJ
2 | 7 | 1 | 11 | 1 | 0 | 2 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0002 | Pipe Supports Structure Drawing For Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-ST-DW-0002 | BK-W007S-PEDCO-110-ST-DW-0002 | BK | W007S | PEDCO | 110 | ST | DW | 0002 | F4M-708054 | AFC | IFC | 2022-10-15 | 2022-10-30 | 2022-10-31 | 15 | 1 | 16 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1445 | 44835 | 1401/07/09 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-05843 | 44842 | 1401/07/16 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285889 | 44864 | 1401/08/08 | 44865 | 1401/08/09 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1445 | 2022-10-01 | 1401/07/09 |  |  |  | BK-SUR-ENG-STR-01-05843 | 44842 | 1401/07/16 | CM-C2 | [6 empty] | 1401-2294-285889 | 2022-10-30 | 1401/08/08 | 44865 | 1401/08/09 | RJ
2 | 7 | 1 | 11 | 1 | 0 | 3 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0003 | Access Platforms Structure Plan & Details For Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-ST-DW-0003 | BK-W007S-PEDCO-110-ST-DW-0003 | BK | W007S | PEDCO | 110 | ST | DW | 0003 | F4M-708055 | AFC | IFC | 2022-10-25 | 2022-11-05 | 2022-11-06 | 11 | 1 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-11 |  |  | D00 | IFC | T-1478 | 44845 | 1401/07/19 | T-1478 | 44845 | 1401/07/19 | BK-SUR-ENG-STR-01-05937 | 44853 | 1401/07/27 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296515 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1478 | 2022-10-11 | 1401/07/19 | T-1478 | 44845 | 1401/07/19 | BK-SUR-ENG-STR-01-05937 | 44853 | 1401/07/27 | CM-C2 | [6 empty] | 1401-2294-296515 | 2022-11-05 | 1401/08/14 | 44871 | 1401/08/15 | CM
2 | 7 | 1 | 11 | 1 | 0 | 4 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0004 | Access Platforms Foundation Drawing For Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-ST-DW-0004 | BK-W007S-PEDCO-110-ST-DW-0004 | BK | W007S | PEDCO | 110 | ST | DW | 0004 | F4Q-708056 | AFC | IFC | 2022-10-25 | 2022-11-05 | 2022-11-06 | 11 | 1 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-11 |  |  | D00 | IFC | T-1478 | 44845 | 1401/07/19 | T-1478 | 44845 | 1401/07/19 | BK-SUR-ENG-STR-01-05937 | 44853 | 1401/07/27 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296515 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1478 | 2022-10-11 | 1401/07/19 | T-1478 | 44845 | 1401/07/19 | BK-SUR-ENG-STR-01-05937 | 44853 | 1401/07/27 | CM-C2 | [6 empty] | 1401-2294-296515 | 2022-11-05 | 1401/08/14 | 44871 | 1401/08/15 | CM
2 | 7 | 1 | 11 | 1 | 0 | 5 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0007 | Fuel Oil Storage Drum Detail Drawing For Well Pads - W007S |  | BK-W007S-PEDCO-110-ST-DW-0007 | BK-W007S-PEDCO-110-ST-DW-0007 | BK | W007S | PEDCO | 110 | ST | DW | 0007 | F4G-708057 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 11 | 1 | 0 | 6 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0008 | Foundation Drawing For Security Building For Well Pads - W007S |  | BK-W007S-PEDCO-110-ST-DW-0008 | BK-W007S-PEDCO-110-ST-DW-0008 | BK | W007S | PEDCO | 110 | ST | DW | 0008 | F4Q-708058 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 11 | 1 | 0 | 7 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0009 | Structural Drawing For Security Building For Well Pads - W007S |  | BK-W007S-PEDCO-110-ST-DW-0009 | BK-W007S-PEDCO-110-ST-DW-0009 | BK | W007S | PEDCO | 110 | ST | DW | 0009 | F4M-708059 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 11 | 1 | 0 | 8 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0010 | Foundation Drawing For Switchgear Building For Well Pads - W007S |  | BK-W007S-PEDCO-110-ST-DW-0010 | BK-W007S-PEDCO-110-ST-DW-0010 | BK | W007S | PEDCO | 110 | ST | DW | 0010 | F4Q-708060 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 11 | 1 | 0 | 9 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0011 | Structural Drawing For Switchgear Building For Well Pads - W007S |  | BK-W007S-PEDCO-110-ST-DW-0011 | BK-W007S-PEDCO-110-ST-DW-0011 | BK | W007S | PEDCO | 110 | ST | DW | 0011 | F4M-708061 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 11 | 1 | 0 | 10 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0012 | Foundation Drawing For Potable Water Tank For Well Pads - W007S |  | BK-W007S-PEDCO-110-ST-DW-0012 | BK-W007S-PEDCO-110-ST-DW-0012 | BK | W007S | PEDCO | 110 | ST | DW | 0012 | F4Q-708062 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 11 | 1 | 0 | 11 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0013 | Foundation Drawing For Diesel Generator Shelter For Well Pads - W007S |  | BK-W007S-PEDCO-110-ST-DW-0013 | BK-W007S-PEDCO-110-ST-DW-0013 | BK | W007S | PEDCO | 110 | ST | DW | 0013 | F4Q-708063 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 11 | 1 | 0 | 12 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0014 | Structural Drawing For Diesel Generator Shelter For Well Pads - W007S |  | BK-W007S-PEDCO-110-ST-DW-0014 | BK-W007S-PEDCO-110-ST-DW-0014 | BK | W007S | PEDCO | 110 | ST | DW | 0014 | F4M-708064 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 11 | 1 | 0 | 13 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0016 | Platform Structure Drawing - W007S |  | BK-W007S-PEDCO-110-ST-DW-0016 | BK-W007S-PEDCO-110-ST-DW-0016 | BK | W007S | PEDCO | 110 | ST | DW | 0016 | F4M-708065 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 11 | 1 | 0 | 15 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0018 | Foundation Drawing For Oil Pump |  | BK-W007S-PEDCO-110-ST-DW-0018 | BK-W007S-PEDCO-110-ST-DW-0018 | BK | W007S | PEDCO | 110 | ST | DW | 0018 | F4Q-708066 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 11 | 1 | 0 | 16 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0019 | Sump Pit Structural Drawing for Oil Pump |  | BK-W007S-PEDCO-110-ST-DW-0019 | BK-W007S-PEDCO-110-ST-DW-0019 | BK | W007S | PEDCO | 110 | ST | DW | 0019 | F4M-708067 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 11 | 1 | 0 | 17 | 2.7.1.11.1 | BK-W007S-PEDCO-110-ST-DW-0020 | Foundation Drawing For Transmission Line Tower - W007S |  | BK-W007S-PEDCO-110-ST-DW-0020 | BK-W007S-PEDCO-110-ST-DW-0020 | BK | W007S | PEDCO | 110 | ST | DW | 0020 | F4Q-708068 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 11 | 2 | 0 | 0 | 2.7.1.11.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 11 | 2 | 0 | 1 | 2.7.1.11 | BK-W007S-PEDCO-110-ST-MT-0001 | MTO For Structural Works - W007S & Manifold Extension |  | BK-W007S-PEDCO-110-ST-MT-0001 | BK-W007S-PEDCO-110-ST-MT-0001 | BK | W007S | PEDCO | 110 | ST | MT | 0001 | F8Z-708069 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 1 | 12 | 0 | 0 | 0 | 2.7.1.12 |  | Geotechnic/Geoelectric | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 1 | 12 | 1 | 0 | 0 | 2.7.1.12.1 |  | Geotechnic
2 | 7 | 1 | 12 | 1 | 1 | 0 | 2.7.12.1.1 |  | Report
2 | 7 | 1 | 12 | 1 | 1 | 1 | 2.7.1.12.1.1.1 | BK-W007S-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - W007S |  | BK-W007S-PEDCO-110-GT-RT-0001 | BK-W007S-PEDCO-110-GT-RT-0001 | BK | W007S | PEDCO | 110 | GT | RT | 0001 | F0Z-708070 | IFI | IFC | 2022-06-25 | 2022-06-21 | 2022-06-25 | -4 | 4 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-11 |  |  | D00 | IFC | T-1059 | 44723 | 1401/03/21 | T-1059 | 44723 | 1401/03/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-111566 | 44733 | 1401/03/31 | 44737 | 1401/04/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1059 | 2022-06-11 | 1401/03/21 | T-1059 | 44723 | 1401/03/21 | [10 empty] | 1401-2294-111566 | 2022-06-21 | 1401/03/31 | 44737 | 1401/04/04 | CM
2 | 7 | 1 | 12 | 1 | 2 | 0 | 2.7.12.1.2 |  | Drawing/Diagram
2 | 7 | 1 | 12 | 1 | 2 | 1 | 2.7.1.12.1.2.1 | BK-W007S-PEDCO-110-SU-DW-0001 | Flow line Plan & Profile Drawings - W007S |  | BK-W007S-PEDCO-110-SU-DW-0001 | BK-W007S-PEDCO-110-SU-DW-0001 | BK | W007S | PEDCO | 110 | SU | DW | 0001 | F4A-708071 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 1 | 12 | 1 | 2 | 2 | 2.7.1.12.1.2.2 | BK-W007S-PEDCO-110-SU-DW-0002 | Over Head Line Plan and Profile - W007S |  | BK-W007S-PEDCO-110-SU-DW-0002 | BK-W007S-PEDCO-110-SU-DW-0002 | BK | W007S | PEDCO | 110 | SU | DW | 0002 | F4A-708072 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 0 | 0 | 0 | 0 | 2.7.2 |  | Procurement Engineering
2 | 7 | 2 | 1 | 0 | 0 | 0 | 2.7.2.1 |  | Mechanical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 1 | 1 | 0 | 0 | 2.7.2.1.1 |  | Pump
2 | 7 | 2 | 1 | 1 | 1 | 0 | 2.7.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 1 | 1 | 1 | 1 | 2.7.2.1.1.1.1 | BK-W007S-PEDCO-110-ME-MR-0001 | PMR For Pumps - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-ME-MR-0001 | BK-W007S-PEDCO-110-ME-MR-0001 | BK | W007S | PEDCO | 110 | ME | MR | 0001 | F0Z-708073 | IFI | IFI | 2022-09-25 | 2022-09-25 | 2022-10-03 | 0 | 8 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-11 |  |  | D00 | IFI | T-1386 | 44815 | 1401/06/20 | T-1386 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05755 | 44828 | 1401/07/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-235916 | 44829 | 1401/07/03 | 44837 | 1401/07/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1386 | 2022-09-11 | 1401/06/20 | T-1386 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05755 | 44828 | 1401/07/02 | CM-C3 | [6 empty] | 1401-2294-235916 | 2022-09-25 | 1401/07/03 | 44837 | 1401/07/11 | CM
2 | 7 | 2 | 1 | 1 | 2 | 0 | 2.7.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 1 | 1 | 2 | 1 | 2.7.2.1.1.2.1 | BK-W007S-PEDCO-110-ME-TB-0001 | TBE For Pumps - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-ME-TB-0001 | BK-W007S-PEDCO-110-ME-TB-0001 | BK | W007S | PEDCO | 110 | ME | TB | 0001 | F0Z-708074 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 1 | 2 | 0 | 0 | 2.7.2.1.2 |  | Drum
2 | 7 | 2 | 1 | 2 | 1 | 0 | 2.7.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 1 | 2 | 1 | 1 | 2.7.2.1.2.1.1 | BK-W007S-PEDCO-110-ME-MR-0002 | PMR For Drums - W007S |  | BK-W007S-PEDCO-110-ME-MR-0002 | BK-W007S-PEDCO-110-ME-MR-0002 | BK | W007S | PEDCO | 110 | ME | MR | 0002 | F0Z-708075 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 1 | 2 | 2 | 0 | 2.7.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 1 | 2 | 2 | 1 | 2.7.2.1.2.2.1 | BK-W007S-PEDCO-110-ME-TB-0002 | TBE For Drums - W007S |  | BK-W007S-PEDCO-110-ME-TB-0002 | BK-W007S-PEDCO-110-ME-TB-0002 | BK | W007S | PEDCO | 110 | ME | TB | 0002 | F0Z-708076 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 1 | 3 | 0 | 0 | 2.7.2.1.3 |  | Elevated Tank
2 | 7 | 2 | 1 | 3 | 1 | 0 | 2.7.1.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 1 | 3 | 1 | 1 | 2.7.2.1.3.1.1 | BK-W007S-PEDCO-110-ME-MR-0003 | PMR For Potable Tanks - W007S |  | BK-W007S-PEDCO-110-ME-MR-0003 | BK-W007S-PEDCO-110-ME-MR-0003 | BK | W007S | PEDCO | 110 | ME | MR | 0003 | F0Z-708077 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 1 | 3 | 2 | 0 | 2.7.1.3.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 1 | 3 | 2 | 1 | 2.7.2.1.3.2.1 | BK-W007S-PEDCO-110-ME-TB-0003 | TBE For Potable Tanks - W007S |  | BK-W007S-PEDCO-110-ME-TB-0003 | BK-W007S-PEDCO-110-ME-TB-0003 | BK | W007S | PEDCO | 110 | ME | TB | 0003 | F0Z-708078 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 2 | 0 | 0 | 0 | 2.7.2.2 |  | HVAC
2 | 7 | 2 | 2 | 1 | 0 | 0 | 2.7.2.2.1 |  | Main HVAC Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 2 | 1 | 1 | 0 | 2.7.2.1.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 2 | 1 | 1 | 1 | 2.7.2.2.1.1.1 | BK-W007S-PEDCO-110-HV-MR-0001 | PMR For Main HVAC Equipment - W007S |  | BK-W007S-PEDCO-110-HV-MR-0001 | BK-W007S-PEDCO-110-HV-MR-0001 | BK | W007S | PEDCO | 110 | HV | MR | 0001 | F0Z-708079 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 2 | 1 | 2 | 0 | 2.7.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 2 | 1 | 2 | 1 | 2.7.2.2.1.2.1 | BK-W007S-PEDCO-110-HV-TB-0001 | TBE For Main HVAC Equipment - W007S |  | BK-W007S-PEDCO-110-HV-TB-0001 | BK-W007S-PEDCO-110-HV-TB-0001 | BK | W007S | PEDCO | 110 | HV | TB | 0001 | F0Z-708080 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 3 | 0 | 0 | 0 | 2.7.2.3 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 1 | 0 | 0 | 2.7.2.3.1 |  | Pipes
2 | 7 | 2 | 3 | 1 | 1 | 0 | 2.7.3.1.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 1 | 1 | 1 | 2.7.2.3.1.1.1 | BK-W007S-PEDCO-110-PI-MR-0001 | PMR For Pipes - W007S |  | BK-W007S-PEDCO-110-PI-MR-0001 | BK-W007S-PEDCO-110-PI-MR-0001 | BK | W007S | PEDCO | 110 | PI | MR | 0001 | F0Z-708081 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 3 | 1 | 2 | 0 | 2.7.3.1.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 1 | 2 | 1 | 2.7.2.3.1.2.1 | BK-W007S-PEDCO-110-PI-TB-0001 | TBE For Pipes - W007S |  | BK-W007S-PEDCO-110-PI-TB-0001 | BK-W007S-PEDCO-110-PI-TB-0001 | BK | W007S | PEDCO | 110 | PI | TB | 0001 | F0Z-708082 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 3 | 2 | 0 | 0 | 2.7.2.3.2 |  | Fittings
2 | 7 | 2 | 3 | 2 | 1 | 0 | 2.7.3.2.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 2 | 1 | 1 | 2.7.2.3.2.1.1 | BK-W007S-PEDCO-110-PI-MR-0002 | PMR For Fittings - W007S |  | BK-W007S-PEDCO-110-PI-MR-0002 | BK-W007S-PEDCO-110-PI-MR-0002 | BK | W007S | PEDCO | 110 | PI | MR | 0002 | F0Z-708083 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 3 | 2 | 2 | 0 | 2.7.3.2.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 2 | 2 | 1 | 2.7.2.3.2.2.1 | BK-W007S-PEDCO-110-PI-TB-0002 | TBE For Fitting - W007S |  | BK-W007S-PEDCO-110-PI-TB-0002 | BK-W007S-PEDCO-110-PI-TB-0002 | BK | W007S | PEDCO | 110 | PI | TB | 0002 | F0Z-708084 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 3 | 3 | 0 | 0 | 2.7.2.3.3 |  | Flanges
2 | 7 | 2 | 3 | 3 | 1 | 0 | 2.7.3.3.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 3 | 1 | 1 | 2.7.2.3.3.1.1 | BK-W007S-PEDCO-110-PI-MR-0003 | PMR For Flanges - W007S |  | BK-W007S-PEDCO-110-PI-MR-0003 | BK-W007S-PEDCO-110-PI-MR-0003 | BK | W007S | PEDCO | 110 | PI | MR | 0003 | F0Z-708085 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 3 | 3 | 2 | 0 | 2.7.3.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 3 | 2 | 1 | 2.7.2.3.3.2.1 | BK-W007S-PEDCO-110-PI-TB-0003 | TBE For Flanges - W007S |  | BK-W007S-PEDCO-110-PI-TB-0003 | BK-W007S-PEDCO-110-PI-TB-0003 | BK | W007S | PEDCO | 110 | PI | TB | 0003 | F0Z-708086 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 3 | 4 | 0 | 0 | 2.7.2.3.4 |  | Manual Valves | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 4 | 1 | 0 | 2.7.3.4.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 4 | 1 | 1 | 2.7.2.3.4.1.1 | BK-W007S-PEDCO-110-PI-MR-0004 | PMR For Manual Valves - W007S |  | BK-W007S-PEDCO-110-PI-MR-0004 | BK-W007S-PEDCO-110-PI-MR-0004 | BK | W007S | PEDCO | 110 | PI | MR | 0004 | F0Z-708087 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 3 | 4 | 2 | 0 | 2.7.3.4.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 4 | 2 | 1 | 2.7.2.3.4.2.1 | BK-W007S-PEDCO-110-PI-TB-0004 | TBE For Manual Valves - W007S |  | BK-W007S-PEDCO-110-PI-TB-0004 | BK-W007S-PEDCO-110-PI-TB-0004 | BK | W007S | PEDCO | 110 | PI | TB | 0004 | F0Z-708088 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 3 | 5 | 0 | 0 | 2.7.2.3.5 |  | Gaskets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 5 | 1 | 0 | 2.7.3.5.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 5 | 1 | 1 | 2.7.2.3.5.1.1 | BK-W007S-PEDCO-110-PI-MR-0005 | PMR For Gaskets - W007S |  | BK-W007S-PEDCO-110-PI-MR-0005 | BK-W007S-PEDCO-110-PI-MR-0005 | BK | W007S | PEDCO | 110 | PI | MR | 0005 | F0Z-708089 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 3 | 5 | 2 | 0 | 2.7.3.5.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 5 | 2 | 1 | 2.7.2.3.5.2.1 | BK-W007S-PEDCO-110-PI-TB-0005 | TBE For Gaskets - W007S |  | BK-W007S-PEDCO-110-PI-TB-0005 | BK-W007S-PEDCO-110-PI-TB-0005 | BK | W007S | PEDCO | 110 | PI | TB | 0005 | F0Z-708090 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 3 | 6 | 0 | 0 | 2.7.2.3.6 |  | Bolt & Nuts
2 | 7 | 2 | 3 | 6 | 1 | 0 | 2.7.3.6.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 6 | 1 | 1 | 2.7.2.3.6.1.1 | BK-W007S-PEDCO-110-PI-MR-0006 | PMR For Bolt/Nuts - W007S |  | BK-W007S-PEDCO-110-PI-MR-0006 | BK-W007S-PEDCO-110-PI-MR-0006 | BK | W007S | PEDCO | 110 | PI | MR | 0006 | F0Z-708091 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 3 | 6 | 2 | 0 | 2.7.3.6.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 6 | 2 | 1 | 2.7.2.3.6.2.1 | BK-W007S-PEDCO-110-PI-TB-0006 | TBE For Bolt/Nuts - W007S |  | BK-W007S-PEDCO-110-PI-TB-0006 | BK-W007S-PEDCO-110-PI-TB-0006 | BK | W007S | PEDCO | 110 | PI | TB | 0006 | F0Z-708092 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 3 | 7 | 0 | 0 | 2.7.2.3.7 |  | Sampling Connection
2 | 7 | 2 | 3 | 7 | 1 | 0 | 2.7.3.7.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 7 | 1 | 1 | 2.7.2.3.7.1.1 | BK-W007S-PEDCO-110-PI-MR-0007 | PMR For Sampling Connection Set - W007S |  | BK-W007S-PEDCO-110-PI-MR-0007 | BK-W007S-PEDCO-110-PI-MR-0007 | BK | W007S | PEDCO | 110 | PI | MR | 0007 | F0Z-708093 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 3 | 7 | 2 | 0 | 2.7.3.7.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 7 | 2 | 1 | 2.7.2.3.7.2.1 | BK-W007S-PEDCO-110-PI-TB-0007 | TBE For Sampling Connection - W007S |  | BK-W007S-PEDCO-110-PI-TB-0007 | BK-W007S-PEDCO-110-PI-TB-0007 | BK | W007S | PEDCO | 110 | PI | TB | 0007 | F0Z-708094 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 3 | 8 | 0 | 0 | 2.7.2.3.8 |  | Stone Trap
2 | 7 | 2 | 3 | 8 | 1 | 0 | 2.7.3.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 8 | 1 | 1 | 2.7.2.3.8.1.1 | BK-W007S-PEDCO-110-PI-MR-0008 | PMR For Stone Trap - W007S |  | BK-W007S-PEDCO-110-PI-MR-0008 | BK-W007S-PEDCO-110-PI-MR-0008 | BK | W007S | PEDCO | 110 | PI | MR | 0008 | F0Z-708095 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 3 | 8 | 2 | 0 | 2.7.3.8.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 8 | 2 | 1 | 2.7.2.3.8.2.1 | BK-W007S-PEDCO-110-PI-TB-0008 | TBE For Stone Trap - W007S |  | BK-W007S-PEDCO-110-PI-TB-0008 | BK-W007S-PEDCO-110-PI-TB-0008 | BK | W007S | PEDCO | 110 | PI | TB | 0008 | F0Z-708096 | IFI | IFI | 2022-06-07 | 2022-06-14 | 2022-06-15 | 7 | 1 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-24 |  |  | D00 | IFI | T-0996 | 44705 | 1401/03/03 | T-0996 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04515 | 44713 | 1401/03/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-102043 | 44726 | 1401/03/24 | 44727 | 1401/03/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03 | T-0996 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04515 | 44713 | 1401/03/11 | CM-C3 | [6 empty] | 1401-2294-102043 | 2022-06-14 | 1401/03/24 | 44727 | 1401/03/25 | CM
2 | 7 | 2 | 3 | 9 | 0 | 0 | 2.7.2.3.9 |  | Pipe Support
2 | 7 | 2 | 3 | 9 | 1 | 0 | 2.7.3.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 9 | 1 | 1 | 2.7.2.3.9.1.1 | BK-W007S-PEDCO-110-PI-MR-0009 | PMR For Pipe Support - W007S |  | BK-W007S-PEDCO-110-PI-MR-0009 | BK-W007S-PEDCO-110-PI-MR-0009 | BK | W007S | PEDCO | 110 | PI | MR | 0009 | F0Z-708097 | IFI | IFI | 2022-11-02 | 2022-11-05 | 2022-11-06 | 3 | 1 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-19 |  |  | D00 | IFI | T-1518 | 44853 | 1401/07/27 | T-1518 | 44853 | 1401/07/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294199 | 44870 | 1401/08/12 | 44871 | 1401/08/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1518 | 2022-10-19 | 1401/07/27 | T-1518 | 44853 | 1401/07/27 | [10 empty] | 1401-2294-294199 | 2022-11-05 | 1401/08/12 | 44871 | 1401/08/15 | CM
2 | 7 | 2 | 3 | 9 | 2 | 0 | 2.7.3.9.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 9 | 2 | 1 | 2.7.2.3.9.2.1 | BK-W007S-PEDCO-110-PI-TB-0009 | TBE For Pipe Support - W007S |  | BK-W007S-PEDCO-110-PI-TB-0009 | BK-W007S-PEDCO-110-PI-TB-0009 | BK | W007S | PEDCO | 110 | PI | TB | 0009 | F0Z-708098 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 3 | 9 | 0 | 0 | 2.7.2.3.9 |  | BURN PIT PIPES
2 | 7 | 2 | 3 | 9 | 1 | 0 | 2.7.3.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 3 | 9 | 1 | 1 | 2.7.2.3.9.1.1 | BK-W007S-PEDCO-110-PI-MR-0009 | PMR FOR BURN PIT PIPES– W007S |  | BK-W007S-PEDCO-110-PI-MR-0011 | BK-W007S-PEDCO-110-PI-MR-0009 | BK | W007S | PEDCO | 110 | PI | MR | 0009 | F0Z-708097 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [11 empty] | D00 | IFI | T-1550 | 44859 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1550 | 2022-10-25 | 1401/08/03 | T-1550 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06180 | 44880 | 1401/08/24 | CM-C2
2 | 7 | 2 | 3 | 9 | 2 | 0 | 2.7.3.9.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 9 | 2 | 1 | 2.7.2.3.9.2.1 | BK-W007S-PEDCO-110-PI-TB-0009 | TBE FOR BURN PIT PIPES– W007S |  | BK-W007S-PEDCO-110-PI-TB-0011 | BK-W007S-PEDCO-110-PI-TB-0009 | BK | W007S | PEDCO | 110 | PI | TB | 0009 | F0Z-708098 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 4 | 0 | 0 | 0 | 2.7.2.4 |  | Pipeline
2 | 7 | 2 | 4 | 1 | 0 | 0 | 2.7.2.4.1 |  | Line Pipe | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 4 | 1 | 1 | 0 | 2.7.4.1.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 4 | 1 | 1 | 1 | 2.7.2.4.1.1.1 | BK-W007S-PEDCO-110-PL-MR-0001 | PMR For Line Pipes - W007S |  | BK-W007S-PEDCO-110-PL-MR-0001 | BK-W007S-PEDCO-110-PL-MR-0001 | BK | W007S | PEDCO | 110 | PL | MR | 0001 | F0Z-708099 | IFI | IFI | 2022-11-06 | 2022-11-05 | 2022-11-09 | -1 | 4 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-23 |  |  | D00 | IFI | T-1529 | 44857 | 1401/08/01 | T-1529 | 44857 | 1401/08/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296595 | 44870 | 1401/08/14 | 44874 | 1401/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1529 | 2022-10-23 | 1401/08/01 | T-1529 | 44857 | 1401/08/01 | [10 empty] | 1401-2294-296595 | 2022-11-05 | 1401/08/14 | 44874 | 1401/08/18 | AP
2 | 7 | 2 | 4 | 1 | 2 | 0 | 2.7.4.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 4 | 1 | 2 | 1 | 2.7.2.4.1.2.1 | BK-W007S-PEDCO-110-PL-TB-0001 | TBE FOR LINE PIPES – W007S |  | BK-W007S-PEDCO-110-PL-TB-0001 | BK-W007S-PEDCO-110-PL-TB-0001 | BK | W007S | PEDCO | 110 | PL | TB | 0001 | F0Z-708100 | IFI | IFI | 2022-03-05 | 2022-03-10 | 2022-03-14 | 5 | 4 | 9 | IFI | 2022-05-28 | 2022-05-31 | 2022-06-07 | 3 | 7 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 44628 | 1400/12/17 | RJ-C4 | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 44634 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 44695 | 1401/02/24 | T-0944 | 44695 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 44704 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PL-TB-0001-D00 | [5 empty] | 1401-2294-84917 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PL-TB-0001-D00
2 | 7 | 2 | 4 | 2 | 0 | 0 | 2.7.2.4.2 |  | Line Pipe | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 4 | 2 | 1 | 0 | 2.7.4.2.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 4 | 2 | 1 | 1 | 2.7.2.4.2.1.1 | BK-W007S-PEDCO-110-PL-MR-0002 | PMR For Flow Line Support - W007S |  | BK-W007S-PEDCO-110-PL-MR-0002 | BK-W007S-PEDCO-110-PL-MR-0002 | BK | W007S | PEDCO | 110 | PL | MR | 0002 | F0Z-708101 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 4 | 2 | 2 | 0 | 2.7.4.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 4 | 2 | 2 | 1 | 2.7.2.4.2.2.1 | BK-W007S-PEDCO-110-PL-TB-0002 | TBE For Flow Line Support - W007S |  | BK-W007S-PEDCO-110-PL-TB-0002 | BK-W007S-PEDCO-110-PL-TB-0002 | BK | W007S | PEDCO | 110 | PL | TB | 0002 | F0Z-708102 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 5 | 0 | 0 | 0 | 2.7.2.5 |  | Control & Instrumentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 1 | 0 | 0 | 2.7.2.5.1 |  | Control System/Console/Furniture
2 | 7 | 2 | 5 | 1 | 1 | 0 | 2.7.5.1.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 1 | 1 | 1 | 2.7.2.5.1.1.1 | BK-W007S-PEDCO-110-IN-MR-0001 | PMR For Control System/Console/Furniture - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0001 | BK-W007S-PEDCO-110-IN-MR-0001 | BK | W007S | PEDCO | 110 | IN | MR | 0001 | F0Z-708103 | IFI | IFI | 2022-08-15 | 2022-09-08 | 2022-09-13 | 24 | 5 | 29 | IFI | 2022-10-15 | 2022-10-24 | 2022-10-26 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-01 |  |  | D01 | IFI | T-1504 | 44835 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-06028 | 44864 | 1401/08/08 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-278708 | 44858 | 1401/08/02 | 44860 | 1401/08/04 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1232 | 2022-08-01 | 1401/05/10 |  |  |  | BK-SUR-ENG-INS-01-05492 | 44793 | 1401/05/29 | CM-C3 | [6 empty] | 1401-2294-216182 | 2022-09-08 | 1401/06/17 | 44817 | 1401/06/22 | CM | [10 empty] | D01 | IFI | T-1504 | 44835 | 1401/07/25 |  |  |  | BK-SUR-ENG-INS-01-06028 | 44864 | 1401/08/08 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0001_D00 | [5 empty] | 1401-2294-278708 | 44858 | 1401/08/02 | 44860 | 1401/08/04 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0001_D00
2 | 7 | 2 | 5 | 1 | 2 | 0 | 2.7.5.1.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 1 | 2 | 1 | 2.7.2.5.1.2.1 | BK-W007S-PEDCO-110-IN-TB-0001 | TBE/TBA For Control System/Console/Furniture - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0001 | BK-W007S-PEDCO-110-IN-TB-0001 | BK | W007S | PEDCO | 110 | IN | TB | 0001 | F0Z-708104 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 2 | 0 | 0 | 2.7.2.5.2 |  | ESD System
2 | 7 | 2 | 5 | 2 | 1 | 0 | 2.7.5.2.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 2 | 1 | 1 | 2.7.2.5.2.1.1 | BK-W007S-PEDCO-110-IN-MR-0002 | PMR For ESD System - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0002 | BK-W007S-PEDCO-110-IN-MR-0002 | BK | W007S | PEDCO | 110 | IN | MR | 0002 | F0Z-708105 | IFI | IFI | 2022-08-17 | 2022-09-08 | 2022-09-13 | 22 | 5 | 27 | IFI | 2022-10-31 | 2022-10-24 | 2022-10-26 | -7 | 2 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-03 |  |  | D01 | IFI | T-1506 | 44851 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-06029 | 44864 | 1401/08/08 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-278705 | 44858 | 1401/08/02 | 44860 | 1401/08/04 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1243 | 2022-08-03 | 1401/05/12 |  |  |  | BK-SUR-ENG-INS-01-05494 | 44793 | 1401/05/029 | CM-C3 | [6 empty] | 1401-2294-216181 | 2022-09-08 | 1401/06/17 | 44817 | 1401/06/22 | CM | [10 empty] | D01 | IFI | T-1506 | 44851 | 1401/07/25 |  |  |  | BK-SUR-ENG-INS-01-06029 | 44864 | 1401/08/08 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0002_D00 | [5 empty] | 1401-2294-278705 | 44858 | 1401/08/02 | 44860 | 1401/08/04 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0002_D00
2 | 7 | 2 | 5 | 2 | 2 | 0 | 2.7.5.2.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 2 | 2 | 1 | 2.7.2.5.2.2.1 | BK-W007S-PEDCO-110-IN-TB-0002 | TBE/TBA For ESD System - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0002 | BK-W007S-PEDCO-110-IN-TB-0002 | BK | W007S | PEDCO | 110 | IN | TB | 0002 | F0Z-708106 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 3 | 0 | 0 | 2.7.2.5.3 |  | F&G System
2 | 7 | 2 | 5 | 3 | 1 | 0 | 2.7.5.3.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 3 | 1 | 1 | 2.7.2.5.3.1.1 | BK-W007S-PEDCO-110-IN-MR-0003 | PMR For F&G System - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0003 | BK-W007S-PEDCO-110-IN-MR-0003 | BK | W007S | PEDCO | 110 | IN | MR | 0003 | F0Z-708107 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 3 | 2 | 0 | 2.7.5.3.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 3 | 2 | 1 | 2.7.2.5.3.2.1 | BK-W007S-PEDCO-110-IN-TB-0003 | TBE/TBA For F&G System - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0003 | BK-W007S-PEDCO-110-IN-TB-0003 | BK | W007S | PEDCO | 110 | IN | TB | 0003 | F0Z-708108 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 4 | 0 | 0 | 2.7.2.5.4 |  | ON/OFF & Shutdown Valves
2 | 7 | 2 | 5 | 4 | 1 | 0 | 2.7.5.4.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 4 | 1 | 1 | 2.7.2.5.4.1.1 | BK-W007S-PEDCO-110-IN-MR-0004 | PMR For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0004 | BK-W007S-PEDCO-110-IN-MR-0004 | BK | W007S | PEDCO | 110 | IN | MR | 0004 | F0Z-708109 | IFI | IFI | 2022-04-09 | 2022-04-09 | 2022-04-12 | 0 | 3 | 3 | IFI | 2022-07-09 | 2022-08-02 | 2022-08-06 | 24 | 4 | 28 | IFI | 2022-10-08 | 2022-10-17 | 2022-10-17 | 9 | 0 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-26 |  |  | D02 | IFI | T-1438 | 44828 | 1401/07/02 | T-1438 | 44828 | 1401/07/02 | BK-SUR-ENG-INS-01-05895 | 44846 | 1401/07/20 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-260358 | 44851 | 1401/07/20 | 44851 | 1401/07/25 | AP | NISCO-CRS-BK-W007S-PEDCO-110-IN-MR-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0738 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03791 | 44660 | 1401/01/20 | CM-C3 | [6 empty] | 1401-2294-16060 | 2022-04-09 | 1401/01/20 | 44663 | 1401/01/23 | CM | [10 empty] | D01 | IFI | T-1112 | 44737 | 1401/04/04 |  |  |  | BK-SUR-ENG-INS-01-05249 | 44768 | 1401/05/04 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0004_D00 | [5 empty] | 1401-2294-163215 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0004_D00 | [9 empty] | D02 | IFI | T-1438 | 44828 | 1401/07/02 | T-1438 | 44828 | 1401/07/02 | BK-SUR-ENG-INS-01-05895 | 44846 | 1401/07/20 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0004_D01 | [5 empty] | 1401-2294-260358 | 44851 | 1401/07/20 | 44851 | 1401/07/25 | AP | NISCO-CRS-BK-W007S-PEDCO-110-IN-MR-0004_D01
2 | 7 | 2 | 5 | 4 | 2 | 0 | 2.7.5.4.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 4 | 2 | 1 | 2.7.2.5.4.2.1 | BK-W007S-PEDCO-110-IN-TB-0004 | TBE/TBA For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0004 | BK-W007S-PEDCO-110-IN-TB-0004 | BK | W007S | PEDCO | 110 | IN | TB | 0004 | F0Z-708110 | IFI | IFI | 2022-10-26 | 0 | 0 | -44860 | 0 | -44860 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-12 |  |  | D00 | IFI | T-1491 | 44846 | 1401/07/20 | T-1491 | 44846 | 1401/07/20 | BK-SUR-ENG-INS-01-06027 | 44865 | 1401/08/08 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1491 | 2022-10-12 | 1401/07/20 | T-1491 | 44846 | 1401/07/20 | BK-SUR-ENG-INS-01-06027 | 44865 | 1401/08/08 | CM-C3
2 | 7 | 2 | 5 | 5 | 0 | 0 | 2.7.2.5.5 |  | Control Valves
2 | 7 | 2 | 5 | 5 | 1 | 0 | 2.7.5.5.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 5 | 1 | 1 | 2.7.2.5.5.1.1 | BK-W007S-PEDCO-110-IN-MR-0005 | PMR For Control Valves - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0005 | BK-W007S-PEDCO-110-IN-MR-0005 | BK | W007S | PEDCO | 110 | IN | MR | 0005 | F0Z-708111 | IFI | IFI | 2022-03-28 | 2022-04-11 | 2022-04-17 | 14 | 6 | 20 | IFI | 2022-07-12 | 2022-09-01 | 2022-09-05 | 51 | 4 | 55 | IFI | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-14 |  |  | D02 | IFI | T-1524 | 44856 | 1401/07/30 | T-1524 | 44856 | 1401/07/30 | BK-SUR-ENG-INS-01-06097 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0733 | 2022-03-14 | 1400/12/23 |  |  |  | BK-SUR-ENG-INS-01-03732 | 44656 | 1401/01/16 | CM-C3 | [6 empty] | 1401-2294-18032 | 2022-04-11 | 1401/01/22 | 44668 | 1401/01/28 | CM | [10 empty] | D01 | IFI | T-1127 | 44740 | 1401/04/08 |  |  |  | BK-SUR-ENG-INS-01-05318 | 44775 | 1401/05/11 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0005_D00 | [5 empty] | 1401-2294-205792 | 44805 | 1401/06/10 | 44809 | 1401/06/14 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0005_D00 | [9 empty] | D02 | IFI | T-1524 | 44856 | 1401/07/30 | T-1524 | 44856 | 1401/07/30 | BK-SUR-ENG-INS-01-06097 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0005_D01 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0005_D01
2 | 7 | 2 | 5 | 5 | 2 | 0 | 2.7.5.5.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 5 | 2 | 1 | 2.7.2.5.5.2.1 | BK-W007S-PEDCO-110-IN-TB-0005 | TBE/TBA For Control Valves - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0005 | BK-W007S-PEDCO-110-IN-TB-0005 | BK | W007S | PEDCO | 110 | IN | TB | 0005 | F0Z-708112 | IFI | IFI | 2022-10-03 | 2022-10-17 | 2022-10-22 | 14 | 5 | 19 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | T-1416 | 44823 | 1401/06/28 | T-1416 | 44823 | 1401/06/28 | BK-SUR-ENG-INS-01-05832 | 44837 | 1401/07/11 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-267237 | 44851 | 1401/07/25 | 44856 | 1401/07/30 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1416 | 2022-09-19 | 1401/06/28 | T-1416 | 44823 | 1401/06/28 | BK-SUR-ENG-INS-01-05832 | 44837 | 1401/07/11 | CM-C2 | [6 empty] | 1401-2294-267237 | 2022-10-17 | 1401/07/25 | 44856 | 1401/07/30 | RJ
2 | 7 | 2 | 5 | 6 | 0 | 0 | 2.7.2.5.6 |  | Pressure Safety Valves (PSV)
2 | 7 | 2 | 5 | 6 | 1 | 0 | 2.7.5.6.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 6 | 1 | 1 | 2.7.2.5.6.1.1 | BK-W007S-PEDCO-110-IN-MR-0006 | PMR For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0006 | BK-W007S-PEDCO-110-IN-MR-0006 | BK | W007S | PEDCO | 110 | IN | MR | 0006 | F0Z-708113 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 6 | 2 | 0 | 2.7.5.6.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 6 | 2 | 1 | 2.7.2.5.6.2.1 | BK-W007S-PEDCO-110-IN-TB-0006 | TBE/TBA For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0006 | BK-W007S-PEDCO-110-IN-TB-0006 | BK | W007S | PEDCO | 110 | IN | TB | 0006 | F0Z-708114 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 7 | 0 | 0 | 2.7.2.5.7 |  | F&G Devices
2 | 7 | 2 | 5 | 7 | 1 | 0 | 2.7.5.7.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 7 | 1 | 1 | 2.7.2.5.7.1.1 | BK-W007S-PEDCO-110-IN-MR-0007 | PMR For F&G Detector - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0007 | BK-W007S-PEDCO-110-IN-MR-0007 | BK | W007S | PEDCO | 110 | IN | MR | 0007 | F0Z-708115 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 7 | 2 | 0 | 2.7.5.7.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 7 | 2 | 1 | 2.7.2.5.7.2.1 | BK-W007S-PEDCO-110-IN-TB-0007 | TBE/TBA For F&G Detector - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0007 | BK-W007S-PEDCO-110-IN-TB-0007 | BK | W007S | PEDCO | 110 | IN | TB | 0007 | F0Z-708116 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 8 | 0 | 0 | 2.7.2.5.8 |  | Orifice and Restriction Orifice Plate
2 | 7 | 2 | 5 | 8 | 1 | 0 | 2.7.5.8.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 8 | 1 | 1 | 2.7.2.5.8.1.1 | BK-W007S-PEDCO-110-IN-MR-0008 | PMR For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0008 | BK-W007S-PEDCO-110-IN-MR-0008 | BK | W007S | PEDCO | 110 | IN | MR | 0008 | F0Z-708117 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 8 | 2 | 0 | 2.7.5.8.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 8 | 2 | 1 | 2.7.2.5.8.2.1 | BK-W007S-PEDCO-110-IN-TB-0008 | TBE/TBA For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0008 | BK-W007S-PEDCO-110-IN-TB-0008 | BK | W007S | PEDCO | 110 | IN | TB | 0008 | F0Z-708118 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 9 | 0 | 0 | 2.7.2.5.9 |  | Corrosion Coupon/Probe
2 | 7 | 2 | 5 | 9 | 1 | 0 | 2.7.5.9.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 9 | 1 | 1 | 2.7.2.5.9.1.1 | BK-W007S-PEDCO-110-IN-MR-0009 | PMR For Corrosion Coupon/Probe - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0009 | BK-W007S-PEDCO-110-IN-MR-0009 | BK | W007S | PEDCO | 110 | IN | MR | 0009 | F0Z-708119 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 9 | 2 | 0 | 2.7.5.9.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 9 | 2 | 1 | 2.7.2.5.9.2.1 | BK-W007S-PEDCO-110-IN-TB-0009 | TBE/TBA For Corrosion Coupon/Probe - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0009 | BK-W007S-PEDCO-110-IN-TB-0009 | BK | W007S | PEDCO | 110 | IN | TB | 0009 | F0Z-708120 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 10 | 0 | 0 | 2.7.2.5.10 |  | Pressure Transmitter
2 | 7 | 2 | 5 | 10 | 1 | 0 | 2.7.5.10.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 10 | 1 | 1 | 2.7.2.5.10.1.1 | BK-W007S-PEDCO-110-IN-MR-0010 | PMR For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0010 | [8 empty] | F0Z-708121 | IFI | IFI | 2022-01-30 | 2021-01-31 | 2022-02-01 | -364 | 366 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-16 |  |  | D00 | IFI | T-0471 | 44577 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390714 | 44227 | 1400/11/11 | 44593 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C3 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 44593 | 1400/11/12 | CM
2 | 7 | 2 | 5 | 10 | 2 | 0 | 2.7.5.10.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 10 | 2 | 1 | 2.7.2.5.10.2.1 | BK-W007S-PEDCO-110-IN-TB-0010 | TBE/TBA For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0010 | [8 empty] | F0Z-708122 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 11 | 0 | 0 | 2.7.2.5.11 |  | Flow Transmitter/ Diff. Pressure Transmitter
2 | 7 | 2 | 5 | 11 | 1 | 0 | 2.7.5.11.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 11 | 1 | 1 | 2.7.2.5.11.1.1 | BK-W007S-PEDCO-110-IN-MR-0011 | PMR For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0011 | BK-W007S-PEDCO-110-IN-MR-0011 | BK | W007S | PEDCO | 110 | IN | MR | 0011 | F0Z-708123 | IFI | IFI | 2022-01-30 | 2021-01-31 | 2022-02-01 | -364 | 366 | 2 | IFI | 2022-09-19 | 2022-09-21 | 2022-10-02 | 2 | 11 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-16 |  |  | D01 | IFI | T-1366 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05717 | 44823 | 1401/06/28 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0011_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233356 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W007S-PEDCO-110-IN-MR-0011_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C3 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 44593 | 1400/11/12 | CM | [10 empty] | D01 | IFI | T-1366 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-INS-01-05717 | 44823 | 1401/06/28 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0011_D00 | [5 empty] | 1401-2294-233356 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W007S-PEDCO-110-IN-MR-0011_D00
2 | 7 | 2 | 5 | 11 | 2 | 0 | 2.7.5.11.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 11 | 2 | 1 | 2.7.2.5.11.2.1 | BK-W007S-PEDCO-110-IN-TB-0011 | TBE/TBA For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0011 | BK-W007S-PEDCO-110-IN-TB-0011 | BK | W007S | PEDCO | 110 | IN | TB | 0011 | F0Z-708124 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 12 | 0 | 0 | 2.7.2.5.12 |  | Instrument/F&G Cable
2 | 7 | 2 | 5 | 12 | 1 | 0 | 2.7.5.12.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 12 | 1 | 1 | 2.7.2.5.12.1.1 | BK-W007S-PEDCO-110-IN-MR-0012 | PMR For Instrument/F&G Cable - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0012 | BK-W007S-PEDCO-110-IN-MR-0012 | BK | W007S | PEDCO | 110 | IN | MR | 0012 | F0Z-708125 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 5 | 12 | 2 | 0 | 2.7.5.12.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 12 | 2 | 1 | 2.7.2.5.12.2.1 | BK-W007S-PEDCO-110-IN-TB-0012 | TBE/TBA For Instrument/F&G Cable - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0012 | BK-W007S-PEDCO-110-IN-TB-0012 | BK | W007S | PEDCO | 110 | IN | TB | 0012 | F0Z-708126 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 5 | 13 | 0 | 0 | 2.7.2.5.13 |  | Instrument/F&G Junction box and Gland | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 13 | 1 | 0 | 2.7.5.13.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 13 | 1 | 1 | 2.7.2.5.13.1.1 | BK-W007S-PEDCO-110-IN-MR-0013 | PMR For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0013 | BK-W007S-PEDCO-110-IN-MR-0013 | BK | W007S | PEDCO | 110 | IN | MR | 0013 | F0Z-708127 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 5 | 13 | 2 | 0 | 2.7.5.13.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 13 | 2 | 1 | 2.7.2.5.13.2.1 | BK-W007S-PEDCO-110-IN-TB-0013 | TBE/TBA For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0013 | BK-W007S-PEDCO-110-IN-TB-0013 | BK | W007S | PEDCO | 110 | IN | TB | 0013 | F0Z-708128 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 5 | 14 | 0 | 0 | 2.7.2.5.14 |  | Instrument Installation Accessories | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 14 | 1 | 0 | 2.7.5.14.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 14 | 1 | 1 | 2.7.2.5.14.1.1 | BK-W007S-PEDCO-110-IN-MR-0014 | PMR For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-MR-0014 | BK-W007S-PEDCO-110-IN-MR-0014 | BK | W007S | PEDCO | 110 | IN | MR | 0014 | F0Z-708129 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 5 | 14 | 2 | 0 | 2.7.5.14.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 14 | 2 | 1 | 2.7.2.5.14.2.1 | BK-W007S-PEDCO-110-IN-TB-0014 | TBE/TBA For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold |  | BK-W007S-PEDCO-110-IN-TB-0014 | BK-W007S-PEDCO-110-IN-TB-0014 | BK | W007S | PEDCO | 110 | IN | TB | 0014 | F0Z-708130 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 15 | 0 | 0 | 2.7.2.5.15 |  | Differential Pressure/Pressure Gauge
2 | 7 | 2 | 5 | 15 | 1 | 0 | 2.7.5.15.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 15 | 1 | 1 | 2.7.2.5.15.1.1 | BK-W007S-PEDCO-110-IN-MR-0015 | PMR For Differential Pressure/Pressure Gauge - Manifold & W007S |  | BK-W007S-PEDCO-110-IN-MR-0015 | BK-W007S-PEDCO-110-IN-MR-0015 | BK | W007S | PEDCO | 110 | IN | MR | 0015 | F0Z-708131 | IFI | IFI | 2022-01-30 | 2021-01-31 | 2022-02-01 | -364 | 366 | 2 | IFI | 2022-09-18 | 2022-09-21 | 2022-10-02 | 3 | 11 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-16 |  |  | D01 | IFI | T-1351 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0015_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W007S-PEDCO-110-IN-MR-0015_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C3 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 44593 | 1400/11/12 | CM | [10 empty] | D01 | IFI | T-1351 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0015_D00 | [5 empty] | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W007S-PEDCO-110-IN-MR-0015_D00
2 | 7 | 2 | 5 | 15 | 2 | 0 | 2.7.5.15.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 15 | 2 | 1 | 2.7.2.5.15.2.1 | BK-W007S-PEDCO-110-IN-TB-0015 | TBE/TBA For Differential Pressure/Pressure Gauge - Manifold & W007S |  | BK-W007S-PEDCO-110-IN-TB-0015 | BK-W007S-PEDCO-110-IN-TB-0015 | BK | W007S | PEDCO | 110 | IN | TB | 0015 | F0Z-708132 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 16 | 0 | 0 | 2.7.2.5.16 |  | Temperature Gauge
2 | 7 | 2 | 5 | 16 | 1 | 0 | 2.7.5.16.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 16 | 1 | 1 | 2.7.2.5.16.1.1 | BK-W007S-PEDCO-110-IN-MR-0016 | PMR For Temperature Gauge - Manifold & W007S |  | BK-W007S-PEDCO-110-IN-MR-0016 | BK-W007S-PEDCO-110-IN-MR-0016 | BK | W007S | PEDCO | 110 | IN | MR | 0016 | F0Z-708133 | IFI | IFI | 2022-01-30 | 2021-01-31 | 2022-02-01 | -364 | 366 | 2 | IFI | 2022-09-18 | 2022-09-21 | 2022-10-02 | 3 | 11 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-16 |  |  | D01 | IFI | T-1351 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0016_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W007S-PEDCO-110-IN-MR-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 44587 | 1400/11/06 | CM-C3 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 44593 | 1400/11/12 | CM | [10 empty] | D01 | IFI | T-1351 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-INS-01-05711 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0016_D00 | [5 empty] | 1401-2294-233404 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | AP | NISCO-CRS-BK-W007S-PEDCO-110-IN-MR-0016_D00
2 | 7 | 2 | 5 | 16 | 2 | 0 | 2.7.5.16.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 16 | 2 | 1 | 2.7.2.5.16.2.1 | BK-W007S-PEDCO-110-IN-TB-0016 | TBE/TBA For Temperature Gauge - Manifold & W007S |  | BK-W007S-PEDCO-110-IN-TB-0016 | BK-W007S-PEDCO-110-IN-TB-0016 | BK | W007S | PEDCO | 110 | IN | TB | 0016 | F0Z-708134 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 17 | 0 | 0 | 2.7.2.5.17 |  | Instrument Tube and Fitting
2 | 7 | 2 | 5 | 17 | 1 | 0 | 2.7.5.17.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 17 | 1 | 1 | 2.7.2.5.17.1.1 | BK-W007S-PEDCO-110-IN-MR-0017 | PMR For Instrument Tube and Fitting - Manifold & W007S |  | BK-W007S-PEDCO-110-IN-MR-0017 | BK-W007S-PEDCO-110-IN-MR-0017 | BK | W007S | PEDCO | 110 | IN | MR | 0017 | F0Z-708135 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 5 | 17 | 2 | 0 | 2.7.5.17.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 17 | 2 | 1 | 2.7.2.5.17.2.1 | BK-W007S-PEDCO-110-IN-TB-0017 | TBE/TBA For Instrument Tube and Fitting - Manifold & W007S |  | BK-W007S-PEDCO-110-IN-TB-0017 | BK-W007S-PEDCO-110-IN-TB-0017 | BK | W007S | PEDCO | 110 | IN | TB | 0017 | F0Z-708136 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 18 | 0 | 0 | 2.7.2.5.18 |  | Instrument Cable Tray
2 | 7 | 2 | 5 | 18 | 1 | 0 | 2.7.5.18.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 18 | 1 | 1 | 2.7.2.5.18.1.1 | BK-W007S-PEDCO-110-IN-MR-0018 | PMR For Instrument Cable Tray/Ladder - Manifold & W007S |  | BK-W007S-PEDCO-110-IN-MR-0018 | BK-W007S-PEDCO-110-IN-MR-0018 | BK | W007S | PEDCO | 110 | IN | MR | 0018 | F0Z-708137 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 5 | 18 | 2 | 0 | 2.7.5.18.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 18 | 2 | 1 | 2.7.2.5.18.2.1 | BK-W007S-PEDCO-110-IN-TB-0018 | TBE/TBA For Instrument Cable Tray/Ladder - Manifold & W007S |  | BK-W007S-PEDCO-110-IN-TB-0018 | BK-W007S-PEDCO-110-IN-TB-0018 | BK | W007S | PEDCO | 110 | IN | TB | 0018 | F0Z-708138 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 18 | 0 | 0 | 2.7.2.5.18 |  | Level Transmitter
2 | 7 | 2 | 5 | 18 | 1 | 0 | 2.7.5.18.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 18 | 1 | 1 | 2.7.2.5.18.1.1 | BK-W007S-PEDCO-110-IN-MR-0019 | PMR For Level Transmitter - W007S & Manifold |  | BK-W007S-PEDCO-110-IN-MR-0019 | BK-W007S-PEDCO-110-IN-MR-0019 | BK | W007S | PEDCO | 110 | IN | MR | 0019 | F0Z-708139 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 5 | 18 | 2 | 0 | 2.7.5.18.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 18 | 2 | 1 | 2.7.2.5.18.2.1 | BK-W007S-PEDCO-110-IN-TB-0019 | TBE/TBA For Level Transmitter - W007S & Manifold |  | BK-W007S-PEDCO-110-IN-TB-0019 | BK-W007S-PEDCO-110-IN-TB-0019 | BK | W007S | PEDCO | 110 | IN | TB | 0019 | F0Z-708140 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 5 | 18 | 0 | 0 | 2.7.2.5.18 |  | Level Transmitter
2 | 7 | 2 | 5 | 18 | 1 | 0 | 2.7.5.18.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 5 | 18 | 1 | 1 | 2.7.2.5.18.1.1 | BK-W007S-PEDCO-110-IN-MR-0020 | PMR For Level Guage - W007S |  | BK-W007S-PEDCO-110-IN-MR-0020 | BK-W007S-PEDCO-110-IN-MR-0020 | BK | W007S | PEDCO | 110 | IN | MR | 0020 | F0Z-709409 | IFI | IFI | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-26 |  |  | D00 | IFI | T-1562 | 44860 | 1401/08/04 | T-1562 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06136 | 44873 | 1401/08/17 | CM-C2 | 0 | BK-SUR-ENG-INS-01-06189 | 44881 | 1401/08/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1562 | 2022-10-26 | 1401/08/04 | T-1562 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06136 | 44873 | 1401/08/17 | CM-C2 |  | BK-SUR-ENG-INS-01-06189 | 44881 | 1401/08/25 | CM-C2
2 | 7 | 2 | 5 | 18 | 2 | 0 | 2.7.5.18.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 18 | 2 | 1 | 2.7.2.5.18.2.1 | BK-W007S-PEDCO-110-IN-TB-0020 | TBE/TBA For Level Guage - W007S |  | BK-W007S-PEDCO-110-IN-TB-0020 | BK-W007S-PEDCO-110-IN-TB-0020 | BK | W007S | PEDCO | 110 | IN | TB | 0020 | F0Z-709410 | IFI | IFI | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-26 |  |  | D00 | IFI | T-1561 | 44860 | 1401/08/04 | T-1561 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06150 | 44874 | 1401/08/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1561 | 2022-10-26 | 1401/08/04 | T-1561 | 44860 | 1401/08/04 | BK-SUR-ENG-INS-01-06150 | 44874 | 1401/08/18 | CM-C3
2 | 7 | 2 | 6 | 0 | 0 | 0 | 2.7.2.6 |  | Safety & Fire Fighting
2 | 7 | 2 | 6 | 1 | 0 | 0 | 2.7.2.6.1 |  | Fire Fighting and Safety Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 6 | 1 | 1 | 0 | 2.7.6.1.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 6 | 1 | 1 | 1 | 2.7.2.6.1.1.1 | BK-W007S-PEDCO-110-SA-MR-0001 | PMR For Fire Fighting and Safety Equipment - Manifold & W007S |  | BK-W007S-PEDCO-110-SA-MR-0001 | BK-W007S-PEDCO-110-SA-MR-0001 | BK | W007S | PEDCO | 110 | SA | MR | 0001 | F0Z-708141 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 6 | 1 | 2 | 0 | 2.7.6.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 6 | 1 | 2 | 1 | 2.7.2.6.1.2.1 | BK-W007S-PEDCO-110-SA-TB-0001 | TBE For Fire Fighting and Safety Equipment - Manifold & W007S |  | BK-W007S-PEDCO-110-SA-TB-0001 | BK-W007S-PEDCO-110-SA-TB-0001 | BK | W007S | PEDCO | 110 | SA | TB | 0001 | F0Z-708142 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 6 | 2 | 0 | 0 | 2.7.2.6.2 |  | Safety Sign | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 6 | 2 | 1 | 0 | 2.7.6.2.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 6 | 2 | 1 | 1 | 2.7.2.6.2.1.1 | BK-W007S-PEDCO-110-SA-MR-0002 | PMR For Fire Safety Sign - Manifold & W007S |  | BK-W007S-PEDCO-110-SA-MR-0002 | BK-W007S-PEDCO-110-SA-MR-0002 | BK | W007S | PEDCO | 110 | SA | MR | 0002 | F0Z-708143 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 6 | 2 | 2 | 0 | 2.7.6.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 6 | 2 | 2 | 1 | 2.7.2.6.2.2.1 | BK-W007S-PEDCO-110-SA-TB-0002 | TBE For Fire Safety Sign - Manifold & W007S |  | BK-W007S-PEDCO-110-SA-TB-0002 | BK-W007S-PEDCO-110-SA-TB-0002 | BK | W007S | PEDCO | 110 | SA | TB | 0002 | F0Z-708144 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 7 | 0 | 0 | 0 | 2.7.2.7 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 1 | 0 | 0 | 2.7.2.7.1 |  | LV Switchgear & MCC
2 | 7 | 2 | 7 | 1 | 1 | 0 | 2.7.7.1.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 1 | 1 | 1 | 2.7.2.7.1.1.1 | BK-W007S-PEDCO-110-EL-MR-0001 | PMR For LV Switchgear & MCC - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MR-0001 | BK-W007S-PEDCO-110-EL-MR-0001 | BK | W007S | PEDCO | 110 | EL | MR | 0001 | F0Z-708145 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 1 | 2 | 0 | 2.7.7.1.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 1 | 2 | 1 | 2.7.2.7.1.2.1 | BK-W007S-PEDCO-110-EL-TB-0001 | TBE For LV Switchgear & MCC - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-TB-0001 | BK-W007S-PEDCO-110-EL-TB-0001 | BK | W007S | PEDCO | 110 | EL | TB | 0001 | F0Z-708146 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 2 | 0 | 0 | 2.7.2.7.2 |  | UPS System
2 | 7 | 2 | 7 | 2 | 1 | 0 | 2.7.7.2.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 2 | 1 | 1 | 2.7.2.7.2.1.1 | BK-W007S-PEDCO-110-EL-MR-0002 | PMR For UPS System - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MR-0002 | BK-W007S-PEDCO-110-EL-MR-0002 | BK | W007S | PEDCO | 110 | EL | MR | 0002 | F0Z-708147 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 2 | 2 | 0 | 2.7.7.2.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 2 | 2 | 1 | 2.7.2.7.2.2.1 | BK-W007S-PEDCO-110-EL-TB-0002 | TBE For UPS System - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-TB-0002 | BK-W007S-PEDCO-110-EL-TB-0002 | BK | W007S | PEDCO | 110 | EL | TB | 0002 | F0Z-708148 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 3 | 0 | 0 | 2.7.2.7.3 |  | DC Charger
2 | 7 | 2 | 7 | 3 | 1 | 0 | 2.7.7.3.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 3 | 1 | 1 | 2.7.2.7.3.1.1 | BK-W007S-PEDCO-110-EL-MR-0003 | PMR For DC Charger - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MR-0003 | BK-W007S-PEDCO-110-EL-MR-0003 | BK | W007S | PEDCO | 110 | EL | MR | 0003 | F0Z-708149 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 3 | 2 | 0 | 2.7.7.3.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 3 | 2 | 1 | 2.7.2.7.3.2.1 | BK-W007S-PEDCO-110-EL-TB-0003 | TBE For DC Charger - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-TB-0003 | BK-W007S-PEDCO-110-EL-TB-0003 | BK | W007S | PEDCO | 110 | EL | TB | 0003 | F0Z-708150 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 4 | 0 | 0 | 2.7.2.7.4 |  | Earthing & Lightning System
2 | 7 | 2 | 7 | 4 | 1 | 0 | 2.7.7.4.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 4 | 1 | 1 | 2.7.2.7.4.1.1 | BK-W007S-PEDCO-110-EL-MR-0004 | PMR For Earthing & Lightning System - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MR-0004 | BK-W007S-PEDCO-110-EL-MR-0004 | BK | W007S | PEDCO | 110 | EL | MR | 0004 | F0Z-708151 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 4 | 2 | 0 | 2.7.7.4.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 4 | 2 | 1 | 2.7.2.7.4.2.1 | BK-W007S-PEDCO-110-EL-TB-0004 | TBE For Earthing & Lightning System - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-TB-0004 | BK-W007S-PEDCO-110-EL-TB-0004 | BK | W007S | PEDCO | 110 | EL | TB | 0004 | F0Z-708152 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 5 | 0 | 0 | 2.7.2.7.5 |  | Power & Control Cables
2 | 7 | 2 | 7 | 5 | 1 | 0 | 2.7.7.5.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 5 | 1 | 1 | 2.7.2.7.5.1.1 | BK-W007S-PEDCO-110-EL-MR-0005 | PMR For Power & Control Cables - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MR-0005 | BK-W007S-PEDCO-110-EL-MR-0005 | BK | W007S | PEDCO | 110 | EL | MR | 0005 | F0Z-708153 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 7 | 5 | 2 | 0 | 2.7.7.5.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 5 | 2 | 1 | 2.7.2.7.5.2.1 | BK-W007S-PEDCO-110-EL-TB-0005 | TBE For Power & Control Cables - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-TB-0005 | BK-W007S-PEDCO-110-EL-TB-0005 | BK | W007S | PEDCO | 110 | EL | TB | 0005 | F0Z-708154 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 7 | 6 | 0 | 0 | 2.7.2.7.6 |  | Tray/Ladder and Accessories | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 6 | 1 | 0 | 2.7.7.6.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 6 | 1 | 1 | 2.7.2.7.6.1.1 | BK-W007S-PEDCO-110-EL-MR-0006 | PMR For Tray/Ladder and Accessories - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MR-0006 | BK-W007S-PEDCO-110-EL-MR-0006 | BK | W007S | PEDCO | 110 | EL | MR | 0006 | F0Z-708155 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 7 | 6 | 2 | 0 | 2.7.7.6.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 6 | 2 | 1 | 2.7.2.7.6.2.1 | BK-W007S-PEDCO-110-EL-TB-0006 | TBE For Tray/Ladder and Accessories - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-TB-0006 | BK-W007S-PEDCO-110-EL-TB-0006 | BK | W007S | PEDCO | 110 | EL | TB | 0006 | F0Z-708156 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 7 | 7 | 0 | 0 | 2.7.2.7.7 |  | Electrical Bulk Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 7 | 1 | 0 | 2.7.7.7.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 7 | 1 | 1 | 2.7.2.7.7.1.1 | BK-W007S-PEDCO-110-EL-MR-0007 | PMR For Electrical Bulk Items - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-MR-0007 | BK-W007S-PEDCO-110-EL-MR-0007 | BK | W007S | PEDCO | 110 | EL | MR | 0007 | F0Z-708157 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 7 | 7 | 2 | 0 | 2.7.7.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 7 | 2 | 1 | 2.7.2.7.7.2.1 | BK-W007S-PEDCO-110-EL-TB-0007 | TBE For Electrical Bulk Items - Manifold & W007S |  | BK-W007S-PEDCO-110-EL-TB-0007 | BK-W007S-PEDCO-110-EL-TB-0007 | BK | W007S | PEDCO | 110 | EL | TB | 0007 | F0Z-708158 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 7 | 8 | 0 | 0 | 2.7.2.7.8 |  | Transformers | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 8 | 1 | 0 | 2.7.7.8.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 8 | 1 | 1 | 2.7.2.7.8.1.1 | BK-W007S-PEDCO-110-EL-MR-0008 | PMR For Transformers - W007S |  | BK-W007S-PEDCO-110-EL-MR-0008 | BK-W007S-PEDCO-110-EL-MR-0008 | BK | W007S | PEDCO | 110 | EL | MR | 0008 | F0Z-708159 | AFD | IFC | 2022-07-27 | 2022-08-03 | 2022-08-09 | 7 | 6 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-07-13 |  |  | D00 | IFC | T-1154 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05234 | 44767 | 1401/05/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-167059 | 44776 | 1401/05/12 | 44782 | 1401/05/18 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1154 | 2022-07-13 | 1401/04/22 |  |  |  | BK-SUR-ENG-ELE-01-05234 | 44767 | 1401/05/03 | CM-C3 | [6 empty] | 1401-2294-167059 | 2022-08-03 | 1401/05/12 | 44782 | 1401/05/18 | CM
2 | 7 | 2 | 7 | 8 | 2 | 0 | 2.7.7.8.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 8 | 2 | 1 | 2.7.2.7.8.2.1 | BK-W007S-PEDCO-110-EL-TB-0008 | TBE For Transformers - W007S |  | BK-W007S-PEDCO-110-EL-TB-0008 | BK-W007S-PEDCO-110-EL-TB-0008 | BK | W007S | PEDCO | 110 | EL | TB | 0008 | F0Z-708160 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 9 | 0 | 0 | 2.7.2.7.9 |  | Emergency Diesel Generator
2 | 7 | 2 | 7 | 9 | 1 | 0 | 2.7.7.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 9 | 1 | 1 | 2.7.2.7.9.1.1 | BK-W007S-PEDCO-110-EL-MR-0009 | PMR For Emergency Diesel Generator - W007S |  | BK-W007S-PEDCO-110-EL-MR-0009 | BK-W007S-PEDCO-110-EL-MR-0009 | BK | W007S | PEDCO | 110 | EL | MR | 0009 | F0Z-708161 | IFI | IFI | 2022-09-03 | 2022-09-08 | 2022-09-12 | 5 | 4 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-20 |  |  | D00 | IFI | T-1293 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216140 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1293 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | [6 empty] | 1401-2294-216140 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | AP
2 | 7 | 2 | 7 | 9 | 2 | 0 | 2.7.7.9.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 9 | 2 | 1 | 2.7.2.7.9.2.1 | BK-W007S-PEDCO-110-EL-TB-0009 | TBE For Emergency Diesel Generator - W007S |  | BK-W007S-PEDCO-110-EL-TB-0009 | BK-W007S-PEDCO-110-EL-TB-0009 | BK | W007S | PEDCO | 110 | EL | TB | 0009 | F0Z-708162 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 10 | 0 | 0 | 2.7.2.7.10 |  | Lighting & Distribution Main Panels
2 | 7 | 2 | 7 | 10 | 1 | 0 | 2.7.7.10.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 10 | 1 | 1 | 2.7.2.7.10.1.1 | BK-W007S-PEDCO-110-EL-MR-0010 | PMR For Lighting & Distribution Main Panels - W007S |  | BK-W007S-PEDCO-110-EL-MR-0010 | BK-W007S-PEDCO-110-EL-MR-0010 | BK | W007S | PEDCO | 110 | EL | MR | 0010 | F0Z-708163 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 7 | 10 | 2 | 0 | 2.7.7.10.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 10 | 2 | 1 | 2.7.2.7.10.2.1 | BK-W007S-PEDCO-110-EL-TB-0010 | TBE For Lighting & Distribution Main Panels - W007S |  | BK-W007S-PEDCO-110-EL-TB-0010 | BK-W007S-PEDCO-110-EL-TB-0010 | BK | W007S | PEDCO | 110 | EL | TB | 0010 | F0Z-708164 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 11 | 0 | 0 | 2.7.2.7.11 |  | Lighting and Small Power Equipment
2 | 7 | 2 | 7 | 11 | 1 | 0 | 2.7.7.11.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 11 | 1 | 1 | 2.7.2.7.11.1.1 | BK-W007S-PEDCO-110-EL-MR-0011 | PMR For Lighting and Small Power Equipment - W007S |  | BK-W007S-PEDCO-110-EL-MR-0011 | BK-W007S-PEDCO-110-EL-MR-0011 | BK | W007S | PEDCO | 110 | EL | MR | 0011 | F0Z-708165 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 11 | 2 | 0 | 2.7.7.11.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 11 | 2 | 1 | 2.7.2.7.11.2.1 | BK-W007S-PEDCO-110-EL-TB-0011 | TBE For Lighting and Small Power Equipment - W007S |  | BK-W007S-PEDCO-110-EL-TB-0011 | BK-W007S-PEDCO-110-EL-TB-0011 | BK | W007S | PEDCO | 110 | EL | TB | 0011 | F0Z-708166 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 12 | 0 | 0 | 2.7.2.7.12 |  | Capacitor Bank
2 | 7 | 2 | 7 | 12 | 1 | 0 | 2.7.7.12.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 12 | 1 | 1 | 2.7.2.7.12.1.1 | BK-W007S-PEDCO-110-EL-MR-0012 | PMR For Capacitor Bank - W007S |  | BK-W007S-PEDCO-110-EL-MR-0012 | BK-W007S-PEDCO-110-EL-MR-0012 | BK | W007S | PEDCO | 110 | EL | MR | 0012 | F0Z-708167 | IFI | IFI | 2022-08-13 | 2022-08-18 | 2022-08-20 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | T-1215 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183488 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1215 | 2022-07-30 | 1401/05/08 |  |  |  | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | [6 empty] | 1401-2294-183488 | 2022-08-18 | 1401/05/27 | 44793 | 1401/05/29 | RJ
2 | 7 | 2 | 7 | 12 | 2 | 0 | 2.7.7.12.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 12 | 2 | 1 | 2.7.2.7.12.2.1 | BK-W007S-PEDCO-110-EL-TB-0012 | TBE For Capacitor Bank - W007S |  | BK-W007S-PEDCO-110-EL-TB-0012 | BK-W007S-PEDCO-110-EL-TB-0012 | BK | W007S | PEDCO | 110 | EL | TB | 0012 | F0Z-708168 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 2 | 7 | 13 | 0 | 0 | 2.7.2.7.13 |  | Transmission Over Head Line Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 2 | 7 | 13 | 1 | 0 | 2.7.7.13.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 13 | 1 | 1 | 2.7.2.7.13.1.1 | BK-W007S-PEDCO-110-EL-MR-0013 | PMR For Transmission Over head Line Equipment - W007S |  | BK-W007S-PEDCO-110-EL-MR-0013 | BK-W007S-PEDCO-110-EL-MR-0013 | BK | W007S | PEDCO | 110 | EL | MR | 0013 | F0Z-708169 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 2 | 7 | 13 | 2 | 0 | 2.7.7.13.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 13 | 2 | 1 | 2.7.2.7.13.2.1 | BK-W007S-PEDCO-110-EL-TB-0013 | TBE For Transmission Over head Line Equipment - W007S |  | BK-W007S-PEDCO-110-EL-TB-0013 | BK-W007S-PEDCO-110-EL-TB-0013 | BK | W007S | PEDCO | 110 | EL | TB | 0013 | F0Z-708170 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 3 | 0 | 0 | 0 | 0 | 2.7.3 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 3 | 0 | 1 | 0 | 0 | 2.7.3.1 |  | Steel Structure Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 3 | 0 | 1 | 1 | 0 | 2.7.3.1.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 3 | 0 | 1 | 1 | 1 | 2.7.3.1.1.1 | BK-W007S-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - W007S/Manifold Extension |  | BK-W007S-PEDCO-110-ST-MR-0001 | BK-W007S-PEDCO-110-ST-MR-0001 | BK | W007S | PEDCO | 110 | ST | MR | 0001 | F0Z-708171 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 3 | 0 | 1 | 2 | 0 | 2.7.3.1.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 3 | 0 | 1 | 2 | 1 | 2.7.3.1.2.1 | BK-W007S-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - W007S/Manifold Extension |  | BK-W007S-PEDCO-110-ST-TB-0001 | BK-W007S-PEDCO-110-ST-TB-0001 | BK | W007S | PEDCO | 110 | ST | TB | 0001 | F0Z-708172 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 3 | 0 | 2 | 0 | 0 | 2.7.3.2 |  | Anchor Bolts
2 | 7 | 3 | 0 | 2 | 1 | 0 | 2.7.3.2.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 3 | 0 | 2 | 1 | 1 | 2.7.3.2.1.1 | BK-W007S-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - W007S/Manifold Extension |  | BK-W007S-PEDCO-110-ST-MR-0002 | BK-W007S-PEDCO-110-ST-MR-0002 | BK | W007S | PEDCO | 110 | ST | MR | 0002 | F0Z-708173 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 3 | 0 | 2 | 2 | 0 | 2.7.3.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 3 | 0 | 2 | 2 | 1 | 2.7.3.2.2.1 | BK-W007S-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - W007S/Manifold Extension |  | BK-W007S-PEDCO-110-ST-TB-0002 | BK-W007S-PEDCO-110-ST-TB-0002 | BK | W007S | PEDCO | 110 | ST | TB | 0002 | F0Z-708174 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 3 | 0 | 3 | 0 | 0 | 2.7.3.3 |  | Blast Proof Doors | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 3 | 0 | 3 | 1 | 0 | 2.7.3.3.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 3 | 0 | 3 | 1 | 1 | 2.7.3.3.1.1 | BK-W007S-PEDCO-110-ST-MR-0003 | PMR For Blast Proof Doors - W007S/Manifold Extension |  | BK-W007S-PEDCO-110-ST-MR-0003 | BK-W007S-PEDCO-110-ST-MR-0003 | BK | W007S | PEDCO | 110 | ST | MR | 0003 | F0Z-708175 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 3 | 0 | 3 | 2 | 0 | 2.7.3.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 3 | 0 | 3 | 2 | 1 | 2.7.3.3.2.1 | BK-W007S-PEDCO-110-ST-TB-0003 | TBE For Blast Proof Doors - W007S/Manifold Extension |  | BK-W007S-PEDCO-110-ST-TB-0003 | BK-W007S-PEDCO-110-ST-TB-0003 | BK | W007S | PEDCO | 110 | ST | TB | 0003 | F0Z-708176 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 4 | 0 | 0 | 0 | 0 | 2.7.4 |  | Civil | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 4 | 0 | 1 | 0 | 0 | 2.7.4.1 |  | Geomembrane
2 | 7 | 4 | 0 | 1 | 1 | 0 | 2.7.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 4 | 0 | 1 | 1 | 1 | 2.7.4.1.1.1 | BK-W007S-PEDCO-110-CV-MR-0001 | PMR For Geomembrane - W007S |  | BK-W007S-PEDCO-110-CV-MR-0001 | BK-W007S-PEDCO-110-CV-MR-0001 | BK | W007S | PEDCO | 110 | CV | MR | 0001 | F0Z-708177 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 4 | 0 | 1 | 2 | 0 | 2.7.4.1.2 |  | Technical Bid Evaluation (TBE)
2 | 7 | 4 | 0 | 1 | 2 | 1 | 2.7.4.1.2.1 | BK-W007S-PEDCO-110-CV-TB-0001 | TBE For Geomembrane - W007S |  | BK-W007S-PEDCO-110-CV-TB-0001 | BK-W007S-PEDCO-110-CV-TB-0001 | BK | W007S | PEDCO | 110 | CV | TB | 0001 | F0Z-708178 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 4 | 0 | 2 | 0 | 0 | 2.7.4.2 |  | Geotextile
2 | 7 | 4 | 0 | 2 | 1 | 0 | 2.7.4.2.1 |  | Purchase Material Requisition (PMR)
2 | 7 | 4 | 0 | 2 | 1 | 1 | 2.7.4.2.1.1 | BK-W007S-PEDCO-110-CV-MR-0002 | PMR For Geotextile - W007S |  | BK-W007S-PEDCO-110-CV-MR-0002 | BK-W007S-PEDCO-110-CV-MR-0002 | BK | W007S | PEDCO | 110 | CV | MR | 0002 | F0Z-708179 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 4 | 0 | 2 | 2 | 0 | 2.7.4.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 4 | 0 | 2 | 2 | 1 | 2.7.4.2.2.1 | BK-W007S-PEDCO-110-CV-TB-0002 | TBE For Geotextile - W007S |  | BK-W007S-PEDCO-110-CV-TB-0002 | BK-W007S-PEDCO-110-CV-TB-0002 | BK | W007S | PEDCO | 110 | CV | TB | 0002 | F0Z-708180 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 5 | 0 | 0 | 0 | 0 | 2.7.5 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 5 | 0 | 0 | 1 | 0 | 2.7.5.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 5 | 0 | 0 | 1 | 1 | 2.7.5.1.1 | BK-W007S-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - Manifold & W007S |  | BK-W007S-PEDCO-110-CO-PR-0001 | BK-W007S-PEDCO-110-CO-PR-0001 | BK | W007S | PEDCO | 110 | CO | PR | 0001 | F0Z-708181 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 6 | 0 | 0 | 0 | 0 | 2.7.6 |  | Field Engineering
2 | 7 | 6 | 0 | 0 | 1 | 0 | 2.7.6.1 |  | Query
2 | 7 | 6 | 0 | 0 | 1 | 1 | 2.7.6.1.1 | BK-W007S-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-W007S-PEDCO-110-GE-TQ-0001 | BK-W007S-PEDCO-110-GE-TQ-0001 | BK | W007S | PEDCO | 110 | GE | TQ | 0001 | F7Z-708182 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 6 | 0 | 0 | 2 | 0 | 2.7.6.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 6 | 0 | 0 | 2 | 1 | 2.7.6.2.1 | BK-W007S-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - Manifold & W007S |  | BK-W007S-PEDCO-110-GE-DO-0001 | BK-W007S-PEDCO-110-GE-DO-0001 | BK | W007S | PEDCO | 110 | GE | DO | 0001 | F0Z-708183 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 7 | 0 | 0 | 0 | 0 | 2.7.7 |  | Engineering Final Documentation
2 | 7 | 7 | 0 | 0 | 1 | 0 | 2.7.7.1 |  | Manual | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 7 | 7 | 0 | 0 | 1 | 1 | 2.7.7.1.1 | BK-W007S-PEDCO-110-GE-ML-0001 | Operating Manual - Manifold & W007S |  | BK-W007S-PEDCO-110-GE-ML-0001 | BK-W007S-PEDCO-110-GE-ML-0001 | BK | W007S | PEDCO | 110 | GE | ML | 0001 | F0Z-708184 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 7 | 7 | 0 | 0 | 2 | 0 | 2.7.7.2 |  | Dossier
2 | 7 | 7 | 0 | 0 | 2 | 1 | 2.7.7.2.1 | BK-W007S-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - Manifold & W007S |  | BK-W007S-PEDCO-110-GE-DO-0001 | [10 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 7 | 7 | 0 | 0 | 2 | 2 | 2.7.7.2.2 | BK-W007S-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - Manifold & W007S |  | BK-W007S-PEDCO-110-GE-DO-0002 | BK-W007S-PEDCO-110-GE-DO-0002 | BK | W007S | PEDCO | 110 | GE | DO | 0002 | F0Z-708185 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 0 | 0 | 0 | 0 | 0 | 2.8 |  | Package 07-Workover # 14 | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 0 | 0 | 0 | 0 | 2.8.1 |  | Detail Design
2 | 8 | 1 | 1 | 0 | 0 | 0 | 2.8.1.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 1 | 1 | 0 | 0 | 2.8.1.1.1 |  | Drawing/Diagram
2 | 8 | 1 | 1 | 1 | 0 | 1 | 2.8.1.1.1 | BK-BK14-PEDCO-110-PR-PI-0001 | P&ID for Diesel Oil Drum- BK14 |  | BK-BK14-PEDCO-110-PR-PI-0001 | [8 empty] | F2A-708186 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-06 | 2022-02-08 | 20 | 2 | 22 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-05-12 | 2022-05-16 | 18 | 4 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-15 |  |  | D03 | IFA | T-0795 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-399153 | 44598 | 1400/11/17 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0648 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 44635 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0795 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D02
2 | 8 | 1 | 1 | 1 | 0 | 2 | 2.8.1.1.1 | BK-BK14-PEDCO-110-PR-PI-0002 | P&ID for Potable Water Tank - BK14 |  | BK-BK14-PEDCO-110-PR-PI-0002 | [8 empty] | F2A-708187 | AFC | [50 empty] | 2021-11-15 |  |  | D03 | IFA | T-0795 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-399153 | 44598 | 1400/11/17 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0648 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 44635 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0795 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D02
2 | 8 | 1 | 1 | 2 | 0 | 0 | 2.8.1.1.2 |  | List
2 | 8 | 1 | 1 | 2 | 0 | 1 | 2.8.1.1.2 | BK-BK14-PEDCO-110-PR-LI-0001 | Line List - BK14 |  | BK-BK14-PEDCO-110-PR-LI-0001 | [8 empty] | F0Z-708188 | AFC | IFC | 2022-03-13 | 2022-03-12 | 2022-03-15 | -1 | 3 | 2 | IFA | 2022-05-14 | 2022-05-31 | 2022-05-06 | 17 | -25 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-27 |  |  | D01 | IFA | T-0877 | 44681 | 1401/02/10 | T-0877 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-83257 | 44712 | 1401/03/10 | 44687 | 1401/03/16 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0650 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03597 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445283 | 2022-03-12 | 1400/12/21 | 44635 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0877 | 44681 | 1401/02/10 | T-0877 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1401-2294-83257 | 44712 | 1401/03/10 | 44687 | 1401/03/16 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-LI-0001_D00
2 | 8 | 1 | 1 | 3 | 0 | 0 | 2.8.1.1.3 |  | Data Sheet | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 1 | 3 | 0 | 1 | 2.8.1.1 | BK-BK14-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - BK14 |  | BK-BK14-PEDCO-110-PR-DT-0001 | [8 empty] | F0Z-708189 | AFC | IFC | 2022-04-26 | 2022-05-14 | 2022-05-16 | 18 | 2 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-12 |  |  | D00 | IFC | T-0807 | 44663 | 1401/01/12 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03991 | 44670 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52773 | 44695 | 1401/02/24 | 44697 | 1401/02/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 44670 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 44697 | 1401/02/26 | AP
2 | 8 | 1 | 2 | 0 | 0 | 0 | 2.8.1.2 |  | HVAC/Plumbing | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 2 | 1 | 0 | 0 | 2.8.1.2.1 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 2 | 1 | 0 | 1 | 2.8.1.2.1 | BK-BK14-PEDCO-110-HV-CN-0001 | HVAC Calculation Note For Switchgear Building - BK14 |  | BK-BK14-PEDCO-110-HV-CN-0001 | BK-BK14-PEDCO-110-HV-CN-0001 | BK | BK14 | PEDCO | 110 | HV | CN | 0001 | F0Z-708190 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 2 | 1 | 0 | 2 | 2.8.1.2.1 | BK-BK14-PEDCO-110-HV-CN-0002 | HVAC Calculation Note For Security Building - BK14 |  | BK-BK14-PEDCO-110-HV-CN-0002 | BK-BK14-PEDCO-110-HV-CN-0002 | BK | BK14 | PEDCO | 110 | HV | CN | 0002 | F0Z-708191 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 2 | 2 | 0 | 0 | 2.8.1.2.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 2 | 2 | 0 | 1 | 2.8.1.2.2 | BK-BK14-PEDCO-110-HV-DT-0001 | Data Sheets For Main HVAC Equipment - BK14 |  | BK-BK14-PEDCO-110-HV-DT-0001 | BK-BK14-PEDCO-110-HV-DT-0001 | BK | BK14 | PEDCO | 110 | HV | DT | 0001 | F0Z-708192 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 2 | 3 | 0 | 0 | 2.8.1.2.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 2 | 3 | 0 | 1 | 2.8.1.2.3 | BK-BK14-PEDCO-110-HV-PY-0001 | HVAC System Layout For Switchgear Building - BK14 |  | BK-BK14-PEDCO-110-HV-PY-0001 | BK-BK14-PEDCO-110-HV-PY-0001 | BK | BK14 | PEDCO | 110 | HV | PY | 0001 | F4B-708193 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 2 | 3 | 0 | 2 | 2.8.1.2.3 | BK-BK14-PEDCO-110-HV-PY-0002 | HVAC System Layout For Security Building - BK14 |  | BK-BK14-PEDCO-110-HV-PY-0002 | BK-BK14-PEDCO-110-HV-PY-0002 | BK | BK14 | PEDCO | 110 | HV | PY | 0002 | F4B-708194 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 2 | 3 | 0 | 3 | 2.8.1.2.3 | BK-BK14-PEDCO-110-HV-PY-0003 | Plumbing & Sewage Piping Layout For Switchgear Building - BK14 |  | BK-BK14-PEDCO-110-HV-PY-0003 | BK-BK14-PEDCO-110-HV-PY-0003 | BK | BK14 | PEDCO | 110 | HV | PY | 0003 | F4B-708195 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 2 | 3 | 0 | 4 | 2.8.1.2.3 | BK-BK14-PEDCO-110-HV-PY-0004 | Plumbing & Sewage Piping Layout For Security Building - BK14 |  | BK-BK14-PEDCO-110-HV-PY-0004 | BK-BK14-PEDCO-110-HV-PY-0004 | BK | BK14 | PEDCO | 110 | HV | PY | 0004 | F4B-708196 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 2 | 4 | 0 | 0 | 2.8.1.2.4 |  | MTO
2 | 8 | 1 | 2 | 4 | 0 | 1 | 2.8.1.2 | BK-BK14-PEDCO-110-HV-MT-0001 | MTO For Building HVAC & Plumbing Systems - BK14 |  | BK-BK14-PEDCO-110-HV-MT-0001 | BK-BK14-PEDCO-110-HV-MT-0001 | BK | BK14 | PEDCO | 110 | HV | MT | 0001 | F8Z-708197 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 3 | 0 | 0 | 0 | 2.8.1.3 |  | Piping
2 | 8 | 1 | 3 | 1 | 0 | 0 | 2.8.1.3.1 |  | Drawing/Diagram
2 | 8 | 1 | 3 | 1 | 0 | 1 | 2.8.1.3 | BK-BK14-PEDCO-110-PI-MT-0001 | Plot Plan Drawing – BK14 |  | BK-BK14-PEDCO-110-PI- PY -0001 | BK-BK14-PEDCO-110-PI-MT-0001 | BK | BK14 | PEDCO | 110 | PI | MT | 0001 | F8Z-708198 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14
2 | 8 | 1 | 3 | 1 | 0 | 0 | 2.8.1.3.1 |  | MTO
2 | 8 | 1 | 3 | 1 | 0 | 1 | 2.8.1.3 | BK-BK14-PEDCO-110-PI-MT-0001 | MTO For Pipes - BK14 |  | BK-BK14-PEDCO-110-PI-MT-0001 | BK-BK14-PEDCO-110-PI-MT-0001 | BK | BK14 | PEDCO | 110 | PI | MT | 0001 | F8Z-708198 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFI | T-1545 | 44859 | 1401/08/03 | T-1545 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1545 | 2022-10-25 | 1401/08/03 | T-1545 | 44859 | 1401/08/03
2 | 8 | 1 | 4 | 0 | 0 | 0 | 2.8.1.4 |  | Electrical
2 | 8 | 1 | 4 | 1 | 0 | 0 | 2.8.1.4.1 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 4 | 1 | 0 | 1 | 2.8.1.4 | BK-BK14-PEDCO-110-EL-MT-0001 | MTO For Transmission Over Head Line - BK14 |  | BK-BK14-PEDCO-110-EL-MT-0001 | BK-BK14-PEDCO-110-EL-MT-0001 | BK | BK14 | PEDCO | 110 | EL | MT | 0001 | F8Z-708199 | IFI | IFI | 2022-09-28 | 2022-10-05 | 2022-10-08 | 7 | 3 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-14 |  |  | D00 | IFI | T-1403 | 44818 | 1401/06/23 | T-1403 | 44818 | 1401/06/23 | BK-SUR-ENG-ELE-01-05771 | 44832 | 1401/07/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249368 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1403 | 2022-09-14 | 1401/06/23 | T-1403 | 44818 | 1401/06/23 | BK-SUR-ENG-ELE-01-05771 | 44832 | 1401/07/06 | CM-C2 | [6 empty] | 1401-2294-249368 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 8 | 1 | 4 | 1 | 0 | 2 | 2.8.1.4 | BK-BK14-PEDCO-110-EL-MT-0002 | MTO For Lighting & Small Powers - BK14 |  | BK-BK14-PEDCO-110-EL-MT-0002 | BK-BK14-PEDCO-110-EL-MT-0002 | BK | BK14 | PEDCO | 110 | EL | MT | 0002 | F8Z-708200 | IFI | IFI | 2022-06-01 | 2022-06-10 | 2022-06-12 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-18 |  |  | D00 | IFI | T-0969 | 44699 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94633 | 44722 | 1401/03/20 | 44724 | 1401/03/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | [6 empty] | 1401-2294-94633 | 2022-06-10 | 1401/03/20 | 44724 | 1401/03/22 | CM
2 | 8 | 1 | 4 | 1 | 0 | 3 | 2.8.1.4 | BK-BK14-PEDCO-110-EL-MT-0003 | MTO For Power & Control Cables - BK14 |  | BK-BK14-PEDCO-110-EL-MT-0003 | BK-BK14-PEDCO-110-EL-MT-0003 | BK | BK14 | PEDCO | 110 | EL | MT | 0003 | F8Z-708201 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 4 | 1 | 0 | 4 | 2.8.1.4 | BK-BK14-PEDCO-110-EL-MT-0004 | MTO For Tray/Ladder and Accessories - BK14 |  | BK-BK14-PEDCO-110-EL-MT-0004 | BK-BK14-PEDCO-110-EL-MT-0004 | BK | BK14 | PEDCO | 110 | EL | MT | 0004 | F8Z-708202 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 4 | 1 | 0 | 5 | 2.8.1.4 | BK-BK14-PEDCO-110-EL-MT-0005 | MTO For Electrical Bulk Items - BK14 |  | BK-BK14-PEDCO-110-EL-MT-0005 | BK-BK14-PEDCO-110-EL-MT-0005 | BK | BK14 | PEDCO | 110 | EL | MT | 0005 | F8Z-708203 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 4 | 1 | 0 | 6 | 2.8.1.4 | BK-BK14-PEDCO-110-EL-MT-0006 | MTO For Earthing & Lightning Systems - BK14 |  | BK-BK14-PEDCO-110-EL-MT-0006 | BK-BK14-PEDCO-110-EL-MT-0006 | BK | BK14 | PEDCO | 110 | EL | MT | 0006 | F8Z-708204 | IFI | IFI | 2022-10-25 | 2022-11-10 | 2022-11-14 | 16 | 4 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-11 |  |  | D00 | IFI | T-1480 | 44845 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-304880 | 44875 | 1401/08/19 | 44879 | 1401/08/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1480 | 2022-10-11 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | [6 empty] | 1401-2294-304880 | 2022-11-10 | 1401/08/19 | 44879 | 1401/08/23 | CM
2 | 8 | 1 | 5 | 0 | 0 | 0 | 2.8.1.5 |  | Architecture | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 5 | 1 | 0 | 0 | 2.8.1.5.1 |  | Drawing/Diagram
2 | 8 | 1 | 5 | 1 | 0 | 1 | 2.8.1.5.1 | BK-BK14-PEDCO-110-AR-DW-0001 | Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-14 |  | BK-BK14-PEDCO-110-AR-DW-0001 | BK-BK14-PEDCO-110-AR-DW-0001 | BK | BK14 | PEDCO | 110 | AR | DW | 0001 | F4B-708205 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-01 |  |  | D00 | IFC | T-0885 | 44682 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 44697 | 1401/02/26 | CM
2 | 8 | 1 | 5 | 1 | 0 | 2 | 2.8.1.5.1 | BK-BK14-PEDCO-110-AR-DW-0002 | Architectural Drawing For Switchgear Building of Well Pads - BK-14 |  | BK-BK14-PEDCO-110-AR-DW-0002 | BK-BK14-PEDCO-110-AR-DW-0002 | BK | BK14 | PEDCO | 110 | AR | DW | 0002 | F4B-708206 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 2022-05-31 | 2022-06-07 | -1 | 7 | 6 | IFC | 2022-09-21 | 2022-10-11 | 2022-10-17 | 20 | 6 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-09-07 |  |  | D02 | IFC | T-1370 | 44811 | 1401/06/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ARC-00-03551 | 44634 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 44645 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 44699 | 1401/02/28 | T-0974 | 44702 | 1401/02/31 | BK-SUR-ENG-ARC-01-04416 | 44705 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D00 | [5 empty] | 1401-2294-85268 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | RJ | NISOC-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D00 | [9 empty] | D02 | IFC | T-1370 | 44811 | 1401/06/16 | [7 empty] | PEDCO-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D01 | [5 empty] | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D01
2 | 8 | 1 | 5 | 1 | 0 | 3 | 2.8.1.5.1 | BK-BK14-PEDCO-110-AR-DW-0003 | Architectural Drawing For Security Building of Well Pads - BK-14 |  | BK-BK14-PEDCO-110-AR-DW-0003 | BK-BK14-PEDCO-110-AR-DW-0003 | BK | BK14 | PEDCO | 110 | AR | DW | 0003 | F4B-708207 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-01 |  |  | D00 | IFC | T-0886 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 44695 | 1401/02/21 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 44697 | 1401/02/26 | CM
2 | 8 | 1 | 5 | 2 | 0 | 0 | 2.8.1.5.2 |  | MTO
2 | 8 | 1 | 5 | 2 | 0 | 1 | 2.8.1.5 | BK-BK14-PEDCO-110-AR-MT-0001 | MTO For Architectural Works - BK14 |  | BK-BK14-PEDCO-110-AR-MT-0001 | BK-BK14-PEDCO-110-AR-MT-0001 | BK | BK14 | PEDCO | 110 | AR | MT | 0001 | F8Z-708208 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 6 | 0 | 0 | 0 | 2.8.1.6 |  | Civil
2 | 8 | 1 | 6 | 1 | 0 | 0 | 2.8.1.6.1 |  | Drawing/Diagram
2 | 8 | 1 | 6 | 1 | 0 | 1 | 2.8.1.6.1 | BK-BK14-PEDCO-110-CV-DW-0001 | Civil and Structural drawings - BK14 |  | BK-BK14-PEDCO-110-CV-DW-0001 | BK-BK14-PEDCO-110-CV-DW-0001 | BK | BK14 | PEDCO | 110 | CV | DW | 0001 | F4S-708209 | AFC | IFC | 2022-11-01 | 2022-11-05 | 2022-11-06 | 4 | 1 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-18 |  |  | D00 | IFC | T-1511 | 44852 | 1401/07/26 | T-1511 | 44852 | 1401/07/26 | BK-SUR-ENG-CIV-01-06036 | 44865 | 1401/08/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296566 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1511 | 2022-10-18 | 1401/07/26 | T-1511 | 44852 | 1401/07/26 | BK-SUR-ENG-CIV-01-06036 | 44865 | 1401/08/09 | CM-C2 | [6 empty] | 1401-2294-296566 | 2022-11-05 | 1401/08/14 | 44871 | 1401/08/15 | CM
2 | 8 | 1 | 6 | 1 | 0 | 2 | 2.8.1.6.1 | BK-BK14-PEDCO-110-CV-PY-0001 | General Civil Layout - BK14 |  | BK-BK14-PEDCO-110-CV-PY-0001 | BK-BK14-PEDCO-110-CV-PY-0001 | BK | BK14 | PEDCO | 110 | CV | PY | 0001 | F4A-708210 | AFC | IFC | 2022-10-03 | 2022-09-26 | 2022-10-02 | -7 | 6 | -1 | IFA | 2022-10-25 | 2022-10-29 | 2022-10-30 | 4 | 1 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-19 |  |  | D01 | IFA | T-1479 | 44845 | 1401/07/19 | T-1479 | 44845 | 1401/07/19 | BK-SUR-ENG-CIV-01-05939 | 44856 | 1401/07/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284599 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | RJ | NISOC-CRS-BK-BK14-PEDCO-110-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1413 | 2022-09-19 | 1401/06/28 | T-1413 | 44823 | 1401/06/28 | BK-SUR-ENG-CIV-01-05774 | 44832 | 1401/07/06 | CM-C3 | [6 empty] | 1401-2294-238123 | 2022-09-26 | 1401/07/04 | 44836 | 1401/07/10 | CM | [10 empty] | D01 | IFA | T-1479 | 44845 | 1401/07/19 | T-1479 | 44845 | 1401/07/19 | BK-SUR-ENG-CIV-01-05939 | 44856 | 1401/07/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-CV-PY-0001_D01 | [5 empty] | 1401-2294-284599 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | RJ | NISOC-CRS-BK-BK14-PEDCO-110-CV-PY-0001_D01
2 | 8 | 1 | 6 | 1 | 0 | 3 | 2.8.1.6.1 | BK-BK14-PEDCO-110-CV-PY-0003 | Rough Grading Plans -BK14 |  | BK-BK14-PEDCO-110-CV-PY-0003 | BK-BK14-PEDCO-110-CV-PY-0003 | BK | BK14 | PEDCO | 110 | CV | PY | 0003 | F4S-708211 | AFC | IFC | 2022-10-29 | 2022-11-05 | 2022-11-06 | 7 | 1 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFC | T-1497 | 44849 | 1401/07/09 | T-1497 | 44849 | 1401/07/09 | BK-SUR-ENG-CIV-01-05950 | 44856 | 1401/07/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296585 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1497 | 2022-10-15 | 1401/07/09 | T-1497 | 44849 | 1401/07/09 | BK-SUR-ENG-CIV-01-05950 | 44856 | 1401/07/30 | CM-C2 | [6 empty] | 1401-2294-296585 | 2022-11-05 | 1401/08/14 | 44871 | 1401/08/15 | RJ
2 | 8 | 1 | 6 | 2 | 0 | 0 | 2.8.1.6.2 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 6 | 2 | 0 | 1 | 2.8.1.6.2 | BK-BK14-PEDCO-110-CV-RT-0001 | Site Visit Report (Civil Work) - BK14 |  | BK-BK14-PEDCO-110-CV-RT-0001 | BK-BK14-PEDCO-110-CV-RT-0001 | BK | BK14 | PEDCO | 110 | CV | RT | 0001 | F0Z-708212 | IFI | IFC | 2021-11-23 | 2021-11-14 | 2021-11-17 | -9 | 3 | -6 | IFA | 2022-03-07 | 2022-02-26 | 2022-02-28 | -9 | 2 | -7 | IFA | 2022-07-11 | 2022-07-04 | 2022-07-05 | -7 | 1 | -6 | IFA | 2022-09-19 | 2022-09-21 | 2022-09-24 | 2 | 3 | 5 | AFC | 2022-10-23 | 0 | 0 | -44857 | 0 | -44857 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-09 | 2022-10-09 |  | D04 | AFC | T-1472 | 44843 | 1401/07/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05865 | 44843 | 1401/07/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0223 | 2021-11-09 | 1400/08/17 |  |  |  | BK-SUR-ENG-CIV-00-02031 | 44517 | 1400/08/26 | CM-C2 | [6 empty] | 1400-2294-275272 | 2021-11-14 | 1400/08/23 | 44517 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0621 | 44613 | 1400/12/02 | [13 empty] | 1400-2294-426672 | 44618 | 1400/12/07 | 44620 | 1400/12/09 | cm | [10 empty] | D02 | IFA | T-1120 | 44739 | 1401/04/06 |  |  |  | BK-SUR-ENG-CIV-01-05019 | 44748 | 1401/04/15 | CM | [6 empty] | 1401-2294-129450 | 44746 | 1401/04/13 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-BK14-PEDCO-110-CV-RT-0001-D01 | [9 empty] | D03 | IFA | T-1367 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-CIV-01-05703 | 44818 | 1401/06/23 | AP | PEDCO-CRS-BK-BK14-PEDCO-110-CV-RT-0001_D02 | [5 empty] | 1401-2294-232017 | 44825 | 1401/06/30 | 44828 | 1401/07/02 | AP | NISOC-CRS-BK-BK14-PEDCO-110-CV-RT-0001_D02 | [9 empty] | D04 | AFC | T-1472 | 44843 | 1401/07/17 |  |  |  | BK-SUR-ENG-CIV-01-05865 | 44843 | 1401/07/17 | AP
2 | 8 | 1 | 6 | 3 | 0 | 0 | 2.8.1.6.3 |  | MTO
2 | 8 | 1 | 6 | 3 | 0 | 1 | 2.8.1.6 | BK-BK14-PEDCO-110-CV-MT-0001 | MTO For Civil Works - BK14 |  | BK-BK14-PEDCO-110-CV-MT-0001 | BK-BK14-PEDCO-110-CV-MT-0001 | BK | BK14 | PEDCO | 110 | CV | MT | 0001 | F8Z-708213 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 7 | 0 | 0 | 0 | 2.8.1.7 |  | Structure
2 | 8 | 1 | 7 | 1 | 0 | 0 | 2.8.1.7.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 7 | 1 | 0 | 1 | 2.8.1.7.1 | BK-BK14-PEDCO-110-ST-DW-0001 | Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-14 |  | BK-BK14-PEDCO-110-ST-DW-0001 | BK-BK14-PEDCO-110-ST-DW-0001 | BK | BK14 | PEDCO | 110 | ST | DW | 0001 | F4G-708214 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 7 | 1 | 0 | 2 | 2.8.1.7.1 | BK-BK14-PEDCO-110-ST-DW-0002 | Foundation Drawing For Security Building For Well Pads - BK-14 |  | BK-BK14-PEDCO-110-ST-DW-0002 | BK-BK14-PEDCO-110-ST-DW-0002 | BK | BK14 | PEDCO | 110 | ST | DW | 0002 | F4Q-708215 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 7 | 1 | 0 | 3 | 2.8.1.7.1 | BK-BK14-PEDCO-110-ST-DW-0003 | Structural Drawing For Security Building For Well Pads - BK-14 |  | BK-BK14-PEDCO-110-ST-DW-0003 | BK-BK14-PEDCO-110-ST-DW-0003 | BK | BK14 | PEDCO | 110 | ST | DW | 0003 | F4M-708216 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 7 | 1 | 0 | 4 | 2.8.1.7.1 | BK-BK14-PEDCO-110-ST-DW-0004 | Foundation Drawing For Switchgear Building For Well Pads - BK-14 |  | BK-BK14-PEDCO-110-ST-DW-0004 | BK-BK14-PEDCO-110-ST-DW-0004 | BK | BK14 | PEDCO | 110 | ST | DW | 0004 | F4Q-708217 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 7 | 1 | 0 | 5 | 2.8.1.7.1 | BK-BK14-PEDCO-110-ST-DW-0005 | Structural Drawing For Switchgear Building For Well Pads - BK-14 |  | BK-BK14-PEDCO-110-ST-DW-0005 | BK-BK14-PEDCO-110-ST-DW-0005 | BK | BK14 | PEDCO | 110 | ST | DW | 0005 | F4M-708218 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 7 | 1 | 0 | 6 | 2.8.1.7.1 | BK-BK14-PEDCO-110-ST-DW-0006 | Foundation Drawing For Potable Water Tank For Well Pads - BK-14 |  | BK-BK14-PEDCO-110-ST-DW-0006 | BK-BK14-PEDCO-110-ST-DW-0006 | BK | BK14 | PEDCO | 110 | ST | DW | 0006 | F4Q-708219 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 7 | 1 | 0 | 7 | 2.8.1.7.1 | BK-BK14-PEDCO-110-ST-DW-0007 | Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-14 |  | BK-BK14-PEDCO-110-ST-DW-0007 | BK-BK14-PEDCO-110-ST-DW-0007 | BK | BK14 | PEDCO | 110 | ST | DW | 0007 | F4Q-708220 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 1 | 7 | 1 | 0 | 8 | 2.8.1.7.1 | BK-BK14-PEDCO-110-ST-DW-0008 | Structural Drawing For Diesel Generator Shelter For Well Pads - BK-14 |  | BK-BK14-PEDCO-110-ST-DW-0008 | BK-BK14-PEDCO-110-ST-DW-0008 | BK | BK14 | PEDCO | 110 | ST | DW | 0008 | F4M-708221 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 7 | 2 | 0 | 0 | 2.8.1.7.2 |  | MTO
2 | 8 | 1 | 7 | 2 | 0 | 1 | 2.8.1.7 | BK-BK14-PEDCO-110-ST-MT-0001 | MTO For Structural Works - BK14 |  | BK-BK14-PEDCO-110-ST-MT-0001 | BK-BK14-PEDCO-110-ST-MT-0001 | BK | BK14 | PEDCO | 110 | ST | MT | 0001 | F8Z-708222 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 1 | 8 | 0 | 0 | 0 | 2.8.1.8 |  | Survey (Topography) & Geotechnic
2 | 8 | 1 | 8 | 1 | 0 | 0 | 2.8.1.8.1 |  | Geotechnic
2 | 8 | 1 | 8 | 2 | 0 | 0 | 2.8.1.8.2 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 8 | 2 | 0 | 1 | 2.8.1.8.2 | BK-BK14-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - BK14 |  | BK-BK14-PEDCO-110-GT-RT-0001 | BK-BK14-PEDCO-110-GT-RT-0001 | BK | BK14 | PEDCO | 110 | GT | RT | 0001 | F0Z-708223 | IFI | IFC | 2022-06-29 | 2022-06-25 | 2022-06-25 | -4 | 0 | -4 | IFA | 2022-11-19 | 0 | 0 | -44884 | 0 | -44884 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-15 |  |  | D01 | IFA | T-1572 | 44870 | 1401/08/14 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-06081 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK14-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1081 | 2022-06-15 | 1401/03/25 |  |  |  | BK-SUR-ENG-CIV-01-04721 | 44727 | 1401/03/25 | RJ-C4 |  | BK-SUR-ENG-CIV-01-04901 | 44738 | 1401/04/06 | CM-C3 |  | 1401-2294-123165 | 2022-06-25 | 1401/04/08 | 44737 | 1401/04/08 | CM | [10 empty] | D01 | IFA | T-1572 | 44870 | 1401/08/14 |  |  |  | BK-SUR-ENG-CIV-01-06081 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-GT-RT-0001_D00 | [11 empty] | NISOC-CRS-BK-BK14-PEDCO-110-GT-RT-0001_D00
2 | 8 | 1 | 8 | 3 | 0 | 0 | 2.8.1.8.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 1 | 8 | 3 | 0 | 1 | 2.8.1 | BK-BK14-PEDCO-110-SU-DW-0001 | Over Head Line Plan and Profile - BK14 |  | BK-BK14-PEDCO-110-SU-DW-0001 | BK-BK14-PEDCO-110-SU-DW-0001 | BK | BK14 | PEDCO | 110 | SU | DW | 0001 | F4P-708224 | AFC | IFC | 2022-03-07 | 2022-03-10 | 2022-03-12 | 3 | 2 | 5 | IFA | 2022-04-25 | 2022-07-19 | 2022-07-24 | 85 | 5 | 90 | IFA | 2022-09-18 | 2022-09-19 | 2022-09-20 | 1 | 1 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-21 |  |  | D02 | IFA | T-1354 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05691 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-229302 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0616 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-ENG-ELE-00-03237 | 44619 | 1400/12/08 | CM-C3 | [6 empty] | 1400-2294-443158 | 2022-03-10 | 1400/12/10 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0802 | 44662 | 1401/01/22 |  |  |  | BK-SUR-ENG-ELE-01-04010 | 44675 | 1401/01/04 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D00 | [5 empty] | 1401-2294-144181 | 44761 | 1401/04/27 | 44766 | 1401/05/02 | CM | NISOC-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D00 | [9 empty] | D02 | IFA | T-1354 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-ELE-01-05691 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D01 | [5 empty] | 1401-2294-229302 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D01
2 | 8 | 2 | 0 | 0 | 0 | 0 | 2.8.2 |  | Procurement Engineering
2 | 8 | 2 | 1 | 0 | 0 | 0 | 2.8.2.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 1 | 1 | 0 | 0 | 2.8.2.1.1 |  | Pipe
2 | 8 | 2 | 1 | 1 | 1 | 0 | 2.8.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 1 | 1 | 1 | 1 | 2.8.2.1.1.1.1 | BK-BK14-PEDCO-110-PI-MR-0001 | PMR For Pipes - BK14 |  | BK-BK14-PEDCO-110-PI-MR-0001 | BK-BK14-PEDCO-110-PI-MR-0001 | BK | BK14 | PEDCO | 110 | PI | MR | 0001 | F0Z-708225 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFI | T-1544 | 44859 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1544 | 2022-10-25 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2
2 | 8 | 2 | 1 | 1 | 2 | 0 | 2.8.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 1 | 1 | 2 | 1 | 2.8.2.1.1.2.1 | BK-BK14-PEDCO-110-PI-TB-0001 | TBE For Pipes - BK14 |  | BK-BK14-PEDCO-110-PI-TB-0001 | BK-BK14-PEDCO-110-PI-TB-0001 | BK | BK14 | PEDCO | 110 | PI | TB | 0001 | F0Z-708226 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 1 | 2 | 0 | 0 | 2.8.2.1.2 |  | Pipe Support
2 | 8 | 2 | 1 | 2 | 1 | 0 | 2.8.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 1 | 2 | 1 | 1 | 2.8.2.1.2.1.1 | BK-BK14-PEDCO-110-PI-MR-0002 | PMR For Pipe Support - BK14 |  | BK-BK14-PEDCO-110-PI-MR-0002 | BK-BK14-PEDCO-110-PI-MR-0002 | BK | BK14 | PEDCO | 110 | PI | MR | 0002 | F0Z-708227 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 1 | 2 | 2 | 0 | 2.8.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 1 | 2 | 2 | 1 | 2.8.2.1.2.2.1 | BK-BK14-PEDCO-110-PI-TB-0002 | TBE For Pipe Support - BK14 |  | BK-BK14-PEDCO-110-PI-TB-0002 | BK-BK14-PEDCO-110-PI-TB-0002 | BK | BK14 | PEDCO | 110 | PI | TB | 0002 | F0Z-708228 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 2 | 0 | 0 | 0 | 2.8.2.2 |  | HVAC
2 | 8 | 2 | 2 | 1 | 0 | 0 | 2.8.2.2.1 |  | Main HVAC Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 2 | 1 | 1 | 0 | 2.8.2.1.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 2 | 1 | 1 | 1 | 2.8.2.2.1.1.1 | BK-BK14-PEDCO-110-HV-MR-0001 | PMR For Main HVAC Equipment - BK14 |  | BK-BK14-PEDCO-110-HV-MR-0001 | BK-BK14-PEDCO-110-HV-MR-0001 | BK | BK14 | PEDCO | 110 | HV | MR | 0001 | F0Z-708229 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 2 | 1 | 2 | 0 | 2.8.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 2 | 1 | 2 | 1 | 2.8.2.2.1.2.1 | BK-BK14-PEDCO-110-HV-TB-0001 | TBE For Main HVAC Equipment - BK14 |  | BK-BK14-PEDCO-110-HV-TB-0001 | BK-BK14-PEDCO-110-HV-TB-0001 | BK | BK14 | PEDCO | 110 | HV | TB | 0001 | F0Z-708230 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 3 | 0 | 0 | 0 | 2.8.2.3 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 1 | 0 | 0 | 2.8.2.3.1 |  | Transformers
2 | 8 | 2 | 3 | 1 | 1 | 0 | 2.8.3.1.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 1 | 1 | 1 | 2.8.2.3.1.1.1 | BK-BK14-PEDCO-110-EL-MR-0001 | PMR For Transformers - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0001 | BK-BK14-PEDCO-110-EL-MR-0001 | BK | BK14 | PEDCO | 110 | EL | MR | 0001 | F0Z-708231 | AFD | IFC | 2022-07-27 | 2022-08-03 | 2022-08-09 | 7 | 6 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-13 |  |  | D00 | IFC | T-1153 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05233 | 44767 | 1401/05/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-167071 | 44776 | 1401/05/12 | 44782 | 1401/05/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1153 | 2022-07-13 | 1401/04/22 |  |  |  | BK-SUR-ENG-ELE-01-05233 | 44767 | 1401/05/03 | CM-C3 | [6 empty] | 1401-2294-167071 | 2022-08-03 | 1401/05/12 | 44782 | 1401/05/18 | AP
2 | 8 | 2 | 3 | 1 | 2 | 0 | 2.8.3.1.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 1 | 2 | 1 | 2.8.2.3.1.2.1 | BK-BK14-PEDCO-110-EL-TB-0001 | TBE For Transformers - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0001 | BK-BK14-PEDCO-110-EL-TB-0001 | BK | BK14 | PEDCO | 110 | EL | TB | 0001 | F0Z-708232 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 2 | 0 | 0 | 2.8.2.3.2 |  | LV Switchgear & MCC
2 | 8 | 2 | 3 | 2 | 1 | 0 | 2.8.3.2.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 2 | 1 | 1 | 2.8.2.3.2.1.1 | BK-BK14-PEDCO-110-EL-MR-0002 | PMR For LV Switchgear & MCC - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0002 | BK-BK14-PEDCO-110-EL-MR-0002 | BK | BK14 | PEDCO | 110 | EL | MR | 0002 | F0Z-708233 | IFI | IFI | 2022-09-25 | 2022-10-05 | 2022-10-08 | 10 | 3 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-11 |  |  | D00 | IFI | T-1393 | 44815 | 1401/06/20 | T-1393 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05759 | 44828 | 1401/07/02 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249409 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1393 | 2022-09-11 | 1401/06/20 | T-1393 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05759 | 44828 | 1401/07/02 | CM-C2 | [6 empty] | 1401-2294-249409 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 8 | 2 | 3 | 2 | 2 | 0 | 2.8.3.2.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 2 | 2 | 1 | 2.8.2.3.2.2.1 | BK-BK14-PEDCO-110-EL-TB-0002 | TBE For LV Switchgear & MCC - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0002 | BK-BK14-PEDCO-110-EL-TB-0002 | BK | BK14 | PEDCO | 110 | EL | TB | 0002 | F0Z-708234 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 3 | 0 | 0 | 2.8.2.3.3 |  | Emergency Diesel Generator
2 | 8 | 2 | 3 | 3 | 1 | 0 | 2.8.3.3.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 3 | 1 | 1 | 2.8.2.3.3.1.1 | BK-BK14-PEDCO-110-EL-MR-0003 | PMR For Emergency Diesel Generator - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0003 | BK-BK14-PEDCO-110-EL-MR-0003 | BK | BK14 | PEDCO | 110 | EL | MR | 0003 | F0Z-708235 | IFI | IFI | 2022-09-03 | 2022-09-08 | 2022-09-12 | 5 | 4 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-20 |  |  | D00 | IFI | T-1293 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216140 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1293 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | [6 empty] | 1401-2294-216140 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | AP
2 | 8 | 2 | 3 | 3 | 2 | 0 | 2.8.3.3.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 3 | 2 | 1 | 2.8.2.3.3.2.1 | BK-BK14-PEDCO-110-EL-TB-0003 | TBE For Emergency Diesel Generator - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0003 | BK-BK14-PEDCO-110-EL-TB-0003 | BK | BK14 | PEDCO | 110 | EL | TB | 0003 | F0Z-708236 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 4 | 0 | 0 | 2.8.2.3.4 |  | UPS System
2 | 8 | 2 | 3 | 4 | 1 | 0 | 2.8.3.4.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 4 | 1 | 1 | 2.8.2.3.4.1.1 | BK-BK14-PEDCO-110-EL-MR-0004 | PMR For UPS System - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0004 | BK-BK14-PEDCO-110-EL-MR-0004 | BK | BK14 | PEDCO | 110 | EL | MR | 0004 | F0Z-708237 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 4 | 2 | 0 | 2.8.3.4.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 4 | 2 | 1 | 2.8.2.3.4.2.1 | BK-BK14-PEDCO-110-EL-TB-0004 | TBE For UPS System - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0004 | BK-BK14-PEDCO-110-EL-TB-0004 | BK | BK14 | PEDCO | 110 | EL | TB | 0004 | F0Z-708238 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 5 | 0 | 0 | 2.8.2.3.5 |  | DC Charger
2 | 8 | 2 | 3 | 5 | 1 | 0 | 2.8.3.5.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 5 | 1 | 1 | 2.8.2.3.5.1.1 | BK-BK14-PEDCO-110-EL-MR-0005 | PMR For DC Charger - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0005 | BK-BK14-PEDCO-110-EL-MR-0005 | BK | BK14 | PEDCO | 110 | EL | MR | 0005 | F0Z-708239 | IFI | IFI | 2022-05-10 | 2022-05-29 | 2022-05-30 | 19 | 1 | 20 | IFI | 2022-09-07 | 2022-09-08 | 2022-09-12 | 1 | 4 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-26 |  |  | D01 | IFI | T-1311 | 44797 | 1401/06/01 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-BK14-PEDCO-110-EL-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-BK14-PEDCO-110-EL-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0864 | 2022-04-26 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04211 | 44691 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78867 | 2022-05-29 | 1401/03/08 | 44711 | 1401/03/09 | CM | [10 empty] | D01 | IFI | T-1311 | 44797 | 1401/06/01 |  |  |  | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-BK14-PEDCO-110-EL-MR-0005_D00 | [5 empty] | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-BK14-PEDCO-110-EL-MR-0005_D00
2 | 8 | 2 | 3 | 5 | 2 | 0 | 2.8.3.5.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 5 | 2 | 1 | 2.8.2.3.5.2.1 | BK-BK14-PEDCO-110-EL-TB-0005 | TBE For DC Charger - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0005 | BK-BK14-PEDCO-110-EL-TB-0005 | BK | BK14 | PEDCO | 110 | EL | TB | 0005 | F0Z-708240 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 3 | 6 | 0 | 0 | 2.8.2.3.6 |  | Capacitor Bank | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 6 | 1 | 0 | 2.8.3.6.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 6 | 1 | 1 | 2.8.2.3.6.1.1 | BK-BK14-PEDCO-110-EL-MR-0006 | PMR For Capacitor Bank - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0006 | BK-BK14-PEDCO-110-EL-MR-0006 | BK | BK14 | PEDCO | 110 | EL | MR | 0006 | F0Z-708241 | IFI | IFI | 2022-08-13 | 2022-08-18 | 2022-08-20 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFI | T-1215 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183488 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1215 | 2022-07-30 | 1401/05/08 |  |  |  | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | [6 empty] | 1401-2294-183488 | 2022-08-18 | 1401/05/27 | 44793 | 1401/05/29 | RJ
2 | 8 | 2 | 3 | 6 | 2 | 0 | 2.8.3.6.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 6 | 2 | 1 | 2.8.2.3.6.2.1 | BK-BK14-PEDCO-110-EL-TB-0006 | TBE For Capacitor Bank - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0006 | BK-BK14-PEDCO-110-EL-TB-0006 | BK | BK14 | PEDCO | 110 | EL | TB | 0006 | F0Z-708242 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 3 | 7 | 0 | 0 | 2.8.2.3.7 |  | Lighting & Distribution Main Panels | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 7 | 1 | 0 | 2.8.3.7.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 7 | 1 | 1 | 2.8.2.3.7.1.1 | BK-BK14-PEDCO-110-EL-MR-0007 | PMR For Lighting & Distribution Main Panels - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0007 | BK-BK14-PEDCO-110-EL-MR-0007 | BK | BK14 | PEDCO | 110 | EL | MR | 0007 | F0Z-708243 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 3 | 7 | 2 | 0 | 2.8.3.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 7 | 2 | 1 | 2.8.2.3.7.2.1 | BK-BK14-PEDCO-110-EL-TB-0007 | TBE For Lighting & Distribution Main Panels - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0007 | BK-BK14-PEDCO-110-EL-TB-0007 | BK | BK14 | PEDCO | 110 | EL | TB | 0007 | F0Z-708244 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 3 | 8 | 0 | 0 | 2.8.2.3.8 |  | Earthing & Lightning System | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 8 | 1 | 0 | 2.8.3.8.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 8 | 1 | 1 | 2.8.2.3.8.1.1 | BK-BK14-PEDCO-110-EL-MR-0008 | PMR For Earthing & Lightning System - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0008 | BK-BK14-PEDCO-110-EL-MR-0008 | BK | BK14 | PEDCO | 110 | EL | MR | 0008 | F0Z-708245 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 3 | 8 | 2 | 0 | 2.8.3.8.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 8 | 2 | 1 | 2.8.2.3.8.2.1 | BK-BK14-PEDCO-110-EL-TB-0008 | TBE For Earthing & Lightning System - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0008 | BK-BK14-PEDCO-110-EL-TB-0008 | BK | BK14 | PEDCO | 110 | EL | TB | 0008 | F0Z-708246 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 9 | 0 | 0 | 2.8.2.3.9 |  | Lighting and Small Power Equipment
2 | 8 | 2 | 3 | 9 | 1 | 0 | 2.8.3.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 9 | 1 | 1 | 2.8.2.3.9.1.1 | BK-BK14-PEDCO-110-EL-MR-0009 | PMR For Lighting and Small Power Equipment - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0009 | BK-BK14-PEDCO-110-EL-MR-0009 | BK | BK14 | PEDCO | 110 | EL | MR | 0009 | F0Z-708247 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 3 | 9 | 2 | 0 | 2.8.3.9.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 9 | 2 | 1 | 2.8.2.3.9.2.1 | BK-BK14-PEDCO-110-EL-TB-0009 | TBE For Lighting and Small Power Equipment - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0009 | BK-BK14-PEDCO-110-EL-TB-0009 | BK | BK14 | PEDCO | 110 | EL | TB | 0009 | F0Z-708248 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 10 | 0 | 0 | 2.8.2.3.10 |  | Tray/Ladder and Accessories
2 | 8 | 2 | 3 | 10 | 1 | 0 | 2.8.3.10.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 10 | 1 | 1 | 2.8.2.3.10.1.1 | BK-BK14-PEDCO-110-EL-MR-0010 | PMR For Tray/Ladder and Accessories - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0010 | BK-BK14-PEDCO-110-EL-MR-0010 | BK | BK14 | PEDCO | 110 | EL | MR | 0010 | F0Z-708249 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 3 | 10 | 2 | 0 | 2.8.3.10.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 10 | 2 | 1 | 2.8.2.3.10.2.1 | BK-BK14-PEDCO-110-EL-TB-0010 | TBE For Tray/Ladder and Accessories - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0010 | BK-BK14-PEDCO-110-EL-TB-0010 | BK | BK14 | PEDCO | 110 | EL | TB | 0010 | F0Z-708250 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 11 | 0 | 0 | 2.8.2.3.11 |  | Power & Control Cables
2 | 8 | 2 | 3 | 11 | 1 | 0 | 2.8.3.11.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 11 | 1 | 1 | 2.8.2.3.11.1.1 | BK-BK14-PEDCO-110-EL-MR-0011 | PMR For Power & Control Cables - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0011 | BK-BK14-PEDCO-110-EL-MR-0011 | BK | BK14 | PEDCO | 110 | EL | MR | 0011 | F0Z-708251 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 11 | 2 | 0 | 2.8.3.11.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 11 | 2 | 1 | 2.8.2.3.11.2.1 | BK-BK14-PEDCO-110-EL-TB-0011 | TBE For Power & Control Cables - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0011 | BK-BK14-PEDCO-110-EL-TB-0011 | BK | BK14 | PEDCO | 110 | EL | TB | 0011 | F0Z-708252 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 12 | 0 | 0 | 2.8.2.3.12 |  | Electrical Bulk Items
2 | 8 | 2 | 3 | 12 | 1 | 0 | 2.8.3.12.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 12 | 1 | 1 | 2.8.2.3.12.1.1 | BK-BK14-PEDCO-110-EL-MR-0012 | PMR For Electrical Bulk Items - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0012 | BK-BK14-PEDCO-110-EL-MR-0012 | BK | BK14 | PEDCO | 110 | EL | MR | 0012 | F0Z-708253 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 3 | 12 | 2 | 0 | 2.8.3.12.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 12 | 2 | 1 | 2.8.2.3.12.2.1 | BK-BK14-PEDCO-110-EL-TB-0012 | TBE For Electrical Bulk Items - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0012 | BK-BK14-PEDCO-110-EL-TB-0012 | BK | BK14 | PEDCO | 110 | EL | TB | 0012 | F0Z-708254 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Moved to Field | 0
2 | 8 | 2 | 3 | 13 | 0 | 0 | 2.8.2.3.13 |  | Transmission Over head Line | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 3 | 13 | 1 | 0 | 2.8.3.13.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 13 | 1 | 1 | 2.8.2.3.13.1.1 | BK-BK14-PEDCO-110-EL-MR-0013 | PMR For Transmission Over head Line - BK14 |  | BK-BK14-PEDCO-110-EL-MR-0013 | BK-BK14-PEDCO-110-EL-MR-0013 | BK | BK14 | PEDCO | 110 | EL | MR | 0013 | F0Z-708255 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 3 | 13 | 2 | 0 | 2.8.3.13.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 13 | 2 | 1 | 2.8.2.3.13.2.1 | BK-BK14-PEDCO-110-EL-TB-0013 | TBE For Transmission Over head Line - BK14 |  | BK-BK14-PEDCO-110-EL-TB-0013 | BK-BK14-PEDCO-110-EL-TB-0013 | BK | BK14 | PEDCO | 110 | EL | TB | 0013 | F0Z-708256 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 4 | 0 | 0 | 0 | 2.8.2.4 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 4 | 1 | 0 | 0 | 2.8.2.4.1 |  | Steel Structure Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 4 | 1 | 1 | 0 | 2.8.4.1.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 4 | 1 | 1 | 1 | 2.8.2.4.1.1.1 | BK-BK14-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - BK14 |  | BK-BK14-PEDCO-110-ST-MR-0001 | BK-BK14-PEDCO-110-ST-MR-0001 | BK | BK14 | PEDCO | 110 | ST | MR | 0001 | F0Z-708257 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 4 | 1 | 2 | 0 | 2.8.4.1.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 4 | 1 | 2 | 1 | 2.8.2.4.1.2.1 | BK-BK14-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - BK14 |  | BK-BK14-PEDCO-110-ST-TB-0001 | BK-BK14-PEDCO-110-ST-TB-0001 | BK | BK14 | PEDCO | 110 | ST | TB | 0001 | F0Z-708258 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 4 | 2 | 0 | 0 | 2.8.2.4.2 |  | Anchor Bolts
2 | 8 | 2 | 4 | 2 | 1 | 0 | 2.8.4.2.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 4 | 2 | 1 | 1 | 2.8.2.4.2.1.1 | BK-BK14-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - BK14 |  | BK-BK14-PEDCO-110-ST-MR-0002 | BK-BK14-PEDCO-110-ST-MR-0002 | BK | BK14 | PEDCO | 110 | ST | MR | 0002 | F0Z-708259 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 4 | 2 | 2 | 0 | 2.8.4.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 4 | 2 | 2 | 1 | 2.8.2.4.2.2.1 | BK-BK14-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - BK14 |  | BK-BK14-PEDCO-110-ST-TB-0002 | BK-BK14-PEDCO-110-ST-TB-0002 | BK | BK14 | PEDCO | 110 | ST | TB | 0002 | F0Z-708260 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 4 | 3 | 0 | 0 | 2.8.2.4.3 |  | Blast Proof Doors | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 4 | 3 | 1 | 0 | 2.8.4.3.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 4 | 3 | 1 | 1 | 2.8.2.4.3.1.1 | BK-BK14-PEDCO-110-ST-MR-0003 | PMR For Blast Proof Doors - BK14 |  | BK-BK14-PEDCO-110-ST-MR-0003 | BK-BK14-PEDCO-110-ST-MR-0003 | BK | BK14 | PEDCO | 110 | ST | MR | 0003 | F0Z-708261 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 4 | 3 | 2 | 0 | 2.8.4.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 4 | 3 | 2 | 1 | 2.8.2.4.3.2.1 | BK-BK14-PEDCO-110-ST-TB-0003 | TBE For Blast Proof Doors - BK14 |  | BK-BK14-PEDCO-110-ST-TB-0003 | BK-BK14-PEDCO-110-ST-TB-0003 | BK | BK14 | PEDCO | 110 | ST | TB | 0003 | F0Z-708262 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 5 | 0 | 0 | 0 | 2.8.2.5 |  | Civil | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 5 | 1 | 0 | 0 | 2.8.2.5.1 |  | Geomembrane
2 | 8 | 2 | 5 | 1 | 1 | 0 | 2.8.5.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 5 | 1 | 1 | 1 | 2.8.2.5.1.1.1 | BK-BK14-PEDCO-110-CV-MR-0001 | PMR For Geomembrane - BK14 |  | BK-BK14-PEDCO-110-CV-MR-0001 | BK-BK14-PEDCO-110-CV-MR-0001 | BK | BK14 | PEDCO | 110 | CV | MR | 0001 | F0Z-708263 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 2 | 5 | 1 | 2 | 0 | 2.8.5.1.2 |  | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 5 | 1 | 2 | 1 | 2.8.2.5.1.2.1 | BK-BK14-PEDCO-110-CV-TB-0001 | TBE For Geomembrane - BK14 |  | BK-BK14-PEDCO-110-CV-TB-0001 | BK-BK14-PEDCO-110-CV-TB-0001 | BK | BK14 | PEDCO | 110 | CV | TB | 0001 | F0Z-708264 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 5 | 2 | 0 | 0 | 2.8.2.5.2 |  | Geotextile
2 | 8 | 2 | 5 | 2 | 1 | 0 | 2.8.5.2.1 |  | Purchase Material Requisition (PMR)
2 | 8 | 2 | 5 | 2 | 1 | 1 | 2.8.2.5.2.1.1 | BK-BK14-PEDCO-110-CV-MR-0002 | PMR For Geotextile - BK14 |  | BK-BK14-PEDCO-110-CV-MR-0002 | BK-BK14-PEDCO-110-CV-MR-0002 | BK | BK14 | PEDCO | 110 | CV | MR | 0002 | F0Z-708265 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 2 | 5 | 2 | 2 | 0 | 2.8.5.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 2 | 5 | 2 | 2 | 1 | 2.8.2.5.2.2.1 | BK-BK14-PEDCO-110-CV-TB-0002 | TBE For Geotextile - BK14 |  | BK-BK14-PEDCO-110-CV-TB-0002 | BK-BK14-PEDCO-110-CV-TB-0002 | BK | BK14 | PEDCO | 110 | CV | TB | 0002 | F0Z-708266 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 3 | 0 | 0 | 0 | 0 | 2.8.3 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 3 | 0 | 0 | 1 | 0 | 2.8.3.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 3 | 0 | 0 | 1 | 1 | 2.8.3.1.1 | BK-BK14-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - BK14 |  | BK-BK14-PEDCO-110-CO-PR-0001 | BK-BK14-PEDCO-110-CO-PR-0001 | BK | BK14 | PEDCO | 110 | CO | PR | 0001 | F0Z-708267 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 4 | 0 | 0 | 0 | 0 | 2.8.4 |  | Field Engineering
2 | 8 | 4 | 0 | 0 | 1 | 0 | 2.8.4.1 |  | Query
2 | 8 | 4 | 0 | 0 | 1 | 1 | 2.8.4.1.1 | BK-BK14-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-BK14-PEDCO-110-GE-TQ-0001 | BK-BK14-PEDCO-110-GE-TQ-0001 | BK | BK14 | PEDCO | 110 | GE | TQ | 0001 | F7Z-708268 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 4 | 0 | 0 | 2 | 0 | 2.8.4.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 4 | 0 | 0 | 2 | 1 | 2.8.4.2.1 | BK-BK14-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - BK14 |  | BK-BK14-PEDCO-110-GE-DO-0001 | BK-BK14-PEDCO-110-GE-DO-0001 | BK | BK14 | PEDCO | 110 | GE | DO | 0001 | F0Z-708269 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 5 | 0 | 0 | 0 | 0 | 2.8.5 |  | Engineering Final Documentation
2 | 8 | 5 | 0 | 0 | 1 | 0 | 2.8.5.1 |  | Manual | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 8 | 5 | 0 | 0 | 1 | 1 | 2.8.5.1.1 | BK-BK14-PEDCO-110-GE-ML-0001 | Operating Manual - BK14 |  | BK-BK14-PEDCO-110-GE-ML-0001 | BK-BK14-PEDCO-110-GE-ML-0001 | BK | BK14 | PEDCO | 110 | GE | ML | 0001 | F0Z-708270 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 8 | 5 | 0 | 0 | 2 | 0 | 2.8.5.2 |  | Dossier
2 | 8 | 5 | 0 | 0 | 2 | 1 | 2.8.5.2.1 | BK-BK14-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - BK14 |  | BK-BK14-PEDCO-110-GE-DO-0001 | [8 empty] | F0Z-708269 |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 8 | 5 | 0 | 0 | 2 | 2 | 2.8.5.2.2 | BK-BK14-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - BK14 |  | BK-BK14-PEDCO-110-GE-DO-0002 | BK-BK14-PEDCO-110-GE-DO-0002 | BK | BK14 | PEDCO | 110 | GE | DO | 0002 | F0Z-708271 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 0 | 0 | 0 | 0 | 0 | 2.9 |  | Package 08-Workover # 12 | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 0 | 0 | 0 | 0 | 2.9.1 |  | Detail Design
2 | 9 | 1 | 1 | 0 | 0 | 0 | 2.9.1.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 1 | 1 | 0 | 0 | 2.9.1.1.1 |  | Drawing/Diagram |  |  |  | BK | BK12 | PEDCO | 110 | PR | PI | 0001
2 | 9 | 1 | 1 | 1 | 0 | 1 | 2.9.1.1.1.1 | BK-BK12-PEDCO-110-PR-PI-0001 | P&ID for Diesel Oil Drum- BK12 |  | BK-BK12-PEDCO-110-PR-PI-0001 | [8 empty] | F2A-708272 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-06 | 2022-02-08 | 20 | 2 | 22 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-05-12 | 2022-05-16 | 18 | 4 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-15 |  |  | D03 | IFA | T-0795 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-399153 | 44598 | 1400/11/17 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0648 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 44635 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0795 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D02
2 | 9 | 1 | 1 | 1 | 0 | 2 | 2.9.1.1.1.2 | BK-BK12-PEDCO-110-PR-PI-0002 | P&ID for Potable Water Tank - BK12 |  | BK-BK12-PEDCO-110-PR-PI-0002 | [8 empty] | F2A-708273 | AFC | [50 empty] | 2021-11-15 |  |  | D03 | IFA | T-0795 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-399153 | 44598 | 1400/11/17 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0648 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 44635 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0795 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D02
2 | 9 | 1 | 1 | 2 | 0 | 0 | 2.9.1.1.2 |  | List
2 | 9 | 1 | 1 | 2 | 0 | 1 | 2.9.1.1.2.1 | BK-BK12-PEDCO-110-PR-LI-0001 | Line List - BK12 |  | BK-BK12-PEDCO-110-PR-LI-0001 | [8 empty] | F0Z-708274 | AFC | IFC | 2022-03-13 | 2022-03-12 | 2022-03-15 | -1 | 3 | 2 | IFA | 2022-05-14 | 2022-05-31 | 2022-05-06 | 17 | -25 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-27 |  |  | D01 | IFA | T-0877 | 44681 | 1401/02/10 | T-0877 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-83257 | 44712 | 1401/03/10 | 44687 | 1401/03/16 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0650 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03597 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445283 | 2022-03-12 | 1400/12/21 | 44635 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0877 | 44681 | 1401/02/10 | T-0877 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1401-2294-83257 | 44712 | 1401/03/10 | 44687 | 1401/03/16 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-LI-0001_D00
2 | 9 | 1 | 1 | 3 | 0 | 0 | 2.9.1.1.3 |  | Data Sheet | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 1 | 3 | 0 | 1 | 2.9.1.1.3.1 | BK-BK12-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - BK12 |  | BK-BK12-PEDCO-110-PR-DT-0001 | [8 empty] | F0Z-708275 | AFC | IFC | 2022-04-26 | 2022-05-14 | 2022-05-16 | 18 | 2 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-12 |  |  | D00 | IFC | T-0807 | 44663 | 1401/01/12 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03991 | 44670 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52773 | 44695 | 1401/02/24 | 44697 | 1401/02/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 44670 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 44697 | 1401/02/26 | AP
2 | 9 | 1 | 2 | 0 | 0 | 0 | 2.9.1.2 |  | HVAC/Plumbing | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 2 | 1 | 0 | 0 | 2.9.1.2.1 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 2 | 1 | 0 | 1 | 2.9.1.2.1.1 | BK-BK12-PEDCO-110-HV-CN-0001 | HVAC Calculation Note For Switchgear Building - BK12 |  | BK-BK12-PEDCO-110-HV-CN-0001 | BK-BK12-PEDCO-110-HV-CN-0001 | BK | BK12 | PEDCO | 110 | HV | CN | 0001 | F0Z-708276 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 1 | 2 | 1 | 0 | 2 | 2.9.1.2.1.2 | BK-BK12-PEDCO-110-HV-CN-0002 | HVAC Calculation Note For Security Building - BK12 |  | BK-BK12-PEDCO-110-HV-CN-0002 | BK-BK12-PEDCO-110-HV-CN-0002 | BK | BK12 | PEDCO | 110 | HV | CN | 0002 | F0Z-708277 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 1 | 2 | 2 | 0 | 0 | 2.9.1.2.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 2 | 2 | 0 | 1 | 2.9.1.2.2.1 | BK-BK12-PEDCO-110-HV-DT-0001 | Data Sheets For Main HVAC Equipment - BK12 |  | BK-BK12-PEDCO-110-HV-DT-0001 | BK-BK12-PEDCO-110-HV-DT-0001 | BK | BK12 | PEDCO | 110 | HV | DT | 0001 | F0Z-708278 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 2 | 3 | 0 | 0 | 2.9.1.2.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 2 | 3 | 0 | 1 | 2.9.1.2.3.1 | BK-BK12-PEDCO-110-HV-PY-0001 | HVAC System Layout For Switchgear Building - BK12 |  | BK-BK12-PEDCO-110-HV-PY-0001 | BK-BK12-PEDCO-110-HV-PY-0001 | BK | BK12 | PEDCO | 110 | HV | PY | 0001 | F4B-708279 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 2 | 3 | 0 | 2 | 2.9.1.2.3.2 | BK-BK12-PEDCO-110-HV-PY-0002 | HVAC System Layout For Security Building - BK12 |  | BK-BK12-PEDCO-110-HV-PY-0002 | BK-BK12-PEDCO-110-HV-PY-0002 | BK | BK12 | PEDCO | 110 | HV | PY | 0002 | F4B-708280 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 2 | 3 | 0 | 3 | 2.9.1.2.3.3 | BK-BK12-PEDCO-110-HV-PY-0003 | Plumbing & Sewage Piping Layout For Switchgear Building - BK12 |  | BK-BK12-PEDCO-110-HV-PY-0003 | BK-BK12-PEDCO-110-HV-PY-0003 | BK | BK12 | PEDCO | 110 | HV | PY | 0003 | F4B-708281 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 1 | 2 | 3 | 0 | 4 | 2.9.1.2.3.4 | BK-BK12-PEDCO-110-HV-PY-0004 | Plumbing & Sewage Piping Layout For Security Building - BK12 |  | BK-BK12-PEDCO-110-HV-PY-0004 | BK-BK12-PEDCO-110-HV-PY-0004 | BK | BK12 | PEDCO | 110 | HV | PY | 0004 | F4B-708282 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 2 | 4 | 0 | 0 | 2.9.1.2.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 2 | 4 | 0 | 1 | 2.9.1.2.4.1 | BK-BK12-PEDCO-110-HV-MT-0001 | MTO For Building HVAC & Plumbing Systems - BK12 |  | BK-BK12-PEDCO-110-HV-MT-0001 | BK-BK12-PEDCO-110-HV-MT-0001 | BK | BK12 | PEDCO | 110 | HV | MT | 0001 | F8Z-708283 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 3 | 0 | 0 | 0 | 2.9.1.3 |  | Piping
2 | 9 | 1 | 3 | 1 | 0 | 0 | 2.9.1.3.1 |  | Drawing/Diagram
2 | 9 | 1 | 3 | 1 | 0 | 1 | 2.9.1.3.1.1 | BK-BK12-PEDCO-110-PI-MT-0001 | Plot Plan Drawing – BK12 |  | BK-BK12-PEDCO-110-PI- PY -0001 | BK-BK12-PEDCO-110-PI-MT-0001 | BK | BK12 | PEDCO | 110 | PI | MT | 0001 | F8Z-708284 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14
2 | 9 | 1 | 3 | 1 | 0 | 0 | 2.9.1.3.1 |  | MTO
2 | 9 | 1 | 3 | 1 | 0 | 1 | 2.9.1.3.1.1 | BK-BK12-PEDCO-110-PI-MT-0001 | MTO For Pipes - BK12 |  | BK-BK12-PEDCO-110-PI-MT-0001 | BK-BK12-PEDCO-110-PI-MT-0001 | BK | BK12 | PEDCO | 110 | PI | MT | 0001 | F8Z-708284 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFI | T-1545 | 44859 | 1401/08/03 | T-1545 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1545 | 2022-10-25 | 1401/08/03 | T-1545 | 44859 | 1401/08/03
2 | 9 | 1 | 4 | 0 | 0 | 0 | 2.9.1.4 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 4 | 1 | 0 | 0 | 2.9.1.4.1 |  | MTO
2 | 9 | 1 | 4 | 1 | 0 | 1 | 2.9.1.4.1.1 | BK-BK12-PEDCO-110-EL-MT-0001 | MTO For Transmission Over Head Line - BK12 |  | BK-BK12-PEDCO-110-EL-MT-0001 | BK-BK12-PEDCO-110-EL-MT-0001 | BK | BK12 | PEDCO | 110 | EL | MT | 0001 | F8Z-708285 | IFI | IFI | 2022-10-03 | 2022-09-29 | 2022-10-08 | -4 | 9 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-19 |  |  | D00 | IFI | T-1417 | 44823 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249371 | 44833 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1417 | 2022-09-19 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | [6 empty] | 1401-2294-249371 | 2022-09-29 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 9 | 1 | 4 | 1 | 0 | 2 | 2.9.1.4.1.2 | BK-BK12-PEDCO-110-EL-MT-0002 | MTO For Lighting & Small Powers - BK12 |  | BK-BK12-PEDCO-110-EL-MT-0002 | BK-BK12-PEDCO-110-EL-MT-0002 | BK | BK12 | PEDCO | 110 | EL | MT | 0002 | F8Z-708286 | IFI | IFI | 2022-06-01 | 2022-06-10 | 2022-06-12 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-18 |  |  | D00 | IFI | T-0969 | 44699 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94633 | 44722 | 1401/03/20 | 44724 | 1401/03/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | [6 empty] | 1401-2294-94633 | 2022-06-10 | 1401/03/20 | 44724 | 1401/03/22 | CM
2 | 9 | 1 | 4 | 1 | 0 | 3 | 2.9.1.4.1.3 | BK-BK12-PEDCO-110-EL-MT-0003 | MTO For Power & Control Cables - BK12 |  | BK-BK12-PEDCO-110-EL-MT-0003 | BK-BK12-PEDCO-110-EL-MT-0003 | BK | BK12 | PEDCO | 110 | EL | MT | 0003 | F8Z-708287 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 4 | 1 | 0 | 4 | 2.9.1.4.1.4 | BK-BK12-PEDCO-110-EL-MT-0004 | MTO For Tray/Ladder and Accessories - BK12 |  | BK-BK12-PEDCO-110-EL-MT-0004 | BK-BK12-PEDCO-110-EL-MT-0004 | BK | BK12 | PEDCO | 110 | EL | MT | 0004 | F8Z-708288 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 1 | 4 | 1 | 0 | 5 | 2.9.1.4.1.5 | BK-BK12-PEDCO-110-EL-MT-0005 | MTO For Electrical Bulk Items - BK12 |  | BK-BK12-PEDCO-110-EL-MT-0005 | BK-BK12-PEDCO-110-EL-MT-0005 | BK | BK12 | PEDCO | 110 | EL | MT | 0005 | F8Z-708289 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 4 | 1 | 0 | 6 | 2.9.1.4.1.6 | BK-BK12-PEDCO-110-EL-MT-0006 | MTO For Earthing & Lightning Systems - BK12 |  | BK-BK12-PEDCO-110-EL-MT-0006 | BK-BK12-PEDCO-110-EL-MT-0006 | BK | BK12 | PEDCO | 110 | EL | MT | 0006 | F8Z-708290 | IFI | IFI | 2022-10-25 | 2022-11-10 | 2022-11-14 | 16 | 4 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-11 |  |  | D00 | IFI | T-1480 | 44845 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-304880 | 44875 | 1401/08/19 | 44879 | 1401/08/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1480 | 2022-10-11 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | [6 empty] | 1401-2294-304880 | 2022-11-10 | 1401/08/19 | 44879 | 1401/08/23 | CM
2 | 9 | 1 | 5 | 0 | 0 | 0 | 2.9.1.5 |  | Architecture
2 | 9 | 1 | 5 | 1 | 0 | 0 | 2.9.1.5.1 |  | Drawing/Diagram
2 | 9 | 1 | 5 | 1 | 0 | 1 | 2.9.1.5.1.1 | BK-BK12-PEDCO-110-AR-DW-0001 | Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-12 |  | BK-BK12-PEDCO-110-AR-DW-0001 | BK-BK12-PEDCO-110-AR-DW-0001 | BK | BK12 | PEDCO | 110 | AR | DW | 0001 | F4A-708291 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-01 |  |  | D00 | IFC | T-0885 | 44682 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 44697 | 1401/02/26 | CM
2 | 9 | 1 | 5 | 1 | 0 | 2 | 2.9.1.5.1.2 | BK-BK12-PEDCO-110-AR-DW-0002 | Architectural Drawing For Switchgear Building of Well Pads - BK-12 |  | BK-BK12-PEDCO-110-AR-DW-0002 | BK-BK12-PEDCO-110-AR-DW-0002 | BK | BK12 | PEDCO | 110 | AR | DW | 0002 | F4B-708292 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 2022-05-31 | 2022-06-07 | -1 | 7 | 6 | IFC | 2022-09-21 | 2022-10-11 | 2022-10-17 | 20 | 6 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D02 | IFC | T-1370 | 44811 | 1401/06/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ARC-00-03551 | 44634 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 44645 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 44699 | 1401/02/28 | T-0974 | 44702 | 1401/02/31 | BK-SUR-ENG-ARC-01-04416 | 44705 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D00 | [5 empty] | 1401-2294-85268 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | RJ | NISOC-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D00 | [9 empty] | D02 | IFC | T-1370 | 44811 | 1401/06/16 | [7 empty] | PEDCO-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D01 | [5 empty] | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D01
2 | 9 | 1 | 5 | 1 | 0 | 3 | 2.9.1.5.1.3 | BK-BK12-PEDCO-110-AR-DW-0003 | Architectural Drawing For Security Building of Well Pads - BK-12 |  | BK-BK12-PEDCO-110-AR-DW-0003 | BK-BK12-PEDCO-110-AR-DW-0003 | BK | BK12 | PEDCO | 110 | AR | DW | 0003 | F4B-708293 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-01 |  |  | D00 | IFC | T-0886 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 44695 | 1401/02/21 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 44697 | 1401/02/26 | CM
2 | 9 | 1 | 5 | 2 | 0 | 0 | 2.9.1.5.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 5 | 2 | 0 | 1 | 2.9.1.5.2.1 | BK-BK12-PEDCO-110-AR-MT-0001 | MTO For Architectural Works - BK12 |  | BK-BK12-PEDCO-110-AR-MT-0001 | BK-BK12-PEDCO-110-AR-MT-0001 | BK | BK12 | PEDCO | 110 | AR | MT | 0001 | F8Z-708294 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 6 | 0 | 0 | 0 | 2.9.1.6 |  | Civil
2 | 9 | 1 | 6 | 1 | 0 | 0 | 2.9.1.6.1 |  | Drawing/Diagram
2 | 9 | 1 | 6 | 1 | 0 | 1 | 2.9.1.6.1.1 | BK-BK12-PEDCO-110-CV-DW-0001 | Civil and Structural drawings - BK12 |  | BK-BK12-PEDCO-110-CV-DW-0001 | BK-BK12-PEDCO-110-CV-DW-0001 | BK | BK12 | PEDCO | 110 | CV | DW | 0001 | F4A-708295 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 1 | 6 | 1 | 0 | 2 | 2.9.1.6.1.2 | BK-BK12-PEDCO-110-CV-PY-0001 | General Civil Layout - BK12 |  | BK-BK12-PEDCO-110-CV-PY-0001 | BK-BK12-PEDCO-110-CV-PY-0001 | BK | BK12 | PEDCO | 110 | CV | PY | 0001 | F4A-708296 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 6 | 1 | 0 | 3 | 2.9.1.6.1.3 | BK-BK12-PEDCO-110-CV-PY-0003 | Rough Grading Plans -BK12 |  | BK-BK12-PEDCO-110-CV-PY-0003 | BK-BK12-PEDCO-110-CV-PY-0003 | BK | BK12 | PEDCO | 110 | CV | PY | 0003 | F4A-708297 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 1 | 6 | 2 | 0 | 0 | 2.9.1.6.2 |  | Report
2 | 9 | 1 | 6 | 2 | 0 | 1 | 2.9.1.6.2.1 | BK-BK12-PEDCO-110-CV-RT-0001 | Site Visit Report (Civil Work) - BK12 |  | BK-BK12-PEDCO-110-CV-RT-0001 | BK-BK12-PEDCO-110-CV-RT-0001 | BK | BK12 | PEDCO | 110 | CV | RT | 0001 | F0Z-708298 | IFI | IFC | 2022-07-09 | 2022-07-05 | 2022-07-09 | -4 | 4 | 0 | IFI | 2022-08-15 | 2022-08-18 | 2022-08-27 | 3 | 9 | 12 | FI | 2022-11-08 | 2022-11-05 | 2022-11-06 | -3 | 1 | -2 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-25 | 2022-11-19 |  | D03 | FI | T-1593 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK12-PEDCO-110-CV-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1113 | 2022-06-25 | 1401/04/04 |  |  |  | BK-SUR-ENG-CIV-01-05039 | 44751 | 1401/04/18 | CM-C2 | [6 empty] | 1401-2294-130256 | 2022-07-05 | 1401/04/14 | 44751 | 1401/04/18 | CM | [10 empty] | D01 | IFI | T-1234 | 44774 | 1401/05/10 |  |  |  | BK-SUR-ENG-CIV-01-05381 | 44782 | 1401/05/18 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-CV-RT-0001_D00 | [5 empty] | 1401-2294-183548 | 44791 | 1401/05/27 | 44800 | 1401/06/05 | AP | NISOC-CRS-BK-BK12-PEDCO-110-CV-RT-0001_D00 | [9 empty] | D02 | FI | T-1548 | 44859 | 1401/08/03 | T-1548 | 44859 | 1401/08/03 | BK-SUR-ENG-CIV-01-05968 | 44859 | 1401/08/03 | AP | PEDCO-CRS-BK-BK12-PEDCO-110-CV-RT-0001_D02 | [5 empty] | 1401-2294-296556 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | [10 empty] | D03 | FI | T-1593 | 44884 | 1401/08/28 | [19 empty] | NISOC-CRS-BK-BK12-PEDCO-110-CV-RT-0001_D02
2 | 9 | 1 | 6 | 3 | 0 | 0 | 2.9.1.6.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 6 | 3 | 0 | 1 | 2.9.1.6.3.1 | BK-BK12-PEDCO-110-CV-MT-0001 | MTO For Civil Works - BK12 |  | BK-BK12-PEDCO-110-CV-MT-0001 | BK-BK12-PEDCO-110-CV-MT-0001 | BK | BK12 | PEDCO | 110 | CV | MT | 0001 | F8Z-708299 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 7 | 0 | 0 | 0 | 2.9.1.7 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 7 | 1 | 0 | 0 | 2.9.1.7.1 |  | Drawing/Diagram
2 | 9 | 1 | 7 | 1 | 0 | 1 | 2.9.1.7.1.1 | BK-BK12-PEDCO-110-ST-DW-0001 | Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-12 |  | BK-BK12-PEDCO-110-ST-DW-0001 | BK-BK12-PEDCO-110-ST-DW-0001 | BK | BK12 | PEDCO | 110 | ST | DW | 0001 | F4G-708300 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 7 | 1 | 0 | 2 | 2.9.1.7.1.2 | BK-BK12-PEDCO-110-ST-DW-0002 | Foundation Drawing For Security Building For Well Pads - BK-12 |  | BK-BK12-PEDCO-110-ST-DW-0002 | BK-BK12-PEDCO-110-ST-DW-0002 | BK | BK12 | PEDCO | 110 | ST | DW | 0002 | F4Q-708301 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 1 | 7 | 1 | 0 | 3 | 2.9.1.7.1.3 | BK-BK12-PEDCO-110-ST-DW-0003 | Structural Drawing For Security Building For Well Pads - BK-12 |  | BK-BK12-PEDCO-110-ST-DW-0003 | BK-BK12-PEDCO-110-ST-DW-0003 | BK | BK12 | PEDCO | 110 | ST | DW | 0003 | F4M-708302 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 7 | 1 | 0 | 4 | 2.9.1.7.1.4 | BK-BK12-PEDCO-110-ST-DW-0004 | Foundation Drawing For Switchgear Building For Well Pads - BK-12 |  | BK-BK12-PEDCO-110-ST-DW-0004 | BK-BK12-PEDCO-110-ST-DW-0004 | BK | BK12 | PEDCO | 110 | ST | DW | 0004 | F4Q-708303 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 1 | 7 | 1 | 0 | 5 | 2.9.1.7.1.5 | BK-BK12-PEDCO-110-ST-DW-0005 | Structural Drawing For Switchgear Building For Well Pads - BK-12 |  | BK-BK12-PEDCO-110-ST-DW-0005 | BK-BK12-PEDCO-110-ST-DW-0005 | BK | BK12 | PEDCO | 110 | ST | DW | 0005 | F4M-708304 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 7 | 1 | 0 | 6 | 2.9.1.7.1.6 | BK-BK12-PEDCO-110-ST-DW-0006 | Foundation Drawing For Potable Water Tank For Well Pads - BK-12 |  | BK-BK12-PEDCO-110-ST-DW-0006 | BK-BK12-PEDCO-110-ST-DW-0006 | BK | BK12 | PEDCO | 110 | ST | DW | 0006 | F4Q-708305 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 7 | 1 | 0 | 7 | 2.9.1.7.1.7 | BK-BK12-PEDCO-110-ST-DW-0007 | Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-12 |  | BK-BK12-PEDCO-110-ST-DW-0007 | BK-BK12-PEDCO-110-ST-DW-0007 | BK | BK12 | PEDCO | 110 | ST | DW | 0007 | F4Q-708306 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 1 | 7 | 1 | 0 | 8 | 2.9.1.7.1.8 | BK-BK12-PEDCO-110-ST-DW-0008 | Structural Drawing For Diesel Generator Shelter For Well Pads - BK-12 |  | BK-BK12-PEDCO-110-ST-DW-0008 | BK-BK12-PEDCO-110-ST-DW-0008 | BK | BK12 | PEDCO | 110 | ST | DW | 0008 | F4M-708307 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 7 | 2 | 0 | 0 | 2.9.1.7.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 7 | 2 | 0 | 1 | 2.9.1.7.2.1 | BK-BK12-PEDCO-110-ST-MT-0001 | MTO For Structural Works - BK12 |  | BK-BK12-PEDCO-110-ST-MT-0001 | BK-BK12-PEDCO-110-ST-MT-0001 | BK | BK12 | PEDCO | 110 | ST | MT | 0001 | F8Z-708308 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 1 | 8 | 0 | 0 | 0 | 2.9.1.0 |  | Geotechnic
2 | 9 | 1 | 8 | 0 | 1 | 0 | 2.9.1.1 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 8 | 0 | 1 | 1 | 2.9.1.8.1.1 | BK-BK12-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - BK12 |  | BK-BK12-PEDCO-110-GT-RT-0001 | BK-BK12-PEDCO-110-GT-RT-0001 | BK | BK12 | PEDCO | 110 | GT | RT | 0001 | F0Z-708309 | IFI | IFC | 2022-06-29 | 2022-06-25 | 2022-06-25 | -4 | 0 | -4 | IFA | 2022-11-19 | 0 | 0 | -44884 | 0 | -44884 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-15 |  |  | D01 | IFA | T-1572 | 44870 | 1401/08/14 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-06081 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK12-PEDCO-110-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1081 | 2022-06-15 | 1401/03/25 |  |  |  | BK-SUR-ENG-CIV-01-04721 | 44727 | 1401/03/25 | RJ-C4 |  | BK-SUR-ENG-CIV-01-04901 | 44738 | 1401/04/06 | CM-C3 |  | 1401-2294-123165 | 2022-06-25 | 1401/04/08 | 44737 | 1401/04/08 | CM | [10 empty] | D01 | IFA | T-1572 | 44870 | 1401/08/14 |  |  |  | BK-SUR-ENG-CIV-01-06081 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-GT-RT-0001_D00 | [11 empty] | NISOC-CRS-BK-BK12-PEDCO-110-GT-RT-0001_D00
2 | 9 | 1 | 8 | 0 | 2 | 0 | 2.9.1.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 1 | 8 | 0 | 2 | 1 | 2.9.1.8.2.1 | BK-BK12-PEDCO-110-SU-DW-0001 | Over Head Line Plan and Profile - BK12 |  | BK-BK12-PEDCO-110-SU-DW-0001 | BK-BK12-PEDCO-110-SU-DW-0001 | BK | BK12 | PEDCO | 110 | SU | DW | 0001 | F4A-708310 | AFC | IFC | 2022-05-30 | 2022-07-27 | 2022-07-30 | 58 | 3 | 61 | IFA | 2022-09-18 | 2022-09-19 | 2022-09-20 | 1 | 1 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-16 |  |  | D01 | IFA | T-1354 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05691 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-SU-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-229302 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0962 | 2022-05-16 | 1401/02/26 | T-0962 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04476 | 44710 | 1401/03/08 | CM-C3 | [6 empty] | 1401-2294-156807 | 2022-07-27 | 1401/05/05 | 44772 | 1401/05/08 | CM | [10 empty] | D01 | IFA | T-1354 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-ELE-01-05691 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-SU-DW-0001_D00 | [5 empty] | 1401-2294-229302 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D01
2 | 9 | 2 | 0 | 0 | 0 | 0 | 2.9.2 |  | Procurement Engineering
2 | 9 | 2 | 1 | 0 | 0 | 0 | 2.9.2.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 1 | 1 | 0 | 0 | 2.9.2.1.1 |  | Pipe
2 | 9 | 2 | 1 | 1 | 1 | 0 | 2.9.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 1 | 1 | 1 | 1 | 2.9.2.1.1.1.1 | BK-BK12-PEDCO-110-PI-MR-0001 | PMR For Pipes - BK12 |  | BK-BK12-PEDCO-110-PI-MR-0001 | BK-BK12-PEDCO-110-PI-MR-0001 | BK | BK12 | PEDCO | 110 | PI | MR | 0001 | F0Z-708311 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFI | T-1544 | 44859 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1544 | 2022-10-25 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2
2 | 9 | 2 | 1 | 1 | 2 | 0 | 2.9.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 1 | 1 | 2 | 1 | 2.9.2.1.1.2.1 | BK-BK12-PEDCO-110-PI-TB-0001 | TBE For Pipes - BK12 |  | BK-BK12-PEDCO-110-PI-TB-0001 | BK-BK12-PEDCO-110-PI-TB-0001 | BK | BK12 | PEDCO | 110 | PI | TB | 0001 | F0Z-708312 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 1 | 2 | 0 | 0 | 2.9.2.1.2 |  | Pipe Support
2 | 9 | 2 | 1 | 2 | 1 | 0 | 2.9.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 1 | 2 | 1 | 1 | 2.9.2.1.2.1.1 | BK-BK12-PEDCO-110-PI-MR-0002 | PMR For Pipe Support - BK12 |  | BK-BK12-PEDCO-110-PI-MR-0002 | BK-BK12-PEDCO-110-PI-MR-0002 | BK | BK12 | PEDCO | 110 | PI | MR | 0002 | F0Z-708313 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 1 | 2 | 2 | 0 | 2.9.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 1 | 2 | 2 | 1 | 2.9.2.1.2.2.1 | BK-BK12-PEDCO-110-PI-TB-0002 | TBE For Pipe Support - BK12 |  | BK-BK12-PEDCO-110-PI-TB-0002 | BK-BK12-PEDCO-110-PI-TB-0002 | BK | BK12 | PEDCO | 110 | PI | TB | 0002 | F0Z-708314 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 2 | 0 | 0 | 0 | 2.9.2.2 |  | HVAC
2 | 9 | 2 | 2 | 1 | 0 | 0 | 2.9.2.2.1 |  | Main HVAC Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 2 | 1 | 1 | 0 | 2.9.2.1.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 2 | 1 | 1 | 1 | 2.9.2.2.1.1.1 | BK-BK12-PEDCO-110-HV-MR-0001 | PMR For Main HVAC Equipment - BK12 |  | BK-BK12-PEDCO-110-HV-MR-0001 | BK-BK12-PEDCO-110-HV-MR-0001 | BK | BK12 | PEDCO | 110 | HV | MR | 0001 | F0Z-708315 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 2 | 1 | 2 | 0 | 2.9.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 2 | 1 | 2 | 1 | 2.9.2.2.1.2.1 | BK-BK12-PEDCO-110-HV-TB-0001 | TBE For Main HVAC Equipment - BK12 |  | BK-BK12-PEDCO-110-HV-TB-0001 | BK-BK12-PEDCO-110-HV-TB-0001 | BK | BK12 | PEDCO | 110 | HV | TB | 0001 | F0Z-708316 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 0 | 0 | 0 | 2.9.2.3 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 1 | 0 | 0 | 2.9.2.3.1 |  | Transformers
2 | 9 | 2 | 3 | 1 | 1 | 0 | 2.9.3.1.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 1 | 1 | 1 | 2.9.2.3.1.1.1 | BK-BK12-PEDCO-110-EL-MR-0001 | PMR For Transformers - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0001 | BK-BK12-PEDCO-110-EL-MR-0001 | BK | BK12 | PEDCO | 110 | EL | MR | 0001 | F0Z-708317 | AFD | IFC | 2022-07-27 | 2022-08-09 | 2022-08-13 | 13 | 4 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-13 |  |  | D00 | IFC | T-1152 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05232 | 44767 | 1401/05/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171111 | 44782 | 1401/05/18 | 44786 | 1401/05/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1152 | 2022-07-13 | 1401/04/22 |  |  |  | BK-SUR-ENG-ELE-01-05232 | 44767 | 1401/05/03 | CM-C3 | [6 empty] | 1401-2294-171111 | 2022-08-09 | 1401/05/18 | 44786 | 1401/05/22 | CM
2 | 9 | 2 | 3 | 1 | 2 | 0 | 2.9.3.1.2 |  | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 1 | 2 | 1 | 2.9.2.3.1.2.1 | BK-BK12-PEDCO-110-EL-TB-0001 | TBE For Transformers - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0001 | BK-BK12-PEDCO-110-EL-TB-0001 | BK | BK12 | PEDCO | 110 | EL | TB | 0001 | F0Z-708318 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 2 | 0 | 0 | 2.9.2.3.2 |  | LV Switchgear & MCC
2 | 9 | 2 | 3 | 2 | 1 | 0 | 2.9.3.2.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 2 | 1 | 1 | 2.9.2.3.2.1.1 | BK-BK12-PEDCO-110-EL-MR-0002 | PMR For LV Switchgear & MCC - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0002 | BK-BK12-PEDCO-110-EL-MR-0002 | BK | BK12 | PEDCO | 110 | EL | MR | 0002 | F0Z-708319 | IFI | IFI | 2022-09-25 | 2022-10-05 | 2022-10-08 | 10 | 3 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-11 |  |  | D00 | IFI | T-1393 | 44815 | 1401/06/20 | T-1393 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05759 | 44828 | 1401/07/02 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249409 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1393 | 2022-09-11 | 1401/06/20 | T-1393 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05759 | 44828 | 1401/07/02 | CM-C2 | [6 empty] | 1401-2294-249409 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 9 | 2 | 3 | 2 | 2 | 0 | 2.9.3.2.2 |  | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 2 | 2 | 1 | 2.9.2.3.2.2.1 | BK-BK12-PEDCO-110-EL-TB-0002 | TBE For LV Switchgear & MCC - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0002 | BK-BK12-PEDCO-110-EL-TB-0002 | BK | BK12 | PEDCO | 110 | EL | TB | 0002 | F0Z-708320 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 3 | 0 | 0 | 2.9.2.3.3 |  | Emergency Diesel Generator
2 | 9 | 2 | 3 | 3 | 1 | 0 | 2.9.3.3.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 3 | 1 | 1 | 2.9.2.3.3.1.1 | BK-BK12-PEDCO-110-EL-MR-0003 | PMR For Emergency Diesel Generator - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0003 | BK-BK12-PEDCO-110-EL-MR-0003 | BK | BK12 | PEDCO | 110 | EL | MR | 0003 | F0Z-708321 | IFI | IFI | 2022-09-03 | 2022-09-08 | 2022-09-12 | 5 | 4 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-20 |  |  | D00 | IFI | T-1293 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216140 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1293 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | [6 empty] | 1401-2294-216140 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | AP
2 | 9 | 2 | 3 | 3 | 2 | 0 | 2.9.3.3.2 |  | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 3 | 2 | 1 | 2.9.2.3.3.2.1 | BK-BK12-PEDCO-110-EL-TB-0003 | TBE For Emergency Diesel Generator - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0003 | BK-BK12-PEDCO-110-EL-TB-0003 | BK | BK12 | PEDCO | 110 | EL | TB | 0003 | F0Z-708322 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 4 | 0 | 0 | 2.9.2.3.4 |  | UPS System
2 | 9 | 2 | 3 | 4 | 1 | 0 | 2.9.3.4.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 4 | 1 | 1 | 2.9.2.3.4.1.1 | BK-BK12-PEDCO-110-EL-MR-0004 | PMR For UPS System - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0004 | BK-BK12-PEDCO-110-EL-MR-0004 | BK | BK12 | PEDCO | 110 | EL | MR | 0004 | F0Z-708323 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 4 | 2 | 0 | 2.9.3.4.2 |  | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 4 | 2 | 1 | 2.9.2.3.4.2.1 | BK-BK12-PEDCO-110-EL-TB-0004 | TBE For UPS System - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0004 | BK-BK12-PEDCO-110-EL-TB-0004 | BK | BK12 | PEDCO | 110 | EL | TB | 0004 | F0Z-708324 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 5 | 0 | 0 | 2.9.2.3.5 |  | DC Charger
2 | 9 | 2 | 3 | 5 | 1 | 0 | 2.9.3.5.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 5 | 1 | 1 | 2.9.2.3.5.1.1 | BK-BK12-PEDCO-110-EL-MR-0005 | PMR For DC Charger - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0005 | BK-BK12-PEDCO-110-EL-MR-0005 | BK | BK12 | PEDCO | 110 | EL | MR | 0005 | F0Z-708325 | IFI | IFI | 2022-05-10 | 2022-05-29 | 2022-05-30 | 19 | 1 | 20 | IFI | 2022-09-07 | 2022-09-08 | 2022-09-12 | 1 | 4 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-26 |  |  | D01 | IFI | T-1311 | 44797 | 1401/06/01 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-BK12-PEDCO-110-EL-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-BK12-PEDCO-110-EL-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0864 | 2022-04-26 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04211 | 44691 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78867 | 2022-05-29 | 1401/03/08 | 44711 | 1401/03/09 | CM | [10 empty] | D01 | IFI | T-1311 | 44797 | 1401/06/01 |  |  |  | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-BK12-PEDCO-110-EL-MR-0005_D00 | [5 empty] | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-BK12-PEDCO-110-EL-MR-0005_D00
2 | 9 | 2 | 3 | 5 | 2 | 0 | 2.9.3.5.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 5 | 2 | 1 | 2.9.2.3.5.2.1 | BK-BK12-PEDCO-110-EL-TB-0005 | TBE For DC Charger - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0005 | BK-BK12-PEDCO-110-EL-TB-0005 | BK | BK12 | PEDCO | 110 | EL | TB | 0005 | F0Z-708326 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 6 | 0 | 0 | 2.9.2.3.6 |  | Capacitor Bank | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 6 | 1 | 0 | 2.9.3.6.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 6 | 1 | 1 | 2.9.2.3.6.1.1 | BK-BK12-PEDCO-110-EL-MR-0006 | PMR For Capacitor Bank - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0006 | BK-BK12-PEDCO-110-EL-MR-0006 | BK | BK12 | PEDCO | 110 | EL | MR | 0006 | F0Z-708327 | IFI | IFI | 2022-08-13 | 2022-08-18 | 2022-08-20 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFI | T-1215 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183488 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1215 | 2022-07-30 | 1401/05/08 |  |  |  | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | [6 empty] | 1401-2294-183488 | 2022-08-18 | 1401/05/27 | 44793 | 1401/05/29 | RJ
2 | 9 | 2 | 3 | 6 | 2 | 0 | 2.9.3.6.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 6 | 2 | 1 | 2.9.2.3.6.2.1 | BK-BK12-PEDCO-110-EL-TB-0006 | TBE For Capacitor Bank - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0006 | BK-BK12-PEDCO-110-EL-TB-0006 | BK | BK12 | PEDCO | 110 | EL | TB | 0006 | F0Z-708328 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 7 | 0 | 0 | 2.9.2.3.7 |  | Lighting & Distribution Main Panels | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 7 | 1 | 0 | 2.9.3.7.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 7 | 1 | 1 | 2.9.2.3.7.1.1 | BK-BK12-PEDCO-110-EL-MR-0007 | PMR For Lighting & Distribution Main Panels - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0007 | BK-BK12-PEDCO-110-EL-MR-0007 | BK | BK12 | PEDCO | 110 | EL | MR | 0007 | F0Z-708329 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 7 | 2 | 0 | 2.9.3.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 7 | 2 | 1 | 2.9.2.3.7.2.1 | BK-BK12-PEDCO-110-EL-TB-0007 | TBE For Lighting & Distribution Main Panels - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0007 | BK-BK12-PEDCO-110-EL-TB-0007 | BK | BK12 | PEDCO | 110 | EL | TB | 0007 | F0Z-708330 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 8 | 0 | 0 | 2.9.2.3.8 |  | Earthing & Lightning System | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 8 | 1 | 0 | 2.9.3.8.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 8 | 1 | 1 | 2.9.2.3.8.1.1 | BK-BK12-PEDCO-110-EL-MR-0008 | PMR For Earthing & Lightning System - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0008 | BK-BK12-PEDCO-110-EL-MR-0008 | BK | BK12 | PEDCO | 110 | EL | MR | 0008 | F0Z-708331 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 8 | 2 | 0 | 2.9.3.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 8 | 2 | 1 | 2.9.2.3.8.2.1 | BK-BK12-PEDCO-110-EL-TB-0008 | TBE For Earthing & Lightning System - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0008 | BK-BK12-PEDCO-110-EL-TB-0008 | BK | BK12 | PEDCO | 110 | EL | TB | 0008 | F0Z-708332 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 9 | 0 | 0 | 2.9.2.3.9 |  | Lighting and Small Power Equipment
2 | 9 | 2 | 3 | 9 | 1 | 0 | 2.9.3.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 9 | 1 | 1 | 2.9.2.3.9.1.1 | BK-BK12-PEDCO-110-EL-MR-0009 | PMR For Lighting and Small Power Equipment - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0009 | BK-BK12-PEDCO-110-EL-MR-0009 | BK | BK12 | PEDCO | 110 | EL | MR | 0009 | F0Z-708333 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 9 | 2 | 0 | 2.9.3.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 9 | 2 | 1 | 2.9.2.3.9.2.1 | BK-BK12-PEDCO-110-EL-TB-0009 | TBE For Lighting and Small Power Equipment - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0009 | BK-BK12-PEDCO-110-EL-TB-0009 | BK | BK12 | PEDCO | 110 | EL | TB | 0009 | F0Z-708334 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 10 | 0 | 0 | 2.9.2.3.10 |  | Tray/Ladder and Accessories
2 | 9 | 2 | 3 | 10 | 1 | 0 | 2.9.3.10.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 10 | 1 | 1 | 2.9.2.3.10.1.1 | BK-BK12-PEDCO-110-EL-MR-0010 | PMR For Tray/Ladder and Accessories - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0010 | BK-BK12-PEDCO-110-EL-MR-0010 | BK | BK12 | PEDCO | 110 | EL | MR | 0010 | F0Z-708335 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 10 | 2 | 0 | 2.9.3.10.2 |  | Technical Bid Evaluation (TBE) | [61 empty] | Moved to Field
2 | 9 | 2 | 3 | 10 | 2 | 1 | 2.9.2.3.10.2.1 | BK-BK12-PEDCO-110-EL-TB-0010 | TBE For Tray/Ladder and Accessories - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0010 | BK-BK12-PEDCO-110-EL-TB-0010 | BK | BK12 | PEDCO | 110 | EL | TB | 0010 | F0Z-708336 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 11 | 0 | 0 | 2.9.2.3.11 |  | Power & Control Cables
2 | 9 | 2 | 3 | 11 | 1 | 0 | 2.9.3.11.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 11 | 1 | 1 | 2.9.2.3.11.1.1 | BK-BK12-PEDCO-110-EL-MR-0011 | PMR For Power & Control Cables - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0011 | BK-BK12-PEDCO-110-EL-MR-0011 | BK | BK12 | PEDCO | 110 | EL | MR | 0011 | F0Z-708337 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 3 | 11 | 2 | 0 | 2.9.3.11.2 |  | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 11 | 2 | 1 | 2.9.2.3.11.2.1 | BK-BK12-PEDCO-110-EL-TB-0011 | TBE For Power & Control Cables - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0011 | BK-BK12-PEDCO-110-EL-TB-0011 | BK | BK12 | PEDCO | 110 | EL | TB | 0011 | F0Z-708338 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 12 | 0 | 0 | 2.9.2.3.12 |  | Electrical Bulk Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 12 | 1 | 0 | 2.9.3.12.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 12 | 1 | 1 | 2.9.2.3.12.1.1 | BK-BK12-PEDCO-110-EL-MR-0012 | PMR For Electrical Bulk Items - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0012 | BK-BK12-PEDCO-110-EL-MR-0012 | BK | BK12 | PEDCO | 110 | EL | MR | 0012 | F0Z-708339 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 12 | 2 | 0 | 2.9.3.12.2 |  | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 12 | 2 | 1 | 2.9.2.3.12.2.1 | BK-BK12-PEDCO-110-EL-TB-0012 | TBE For Electrical Bulk Items - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0012 | BK-BK12-PEDCO-110-EL-TB-0012 | BK | BK12 | PEDCO | 110 | EL | TB | 0012 | F0Z-708340 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 13 | 0 | 0 | 2.9.2.3.13 |  | Transmission Over head Line
2 | 9 | 2 | 3 | 13 | 1 | 0 | 2.9.3.13.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 13 | 1 | 1 | 2.9.2.3.13.1.1 | BK-BK12-PEDCO-110-EL-MR-0013 | PMR For Transmission Over head Line - BK12 |  | BK-BK12-PEDCO-110-EL-MR-0013 | BK-BK12-PEDCO-110-EL-MR-0013 | BK | BK12 | PEDCO | 110 | EL | MR | 0013 | F0Z-708341 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 3 | 13 | 2 | 0 | 2.9.3.13.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 3 | 13 | 2 | 1 | 2.9.2.3.13.2.1 | BK-BK12-PEDCO-110-EL-TB-0013 | TBE For Transmission Over head Line - BK12 |  | BK-BK12-PEDCO-110-EL-TB-0013 | BK-BK12-PEDCO-110-EL-TB-0013 | BK | BK12 | PEDCO | 110 | EL | TB | 0013 | F0Z-708342 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 4 | 0 | 0 | 0 | 2.9.2.4 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 4 | 1 | 0 | 0 | 2.9.2.4.1 |  | Steel Structure Items
2 | 9 | 2 | 4 | 1 | 1 | 0 | 2.9.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 4 | 1 | 1 | 1 | 2.9.2.4.1.1.1 | BK-BK12-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - BK12 |  | BK-BK12-PEDCO-110-ST-MR-0001 | BK-BK12-PEDCO-110-ST-MR-0001 | BK | BK12 | PEDCO | 110 | ST | MR | 0001 | F0Z-708343 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 4 | 1 | 2 | 0 | 2.9.4.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 4 | 1 | 2 | 1 | 2.9.2.4.1.2.1 | BK-BK12-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - BK12 |  | BK-BK12-PEDCO-110-ST-TB-0001 | BK-BK12-PEDCO-110-ST-TB-0001 | BK | BK12 | PEDCO | 110 | ST | TB | 0001 | F0Z-708344 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 4 | 2 | 0 | 0 | 2.9.2.4.2 |  | Anchor Bolts
2 | 9 | 2 | 4 | 2 | 1 | 0 | 2.9.4.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 4 | 2 | 1 | 1 | 2.9.2.4.2.1.1 | BK-BK12-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - BK12 |  | BK-BK12-PEDCO-110-ST-MR-0002 | BK-BK12-PEDCO-110-ST-MR-0002 | BK | BK12 | PEDCO | 110 | ST | MR | 0002 | F0Z-708345 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 2 | 4 | 2 | 2 | 0 | 2.9.4.2.2 |  | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 4 | 2 | 2 | 1 | 2.9.2.4.2.2.1 | BK-BK12-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - BK12 |  | BK-BK12-PEDCO-110-ST-TB-0002 | BK-BK12-PEDCO-110-ST-TB-0002 | BK | BK12 | PEDCO | 110 | ST | TB | 0002 | F0Z-708346 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 4 | 3 | 0 | 0 | 2.9.2.4.3 |  | Blast Proof Doors
2 | 9 | 2 | 4 | 3 | 1 | 0 | 2.9.4.3.1 |  | Purchase Material Requisition (PMR)
2 | 9 | 2 | 4 | 3 | 1 | 1 | 2.9.2.4.3.1.1 | BK-BK12-PEDCO-110-ST-MR-0003 | PMR For Blast Proof Doors - BK12 |  | BK-BK12-PEDCO-110-ST-MR-0003 | BK-BK12-PEDCO-110-ST-MR-0003 | BK | BK12 | PEDCO | 110 | ST | MR | 0003 | F0Z-708347 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 2 | 4 | 3 | 2 | 0 | 2.9.4.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 2 | 4 | 3 | 2 | 1 | 2.9.2.4.3.2.1 | BK-BK12-PEDCO-110-ST-TB-0003 | TBE For Blast Proof Doors - BK12 |  | BK-BK12-PEDCO-110-ST-TB-0003 | BK-BK12-PEDCO-110-ST-TB-0003 | BK | BK12 | PEDCO | 110 | ST | TB | 0003 | F0Z-708348 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 3 | 0 | 0 | 0 | 0 | 2.9.3 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 3 | 0 | 0 | 1 | 0 | 2.9.3.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 3 | 0 | 0 | 1 | 1 | 2.9.3.1 | BK-BK12-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - BK12 |  | BK-BK12-PEDCO-110-CO-PR-0001 | BK-BK12-PEDCO-110-CO-PR-0001 | BK | BK12 | PEDCO | 110 | CO | PR | 0001 | F0Z-708349 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 3 | 0 | 1 | 0 | 0 | 2.9.3.1 |  | Field Engineering
2 | 9 | 3 | 0 | 1 | 1 | 0 | 2.9.3.1 |  | Query
2 | 9 | 3 | 0 | 1 | 1 | 1 | 2.9.3.1.1.1 | BK-BK12-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-BK12-PEDCO-110-GE-TQ-0001 | BK-BK12-PEDCO-110-GE-TQ-0001 | BK | BK12 | PEDCO | 110 | GE | TQ | 0001 | F7Z-708350 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 3 | 0 | 1 | 2 | 0 | 2.9.3.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 3 | 0 | 1 | 2 | 1 | 2.9.3.1.2.1 | BK-BK12-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - BK12 |  | BK-BK12-PEDCO-110-GE-DO-0001 | BK-BK12-PEDCO-110-GE-DO-0001 | BK | BK12 | PEDCO | 110 | GE | DO | 0001 | F0Z-708351 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 4 | 0 | 0 | 0 | 0 | 2.9.4 |  | Engineering Final Documentation
2 | 9 | 4 | 0 | 0 | 1 | 0 | 2.9.4.1 |  | Manual | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 9 | 4 | 0 | 0 | 1 | 1 | 2.9.4.1 | BK-BK12-PEDCO-110-GE-ML-0001 | Operating Manual - BK12 |  | BK-BK12-PEDCO-110-GE-ML-0001 | BK-BK12-PEDCO-110-GE-ML-0001 | BK | BK12 | PEDCO | 110 | GE | ML | 0001 | F0Z-708352 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 9 | 4 | 0 | 0 | 2 | 0 | 2.9.4.2 |  | Dossier
2 | 9 | 4 | 0 | 0 | 2 | 1 | 2.9.4.2 | BK-BK12-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - BK12 |  | BK-BK12-PEDCO-110-GE-DO-0001 | [8 empty] | F0Z-708351 |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 9 | 4 | 0 | 0 | 2 | 2 | 2.9.4.2 | BK-BK12-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - BK12 |  | BK-BK12-PEDCO-110-GE-DO-0002 | BK-BK12-PEDCO-110-GE-DO-0002 | BK | BK12 | PEDCO | 110 | GE | DO | 0002 | F0Z-708353 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 0 | 0 | 0 | 0 | 0 | 2.10 |  | Package 09-Workover # 15 | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 0 | 0 | 0 | 0 | 2.10.1 |  | Detail Design
2 | 10 | 1 | 1 | 0 | 0 | 0 | 2.10.1.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 1 | 1 | 0 | 0 | 2.10.1.1.1 |  | Drawing/Diagram
2 | 10 | 1 | 1 | 1 | 0 | 1 | 2.10.1.1.1.1 | BK-BK15-PEDCO-110-PR-PI-0001 | P&ID for Diesel Oil Drum- BK15 |  | BK-BK15-PEDCO-110-PR-PI-0001 | [8 empty] | F2A-708354 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-10-18 | 2022-10-12 | 177 | -6 | 171 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-15 |  |  | D03 | IFA | T-0794 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-402841 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | AP | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0649 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 44634 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0794 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D02
2 | 10 | 1 | 1 | 1 | 0 | 2 | 2.10.1.1.1.2 | BK-BK15-PEDCO-110-PR-PI-0002 | P&ID for Potable Water Tank - BK15 |  | BK-BK15-PEDCO-110-PR-PI-0002 | [8 empty] | F2A-708355 | AFC | [50 empty] | 2021-11-15 |  |  | D03 | IFA | T-0794 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | RJ | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-402841 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | AP | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0649 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 44634 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0794 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-255980 | 44852 | 1401/07/18 | 44846 | 1401/07/20 | RJ | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D02
2 | 10 | 1 | 1 | 2 | 0 | 0 | 2.10.1.1.2 |  | List
2 | 10 | 1 | 1 | 2 | 0 | 1 | 2.10.1.1.2.1 | BK-BK15-PEDCO-110-PR-LI-0001 | Line List - BK15 |  | BK-BK15-PEDCO-110-PR-LI-0001 | [8 empty] | F0Z-708356 | AFC | IFC | 2022-03-13 | 2022-03-12 | 2022-03-15 | -1 | 3 | 2 | IFA | 2022-05-14 | 2022-05-31 | 2022-05-06 | 17 | -25 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-27 |  |  | D01 | IFA | T-0877 | 44681 | 1401/02/10 | T-0877 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-83257 | 44712 | 1401/03/10 | 44687 | 1401/03/16 | CM | NISOC-CRS-BK-BK15-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0650 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03597 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445283 | 2022-03-12 | 1400/12/21 | 44635 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0877 | 44681 | 1401/02/10 | T-0877 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1401-2294-83257 | 44712 | 1401/03/10 | 44687 | 1401/03/16 | CM | NISOC-CRS-BK-BK15-PEDCO-110-PR-LI-0001_D00
2 | 10 | 1 | 1 | 3 | 0 | 0 | 2.10.1.1.3 |  | Data Sheet | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 1 | 3 | 0 | 1 | 2.10.1.1.3.1 | BK-BK15-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - BK15 |  | BK-BK15-PEDCO-110-PR-DT-0001 | [8 empty] | F0Z-708357 | AFC | IFC | 2022-04-26 | 2022-05-14 | 2022-05-16 | 18 | 2 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-12 |  |  | D00 | IFC | T-0807 | 44663 | 1401/01/12 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03991 | 44670 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52773 | 44695 | 1401/02/24 | 44697 | 1401/02/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 44670 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 44697 | 1401/02/26 | AP
2 | 10 | 1 | 2 | 0 | 0 | 0 | 2.10.1.2 |  | HVAC/Plumbing | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 2 | 1 | 0 | 0 | 2.10.1.2.1 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 2 | 1 | 0 | 1 | 2.10.1.2.1.1 | BK-BK15-PEDCO-110-HV-CN-0001 | HVAC Calculation Note For Switchgear Building - BK15 |  | BK-BK15-PEDCO-110-HV-CN-0001 | BK-BK15-PEDCO-110-HV-CN-0001 | BK | BK15 | PEDCO | 110 | HV | CN | 0001 | F0Z-708358 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 1 | 2 | 1 | 0 | 2 | 2.10.1.2.1.2 | BK-BK15-PEDCO-110-HV-CN-0002 | HVAC Calculation Note For Security Building - BK15 |  | BK-BK15-PEDCO-110-HV-CN-0002 | BK-BK15-PEDCO-110-HV-CN-0002 | BK | BK15 | PEDCO | 110 | HV | CN | 0002 | F0Z-708359 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 1 | 2 | 2 | 0 | 0 | 2.10.1.2.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 2 | 2 | 0 | 1 | 2.10.1.2.2.1 | BK-BK15-PEDCO-110-HV-DT-0001 | Data Sheets For Main HVAC Equipment - BK15 |  | BK-BK15-PEDCO-110-HV-DT-0001 | BK-BK15-PEDCO-110-HV-DT-0001 | BK | BK15 | PEDCO | 110 | HV | DT | 0001 | F0Z-708360 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 2 | 3 | 0 | 0 | 2.10.1.2.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 2 | 3 | 0 | 1 | 2.10.1.2.3.1 | BK-BK15-PEDCO-110-HV-PY-0001 | HVAC System Layout For Switchgear Building - BK15 |  | BK-BK15-PEDCO-110-HV-PY-0001 | BK-BK15-PEDCO-110-HV-PY-0001 | BK | BK15 | PEDCO | 110 | HV | PY | 0001 | F4B-708361 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 2 | 3 | 0 | 2 | 2.10.1.2.3.2 | BK-BK15-PEDCO-110-HV-PY-0002 | HVAC System Layout For Security Building - BK15 |  | BK-BK15-PEDCO-110-HV-PY-0002 | BK-BK15-PEDCO-110-HV-PY-0002 | BK | BK15 | PEDCO | 110 | HV | PY | 0002 | F4B-708362 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 2 | 3 | 0 | 3 | 2.10.1.2.3.3 | BK-BK15-PEDCO-110-HV-PY-0003 | Plumbing & Sewage Piping Layout For Switchgear Building - BK15 |  | BK-BK15-PEDCO-110-HV-PY-0003 | BK-BK15-PEDCO-110-HV-PY-0003 | BK | BK15 | PEDCO | 110 | HV | PY | 0003 | F4B-708363 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 1 | 2 | 3 | 0 | 4 | 2.10.1.2.3.4 | BK-BK15-PEDCO-110-HV-PY-0004 | Plumbing & Sewage Piping Layout For Security Building - BK15 |  | BK-BK15-PEDCO-110-HV-PY-0004 | BK-BK15-PEDCO-110-HV-PY-0004 | BK | BK15 | PEDCO | 110 | HV | PY | 0004 | F4B-708364 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 2 | 4 | 0 | 0 | 2.10.1.2.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 2 | 4 | 0 | 1 | 2.10.1.2.4.1 | BK-BK15-PEDCO-110-HV-MT-0001 | MTO For Building HVAC & Plumbing Systems - BK15 |  | BK-BK15-PEDCO-110-HV-MT-0001 | BK-BK15-PEDCO-110-HV-MT-0001 | BK | BK15 | PEDCO | 110 | HV | MT | 0001 | F8Z-708365 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 3 | 0 | 0 | 0 | 2.10.1.3 |  | Piping
2 | 10 | 1 | 3 | 1 | 0 | 0 | 2.10.1.3.1 |  | Drawing/Diagram
2 | 10 | 1 | 3 | 1 | 0 | 1 | 2.10.1.3.1.1 | BK-BK15-PEDCO-110-PI-MT-0001 | Plot Plan Drawing – BK15 |  | BK-BK15-PEDCO-110-PI- PY -0001 | BK-BK15-PEDCO-110-PI-MT-0001 | BK | BK15 | PEDCO | 110 | PI | MT | 0001 | F8Z-708366 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14
2 | 10 | 1 | 3 | 1 | 0 | 0 | 2.10.1.3.1 |  | MTO
2 | 10 | 1 | 3 | 1 | 0 | 1 | 2.10.1.3.1.1 | BK-BK15-PEDCO-110-PI-MT-0001 | MTO For Pipes - BK15 |  | BK-BK15-PEDCO-110-PI-MT-0001 | BK-BK15-PEDCO-110-PI-MT-0001 | BK | BK15 | PEDCO | 110 | PI | MT | 0001 | F8Z-708366 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFI | T-1545 | 44859 | 1401/08/03 | T-1545 | 44859 | 1401/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1545 | 2022-10-25 | 1401/08/03 | T-1545 | 44859 | 1401/08/03
2 | 10 | 1 | 4 | 0 | 0 | 0 | 2.10.1.4 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 4 | 1 | 0 | 0 | 2.10.1.4.1 |  | MTO
2 | 10 | 1 | 4 | 1 | 0 | 1 | 2.10.1.4.1.1 | BK-BK15-PEDCO-110-EL-MT-0001 | MTO For Transmission Over Head Line - BK15 |  | BK-BK15-PEDCO-110-EL-MT-0001 | BK-BK15-PEDCO-110-EL-MT-0001 | BK | BK15 | PEDCO | 110 | EL | MT | 0001 | F8Z-708367 | IFI | IFI | 2022-10-03 | 2022-09-29 | 2022-10-08 | -4 | 9 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-19 |  |  | D00 | IFI | T-1417 | 44823 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249371 | 44833 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1417 | 2022-09-19 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | [6 empty] | 1401-2294-249371 | 2022-09-29 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 10 | 1 | 4 | 1 | 0 | 2 | 2.10.1.4.1.2 | BK-BK15-PEDCO-110-EL-MT-0002 | MTO For Lighting & Small Powers - BK15 |  | BK-BK15-PEDCO-110-EL-MT-0002 | BK-BK15-PEDCO-110-EL-MT-0002 | BK | BK15 | PEDCO | 110 | EL | MT | 0002 | F8Z-708368 | IFI | IFI | 2022-06-01 | 2022-06-10 | 2022-06-12 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-18 |  |  | D00 | IFI | T-0969 | 44699 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94633 | 44722 | 1401/03/20 | 44724 | 1401/03/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | [6 empty] | 1401-2294-94633 | 2022-06-10 | 1401/03/20 | 44724 | 1401/03/22 | CM
2 | 10 | 1 | 4 | 1 | 0 | 3 | 2.10.1.4.1.3 | BK-BK15-PEDCO-110-EL-MT-0003 | MTO For Power & Control Cables - BK15 |  | BK-BK15-PEDCO-110-EL-MT-0003 | BK-BK15-PEDCO-110-EL-MT-0003 | BK | BK15 | PEDCO | 110 | EL | MT | 0003 | F8Z-708369 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 4 | 1 | 0 | 4 | 2.10.1.4.1.4 | BK-BK15-PEDCO-110-EL-MT-0004 | MTO For Tray/Ladder and Accessories - BK15 |  | BK-BK15-PEDCO-110-EL-MT-0004 | BK-BK15-PEDCO-110-EL-MT-0004 | BK | BK15 | PEDCO | 110 | EL | MT | 0004 | F8Z-708370 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 1 | 4 | 1 | 0 | 5 | 2.10.1.4.1.5 | BK-BK15-PEDCO-110-EL-MT-0005 | MTO For Electrical Bulk Items - BK15 |  | BK-BK15-PEDCO-110-EL-MT-0005 | BK-BK15-PEDCO-110-EL-MT-0005 | BK | BK15 | PEDCO | 110 | EL | MT | 0005 | F8Z-708371 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 4 | 1 | 0 | 6 | 2.10.1.4.1.6 | BK-BK15-PEDCO-110-EL-MT-0006 | MTO For Earthing & Lightning Systems - BK15 |  | BK-BK15-PEDCO-110-EL-MT-0006 | BK-BK15-PEDCO-110-EL-MT-0006 | BK | BK15 | PEDCO | 110 | EL | MT | 0006 | F8Z-708372 | IFI | IFI | 2022-10-25 | 2022-11-10 | 2022-11-14 | 16 | 4 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-11 |  |  | D00 | IFI | T-1480 | 44845 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-304880 | 44875 | 1401/08/19 | 44879 | 1401/08/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1480 | 2022-10-11 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | [6 empty] | 1401-2294-304880 | 2022-11-10 | 1401/08/19 | 44879 | 1401/08/23 | CM
2 | 10 | 1 | 5 | 0 | 0 | 0 | 2.10.1.5 |  | Architecture
2 | 10 | 1 | 5 | 1 | 0 | 0 | 2.10.1.5.1 |  | Drawing/Diagram
2 | 10 | 1 | 5 | 1 | 0 | 1 | 2.10.1.5.1.1 | BK-BK15-PEDCO-110-AR-DW-0001 | Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-15 |  | BK-BK15-PEDCO-110-AR-DW-0001 | BK-BK15-PEDCO-110-AR-DW-0001 | BK | BK15 | PEDCO | 110 | AR | DW | 0001 | F4B-708373 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-01 |  |  | D00 | IFC | T-0885 | 44682 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 44697 | 1401/02/26 | CM
2 | 10 | 1 | 5 | 1 | 0 | 2 | 2.10.1.5.1.2 | BK-BK15-PEDCO-110-AR-DW-0002 | Architectural Drawing For Switchgear Building of Well Pads - BK-15 |  | BK-BK15-PEDCO-110-AR-DW-0002 | BK-BK15-PEDCO-110-AR-DW-0002 | BK | BK15 | PEDCO | 110 | AR | DW | 0002 | F4B-708374 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 2022-05-31 | 2022-06-07 | -1 | 7 | 6 | IFC | 2022-09-21 | 2022-10-11 | 2022-10-17 | 20 | 6 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D02 | IFC | T-1370 | 44811 | 1401/06/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ARC-00-03551 | 44634 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 44645 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 44699 | 1401/02/28 | T-0974 | 44702 | 1401/02/31 | BK-SUR-ENG-ARC-01-04416 | 44705 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D00 | [5 empty] | 1401-2294-85268 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | RJ | NISOC-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D00 | [9 empty] | D02 | IFC | T-1370 | 44811 | 1401/06/16 | [7 empty] | PEDCO-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D01 | [5 empty] | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D01
2 | 10 | 1 | 5 | 1 | 0 | 3 | 2.10.1.5.1.3 | BK-BK15-PEDCO-110-AR-DW-0003 | Architectural Drawing For Security Building of Well Pads - BK-15 |  | BK-BK15-PEDCO-110-AR-DW-0003 | BK-BK15-PEDCO-110-AR-DW-0003 | BK | BK15 | PEDCO | 110 | AR | DW | 0003 | F4B-708375 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-01 |  |  | D00 | IFC | T-0886 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 44695 | 1401/02/21 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 44697 | 1401/02/26 | CM
2 | 10 | 1 | 5 | 2 | 0 | 0 | 2.10.1.5.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 5 | 2 | 0 | 1 | 2.10.1.5.2.1 | BK-BK15-PEDCO-110-AR-MT-0001 | MTO For Architectural Works - BK15 |  | BK-BK15-PEDCO-110-AR-MT-0001 | BK-BK15-PEDCO-110-AR-MT-0001 | BK | BK15 | PEDCO | 110 | AR | MT | 0001 | F8Z-708376 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 6 | 0 | 0 | 0 | 2.10.1.6 |  | Civil
2 | 10 | 1 | 6 | 1 | 0 | 0 | 2.10.1.6.1 |  | Drawing/Diagram
2 | 10 | 1 | 6 | 1 | 0 | 1 | 2.10.1.6.1.1 | BK-BK15-PEDCO-110-CV-DW-0001 | Civil and Structural drawings - BK15 |  | BK-BK15-PEDCO-110-CV-DW-0001 | BK-BK15-PEDCO-110-CV-DW-0001 | BK | BK15 | PEDCO | 110 | CV | DW | 0001 | F4S-708377 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 1 | 6 | 1 | 0 | 2 | 2.10.1.6.1.2 | BK-BK15-PEDCO-110-CV-PY-0001 | General Civil Layout - BK15 |  | BK-BK15-PEDCO-110-CV-PY-0001 | BK-BK15-PEDCO-110-CV-PY-0001 | BK | BK15 | PEDCO | 110 | CV | PY | 0001 | F4A-708378 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 6 | 1 | 0 | 3 | 2.10.1.6.1.3 | BK-BK15-PEDCO-110-CV-PY-0003 | Rough Grading Plans -BK15 |  | BK-BK15-PEDCO-110-CV-PY-0003 | BK-BK15-PEDCO-110-CV-PY-0003 | BK | BK15 | PEDCO | 110 | CV | PY | 0003 | F4S-708379 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 1 | 6 | 2 | 0 | 0 | 2.10.1.6.2 |  | Report
2 | 10 | 1 | 6 | 2 | 0 | 1 | 2.10.1.6.2.1 | BK-BK15-PEDCO-110-CV-RT-0001 | Site Visit Report (Civil Work) - BK15 |  | BK-BK15-PEDCO-110-CV-RT-0001 | BK-BK15-PEDCO-110-CV-RT-0001 | BK | BK15 | PEDCO | 110 | CV | RT | 0001 | F0Z-708380 | IFI | IFC | 2022-07-09 | 2022-07-05 | 2022-07-09 | -4 | 4 | 0 | IFI | 2022-08-15 | 2022-08-18 | 2022-08-27 | 3 | 9 | 12 | FI | 2022-11-08 | 2022-11-05 | 2022-11-06 | -3 | 1 | -2 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-25 | 2022-11-19 |  | D03 | FI | T-1593 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK15-PEDCO-110-CV-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1113 | 2022-06-25 | 1401/04/04 |  |  |  | BK-SUR-ENG-CIV-01-05039 | 44751 | 1401/04/18 | CM-C2 | [6 empty] | 1401-2294-130256 | 2022-07-05 | 1401/04/14 | 44751 | 1401/04/18 | CM | [10 empty] | D01 | IFI | T-1234 | 44774 | 1401/05/10 |  |  |  | BK-SUR-ENG-CIV-01-05381 | 44782 | 1401/05/18 | AP | PEDCO-CRS-BK-BK15-PEDCO-110-CV-RT-0001_D00 | [5 empty] | 1401-2294-183548 | 44791 | 1401/05/27 | 44800 | 1401/06/05 | AP | NISOC-CRS-BK-BK15-PEDCO-110-CV-RT-0001_D00 | [9 empty] | D02 | FI | T-1548 | 44859 | 1401/08/03 | T-1548 | 44859 | 1401/08/03 | BK-SUR-ENG-CIV-01-05968 | 44859 | 1401/08/03 | AP | [6 empty] | 1401-2294-296556 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | [10 empty] | D03 | FI | T-1593 | 44884 | 1401/08/28 | [19 empty] | NISOC-CRS-BK-BK15-PEDCO-110-CV-RT-0001_D02
2 | 10 | 1 | 6 | 3 | 0 | 0 | 2.10.1.6.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 6 | 3 | 0 | 1 | 2.10.1.6.3.1 | BK-BK15-PEDCO-110-CV-MT-0001 | MTO For Civil Works - BK15 |  | BK-BK15-PEDCO-110-CV-MT-0001 | BK-BK15-PEDCO-110-CV-MT-0001 | BK | BK15 | PEDCO | 110 | CV | MT | 0001 | F8Z-708381 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 7 | 0 | 0 | 0 | 2.10.1.7 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 7 | 1 | 0 | 0 | 2.10.1.7.1 |  | Drawing/Diagram
2 | 10 | 1 | 7 | 1 | 0 | 1 | 2.10.1.7.1.1 | BK-BK15-PEDCO-110-ST-DW-0001 | Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-15 |  | BK-BK15-PEDCO-110-ST-DW-0001 | BK-BK15-PEDCO-110-ST-DW-0001 | BK | BK15 | PEDCO | 110 | ST | DW | 0001 | F4G-708382 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 7 | 1 | 0 | 2 | 2.10.1.7.1.2 | BK-BK15-PEDCO-110-ST-DW-0002 | Foundation Drawing For Security Building For Well Pads - BK-15 |  | BK-BK15-PEDCO-110-ST-DW-0002 | BK-BK15-PEDCO-110-ST-DW-0002 | BK | BK15 | PEDCO | 110 | ST | DW | 0002 | F4Q-708383 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 1 | 7 | 1 | 0 | 3 | 2.10.1.7.1.3 | BK-BK15-PEDCO-110-ST-DW-0003 | Structural Drawing For Security Building For Well Pads - BK-15 |  | BK-BK15-PEDCO-110-ST-DW-0003 | BK-BK15-PEDCO-110-ST-DW-0003 | BK | BK15 | PEDCO | 110 | ST | DW | 0003 | F4M-708384 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 7 | 1 | 0 | 4 | 2.10.1.7.1.4 | BK-BK15-PEDCO-110-ST-DW-0004 | Foundation Drawing For Switchgear Building For Well Pads - BK-15 |  | BK-BK15-PEDCO-110-ST-DW-0004 | BK-BK15-PEDCO-110-ST-DW-0004 | BK | BK15 | PEDCO | 110 | ST | DW | 0004 | F4Q-708385 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 1 | 7 | 1 | 0 | 5 | 2.10.1.7.1.5 | BK-BK15-PEDCO-110-ST-DW-0005 | Structural Drawing For Switchgear Building For Well Pads - BK-15 |  | BK-BK15-PEDCO-110-ST-DW-0005 | BK-BK15-PEDCO-110-ST-DW-0005 | BK | BK15 | PEDCO | 110 | ST | DW | 0005 | F4M-708386 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 7 | 1 | 0 | 6 | 2.10.1.7.1.6 | BK-BK15-PEDCO-110-ST-DW-0006 | Foundation Drawing For Potable Water Tank For Well Pads - BK-15 |  | BK-BK15-PEDCO-110-ST-DW-0006 | BK-BK15-PEDCO-110-ST-DW-0006 | BK | BK15 | PEDCO | 110 | ST | DW | 0006 | F4Q-708387 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 7 | 1 | 0 | 7 | 2.10.1.7.1.7 | BK-BK15-PEDCO-110-ST-DW-0007 | Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-15 |  | BK-BK15-PEDCO-110-ST-DW-0007 | BK-BK15-PEDCO-110-ST-DW-0007 | BK | BK15 | PEDCO | 110 | ST | DW | 0007 | F4Q-708388 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 1 | 7 | 1 | 0 | 8 | 2.10.1.7.1.8 | BK-BK15-PEDCO-110-ST-DW-0008 | Structural Drawing For Diesel Generator Shelter For Well Pads - BK-15 |  | BK-BK15-PEDCO-110-ST-DW-0008 | BK-BK15-PEDCO-110-ST-DW-0008 | BK | BK15 | PEDCO | 110 | ST | DW | 0008 | F4M-708389 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 7 | 2 | 0 | 0 | 2.10.1.7.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 7 | 2 | 0 | 1 | 2.10.1.7.2.1 | BK-BK15-PEDCO-110-ST-MT-0001 | MTO For Structural Works - BK15 |  | BK-BK15-PEDCO-110-ST-MT-0001 | BK-BK15-PEDCO-110-ST-MT-0001 | BK | BK15 | PEDCO | 110 | ST | MT | 0001 | F8Z-708390 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 1 | 8 | 0 | 0 | 0 | 2.10.1.8 |  | Survey (Topography) & Geotechnic
2 | 10 | 1 | 8 | 0 | 1 | 0 | 2.10.1.1 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 8 | 0 | 1 | 1 | 2.10.1.8.1.1 | BK-BK15-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - BK15 |  | BK-BK15-PEDCO-110-GT-RT-0001 | BK-BK15-PEDCO-110-GT-RT-0001 | BK | BK15 | PEDCO | 110 | GT | RT | 0001 | F0Z-708391 | IFI | IFI | 2022-07-20 | 2022-07-18 | 2022-07-20 | -2 | 2 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-07-06 |  |  | D00 | IFI | T-1146 | 44748 | 1401/04/15 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05145 | 44758 | 1401/04/25 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-144182 | 44760 | 1401/04/27 | 44762 | 1401/04/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1146 | 2022-07-06 | 1401/04/15 |  |  |  | BK-SUR-ENG-CIV-01-05145 | 44758 | 1401/04/25 | CM-C3 | [6 empty] | 1401-2294-144182 | 2022-07-18 | 1401/04/27 | 44762 | 1401/04/29 | CM
2 | 10 | 1 | 8 | 0 | 2 | 0 | 2.10.1.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 1 | 8 | 0 | 2 | 1 | 2.10.1.8.2.1 | BK-BK15-PEDCO-110-SU-DW-0001 | Over Head Line Plan and Profile - BK15 |  | BK-BK15-PEDCO-110-SU-DW-0001 | BK-BK15-PEDCO-110-SU-DW-0001 | BK | BK15 | PEDCO | 110 | SU | DW | 0001 | F4P-708392 | AFC | IFC | 2022-05-30 | 2022-07-27 | 2022-07-30 | 58 | 3 | 61 | IFA | 2022-09-18 | 2022-09-19 | 2022-09-20 | 1 | 1 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-16 |  |  | D01 | IFA | T-1354 | 44808 | 1401/06/13 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05691 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-SU-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-229302 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-BK15-PEDCO-110-SU-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0962 | 2022-05-16 | 1401/02/26 | T-0962 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04476 | 44710 | 1401/03/08 | CM-C3 | [6 empty] | 1401-2294-156807 | 2022-07-27 | 1401/05/05 | 44772 | 1401/05/08 | CM | [10 empty] | D01 | IFA | T-1354 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-ELE-01-05691 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-SU-DW-0001_D00 | [5 empty] | 1401-2294-229302 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-BK15-PEDCO-110-SU-DW-0001_D00
2 | 10 | 2 | 0 | 0 | 0 | 0 | 2.10.2 |  | Procurement Engineering
2 | 10 | 2 | 1 | 0 | 0 | 0 | 2.10.2.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 1 | 1 | 0 | 0 | 2.10.2.1.1 |  | Pipe
2 | 10 | 2 | 1 | 1 | 1 | 0 | 2.10.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 1 | 1 | 1 | 1 | 2.10.2.1.1.1.1 | BK-BK15-PEDCO-110-PI-MR-0001 | PMR For Pipes - BK15 |  | BK-BK15-PEDCO-110-PI-MR-0001 | BK-BK15-PEDCO-110-PI-MR-0001 | BK | BK15 | PEDCO | 110 | PI | MR | 0001 | F0Z-708393 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFI | T-1544 | 44859 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1544 | 2022-10-25 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2
2 | 10 | 2 | 1 | 1 | 2 | 0 | 2.10.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 1 | 1 | 2 | 1 | 2.10.2.1.1.2.1 | BK-BK15-PEDCO-110-PI-TB-0001 | TBE For Pipes - BK15 |  | BK-BK15-PEDCO-110-PI-TB-0001 | BK-BK15-PEDCO-110-PI-TB-0001 | BK | BK15 | PEDCO | 110 | PI | TB | 0001 | F0Z-708394 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 1 | 2 | 0 | 0 | 2.10.2.1.2 |  | Pipe Support
2 | 10 | 2 | 1 | 2 | 1 | 0 | 2.10.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 1 | 2 | 1 | 1 | 2.10.2.1.2.1.1 | BK-BK15-PEDCO-110-PI-MR-0002 | PMR For Pipe Support - BK15 |  | BK-BK15-PEDCO-110-PI-MR-0002 | BK-BK15-PEDCO-110-PI-MR-0002 | BK | BK15 | PEDCO | 110 | PI | MR | 0002 | F0Z-708395 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 1 | 2 | 2 | 0 | 2.10.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 1 | 2 | 2 | 1 | 2.10.2.1.2.2.1 | BK-BK15-PEDCO-110-PI-TB-0002 | TBE For Pipe Support - BK15 |  | BK-BK15-PEDCO-110-PI-TB-0002 | BK-BK15-PEDCO-110-PI-TB-0002 | BK | BK15 | PEDCO | 110 | PI | TB | 0002 | F0Z-708396 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 2 | 0 | 0 | 0 | 2.10.2.2 |  | HVAC
2 | 10 | 2 | 2 | 1 | 0 | 0 | 2.10.2.2.1 |  | Main HVAC Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 2 | 1 | 1 | 0 | 2.10.2.1.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 2 | 1 | 1 | 1 | 2.10.2.2.1.1.1 | BK-BK15-PEDCO-110-HV-MR-0001 | PMR For Main HVAC Equipment - BK15 |  | BK-BK15-PEDCO-110-HV-MR-0001 | BK-BK15-PEDCO-110-HV-MR-0001 | BK | BK15 | PEDCO | 110 | HV | MR | 0001 | F0Z-708397 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 2 | 1 | 2 | 0 | 2.10.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 2 | 1 | 2 | 1 | 2.10.2.2.1.2.1 | BK-BK15-PEDCO-110-HV-TB-0001 | TBE For Main HVAC Equipment - BK15 |  | BK-BK15-PEDCO-110-HV-TB-0001 | BK-BK15-PEDCO-110-HV-TB-0001 | BK | BK15 | PEDCO | 110 | HV | TB | 0001 | F0Z-708398 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 0 | 0 | 0 | 2.10.2.3 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 1 | 0 | 0 | 2.10.2.3.1 |  | Transformers
2 | 10 | 2 | 3 | 1 | 1 | 0 | 2.10.3.1.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 1 | 1 | 1 | 2.10.2.3.1.1.1 | BK-BK15-PEDCO-110-EL-MR-0001 | PMR For Transformers - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0001 | BK-BK15-PEDCO-110-EL-MR-0001 | BK | BK15 | PEDCO | 110 | EL | MR | 0001 | F0Z-708399 | AFD | IFC | 2022-07-27 | 2022-08-03 | 2022-08-09 | 7 | 6 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-13 |  |  | D00 | IFC | T-1156 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05235 | 44767 | 1401/05/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-167067 | 44776 | 1401/05/12 | 44782 | 1401/05/18 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1156 | 2022-07-13 | 1401/04/22 |  |  |  | BK-SUR-ENG-ELE-01-05235 | 44767 | 1401/05/03 | CM-C3 | [6 empty] | 1401-2294-167067 | 2022-08-03 | 1401/05/12 | 44782 | 1401/05/18 | CM
2 | 10 | 2 | 3 | 1 | 2 | 0 | 2.10.3.1.2 |  | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 1 | 2 | 1 | 2.10.2.3.1.2.1 | BK-BK15-PEDCO-110-EL-TB-0001 | TBE For Transformers - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0001 | BK-BK15-PEDCO-110-EL-TB-0001 | BK | BK15 | PEDCO | 110 | EL | TB | 0001 | F0Z-708400 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 2 | 0 | 0 | 2.10.2.3.2 |  | LV Switchgear & MCC
2 | 10 | 2 | 3 | 2 | 1 | 0 | 2.10.3.2.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 2 | 1 | 1 | 2.10.2.3.2.1.1 | BK-BK15-PEDCO-110-EL-MR-0002 | PMR For LV Switchgear & MCC - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0002 | BK-BK15-PEDCO-110-EL-MR-0002 | BK | BK15 | PEDCO | 110 | EL | MR | 0002 | F0Z-708401 | IFI | IFI | 2022-09-25 | 2022-10-05 | 2022-10-08 | 10 | 3 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-11 |  |  | D00 | IFI | T-1393 | 44815 | 1401/06/20 | T-1393 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05759 | 44828 | 1401/07/02 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249409 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1393 | 2022-09-11 | 1401/06/20 | T-1393 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05759 | 44828 | 1401/07/02 | CM-C2 | [6 empty] | 1401-2294-249409 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 10 | 2 | 3 | 2 | 2 | 0 | 2.10.3.2.2 |  | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 2 | 2 | 1 | 2.10.2.3.2.2.1 | BK-BK15-PEDCO-110-EL-TB-0002 | TBE For LV Switchgear & MCC - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0002 | BK-BK15-PEDCO-110-EL-TB-0002 | BK | BK15 | PEDCO | 110 | EL | TB | 0002 | F0Z-708402 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 3 | 0 | 0 | 2.10.2.3.3 |  | Emergency Diesel Generator
2 | 10 | 2 | 3 | 3 | 1 | 0 | 2.10.3.3.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 3 | 1 | 1 | 2.10.2.3.3.1.1 | BK-BK15-PEDCO-110-EL-MR-0003 | PMR For Emergency Diesel Generator - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0003 | BK-BK15-PEDCO-110-EL-MR-0003 | BK | BK15 | PEDCO | 110 | EL | MR | 0003 | F0Z-708403 | IFI | IFI | 2022-09-03 | 2022-09-08 | 2022-09-12 | 5 | 4 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-20 |  |  | D00 | IFI | T-1293 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216140 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1293 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | [6 empty] | 1401-2294-216140 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | AP
2 | 10 | 2 | 3 | 3 | 2 | 0 | 2.10.3.3.2 |  | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 3 | 2 | 1 | 2.10.2.3.3.2.1 | BK-BK15-PEDCO-110-EL-TB-0003 | TBE For Emergency Diesel Generator - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0003 | BK-BK15-PEDCO-110-EL-TB-0003 | BK | BK15 | PEDCO | 110 | EL | TB | 0003 | F0Z-708404 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 4 | 0 | 0 | 2.10.2.3.4 |  | UPS System
2 | 10 | 2 | 3 | 4 | 1 | 0 | 2.10.3.4.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 4 | 1 | 1 | 2.10.2.3.4.1.1 | BK-BK15-PEDCO-110-EL-MR-0004 | PMR For UPS System - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0004 | BK-BK15-PEDCO-110-EL-MR-0004 | BK | BK15 | PEDCO | 110 | EL | MR | 0004 | F0Z-708405 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 4 | 2 | 0 | 2.10.3.4.2 |  | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 4 | 2 | 1 | 2.10.2.3.4.2.1 | BK-BK15-PEDCO-110-EL-TB-0004 | TBE For UPS System - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0004 | BK-BK15-PEDCO-110-EL-TB-0004 | BK | BK15 | PEDCO | 110 | EL | TB | 0004 | F0Z-708406 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 5 | 0 | 0 | 2.10.2.3.5 |  | DC Charger
2 | 10 | 2 | 3 | 5 | 1 | 0 | 2.10.3.5.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 5 | 1 | 1 | 2.10.2.3.5.1.1 | BK-BK15-PEDCO-110-EL-MR-0005 | PMR For DC Charger - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0005 | BK-BK15-PEDCO-110-EL-MR-0005 | BK | BK15 | PEDCO | 110 | EL | MR | 0005 | F0Z-708407 | IFI | IFI | 2022-05-11 | 2022-05-28 | 2022-05-29 | 17 | 1 | 18 | IFI | 2022-09-07 | 2022-09-08 | 2022-09-12 | 1 | 4 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-27 |  |  | D01 | IFI | T-1311 | 44797 | 1401/06/01 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-BK15-PEDCO-110-EL-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-BK15-PEDCO-110-EL-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0866 | 2022-04-27 | 1401/02/07 | T-0866 | 44678 | 1401/02/07 | BK-SUR-ENG-ELE-01-04213 | 44691 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78862 | 2022-05-28 | 1401/03/08 | 44710 | 1401/03/09 | CM | [10 empty] | D01 | IFI | T-1311 | 44797 | 1401/06/01 |  |  |  | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | PEDCO-CRS-BK-BK15-PEDCO-110-EL-MR-0005_D00 | [5 empty] | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-BK15-PEDCO-110-EL-MR-0005_D00
2 | 10 | 2 | 3 | 5 | 2 | 0 | 2.10.3.5.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 5 | 2 | 1 | 2.10.2.3.5.2.1 | BK-BK15-PEDCO-110-EL-TB-0005 | TBE For DC Charger - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0005 | BK-BK15-PEDCO-110-EL-TB-0005 | BK | BK15 | PEDCO | 110 | EL | TB | 0005 | F0Z-708408 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 6 | 0 | 0 | 2.10.2.3.6 |  | Capacitor Bank | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 6 | 1 | 0 | 2.10.3.6.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 6 | 1 | 1 | 2.10.2.3.6.1.1 | BK-BK15-PEDCO-110-EL-MR-0006 | PMR For Capacitor Bank - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0006 | BK-BK15-PEDCO-110-EL-MR-0006 | BK | BK15 | PEDCO | 110 | EL | MR | 0006 | F0Z-708409 | IFI | IFI | 2022-08-13 | 2022-08-18 | 2022-08-20 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFI | T-1215 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183488 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1215 | 2022-07-30 | 1401/05/08 |  |  |  | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | [6 empty] | 1401-2294-183488 | 2022-08-18 | 1401/05/27 | 44793 | 1401/05/29 | RJ
2 | 10 | 2 | 3 | 6 | 2 | 0 | 2.10.3.6.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 6 | 2 | 1 | 2.10.2.3.6.2.1 | BK-BK15-PEDCO-110-EL-TB-0006 | TBE For Capacitor Bank - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0006 | BK-BK15-PEDCO-110-EL-TB-0006 | BK | BK15 | PEDCO | 110 | EL | TB | 0006 | F0Z-708410 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 7 | 0 | 0 | 2.10.2.3.7 |  | Lighting & Distribution Main Panels | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 7 | 1 | 0 | 2.10.3.7.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 7 | 1 | 1 | 2.10.2.3.7.1.1 | BK-BK15-PEDCO-110-EL-MR-0007 | PMR For Lighting & Distribution Main Panels - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0007 | BK-BK15-PEDCO-110-EL-MR-0007 | BK | BK15 | PEDCO | 110 | EL | MR | 0007 | F0Z-708411 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 7 | 2 | 0 | 2.10.3.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 7 | 2 | 1 | 2.10.2.3.7.2.1 | BK-BK15-PEDCO-110-EL-TB-0007 | TBE For Lighting & Distribution Main Panels - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0007 | BK-BK15-PEDCO-110-EL-TB-0007 | BK | BK15 | PEDCO | 110 | EL | TB | 0007 | F0Z-708412 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 8 | 0 | 0 | 2.10.2.3.8 |  | Earthing & Lightning System | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 8 | 1 | 0 | 2.10.3.8.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 8 | 1 | 1 | 2.10.2.3.8.1.1 | BK-BK15-PEDCO-110-EL-MR-0008 | PMR For Earthing & Lightning System - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0008 | BK-BK15-PEDCO-110-EL-MR-0008 | BK | BK15 | PEDCO | 110 | EL | MR | 0008 | F0Z-708413 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 8 | 2 | 0 | 2.10.3.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 8 | 2 | 1 | 2.10.2.3.8.2.1 | BK-BK15-PEDCO-110-EL-TB-0008 | TBE For Earthing & Lightning System - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0008 | BK-BK15-PEDCO-110-EL-TB-0008 | BK | BK15 | PEDCO | 110 | EL | TB | 0008 | F0Z-708414 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 9 | 0 | 0 | 2.10.2.3.9 |  | Lighting and Small Power Equipment
2 | 10 | 2 | 3 | 9 | 1 | 0 | 2.10.3.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 9 | 1 | 1 | 2.10.2.3.9.1.1 | BK-BK15-PEDCO-110-EL-MR-0009 | PMR For Lighting and Small Power Equipment - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0009 | BK-BK15-PEDCO-110-EL-MR-0009 | BK | BK15 | PEDCO | 110 | EL | MR | 0009 | F0Z-708415 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 9 | 2 | 0 | 2.10.3.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 9 | 2 | 1 | 2.10.2.3.9.2.1 | BK-BK15-PEDCO-110-EL-TB-0009 | TBE For Lighting and Small Power Equipment - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0009 | BK-BK15-PEDCO-110-EL-TB-0009 | BK | BK15 | PEDCO | 110 | EL | TB | 0009 | F0Z-708416 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 10 | 0 | 0 | 2.10.2.3.10 |  | Tray/Ladder and Accessories
2 | 10 | 2 | 3 | 10 | 1 | 0 | 2.10.3.10.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 10 | 1 | 1 | 2.10.2.3.10.1.1 | BK-BK15-PEDCO-110-EL-MR-0010 | PMR For Tray/Ladder and Accessories - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0010 | BK-BK15-PEDCO-110-EL-MR-0010 | BK | BK15 | PEDCO | 110 | EL | MR | 0010 | F0Z-708417 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 10 | 2 | 0 | 2.10.3.10.2 |  | Technical Bid Evaluation (TBE) | [61 empty] | Moved to Field
2 | 10 | 2 | 3 | 10 | 2 | 1 | 2.10.2.3.10.2.1 | BK-BK15-PEDCO-110-EL-TB-0010 | TBE For Tray/Ladder and Accessories - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0010 | BK-BK15-PEDCO-110-EL-TB-0010 | BK | BK15 | PEDCO | 110 | EL | TB | 0010 | F0Z-708418 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 11 | 0 | 0 | 2.10.2.3.11 |  | Power & Control Cables
2 | 10 | 2 | 3 | 11 | 1 | 0 | 2.10.3.11.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 11 | 1 | 1 | 2.10.2.3.11.1.1 | BK-BK15-PEDCO-110-EL-MR-0011 | PMR For Power & Control Cables - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0011 | BK-BK15-PEDCO-110-EL-MR-0011 | BK | BK15 | PEDCO | 110 | EL | MR | 0011 | F0Z-708419 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 3 | 11 | 2 | 0 | 2.10.3.11.2 |  | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 11 | 2 | 1 | 2.10.2.3.11.2.1 | BK-BK15-PEDCO-110-EL-TB-0011 | TBE For Power & Control Cables - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0011 | BK-BK15-PEDCO-110-EL-TB-0011 | BK | BK15 | PEDCO | 110 | EL | TB | 0011 | F0Z-708420 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 12 | 0 | 0 | 2.10.2.3.12 |  | Electrical Bulk Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 12 | 1 | 0 | 2.10.3.12.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 12 | 1 | 1 | 2.10.2.3.12.1.1 | BK-BK15-PEDCO-110-EL-MR-0012 | PMR For Electrical Bulk Items - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0012 | BK-BK15-PEDCO-110-EL-MR-0012 | BK | BK15 | PEDCO | 110 | EL | MR | 0012 | F0Z-708421 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 12 | 2 | 0 | 2.10.3.12.2 |  | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 12 | 2 | 1 | 2.10.2.3.12.2.1 | BK-BK15-PEDCO-110-EL-TB-0012 | TBE For Electrical Bulk Items - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0012 | BK-BK15-PEDCO-110-EL-TB-0012 | BK | BK15 | PEDCO | 110 | EL | TB | 0012 | F0Z-708422 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 13 | 0 | 0 | 2.10.2.3.13 |  | Transmission Over head Line
2 | 10 | 2 | 3 | 13 | 1 | 0 | 2.10.3.13.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 13 | 1 | 1 | 2.10.2.3.13.1.1 | BK-BK15-PEDCO-110-EL-MR-0013 | PMR For Transmission Over head Line - BK15 |  | BK-BK15-PEDCO-110-EL-MR-0013 | BK-BK15-PEDCO-110-EL-MR-0013 | BK | BK15 | PEDCO | 110 | EL | MR | 0013 | F0Z-708423 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 3 | 13 | 2 | 0 | 2.10.3.13.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 3 | 13 | 2 | 1 | 2.10.2.3.13.2.1 | BK-BK15-PEDCO-110-EL-TB-0013 | TBE For Transmission Over head Line - BK15 |  | BK-BK15-PEDCO-110-EL-TB-0013 | BK-BK15-PEDCO-110-EL-TB-0013 | BK | BK15 | PEDCO | 110 | EL | TB | 0013 | F0Z-708424 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 4 | 0 | 0 | 0 | 2.10.2.4 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 4 | 1 | 0 | 0 | 2.10.2.4.1 |  | Steel Structure Items
2 | 10 | 2 | 4 | 1 | 1 | 0 | 2.10.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 4 | 1 | 1 | 1 | 2.10.2.4.1.1.1 | BK-BK15-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - BK15 |  | BK-BK15-PEDCO-110-ST-MR-0001 | BK-BK15-PEDCO-110-ST-MR-0001 | BK | BK15 | PEDCO | 110 | ST | MR | 0001 | F0Z-708425 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 4 | 1 | 2 | 0 | 2.10.4.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 4 | 1 | 2 | 1 | 2.10.2.4.1.2.1 | BK-BK15-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - BK15 |  | BK-BK15-PEDCO-110-ST-TB-0001 | BK-BK15-PEDCO-110-ST-TB-0001 | BK | BK15 | PEDCO | 110 | ST | TB | 0001 | F0Z-708426 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 4 | 2 | 0 | 0 | 2.10.2.4.2 |  | Anchor Bolts
2 | 10 | 2 | 4 | 2 | 1 | 0 | 2.10.4.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 4 | 2 | 1 | 1 | 2.10.2.4.2.1.1 | BK-BK15-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - BK15 |  | BK-BK15-PEDCO-110-ST-MR-0002 | BK-BK15-PEDCO-110-ST-MR-0002 | BK | BK15 | PEDCO | 110 | ST | MR | 0002 | F0Z-708427 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 2 | 4 | 2 | 2 | 0 | 2.10.4.2.2 |  | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 4 | 2 | 2 | 1 | 2.10.2.4.2.2.1 | BK-BK15-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - BK15 |  | BK-BK15-PEDCO-110-ST-TB-0002 | BK-BK15-PEDCO-110-ST-TB-0002 | BK | BK15 | PEDCO | 110 | ST | TB | 0002 | F0Z-708428 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 4 | 3 | 0 | 0 | 2.10.2.4.3 |  | Blast Proof Doors
2 | 10 | 2 | 4 | 3 | 1 | 0 | 2.10.4.3.1 |  | Purchase Material Requisition (PMR)
2 | 10 | 2 | 4 | 3 | 1 | 1 | 2.10.2.4.3.1.1 | BK-BK15-PEDCO-110-ST-MR-0003 | PMR For Blast Proof Doors - BK15 |  | BK-BK15-PEDCO-110-ST-MR-0003 | BK-BK15-PEDCO-110-ST-MR-0003 | BK | BK15 | PEDCO | 110 | ST | MR | 0003 | F0Z-708429 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 2 | 4 | 3 | 2 | 0 | 2.10.4.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 2 | 4 | 3 | 2 | 1 | 2.10.2.4.3.2.1 | BK-BK15-PEDCO-110-ST-TB-0003 | TBE For Blast Proof Doors - BK15 |  | BK-BK15-PEDCO-110-ST-TB-0003 | BK-BK15-PEDCO-110-ST-TB-0003 | BK | BK15 | PEDCO | 110 | ST | TB | 0003 | F0Z-708430 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 3 | 0 | 0 | 0 | 0 | 2.10.3 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 3 | 0 | 0 | 1 | 0 | 2.10.3.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 3 | 0 | 0 | 1 | 1 | 2.10.3.1 | BK-BK15-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - BK15 |  | BK-BK15-PEDCO-110-CO-PR-0001 | BK-BK15-PEDCO-110-CO-PR-0001 | BK | BK15 | PEDCO | 110 | CO | PR | 0001 | F0Z-708431 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 4 | 0 | 0 | 0 | 0 | 2.10.4 |  | Field Engineering
2 | 10 | 4 | 0 | 0 | 1 | 0 | 2.10.4.1 |  | Query
2 | 10 | 4 | 0 | 0 | 1 | 1 | 2.10.4.1 | BK-BK15-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-BK15-PEDCO-110-GE-TQ-0001 | BK-BK15-PEDCO-110-GE-TQ-0001 | BK | BK15 | PEDCO | 110 | GE | TQ | 0001 | F7Z-708432 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 4 | 0 | 0 | 2 | 0 | 2.10.4.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 4 | 0 | 0 | 2 | 1 | 2.10.4.2 | BK-BK15-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - BK15 |  | BK-BK15-PEDCO-110-GE-DO-0001 | BK-BK15-PEDCO-110-GE-DO-0001 | BK | BK15 | PEDCO | 110 | GE | DO | 0001 | F0Z-708433 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 5 | 0 | 0 | 0 | 0 | 2.10.5 |  | Engineering Final Documentation
2 | 10 | 5 | 0 | 0 | 1 | 0 | 2.10.5.1 |  | Manual | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 10 | 5 | 0 | 0 | 1 | 1 | 2.10.5.1 | BK-BK15-PEDCO-110-GE-ML-0001 | Operating Manual - BK15 |  | BK-BK15-PEDCO-110-GE-ML-0001 | BK-BK15-PEDCO-110-GE-ML-0001 | BK | BK15 | PEDCO | 110 | GE | ML | 0001 | F0Z-708434 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 10 | 5 | 0 | 0 | 2 | 0 | 2.10.5.2 |  | Dossier
2 | 10 | 5 | 0 | 0 | 2 | 1 | 2.10 | BK-BK15-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - BK15 |  | BK-BK15-PEDCO-110-GE-DO-0001 | [8 empty] | F0Z-708433 |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 10 | 5 | 0 | 0 | 2 | 2 | 2.10 | BK-BK15-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - BK15 |  | BK-BK15-PEDCO-110-GE-DO-0002 | BK-BK15-PEDCO-110-GE-DO-0002 | BK | BK15 | PEDCO | 110 | GE | DO | 0002 | F0Z-708435 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 0 | 0 | 0 | 0 | 0 | 2.11 |  | Package 10-Workover # 05 | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 0 | 0 | 0 | 0 | 2.11.1 |  | Detail Design
2 | 11 | 1 | 1 | 0 | 0 | 0 | 2.11.1.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 1 | 1 | 0 | 0 | 2.11.1.1.1 |  | Drawing/Diagram
2 | 11 | 1 | 1 | 1 | 0 | 1 | 2.11.1.1.1 | BK-BK05-PEDCO-110-PR-PI-0001 | P&ID for Diesel Oil Drum- BK05 |  | BK-BK05-PEDCO-110-PR-PI-0001 | [8 empty] | F2A-708436 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-06 | 2022-02-08 | 20 | 2 | 22 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-05-12 | 2022-05-16 | 18 | 4 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-15 |  |  | D03 | IFA | T-0795 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-399153 | 44598 | 1400/11/17 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0648 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 44635 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0795 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D02
2 | 11 | 1 | 1 | 1 | 0 | 2 | 2.11.1.1.1 | BK-BK05-PEDCO-110-PR-PI-0002 | P&ID for Potable Water Tank - BK05 |  | BK-BK05-PEDCO-110-PR-PI-0002 | [8 empty] | F2A-708437 | AFC | [50 empty] | 2021-11-15 |  |  | D03 | IFA | T-0795 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 44536 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-399153 | 44598 | 1400/11/17 | 44600 | 1400/11/19 | AP | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0648 | 44619 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 44635 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 44630 | 1400/12/19 | 44634 | 1400/12/24 | RJ | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0795 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-59474 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D02
2 | 11 | 1 | 1 | 2 | 0 | 0 | 2.11.1.1.2 |  | List
2 | 11 | 1 | 1 | 2 | 0 | 1 | 2.11.1.1.2 | BK-BK05-PEDCO-110-PR-LI-0001 | Line List - BK05 |  | BK-BK05-PEDCO-110-PR-LI-0001 | [8 empty] | F0Z-708438 | AFC | IFC | 2022-03-13 | 2022-03-12 | 2022-03-15 | -1 | 3 | 2 | IFA | 2022-05-14 | 2022-05-31 | 2022-05-06 | 17 | -25 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-27 |  |  | D01 | IFA | T-0877 | 44681 | 1401/02/10 | T-0877 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-83257 | 44712 | 1401/03/10 | 44687 | 1401/03/16 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0650 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03597 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445283 | 2022-03-12 | 1400/12/21 | 44635 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0877 | 44681 | 1401/02/10 | T-0877 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 44704 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1401-2294-83257 | 44712 | 1401/03/10 | 44687 | 1401/03/16 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-LI-0001_D00
2 | 11 | 1 | 1 | 3 | 0 | 0 | 2.11.1.1.3 |  | Data Sheet | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 1 | 3 | 0 | 1 | 2.11.1.1 | BK-BK05-PEDCO-110-PR-DT-0001 | Process Data Sheets For Instrument Devices - BK05 |  | BK-BK05-PEDCO-110-PR-DT-0001 | [8 empty] | F0Z-708439 | AFC | IFC | 2022-04-26 | 2022-05-14 | 2022-05-16 | 18 | 2 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-12 |  |  | D00 | IFC | T-0807 | 44663 | 1401/01/12 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03991 | 44670 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52773 | 44695 | 1401/02/24 | 44697 | 1401/02/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 44670 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 44697 | 1401/02/26 | AP
2 | 11 | 1 | 2 | 0 | 0 | 0 | 2.11.1.2 |  | HVAC/Plumbing | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 2 | 1 | 0 | 0 | 2.11.1.2.1 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 2 | 1 | 0 | 1 | 2.11.1.2.1 | BK-BK05-PEDCO-110-HV-CN-0001 | HVAC Calculation Note For Switchgear Building - BK05 |  | BK-BK05-PEDCO-110-HV-CN-0001 | BK-BK05-PEDCO-110-HV-CN-0001 | BK | BK05 | PEDCO | 110 | HV | CN | 0001 | F0Z-708440 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 1 | 2 | 1 | 0 | 2 | 2.11.1.2.1 | BK-BK05-PEDCO-110-HV-CN-0002 | HVAC Calculation Note For Security Building - BK05 |  | BK-BK05-PEDCO-110-HV-CN-0002 | BK-BK05-PEDCO-110-HV-CN-0002 | BK | BK05 | PEDCO | 110 | HV | CN | 0002 | F0Z-708441 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 1 | 2 | 2 | 0 | 0 | 2.11.1.2.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 2 | 2 | 0 | 1 | 2.11.1.2.2 | BK-BK05-PEDCO-110-HV-DT-0001 | Data Sheets For Main HVAC Equipment - BK05 |  | BK-BK05-PEDCO-110-HV-DT-0001 | BK-BK05-PEDCO-110-HV-DT-0001 | BK | BK05 | PEDCO | 110 | HV | DT | 0001 | F0Z-708442 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 2 | 3 | 0 | 0 | 2.11.1.2.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 2 | 3 | 0 | 1 | 2.11.1.2.3 | BK-BK05-PEDCO-110-HV-PY-0001 | HVAC System Layout For Switchgear Building - BK05 |  | BK-BK05-PEDCO-110-HV-PY-0001 | BK-BK05-PEDCO-110-HV-PY-0001 | BK | BK05 | PEDCO | 110 | HV | PY | 0001 | F4B-708443 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 2 | 3 | 0 | 2 | 2.11.1.2.3 | BK-BK05-PEDCO-110-HV-PY-0002 | HVAC System Layout For Security Building - BK05 |  | BK-BK05-PEDCO-110-HV-PY-0002 | BK-BK05-PEDCO-110-HV-PY-0002 | BK | BK05 | PEDCO | 110 | HV | PY | 0002 | F4B-708444 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 2 | 3 | 0 | 3 | 2.11.1.2.3 | BK-BK05-PEDCO-110-HV-PY-0003 | Plumbing & Sewage Piping Layout For Switchgear Building - BK05 |  | BK-BK05-PEDCO-110-HV-PY-0003 | BK-BK05-PEDCO-110-HV-PY-0003 | BK | BK05 | PEDCO | 110 | HV | PY | 0003 | F4B-708445 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 1 | 2 | 3 | 0 | 4 | 2.11.1.2.3 | BK-BK05-PEDCO-110-HV-PY-0004 | Plumbing & Sewage Piping Layout For Security Building - BK05 |  | BK-BK05-PEDCO-110-HV-PY-0004 | BK-BK05-PEDCO-110-HV-PY-0004 | BK | BK05 | PEDCO | 110 | HV | PY | 0004 | F4B-708446 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 2 | 4 | 0 | 0 | 2.11.1.2.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 2 | 4 | 0 | 1 | 2.11.1.2 | BK-BK05-PEDCO-110-HV-MT-0001 | MTO For Building HVAC & Plumbing Systems - BK05 |  | BK-BK05-PEDCO-110-HV-MT-0001 | BK-BK05-PEDCO-110-HV-MT-0001 | BK | BK05 | PEDCO | 110 | HV | MT | 0001 | F8Z-708447 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 3 | 0 | 0 | 0 | 2.11.1.3 |  | Piping
2 | 11 | 1 | 3 | 1 | 0 | 0 | 2.11.1.3.1 |  | Drawing/Diagram
2 | 11 | 1 | 3 | 1 | 0 | 1 | 2.11.1.3 | BK-BK05-PEDCO-110-PI-MT-0001 | Plot Plan Drawing – BK05 |  | BK-BK05-PEDCO-110-PI-PY-0001 | BK-BK05-PEDCO-110-PI-MT-0001 | BK | BK05 | PEDCO | 110 | PI | MT | 0001 | F8Z-708448 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14
2 | 11 | 1 | 3 | 1 | 0 | 0 | 2.11.1.3.1 |  | MTO
2 | 11 | 1 | 3 | 1 | 0 | 1 | 2.11.1.3 | BK-BK05-PEDCO-110-PI-MT-0001 | MTO For Pipes - BK05 |  | BK-BK05-PEDCO-110-PI-MT-0001 | BK-BK05-PEDCO-110-PI-MT-0001 | BK | BK05 | PEDCO | 110 | PI | MT | 0001 | F8Z-708448 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFI | T-1544 | 44859 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1544 | 2022-10-25 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2
2 | 11 | 1 | 4 | 0 | 0 | 0 | 2.11.1.4 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 4 | 1 | 0 | 0 | 2.11.1.4.1 |  | MTO
2 | 11 | 1 | 4 | 1 | 0 | 1 | 2.11.1.4 | BK-BK05-PEDCO-110-EL-MT-0001 | MTO For Transmission Over Head Line - BK05 |  | BK-BK05-PEDCO-110-EL-MT-0001 | BK-BK05-PEDCO-110-EL-MT-0001 | BK | BK05 | PEDCO | 110 | EL | MT | 0001 | F8Z-708449 | IFI | IFI | 2022-10-03 | 2022-09-29 | 2022-10-08 | -4 | 9 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-19 |  |  | D00 | IFI | T-1417 | 44823 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249371 | 44833 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1417 | 2022-09-19 | 1401/06/28 | T-1417 | 44823 | 1401/06/28 | BK-SUR-ENG-ELE-01-05784 | 44836 | 1401/07/10 | CM-C2 | [6 empty] | 1401-2294-249371 | 2022-09-29 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 11 | 1 | 4 | 1 | 0 | 2 | 2.11.1.4 | BK-BK05-PEDCO-110-EL-MT-0002 | MTO For Lighting & Small Powers - BK05 |  | BK-BK05-PEDCO-110-EL-MT-0002 | BK-BK05-PEDCO-110-EL-MT-0002 | BK | BK05 | PEDCO | 110 | EL | MT | 0002 | F8Z-708450 | IFI | IFI | 2022-06-01 | 2022-06-10 | 2022-06-12 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-18 |  |  | D00 | IFI | T-0969 | 44699 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94633 | 44722 | 1401/03/20 | 44724 | 1401/03/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | T-0969 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04483 | 44710 | 1401/03/09 | CM-C2 | [6 empty] | 1401-2294-94633 | 2022-06-10 | 1401/03/20 | 44724 | 1401/03/22 | CM
2 | 11 | 1 | 4 | 1 | 0 | 3 | 2.11.1.4 | BK-BK05-PEDCO-110-EL-MT-0003 | MTO For Power & Control Cables - BK05 |  | BK-BK05-PEDCO-110-EL-MT-0003 | BK-BK05-PEDCO-110-EL-MT-0003 | BK | BK05 | PEDCO | 110 | EL | MT | 0003 | F8Z-708451 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 4 | 1 | 0 | 4 | 2.11.1.4 | BK-BK05-PEDCO-110-EL-MT-0004 | MTO For Tray/Ladder and Accessories - BK05 |  | BK-BK05-PEDCO-110-EL-MT-0004 | BK-BK05-PEDCO-110-EL-MT-0004 | BK | BK05 | PEDCO | 110 | EL | MT | 0004 | F8Z-708452 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 1 | 4 | 1 | 0 | 5 | 2.11.1.4 | BK-BK05-PEDCO-110-EL-MT-0005 | MTO For Electrical Bulk Items - BK05 |  | BK-BK05-PEDCO-110-EL-MT-0005 | BK-BK05-PEDCO-110-EL-MT-0005 | BK | BK05 | PEDCO | 110 | EL | MT | 0005 | F8Z-708453 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 4 | 1 | 0 | 6 | 2.11.1.4 | BK-BK05-PEDCO-110-EL-MT-0006 | MTO For Earthing & Lightning Systems - BK05 |  | BK-BK05-PEDCO-110-EL-MT-0006 | BK-BK05-PEDCO-110-EL-MT-0006 | BK | BK05 | PEDCO | 110 | EL | MT | 0006 | F8Z-708454 | IFI | IFI | 2022-10-25 | 2022-11-10 | 2022-11-14 | 16 | 4 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-11 |  |  | D00 | IFI | T-1480 | 44845 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-304880 | 44875 | 1401/08/19 | 44879 | 1401/08/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1480 | 2022-10-11 | 1401/07/19 | T-1480 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05970 | 44859 | 1401/08/03 | CM-C3 | [6 empty] | 1401-2294-304880 | 2022-11-10 | 1401/08/19 | 44879 | 1401/08/23 | CM
2 | 11 | 1 | 5 | 0 | 0 | 0 | 2.11.1.5 |  | Architecture
2 | 11 | 1 | 5 | 1 | 0 | 0 | 2.11.1.5.1 |  | Drawing/Diagram
2 | 11 | 1 | 5 | 1 | 0 | 1 | 2.11.1.5.1 | BK-BK05-PEDCO-110-AR-DW-0001 | Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-05 |  | BK-BK05-PEDCO-110-AR-DW-0001 | BK-BK05-PEDCO-110-AR-DW-0001 | BK | BK05 | PEDCO | 110 | AR | DW | 0001 | F4B-708455 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-01 |  |  | D00 | IFC | T-0885 | 44682 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 44697 | 1401/02/26 | CM
2 | 11 | 1 | 5 | 1 | 0 | 2 | 2.11.1.5.1 | BK-BK05-PEDCO-110-AR-DW-0002 | Architectural Drawing For Switchgear Building of Well Pads - BK-05 |  | BK-BK05-PEDCO-110-AR-DW-0002 | BK-BK05-PEDCO-110-AR-DW-0002 | BK | BK05 | PEDCO | 110 | AR | DW | 0002 | F4B-708456 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 2022-05-31 | 2022-06-07 | -1 | 7 | 6 | IFC | 2022-09-21 | 2022-10-11 | 2022-10-17 | 20 | 6 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D02 | IFC | T-1370 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-05721 | 44824 | 1401/06/29 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ARC-00-03551 | 44634 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 44645 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 44699 | 1401/02/28 | T-0974 | 44702 | 1401/02/31 | BK-SUR-ENG-ARC-01-04416 | 44705 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D00 | [5 empty] | 1401-2294-85268 | 44712 | 1401/03/10 | 44719 | 1401/03/17 | RJ | NISOC-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D00 | [9 empty] | D02 | IFC | T-1370 | 44811 | 1401/06/16 |  |  |  | BK-SUR-ENG-ARC-01-05721 | 44824 | 1401/06/29 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D01 | [5 empty] | 1401-2294-258370 | 44845 | 1401/07/19 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D01
2 | 11 | 1 | 5 | 1 | 0 | 3 | 2.11.1.5.1 | BK-BK05-PEDCO-110-AR-DW-0003 | Architectural Drawing For Security Building of Well Pads - BK-05 |  | BK-BK05-PEDCO-110-AR-DW-0003 | BK-BK05-PEDCO-110-AR-DW-0003 | BK | BK05 | PEDCO | 110 | AR | DW | 0003 | F4B-708457 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-01 |  |  | D00 | IFC | T-0886 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 44695 | 1401/02/21 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 44697 | 1401/02/26 | CM
2 | 11 | 1 | 5 | 2 | 0 | 0 | 2.11.1.5.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 5 | 2 | 0 | 1 | 2.11.1.5 | BK-BK05-PEDCO-110-AR-MT-0001 | MTO For Architectural Works - BK05 |  | BK-BK05-PEDCO-110-AR-MT-0001 | BK-BK05-PEDCO-110-AR-MT-0001 | BK | BK05 | PEDCO | 110 | AR | MT | 0001 | F8Z-708458 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 6 | 0 | 0 | 0 | 2.11.1.6 |  | Civil
2 | 11 | 1 | 6 | 1 | 0 | 0 | 2.11.1.6.1 |  | Drawing/Diagram
2 | 11 | 1 | 6 | 1 | 0 | 1 | 2.11.1.6.1 | BK-BK05-PEDCO-110-CV-DW-0001 | Civil and Structural drawings - BK05 |  | BK-BK05-PEDCO-110-CV-DW-0001 | BK-BK05-PEDCO-110-CV-DW-0001 | BK | BK05 | PEDCO | 110 | CV | DW | 0001 | F4S-708459 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 1 | 6 | 1 | 0 | 2 | 2.11.1.6.1 | BK-BK05-PEDCO-110-CV-PY-0001 | General Civil Layout - BK05 |  | BK-BK05-PEDCO-110-CV-PY-0001 | BK-BK05-PEDCO-110-CV-PY-0001 | BK | BK05 | PEDCO | 110 | CV | PY | 0001 | F4A-708460 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 6 | 1 | 0 | 3 | 2.11.1.6.1 | BK-BK05-PEDCO-110-CV-PY-0003 | Rough Grading Plans -BK05 |  | BK-BK05-PEDCO-110-CV-PY-0003 | BK-BK05-PEDCO-110-CV-PY-0003 | BK | BK05 | PEDCO | 110 | CV | PY | 0003 | F4S-708461 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 1 | 6 | 2 | 0 | 0 | 2.11.1.6.2 |  | Report
2 | 11 | 1 | 6 | 2 | 0 | 1 | 2.11.1.6.2 | BK-BK05-PEDCO-110-CV-RT-0001 | Site Visit Report (Civil Work) - BK05 |  | BK-BK05-PEDCO-110-CV-RT-0001 | BK-BK05-PEDCO-110-CV-RT-0001 | BK | BK05 | PEDCO | 110 | CV | RT | 0001 | F0Z-708462 | IFI | IFC | 2022-07-19 | 2022-07-20 | 2022-07-20 | 1 | 0 | 1 | IFI | 2022-08-14 | 2022-08-28 | 2022-08-31 | 14 | 3 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-07-05 |  |  | D01 | IFI | T-1222 | 44773 | 1401/05/09 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05336 | 44775 | 1401/05/11 | AP | PEDCO-CRS-BK-BK05-PEDCO-110-CV-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-197403 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | CM | NISOC-CRS-BK-BK05-PEDCO-110-CV-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1137 | 2022-07-05 | 1401/04/14 |  |  |  | BK-SUR-ENG-CIV-01-05117 | 44751 | 1401/04/25 | AP | [6 empty] | 1401-2290-144330 | 2022-07-20 | 1401/04/29 | 44762 | 1401/04/29 | CM | [10 empty] | D01 | IFI | T-1222 | 44773 | 1401/05/09 |  |  |  | BK-SUR-ENG-CIV-01-05336 | 44775 | 1401/05/11 | AP | PEDCO-CRS-BK-BK05-PEDCO-110-CV-RT-0001_D01 | [5 empty] | 1401-2294-197403 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | CM | NISOC-CRS-BK-BK05-PEDCO-110-CV-RT-0001_D01
2 | 11 | 1 | 6 | 3 | 0 | 0 | 2.11.1.6.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 6 | 3 | 0 | 1 | 2.11.1.6 | BK-BK05-PEDCO-110-CV-MT-0001 | MTO For Civil Works - BK05 |  | BK-BK05-PEDCO-110-CV-MT-0001 | BK-BK05-PEDCO-110-CV-MT-0001 | BK | BK05 | PEDCO | 110 | CV | MT | 0001 | F8Z-708463 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 7 | 0 | 0 | 0 | 2.11.1.7 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 7 | 1 | 0 | 0 | 2.11.1.7.1 |  | Drawing/Diagram
2 | 11 | 1 | 7 | 1 | 0 | 1 | 2.11.1.7.1 | BK-BK05-PEDCO-110-ST-DW-0001 | Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-05 |  | BK-BK05-PEDCO-110-ST-DW-0001 | BK-BK05-PEDCO-110-ST-DW-0001 | BK | BK05 | PEDCO | 110 | ST | DW | 0001 | F4G-708464 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 7 | 1 | 0 | 2 | 2.11.1.7.1 | BK-BK05-PEDCO-110-ST-DW-0002 | Foundation Drawing For Security Building For Well Pads - BK-05 |  | BK-BK05-PEDCO-110-ST-DW-0002 | BK-BK05-PEDCO-110-ST-DW-0002 | BK | BK05 | PEDCO | 110 | ST | DW | 0002 | F4Q-708465 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 1 | 7 | 1 | 0 | 3 | 2.11.1.7.1 | BK-BK05-PEDCO-110-ST-DW-0003 | Structural Drawing For Security Building For Well Pads - BK-05 |  | BK-BK05-PEDCO-110-ST-DW-0003 | BK-BK05-PEDCO-110-ST-DW-0003 | BK | BK05 | PEDCO | 110 | ST | DW | 0003 | F4M-708466 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 7 | 1 | 0 | 4 | 2.11.1.7.1 | BK-BK05-PEDCO-110-ST-DW-0004 | Foundation Drawing For Switchgear Building For Well Pads - BK-05 |  | BK-BK05-PEDCO-110-ST-DW-0004 | BK-BK05-PEDCO-110-ST-DW-0004 | BK | BK05 | PEDCO | 110 | ST | DW | 0004 | F4Q-708467 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 1 | 7 | 1 | 0 | 5 | 2.11.1.7.1 | BK-BK05-PEDCO-110-ST-DW-0005 | Structural Drawing For Switchgear Building For Well Pads - BK-05 |  | BK-BK05-PEDCO-110-ST-DW-0005 | BK-BK05-PEDCO-110-ST-DW-0005 | BK | BK05 | PEDCO | 110 | ST | DW | 0005 | F4M-708468 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 7 | 1 | 0 | 6 | 2.11.1.7.1 | BK-BK05-PEDCO-110-ST-DW-0006 | Foundation Drawing For Potable Water Tank For Well Pads - BK-05 |  | BK-BK05-PEDCO-110-ST-DW-0006 | BK-BK05-PEDCO-110-ST-DW-0006 | BK | BK05 | PEDCO | 110 | ST | DW | 0006 | F4Q-708469 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 7 | 1 | 0 | 7 | 2.11.1.7.1 | BK-BK05-PEDCO-110-ST-DW-0007 | Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-05 |  | BK-BK05-PEDCO-110-ST-DW-0007 | BK-BK05-PEDCO-110-ST-DW-0007 | BK | BK05 | PEDCO | 110 | ST | DW | 0007 | F4Q-708470 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 1 | 7 | 1 | 0 | 8 | 2.11.1.7.1 | BK-BK05-PEDCO-110-ST-DW-0008 | Structural Drawing For Diesel Generator Shelter For Well Pads - BK-05 |  | BK-BK05-PEDCO-110-ST-DW-0008 | BK-BK05-PEDCO-110-ST-DW-0008 | BK | BK05 | PEDCO | 110 | ST | DW | 0008 | F4M-708471 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 7 | 2 | 0 | 0 | 2.11.1.7.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 7 | 2 | 0 | 1 | 2.11.1.7 | BK-BK05-PEDCO-110-ST-MT-0001 | MTO For Structural Works - BK05 |  | BK-BK05-PEDCO-110-ST-MT-0001 | BK-BK05-PEDCO-110-ST-MT-0001 | BK | BK05 | PEDCO | 110 | ST | MT | 0001 | F8Z-708472 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 1 | 8 | 0 | 0 | 0 | 2.11.1.8 |  | Geotechnic
2 | 11 | 1 | 8 | 1 | 0 | 0 | 2.11.1.8.1 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 8 | 1 | 0 | 1 | 2.11.1.8.1 | BK-BK05-PEDCO-110-GT-RT-0001 | Geotechnical Investigation Report - BK05 |  | BK-BK05-PEDCO-110-GT-RT-0001 | BK-BK05-PEDCO-110-GT-RT-0001 | BK | BK05 | PEDCO | 110 | GT | RT | 0001 | F0Z-708473 | IFI | IFI | 2022-08-17 | 2022-08-27 | 2022-08-28 | 10 | 1 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-03 |  |  | D00 | IFI | T-1239 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05541 | 44801 | 1401/06/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-196157 | 44800 | 1401/06/05 | 44801 | 1401/06/06 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1239 | 2022-08-03 | 1401/05/12 |  |  |  | BK-SUR-ENG-CIV-01-05541 | 44801 | 1401/06/06 | CM-C2 | [6 empty] | 1401-2294-196157 | 2022-08-27 | 1401/06/05 | 44801 | 1401/06/06 | CM
2 | 11 | 1 | 8 | 2 | 0 | 0 | 2.11.1.8.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 1 | 8 | 2 | 0 | 1 | 2.11.1 | BK-BK05-PEDCO-110-SU-DW-0001 | Over Head Line Plan and Profile - BK05 |  | BK-BK05-PEDCO-110-SU-DW-0001 | BK-BK05-PEDCO-110-SU-DW-0001 | BK | BK05 | PEDCO | 110 | SU | DW | 0001 | F4P-708474 | AFC | IFC | 2022-06-01 | 2022-07-20 | 2022-07-24 | 49 | 4 | 53 | IFA | 2022-09-25 | 2022-09-19 | 2022-09-20 | -6 | 1 | -5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-18 |  |  | D01 | IFA | T-1383 | 44815 | 1401/06/20 | T-1383 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05726 | 44824 | 1401/06/29 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-SU-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-229284 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-BK05-PEDCO-110-SU-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0971 | 2022-05-18 | 1401/02/28 | T-0971 | 44702 | 1401/02/31 | BK-SUR-ENG-ELE-01-04486 | 44710 | 1401/03/09 | CM-C3 | [6 empty] | 1401-2294-145879 | 2022-07-20 | 1401/04/29 | 44766 | 1401/05/02 | CM | [10 empty] | D01 | IFA | T-1383 | 44815 | 1401/06/20 | T-1383 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05726 | 44824 | 1401/06/29 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-SU-DW-0001_D00 | [5 empty] | 1401-2294-229284 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-BK05-PEDCO-110-SU-DW-0001_D00
2 | 11 | 2 | 0 | 0 | 0 | 0 | 2.11.2 |  | Procurement Engineering
2 | 11 | 2 | 1 | 0 | 0 | 0 | 2.11.2.1 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 1 | 1 | 0 | 0 | 2.11.2.1.1 |  | Pipe
2 | 11 | 2 | 1 | 1 | 1 | 0 | 2.11.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 1 | 1 | 1 | 1 | 2.11.2.1.1.1.1 | BK-BK05-PEDCO-110-PI-MR-0001 | PMR For Pipes - BK05 |  | BK-BK05-PEDCO-110-PI-MR-0001 | BK-BK05-PEDCO-110-PI-MR-0001 | BK | BK05 | PEDCO | 110 | PI | MR | 0001 | F0Z-708475 | IFI | IFI | 2022-11-08 | 0 | 0 | -44873 | 0 | -44873 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFI | T-1544 | 44859 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1544 | 2022-10-25 | 1401/08/03 | T-1544 | 44859 | 1401/08/03 | BK-SUR-ENG-PIP-01-06158 | 44877 | 1401/08/21 | CM-C2
2 | 11 | 2 | 1 | 1 | 2 | 0 | 2.11.1.1.2 |  | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 1 | 1 | 2 | 1 | 2.11.2.1.1.2.1 | BK-BK05-PEDCO-110-PI-TB-0001 | TBE For Pipes - BK05 |  | BK-BK05-PEDCO-110-PI-TB-0001 | BK-BK05-PEDCO-110-PI-TB-0001 | BK | BK05 | PEDCO | 110 | PI | TB | 0001 | F0Z-708476 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 1 | 2 | 0 | 0 | 2.11.2.1.2 |  | Pipe Support
2 | 11 | 2 | 1 | 2 | 1 | 0 | 2.11.1.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 1 | 2 | 1 | 1 | 2.11.2.1.2.1.1 | BK-BK05-PEDCO-110-PI-MR-0002 | PMR For Pipe Support - BK05 |  | BK-BK05-PEDCO-110-PI-MR-0002 | BK-BK05-PEDCO-110-PI-MR-0002 | BK | BK05 | PEDCO | 110 | PI | MR | 0002 | F0Z-708477 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 1 | 2 | 2 | 0 | 2.11.1.2.2 |  | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 1 | 2 | 2 | 1 | 2.11.2.1.2.2.1 | BK-BK05-PEDCO-110-PI-TB-0002 | TBE For Pipe Support - BK05 |  | BK-BK05-PEDCO-110-PI-TB-0002 | BK-BK05-PEDCO-110-PI-TB-0002 | BK | BK05 | PEDCO | 110 | PI | TB | 0002 | F0Z-708478 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 2 | 0 | 0 | 0 | 2.11.2.2 |  | HVAC
2 | 11 | 2 | 2 | 1 | 0 | 0 | 2.11.2.2.1 |  | Main HVAC Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 2 | 1 | 1 | 0 | 2.11.2.1.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 2 | 1 | 1 | 1 | 2.11.2.2.1.1.1 | BK-BK05-PEDCO-110-HV-MR-0001 | PMR For Main HVAC Equipment - BK05 |  | BK-BK05-PEDCO-110-HV-MR-0001 | BK-BK05-PEDCO-110-HV-MR-0001 | BK | BK05 | PEDCO | 110 | HV | MR | 0001 | F0Z-708479 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 2 | 1 | 2 | 0 | 2.11.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 2 | 1 | 2 | 1 | 2.11.2.2.1.2.1 | BK-BK05-PEDCO-110-HV-TB-0001 | TBE For Main HVAC Equipment - BK05 |  | BK-BK05-PEDCO-110-HV-TB-0001 | BK-BK05-PEDCO-110-HV-TB-0001 | BK | BK05 | PEDCO | 110 | HV | TB | 0001 | F0Z-708480 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 0 | 0 | 0 | 2.11.2.3 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 1 | 0 | 0 | 2.11.2.3.1 |  | Transformers
2 | 11 | 2 | 3 | 1 | 1 | 0 | 2.11.3.1.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 1 | 1 | 1 | 2.11.2.3.1.1.1 | BK-BK05-PEDCO-110-EL-MR-0001 | PMR For Transformers - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0001 | BK-BK05-PEDCO-110-EL-MR-0001 | BK | BK05 | PEDCO | 110 | EL | MR | 0001 | F0Z-708481 | AFD | IFC | 2022-07-27 | 2022-08-03 | 2022-08-09 | 7 | 6 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-13 |  |  | D00 | IFC | T-1156 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05235 | 44767 | 1401/05/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-167067 | 44776 | 1401/05/12 | 44782 | 1401/05/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1156 | 2022-07-13 | 1401/04/22 |  |  |  | BK-SUR-ENG-ELE-01-05235 | 44767 | 1401/05/03 | CM-C3 | [6 empty] | 1401-2294-167067 | 2022-08-03 | 1401/05/12 | 44782 | 1401/05/18 | AP
2 | 11 | 2 | 3 | 1 | 2 | 0 | 2.11.3.1.2 |  | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 1 | 2 | 1 | 2.11.2.3.1.2.1 | BK-BK05-PEDCO-110-EL-TB-0001 | TBE For Transformers - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0001 | BK-BK05-PEDCO-110-EL-TB-0001 | BK | BK05 | PEDCO | 110 | EL | TB | 0001 | F0Z-708482 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 3 | 2 | 0 | 0 | 2.11.2.3.2 |  | LV Switchgear & MCC
2 | 11 | 2 | 3 | 2 | 1 | 0 | 2.11.3.2.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 2 | 1 | 1 | 2.11.2.3.2.1.1 | BK-BK05-PEDCO-110-EL-MR-0002 | PMR For LV Switchgear & MCC - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0002 | BK-BK05-PEDCO-110-EL-MR-0002 | BK | BK05 | PEDCO | 110 | EL | MR | 0002 | F0Z-708483 | IFI | IFI | 2022-09-25 | 2022-10-05 | 2022-10-08 | 10 | 3 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-11 |  |  | D00 | IFI | T-1393 | 44815 | 1401/06/20 | T-1393 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05759 | 44828 | 1401/07/02 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249409 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1393 | 2022-09-11 | 1401/06/20 | T-1393 | 44815 | 1401/06/20 | BK-SUR-ENG-ELE-01-05759 | 44828 | 1401/07/02 | CM-C2 | [6 empty] | 1401-2294-249409 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
2 | 11 | 2 | 3 | 2 | 2 | 0 | 2.11.3.2.2 |  | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 2 | 2 | 1 | 2.11.2.3.2.2.1 | BK-BK05-PEDCO-110-EL-TB-0002 | TBE For LV Switchgear & MCC - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0002 | BK-BK05-PEDCO-110-EL-TB-0002 | BK | BK05 | PEDCO | 110 | EL | TB | 0002 | F0Z-708484 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 3 | 3 | 0 | 0 | 2.11.2.3.3 |  | Emergency Diesel Generator
2 | 11 | 2 | 3 | 3 | 1 | 0 | 2.11.3.3.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 3 | 1 | 1 | 2.11.2.3.3.1.1 | BK-BK05-PEDCO-110-EL-MR-0003 | PMR For Emergency Diesel Generator - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0003 | BK-BK05-PEDCO-110-EL-MR-0003 | BK | BK05 | PEDCO | 110 | EL | MR | 0003 | F0Z-708485 | IFI | IFI | 2022-09-03 | 2022-09-08 | 2022-09-12 | 5 | 4 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-20 |  |  | D00 | IFI | T-1293 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216140 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1293 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-ELE-01-05545 | 44801 | 1401/06/06 | CM-C2 | [6 empty] | 1401-2294-216140 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | AP
2 | 11 | 2 | 3 | 3 | 2 | 0 | 2.11.3.3.2 |  | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 3 | 2 | 1 | 2.11.2.3.3.2.1 | BK-BK05-PEDCO-110-EL-TB-0003 | TBE For Emergency Diesel Generator - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0003 | BK-BK05-PEDCO-110-EL-TB-0003 | BK | BK05 | PEDCO | 110 | EL | TB | 0003 | F0Z-708486 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 3 | 4 | 0 | 0 | 2.11.2.3.4 |  | UPS System
2 | 11 | 2 | 3 | 4 | 1 | 0 | 2.11.3.4.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 4 | 1 | 1 | 2.11.2.3.4.1.1 | BK-BK05-PEDCO-110-EL-MR-0004 | PMR For UPS System - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0004 | BK-BK05-PEDCO-110-EL-MR-0004 | BK | BK05 | PEDCO | 110 | EL | MR | 0004 | F0Z-708487 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 3 | 4 | 2 | 0 | 2.11.3.4.2 |  | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 4 | 2 | 1 | 2.11.2.3.4.2.1 | BK-BK05-PEDCO-110-EL-TB-0004 | TBE For UPS System - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0004 | BK-BK05-PEDCO-110-EL-TB-0004 | BK | BK05 | PEDCO | 110 | EL | TB | 0004 | F0Z-708488 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 3 | 5 | 0 | 0 | 2.11.2.3.5 |  | DC Charger
2 | 11 | 2 | 3 | 5 | 1 | 0 | 2.11.3.5.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 5 | 1 | 1 | 2.11.2.3.5.1.1 | BK-BK05-PEDCO-110-EL-MR-0005 | PMR For DC Charger - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0005 | BK-BK05-PEDCO-110-EL-MR-0005 | BK | BK05 | PEDCO | 110 | EL | MR | 0005 | F0Z-708489 | IFI | IFI | 2022-05-11 | 2022-05-28 | 2022-05-29 | 17 | 1 | 18 | IFI | 2022-09-07 | 2022-09-08 | 2022-09-12 | 1 | 4 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-27 |  |  | D01 | IFI | T-1311 | 44797 | 1401/06/01 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-BK05-PEDCO-110-EL-MR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0866 | 2022-04-27 | 1401/02/07 | T-0866 | 44678 | 1401/02/07 | BK-SUR-ENG-ELE-01-04213 | 44691 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78862 | 2022-05-28 | 1401/03/08 | 44710 | 1401/03/09 | CM | [10 empty] | D01 | IFI | T-1311 | 44797 | 1401/06/01 |  |  |  | BK-SUR-ENG-ELE-01-05607 | 44811 | 1401/06/16 | AP | [6 empty] | 1401-2294-216127 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-BK05-PEDCO-110-EL-MR-0005_D00
2 | 11 | 2 | 3 | 5 | 2 | 0 | 2.11.3.5.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 5 | 2 | 1 | 2.11.2.3.5.2.1 | BK-BK05-PEDCO-110-EL-TB-0005 | TBE For DC Charger - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0005 | BK-BK05-PEDCO-110-EL-TB-0005 | BK | BK05 | PEDCO | 110 | EL | TB | 0005 | F0Z-708490 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 6 | 0 | 0 | 2.11.2.3.6 |  | Capacitor Bank | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 6 | 1 | 0 | 2.11.3.6.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 6 | 1 | 1 | 2.11.2.3.6.1.1 | BK-BK05-PEDCO-110-EL-MR-0006 | PMR For Capacitor Bank - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0006 | BK-BK05-PEDCO-110-EL-MR-0006 | BK | BK05 | PEDCO | 110 | EL | MR | 0006 | F0Z-708491 | IFI | IFI | 2022-08-13 | 2022-08-18 | 2022-08-20 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFI | T-1215 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183488 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1215 | 2022-07-30 | 1401/05/08 |  |  |  | BK-SUR-ENG-ELE-01-05415 | 44786 | 1401/05/22 | AP | [6 empty] | 1401-2294-183488 | 2022-08-18 | 1401/05/27 | 44793 | 1401/05/29 | RJ
2 | 11 | 2 | 3 | 6 | 2 | 0 | 2.11.3.6.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 6 | 2 | 1 | 2.11.2.3.6.2.1 | BK-BK05-PEDCO-110-EL-TB-0006 | TBE For Capacitor Bank - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0006 | BK-BK05-PEDCO-110-EL-TB-0006 | BK | BK05 | PEDCO | 110 | EL | TB | 0006 | F0Z-708492 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 7 | 0 | 0 | 2.11.2.3.7 |  | Lighting & Distribution Main Panels | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 7 | 1 | 0 | 2.11.3.7.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 7 | 1 | 1 | 2.11.2.3.7.1.1 | BK-BK05-PEDCO-110-EL-MR-0007 | PMR For Lighting & Distribution Main Panels - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0007 | BK-BK05-PEDCO-110-EL-MR-0007 | BK | BK05 | PEDCO | 110 | EL | MR | 0007 | F0Z-708493 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 7 | 2 | 0 | 2.11.3.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 7 | 2 | 1 | 2.11.2.3.7.2.1 | BK-BK05-PEDCO-110-EL-TB-0007 | TBE For Lighting & Distribution Main Panels - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0007 | BK-BK05-PEDCO-110-EL-TB-0007 | BK | BK05 | PEDCO | 110 | EL | TB | 0007 | F0Z-708494 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 8 | 0 | 0 | 2.11.2.3.8 |  | Earthing & Lightning System | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 8 | 1 | 0 | 2.11.3.8.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 8 | 1 | 1 | 2.11.2.3.8.1.1 | BK-BK05-PEDCO-110-EL-MR-0008 | PMR For Earthing & Lightning System - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0008 | BK-BK05-PEDCO-110-EL-MR-0008 | BK | BK05 | PEDCO | 110 | EL | MR | 0008 | F0Z-708495 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 8 | 2 | 0 | 2.11.3.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 8 | 2 | 1 | 2.11.2.3.8.2.1 | BK-BK05-PEDCO-110-EL-TB-0008 | TBE For Earthing & Lightning System - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0008 | BK-BK05-PEDCO-110-EL-TB-0008 | BK | BK05 | PEDCO | 110 | EL | TB | 0008 | F0Z-708496 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 9 | 0 | 0 | 2.11.2.3.9 |  | Lighting and Small Power Equipment
2 | 11 | 2 | 3 | 9 | 1 | 0 | 2.11.3.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 9 | 1 | 1 | 2.11.2.3.9.1.1 | BK-BK05-PEDCO-110-EL-MR-0009 | PMR For Lighting and Small Power Equipment - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0009 | BK-BK05-PEDCO-110-EL-MR-0009 | BK | BK05 | PEDCO | 110 | EL | MR | 0009 | F0Z-708497 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 9 | 2 | 0 | 2.11.3.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 9 | 2 | 1 | 2.11.2.3.9.2.1 | BK-BK05-PEDCO-110-EL-TB-0009 | TBE For Lighting and Small Power Equipment - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0009 | BK-BK05-PEDCO-110-EL-TB-0009 | BK | BK05 | PEDCO | 110 | EL | TB | 0009 | F0Z-708498 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 10 | 0 | 0 | 2.11.2.3.10 |  | Tray/Ladder and Accessories
2 | 11 | 2 | 3 | 10 | 1 | 0 | 2.11.3.10.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 10 | 1 | 1 | 2.11.2.3.10.1.1 | BK-BK05-PEDCO-110-EL-MR-0010 | PMR For Tray/Ladder and Accessories - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0010 | BK-BK05-PEDCO-110-EL-MR-0010 | BK | BK05 | PEDCO | 110 | EL | MR | 0010 | F0Z-708499 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 10 | 2 | 0 | 2.11.3.10.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 10 | 2 | 1 | 2.11.2.3.10.2.1 | BK-BK05-PEDCO-110-EL-TB-0010 | TBE For Tray/Ladder and Accessories - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0010 | BK-BK05-PEDCO-110-EL-TB-0010 | BK | BK05 | PEDCO | 110 | EL | TB | 0010 | F0Z-708500 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 3 | 11 | 0 | 0 | 2.11.2.3.11 |  | Power & Control Cables
2 | 11 | 2 | 3 | 11 | 1 | 0 | 2.11.3.11.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 11 | 1 | 1 | 2.11.2.3.11.1.1 | BK-BK05-PEDCO-110-EL-MR-0011 | PMR For Power & Control Cables - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0011 | BK-BK05-PEDCO-110-EL-MR-0011 | BK | BK05 | PEDCO | 110 | EL | MR | 0011 | F0Z-708501 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 11 | 2 | 0 | 2.11.3.11.2 |  | Technical Bid Evaluation (TBE) | [61 empty] | Deleted
2 | 11 | 2 | 3 | 11 | 2 | 1 | 2.11.2.3.11.2.1 | BK-BK05-PEDCO-110-EL-TB-0011 | TBE For Power & Control Cables - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0011 | BK-BK05-PEDCO-110-EL-TB-0011 | BK | BK05 | PEDCO | 110 | EL | TB | 0011 | F0Z-708502 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 12 | 0 | 0 | 2.11.2.3.12 |  | Electrical Bulk Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 12 | 1 | 0 | 2.11.3.12.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 12 | 1 | 1 | 2.11.2.3.12.1.1 | BK-BK05-PEDCO-110-EL-MR-0012 | PMR For Electrical Bulk Items - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0012 | BK-BK05-PEDCO-110-EL-MR-0012 | BK | BK05 | PEDCO | 110 | EL | MR | 0012 | F0Z-708503 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 3 | 12 | 2 | 0 | 2.11.3.12.2 |  | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 12 | 2 | 1 | 2.11.2.3.12.2.1 | BK-BK05-PEDCO-110-EL-TB-0012 | TBE For Electrical Bulk Items - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0012 | BK-BK05-PEDCO-110-EL-TB-0012 | BK | BK05 | PEDCO | 110 | EL | TB | 0012 | F0Z-708504 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 3 | 13 | 0 | 0 | 2.11.2.3.13 |  | Transmission Over head Line
2 | 11 | 2 | 3 | 13 | 1 | 0 | 2.11.3.13.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 13 | 1 | 1 | 2.11.2.3.13.1.1 | BK-BK05-PEDCO-110-EL-MR-0013 | PMR For Transmission Over head Line - BK05 |  | BK-BK05-PEDCO-110-EL-MR-0013 | BK-BK05-PEDCO-110-EL-MR-0013 | BK | BK05 | PEDCO | 110 | EL | MR | 0013 | F0Z-708505 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 3 | 13 | 2 | 0 | 2.11.3.13.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 3 | 13 | 2 | 1 | 2.11.2.3.13.2.1 | BK-BK05-PEDCO-110-EL-TB-0013 | TBE For Transmission Over head Line - BK05 |  | BK-BK05-PEDCO-110-EL-TB-0013 | BK-BK05-PEDCO-110-EL-TB-0013 | BK | BK05 | PEDCO | 110 | EL | TB | 0013 | F0Z-708506 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 4 | 0 | 0 | 0 | 2.11.2.4 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 4 | 1 | 0 | 0 | 2.11.2.4.1 |  | Steel Structure Items
2 | 11 | 2 | 4 | 1 | 1 | 0 | 2.11.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 4 | 1 | 1 | 1 | 2.11.2.4.1.1.1 | BK-BK05-PEDCO-110-ST-MR-0001 | PMR For Steel Structure Items - BK05 |  | BK-BK05-PEDCO-110-ST-MR-0001 | BK-BK05-PEDCO-110-ST-MR-0001 | BK | BK05 | PEDCO | 110 | ST | MR | 0001 | F0Z-708507 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 4 | 1 | 2 | 0 | 2.11.4.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 4 | 1 | 2 | 1 | 2.11.2.4.1.2.1 | BK-BK05-PEDCO-110-ST-TB-0001 | TBE For Steel Structure Items - BK05 |  | BK-BK05-PEDCO-110-ST-TB-0001 | BK-BK05-PEDCO-110-ST-TB-0001 | BK | BK05 | PEDCO | 110 | ST | TB | 0001 | F0Z-708508 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 2 | 4 | 2 | 0 | 0 | 2.11.2.4.2 |  | Anchor Bolts | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 4 | 2 | 1 | 0 | 2.11.4.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 4 | 2 | 1 | 1 | 2.11.2.4.2.1.1 | BK-BK05-PEDCO-110-ST-MR-0002 | PMR For Anchor Bolts - BK05 |  | BK-BK05-PEDCO-110-ST-MR-0002 | BK-BK05-PEDCO-110-ST-MR-0002 | BK | BK05 | PEDCO | 110 | ST | MR | 0002 | F0Z-708509 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 4 | 2 | 2 | 0 | 2.11.4.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 4 | 2 | 2 | 1 | 2.11.2.4.2.2.1 | BK-BK05-PEDCO-110-ST-TB-0002 | TBE For Anchor Bolts - BK05 |  | BK-BK05-PEDCO-110-ST-TB-0002 | BK-BK05-PEDCO-110-ST-TB-0002 | BK | BK05 | PEDCO | 110 | ST | TB | 0002 | F0Z-708510 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 4 | 3 | 0 | 0 | 2.11.2.4.3 |  | Blast Proof Doors | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 2 | 4 | 3 | 1 | 0 | 2.11.4.3.1 |  | Purchase Material Requisition (PMR)
2 | 11 | 2 | 4 | 3 | 1 | 1 | 2.11.2.4.3.1.1 | BK-BK05-PEDCO-110-ST-MR-0003 | PMR For Blast Proof Doors - BK05 |  | BK-BK05-PEDCO-110-ST-MR-0003 | BK-BK05-PEDCO-110-ST-MR-0003 | BK | BK05 | PEDCO | 110 | ST | MR | 0003 | F0Z-708511 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 2 | 4 | 3 | 2 | 0 | 2.11.4.3.2 |  | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 4 | 3 | 2 | 1 | 2.11.2.4.3.2.1 | BK-BK05-PEDCO-110-ST-TB-0003 | TBE For Blast Proof Doors - BK05 |  | BK-BK05-PEDCO-110-ST-TB-0003 | BK-BK05-PEDCO-110-ST-TB-0003 | BK | BK05 | PEDCO | 110 | ST | TB | 0003 | F0Z-708512 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 3 | 0 | 0 | 0 | 0 | 2.11.3 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 3 | 0 | 0 | 1 | 0 | 2.11.3.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 3 | 0 | 0 | 1 | 1 | 2.11.3.1 | BK-BK05-PEDCO-110-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure - BK05 |  | BK-BK05-PEDCO-110-CO-PR-0001 | BK-BK05-PEDCO-110-CO-PR-0001 | BK | BK05 | PEDCO | 110 | CO | PR | 0001 | F0Z-708513 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
2 | 11 | 4 | 0 | 0 | 0 | 0 | 2.11.4 |  | Field Engineering
2 | 11 | 4 | 0 | 0 | 1 | 0 | 2.11.4.1 |  | Query | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 4 | 0 | 0 | 1 | 1 | 2.11.4.1 | BK-BK05-PEDCO-110-GE-TQ-0001 | Technical/Site Queries |  | BK-BK05-PEDCO-110-GE-TQ-0001 | BK-BK05-PEDCO-110-GE-TQ-0001 | BK | BK05 | PEDCO | 110 | GE | TQ | 0001 | F7Z-708514 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 4 | 0 | 0 | 2 | 0 | 2.11.4.2 |  | Dossier
2 | 11 | 4 | 0 | 0 | 2 | 1 | 2.11.4.2 | BK-BK05-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - BK05 |  | BK-BK05-PEDCO-110-GE-DO-0001 | BK-BK05-PEDCO-110-GE-DO-0001 | BK | BK05 | PEDCO | 110 | GE | DO | 0001 | F0Z-708515 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 5 | 0 | 0 | 0 | 0 | 2.11.5 |  | Engineering Final Documentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 5 | 0 | 0 | 1 | 0 | 2.11.5.1 |  | Manual
2 | 11 | 5 | 0 | 0 | 1 | 1 | 2.11.5.1 | BK-BK05-PEDCO-110-GE-ML-0001 | Operating Manual - BK05 |  | BK-BK05-PEDCO-110-GE-ML-0001 | BK-BK05-PEDCO-110-GE-ML-0001 | BK | BK05 | PEDCO | 110 | GE | ML | 0001 | F0Z-708516 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 5 | 0 | 0 | 2 | 0 | 2.11.5.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
2 | 11 | 5 | 0 | 0 | 2 | 1 | 2.11.5.2 | BK-BK05-PEDCO-110-GE-DO-0001 | As-Built Document Booklets - BK05 |  | BK-BK05-PEDCO-110-GE-DO-0001 | [10 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
2 | 11 | 5 | 0 | 0 | 2 | 2 | 2.11.5.2 | BK-BK05-PEDCO-110-GE-DO-0002 | Final Engineering Dossier - BK05 |  | BK-BK05-PEDCO-110-GE-DO-0002 | BK-BK05-PEDCO-110-GE-DO-0002 | BK | BK05 | PEDCO | 110 | GE | DO | 0002 | F0Z-708517 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  | SURFACE DEVELOPMENT | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 0 | 0 | 0 | 0 | 0 | 3.1 |  | Package 11- EPC Pipeline 8" & 4"
3 | 1 | 1 | 0 | 0 | 0 | 0 | 3.1.1 |  | Basic Design Endorsement | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 1 | 0 | 0 | 0 | 1 | 3.1.1.1 | BK-PPL-PEDCO-320-GE-RT-0001 | Endorsement Report For Basic Design & Scope of Work |  | BK-PPL-PEDCO-320-GE-RT-0001 | [8 empty] | - |  | IFC | 2021-08-14 | 2021-08-28 | 2021-09-07 | 14 | 10 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-31 |  |  | B00 | IFC | T-0023 | 44408 | 1400/05/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-176098 | 44436 | 1400/06/06 | 44446 | 1400/06/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B00-Reject |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | [13 empty] | 1400-2294-176098 | 2021-08-28 | 1400/06/06 | 44446 | 1400/06/16 | CM | [8 empty] | B00-Reject
3 | 1 | 2 | 0 | 0 | 0 | 0 | 3.1.2 |  | Value Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 2 | 0 | 0 | 0 | 1 | 3.1.2.1 | BK-PPL-PEDCO-320-GE-RT-0002 | Value Engineering Study Report |  | BK-PPL-PEDCO-320-GE-RT-0002 | BK-PPL-PEDCO-320-GE-RT-0002 | BK | PPL | PEDCO | 320 | GE | RT | 0002 | F0Z-708518 | IFI | IFC | 2022-02-15 | 2022-03-10 | 2022-03-15 | 23 | 5 | 28 | IFA | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | IFA | 2022-07-27 | 2022-08-03 | 2022-08-13 | 7 | 10 | 17 | IFA | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-01 |  |  | D03 | IFA | T-1558 | 44860 | 1401/08/04 | T-1558 | 44860 | 1401/08/04 | BK-SUR-ENG-GEN-01-06197 | 44881 | 1401/08/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-GE-RT-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0531 | 2022-02-01 | 1400/11/12 |  |  |  | BK-SUR-ENG-PCS-00-03282 | 44622 | 1400/12/11 | CM-C2 | [6 empty] | 1400-2294-443284 | 2022-03-10 | 1400/12/19 | 44635 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0785 | 44661 | 1400/01/21 | [7 empty] | PEDCO-CRS-BK-PPL-PEDCO-320-GE-RT-0002-D00 | [5 empty] | 1401-2294-68426 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-PPL-PEDCO-320-GE-RT-0002_D00 | [9 empty] | D02 | IFA | T-1150 | 44755 | 1401/04/22 | [13 empty] | 1401-2294-165152 | 44776 | 1401/05/12 | 44786 | 1401/05/22 | RJ | NISOC-CRS-BK-PPL-PEDCO-320-GE-RT-0002_D01 | [9 empty] | D03 | IFA | T-1558 | 44860 | 1401/08/04 | T-1558 | 44860 | 1401/08/04 | BK-SUR-ENG-GEN-01-06197 | 44881 | 1401/08/25 | CM-C2 | [12 empty] | NISOC-CRS-BK-PPL-PEDCO-320-GE-RT-0002_D02
3 | 1 | 2 | 0 | 0 | 0 | 2 | 3.1.2.2 | BK-PPL-PEDCO-320-GE-RT-0003 | HAZID Report For Pipeline |  | BK-PPL-PEDCO-320-GE-RT-0003 | BK-PPL-PEDCO-320-GE-RT-0003 | BK | PPL | PEDCO | 320 | GE | RT | 0003 | F0Z-708519 | IFI | IFI | 2022-08-15 | 2022-09-19 | 2022-09-26 | 35 | 7 | 42 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-01 | 2022-11-19 |  | D01 | FI | T-1591 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1233 | 2022-08-01 | 1401/05/10 | [13 empty] | 1401-2294-228737 | 2022-09-19 | 1401/06/28 | 44830 | 1401/07/04 | AP | [10 empty] | D01 | FI | T-1591 | 44884 | 1401/08/28
3 | 1 | 2 | 0 | 0 | 0 | 3 | 3.1.2.3 | BK-PPL-PEDCO-320-GE-RT-0004 | HAZOP Report For Pipeline |  | BK-PPL-PEDCO-320-GE-RT-0004 | BK-PPL-PEDCO-320-GE-RT-0004 | BK | PPL | PEDCO | 320 | GE | RT | 0004 | F0Z-708520 | IFI | IFI | 2022-08-15 | 2022-09-19 | 2022-09-26 | 35 | 7 | 42 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-01 | 2022-11-19 |  | D01 | FI | T-1591 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1233 | 2022-08-01 | 1401/05/10 | [13 empty] | 1401-2294-228737 | 2022-09-19 | 1401/06/28 | 44830 | 1401/07/04 | AP | [10 empty] | D01 | FI | T-1591 | 44884 | 1401/08/28
3 | 1 | 3 | 0 | 0 | 0 | 0 | 3.1.3 |  | Detail Design
3 | 1 | 3 | 1 | 0 | 0 | 0 | 3.1.3.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 1 | 0 | 1 | 0 | 3.1.3.1 |  | Philosophy | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 1 | 0 | 1 | 1 | 3.1.3.1.1.1 | BK-PPL-PEDCO-320-PR-PH-0001 | Drainage Philosophy |  | BK-PPL-PEDCO-320-PR-PH-0001 | BK-PPL-PEDCO-320-PR-PH-0001 | BK | PPL | PEDCO | 320 | PR | PH | 0001 | F0Z-708521 | AFD | IFC | 2022-02-14 | 2022-02-26 | 2022-02-21 | 12 | -5 | 7 | IFA | 2022-04-24 | 2022-05-07 | 2022-05-18 | 13 | 11 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-31 |  |  | D01 | IFA | T-0798 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03987 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-49890 | 44688 | 1401/02/17 | 44699 | 1401/02/28 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PH-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0527 | 2022-01-31 | 1400/11/11 |  |  |  | BK-SUR-ENG-PCS-00-03180 | 44614 | 1400/12/03 | CM-C2 | [6 empty] | 1400-2294-419620 | 2022-02-26 | 1400/12/07 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0798 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03987 | 44670 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D00 | [5 empty] | 1401-2294-49890 | 44688 | 1401/02/17 | 44699 | 1401/02/28 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PH-0001_D00
3 | 1 | 3 | 1 | 0 | 1 | 2 | 3.1.3.1.1.2 | BK-PPL-PEDCO-320-PR-PH-0002 | Control Philosophy |  | BK-PPL-PEDCO-320-PR-PH-0002 | BK-PPL-PEDCO-320-PR-PH-0002 | BK | PPL | PEDCO | 320 | PR | PH | 0002 | F0Z-708522 | AFD | IFC | 2022-05-23 | 2022-06-13 | 2022-06-15 | 21 | 2 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-09 |  |  | D00 | IFC | T-0921 | 44690 | 1401/02/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-100891 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 |  |  |  | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C2 | [6 empty] | 1401-2294-100891 | 2022-06-13 | 1401/03/23 | 44727 | 1401/03/25 | CM
3 | 1 | 3 | 1 | 0 | 1 | 3 | 3.1.3.1.1.3 | BK-PPL-PEDCO-320-PR-PH-0003 | Flare,Blow Down And Relief Philosophy |  | BK-PPL-PEDCO-320-PR-PH-0003 | BK-PPL-PEDCO-320-PR-PH-0003 | BK | PPL | PEDCO | 320 | PR | PH | 0003 | F0Z-708523 | AFD | IFC | 2022-02-20 | 2022-03-08 | 2022-03-06 | 16 | -2 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-0555 | 44598 | 1400/11/17 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03181 | 44614 | 1400/12/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-437177 | 44628 | 1400/12/18 | 44626 | 1400/12/15 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0555 | 2022-02-06 | 1400/11/17 |  |  |  | BK-SUR-ENG-PCS-00-03181 | 44614 | 1400/12/03 | CM-C3 | [6 empty] | 1400-2294-437177 | 2022-03-08 | 1400/12/18 | 44626 | 1400/12/15 | RJ
3 | 1 | 3 | 1 | 0 | 1 | 4 | 3.1.3.1.1.4 | BK-PPL-PEDCO-320-PR-PH-0004 | Isolation Philosophy |  | BK-PPL-PEDCO-320-PR-PH-0004 | BK-PPL-PEDCO-320-PR-PH-0004 | BK | PPL | PEDCO | 320 | PR | PH | 0004 | F0Z-708524 | AFD | IFC | 2021-12-05 | 2021-12-11 | 2021-12-14 | 6 | 3 | 9 | IFA | 2022-02-12 | 2022-03-06 | 2022-03-08 | 22 | 2 | 24 | IFA | 2022-05-09 | 2022-05-31 | 2022-06-06 | 22 | 6 | 28 | AFD | 2022-09-03 | 2022-10-25 | 2022-10-30 | 52 | 5 | 57 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-21 | 2022-08-20 |  | D03 | AFD | T-1290 | 44793 | 1401/05/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281108 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 44537 | 1400/09/16 | CM-C2 | [6 empty] | 1400-2294-312238 | 2021-12-11 | 1400/09/20 | 44544 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0520 | 44590 | 1400/11/09 |  |  |  | BK-SUR-ENG-PCS-00-03179 | 44614 | 1400/12/03 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D00 | [5 empty] | 1400-2294-436900 | 44626 | 1400/12/15 | 44628 | 1400/12/17 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D00 | [9 empty] | D02 | IFA | T-0863 | 44676 | 1401/02/06 |  |  |  | BK-SUR-ENG-CIV-01-04056 | 44676 | 1401/02/05 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D01 | BK-SUR-ENG-PCS-01-04346 | 44703 | 1401/03/01 | CM-C2 |  | 1401-2294-85238 | 44712 | 1401/03/10 | 44718 | 1401/03/16 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D01 | [9 empty] | D03 | AFD | T-1290 | 44793 | 1401/05/29 | [13 empty] | 1401-2294-281108 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | AP
3 | 1 | 3 | 1 | 0 | 1 | 5 | 3.1.3.1.1.5 | BK-PPL-PEDCO-320-PR-PH-0005 | ESD Philosophy |  | BK-PPL-PEDCO-320-PR-PH-0005 | BK-PPL-PEDCO-320-PR-PH-0005 | BK | PPL | PEDCO | 320 | PR | PH | 0005 | F0Z-708525 | AFD | IFC | 2022-05-23 | 2022-06-13 | 2022-06-15 | 21 | 2 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-09 |  |  | D00 | IFC | T-0921 | 44690 | 1401/02/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-100891 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 |  |  |  | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C2 | [6 empty] | 1401-2294-100891 | 2022-06-13 | 1401/03/23 | 44727 | 1401/03/25 | CM
3 | 1 | 3 | 1 | 0 | 2 | 0 | 3.1.3.2 |  | Description | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 1 | 0 | 2 | 1 | 3.1.3.1.2.1 | BK-PPL-PEDCO-320-PR-DP-0001 | Process Description |  | BK-PPL-PEDCO-320-PR-DP-0001 | BK-PPL-PEDCO-320-PR-DP-0001 | BK | PPL | PEDCO | 320 | PR | DP | 0001 | F0Z-708526 | AFD | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-06-05 | 2022-06-15 | 2022-06-20 | 10 | 5 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-19 |  |  | D01 | IFA | T-0990 | 44703 | 1401/03/01 | T-0990 | 44704 | 1401/03/02 | BK-SUR-ENG-PCS-01-04737 | 44730 | 1401/03/28 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-DP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-104506 | 44727 | 1401/03/25 | 44732 | 1401/03/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-DP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0607 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PCS-00-03322 | 44625 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-443237 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0990 | 44703 | 1401/03/01 | T-0990 | 44704 | 1401/03/02 | BK-SUR-ENG-PCS-01-04737 | 44730 | 1401/03/28 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-DP-0001_D00 | [5 empty] | 1401-2294-104506 | 44727 | 1401/03/25 | 44732 | 1401/03/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-DP-0001_D00
3 | 1 | 3 | 1 | 0 | 3 | 0 | 3.1.3.3 |  | Calculation
3 | 1 | 3 | 1 | 0 | 3 | 1 | 3.1.3.1.3.1 | BK-PPL-PEDCO-320-PR-CN-0001 | Calculation Note For PSV Sizing |  | BK-PPL-PEDCO-320-PR-CN-0001 | BK-PPL-PEDCO-320-PR-CN-0001 | BK | PPL | PEDCO | 320 | PR | CN | 0001 | F0Z-708527 | AFD | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-06-05 | 2022-06-15 | 2022-06-20 | 10 | 5 | 15 | AFD | 2022-11-07 | 0 | 0 | -44872 | 0 | -44872 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-19 | 2022-10-24 |  | D02 | AFD | T-1543 | 44858 | 1401/08/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-06115 | 44872 | 1401/08/16 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0607 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PCS-00-03322 | 44625 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-443237 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0990 | 44703 | 1401/03/01 | T-0990 | 44704 | 1401/03/02 | BK-SUR-ENG-PCS-01-04737 | 44730 | 1401/03/28 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-CN-0001_D00 | [5 empty] | 1401-2294-104506 | 44727 | 1401/03/25 | 44732 | 1401/03/30 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PR-CN-0001_D00 | [9 empty] | D02 | AFD | T-1543 | 44858 | 1401/08/02 |  |  |  | BK-SUR-ENG-PCS-01-06115 | 44872 | 1401/08/16 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-CN-0001_D01
3 | 1 | 3 | 1 | 0 | 4 | 0 | 3.1.3.4 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 1 | 0 | 4 | 1 | 3.1.3.1.4.1 | BK-PPL-PEDCO-320-PR-PI-0003 | Symbol & Legend For PFD and P&ID |  | BK-PPL-PEDCO-320-PR-PI-0003 | BK-PPL-PEDCO-320-PR-PI-0003 | BK | PPL | PEDCO | 320 | PR | PI | 0003 | F2A-708528 | AFC | IFC | 2022-02-07 | 2022-02-12 | 2022-02-22 | 5 | 10 | 15 | IFA | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-24 |  |  | D01 | IFA | T-0713 | 44629 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03831 | 44661 | 1401/01/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43235 | 44680 | 1401/02/09 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0499 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-PCS-00-03085 | 44608 | 1400/11/27 | CM-C3 | [6 empty] | 1400-2294-407038 | 2022-02-12 | 1400/11/23 | 44614 | 1400/12/03 | CM | [10 empty] | D01 | IFA | T-0713 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03831 | 44661 | 1401/01/21 | CM-C2 | [6 empty] | 1401-2294-43235 | 44680 | 1401/02/09 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0003_D00
3 | 1 | 3 | 1 | 0 | 4 | 2 | 3.1.3.1.4.2 | BK-PPL-PEDCO-320-PR-PF-0001 | Process Flow Diagram For pipelines |  | BK-PPL-PEDCO-320-PR-PF-0001 | BK-PPL-PEDCO-320-PR-PF-0001 | BK | PPL | PEDCO | 320 | PR | PF | 0001 | F2A-708529 | AFC | IFC | 2021-12-01 | 2021-12-08 | 2021-12-14 | 7 | 6 | 13 | IFA | 2022-02-08 | 2022-02-20 | 2022-02-22 | 12 | 2 | 14 | IFA | 2022-04-30 | 2022-05-12 | 2022-05-16 | 12 | 4 | 16 | AFC | 2022-10-16 | 2022-11-15 | 2022-11-16 | 30 | 1 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-17 |  |  | D03 | AFC | T-1448 | 44836 | 1401/07/10 | T-1448 | 44837 | 1401/07/11 | BK-SUR-ENG-PCS-01-05944 | 44856 | 1401/07/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-312894 | 44880 | 1401/08/24 | 44881 | 1401/08/25 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0254 | 2021-11-17 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02171 | 44531 | 1400/09/10 | CM-C3 | [6 empty] | 1400-2294-310826 | 2021-12-08 | 1400/09/17 | 44544 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0508 | 44586 | 1400/11/05 |  |  |  | BK-SUR-ENG-PCS-00-03124 | 44611 | 1400/11/30 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D00 | [5 empty] | 1400-2294-415917 | 44612 | 1400/12/01 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D00 | [9 empty] | D02 | IFA | T-0816 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PCS-01-04101 | 44682 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D01 | [5 empty] | 1401-2294-59525 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D01 | [9 empty] | D03 | AFC | T-1448 | 44836 | 1401/07/10 | T-1448 | 44837 | 1401/07/11 | BK-SUR-ENG-PCS-01-05944 | 44856 | 1401/07/30 | AP | [6 empty] | 1401-2294-312894 | 44880 | 1401/08/24 | 44881 | 1401/08/25 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D02
3 | 1 | 3 | 1 | 0 | 4 | 3 | 3.1.3.1.4.3 | BK-PPL-PEDCO-320-PR-PI-0001 | P&ID - Gas Pipeline (to Siahmakan G.I. Station) |  | BK-PPL-PEDCO-320-PR-PI-0001 | BK-PPL-PEDCO-320-PR-PI-0001 | BK | PPL | PEDCO | 320 | PR | PI | 0001 | F2A-708530 | AFC | IFC | 2021-12-01 | 2021-12-08 | 2021-12-14 | 7 | 6 | 13 | IFA | 2022-02-07 | 2022-02-26 | 2022-02-20 | 19 | -6 | 13 | IFA | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | IFA | 2022-09-12 | 0 | 0 | -44816 | 0 | -44816 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-17 |  |  | D03 | IFA | T-1337 | 44802 | 1401/06/7 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05704 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0254 | 2021-11-17 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02171 | 44531 | 1400/09/10 | CM-C3 | [6 empty] | 1400-2294-310826 | 2021-12-08 | 1400/09/17 | 44544 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0503 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-PCS-00-03096 | 44611 | 1400/11/30 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D00 | [5 empty] | 1400-2294-416040 | 44618 | 1400/12/07 | 44612 | 1400/12/01 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0713 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03831 | 44661 | 1401/01/21 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D01 | [5 empty] | 1401-2294-43235 | 44680 | 1401/02/09 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-1337 | 44802 | 1401/06/7 |  |  |  | BK-SUR-ENG-PCS-01-05704 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D02 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D02
3 | 1 | 3 | 1 | 0 | 4 | 4 | 3.1.3.1.4.4 | BK-PPL-PEDCO-320-PR-PI-0002 | P&ID - Condensate Pipeline (to Binak PU) |  | BK-PPL-PEDCO-320-PR-PI-0002 | BK-PPL-PEDCO-320-PR-PI-0002 | BK | PPL | PEDCO | 320 | PR | PI | 0002 | F2A-708531 | AFC | IFC | 2021-12-01 | 2021-12-08 | 2021-12-14 | 7 | 6 | 13 | IFA | 2022-02-07 | 2022-02-26 | 2022-02-20 | 19 | -6 | 13 | IFA | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | IFA | 2022-09-11 | 0 | 0 | -44815 | 0 | -44815 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-17 |  |  | D03 | IFA | T-1328 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05632 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0254 | 2021-11-17 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02171 | 44531 | 1400/09/10 | CM-C3 | [6 empty] | 1400-2294-310826 | 2021-12-08 | 1400/09/17 | 44544 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0503 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-PCS-00-03096 | 44611 | 1400/11/30 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D00 | [5 empty] | 1400-2294-416040 | 44618 | 1400/12/07 | 44612 | 1400/12/01 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0713 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03831 | 44661 | 1401/01/21 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D01 | [5 empty] | 1401-2294-43235 | 44680 | 1401/02/09 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-1328 | 44801 | 1401/06/06 |  |  |  | BK-SUR-ENG-PCS-01-05632 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D02 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D02
3 | 1 | 3 | 1 | 0 | 4 | 5 | 3.1.3.1.4.5 | BK-PPL-PEDCO-320-PR-BD-0001 | ESD Block Diagram |  | BK-PPL-PEDCO-320-PR-BD-0001 | BK-PPL-PEDCO-320-PR-BD-0001 | BK | PPL | PEDCO | 320 | PR | BD | 0001 | F2J-708532 | AFC | IFC | 2022-06-13 | 2022-06-22 | 2022-06-22 | 9 | 0 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Deleted | 2022-05-30 |  |  | D00 | IFC | T-1022 | 44711 | 1401/03/09 | T-1022 | 44711 | 1401/03/09 | BK-SUR-ENG-PCS-01-04825 | 44723 | 1401/04/01 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-109262 | 44734 | 1401/03/30 | 44734 | 1401/04/01 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1022 | 2022-05-30 | 1401/03/09 | T-1022 | 44711 | 1401/03/09 | BK-SUR-ENG-PCS-01-04825 | 44723 | 1401/04/01 | CM-C3 | [6 empty] | 1401-2294-109262 | 2022-06-22 | 1401/03/30 | 44734 | 1401/04/01 | CM
3 | 1 | 3 | 1 | 0 | 4 | 6 | 3.1.3.1.4.6 | BK-PPL-PEDCO-320-PR-CE-0001 | Cause & Effect Diagram |  | BK-PPL-PEDCO-320-PR-CE-0001 | BK-PPL-PEDCO-320-PR-CE-0001 | BK | PPL | PEDCO | 320 | PR | CE | 0001 | F0Z-708533 | AFC | IFC | 2022-06-25 | 2022-10-10 | 2022-10-12 | 107 | 2 | 109 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-11 |  |  | D00 | IFC | T-1053 | 44723 | 1401/03/21 | T-1053 | 44723 | 1401/03/21 | BK-SUR-ENG-PCS-01-04989 | 44747 | 1401/04/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255985 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1053 | 2022-06-11 | 1401/03/21 | T-1053 | 44723 | 1401/03/21 | BK-SUR-ENG-PCS-01-04989 | 44747 | 1401/04/14 | CM-C3 | [6 empty] | 1401-2294-255985 | 2022-10-10 | 1401/07/18 | 44846 | 1401/07/20 | CM
3 | 1 | 3 | 1 | 0 | 5 | 0 | 3.1.3.5 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 1 | 0 | 5 | 1 | 3.1.3.1.5.1 | BK-PPL-PEDCO-320-PR-RT-0001 | Pipelines Hydraulic Calculation Report |  | BK-PPL-PEDCO-320-PR-RT-0001 | BK-PPL-PEDCO-320-PR-RT-0001 | BK | PPL | PEDCO | 320 | PR | RT | 0001 | F0Z-708534 | IFI | IFC | 2021-12-01 | 2021-12-08 | 2021-12-14 | 7 | 6 | 13 | IFA | 2022-02-08 | 2022-02-20 | 2022-02-22 | 12 | 2 | 14 | IFA | 2022-04-30 | 2022-05-12 | 2022-05-16 | 12 | 4 | 16 | IFA | 2022-10-16 | 2022-11-15 | 2022-11-16 | 30 | 1 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-17 |  |  | D03 | IFA | T-1448 | 44836 | 1401/07/10 | T-1448 | 44837 | 1401/07/11 | BK-SUR-ENG-PCS-01-05944 | 44856 | 1401/07/30 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-312894 | 44880 | 1401/08/24 | 44881 | 1401/08/25 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0254 | 2021-11-17 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02171 | 44531 | 1400/09/10 | CM-C3 | [6 empty] | 1400-2294-310826 | 2021-12-08 | 1400/09/17 | 44544 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0508 | 44586 | 1400/11/05 |  |  |  | BK-SUR-ENG-PCS-00-03124 | 44611 | 1400/11/30 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D00 | [5 empty] | 1400-2294-415917 | 44612 | 1400/12/01 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0816 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-PCS-01-04101 | 44682 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D01 | [5 empty] | 1401-2294-59525 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-1448 | 44836 | 1401/07/10 | T-1448 | 44837 | 1401/07/11 | BK-SUR-ENG-PCS-01-05944 | 44856 | 1401/07/30 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D02 | [5 empty] | 1401-2294-312894 | 44880 | 1401/08/24 | 44881 | 1401/08/25 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D02
3 | 1 | 3 | 1 | 0 | 6 | 0 | 3.1.3.6 |  | List
3 | 1 | 3 | 1 | 0 | 6 | 1 | 3.1.3.1.6.1 | BK-PPL-PEDCO-320-PR-LI-0001 | Equipment List |  | BK-PPL-PEDCO-320-PR-LI-0001 | BK-PPL-PEDCO-320-PR-LI-0001 | BK | PPL | PEDCO | 320 | PR | LI | 0001 | F0Z-708535 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-19 |  |  | D00 | IFC | T-0607 | 44611 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03322 | 44625 | 1400/12/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443237 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0607 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PCS-00-03322 | 44625 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-443237 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | CM
3 | 1 | 3 | 1 | 0 | 6 | 2 | 3.1.3.1.6.2 | BK-PPL-PEDCO-320-PR-LI-0002 | Line List |  | BK-PPL-PEDCO-320-PR-LI-0002 | BK-PPL-PEDCO-320-PR-LI-0002 | BK | PPL | PEDCO | 320 | PR | LI | 0002 | F0Z-708536 | AFC | IFC | 2022-03-02 | 2022-03-10 | 2022-03-11 | 8 | 1 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-16 |  |  | D00 | IFC | T-0598 | 44608 | 1400/11/27 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03269 | 44620 | 1400/12/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443211 | 44630 | 1400/12/19 | 44631 | 1400/12/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0598 | 2022-02-16 | 1400/11/27 |  |  |  | BK-SUR-ENG-PCS-00-03269 | 44620 | 1400/12/09 | CM-C3 | [6 empty] | 1400-2294-443211 | 2022-03-10 | 1400/12/19 | 44631 | 1400/12/21 | CM
3 | 1 | 3 | 1 | 0 | 6 | 3 | 3.1.3.1.6.3 | BK-PPL-PEDCO-320-PR-LI-0003 | Relief Load Summary |  | BK-PPL-PEDCO-320-PR-LI-0003 | BK-PPL-PEDCO-320-PR-LI-0003 | BK | PPL | PEDCO | 320 | PR | LI | 0003 | F0Z-708537 | AFC | IFC | 2022-04-26 | 2022-05-09 | 2022-05-16 | 13 | 7 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-12 |  |  | D00 | IFC | T-0809 | 44663 | 1401/01/23 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04095 | 44681 | 1401/02/10 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55025 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0809 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04095 | 44681 | 1401/02/10 | CM-C3 | [6 empty] | 1401-2294-55025 | 2022-05-09 | 1401/02/19 | 44697 | 1401/02/26 | CM
3 | 1 | 3 | 1 | 0 | 6 | 4 | 3.1.3.1.6.4 | BK-PPL-PEDCO-320-PR-LI-0004 | Tie in list |  | BK-PPL-PEDCO-320-PR-LI-0004 | BK-PPL-PEDCO-320-PR-LI-0004 | BK | PPL | PEDCO | 320 | PR | LI | 0004 | F0Z-708538 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-05-30 | 2022-06-13 | 2022-06-15 | 14 | 2 | 16 | IFA | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-19 |  |  | D02 | IFA | T-1559 | 44860 | 1401/08/04 | T-1559 | 44860 | 1401/08/04 | BK-SUR-ENG-PCS-01-06113 | 44872 | 1401/08/16 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0607 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PCS-00-03322 | 44625 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-443237 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0960 | 44697 | 1401/02/26 | T-0960 | 44697 | 1401/02/26 | BK-SUR-ENG-PCS-01-04509 | 44712 | 1401/03/10 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D00 | [5 empty] | 1401-2294-100884 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D00 | [9 empty] | D02 | IFA | T-1559 | 44860 | 1401/08/04 | T-1559 | 44860 | 1401/08/04 | BK-SUR-ENG-PCS-01-06113 | 44872 | 1401/08/16 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D01 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D01
3 | 1 | 3 | 1 | 0 | 7 | 0 | 3.1.3.7 |  | Data Sheet
3 | 1 | 3 | 1 | 0 | 7 | 1 | 3.1.3.1.7.1 | BK-PPL-PEDCO-320-PR-DT-0001 | Process Data Sheets For Instrument Devices |  | BK-PPL-PEDCO-320-PR-DT-0001 | BK-PPL-PEDCO-320-PR-DT-0001 | BK | PPL | PEDCO | 320 | PR | DT | 0001 | F0Z-708539 | AFC | IFC | 2022-04-26 | 2022-05-14 | 2022-05-16 | 18 | 2 | 20 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-12 |  |  | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-PR-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 44670 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 44697 | 1401/02/26 | CM | [10 empty] | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-DT-0001_D00 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-PR-DT-0001_D00
3 | 1 | 3 | 2 | 0 | 0 | 0 | 3.1.3.2 |  | Mechanical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 2 | 0 | 1 | 0 | 3.1.3.1 |  | Specification | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 2 | 0 | 2 | 0 | 3.1.3.2.2 |  | Fixed Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 2 | 0 | 2 | 1 | 3.1.3.2.2.1 | BK-PPL-PEDCO-320-ME-SP-0001 | Specification For Pig Traps |  | BK-PPL-PEDCO-320-ME-SP-0001 | BK-PPL-PEDCO-320-ME-SP-0001 | BK | PPL | PEDCO | 320 | ME | SP | 0001 | F0Z-708540 | AFD | IFC | 2021-09-18 | 2021-10-13 | 2021-10-17 | 25 | 4 | 29 | IFA | 2021-12-08 | 2021-11-30 | 2021-12-05 | -8 | 5 | -3 | AFD | 2022-02-14 | 2022-03-13 | 2022-03-26 | 27 | 13 | 40 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-09-04 | 2022-01-31 |  | D02 | AFD | T-0528 | 44592 | 1400/11/11 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02920 | 44594 | 1400/11/13 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-447211 | 44633 | 1400/12/22 | 44646 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0076 | 2021-09-04 | 1400/06/13 |  |  |  | BK-SUR-ENG-FXE-00-01789 | 44488 | 1400/07/27 | CM-C3 | [6 empty] | 1400-2294-206346 | 2021-09-20 | 1400/06/29 | 44486 | 1400/07/25 | CM |  | 1400-2294-234189 | 44482 | 1400/07/21 |  |  | CM |  |  |  | D01 | IFA | T-0269 | 44524 | 1400/09/03 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-320-ME-SP-0001-D00 | [5 empty] | 1400-2290-298671 | 44530 | 1400/09/09 | 44535 | 1400/09/14 | AP | NISOC-CRS-BK-GCS-PEDCO-320-ME-SP-0001-D00 | [9 empty] | D02 | AFD | T-0528 | 44592 | 1400/11/11 |  |  |  | BK-SUR-ENG-MEC-00-02920 | 44594 | 1400/11/13 | AP | [6 empty] | 1400-2294-447211 | 44633 | 1400/12/22 | 44646 | 1401/01/09 | AP
3 | 1 | 3 | 2 | 1 | 0 | 0 | 3.1.3.2.1 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 2 | 1 | 1 | 0 | 3.1.2.1.1 |  | Fixed Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 2 | 1 | 1 | 1 | 3.1.3.2.1.1.1 | BK-PPL-PEDCO-320-ME-DT-0001 | Data Sheets For Pig Traps |  | BK-PPL-PEDCO-320-ME-DT-0001 | BK-PPL-PEDCO-320-ME-DT-0001 | BK | PPL | PEDCO | 320 | ME | DT | 0001 | F0Z-708541 | AFC | IFC | 2021-12-27 | 2022-12-21 | 2022-06-11 | 359 | -193 | 166 | IFA | 2022-07-06 | 2022-07-14 | 2022-07-30 | 8 | 16 | 24 | IFA | 2022-08-29 | 2022-08-31 | 2022-09-03 | 2 | 3 | 5 | AFC | 2022-09-18 | 2022-10-05 | 2022-10-11 | 17 | 6 | 23 | AFC | 2022-10-26 | 0 | 0 | -44860 | 0 | -44860 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-13 | 2022-10-12 |  | D04 | AFC | T-1487 | 44846 | 1401/07/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-ME-DT-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0338 | 2021-12-13 | 1400/09/23 |  |  |  | BK-SUR-ENG-FXE-00-02541 | 44564 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-329500 | 2022-12-21 | 1400/09/30 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1111 | 44734 | 1401/04/01 |  |  |  | BK-SUR-ENG-MEC-01-05342 | 44776 | 1401/05/12 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-ME-DT-0001_D00 | [5 empty] | 1401-2294-139946 | 44756 | 1401/04/023 | 44772 | 1401/05/08 | CM | NISOC-CRS-BK-PPL-PEDCO-320-ME-DT-0001_D00 | [9 empty] | D02 | IFA | T-1276 | 44788 | 1401/05/24 |  |  |  | BK-SUR-ENG-MEC-01-05579 | 44807 | 1401/06/12 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-ME-DT-0001_D01 | [5 empty] | 1401-2294-205540 | 44804 | 1401/06/09 | 44807 | 1401/06/12 | AP | NISOC-CRS-BK-PPL-PEDCO-320-ME-DT-0001_D01 | [9 empty] | D03 | AFC | T-1356 | 44808 | 1401/06/13 |  |  |  | BK-SUR-ENG-MEC-01-05795 | 44836 | 1401/07/10 | AP | [6 empty] | 1401-2294-249441 | 44839 | 1401/07/13 | 44845 | 1401/07/19 | CM | NISOC-CRS-BK-PPL-PEDCO-320-ME-DT-0001_D02 | [9 empty] | D04 | AFC | T-1487 | 44846 | 1401/07/20 | [19 empty] | NISOC-CRS-BK-PPL-PEDCO-320-ME-DT-0001_D03
3 | 1 | 3 | 3 | 0 | 0 | 0 | 3.1.3.3 |  | Piping | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 3 | 1 | 0 | 0 | 3.1.3.3.1 |  | Specification
3 | 1 | 3 | 3 | 1 | 0 | 1 | 3.1.3.3.1 | BK-PPL-PEDCO-320-PI-SP-0001 | Piping Material Specification |  | BK-PPL-PEDCO-320-PI-SP-0001 | BK-PPL-PEDCO-320-PI-SP-0001 | BK | PPL | PEDCO | 320 | PI | SP | 0001 | F0Z-708542 | AFD | IFC | 2021-12-26 | 0 | 0 | -44556 | 0 | -44556 | IFA | 2022-03-20 | 2022-01-17 | 2022-04-19 | -62 | 92 | 30 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-13 | 33 | 2 | 35 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-12 |  |  | D02 | IFA | T-1202 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05280 | 44772 | 1401/05/08 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-220418 | 44815 | 1401/06/20 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0330 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02468 | 44557 | 1400/10/06 | CM-C2 | [22 empty] | D01 | IFA | T-0677 | 44626 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 44634 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D00 | [5 empty] | 1401-2294-27248 | 44578 | 1401/01/28 | 44670 | 1401/01/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D00 | [9 empty] | D02 | IFA | T-1202 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PIP-01-05280 | 44772 | 1401/05/08 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D01 | [5 empty] | 1401-2294-220418 | 44815 | 1401/06/20 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D01
3 | 1 | 3 | 3 | 2 | 0 | 0 | 3.1.3.3.2 |  | Drawing/Diagram
3 | 1 | 3 | 3 | 2 | 0 | 1 | 3.1.3.3.2 | BK-PPL-PEDCO-320-PI-PY-0001 | Unit Plot Plan For Pig Receiver Area (in Siahmakan G.I. Station) |  | BK-PPL-PEDCO-320-PI-PY-0001 | BK-PPL-PEDCO-320-PI-PY-0001 | BK | PPL | PEDCO | 320 | PI | PY | 0001 | F5A-708543 | AFC | IFC | 2022-07-11 | 2022-08-04 | 2022-08-13 | 24 | 9 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1126 | 44739 | 1401/04/06 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05150 | 44759 | 1401/04/26 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-167305 | 44777 | 1401/05/13 | 44786 | 1401/05/22 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1126 | 2022-06-27 | 1401/04/06 |  |  |  | BK-SUR-ENG-PIP-01-05150 | 44759 | 1401/04/26 | CM-C3 | [6 empty] | 1401-2294-167305 | 2022-08-04 | 1401/05/13 | 44786 | 1401/05/22 | RJ
3 | 1 | 3 | 3 | 2 | 0 | 2 | 3.1.3.3.2 | BK-PPL-PEDCO-320-PI-DW-0001 | A/G Piping Plan |  | BK-PPL-PEDCO-320-PI-DW-0001 | BK-PPL-PEDCO-320-PI-DW-0001 | BK | PPL | PEDCO | 320 | PI | DW | 0001 | F4L-708544 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 2 | 0 | 3 | 3.1.3.3.2 | BK-PPL-PEDCO-320-PI-DW-0002 | A/G Piping Isometric |  | BK-PPL-PEDCO-320-PI-DW-0002 | BK-PPL-PEDCO-320-PI-DW-0002 | BK | PPL | PEDCO | 320 | PI | DW | 0002 | F2L-708545 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 2 | 0 | 4 | 3.1.3.3.2 | BK-PPL-PEDCO-320-PI-PY-0002 | Unit Plot Plan For Binak Production Unit |  | BK-PPL-PEDCO-320-PI-PY-0002 | BK-PPL-PEDCO-320-PI-PY-0002 | BK | PPL | PEDCO | 320 | PI | PY | 0002 | F5A-708546 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 3 | 3 | 0 | 0 | 3.1.3.3.3 |  | Procedure/Plan
3 | 1 | 3 | 3 | 3 | 0 | 1 | 3.1.3.3.3 | BK-PPL-PEDCO-320-PI-PR-0001 | Piping Hydrostatic Test Diagram - PPL |  | BK-PPL-PEDCO-320-PI-PR-0001 | BK-PPL-PEDCO-320-PI-PR-0001 | BK | PPL | PEDCO | 320 | PI | PR | 0001 | F0Z-708547 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Deleted | 0
3 | 1 | 3 | 3 | 4 | 0 | 0 | 3.1.3.3.4 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 3 | 4 | 0 | 1 | 3.1.3.3.4 | BK-PPL-PEDCO-320-PI-RT-0001 | Corrosion Study & Material Selection Report |  | BK-PPL-PEDCO-320-PI-RT-0001 | BK-PPL-PEDCO-320-PI-RT-0001 | BK | PPL | PEDCO | 320 | PI | RT | 0001 | F0Z-708548 | IFI | IFC | 2021-12-26 | 0 | 0 | -44556 | 0 | -44556 | IFA | 2022-02-19 | 2022-03-10 | 2022-03-12 | 19 | 2 | 21 | AFD | 2022-08-14 | 2022-08-31 | 2022-09-03 | 17 | 3 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-12 | 2022-07-31 |  | D02 | AFD | T-1228 | 44773 | 1401/05/09 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05576 | 44807 | 1401/06/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205352 | 44804 | 1401/06/09 | 44807 | 1401/06/12 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0330 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02468 | 44557 | 1400/10/06 |  |  | BK-SUR-ENG-PIP-00-02544 | 44564 | 1400/10/13 | CM-C2 | [17 empty] | D01 | IFA | T-0550 | 44597 | 1400/11/16 | [7 empty] | PEDCO-CRS-BK-PPL-PEDCO-320-PI-RT-0001_D00 | [5 empty] | 1400-2294-443249 | 44630 | 1400/12/19 | 44632 | 1400/12/19 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0001_D00 | [9 empty] | D02 | AFD | T-1228 | 44773 | 1401/05/09 |  |  |  | BK-SUR-ENG-PIP-01-05576 | 44807 | 1401/06/12 | AP | [6 empty] | 1401-2294-205352 | 44804 | 1401/06/09 | 44807 | 1401/06/12 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0001_D01
3 | 1 | 3 | 3 | 4 | 0 | 2 | 3.1.3.3.4 | BK-PPL-PEDCO-320-PI-RT-0002 | Wall Thickness Calculation Report |  | BK-PPL-PEDCO-320-PI-RT-0002 | BK-PPL-PEDCO-320-PI-RT-0002 | BK | PPL | PEDCO | 320 | PI | RT | 0002 | F0Z-708549 | IFI | IFC | 2021-12-26 | 2021-12-20 | 2021-12-26 | -6 | 6 | 0 | IFA | 2022-03-20 | 2022-01-17 | 2022-04-19 | -62 | 92 | 30 | IFA | 2022-07-27 | 2022-09-01 | 2022-09-04 | 36 | 3 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-12 |  |  | D02 | IFA | T-1148 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05199 | 44762 | 1401/04/29 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205787 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0330 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02468 | 44557 | 1400/10/06 | CM-C2 | [6 empty] | 1400-2294-327385 | 2021-12-20 | 1400/09/29 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0677 | 44626 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 44634 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D00 | [5 empty] | 1401-2294-27248 | 44578 | 1401/01/28 | 44670 | 1401/01/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D00 | [9 empty] | D02 | IFA | T-1148 | 44755 | 1401/04/22 |  |  |  | BK-SUR-ENG-PIP-01-05199 | 44762 | 1401/04/29 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D01 | [5 empty] | 1401-2294-205787 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D01
3 | 1 | 3 | 3 | 4 | 0 | 3 | 3.1.3.3.4 | BK-PPL-PEDCO-320-PI-RT-0003 | Stress Analysis Calculations Report |  | BK-PPL-PEDCO-320-PI-RT-0003 | BK-PPL-PEDCO-320-PI-RT-0003 | BK | PPL | PEDCO | 320 | PI | RT | 0003 | F0Z-708550 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 4 | 0 | 4 | 3.1.3.3.4 | BK-PPL-PEDCO-320-PI-RT-0004 | PDMS Model Review Report (30%) |  | BK-PPL-PEDCO-320-PI-RT-0004 | BK-PPL-PEDCO-320-PI-RT-0004 | BK | PPL | PEDCO | 320 | PI | RT | 0004 | F0Z-708551 | IFI | IFI | 2022-09-19 | 2022-10-05 | 2022-10-08 | 16 | 3 | 19 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-05 |  |  | D00 | IFI | T-1363 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05621 | 44814 | 1401/06/19 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249447 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1363 | 2022-09-05 | 1401/06/14 |  |  |  | BK-SUR-ENG-PIP-01-05621 | 44814 | 1401/06/19 | CM-C2 | [6 empty] | 1401-2294-249447 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
3 | 1 | 3 | 3 | 4 | 0 | 5 | 3.1.3.3.4 | BK-PPL-PEDCO-320-PI-RT-0005 | PDMS Model Review Report (60%) |  | BK-PPL-PEDCO-320-PI-RT-0005 | BK-PPL-PEDCO-320-PI-RT-0005 | BK | PPL | PEDCO | 320 | PI | RT | 0005 | F0Z-708552 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 4 | 0 | 6 | 3.1.3.3.4 | BK-PPL-PEDCO-320-PI-RT-0006 | PDMS Model Review Report (90%) |  | BK-PPL-PEDCO-320-PI-RT-0006 | BK-PPL-PEDCO-320-PI-RT-0006 | BK | PPL | PEDCO | 320 | PI | RT | 0006 | F0Z-708553 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 5 | 0 | 0 | 3.1.3.3.5 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 3 | 5 | 0 | 1 | 3.1.3.3.5 | BK-PPL-PEDCO-320-PI-LI-0001 | Pipe Support List |  | BK-PPL-PEDCO-320-PI-LI-0001 | BK-PPL-PEDCO-320-PI-LI-0001 | BK | PPL | PEDCO | 320 | PI | LI | 0001 | F0Z-708554 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 5 | 0 | 2 | 3.1.3.3.5 | BK-PPL-PEDCO-320-PI-LI-0002 | Piping Tie-In List |  | BK-PPL-PEDCO-320-PI-LI-0002 | BK-PPL-PEDCO-320-PI-LI-0002 | BK | PPL | PEDCO | 320 | PI | LI | 0002 | F0Z-708555 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 6 | 0 | 0 | 3.1.3.3.6 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 3 | 6 | 0 | 1 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0001 | MTO For Pipes |  | BK-PPL-PEDCO-320-PI-MT-0001 | BK-PPL-PEDCO-320-PI-MT-0001 | BK | PPL | PEDCO | 320 | PI | MT | 0001 | F8Z-708556 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 6 | 0 | 2 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0002 | MTO For Fittings |  | BK-PPL-PEDCO-320-PI-MT-0002 | BK-PPL-PEDCO-320-PI-MT-0002 | BK | PPL | PEDCO | 320 | PI | MT | 0002 | F8Z-708557 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 3 | 6 | 0 | 3 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0003 | MTO For Flanges |  | BK-PPL-PEDCO-320-PI-MT-0003 | BK-PPL-PEDCO-320-PI-MT-0003 | BK | PPL | PEDCO | 320 | PI | MT | 0003 | F8Z-708558 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 6 | 0 | 4 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0004 | MTO For Manual Valves |  | BK-PPL-PEDCO-320-PI-MT-0004 | BK-PPL-PEDCO-320-PI-MT-0004 | BK | PPL | PEDCO | 320 | PI | MT | 0004 | F8Z-708559 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 6 | 0 | 5 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0005 | MTO For Gaskets |  | BK-PPL-PEDCO-320-PI-MT-0005 | BK-PPL-PEDCO-320-PI-MT-0005 | BK | PPL | PEDCO | 320 | PI | MT | 0005 | F8Z-708560 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 6 | 0 | 6 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0006 | MTO For Bolt & Nuts |  | BK-PPL-PEDCO-320-PI-MT-0006 | BK-PPL-PEDCO-320-PI-MT-0006 | BK | PPL | PEDCO | 320 | PI | MT | 0006 | F8Z-708561 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 6 | 0 | 7 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0007 | MTO For Insulation Joints |  | BK-PPL-PEDCO-320-PI-MT-0007 | [8 empty] | F8Z-708562 |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 6 | 0 | 8 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0008 | MTO For Insulation |  | BK-PPL-PEDCO-320-PI-MT-0008 | BK-PPL-PEDCO-320-PI-MT-0008 | BK | PPL | PEDCO | 320 | PI | MT | 0008 | F8Z-708563 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 6 | 0 | 9 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0009 | MTO For Painting |  | BK-PPL-PEDCO-320-PI-MT-0009 | BK-PPL-PEDCO-320-PI-MT-0009 | BK | PPL | PEDCO | 320 | PI | MT | 0009 | F8Z-708564 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 3 | 6 | 0 | 10 | 3.1.3.3 | BK-PPL-PEDCO-320-PI-MT-0010 | MTO For Coating of Underground Piping |  | BK-PPL-PEDCO-320-PI-MT-0010 | [8 empty] | F8Z-708565 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 4 | 0 | 0 | 0 | 3.1.3.4 |  | Pipeline | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 4 | 1 | 0 | 0 | 3.1.3.4.1 |  | Specification | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 4 | 1 | 0 | 1 | 3.1.3.4.1 | BK-PPL-PEDCO-320-PL-SP-0001 | Pipeline Material Specification |  | BK-PPL-PEDCO-320-PL-SP-0001 | BK-PPL-PEDCO-320-PL-SP-0001 | BK | PPL | PEDCO | 320 | PL | SP | 0001 | F0Z-708566 | AFD | IFC | 2021-12-26 | 2022-01-20 | 2022-01-29 | 25 | 9 | 34 | IFA | 2022-03-20 | 2022-03-27 | 2022-04-03 | 7 | 7 | 14 | IFA | 2022-08-20 | 2022-09-06 | 2022-09-12 | 17 | 6 | 23 | AFD | 2022-10-22 | 2022-10-25 | 2022-10-29 | 3 | 4 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-12 | 2022-10-08 |  | D03 | AFD | T-1465 | 44842 | 1401/07/16 | T-1465 | 44842 | 1401/07/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279785 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0332 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PPL-00-02470 | 44557 | 1400/10/06 | CM-C2 | [6 empty] | 1400-2294-342111 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM |  | 1400-2294-372866 | 44581 | 1400/10/30 | 44590 | 1400/11/10 | CM |  |  |  | D01 | IFA | T-0685 | 44626 | 1400/12/15 |  |  |  | BK-SUR-ENG-PPL-00-03544 | 44634 | 1400/12/23 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PL-SP-0001_D00 | [5 empty] | 1401-2294-6239 | 44647 | 1401/01/10 | 44654 | 1401/01/14 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PL-SP-0001_D00 | [9 empty] | D02 | IFA | T-1251 | 44779 | 1401/05/15 |  |  |  | BK-SUR-ENG-PPL-01-05442 | 44788 | 1401/05/24 | AP | [6 empty] | 1401-2204-213795 | 44810 | 1401/06/15 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PL-SP-0001_D01 | [9 empty] | D03 | AFD | T-1465 | 44842 | 1401/07/16 | T-1465 | 44842 | 1401/07/16 | [10 empty] | 1401-2294-279785 | 44859 | 1401/08/03 | 44863 | 1401/08/07
3 | 1 | 3 | 4 | 2 | 0 | 0 | 3.1.3.4.2 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 4 | 2 | 0 | 1 | 3.1.3.4.2 | BK-PPL-PEDCO-320-PL-CN-0001 | Calculation Note For Pipeline Wall Thickness |  | BK-PPL-PEDCO-320-PL-CN-0001 | BK-PPL-PEDCO-320-PL-CN-0001 | BK | PPL | PEDCO | 320 | PL | CN | 0001 | F0Z-708567 | AFD | IFC | 2021-12-26 | 2022-01-20 | 2022-01-29 | 25 | 9 | 34 | IFA | 2022-03-19 | 2022-03-27 | 2022-04-03 | 8 | 7 | 15 | IFA | 2022-08-20 | 2022-09-06 | 2022-09-12 | 17 | 6 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-12 |  |  | D02 | IFA | T-1251 | 44779 | 1401/05/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05442 | 44788 | 1401/05/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2204-213795 | 44810 | 1401/06/15 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0332 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PPL-00-02470 | 44557 | 1400/10/06 | CM-C2 | [6 empty] | 1400-2294-342111 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM |  | 1400-2294-372866 | 44581 | 1400/10/30 | 44590 | 1400/11/10 | CM |  |  |  | D01 | IFA | T-0672 | 44625 | 1400/12/15 |  |  |  | BK-SUR-ENG-PPL-00-03534 | 44633 | 1400/12/22 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D00 | [5 empty] | 1401-2294-6202 | 44647 | 1401/01/10 | 44654 | 1401/01/14 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D00 | [9 empty] | D02 | IFA | T-1251 | 44779 | 1401/05/15 |  |  |  | BK-SUR-ENG-PPL-01-05442 | 44788 | 1401/05/24 | AP | [6 empty] | 1401-2204-213795 | 44810 | 1401/06/15 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D01
3 | 1 | 3 | 4 | 3 | 0 | 0 | 3.1.3.4.3 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 4 | 3 | 0 | 1 | 3.1.3.4.3 | BK-PPL-PEDCO-320-PL-DT-0001 | Data Sheets For Anchor Flanges |  | BK-PPL-PEDCO-320-PL-DT-0001 | BK-PPL-PEDCO-320-PL-DT-0001 | BK | PPL | PEDCO | 320 | PL | DT | 0001 | F0Z-708568 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 4 | 3 | 0 | 2 | 3.1.3.4.3 | BK-PPL-PEDCO-320-PL-DT-0002 | Data Sheets For Barred Tee |  | BK-PPL-PEDCO-320-PL-DT-0002 | BK-PPL-PEDCO-320-PL-DT-0002 | BK | PPL | PEDCO | 320 | PL | DT | 0002 | F0Z-708569 | AFC | IFC | 2022-04-10 | 2022-04-13 | 2022-04-16 | 3 | 3 | 6 | IFA | 2022-08-09 | 2022-09-08 | 2022-09-12 | 30 | 4 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Deleted | 2022-03-27 |  |  | D01 | IFA | T-1203 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05324 | 44774 | 1401/05/10 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PL-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216165 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | RJ | NISOC-CRS-BK-PPL-PEDCO-320-PL-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0756 | 2022-03-27 | 1401/01/07 |  |  |  | BK-SUR-ENG-PPL-01-03864 | 44662 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-22785 | 2022-04-13 | 1401/01/24 | 44667 | 1401/01/27 | CM | [10 empty] | D01 | IFA | T-1203 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PPL-01-05324 | 44774 | 1401/05/10 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PL-DT-0002_D00 | [5 empty] | 1401-2294-216165 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | RJ | NISOC-CRS-BK-PPL-PEDCO-320-PL-DT-0002_D00
3 | 1 | 3 | 4 | 3 | 0 | 3 | 3.1.3.4.3 | BK-PPL-PEDCO-320-PL-DT-0003 | Data Sheets For Insulation Joints |  | BK-PPL-PEDCO-320-PL-DT-0003 | BK-PPL-PEDCO-320-PL-DT-0003 | BK | PPL | PEDCO | 320 | PL | DT | 0003 | F0Z-708570 | AFC | IFC | 2022-06-20 | 2022-06-26 | 2022-06-29 | 6 | 3 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Deleted | 2022-06-06 |  |  | D00 | IFC | T-1042 | 44718 | 1401/03/16 | T-1042 | 44718 | 1401/03/17 | BK-SUR-ENG-PPL-01-04773 | 44732 | 1401/03/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-118080 | 44738 | 1401/04/05 | 44741 | 1401/04/08 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1042 | 2022-06-06 | 1401/03/16 | T-1042 | 44718 | 1401/03/17 | BK-SUR-ENG-PPL-01-04773 | 44732 | 1401/03/30 | CM-C2 | [6 empty] | 1401-2294-118080 | 2022-06-26 | 1401/04/05 | 44741 | 1401/04/08 | CM
3 | 1 | 3 | 4 | 3 | 0 | 4 | 3.1.3.4.3 | BK-PPL-PEDCO-320-PL-DT-0004 | Data Sheets For Rock Shield |  | BK-PPL-PEDCO-320-PL-DT-0004 | BK-PPL-PEDCO-320-PL-DT-0004 | BK | PPL | PEDCO | 320 | PL | DT | 0004 | F0Z-708571 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 4 | 4 | 0 | 0 | 3.1.3.4.4 |  | Drawing/Diagram
3 | 1 | 3 | 4 | 4 | 0 | 1 | 3.1.3.4.4 | BK-PPL-PEDCO-320-PL-DW-0001 | Standard Support Drawings |  | BK-PPL-PEDCO-320-PL-DW-0001 | BK-PPL-PEDCO-320-PL-DW-0001 | BK | PPL | PEDCO | 320 | PL | DW | 0001 | F1L-708572 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 4 | 4 | 0 | 5 | 3.1.3.4.4 | BK-PPL-PEDCO-320-PL-DW-0006 | Pipeline Standard Drawings |  | BK-PPL-PEDCO-320-PL-DW-0006 | BK-PPL-PEDCO-320-PL-DW-0006 | BK | PPL | PEDCO | 320 | PL | DW | 0006 | F2L-708573 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 4 | 5 | 0 | 0 | 3.1.3.4.5 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 4 | 5 | 0 | 1 | 3.1.3.4.5 | BK-PPL-PEDCO-320-PL-PR-0001 | Pipeline Hydrostatic Test Diagram - PPL |  | BK-PPL-PEDCO-320-PL-PR-0001 | BK-PPL-PEDCO-320-PL-PR-0001 | BK | PPL | PEDCO | 320 | PL | PR | 0001 | F0Z-708574 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 4 | 6 | 0 | 0 | 3.1.3.4.6 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 4 | 6 | 0 | 1 | 3.1.3.4.6 | BK-PPL-PEDCO-320-PL-RT-0001 | Stress Analysis Calculations Report For Pipelines |  | BK-PPL-PEDCO-320-PL-RT-0001 | [8 empty] | F0Z-708575 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 4 | 7 | 0 | 0 | 3.1.3.4.7 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 4 | 7 | 0 | 1 | 3.1.3.4 | BK-PPL-PEDCO-320-PL-MT-0001 | MTO For Line Pipe |  | BK-PPL-PEDCO-320-PL-MT-0001 | BK-PPL-PEDCO-320-PL-MT-0001 | BK | PPL | PEDCO | 320 | PL | MT | 0001 | F8Z-708576 | IFI | IFI | 2021-09-05 | 2021-08-30 | 2021-09-05 | -6 | 6 | 0 | IFI | 2022-09-20 | 2022-09-18 | 2022-09-18 | -2 | 0 | -2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D01 | IFI | T-1369 | 44810 | 1401/06/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05702 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-226084 | 44822 | 1401/06/27 | 44822 | 1401/06/27 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PL-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 44430 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 44444 | 1400/06/14 | CM | [10 empty] | D01 | IFI | T-1369 | 44810 | 1401/06/15 |  |  |  | BK-SUR-ENG-PPL-01-05702 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PL-MT-0001_D00 | [5 empty] | 1401-2294-226084 | 44822 | 1401/06/27 | 44822 | 1401/06/27 | AP | NISOC-CRS-BK-PPL-PEDCO-320-PL-MT-0001_D00
3 | 1 | 3 | 4 | 7 | 0 | 2 | 3.1.3.4 | BK-PPL-PEDCO-320-PL-MT-0002 | MTO For Pipeline Field Joints Coating |  | BK-PPL-PEDCO-320-PL-MT-0002 | BK-PPL-PEDCO-320-PL-MT-0002 | BK | PPL | PEDCO | 320 | PL | MT | 0002 | F8Z-708577 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 4 | 7 | 0 | 3 | 3.1.3.4 | BK-PPL-PEDCO-320-PL-MT-0003 | MTO For Pipeline Flange, Fittings, Gasket and Bolt |  | BK-PPL-PEDCO-320-PL-MT-0003 | BK-PPL-PEDCO-320-PL-MT-0003 | BK | PPL | PEDCO | 320 | PL | MT | 0003 | F8Z-708578 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 0 | 0 | 0 | 3.1.3.5 |  | Control & Instrumentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 5 | 1 | 0 | 0 | 3.1.3.5.1 |  | Basis/Criteria | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 5 | 1 | 0 | 1 | 3.1.3.5.1 | BK-PPL-PEDCO-320-IN-DB-0001 | Instrument & Control System Basis of Design |  | BK-PPL-PEDCO-320-IN-DB-0001 | [8 empty] | - |  | IFC | 2021-09-05 | 2021-08-30 | 2021-09-12 | -6 | 13 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-0062 | 44430 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01499 | 44451 | 1400/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179382 | 44438 | 1400/06/08 | 44451 | 1400/06/21 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0062 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-INS-00-01499 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-179382 | 2021-08-30 | 1400/06/08 | 44451 | 1400/06/21 | RJ
3 | 1 | 3 | 5 | 1 | 0 | 2 | 3.1.3.5.1 | BK-PPL-PEDCO-320-IN-DC-0001 | Instrument & Control System Design Criteria |  | BK-PPL-PEDCO-320-IN-DC-0001 | BK-PPL-PEDCO-320-IN-DC-0001 | BK | PPL | PEDCO | 320 | IN | DC | 0001 | F0Z-708579 | AFD | IFC | 2022-01-17 | 2022-02-16 | 2022-02-21 | 30 | 5 | 35 | IFA | 2022-06-11 | 2022-07-14 | 2022-07-17 | 33 | 3 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-03 |  |  | D01 | IFA | T-1013 | 44709 | 1401/03/07 | T-1013 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-04676 | 44723 | 1401/03/21 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DC-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-139968 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | AP | NISOC-CRS-BK-PPL-PEDCO-320-IN-DC-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0420 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-INS-00-02625 | 44571 | 1400/10/20 | CM-C3 | [6 empty] | 1400-2294-412682 | 2022-02-16 | 1400/11/27 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-1013 | 44709 | 1401/03/07 | T-1013 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-04676 | 44723 | 1401/03/21 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DC-0001_D00 | [5 empty] | 1401-2294-139968 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | AP | NISOC-CRS-BK-PPL-PEDCO-320-IN-DC-0001_D00
3 | 1 | 3 | 5 | 1 | 0 | 3 | 3.1.3.5.1 | BK-PPL-PEDCO-320-IN-DC-0002 | Fire & Gas Detection Design Criteria |  | BK-PPL-PEDCO-320-IN-DC-0002 | [8 empty] | F0Z-708580 | AFD | IFC | 2022-06-14 | 2022-08-09 | 2022-08-14 | 56 | 5 | 61 | AFD | 2022-09-05 | 0 | 0 | -44809 | 0 | -44809 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-31 | 2022-08-22 |  | D01 | AFD | T-1297 | 44795 | 1401/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05516 | 44796 | 1401/06/01 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DC-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1028 | 2022-05-31 | 1401/03/10 | T-1028 | 44712 | 1401/03/10 | BK-SUR-ENG-INS-01-04740 | 44730 | 1401/03/28 | RJ-C4 | [6 empty] | 1401-2294-171153 | 2022-08-09 | 1401/05/18 | 44787 | 1401/05/23 | AP | [10 empty] | D01 | AFD | T-1297 | 44795 | 1401/05/31 |  |  |  | BK-SUR-ENG-INS-01-05516 | 44796 | 1401/06/01 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DC-0002_D00
3 | 1 | 3 | 5 | 2 | 0 | 0 | 3.1.3.5.2 |  | Data Sheets
3 | 1 | 3 | 5 | 2 | 0 | 1 | 3.1.3.5.2 | BK-PPL-PEDCO-320-IN-DT-0001 | Data Sheets For Pressure & Diff. Pressure Gauge |  | BK-PPL-PEDCO-320-IN-DT-0001 | BK-PPL-PEDCO-320-IN-DT-0001 | BK | PPL | PEDCO | 320 | IN | DT | 0001 | F9Z-708581 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-25 | 27 | 10 | 37 | IFA | 2022-05-14 | 2022-05-21 | 2022-05-23 | 7 | 2 | 9 | IFA | 2022-10-15 | 2022-11-05 | 2022-11-07 | 21 | 2 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-02 |  |  | D02 | IFA | T-1450 | 44835 | 1401/07/11 | T-1450 | 44835 | 1401/07/11 | BK-SUR-ENG-INS-01-05923 | 44852 | 1401/07/26 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296403 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-PPL-PEDCO-320-IN-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 44606 | 1400/11/25 | CM-C3 | [6 empty] | 1400-2294-449416 | 2022-03-15 | 1400/12/24 | 44645 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0883 | 44681 | 1401/02/10 | T-0883 | 44681 | 1401/02/10 | BK-SUR-ENG-INS-01-04312 | 44699 | 1401/02/28 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0001_D00 | [5 empty] | 1401-2294-70739 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-NISCO-320-IN-DT-0001_D00 | [9 empty] | D02 | IFA | T-1450 | 44835 | 1401/07/11 | T-1450 | 44835 | 1401/07/11 | BK-SUR-ENG-INS-01-05923 | 44852 | 1401/07/26 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0001_D01 | [5 empty] | 1401-2294-296403 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-PPL-PEDCO-320-IN-DT-0001_D01
3 | 1 | 3 | 5 | 2 | 0 | 2 | 3.1.3.5.2 | BK-PPL-PEDCO-320-IN-DT-0002 | Data Sheets For Temperature Gauge |  | BK-PPL-PEDCO-320-IN-DT-0002 | BK-PPL-PEDCO-320-IN-DT-0002 | BK | PPL | PEDCO | 320 | IN | DT | 0002 | F9Z-708582 | AFC | IFC | 2022-02-19 | 2022-03-09 | 2022-03-12 | 18 | 3 | 21 | IFA | 2022-05-15 | 2022-05-17 | 2022-05-23 | 2 | 6 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-05 |  |  | D01 | IFA | T-0888 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04313 | 44703 | 1401/03/01 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65632 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0549 | 2022-02-05 | 1400/11/16 |  |  |  | BK-SUR-ENG-INS-00-03113 | 44611 | 1400/11/30 | CM-C3 | [6 empty] | 1400-2294-442081 | 2022-03-09 | 1400/12/18 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0888 | 44682 | 1401/02/11 |  |  |  | BK-SUR-ENG-INS-01-04313 | 44703 | 1401/03/01 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0002_D00 | [5 empty] | 1401-2294-65632 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0002_D00
3 | 1 | 3 | 5 | 2 | 0 | 3 | 3.1.3.5.2 | BK-PPL-PEDCO-320-IN-DT-0003 | Data Sheets For Pressure/Diff. Pressure Transmitter |  | BK-PPL-PEDCO-320-IN-DT-0003 | BK-PPL-PEDCO-320-IN-DT-0003 | BK | PPL | PEDCO | 320 | IN | DT | 0003 | F9Z-708583 | AFC | IFC | 2022-02-27 | 2022-03-03 | 2022-03-08 | 4 | 5 | 9 | IFA | 2022-07-09 | 2022-09-07 | 2022-09-12 | 60 | 5 | 65 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-13 |  |  | D01 | IFA | T-1117 | 44737 | 1401/04/04 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05266 | 44772 | 1401/05/08 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-210036 | 44811 | 1401/06/13 | 44816 | 1401/06/21 | AP | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0587 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-INS-00-03250 | 44619 | 1400/12/08 | CM-C3 | [6 empty] | 1400-2294-432761 | 2022-03-03 | 1400/12/12 | 44628 | 1400/12/17 | CM | [10 empty] | D01 | IFA | T-1117 | 44737 | 1401/04/04 |  |  |  | BK-SUR-ENG-INS-01-05266 | 44772 | 1401/05/08 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0003_D00 | [5 empty] | 1401-2294-210036 | 44811 | 1401/06/13 | 44816 | 1401/06/21 | AP | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0003_D00
3 | 1 | 3 | 5 | 2 | 0 | 5 | 3.1.3.5.2 | BK-PPL-PEDCO-320-IN-DT-0005 | Data Sheets For Pressure & Safety Relief Valves |  | BK-PPL-PEDCO-320-IN-DT-0005 | BK-PPL-PEDCO-320-IN-DT-0005 | BK | PPL | PEDCO | 320 | IN | DT | 0005 | F9Z-708584 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | IFA | 2022-06-11 | 2022-08-04 | 2022-08-06 | 54 | 2 | 56 | IFA | 2022-11-05 | 2022-11-14 | 2022-11-16 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-27 |  |  | D02 | IFA | T-1527 | 44856 | 1401/07/30 | T-1527 | 44856 | 1401/07/30 | BK-SUR-ENG-INS-01-06098 | 44871 | 1401/08/15 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-310857 | 44879 | 1401/08/23 | 44881 | 1401/08/25 | AP | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0749 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03938 | 44667 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-27269 | 2022-04-17 | 1401/01/28 | 44676 | 1401/02/05 | CM | [10 empty] | D01 | IFA | T-1015 | 44709 | 1401/03/07 | T-1015 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-04679 | 44723 | 1401/03/21 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D00 | [5 empty] | 1401-2294-167263 | 44777 | 1401/05/13 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D00 | [9 empty] | D02 | IFA | T-1527 | 44856 | 1401/07/30 | T-1527 | 44856 | 1401/07/30 | BK-SUR-ENG-INS-01-06098 | 44871 | 1401/08/15 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D01 | [5 empty] | 1401-2294-310857 | 44879 | 1401/08/23 | 44881 | 1401/08/25 | AP | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D01
3 | 1 | 3 | 5 | 2 | 0 | 6 | 3.1.3.5.2 | BK-PPL-PEDCO-320-IN-DT-0006 | Data Sheets For ON/OFF & Shutdown Valves |  | BK-PPL-PEDCO-320-IN-DT-0006 | BK-PPL-PEDCO-320-IN-DT-0006 | BK | PPL | PEDCO | 320 | IN | DT | 0006 | F9Z-708585 | AFC | IFC | 2022-06-11 | 2022-08-14 | 2022-08-16 | 64 | 2 | 66 | IFA | 2022-10-31 | 2022-11-05 | 2022-11-07 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-28 |  |  | D01 | IFA | T-1503 | 44851 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-PPL-NISOC-320-IN-DT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1014 | 2022-05-28 | 1401/03/07 | T-1014 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-04678 | 44723 | 1401/03/21 | CM-C3 | [6 empty] | 1401-2294-177069 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM | [10 empty] | D01 | IFA | T-1503 | 44851 | 1401/07/25 |  |  |  | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0006_D00 | [5 empty] | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-PPL-NISOC-320-IN-DT-0006_D00
3 | 1 | 3 | 5 | 2 | 0 | 7 | 3.1.3.5.2 | BK-PPL-PEDCO-320-IN-DT-0009 | Data Sheets For Corrosion Coupon/ Probe |  | BK-PPL-PEDCO-320-IN-DT-0009 | BK-PPL-PEDCO-320-IN-DT-0009 | BK | PPL | PEDCO | 320 | IN | DT | 0009 | F9Z-708586 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-25 | 27 | 10 | 37 | IFA | 2022-05-22 | 2022-05-31 | 2022-06-08 | 9 | 8 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-02 |  |  | D01 | IFA | T-0907 | 44689 | 1401/02/18 | T-0907 | 44689 | 1401/02/18 | BK-SUR-ENG-INS-01-04429 | 44706 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-85248 | 44712 | 1401/03/10 | 44720 | 1401/03/18 | AP | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 44606 | 1400/11/25 | CM-C3 | [6 empty] | 1400-2294-449416 | 2022-03-15 | 1400/12/24 | 44645 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0907 | 44689 | 1401/02/18 | T-0907 | 44689 | 1401/02/18 | BK-SUR-ENG-INS-01-04429 | 44706 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D00 | [5 empty] | 1401-2294-85248 | 44712 | 1401/03/10 | 44720 | 1401/03/18 | AP | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D00
3 | 1 | 3 | 5 | 2 | 0 | 8 | 3.1.3.5.2 | BK-PPL-PEDCO-320-IN-DT-0010 | Data Sheets For Pig Signaler |  | BK-PPL-PEDCO-320-IN-DT-0010 | BK-PPL-PEDCO-320-IN-DT-0010 | BK | PPL | PEDCO | 320 | IN | DT | 0010 | F9Z-708587 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-25 | 27 | 10 | 37 | IFA | 2022-05-15 | 2022-05-17 | 2022-05-23 | 2 | 6 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-02 |  |  | D01 | IFA | T-0888 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04313 | 44703 | 1401/03/01 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65632 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 44606 | 1400/11/25 | CM-C3 | [6 empty] | 1400-2294-449416 | 2022-03-15 | 1400/12/24 | 44645 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0888 | 44682 | 1401/02/11 |  |  |  | BK-SUR-ENG-INS-01-04313 | 44703 | 1401/03/01 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0010_D00 | [5 empty] | 1401-2294-65632 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0010_D00
3 | 1 | 3 | 5 | 2 | 0 | 9 | 3.1.3.5.2 | BK-PPL-PEDCO-320-IN-DT-0011 | Data Sheets For F&G Detectors & Equipment |  | BK-PPL-PEDCO-320-IN-DT-0011 | [8 empty] | F9Z-708588 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 2 | 0 | 10 | 3.1.3.5.2 | BK-PPL-PEDCO-320-IN-DT-0012 | Data Sheets For LBV |  | BK-PPL-PEDCO-320-IN-DT-0012 | BK-PPL-PEDCO-320-IN-DT-0012 | BK | PPL | PEDCO | 320 | IN | DT | 0012 | F9Z-708589 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | IFA | 2022-07-09 | 2022-09-07 | 2022-09-12 | 60 | 5 | 65 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-27 |  |  | D01 | IFA | T-1117 | 44737 | 1401/04/04 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05266 | 44772 | 1401/05/08 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0012_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-210036 | 44811 | 1401/06/13 | 44816 | 1401/06/21 | AP | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0012_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0749 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03938 | 44667 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-27269 | 2022-04-17 | 1401/01/28 | 44676 | 1401/02/05 | CM | [10 empty] | D01 | IFA | T-1117 | 44737 | 1401/04/04 |  |  |  | BK-SUR-ENG-INS-01-05266 | 44772 | 1401/05/08 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0012_D00 | [5 empty] | 1401-2294-210036 | 44811 | 1401/06/13 | 44816 | 1401/06/21 | AP | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0012_D00
3 | 1 | 3 | 5 | 3 | 0 | 0 | 3.1.3.5.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 5 | 3 | 0 | 1 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-DW-0001 | Typical Instrument Installation Drawing |  | BK-PPL-PEDCO-320-IN-DW-0001 | BK-PPL-PEDCO-320-IN-DW-0001 | BK | PPL | PEDCO | 320 | IN | DW | 0001 | F2J-708590 | IFI | IFI | 2022-06-25 | 2022-08-27 | 2022-08-28 | 63 | 1 | 64 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFI | T-1061 | 44723 | 1401/03/21 | T-1061 | 44723 | 1401/03/21 | BK-SUR-ENG-INS-01-04839 | 44734 | 1401/04/01 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-195659 | 44800 | 1401/06/05 | 44801 | 1401/06/06 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1061 | 2022-06-11 | 1401/03/21 | T-1061 | 44723 | 1401/03/21 | BK-SUR-ENG-INS-01-04839 | 44734 | 1401/04/01 | CM-C2 | [6 empty] | 1401-2294-195659 | 2022-08-27 | 1401/06/05 | 44801 | 1401/06/06 | RJ
3 | 1 | 3 | 5 | 3 | 0 | 2 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-BD-0001 | Block Diagram Configuration For Control/ESD/F&G System |  | BK-PPL-PEDCO-320-IN-BD-0001 | BK-PPL-PEDCO-320-IN-BD-0001 | BK | PPL | PEDCO | 320 | IN | BD | 0001 | F2J-708591 | AFC | IFC | 2021-09-15 | 2021-09-29 | 2021-10-09 | 14 | 10 | 24 | IFA | 2021-11-15 | 2021-11-21 | 2021-11-27 | 6 | 6 | 12 | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 | IFA | 2022-04-24 | 2022-05-16 | 2022-05-16 | 22 | 0 | 22 | IFA | 2022-08-17 | 2022-09-03 | 2022-09-10 | 17 | 7 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-01 |  |  | D04 | IFA | T-1238 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05468 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-208224 | 44807 | 1401/06/12 | 44814 | 1401/06/19 | AP | NISOC-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0074 | 2021-09-01 | 1400/06/10 |  |  |  | BK-SUR-ENG-INS-00BK-SUR-ENG-INS-00-01552 | 44459 | 1400/06/024 | CM-C3 | [6 empty] | 1400-2294-217809 | 2021-09-29 | 1400/07/07 | 44478 | 1400/07/17 | CM | [10 empty] | D01 | IFA | T-0202 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-INS-00-01995 | 44514 | 1400/08/23 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001-D00 | [5 empty] | 1400-2294-283464 | 44521 | 1400/08/30 | 44527 | 1400/09/06 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-BD-0001-D00 | [9 empty] | D02 | IFA | T-0444 | 44571 | 1400/10/20 |  |  |  | BK-SUR-ENG-INS-00-02815 | 44586 | 1400/11/05 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001-D01 | [5 empty] | 1400-2294-385430 | 44590 | 1400/11/09 | 44591 | 1400/11/10 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-BD-0001-D01 | [9 empty] | D03 | IFA | T-0801 | 44661 | 1401/01/21 |  |  |  | BK-SUR-ENG-INS-01-04119 | 44682 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D02 | [5 empty] | 1401-2294-59533 | 44697 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D02 | [9 empty] | D04 | IFA | T-1238 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-INS-01-05468 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D03 | [5 empty] | 1401-2294-208224 | 44807 | 1401/06/12 | 44814 | 1401/06/19 | AP | NISOC-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D03
3 | 1 | 3 | 5 | 3 | 0 | 3 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-DG-0001 | Instrument Earthing Typical Diagram |  | BK-PPL-PEDCO-320-IN-DG-0001 | BK-PPL-PEDCO-320-IN-DG-0001 | BK | PPL | PEDCO | 320 | IN | DG | 0001 | F2J-708592 | IFI | IFI | 2022-01-12 | 2022-01-13 | 2022-01-15 | 1 | 2 | 3 | IFI | 2022-05-01 | 2022-05-12 | 2022-05-16 | 11 | 4 | 15 | IFI | 2022-08-13 | 2022-09-08 | 2022-09-13 | 26 | 5 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-29 |  |  | D02 | IFI | T-1218 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0408 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-INS-00-02612 | 44570 | 1400/10/19 | CM-C2 | [6 empty] | 1400-2294-362541 | 2022-01-13 | 1400/10/23 | 44576 | 1400/10/25 | CM | [10 empty] | D01 | IFI | T-0828 | 44668 | 1401/01/28 |  |  |  | BK-SUR-ENG-INS-01-04154 | 44688 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D00 | [5 empty] | 1401-2294-59512 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D00 | [9 empty] | D02 | IFI | T-1218 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05455 | 44788 | 1401/05/24 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D01 | [5 empty] | 1401-2294-216168 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D01
3 | 1 | 3 | 5 | 3 | 0 | 4 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-DG-0002 | Instrument Hook-up Diagram |  | BK-PPL-PEDCO-320-IN-DG-0002 | BK-PPL-PEDCO-320-IN-DG-0002 | BK | PPL | PEDCO | 320 | IN | DG | 0002 | F2J-708593 | AFC | IFC | 2022-06-29 | 2022-08-17 | 2022-08-21 | 49 | 4 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-15 |  |  | D00 | IFC | T-1080 | 44727 | 1401/03/25 | 44727 | 0 | 0 | BK-SUR-ENG-INS-01-05231 | 44767 | 1401/05/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183423 | 44790 | 1401/05/26 | 44794 | 1401/05/30 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1080 | 2022-06-15 | 1401/03/25 | 44727 |  |  | BK-SUR-ENG-INS-01-05231 | 44767 | 1401/05/03 | CM-C3 | [6 empty] | 1401-2294-183423 | 2022-08-17 | 1401/05/26 | 44794 | 1401/05/30 | CM
3 | 1 | 3 | 5 | 3 | 0 | 5 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-DG-0003 | ESD Level Hierarchy |  | BK-PPL-PEDCO-320-IN-DG-0003 | [8 empty] | F2J-708594 | AFC | [50 empty] | 0
3 | 1 | 3 | 5 | 3 | 0 | 6 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-DG-0004 | ESD System Loop Diagram |  | BK-PPL-PEDCO-320-IN-DG-0004 | [8 empty] | F2J-708595 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 3 | 0 | 7 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-DG-0005 | Control System/ESD system Loop Diagram | Control System Loop Diagram | BK-PPL-PEDCO-320-IN-DG-0005 | BK-PPL-PEDCO-320-IN-DG-0005 | BK | PPL | PEDCO | 320 | IN | DG | 0005 | F2J-708596 | AFC | IFC | 2022-07-09 | 2022-09-04 | 2022-09-13 | 57 | 9 | 66 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-25 |  |  | D00 | IFC | T-1115 | 44737 | 1401/04/04 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05253 | 44768 | 1401/05/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-210033 | 44808 | 1401/06/13 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1115 | 2022-06-25 | 1401/04/04 |  |  |  | BK-SUR-ENG-INS-01-05253 | 44768 | 1401/05/04 | CM-C3 | [6 empty] | 1401-2294-210033 | 2022-09-04 | 1401/06/13 | 44817 | 1401/06/22 | CM
3 | 1 | 3 | 5 | 3 | 0 | 8 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-DG-0006 | Instrument Air Piping and Air Header Diagram |  | BK-PPL-PEDCO-320-IN-DG-0006 | BK-PPL-PEDCO-320-IN-DG-0006 | BK | PPL | PEDCO | 320 | IN | DG | 0006 | F2J-708597 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 5 | 3 | 0 | 9 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-DG-0007 | Instrument Junction Box Termination Diagram | Instrument & F&G Junction Box Termination Diagram | BK-PPL-PEDCO-320-IN-DG-0007 | BK-PPL-PEDCO-320-IN-DG-0007 | BK | PPL | PEDCO | 320 | IN | DG | 0007 | F2J-708598 | AFC | IFC | 2022-07-03 | 2022-08-18 | 2022-08-23 | 46 | 5 | 51 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-19 |  |  | D00 | IFC | T-1092 | 44731 | 1401/03/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05248 | 44768 | 1401/05/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183561 | 44791 | 1401/05/27 | 44796 | 1401/06/01 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1092 | 2022-06-19 | 1401/03/30 |  |  |  | BK-SUR-ENG-INS-01-05248 | 44768 | 1401/05/04 | CM-C3 | [6 empty] | 1401-2294-183561 | 2022-08-18 | 1401/05/27 | 44796 | 1401/06/01 | CM
3 | 1 | 3 | 5 | 3 | 0 | 10 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-LD-0001 | Control System /ESD Logic Diagram | Control System Logic Diagram | BK-PPL-PEDCO-320-IN-LD-0001 | BK-PPL-PEDCO-320-IN-LD-0001 | BK | PPL | PEDCO | 320 | IN | LD | 0001 | F1J-708599 | AFC | IFC | 2022-07-06 | 2022-09-06 | 2022-09-13 | 62 | 7 | 69 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-22 |  |  | D00 | IFC | T-1110 | 44734 | 1401/04/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05018 | 44748 | 1401/04/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213331 | 44810 | 1401/06/15 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1110 | 2022-06-22 | 1401/04/01 |  |  |  | BK-SUR-ENG-INS-01-05018 | 44748 | 1401/04/15 | CM-C3 | [6 empty] | 1401-2294-213331 | 2022-09-06 | 1401/06/15 | 44817 | 1401/06/22 | CM
3 | 1 | 3 | 5 | 3 | 0 | 11 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-LD-0002 | ESD Logic Diagram |  | BK-PPL-PEDCO-320-IN-LD-0002 | [8 empty] | F1J-708600 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 3 | 0 | 12 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-PY-0001 | Control Room Cable Route Layout |  | BK-PPL-PEDCO-320-IN-PY-0001 | [8 empty] | F2J-708601 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 3 | 0 | 13 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-PY-0002 | Instrument Location Layout |  | BK-PPL-PEDCO-320-IN-PY-0002 | BK-PPL-PEDCO-320-IN-PY-0002 | BK | PPL | PEDCO | 320 | IN | PY | 0002 | F2J-708602 | AFC | IFC | 2022-08-06 | 2022-09-21 | 2022-10-02 | 46 | 11 | 57 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-07-23 |  |  | D00 | IFC | T-1178 | 44765 | 1401/05/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05365 | 44779 | 1401/05/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233417 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1178 | 2022-07-23 | 1401/05/01 |  |  |  | BK-SUR-ENG-INS-01-05365 | 44779 | 1401/05/15 | CM-C3 | [6 empty] | 1401-2294-233417 | 2022-09-21 | 1401/06/30 | 44836 | 1401/07/10 | CM
3 | 1 | 3 | 5 | 3 | 0 | 14 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-PY-0003 | Instrument Cable Trench/Route Layout Drawing |  | BK-PPL-PEDCO-320-IN-PY-0003 | BK-PPL-PEDCO-320-IN-PY-0003 | BK | PPL | PEDCO | 320 | IN | PY | 0003 | F2J-708603 | AFC | IFC | 2022-08-10 | 2022-09-28 | 2022-10-02 | 49 | 4 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-27 |  |  | D00 | IFC | T-1206 | 44769 | 1401/05/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05408 | 44783 | 1401/05/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240268 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1206 | 2022-07-27 | 1401/05/05 |  |  |  | BK-SUR-ENG-INS-01-05408 | 44783 | 1401/05/19 | CM-C3 | [6 empty] | 1401-2294-240268 | 2022-09-28 | 1401/07/06 | 44836 | 1401/07/10 | CM
3 | 1 | 3 | 5 | 3 | 0 | 15 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-PY-0006 | Control Room Arrangement Layout |  | BK-PPL-PEDCO-320-IN-PY-0006 | [8 empty] | F2J-708604 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 3 | 0 | 16 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-PY-0007 | F&G System Loop Diagram |  | BK-PPL-PEDCO-320-IN-PY-0007 | [8 empty] | F2J-708605 |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 3 | 0 | 17 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-PY-0008 | F&G Cause and Effect Diagram |  | BK-PPL-PEDCO-320-IN-PY-0008 | [8 empty] | F2J-708606 |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 3 | 0 | 18 | 3.1.3.5.3 | BK-PPL-PEDCO-320-IN-PY-0009 | F&G Location Layout For Process Area |  | BK-PPL-PEDCO-320-IN-PY-0009 | [8 empty] | F2J-708607 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 4 | 0 | 0 | 3.1.3.5.4 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 5 | 4 | 0 | 1 | 3.1.3.5.4 | BK-PPL-PEDCO-320-IN-LI-0001 | Instrument Index |  | BK-PPL-PEDCO-320-IN-LI-0001 | BK-PPL-PEDCO-320-IN-LI-0001 | BK | PPL | PEDCO | 320 | IN | LI | 0001 | F0Z-708608 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-25 | 27 | 10 | 37 | IFA | 2022-05-15 | 2022-05-17 | 2022-05-23 | 2 | 6 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-02 |  |  | D01 | IFA | T-0888 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04313 | 44703 | 1401/03/01 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65632 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 44606 | 1400/11/25 | CM-C3 | [6 empty] | 1400-2294-449416 | 2022-03-15 | 1400/12/24 | 44645 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0888 | 44682 | 1401/02/11 |  |  |  | BK-SUR-ENG-INS-01-04313 | 44703 | 1401/03/01 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-LI-0001_D00 | [5 empty] | 1401-2294-65632 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-LI-0001_D00
3 | 1 | 3 | 5 | 4 | 0 | 2 | 3.1.3.5.4 | BK-PPL-PEDCO-320-IN-LI-0002 | I/O List For Control /ESD System |  | BK-PPL-PEDCO-320-IN-LI-0002 | BK-PPL-PEDCO-320-IN-LI-0002 | BK | PPL | PEDCO | 320 | IN | LI | 0002 | F0Z-708609 | AFC | IFC | 2022-07-05 | 2022-09-06 | 2022-09-13 | 63 | 7 | 70 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-21 |  |  | D00 | IFC | T-1105 | 44733 | 1401/03/31 | T-1103 | 44733 | 1401/03/31 | BK-SUR-ENG-INS-01-05000 | 44747 | 1401/04/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213364 | 44810 | 1401/06/15 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1105 | 2022-06-21 | 1401/03/31 | T-1103 | 44733 | 1401/03/31 | BK-SUR-ENG-INS-01-05000 | 44747 | 1401/04/14 | CM-C3 | [6 empty] | 1401-2294-213364 | 2022-09-06 | 1401/06/15 | 44817 | 1401/06/22 | CM
3 | 1 | 3 | 5 | 4 | 0 | 3 | 3.1.3.5.4 | BK-PPL-PEDCO-320-IN-LI-0003 | I/O List For ESD /F&G System |  | BK-PPL-PEDCO-320-IN-LI-0003 | [8 empty] | F0Z-708610 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 4 | 0 | 4 | 3.1.3.5.4 | BK-PPL-PEDCO-320-IN-LI-0004 | Panels & Junction Box List |  | BK-PPL-PEDCO-320-IN-LI-0004 | BK-PPL-PEDCO-320-IN-LI-0004 | BK | PPL | PEDCO | 320 | IN | LI | 0004 | F0Z-708611 | AFC | IFC | 2022-07-06 | 2022-09-06 | 2022-09-13 | 62 | 7 | 69 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-22 |  |  | D00 | IFC | T-1110 | 44734 | 1401/04/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05018 | 44748 | 1401/04/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213331 | 44810 | 1401/06/15 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1110 | 2022-06-22 | 1401/04/01 |  |  |  | BK-SUR-ENG-INS-01-05018 | 44748 | 1401/04/15 | CM-C3 | [6 empty] | 1401-2294-213331 | 2022-09-06 | 1401/06/15 | 44817 | 1401/06/22 | CM
3 | 1 | 3 | 5 | 4 | 0 | 5 | 3.1.3.5.4 | BK-PPL-PEDCO-320-IN-LI-0005 | Set Point & Alarm List |  | BK-PPL-PEDCO-320-IN-LI-0005 | BK-PPL-PEDCO-320-IN-LI-0005 | BK | PPL | PEDCO | 320 | IN | LI | 0005 | F0Z-708612 | AFC | IFC | 2022-07-06 | 2022-09-06 | 2022-09-13 | 62 | 7 | 69 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-22 |  |  | D00 | IFC | T-1110 | 44734 | 1401/04/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05018 | 44748 | 1401/04/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213331 | 44810 | 1401/06/15 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1110 | 2022-06-22 | 1401/04/01 |  |  |  | BK-SUR-ENG-INS-01-05018 | 44748 | 1401/04/15 | CM-C3 | [6 empty] | 1401-2294-213331 | 2022-09-06 | 1401/06/15 | 44817 | 1401/06/22 | CM
3 | 1 | 3 | 5 | 4 | 0 | 6 | 3.1.3.5.4 | BK-PPL-PEDCO-320-IN-LI-0006 | I&C Power Consumption Summary |  | BK-PPL-PEDCO-320-IN-LI-0006 | [8 empty] | F0Z-708613 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 4 | 0 | 7 | 3.1.3.5.4 | BK-PPL-PEDCO-320-IN-LI-0007 | Instrument Cable List | Instrument and F&G Cable List | BK-PPL-PEDCO-320-IN-LI-0007 | BK-PPL-PEDCO-320-IN-LI-0007 | BK | PPL | PEDCO | 320 | IN | LI | 0007 | F0Z-708614 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 4 | 0 | 8 | 3.1.3.5.4 | BK-PPL-PEDCO-320-IN-LI-0008 | F&G Detector List |  | BK-PPL-PEDCO-320-IN-LI-0008 | [8 empty] | F0Z-708615 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 5 | 0 | 0 | 3.1.3.5.5 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 5 | 5 | 0 | 1 | 3.1.3.5 | BK-PPL-PEDCO-320-IN-MT-0001 | MTO for Bulk Item and Installation Accessories |  | BK-PPL-PEDCO-320-IN-MT-0001 | BK-PPL-PEDCO-320-IN-MT-0001 | BK | PPL | PEDCO | 320 | IN | MT | 0001 | F8Z-708616 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 5 | 0 | 2 | 3.1.3.5 | BK-PPL-PEDCO-320-IN-MT-0002 | MTO For Instrument Cable | MTO For Instrument/F&G Cable | BK-PPL-PEDCO-320-IN-MT-0002 | BK-PPL-PEDCO-320-IN-MT-0002 | BK | PPL | PEDCO | 320 | IN | MT | 0002 | F8Z-708617 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 5 | 5 | 0 | 3 | 3.1.3.5 | BK-PPL-PEDCO-320-IN-MT-0003 | MTO For Instrument Junction box and Gland | MTO For Instrument/F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-MT-0003 | BK-PPL-PEDCO-320-IN-MT-0003 | BK | PPL | PEDCO | 320 | IN | MT | 0003 | F8Z-708618 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 5 | 5 | 0 | 4 | 3.1.3.5 | BK-PPL-PEDCO-320-IN-MT-0004 | MTO For Instrument Tube and Fitting |  | BK-PPL-PEDCO-320-IN-MT-0004 | BK-PPL-PEDCO-320-IN-MT-0004 | BK | PPL | PEDCO | 320 | IN | MT | 0004 | F8Z-708619 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 5 | 0 | 5 | 3.1.3.5 | BK-PPL-PEDCO-320-IN-MT-0005 | MTO For Instrument Cable Tray/Ladder |  | BK-PPL-PEDCO-320-IN-MT-0005 | BK-PPL-PEDCO-320-IN-MT-0005 | BK | PPL | PEDCO | 320 | IN | MT | 0005 | F8Z-708620 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 5 | 5 | 0 | 6 | 3.1.3.5 | BK-PPL-PEDCO-320-SA-MT-0002 | MTO For Safety Sign |  | BK-PPL-PEDCO-320-SA-MT-0002 | BK-PPL-PEDCO-320-SA-MT-0002 | BK | PPL | PEDCO | 320 | SA | MT | 0002 | F8Z-708621 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 6 | 0 | 0 | 0 | 3.1.3.6 |  | Safety & Fire Fighting | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 6 | 1 | 0 | 0 | 3.1.3.6.1 |  | Basis/Criteria
3 | 1 | 3 | 6 | 1 | 0 | 1 | 3.1.3.6.1 | BK-PPL-PEDCO-320-SA-DB-0001 | Active Fire Protection and Safety Concept |  | BK-PPL-PEDCO-320-SA-DB-0001 | BK-PPL-PEDCO-320-SA-DB-0001 | BK | PPL | PEDCO | 320 | SA | DB | 0001 | F0Z-708622 | AFD | IFC | 2021-11-30 | 2022-11-30 | 2022-11-30 | 365 | 0 | 365 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-16 |  |  | D00 | IFC | T-0252 | 44516 | 1400/08/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-305193 | 44895 | 1400/09/15 | 44895 | 1400/09/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0252 | 2021-11-16 | 1400/08/25 | [13 empty] | 1400-2294-305193 | 2022-11-30 | 1400/09/15 | 44895 | 1400/09/15 | CM
3 | 1 | 3 | 6 | 2 | 0 | 0 | 3.1.3.6.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 6 | 2 | 0 | 1 | 3.1.3.6.2 | BK-PPL-PEDCO-320-SA-DT-0002 | Data Sheets For Safety Equipment |  | BK-PPL-PEDCO-320-SA-DT-0002 | [8 empty] | F0Z-708623 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 6 | 2 | 0 | 2 | 3.1.3.6.2 | BK-PPL-PEDCO-320-SA-DT-0003 | Data Sheets For fire fighting Equipment |  | BK-PPL-PEDCO-320-SA-DT-0003 | [8 empty] | F0Z-708624 | AFC | [50 empty] | 0
3 | 1 | 3 | 6 | 2 | 0 | 3 | 3.1.3.6.2 | BK-PPL-PEDCO-320-SA-DT-0004 | Data Sheets For safety sign |  | BK-PPL-PEDCO-320-SA-DT-0004 | [8 empty] | F0Z-708625 | AFC | [50 empty] | 0
3 | 1 | 3 | 6 | 3 | 0 | 0 | 3.1.3.6.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 6 | 3 | 0 | 1 | 3.1.3.6.3 | BK-PPL-PEDCO-320-SA-PY-0001 | Hazardous Area Classification Layout |  | BK-PPL-PEDCO-320-SA-PY-0001 | BK-PPL-PEDCO-320-SA-PY-0001 | BK | PPL | PEDCO | 320 | SA | PY | 0001 | F2L-708626 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 6 | 3 | 0 | 2 | 3.1.3.6.3 | BK-PPL-PEDCO-320-SA-PY-0002 | Safety & Fire Fighting Equipment Location Layout |  | BK-PPL-PEDCO-320-SA-PY-0002 | [8 empty] | F2L-708627 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 6 | 3 | 0 | 3 | 3.1.3.6.3 | BK-PPL-PEDCO-320-SA-PY-0003 | Escape Route & Safety Sign Layout |  | BK-PPL-PEDCO-320-SA-PY-0003 | [8 empty] | F2L-708628 | AFC | [50 empty] | 0
3 | 1 | 3 | 6 | 4 | 0 | 0 | 3.1.3.6.4 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 6 | 4 | 0 | 1 | 3.1.3.6.4 | BK-PPL-PEDCO-320-SA-RT-0003 | QRA Report |  | BK-PPL-PEDCO-320-SA-RT-0003 | BK-PPL-PEDCO-320-SA-RT-0003 | BK | PPL | PEDCO | 320 | SA | RT | 0003 | F0Z-708629 | IFI | IFC | 2022-08-20 | 2022-10-05 | 2022-10-11 | 46 | 6 | 52 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-06 |  |  | D00 | IFC | T-1253 | 44779 | 1401/05/12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249402 | 44839 | 1401/07/13 | 44845 | 1401/07/19 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1253 | 2022-08-06 | 1401/05/12 | [13 empty] | 1401-2294-249402 | 2022-10-05 | 1401/07/13 | 44845 | 1401/07/19 | CM
3 | 1 | 3 | 6 | 5 | 0 | 0 | 3.1.3.6.5 |  | List
3 | 1 | 3 | 6 | 5 | 0 | 1 | 3.1.3.6.5 | BK-PPL-PEDCO-320-SA-LI-0001 | Hazard Source List |  | BK-PPL-PEDCO-320-SA-LI-0001 | BK-PPL-PEDCO-320-SA-LI-0001 | BK | PPL | PEDCO | 320 | SA | LI | 0001 | F0Z-708630 | AFC | IFC | 2021-11-30 | 2022-11-30 | 2022-11-30 | 365 | 0 | 365 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-16 |  |  | D00 | IFC | T-0252 | 44516 | 1400/08/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-305193 | 44895 | 1400/09/15 | 44895 | 1400/09/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0252 | 2021-11-16 | 1400/08/25 | [13 empty] | 1400-2294-305193 | 2022-11-30 | 1400/09/15 | 44895 | 1400/09/15 | CM
3 | 1 | 3 | 6 | 6 | 0 | 0 | 3.1.3.6.6 |  | MTO
3 | 1 | 3 | 6 | 6 | 0 | 1 | 3.1.3.6 | BK-PPL-PEDCO-320-SA-MT-0001 | MTO For Safety & Fire Fighting Equipment |  | BK-PPL-PEDCO-320-SA-MT-0001 | [8 empty] | F8Z-708631 | IFI | [50 empty] | 0
3 | 1 | 3 | 7 | 0 | 0 | 0 | 3.1.3.7 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 7 | 1 | 0 | 0 | 3.1.3.7.1 |  | Calculation
3 | 1 | 3 | 7 | 1 | 0 | 1 | 3.1.3.7.1 | BK-PPL-PEDCO-320-EL-CN-0001 | Calculation Note For Cathodic Protection System for Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-CN-0001 | [8 empty] | F0Z-708632 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 7 | 2 | 0 | 0 | 3.1.3.7.2 |  | Data Sheets
3 | 1 | 3 | 7 | 2 | 0 | 1 | 3.1.3.7.2 | BK-PPL-PEDCO-320-EL-DT-0001 | Data Sheets For Expansion of LV Switchgear in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-DT-0001 | BK-PPL-PEDCO-320-EL-DT-0001 | BK | PPL | PEDCO | 320 | EL | DT | 0001 | F0Z-708633 | AFC | IFC | 2022-10-05 | 2022-10-17 | 2022-10-19 | 12 | 2 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFC | T-1433 | 44825 | 1401/06/30 | T-1433 | 44825 | 1401/06/30 | BK-SUR-ENG-ELE-01-05838 | 44838 | 1401/07/12 | RJ-C4 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-267457 | 44851 | 1401/07/25 | 44853 | 1401/07/27 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1433 | 2022-09-21 | 1401/06/30 | T-1433 | 44825 | 1401/06/30 | BK-SUR-ENG-ELE-01-05838 | 44838 | 1401/07/12 | RJ-C4 | [6 empty] | 1401-2294-267457 | 2022-10-17 | 1401/07/25 | 44853 | 1401/07/27 | RJ
3 | 1 | 3 | 7 | 2 | 0 | 2 | 3.1.3.7.2 | BK-PPL-PEDCO-320-EL-DT-0002 | Data Sheets For Cathodic Protection System for Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-DT-0002 | BK-PPL-PEDCO-320-EL-DT-0002 | BK | PPL | PEDCO | 320 | EL | DT | 0002 | F0Z-708634 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 7 | 3 | 0 | 0 | 3.1.3.7.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 7 | 3 | 0 | 1 | 3.1.3.7.3 | BK-PPL-PEDCO-320-EL-SL-0001 | Single Line Diagram For Expansion Of Upstream LV Switchgear in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-SL-0001 | BK-PPL-PEDCO-320-EL-SL-0001 | BK | PPL | PEDCO | 320 | EL | SL | 0001 | F2P-708635 | AFC | IFC | 2022-06-14 | 2022-06-21 | 2022-07-02 | 7 | 11 | 18 | IFA | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-31 |  |  | D01 | IFA | T-1509 | 44852 | 1401/07/26 | T-1509 | 44852 | 1401/07/26 | BK-SUR-ENG-ELE-01-06039 | 44865 | 1401/08/09 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-EL-SL-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-EL-SL-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1026 | 2022-05-31 | 1401/03/10 | T-1026 | 44712 | 1401/03/10 | BK-SUR-ENG-ELE-01-04696 | 44726 | 1401/03/24 | CM-C2 | [6 empty] | 1401-2294-111571 | 2022-06-21 | 1401/03/31 | 44744 | 1401/04/11 | CM | [10 empty] | D01 | IFA | T-1509 | 44852 | 1401/07/26 | T-1509 | 44852 | 1401/07/26 | BK-SUR-ENG-ELE-01-06039 | 44865 | 1401/08/09 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-EL-SL-0001_D00 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-EL-SL-0001_D00
3 | 1 | 3 | 7 | 3 | 0 | 2 | 3.1.3.7.3 | BK-PPL-PEDCO-320-EL-DG-0002 | Interconnection Wiring Diagram in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-DG-0002 | BK-PPL-PEDCO-320-EL-DG-0002 | BK | PPL | PEDCO | 320 | EL | DG | 0002 | F2P-708636 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 7 | 3 | 0 | 3 | 3.1.3.7.3 | BK-PPL-PEDCO-320-EL-DG-0003 | Interconnection Wiring Diagrams For Cathodic Protection Systems for Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-DG-0003 | BK-PPL-PEDCO-320-EL-DG-0003 | BK | PPL | PEDCO | 320 | EL | DG | 0003 | F2P-708637 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 7 | 3 | 0 | 4 | 3.1.3.7.3 | BK-PPL-PEDCO-320-EL-PY-0001 | Area Earthing Layout in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-PY-0001 | BK-PPL-PEDCO-320-EL-PY-0001 | BK | PPL | PEDCO | 320 | EL | PY | 0001 | F2P-708638 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 7 | 3 | 0 | 5 | 3.1.3.7.3 | BK-PPL-PEDCO-320-EL-PY-0002 | Area Electrical Cable Route & Section Layout in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-PY-0002 | BK-PPL-PEDCO-320-EL-PY-0002 | BK | PPL | PEDCO | 320 | EL | PY | 0002 | F2P-708639 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 7 | 3 | 0 | 6 | 3.1.3.7.3 | BK-PPL-PEDCO-320-EL-PY-0003 | Layout For Cathodic Protection System for Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-PY-0003 | BK-PPL-PEDCO-320-EL-PY-0003 | BK | PPL | PEDCO | 320 | EL | PY | 0003 | F2P-708640 | AFC | IFC | 2022-05-16 | 2022-05-31 | 2022-06-06 | 15 | 6 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-02 |  |  | D00 | IFC | T-0898 | 44683 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04280 | 44696 | 1401/02/25 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-85151 | 44712 | 1401/03/10 | 44718 | 1401/03/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0898 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-ELE-01-04280 | 44696 | 1401/02/25 | CM-C3 | [6 empty] | 1401-2294-85151 | 2022-05-31 | 1401/03/10 | 44718 | 1401/03/16 | CM
3 | 1 | 3 | 7 | 4 | 0 | 0 | 3.1.3.7.4 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 7 | 4 | 0 | 1 | 3.1.3.7.4 | BK-PPL-PEDCO-320-EL-LI-0001 | Electrical Load List in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-LI-0001 | BK-PPL-PEDCO-320-EL-LI-0001 | BK | PPL | PEDCO | 320 | EL | LI | 0001 | F0Z-708641 | AFC | IFC | 2022-06-13 | 2022-06-21 | 2022-07-02 | 8 | 11 | 19 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-30 |  |  | D00 | IFC | T-1024 | 44711 | 1401/03/09 | T-1024 | 44711 | 1401/03/09 | BK-SUR-ENG-ELE-01-04683 | 44724 | 1401/03/22 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-111531 | 44733 | 1401/03/31 | 44744 | 1401/04/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1024 | 2022-05-30 | 1401/03/09 | T-1024 | 44711 | 1401/03/09 | BK-SUR-ENG-ELE-01-04683 | 44724 | 1401/03/22 | CM-C2 | [6 empty] | 1401-2294-111531 | 2022-06-21 | 1401/03/31 | 44744 | 1401/04/11 | AP
3 | 1 | 3 | 7 | 4 | 0 | 2 | 3.1.3.7.4 | BK-PPL-PEDCO-320-EL-LI-0002 | Electrical Power & Control Cable List in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-LI-0002 | BK-PPL-PEDCO-320-EL-LI-0002 | BK | PPL | PEDCO | 320 | EL | LI | 0002 | F0Z-708642 | AFC | IFC | 2022-06-14 | 2022-06-21 | 2022-07-02 | 7 | 11 | 18 | IFA | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-31 |  |  | D01 | IFA | T-1513 | 44852 | 1401/07/26 | T-1513 | 44852 | 1401/07/26 | BK-SUR-ENG-ELE-01-06041 | 44865 | 1401/09/09 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-EL-LI-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-EL-LI-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1026 | 2022-05-31 | 1401/03/10 | T-1026 | 44712 | 1401/03/10 | BK-SUR-ENG-ELE-01-04696 | 44726 | 1401/03/24 | CM-C2 | [6 empty] | 1401-2294-111571 | 2022-06-21 | 1401/03/31 | 44744 | 1401/04/11 | CM | [10 empty] | D01 | IFA | T-1513 | 44852 | 1401/07/26 | T-1513 | 44852 | 1401/07/26 | BK-SUR-ENG-ELE-01-06041 | 44865 | 1401/09/09 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-EL-LI-0002_D00 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-EL-LI-0002_D00
3 | 1 | 3 | 7 | 4 | 0 | 3 | 3.1.3.7.4 | BK-PPL-PEDCO-320-EL-LI-0003 | Cable Schedule For Cathodic Protection System for Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-LI-0003 | BK-PPL-PEDCO-320-EL-LI-0003 | BK | PPL | PEDCO | 320 | EL | LI | 0003 | F0Z-708643 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 7 | 5 | 0 | 0 | 3.1.3.7.5 |  | MTO
3 | 1 | 3 | 7 | 5 | 0 | 1 | 3.1.3.7 | BK-PPL-PEDCO-320-EL-MT-0001 | MTO For Earthing & Lightning Systems in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-MT-0001 | BK-PPL-PEDCO-320-EL-MT-0001 | BK | PPL | PEDCO | 320 | EL | MT | 0001 | F8Z-708644 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 7 | 5 | 0 | 2 | 3.1.3.7 | BK-PPL-PEDCO-320-EL-MT-0002 | MTO For Power & Control Cables in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-MT-0002 | BK-PPL-PEDCO-320-EL-MT-0002 | BK | PPL | PEDCO | 320 | EL | MT | 0002 | F8Z-708645 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 7 | 5 | 0 | 3 | 3.1.3.7 | BK-PPL-PEDCO-320-EL-MT-0003 | MTO For Cathodic Protection System for Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-MT-0003 | BK-PPL-PEDCO-320-EL-MT-0003 | BK | PPL | PEDCO | 320 | EL | MT | 0003 | F8Z-708646 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 7 | 5 | 0 | 4 | 3.1.3.7 | BK-PPL-PEDCO-320-EL-MT-0004 | MTO For Electrical Bulk Items in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-MT-0004 | BK-PPL-PEDCO-320-EL-MT-0004 | BK | PPL | PEDCO | 320 | EL | MT | 0004 | F8Z-708647 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 7 | 5 | 0 | 5 | 3.1.3.7 | BK-PPL-PEDCO-320-EL-MT-0006 | MTO For Lighting & Small Powers in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-MT-0006 | BK-PPL-PEDCO-320-EL-MT-0006 | BK | PPL | PEDCO | 320 | EL | MT | 0006 | F8Z-708648 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 8 | 0 | 0 | 0 | 3.1.3.8 |  | Civil | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 8 | 1 | 0 | 0 | 3.1.3.8.1 |  | Drawing/Diagram
3 | 1 | 3 | 8 | 1 | 0 | 1 | 3.1.3.8.1 | BK-PPL-PEDCO-320-CV-PY-0001 | Civil Layout For Pig Receiver Area (In Siahmakan G.I. Station) |  | BK-PPL-PEDCO-320-CV-PY-0001 | BK-PPL-PEDCO-320-CV-PY-0001 | BK | PPL | PEDCO | 320 | CV | PY | 0001 | F4A-708649 | AFC | IFC | 2022-06-28 | 2022-06-23 | 2022-06-27 | -5 | 4 | -1 | IFA | 2022-09-19 | 2022-09-18 | 2022-09-20 | -1 | 2 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-14 |  |  | D01 | IFA | T-1358 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05701 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-227945 | 44822 | 1401/06/27 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-PPL-PEDCO-320-CV-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1072 | 2022-06-14 | 1401/03/24 |  |  |  | BK-SUR-ENG-CIV-01-04733 | 44730 | 1401/03/28 | CM-C2 | [6 empty] | 1401-2294-113888 | 2022-06-23 | 1401/04/02 | 44739 | 1401/04/06 | CM | [10 empty] | D01 | IFA | T-1358 | 44809 | 1401/06/14 |  |  |  | BK-SUR-ENG-CIV-01-05701 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-CV-PY-0001_D01 | [5 empty] | 1401-2294-227945 | 44822 | 1401/06/27 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-PPL-PEDCO-320-CV-PY-0001_D01
3 | 1 | 3 | 8 | 1 | 0 | 2 | 3.1.3.8.1 | BK-PPL-PEDCO-320-CV-PY-0002 | Civil Layout For LBV Stations |  | BK-PPL-PEDCO-320-CV-PY-0002 | BK-PPL-PEDCO-320-CV-PY-0002 | BK | PPL | PEDCO | 320 | CV | PY | 0002 | F4A-708650 | AFC | IFC | 2022-09-14 | 2022-10-30 | 2022-10-31 | 46 | 1 | 47 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-31 |  |  | D00 | IFC | T-1343 | 44804 | 1401/06/09 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05627 | 44815 | 1401/06/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285895 | 44864 | 1401/08/08 | 44865 | 1401/08/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1343 | 2022-08-31 | 1401/06/09 |  |  |  | BK-SUR-ENG-CIV-01-05627 | 44815 | 1401/06/20 | CM-C2 | [6 empty] | 1401-2294-285895 | 2022-10-30 | 1401/08/08 | 44865 | 1401/08/09 | CM
3 | 1 | 3 | 8 | 2 | 0 | 0 | 3.1.3.8.2 |  | Report
3 | 1 | 3 | 8 | 2 | 0 | 1 | 3.1.3.8 | BK-PPL-PEDCO-320-CV-RT-0001 | Site Visit Report (Civil Work) - 8" & 4" Pipelines |  | BK-PPL-PEDCO-320-CV-RT-0001 | BK-PPL-PEDCO-110-CV-RT-0001 | BK | PPL | PEDCO | 110 | CV | RT | 0001 | F0Z-708651 | IFI | IFI | 2022-06-25 | 2022-06-26 | 2022-06-29 | 1 | 3 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-11 |  |  | D00 | IFI | T-1063 | 44723 | 1401/03/21 | T-1063 | 44723 | 1401/03/21 | BK-SUR-ENG-CIV-01-04718 | 44727 | 1401/03/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-118145 | 44738 | 1401/04/05 | 44741 | 1401/04/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1063 | 2022-06-11 | 1401/03/21 | T-1063 | 44723 | 1401/03/21 | BK-SUR-ENG-CIV-01-04718 | 44727 | 1401/03/25 | CM-C2 | [6 empty] | 1401-2294-118145 | 2022-06-26 | 1401/04/05 | 44741 | 1401/04/08 | AP
3 | 1 | 3 | 9 | 0 | 0 | 0 | 3.1.3.9 |  | Structure
3 | 1 | 3 | 9 | 1 | 0 | 0 | 3.1.3.9.1 |  | Drawing/Diagram
3 | 1 | 3 | 9 | 1 | 0 | 1 | 3.1.3.9 | BK-PPL-PEDCO-320-ST-DW-0001 | Foundation Drawing For Pig Receiver (PL-3101 In Siahmakan G.I. Station) |  | BK-PPL-PEDCO-320-ST-DW-0001 | BK-PPL-PEDCO-320-ST-DW-0001 | BK | PPL | PEDCO | 320 | ST | DW | 0001 | F4Q-708652 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 3 | 9 | 1 | 0 | 2 | 3.1.3.9 | BK-PPL-PEDCO-320-ST-DW-0002 | Structural Drawing For LBV Pits |  | BK-PPL-PEDCO-320-ST-DW-0002 | BK-PPL-PEDCO-320-ST-DW-0002 | BK | PPL | PEDCO | 320 | ST | DW | 0002 | F4M-708653 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 3 | 10 | 0 | 0 | 0 | 3.1.3.10 |  | Survey (Topography) & Geotechnic/Geoelectric
3 | 1 | 3 | 10 | 0 | 1 | 0 | 3.1.3.10.1 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 3 | 10 | 0 | 1 | 1 | 3.1.3.10.1.1 | BK-PPL-PEDCO-320-GT-PR-0001 | Geotechnical Investigation Plan for Pipelines |  | BK-PPL-PEDCO-320-GT-PR-0001 | BK-PPL-PEDCO-320-GT-PR-0001 | BK | PPL | PEDCO | 320 | GT | PR | 0001 | F0Z-708654 | AFC | IFC | 2021-08-25 | 2021-08-15 | 2021-08-23 | -10 | 8 | -2 | IFA | 2021-09-21 | 2021-09-13 | 0 | -8 | -44452 | -44460 | IFA | 2021-10-16 | 2021-10-07 | 2021-10-11 | -9 | 4 | -5 | AFC | 2021-11-08 | 2021-10-29 | 2021-11-02 | -10 | 4 | -6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-08-11 | 2021-10-25 |  | D03 | AFC | T-0181 | 44494 | 1400/08/03 | 0 | 0 | 0 | BK-SUR-ENG-GEN-00-01893 | 44502 | 1400/08/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-251689 | 44498 | 1400/08/07 | 44502 | 1400/08/11 | AP | NISOC-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0043 | 2021-08-11 | 1400/05/20 |  |  |  | BK-SUR-ENG-CIV-00-01344 | 44425 | 1400/05/26 | CM-C3 | [6 empty] | 1400/2294/166479 | 2021-08-15 | 1400/05/24 | 44431 | 1400/06/01 | CM | [8 empty] | L-7572 |  | D01 | IFA | T-0082 | 44446 | 1400/06/16 |  |  |  | BK-SUR-ENG-GEN-00-01491 | 44450 | 1400/06/20 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D00 | [5 empty] | 1400-2294-197155 | 44452 | 1400/06/22 |  |  | CM | NISOC-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D00 | [9 empty] | D02 | IFA | T-0127 | 44471 | 1400/07/10 |  |  |  | BK-SUR-ENG-GEN-00-01679 | 44475 | 1400/07/14 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D01 | [5 empty] | 1400-2290-225564 | 44476 | 1400/07/15 | 44480 | 1400/07/19 | CM | NISOC-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D01 | [9 empty] | D03 | AFC | T-0181 | 44494 | 1400/08/03 |  |  |  | BK-SUR-ENG-GEN-00-01893 | 44502 | 1400/08/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D02 | [5 empty] | 1400-2294-251689 | 44498 | 1400/08/07 | 44502 | 1400/08/11 | AP | NISOC-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D02
3 | 1 | 3 | 10 | 0 | 2 | 0 | 3.1.3.10.2 |  | Report
3 | 1 | 3 | 10 | 0 | 2 | 1 | 3.1.3.10.2.1 | BK-PPL-PEDCO-320-GT-RT-0001 | Geotechnical Investigation Report for Pipelines |  | BK-PPL-PEDCO-320-GT-RT-0001 | BK-PPL-PEDCO-320-GT-RT-0001 | BK | PPL | PEDCO | 320 | GT | RT | 0001 | F0Z-708655 | IFI | IFI | 2022-08-30 | 2022-08-30 | 2022-08-31 | 0 | 1 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-16 |  |  | D00 | IFI | T-1278 | 44789 | 1401/05/25 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05550 | 44802 | 1401/06/07 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-201788 | 44803 | 1401/06/08 | 44804 | 1401/06/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1278 | 2022-08-16 | 1401/05/25 |  |  |  | BK-SUR-ENG-CIV-01-05550 | 44802 | 1401/06/07 | CM-C2 | [6 empty] | 1401-2294-201788 | 2022-08-30 | 1401/06/08 | 44804 | 1401/06/09 | CM
3 | 1 | 3 | 10 | 0 | 3 | 0 | 3.1.3.10.3 |  | Drawing/Diagram
3 | 1 | 3 | 10 | 0 | 3 | 1 | 3.1.3.10.3.1 | BK-PPL-PEDCO-320-SU-DW-0001 | Plan & Profile Drawings For Gas Pipeline (to Siahmakan) |  | BK-PPL-PEDCO-320-SU-DW-0001 | BK-PPL-PEDCO-320-SU-DW-0001 | BK | PPL | PEDCO | 320 | SU | DW | 0001 | F4A-708656 | AFC | IFC | 2022-09-11 | 2022-09-13 | 2022-09-14 | 2 | 1 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-28 |  |  | D00 | IFC | T-1329 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-05615 | 44811 | 1401/06/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-222850 | 44817 | 1401/06/22 | 44818 | 1401/06/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1329 | 2022-08-28 | 1401/06/06 |  |  |  | BK-SUR-ENG-PPL-01-05615 | 44811 | 1401/06/16 | CM-C3 | [6 empty] | 1401-2294-222850 | 2022-09-13 | 1401/06/22 | 44818 | 1401/06/23 | CM
3 | 1 | 3 | 10 | 0 | 3 | 2 | 3.1.3.10.3.2 | BK-PPL-PEDCO-320-SU-DW-0002 | Plan & Profile Drawings For Condensate Pipeline (to Binak PU) |  | BK-PPL-PEDCO-320-SU-DW-0002 | BK-PPL-PEDCO-320-SU-DW-0002 | BK | PPL | PEDCO | 320 | SU | DW | 0002 | F4A-708657 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
[8 empty] | BK-PPL-PEDCO-320-SU-DW-0003 | Transversal Profiles For Gas Pipeline (to Siahmakan) |  | BK-PPL-PEDCO-320-SU-DW-0003 | BK-PPL-PEDCO-320-SU-DW-0003 | BK | PPL | PEDCO | 320 | SU | DW | 0003 | F4A-708658 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
[8 empty] | BK-PPL-PEDCO-320-SU-DW-0004 | Transversal Profiles For Condensate Pipeline (to Binak PU) |  | BK-PPL-PEDCO-320-SU-DW-0004 | BK-PPL-PEDCO-320-SU-DW-0004 | BK | PPL | PEDCO | 320 | SU | DW | 0004 | F4A-708659 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 0 | 0 | 0 | 0 | 3.1.4 |  | Procurement Engineering
3 | 1 | 4 | 1 | 0 | 0 | 0 | 3.1.4.1 |  | Mechanical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 1 | 1 | 0 | 0 | 3.1.4.1.1 |  | Pig Traps
3 | 1 | 4 | 1 | 1 | 1 | 0 | 3.1.1.1.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 1 | 1 | 1 | 1 | 3.1.4.1.1.1.1 | BK-PPL-PEDCO-320-ME-MR-0001 | PMR For Pig Traps |  | BK-PPL-PEDCO-320-ME-MR-0001 | BK-PPL-PEDCO-320-ME-MR-0001 | BK | PPL | PEDCO | 320 | ME | MR | 0001 | F0Z-708660 | IFI | IFI | 2022-03-07 | 2022-03-08 | 2022-03-12 | 1 | 4 | 5 | IFI | 2022-08-07 | 2022-08-18 | 2022-08-21 | 11 | 3 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-24 |  |  | D01 | IFI | T-1188 | 44766 | 1401/05/02 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05344 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-ME-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183487 | 44791 | 1401/05/27 | 44794 | 1401/05/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-ME-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0618 | 2022-02-21 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03302 | 44622 | 1400/12/11 | CM-C3 | [6 empty] | 1400-2294-440957 | 2022-03-08 | 1400/12/17 | 44632 | 1400/12/21 | RJ | [10 empty] | D01 | IFI | T-1188 | 44766 | 1401/05/02 |  |  |  | BK-SUR-ENG-MEC-01-05344 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-ME-MR-0001_D00 | [5 empty] | 1401-2294-183487 | 44791 | 1401/05/27 | 44794 | 1401/05/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-ME-MR-0001_D00
3 | 1 | 4 | 1 | 1 | 2 | 0 | 3.1.1.1.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 1 | 1 | 2 | 1 | 3.1.4.1.1.2.1 | BK-PPL-PEDCO-320-ME-TB-0001 | TBE For Pig Traps |  | BK-PPL-PEDCO-320-ME-TB-0001 | BK-PPL-PEDCO-320-ME-TB-0001 | BK | PPL | PEDCO | 320 | ME | TB | 0001 | F0Z-708661 | IFI | IFI | 2022-06-20 | 2022-06-21 | 2022-06-27 | 1 | 6 | 7 | IFI | 2022-08-15 | 2022-08-18 | 2022-08-27 | 3 | 9 | 12 | IFI | 2022-11-16 | 0 | 0 | -44881 | 0 | -44881 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-06 |  |  | D02 | IFI | T-1570 | 44867 | 1401/08/10 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-06202 | 44884 | 1401/08/28 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-ME-TB-0001-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-ME-TB-0001-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1039 | 2022-06-06 | 1401/03/16 | T-1039 | 44718 | 1401/03/17 | [10 empty] | 1401-2294-111535 | 2022-06-21 | 1401/03/31 | 44739 | 1401/04/06 | CM | [10 empty] | D01 | IFI | T-1229 | 44774 | 1401/05/10 |  |  |  | BK-SUR-ENG-MEC-01-05421 | 44786 | 1401/05/22 | CM-C2 | [6 empty] | 1401-2294-183579 | 44791 | 1401/05/27 | 44800 | 1401/06/05 | CM | NISOC-CRS-BK-PPL-PEDCO-320-ME-TB-0001_D00 | [9 empty] | D02 | IFI | T-1570 | 44867 | 1401/08/10 |  |  |  | BK-SUR-ENG-MEC-01-06202 | 44884 | 1401/08/28 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-ME-TB-0001-D01 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-ME-TB-0001-D01
3 | 1 | 4 | 2 | 0 | 0 | 0 | 3.1.4.2 |  | Pipeline
3 | 1 | 4 | 2 | 1 | 0 | 0 | 3.1.4.2.1 |  | Line Pipe
3 | 1 | 4 | 2 | 1 | 1 | 0 | 3.1.2.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 1 | 1 | 1 | 3.1.4.2.1.1.1 | BK-PPL-PEDCO-320-PL-MR-0001 | PMR For Line Pipe |  | BK-PPL-PEDCO-320-PL-MR-0001 | BK-PPL-PEDCO-320-PL-MR-0001 | BK | PPL | PEDCO | 320 | PL | MR | 0001 | F0Z-708662 | IFI | IFI | 2021-12-20 | 2021-12-19 | 2021-12-21 | -1 | 2 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-06 |  |  | D00 | IFI | T-0300 | 44536 | 1400/09/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02309 | 44545 | 1400/09/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-323356 | 44549 | 1400/09/28 | 44551 | 1400/09/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0300 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PPL-00-02309 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-323356 | 2021-12-19 | 1400/09/28 | 44551 | 1400/09/30 | AP
3 | 1 | 4 | 2 | 1 | 2 | 0 | 3.1.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 1 | 2 | 1 | 3.1.4.2.1.2.1 | BK-PPL-PEDCO-320-PL-TB-0001 | TBE For Line Pipe |  | BK-PPL-PEDCO-320-PL-TB-0001 | BK-PPL-PEDCO-320-PL-TB-0001 | BK | PPL | PEDCO | 320 | PL | TB | 0001 | F0Z-708663 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 2 | 2 | 0 | 0 | 3.1.4.2.2 |  | Insulation Joints
3 | 1 | 4 | 2 | 2 | 1 | 0 | 3.1.2.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 2 | 1 | 1 | 3.1.4.2.2.1.1 | BK-PPL-PEDCO-320-PL-MR-0002 | PMR For Line Insulation Joints |  | BK-PPL-PEDCO-320-PL-MR-0002 | BK-PPL-PEDCO-320-PL-MR-0002 | BK | PPL | PEDCO | 320 | PL | MR | 0002 | F0Z-708664 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 2 | 2 | 2 | 0 | 3.1.2.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 2 | 2 | 1 | 3.1.4.2.2.2.1 | BK-PPL-PEDCO-320-PL-TB-0002 | TBE For Line Insulation Joints |  | BK-PPL-PEDCO-320-PL-TB-0002 | BK-PPL-PEDCO-320-PL-TB-0002 | BK | PPL | PEDCO | 320 | PL | TB | 0002 | F0Z-708665 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 2 | 3 | 0 | 0 | 3.1.4.2.3 |  | Anchor Flanges
3 | 1 | 4 | 2 | 3 | 1 | 0 | 3.1.2.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 3 | 1 | 1 | 3.1.4.2.3.1.1 | BK-PPL-PEDCO-320-PL-MR-0003 | PMR For Anchor Flanges |  | BK-PPL-PEDCO-320-PL-MR-0003 | BK-PPL-PEDCO-320-PL-MR-0003 | BK | PPL | PEDCO | 320 | PL | MR | 0003 | F0Z-708666 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 2 | 3 | 2 | 0 | 3.1.2.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 3 | 2 | 1 | 3.1.4.2.3.2.1 | BK-PPL-PEDCO-320-PL-TB-0003 | TBE For Anchor Flanges |  | BK-PPL-PEDCO-320-PL-TB-0003 | BK-PPL-PEDCO-320-PL-TB-0003 | BK | PPL | PEDCO | 320 | PL | TB | 0003 | F0Z-708667 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 2 | 4 | 0 | 0 | 3.1.4.2.4 |  | Pipeline Flange, Fittings, Gasket and Bolt
3 | 1 | 4 | 2 | 4 | 1 | 0 | 3.1.2.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 4 | 1 | 1 | 3.1.4.2.4.1.1 | BK-PPL-PEDCO-320-PL-MR-0004 | PMR For Pipeline Flange, Fittings, Gasket and Bolt |  | BK-PPL-PEDCO-320-PL-MR-0004 | BK-PPL-PEDCO-320-PL-MR-0004 | BK | PPL | PEDCO | 320 | PL | MR | 0004 | F0Z-708668 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 2 | 4 | 2 | 0 | 3.1.2.4.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 4 | 2 | 1 | 3.1.4.2.4.2.1 | BK-PPL-PEDCO-320-PL-TB-0004 | TBE For Pipeline Flange, Fittings, Gasket and Bolt |  | BK-PPL-PEDCO-320-PL-TB-0004 | BK-PPL-PEDCO-320-PL-TB-0004 | BK | PPL | PEDCO | 320 | PL | TB | 0004 | F0Z-708669 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 2 | 5 | 0 | 0 | 3.1.4.2.5 |  | Pipeline Rock Shield
3 | 1 | 4 | 2 | 5 | 1 | 0 | 3.1.2.5.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 5 | 1 | 1 | 3.1.4.2.5.1.1 | BK-PPL-PEDCO-320-PL-MR-0005 | PMR For Pipeline Rock Shield |  | BK-PPL-PEDCO-320-PL-MR-0005 | BK-PPL-PEDCO-320-PL-MR-0005 | BK | PPL | PEDCO | 320 | PL | MR | 0005 | F0Z-708670 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 2 | 5 | 2 | 0 | 3.1.2.5.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 2 | 5 | 2 | 1 | 3.1.4.2.5.2.1 | BK-PPL-PEDCO-320-PL-TB-0005 | TBE For Pipeline Rock Shield |  | BK-PPL-PEDCO-320-PL-TB-0005 | BK-PPL-PEDCO-320-PL-TB-0005 | BK | PPL | PEDCO | 320 | PL | TB | 0005 | F0Z-708671 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 0 | 0 | 0 | 3.1.4.3 |  | Control & Instrumentation
3 | 1 | 4 | 3 | 1 | 0 | 0 | 3.1.4.3.1 |  | Control System/Console/Furniture | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 1 | 1 | 0 | 3.1.3.1.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 1 | 1 | 1 | 3.1.4.3.1.1.1 | BK-PPL-PEDCO-320-IN-MR-0001 | PMR For Control System/ESD | PMR For Control System/Console/Furniture | BK-PPL-PEDCO-320-IN-MR-0001 | BK-PPL-PEDCO-320-IN-MR-0001 | BK | PPL | PEDCO | 320 | IN | MR | 0001 | F0Z-708672 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 1 | 2 | 0 | 3.1.3.1.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 1 | 2 | 1 | 3.1.4.3.1.2.1 | BK-PPL-PEDCO-320-IN-TB-0001 | TBE For Control System/ESD | TBE For Control System/Console/Furniture | BK-PPL-PEDCO-320-IN-TB-0001 | BK-PPL-PEDCO-320-IN-TB-0001 | BK | PPL | PEDCO | 320 | IN | TB | 0001 | F0Z-708673 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 2 | 0 | 0 | 3.1.4.3.2 |  | ESD System | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 2 | 1 | 0 | 3.1.3.2.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 2 | 1 | 1 | 3.1.4.3.2.1.1 | BK-PPL-PEDCO-320-IN-MR-0002 | PMR For ESD System |  | BK-PPL-PEDCO-320-IN-MR-0002 | [8 empty] | F0Z-708674 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 2 | 2 | 0 | 3.1.3.2.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 2 | 2 | 1 | 3.1.4.3.2.2.1 | BK-PPL-PEDCO-320-IN-TB-0002 | TBE For ESD System |  | BK-PPL-PEDCO-320-IN-TB-0002 | [8 empty] | F0Z-708675 | IFI | [50 empty] | 0
3 | 1 | 4 | 3 | 3 | 0 | 0 | 3.1.4.3.3 |  | Corrosion Probe/Coupon | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 3 | 1 | 0 | 3.1.3.3.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 3 | 1 | 1 | 3.1.4.3.3.1.1 | BK-PPL-PEDCO-320-IN-MR-0003 | PMR For Corrosion Probe/Coupon |  | BK-PPL-PEDCO-320-IN-MR-0003 | BK-PPL-PEDCO-320-IN-MR-0003 | BK | PPL | PEDCO | 320 | IN | MR | 0003 | F0Z-708676 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 3 | 2 | 0 | 3.1.3.3.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 3 | 2 | 1 | 3.1.4.3.3.2.1 | BK-PPL-PEDCO-320-IN-TB-0003 | TBE For Corrosion Probe/Coupon |  | BK-PPL-PEDCO-320-IN-TB-0003 | BK-PPL-PEDCO-320-IN-TB-0003 | BK | PPL | PEDCO | 320 | IN | TB | 0003 | F0Z-708677 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 4 | 0 | 0 | 3.1.4.3.4 |  | ON/OFF & Shutdown Valves | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 4 | 1 | 0 | 3.1.3.4.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 4 | 1 | 1 | 3.1.4.3.4.1.1 | BK-PPL-PEDCO-320-IN-MR-0004 | PMR For ON/OFF & Shutdown Valves |  | BK-PPL-PEDCO-320-IN-MR-0004 | BK-PPL-PEDCO-320-IN-MR-0004 | BK | PPL | PEDCO | 320 | IN | MR | 0004 | F0Z-708678 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 4 | 2 | 0 | 3.1.3.4.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 4 | 2 | 1 | 3.1.4.3.4.2.1 | BK-PPL-PEDCO-320-IN-TB-0004 | TBE For ON/OFF & Shutdown Valves |  | BK-PPL-PEDCO-320-IN-TB-0004 | BK-PPL-PEDCO-320-IN-TB-0004 | BK | PPL | PEDCO | 320 | IN | TB | 0004 | F0Z-708679 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 5 | 0 | 0 | 3.1.4.3.5 |  | Pressure Safety Valves (PSV) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 5 | 1 | 0 | 3.1.3.5.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 5 | 1 | 1 | 3.1.4.3.5.1.1 | BK-PPL-PEDCO-320-IN-MR-0006 | PMR For Pressure Safety Valves (PSV) |  | BK-PPL-PEDCO-320-IN-MR-0006 | BK-PPL-PEDCO-320-IN-MR-0006 | BK | PPL | PEDCO | 320 | IN | MR | 0006 | F0Z-708680 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 5 | 2 | 0 | 3.1.3.5.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 5 | 2 | 1 | 3.1.4.3.5.2.1 | BK-PPL-PEDCO-320-IN-TB-0006 | TBE For Pressure Safety Valves (PSV) |  | BK-PPL-PEDCO-320-IN-TB-0006 | BK-PPL-PEDCO-320-IN-TB-0006 | BK | PPL | PEDCO | 320 | IN | TB | 0006 | F0Z-708681 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 6 | 0 | 0 | 3.1.4.3.6 |  | Differential Pressure/Pressure Gauge | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 6 | 1 | 0 | 3.1.3.6.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 6 | 1 | 1 | 3.1.4.3.6.1.1 | BK-PPL-PEDCO-320-IN-MR-0008 | PMR For Differential Pressure/Pressure Gauge |  | BK-PPL-PEDCO-320-IN-MR-0008 | BK-PPL-PEDCO-320-IN-MR-0008 | BK | PPL | PEDCO | 320 | IN | MR | 0008 | F0Z-708682 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 6 | 2 | 0 | 3.1.3.6.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 6 | 2 | 1 | 3.1.4.3.6.2.1 | BK-PPL-PEDCO-320-IN-TB-0008 | TBE For Differential Pressure/Pressure Gauge |  | BK-PPL-PEDCO-320-IN-TB-0008 | BK-PPL-PEDCO-320-IN-TB-0008 | BK | PPL | PEDCO | 320 | IN | TB | 0008 | F0Z-708683 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 7 | 0 | 0 | 3.1.4.3.7 |  | Pressure/Diff. Pressure Transmitter | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 7 | 1 | 0 | 3.1.3.7.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 7 | 1 | 1 | 3.1.4.3.7.1.1 | BK-PPL-PEDCO-320-IN-MR-0009 | PMR For Pressure/Diff. Pressure Transmitter |  | BK-PPL-PEDCO-320-IN-MR-0009 | BK-PPL-PEDCO-320-IN-MR-0009 | BK | PPL | PEDCO | 320 | IN | MR | 0009 | F0Z-708684 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 7 | 2 | 0 | 3.1.3.7.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 7 | 2 | 1 | 3.1.4.3.7.2.1 | BK-PPL-PEDCO-320-IN-TB-0009 | TBE For Pressure/Diff. Pressure Transmitter |  | BK-PPL-PEDCO-320-IN-TB-0009 | BK-PPL-PEDCO-320-IN-TB-0009 | BK | PPL | PEDCO | 320 | IN | TB | 0009 | F0Z-708685 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 8 | 0 | 0 | 3.1.4.3.8 |  | Temperature Gauge
3 | 1 | 4 | 3 | 8 | 1 | 0 | 3.1.3.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 8 | 1 | 1 | 3.1.4.3.8.1.1 | BK-PPL-PEDCO-320-IN-MR-0010 | PMR For Temperature Gauge |  | BK-PPL-PEDCO-320-IN-MR-0010 | BK-PPL-PEDCO-320-IN-MR-0010 | BK | PPL | PEDCO | 320 | IN | MR | 0010 | F0Z-708686 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 8 | 2 | 0 | 3.1.3.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 8 | 2 | 1 | 3.1.4.3.8.2.1 | BK-PPL-PEDCO-320-IN-TB-0010 | TBE For Temperature Gauge |  | BK-PPL-PEDCO-320-IN-TB-0010 | BK-PPL-PEDCO-320-IN-TB-0010 | BK | PPL | PEDCO | 320 | IN | TB | 0010 | F0Z-708687 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 9 | 0 | 0 | 3.1.4.3.9 |  | Pig Signaler
3 | 1 | 4 | 3 | 9 | 1 | 0 | 3.1.3.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 9 | 1 | 1 | 3.1.4.3.9.1.1 | BK-PPL-PEDCO-320-IN-MR-0013 | PMR For Pig Signaler |  | BK-PPL-PEDCO-320-IN-MR-0013 | BK-PPL-PEDCO-320-IN-MR-0013 | BK | PPL | PEDCO | 320 | IN | MR | 0013 | F0Z-708688 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 9 | 2 | 0 | 3.1.3.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 9 | 2 | 1 | 3.1.4.3.9.2.1 | BK-PPL-PEDCO-320-IN-TB-0013 | TBE For Pig Signaler |  | BK-PPL-PEDCO-320-IN-TB-0013 | BK-PPL-PEDCO-320-IN-TB-0013 | BK | PPL | PEDCO | 320 | IN | TB | 0013 | F0Z-708689 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 10 | 0 | 0 | 3.1.4.3.10 |  | Instrument Installation Accessories
3 | 1 | 4 | 3 | 10 | 1 | 0 | 3.1.3.10.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 10 | 1 | 1 | 3.1.4.3.10.1.1 | BK-PPL-PEDCO-320-IN-MR-0014 | PMR For Instrument Installation Accessories |  | BK-PPL-PEDCO-320-IN-MR-0014 | BK-PPL-PEDCO-320-IN-MR-0014 | BK | PPL | PEDCO | 320 | IN | MR | 0014 | F0Z-708690 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 10 | 2 | 0 | 3.1.3.10.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 10 | 2 | 1 | 3.1.4.3.10.2.1 | BK-PPL-PEDCO-320-IN-TB-0014 | TBE For Instrument Installation Accessories |  | BK-PPL-PEDCO-320-IN-TB-0014 | BK-PPL-PEDCO-320-IN-TB-0014 | BK | PPL | PEDCO | 320 | IN | TB | 0014 | F0Z-708691 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 3 | 11 | 0 | 0 | 3.1.4.3.11 |  | Instrument Cable Tray
3 | 1 | 4 | 3 | 11 | 1 | 0 | 3.1.3.11.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 11 | 1 | 1 | 3.1.4.3.11.1.1 | BK-PPL-PEDCO-320-IN-MR-0015 | PMR For Instrument Cable Tray |  | BK-PPL-PEDCO-320-IN-MR-0015 | BK-PPL-PEDCO-320-IN-MR-0015 | BK | PPL | PEDCO | 320 | IN | MR | 0015 | F0Z-708692 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 11 | 2 | 0 | 3.1.3.11.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 11 | 2 | 1 | 3.1.4.3.11.2.1 | BK-PPL-PEDCO-320-IN-TB-0015 | TBE For Instrument Cable Tray |  | BK-PPL-PEDCO-320-IN-TB-0015 | BK-PPL-PEDCO-320-IN-TB-0015 | BK | PPL | PEDCO | 320 | IN | TB | 0015 | F0Z-708693 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 12 | 0 | 0 | 3.1.4.3.12 |  | Instrument Junction box and Gland
3 | 1 | 4 | 3 | 12 | 1 | 0 | 3.1.3.12.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 12 | 1 | 1 | 3.1.4.3.12.1.1 | BK-PPL-PEDCO-320-IN-MR-0016 | PMR For Instrument Junction box and Gland | PMR For Instrument and F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-MR-0016 | BK-PPL-PEDCO-320-IN-MR-0016 | BK | PPL | PEDCO | 320 | IN | MR | 0016 | F0Z-708694 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 12 | 2 | 0 | 3.1.3.12.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 12 | 2 | 1 | 3.1.4.3.12.2.1 | BK-PPL-PEDCO-320-IN-TB-0016 | TBE For Instrument Junction box and Gland | TBE For Instrument and F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-TB-0016 | BK-PPL-PEDCO-320-IN-TB-0016 | BK | PPL | PEDCO | 320 | IN | TB | 0016 | F0Z-708695 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 13 | 0 | 0 | 3.1.4.3.13 |  | Instrument Tube and Fitting
3 | 1 | 4 | 3 | 13 | 1 | 0 | 3.1.3.13.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 13 | 1 | 1 | 3.1.4.3.13.1.1 | BK-PPL-PEDCO-320-IN-MR-0017 | PMR For Instrument Tube and Fitting |  | BK-PPL-PEDCO-320-IN-MR-0017 | BK-PPL-PEDCO-320-IN-MR-0017 | BK | PPL | PEDCO | 320 | IN | MR | 0017 | F0Z-708696 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 13 | 2 | 0 | 3.1.3.13.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 13 | 2 | 1 | 3.1.4.3.13.2.1 | BK-PPL-PEDCO-320-IN-TB-0017 | TBE For Instrument Tube and Fitting |  | BK-PPL-PEDCO-320-IN-TB-0017 | BK-PPL-PEDCO-320-IN-TB-0017 | BK | PPL | PEDCO | 320 | IN | TB | 0017 | F0Z-708697 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 14 | 0 | 0 | 3.1.4.3.14 |  | Instrument Cable
3 | 1 | 4 | 3 | 14 | 1 | 0 | 3.1.3.14.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 14 | 1 | 1 | 3.1.4.3.14.1.1 | BK-PPL-PEDCO-320-IN-MR-0018 | PMR For Instrument Cable | PMR For Instrument and F&G Cable | BK-PPL-PEDCO-320-IN-MR-0018 | BK-PPL-PEDCO-320-IN-MR-0018 | BK | PPL | PEDCO | 320 | IN | MR | 0018 | F0Z-708698 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 14 | 2 | 0 | 3.1.3.14.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 14 | 2 | 1 | 3.1.4.3.14.2.1 | BK-PPL-PEDCO-320-IN-TB-0018 | TBE For Instrument Cable | TBE For Instrument and F&G Cable | BK-PPL-PEDCO-320-IN-TB-0018 | BK-PPL-PEDCO-320-IN-TB-0018 | BK | PPL | PEDCO | 320 | IN | TB | 0018 | F0Z-708699 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 15 | 0 | 0 | 3.1.4.3.15 |  | F&G Devices
3 | 1 | 4 | 3 | 15 | 1 | 0 | 3.1.3.15.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 15 | 1 | 1 | 3.1.4.3.15.1.1 | BK-PPL-PEDCO-320-IN-MR-0019 | PMR For F&G Devices |  | BK-PPL-PEDCO-320-IN-MR-0019 | [8 empty] | F0Z-708700 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 15 | 2 | 0 | 3.1.3.15.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 15 | 2 | 1 | 3.1.4.3.15.2.1 | BK-PPL-PEDCO-320-IN-TB-0019 | TBE For F&G Devices |  | BK-PPL-PEDCO-320-IN-TB-0019 | [8 empty] | F0Z-708701 | IFI | [50 empty] | 0
3 | 1 | 4 | 3 | 16 | 0 | 0 | 3.1.4.3.16 |  | LBV | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 3 | 16 | 1 | 0 | 3.1.3.16.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 16 | 1 | 1 | 3.1.4.3.16.1.1 | BK-PPL-PEDCO-320-IN-MR-0020 | PMR For LBV |  | BK-PPL-PEDCO-320-IN-MR-0020 | BK-PPL-PEDCO-320-IN-MR-0020 | BK | PPL | PEDCO | 320 | IN | MR | 0020 | F0Z-708702 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 3 | 16 | 2 | 0 | 3.1.3.16.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 16 | 2 | 1 | 3.1.4.3.16.2.1 | BK-PPL-PEDCO-320-IN-TB-0020 | TBE For LBV |  | BK-PPL-PEDCO-320-IN-TB-0020 | BK-PPL-PEDCO-320-IN-TB-0020 | BK | PPL | PEDCO | 320 | IN | TB | 0020 | F0Z-708703 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 4 | 4 | 0 | 0 | 0 | 3.1.4.4 |  | Safety & Fire Fighting | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 4 | 1 | 0 | 0 | 3.1.4.4.1 |  | Safety Equipment
3 | 1 | 4 | 4 | 1 | 1 | 0 | 3.1.4.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 4 | 1 | 1 | 1 | 3.1.4.4.1.1.1 | BK-PPL-PEDCO-320-SA-MR-0001 | PMR For Safety Equipment |  | BK-PPL-PEDCO-320-SA-MR-0001 | [8 empty] | F0Z-708704 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 4 | 1 | 2 | 0 | 3.1.4.1.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 4 | 1 | 2 | 1 | 3.1.4.4.1.2.1 | BK-PPL-PEDCO-320-SA-TB-0001 | TBE For Safety Equipment |  | BK-PPL-PEDCO-320-SA-TB-0001 | [8 empty] | F0Z-708705 | IFI | [50 empty] | 0
3 | 1 | 4 | 4 | 2 | 0 | 0 | 3.1.4.4.2 |  | Fire Fighting Equipment | [61 empty] | Deleted
3 | 1 | 4 | 4 | 2 | 1 | 0 | 3.1.4.2.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 4 | 2 | 1 | 1 | 3.1.4.4.2.1.1 | BK-PPL-PEDCO-320-SA-MR-0002 | PMR For Fire Fighting Equipment |  | BK-PPL-PEDCO-320-SA-MR-0002 | [8 empty] | F0Z-708706 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 4 | 2 | 2 | 0 | 3.1.4.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 4 | 2 | 2 | 1 | 3.1.4.4.2.2.1 | BK-PPL-PEDCO-320-SA-TB-0002 | TBE For Fire Fighting Equipment |  | BK-PPL-PEDCO-320-SA-TB-0002 | [8 empty] | F0Z-708707 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 4 | 3 | 0 | 0 | 3.1.4.4.3 |  | Safety Signs | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 4 | 3 | 1 | 0 | 3.1.4.3.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 4 | 3 | 1 | 1 | 3.1.4.4.3.1.1 | BK-PPL-PEDCO-320-SA-MR-0003 | PMR For Safety Signs |  | BK-PPL-PEDCO-320-SA-MR-0003 | [8 empty] | F0Z-708708 | IFI | [50 empty] | 0
3 | 1 | 4 | 4 | 3 | 2 | 0 | 3.1.4.3.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 4 | 3 | 2 | 1 | 3.1.4.4.3.2.1 | BK-PPL-PEDCO-320-SA-TB-0003 | TBE For Safety Signs |  | BK-PPL-PEDCO-320-SA-TB-0003 | [8 empty] | F0Z-708709 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 5 | 0 | 0 | 0 | 3.1.4.5 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 5 | 1 | 0 | 0 | 3.1.4.5.1 |  | Expansion Of LV Switchgear | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 5 | 1 | 1 | 0 | 3.1.5.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 5 | 1 | 1 | 1 | 3.1.4.5.1.1.1 | BK-PPL-PEDCO-320-EL-MR-0001 | PMR For Expansion Of LV Switchgear in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-MR-0001 | BK-PPL-PEDCO-320-EL-MR-0001 | BK | PPL | PEDCO | 320 | EL | MR | 0001 | F0Z-708710 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 5 | 1 | 2 | 0 | 3.1.5.1.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 5 | 1 | 2 | 1 | 3.1.4.5.1.2.1 | BK-PPL-PEDCO-320-EL-TB-0001 | TBE For Expansion Of LV Switchgear in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-TB-0001 | BK-PPL-PEDCO-320-EL-TB-0001 | BK | PPL | PEDCO | 320 | EL | TB | 0001 | F0Z-708711 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 5 | 2 | 0 | 0 | 3.1.4.5.2 |  | Power & Control Cables | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 5 | 2 | 1 | 0 | 3.1.5.2.1 |  | Purchase Material Requisition (PMR)
3 | 1 | 4 | 5 | 2 | 1 | 1 | 3.1.4.5.2.1.1 | BK-PPL-PEDCO-320-EL-MR-0002 | PMR For Power & Control Cables in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-MR-0002 | BK-PPL-PEDCO-320-EL-MR-0002 | BK | PPL | PEDCO | 320 | EL | MR | 0002 | F0Z-708712 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 5 | 2 | 2 | 0 | 3.1.5.2.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 5 | 2 | 2 | 1 | 3.1.4.5.2.2.1 | BK-PPL-PEDCO-320-EL-TB-0002 | TBE For Power & Control Cables in Siahmakan Gas Injection |  | BK-PPL-PEDCO-320-EL-TB-0002 | BK-PPL-PEDCO-320-EL-TB-0002 | BK | PPL | PEDCO | 320 | EL | TB | 0002 | F0Z-708713 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 5 | 3 | 0 | 0 | 3.1.4.5.3 |  | Cathodic Protection System | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 5 | 3 | 1 | 0 | 3.1.5.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 5 | 3 | 1 | 1 | 3.1.4.5.3.1.1 | BK-PPL-PEDCO-320-EL-MR-0003 | PMR For Cathodic Protection System |  | BK-PPL-PEDCO-320-EL-MR-0003 | BK-PPL-PEDCO-320-EL-MR-0003 | BK | PPL | PEDCO | 320 | EL | MR | 0003 | F0Z-708714 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 5 | 3 | 2 | 0 | 3.1.5.3.2 |  | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 5 | 3 | 2 | 1 | 3.1.4.5.3.2.1 | BK-PPL-PEDCO-320-EL-TB-0003 | TBE For Cathodic Protection System |  | BK-PPL-PEDCO-320-EL-TB-0003 | BK-PPL-PEDCO-320-EL-TB-0003 | BK | PPL | PEDCO | 320 | EL | TB | 0003 | F0Z-708715 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 5 | 4 | 0 | 0 | 3.1.4.5.4 |  | Electrical Bulk Items & Earthing | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 5 | 4 | 1 | 0 | 3.1.5.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 5 | 4 | 1 | 1 | 3.1.4.5.4.1.1 | BK-PPL-PEDCO-320-EL-MR-0004 | PMR For Bulk Items, Earthing & Lighting in Siahmakan Gas Injection | PMR For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0004 | BK-PPL-PEDCO-320-EL-MR-0004 | BK | PPL | PEDCO | 320 | EL | MR | 0004 | F0Z-708716 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 4 | 5 | 4 | 2 | 0 | 3.1.5.4.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 4 | 5 | 4 | 2 | 1 | 3.1.4.5.4.2.1 | BK-PPL-PEDCO-320-EL-TB-0004 | TBE For Electrical Bulk Items, Earthing & Lighting in Siahmakan Gas Injection | TBE For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0004 | BK-PPL-PEDCO-320-EL-TB-0004 | BK | PPL | PEDCO | 320 | EL | TB | 0004 | F0Z-708717 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 5 | 0 | 0 | 0 | 0 | 3.1.5 |  | Commissioning Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 5 | 0 | 1 | 0 | 0 | 3.1.5.1 |  | Procedure/Plan
3 | 1 | 5 | 0 | 1 | 0 | 1 | 3.1.5 | BK-PPL-PEDCO-320-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure |  | BK-PPL-PEDCO-320-CO-PR-0001 | BK-PPL-PEDCO-320-CO-PR-0001 | BK | PPL | PEDCO | 320 | CO | PR | 0001 | F0Z-708718 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 1 | 6 | 0 | 0 | 0 | 0 | 3.1.6 |  | Field Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 6 | 0 | 1 | 0 | 0 | 3.1.6.1 |  | Query | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 6 | 0 | 1 | 0 | 1 | 3.1.6.1.1 | BK-PPL-PEDCO-320-GE-TQ-0001 | Technical/Site Queries |  | BK-PPL-PEDCO-320-GE-TQ-0001 | BK-PPL-PEDCO-320-GE-TQ-0001 | BK | PPL | PEDCO | 320 | GE | TQ | 0001 | F7Z-708719 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 6 | 0 | 2 | 0 | 0 | 3.1.6.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 6 | 0 | 2 | 0 | 1 | 3.1.6 | BK-PPL-PEDCO-320-GE-DO-0001 | As-Built Document Booklets |  | BK-PPL-PEDCO-320-GE-DO-0001 | BK-PPL-PEDCO-320-GE-DO-0001 | BK | PPL | PEDCO | 320 | GE | DO | 0001 | F0Z-708720 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 7 | 0 | 0 | 0 | 0 | 3.1.7 |  | Engineering Final Documentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 7 | 0 | 1 | 0 | 0 | 3.1.7.1 |  | Manual | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 7 | 0 | 1 | 0 | 1 | 3.1.7.1.1 | BK-PPL-PEDCO-320-GE-ML-0001 | Operating Manual |  | BK-PPL-PEDCO-320-GE-ML-0001 | BK-PPL-PEDCO-320-GE-ML-0001 | BK | PPL | PEDCO | 320 | GE | ML | 0001 | F0Z-708721 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 7 | 0 | 2 | 0 | 0 | 3.1.7.2 |  | Dossier | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 1 | 7 | 0 | 2 | 0 | 1 | 3.1 | BK-PPL-PEDCO-320-GE-DO-0001 | As-Built Document Booklets |  | BK-PPL-PEDCO-320-GE-DO-0001 | [8 empty] | F0Z-708720 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 1 | 7 | 0 | 2 | 0 | 2 | 3.1 | BK-PPL-PEDCO-320-GE-DO-0002 | Final Engineering Dossier |  | BK-PPL-PEDCO-320-GE-DO-0002 | BK-PPL-PEDCO-320-GE-DO-0002 | BK | PPL | PEDCO | 320 | GE | DO | 0002 | F0Z-708722 | AB-A | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 0 | 0 | 0 | 0 | 0 | 3.2 |  | Package 12- EPC # Compressor Station | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 1 | 0 | 0 | 0 | 0 | 3.2.1 |  | Basic Design Endorsement | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 1 | 0 | 0 | 0 | 1 | 3.2.1 | BK-GCS-PEDCO-120-GE-RT-0001 | Endorsement Report For Basic Design & Scope of Work |  | BK-GCS-PEDCO-120-GE-RT-0001 | [8 empty] | - |  | IFC | 2021-08-14 | 2021-08-28 | 2021-09-07 | 14 | 10 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-31 |  |  | B00 | IFC | T-0023 | 44408 | 1400/05/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-176098 | 44436 | 1400/06/06 | 44446 | 1400/06/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B00-Reject |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | [13 empty] | 1400-2294-176098 | 2021-08-28 | 1400/06/06 | 44446 | 1400/06/16 | CM | [8 empty] | B00-Reject
3 | 2 | 2 | 0 | 0 | 0 | 0 | 3.2.2 |  | Value Engineering | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 2 | 0 | 0 | 0 | 1 | 3.2.2 | BK-GCS-PEDCO-120-GE-RT-0002 | Value Engineering Study Report |  | BK-GCS-PEDCO-120-GE-RT-0002 | BK-GCS-PEDCO-120-GE-RT-0002 | BK | GCS | PEDCO | 120 | GE | RT | 0002 | F0Z-708723 | IFI | IFC | 2022-02-15 | 2022-03-10 | 2022-03-15 | 23 | 5 | 28 | IFA | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | IFA | 2022-07-27 | 2022-08-03 | 2022-08-14 | 7 | 11 | 18 | IFA | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-01 |  |  | D03 | IFA | T-1563 | 44860 | 1401/08/04 | T-1563 | 44860 | 1401/08/04 | BK-SUR-ENG-GEN-01-06196 | 44881 | 1401/08/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-GE-RT-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0531 | 2022-02-01 | 1400/11/12 |  |  |  | BK-SUR-ENG-PCS-00-03282 | 44622 | 1400/12/11 | CM-C2 | [6 empty] | 1400-2294-443284 | 2022-03-10 | 1400/12/19 | 44635 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0785 | 44661 | 1400/01/21 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-GE-RT-0002-D00 | [5 empty] | 1401-2294-68426 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-GE-RT-0002_D00 | [9 empty] | D02 | IFA | T-1149 | 44755 | 1401/04/22 | [13 empty] | 1401-2294-165128 | 44776 | 1401/05/12 | 44787 | 1401/05/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-GE-RT-0002_D01 | [9 empty] | D03 | IFA | T-1563 | 44860 | 1401/08/04 | T-1563 | 44860 | 1401/08/04 | BK-SUR-ENG-GEN-01-06196 | 44881 | 1401/08/25 | CM-C2 | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-GE-RT-0002_D02
3 | 2 | 2 | 0 | 0 | 0 | 2 | 3.2.2 | BK-GCS-PEDCO-120-GE-RT-0003 | HAZID Report For Compressor Station |  | BK-GCS-PEDCO-120-GE-RT-0003 | BK-GCS-PEDCO-120-GE-RT-0003 | BK | GCS | PEDCO | 120 | GE | RT | 0003 | F0Z-708724 | IFI | IFI | 2022-08-15 | 2022-09-19 | 2022-09-26 | 35 | 7 | 42 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-01 | 2022-11-19 |  | D01 | FI | T-1591 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1233 | 2022-08-01 | 1401/05/10 | [13 empty] | 1401-2294-228737 | 2022-09-19 | 1401/06/28 | 44830 | 1401/07/04 | AP | [10 empty] | D01 | FI | T-1591 | 44884 | 1401/08/28
3 | 2 | 2 | 0 | 0 | 0 | 3 | 3.2.2 | BK-GCS-PEDCO-120-GE-RT-0004 | HAZOP Report For Compressor Station |  | BK-GCS-PEDCO-120-GE-RT-0004 | BK-GCS-PEDCO-120-GE-RT-0004 | BK | GCS | PEDCO | 120 | GE | RT | 0004 | F0Z-708725 | IFI | IFI | 2022-08-15 | 2022-09-19 | 2022-09-26 | 35 | 7 | 42 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-01 | 2022-11-19 |  | D01 | FI | T-1591 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1233 | 2022-08-01 | 1401/05/10 | [13 empty] | 1401-2294-228737 | 2022-09-19 | 1401/06/28 | 44830 | 1401/07/04 | AP | [10 empty] | D01 | FI | T-1591 | 44884 | 1401/08/28
3 | 2 | 2 | 0 | 0 | 0 | 4 | 3.2.2 | BK-GCS-PEDCO-120-GE-RT-0005 | SIL Report For Compressor Station |  | BK-GCS-PEDCO-120-GE-RT-0005 | BK-GCS-PEDCO-120-GE-RT-0005 | BK | GCS | PEDCO | 120 | GE | RT | 0005 | F0Z-708726 | IFI | IFI | 2022-08-15 | 2022-09-19 | 2022-09-26 | 35 | 7 | 42 | FI | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-01 | 2022-11-19 |  | D01 | FI | T-1591 | 44884 | 1401/08/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1233 | 2022-08-01 | 1401/05/10 | [13 empty] | 1401-2294-228737 | 2022-09-19 | 1401/06/28 | 44830 | 1401/07/04 | AP | [10 empty] | D01 | FI | T-1591 | 44884 | 1401/08/28
3 | 2 | 3 | 0 | 0 | 0 | 0 | 3.2.3 |  | Detail Design | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 0 | 0 | 0 | 3.2.3.1 |  | Process | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 1 | 0 | 0 | 3.2.3.1.1 |  | Philosophy | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 1 | 0 | 1 | 3.2.3.1.1 | BK-GCS-PEDCO-120-PR-PH-0001 | Drainage Philosophy |  | BK-GCS-PEDCO-120-PR-PH-0001 | BK-GCS-PEDCO-120-PR-PH-0001 | BK | GCS | PEDCO | 120 | PR | PH | 0001 | F0Z-708727 | AFD | IFC | 2021-12-05 | 2021-12-11 | 2021-12-14 | 6 | 3 | 9 | IFA | 2022-02-12 | 2022-03-06 | 2022-03-08 | 22 | 2 | 24 | IFA | 2022-07-30 | 2022-08-18 | 2022-08-21 | 19 | 3 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-21 |  |  | D02 | IFA | T-1161 | 44758 | 1401/04/25 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05322 | 44774 | 1401/05/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183501 | 44791 | 1401/05/27 | 44794 | 1401/05/30 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 44537 | 1400/09/16 | CM-C2 | [6 empty] | 1400-2294-312238 | 2021-12-11 | 1400/09/20 | 44544 | 1400/09/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0001_D00 | [9 empty] | D01 | IFA | T-0520 | 44590 | 1400/11/09 |  |  |  | BK-SUR-ENG-PCS-00-03179 | 44614 | 1400/12/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0001_D00 | [5 empty] | 1400-2294-436900 | 44626 | 1400/12/15 | 44628 | 1400/12/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0001_D00 | [9 empty] | D02 | IFA | T-1161 | 44758 | 1401/04/25 |  |  |  | BK-SUR-ENG-PCS-01-05322 | 44774 | 1401/05/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0001 _D01 | [5 empty] | 1401-2294-183501 | 44791 | 1401/05/27 | 44794 | 1401/05/30 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0001 _D01
3 | 2 | 3 | 1 | 1 | 0 | 2 | 3.2.3.1.1 | BK-GCS-PEDCO-120-PR-PH-0002 | Control Philosophy |  | BK-GCS-PEDCO-120-PR-PH-0002 | BK-GCS-PEDCO-120-PR-PH-0002 | BK | GCS | PEDCO | 120 | PR | PH | 0002 | F0Z-708728 | AFD | IFC | 2022-03-06 | 2022-03-13 | 2022-04-01 | 7 | 19 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-20 |  |  | D00 | IFC | T-0612 | 44612 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03621 | 44635 | 1400/12/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445277 | 44632 | 1400/12/21 | 44635 | 1400/12/24 | CM | 0 | 1400-2294-447187 | 44633 | 1400/12/22 | 44652 | 1401/01/14 | CM | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 44635 | 1400/12/24 | CM |  | 1400-2294-447187 | 44633 | 1400/12/22 | 44652 | 1401/01/14 | CM
3 | 2 | 3 | 1 | 1 | 0 | 3 | 3.2.3.1.1 | BK-GCS-PEDCO-120-PR-PH-0003 | Flare,Blow Down And Relief Philosophy |  | BK-GCS-PEDCO-120-PR-PH-0003 | BK-GCS-PEDCO-120-PR-PH-0003 | BK | GCS | PEDCO | 120 | PR | PH | 0003 | F0Z-708729 | AFD | IFC | 2021-12-05 | 2021-12-11 | 2021-12-14 | 6 | 3 | 9 | IFA | 2022-05-09 | 2022-05-22 | 2022-05-23 | 13 | 1 | 14 | AFD | 2022-08-17 | 2022-08-18 | 2022-08-22 | 1 | 4 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-21 | 2022-08-03 |  | D02 | AFD | T-1245 | 44776 | 1401/05/12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401/-2294-183500 | 44791 | 1401/05/27 | 44795 | 1401/05/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 44537 | 1400/09/16 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-PH-0001_D00 | [5 empty] | 1400-2294-312238 | 2021-12-11 | 1400/09/20 | 44544 | 1400/09/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-PH-0001_D00 | [9 empty] | D01 | IFA | T-0862 | 44676 | 1401/02/06 |  |  |  | BK-SUR-ENG-PCS-01-04334 | 44702 | 1401/02/31 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0003_D00 | [5 empty] | 1401-2294-70050 | 44703 | 1401/02/31 | 44704 | 1401/03/02 | AP | NISOC-CRS-BK-GCS-PEDCO-000-PR-PH-0003_D00 | [9 empty] | D02 | AFD | T-1245 | 44776 | 1401/05/12 | [13 empty] | 1401/-2294-183500 | 44791 | 1401/05/27 | 44795 | 1401/05/31 | AP
3 | 2 | 3 | 1 | 1 | 0 | 4 | 3.2.3.1.1 | BK-GCS-PEDCO-120-PR-PH-0004 | Isolation Philosophy |  | BK-GCS-PEDCO-120-PR-PH-0004 | BK-GCS-PEDCO-120-PR-PH-0004 | BK | GCS | PEDCO | 120 | PR | PH | 0004 | F0Z-708730 | AFD | IFC | 2021-12-05 | 2022-03-21 | 2021-12-14 | 106 | -97 | 9 | IFA | 2022-05-02 | 2022-05-12 | 2022-05-16 | 10 | 4 | 14 | AFD | 2022-06-05 | 2022-06-14 | 2022-06-20 | 9 | 6 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-21 | 2022-05-22 |  | D02 | AFD | T-0945 | 44703 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-102603 | 44726 | 1401/03/24 | 44732 | 1401/03/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 44537 | 1400/09/16 | CM-C2 | [6 empty] | 1400-2294-312238 | 2021-12-11 | 1400/09/20 | 44544 | 1400/09/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-PH-0004_D00 | 1400-2294-419621 | 44641 | 1400/12/02 |  |  | CM |  |  |  | D01 | IFA | T-0838 | 44669 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04189 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D00 | [5 empty] | 1401-2294-59548 | 44693 | 1400/02/22 | 44697 | 1400/02/26 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D00 | [9 empty] | D02 | AFD | T-0945 | 44703 | 1401/03/01 | [13 empty] | 1401-2294-102603 | 44726 | 1401/03/24 | 44732 | 1401/03/30 | AP
3 | 2 | 3 | 1 | 1 | 0 | 5 | 3.2.3.1.1 | BK-GCS-PEDCO-120-PR-PH-0005 | ESD Philosophy |  | BK-GCS-PEDCO-120-PR-PH-0005 | BK-GCS-PEDCO-120-PR-PH-0005 | BK | GCS | PEDCO | 120 | PR | PH | 0005 | F0Z-708731 | AFD | IFC | 2022-03-06 | 2022-03-13 | 2022-04-01 | 7 | 19 | 26 | IFA | 2022-06-11 | 2022-06-15 | 2022-06-21 | 4 | 6 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-20 |  |  | D01 | IFA | T-1010 | 44709 | 1401/03/07 | T-1010 | 44709 | 1401/03/07 | BK-SUR-ENG-PCS-01-04781 | 44733 | 1401/03/31 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-104572 | 44727 | 1401/03/25 | 44733 | 1401/03/31 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 44635 | 1400/12/24 | CM |  | 1400-2294-447187 | 44633 | 1400/12/22 | 44652 | 1401/01/14 | CM |  |  |  | D01 | IFA | T-1010 | 44709 | 1401/03/07 | T-1010 | 44709 | 1401/03/07 | BK-SUR-ENG-PCS-01-04781 | 44733 | 1401/03/31 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0005_D00 | [5 empty] | 1401-2294-104572 | 44727 | 1401/03/25 | 44733 | 1401/03/31 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0005_D00
3 | 2 | 3 | 1 | 2 | 0 | 0 | 3.2.3.1.2 |  | Procedure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 2 | 0 | 1 | 3.2.3.1.2 | BK-GCS-PEDCO-120-PR-PR-0001 | Chemical Regeneration Procedure |  | BK-GCS-PEDCO-120-PR-PR-0001 | BK-GCS-PEDCO-120-PR-PR-0001 | BK | GCS | PEDCO | 120 | PR | PR | 0001 | F0Z-708732 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 1 | 2 | 0 | 2 | 3.2.3.1.2 | BK-GCS-PEDCO-120-PR-PR-0002 | Startup And Shutdown Procedure |  | BK-GCS-PEDCO-120-PR-PR-0002 | BK-GCS-PEDCO-120-PR-PR-0002 | BK | GCS | PEDCO | 120 | PR | PR | 0002 | F0Z-708733 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 1 | 3 | 0 | 0 | 3.2.3.1.3 |  | Description | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 3 | 0 | 1 | 3.2.3.1.3 | BK-GCS-PEDCO-120-PR-DP-0001 | Process & Utility Description |  | BK-GCS-PEDCO-120-PR-DP-0001 | BK-GCS-PEDCO-120-PR-DP-0001 | BK | GCS | PEDCO | 120 | PR | DP | 0001 | F0Z-708734 | AFD | IFC | 2022-03-06 | 2022-03-13 | 2022-04-01 | 7 | 19 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-20 |  |  | D00 | IFC | T-0612 | 44612 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03621 | 44635 | 1400/12/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445277 | 44632 | 1400/12/21 | 44635 | 1400/12/24 | CM | 0 | 1400-2294-447187 | 44633 | 1400/12/22 | 44652 | 1401/01/14 | CM | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 44635 | 1400/12/24 | CM |  | 1400-2294-447187 | 44633 | 1400/12/22 | 44652 | 1401/01/14 | CM
3 | 2 | 3 | 1 | 4 | 0 | 0 | 3.2.3.1.4 |  | Duty Specification
3 | 2 | 3 | 1 | 4 | 0 | 1 | 3.2.3.1.4 | BK-GCS-PEDCO-120-PR-SP-0001 | Duty Specification For Gas Dehydration Package |  | BK-GCS-PEDCO-120-PR-SP-0001 | BK-GCS-PEDCO-120-PR-SP-0001 | BK | GCS | PEDCO | 120 | PR | SP | 0001 | F0Z-708735 | AFD | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-12-22 | 2021-12-26 | 2021-12-28 | 4 | 2 | 6 | IFA | 2022-02-05 | 2022-03-10 | 2022-03-13 | 33 | 3 | 36 | IFA | 2022-05-28 | 2022-06-13 | 2022-06-15 | 16 | 2 | 18 | IFA | 2022-09-10 | 2022-10-29 | 2022-11-01 | 49 | 3 | 52 | AFD | 2022-11-22 | 2022-11-19 | 2022-11-20 | -3 | 1 | -2 | [7 empty] | Modify | 2021-12-08 | 2022-11-08 |  | D05 | AFD | T-1582 | 44873 | 1401/08/17 | T-1582 | 44873 | 1401/08/17 | BK-SUR-ENG-PCS-01-06148 | 44874 | 1401/08/18 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D04 | BK-SUR-ENG-PCS-01-06220 | 20-NON-2022 | 1401/08/29 | AP | 0 | 1401-2294-316930 | 44884 | 1401/08/28 | 44885 | 1401/08/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 44436 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/181042 | 2021-08-31 | 1400/06/09 | 44447 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0324 | 44538 | 1400/09/17 |  |  |  | BK-SUR-ENG-PCS-00-02423 | 44556 | 1400/10/05 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D00 | [5 empty] | 1400-2294-336102 | 44556 | 1400/10/05 | 44558 | 1400/10/07 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D00 | [9 empty] | D02 | IFA | T-0486 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-PCS-00-03083 | 44608 | 1400/11/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D01 | [5 empty] | 1400-2294-412912 | 44608 | 1400/11/27 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D01 | 1400-2294-443242 | 44630 | 1400/12/19 | 44633 | 1400/12/22 | CM |  |  |  | D03 | IFA | T-0940 | 44695 | 1401/02/24 | T-0940 | 44695 | 1401/02/24 | BK-SUR-ENG-PCS-01-04723 | 44727 | 1401/03/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D02 | [5 empty] | 1401-2294-100887 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D02 | [9 empty] | D04 | IFA | T-1317 | 44800 | 1401/06/05 |  |  |  | BK-SUR-ENG-PCS-01-05764 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D03 | [5 empty] | 1401-2294-285756 | 44863 | 1401/08/07 | 44866 | 1401/08/01 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D03 | [9 empty] | D05 | AFD | T-1582 | 44873 | 1401/08/17 | T-1582 | 44873 | 1401/08/17 | BK-SUR-ENG-PCS-01-06148 | 44874 | 1401/08/18 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D04 | BK-SUR-ENG-PCS-01-06220 | 20-NON-2022 | 1401/08/29 | AP |  | 1401-2294-316930 | 44884 | 1401/08/28 | 44885 | 1401/08/29 | AP
3 | 2 | 3 | 1 | 4 | 0 | 2 | 3.2.3.1.4 | BK-GCS-PEDCO-120-PR-SP-0002 | Duty Specification for Instrument/Plant Air & Nitrogen Packages |  | BK-GCS-PEDCO-120-PR-SP-0002 | BK-GCS-PEDCO-120-PR-SP-0002 | BK | GCS | PEDCO | 120 | PR | SP | 0002 | F0Z-708736 | AFD | IFC | 2022-01-11 | 2022-01-01 | 2022-01-04 | -10 | 3 | -7 | IFA | 2022-03-23 | 2022-04-22 | 2022-04-30 | 30 | 8 | 38 | IFA | 2022-08-24 | 2022-09-22 | 2022-10-02 | 29 | 10 | 39 | IFA | 2022-12-06 | 0 | 0 | -44901 | 0 | -44901 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-28 |  |  | D03 | IFA | T-1595 | 44887 | 1401/09/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0390 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02559 | 44565 | 1400/10/14 | CM-C3 | [6 empty] | 1400-2294-344439 | 2022-01-01 | 1400/10/11 | 44565 | 1400/10/14 | CM | [10 empty] | D01 | IFA | T-0702 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03818 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D01 | [5 empty] | 1401-2294-33758 | 44673 | 1401/02/02 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D00 | [9 empty] | D02 | IFA | T-1264 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05519 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D01 | [5 empty] | 1401-2294-233609 | 44826 | 1401/06/31 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D01 | [9 empty] | D03 | IFA | T-1595 | 44887 | 1401/09/01 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D02
3 | 2 | 3 | 1 | 4 | 0 | 3 | 3.2.3.1.4 | BK-GCS-PEDCO-120-PR-SP-0003 | Duty Specification for LP Flare Package (PK-2201) | Duty Specification for LP Flare Package | BK-GCS-PEDCO-120-PR-SP-0003 | BK-GCS-PEDCO-120-PR-SP-0003 | BK | GCS | PEDCO | 120 | PR | SP | 0003 | F0Z-708737 | AFD | IFC | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | IFA | 2022-10-22 | 0 | 0 | -44856 | 0 | -44856 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-09 |  |  | D01 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0703 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03869 | 44664 | 1401/01/23 | CM-C3 | [6 empty] | 1401-2294-43236 | 2022-04-29 | 1401/02/09 | 44682 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0003_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0003_D00
3 | 2 | 3 | 1 | 4 | 0 | 4 | 3.2.3.1.4 | BK-GCS-PEDCO-120-PR-SP-0004 | Duty Specification for Chemical Injection Package |  | BK-GCS-PEDCO-120-PR-SP-0004 | BK-GCS-PEDCO-120-PR-SP-0004 | BK | GCS | PEDCO | 120 | PR | SP | 0004 | F0Z-708738 | AFD | IFC | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | IFA | 2022-08-31 | 2022-10-25 | 2022-10-30 | 55 | 5 | 60 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-09 |  |  | D01 | IFA | T-1283 | 44790 | 1401/05/26 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05604 | 44809 | 1401/06/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281110 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0703 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03869 | 44664 | 1401/01/23 | CM-C3 | [6 empty] | 1401-2294-43236 | 2022-04-29 | 1401/02/09 | 44682 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-1283 | 44790 | 1401/05/26 |  |  |  | BK-SUR-ENG-PCS-01-05604 | 44809 | 1401/06/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0004_D00 | [5 empty] | 1401-2294-281110 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0004_D00
3 | 2 | 3 | 1 | 5 | 0 | 0 | 3.2.3.1.5 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 5 | 0 | 1 | 3.2.3.1.5 | BK-GCS-PEDCO-120-PR-CN-0001 | Calculation Note For Pumps |  | BK-GCS-PEDCO-120-PR-CN-0001 | BK-GCS-PEDCO-120-PR-CN-0001 | BK | GCS | PEDCO | 120 | PR | CN | 0001 | F0Z-708739 | AFD | IFC | 2021-12-27 | 2022-01-03 | 2022-01-05 | 7 | 2 | 9 | IFA | 2022-02-12 | 2022-03-06 | 2022-03-08 | 22 | 2 | 24 | IFA | 2022-04-09 | 2022-05-04 | 2022-05-08 | 25 | 4 | 29 | IFA | 2022-08-06 | 2022-08-18 | 2022-08-22 | 12 | 4 | 16 | IFA | 2022-09-07 | 2022-10-19 | 2022-10-23 | 42 | 4 | 46 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D04 | IFA | T-1310 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05608 | 44813 | 1401/06/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-271653 | 44853 | 1401/07/27 | 44857 | 1401/08/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0335 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-PCS-00-02475 | 44558 | 1400/10/07 | CM-C3 | [6 empty] | 1400-2294-348115 | 2022-01-03 | 1400/10/13 | 44566 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0520 | 44590 | 1400/11/09 |  |  |  | BK-SUR-ENG-PCS-00-03179 | 44614 | 1400/12/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D00 | [5 empty] | 1400-2294-436900 | 44626 | 1400/12/15 | 44628 | 1400/12/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D00 | [9 empty] | D02 | IFA | T-0744 | 44646 | 1401/01/06 |  |  |  | BK-SUR-ENG-PCS-01-03974 | 44669 | 1401/01/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D01 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D01 | [9 empty] | D03 | IFA | T-1179 | 44765 | 1401/05/01 |  |  |  | BK-SUR-ENG-PCS-01-05338 | 44775 | 1401/05/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D02 | [5 empty] | 1401-2294-183542 | 44791 | 1401/05/27 | 44795 | 1401/05/31 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D02 | [9 empty] | D04 | IFA | T-1310 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05608 | 44813 | 1401/06/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D03 | [5 empty] | 1401-2294-271653 | 44853 | 1401/07/27 | 44857 | 1401/08/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D03
3 | 2 | 3 | 1 | 5 | 0 | 2 | 3.2.3.1.5 | BK-GCS-PEDCO-120-PR-CN-0002 | Calculation Note For Drum Sizing |  | BK-GCS-PEDCO-120-PR-CN-0002 | BK-GCS-PEDCO-120-PR-CN-0002 | BK | GCS | PEDCO | 120 | PR | CN | 0002 | F0Z-708740 | AFD | IFC | 2021-10-10 | 2021-10-31 | 2021-11-06 | 21 | 6 | 27 | IFA | 2021-11-23 | 2021-11-27 | 2021-11-29 | 4 | 2 | 6 | IFA | 2022-01-11 | 2022-01-26 | 2022-01-29 | 15 | 3 | 18 | IFA | 2022-05-02 | 2022-05-12 | 2022-05-16 | 10 | 4 | 14 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-13 | 33 | 2 | 35 | IFA | 2022-11-06 | 0 | 0 | -44871 | 0 | -44871 | [7 empty] | Modify | 2021-09-26 |  |  | D05 | IFA | T-1530 | 44857 | 1401/08/01 | T-1530 | 44857 | 1401/08/01 | BK-SUR-ENG-PCS-01-06118 | 44872 | 1401/08/16 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0122 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01824 | 44492 | 1400/08/01 | RJ-C4 | [6 empty] | 1400-2294-255291 | 2021-10-31 | 1400/08/09 | 44506 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0221 | 44509 | 1400/08/18 |  |  |  | BK-SUR-ENG-PCS-00-02145 | 44529 | 1400/09/08 | C4-RJ | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002-D00 | [5 empty] | 1400-2290-293081 | 44527 | 1400/09/06 | 44529 | 1400/09/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002-D00 | [9 empty] | D02 | IFA | T-0391 | 44558 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02636 | 44572 | 1400/10/21 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D01 | [5 empty] | 1400-2294-383221 | 44587 | 1400/11/06 | 44590 | 1400/11/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D01 | [9 empty] | D03 | IFA | T-0838 | 44669 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04189 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02 | [5 empty] | 1401-2294-59548 | 44693 | 1400/02/22 | 44697 | 1400/02/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02 | [9 empty] | D04 | IFA | T-1194 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PCS-01-05355 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D03 | [5 empty] | 1401-2294-219105 | 44815 | 1401/06/20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D03 | [9 empty] | D05 | IFA | T-1530 | 44857 | 1401/08/01 | T-1530 | 44857 | 1401/08/01 | BK-SUR-ENG-PCS-01-06118 | 44872 | 1401/08/16 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D04 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D04
3 | 2 | 3 | 1 | 5 | 0 | 3 | 3.2.3.1.5 | BK-GCS-PEDCO-120-PR-CN-0003 | Calculation Note For Flow Element Sizing |  | BK-GCS-PEDCO-120-PR-CN-0003 | BK-GCS-PEDCO-120-PR-CN-0003 | BK | GCS | PEDCO | 120 | PR | CN | 0003 | F0Z-708741 | AFD | IFC | 2022-06-26 | 2022-07-21 | 2022-07-24 | 25 | 3 | 28 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-12 |  |  | D00 | IFC | T-1068 | 44724 | 1401/03/21 | T-1068 | 44724 | 1401/03/22 | BK-SUR-ENG-PCS-01-05011 | 44748 | 1401/04/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-146657 | 44763 | 1401/04/30 | 44766 | 1401/05/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1068 | 2022-06-12 | 1401/03/21 | T-1068 | 44724 | 1401/03/22 | BK-SUR-ENG-PCS-01-05011 | 44748 | 1401/04/15 | CM-C3 | [6 empty] | 1401-2294-146657 | 2022-07-21 | 1401/04/30 | 44766 | 1401/05/02 | CM
3 | 2 | 3 | 1 | 5 | 0 | 4 | 3.2.3.1.5 | BK-GCS-PEDCO-120-PR-CN-0004 | Calculation Note For PSV Sizing |  | BK-GCS-PEDCO-120-PR-CN-0004 | BK-GCS-PEDCO-120-PR-CN-0004 | BK | GCS | PEDCO | 120 | PR | CN | 0004 | F0Z-708742 | AFD | IFC | 2021-10-10 | 2021-10-31 | 2021-11-06 | 21 | 6 | 27 | IFA | 2022-02-09 | 2022-03-06 | 2022-03-08 | 25 | 2 | 27 | IFA | 2022-05-30 | 2022-06-13 | 2022-06-15 | 14 | 2 | 16 | IFA | 2022-10-22 | 0 | 0 | -44856 | 0 | -44856 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D03 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0122 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01824 | 44492 | 1400/08/01 | RJ-C4 | [6 empty] | 1400-2294-255291 | 2021-10-31 | 1400/08/09 | 44506 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0516 | 44587 | 1400/11/06 |  |  |  | BK-SUR-ENG-PCS-00-03137 | 44612 | 1400/12/01 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D00 | [5 empty] | 1400-2294-436867 | 44626 | 1400/12/15 | 44628 | 1400/12/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D00 | [9 empty] | D02 | IFA | T-0960 | 44697 | 1401/02/26 | T-0960 | 44697 | 1401/02/26 | BK-SUR-ENG-PCS-01-04509 | 44712 | 1401/03/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D01 | [5 empty] | 1401-2294-100884 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D01 | [9 empty] | D03 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D02
3 | 2 | 3 | 1 | 5 | 0 | 5 | 3.2.3.1.5 | BK-GCS-PEDCO-120-PR-CN-0005 | Calculation Note For Line Sizing |  | BK-GCS-PEDCO-120-PR-CN-0005 | BK-GCS-PEDCO-120-PR-CN-0005 | BK | GCS | PEDCO | 120 | PR | CN | 0005 | F0Z-708743 | AFD | IFC | 2021-10-10 | 2021-10-31 | 2021-11-06 | 21 | 6 | 27 | IFA | 2022-01-19 | 2022-02-12 | 2022-02-22 | 24 | 10 | 34 | IFA | 2022-05-28 | 2022-06-13 | 2022-06-15 | 16 | 2 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D02 | IFA | T-0940 | 44695 | 1401/02/24 | T-0940 | 44695 | 1401/02/24 | BK-SUR-ENG-PCS-01-04723 | 44727 | 1401/03/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-100887 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0122 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01824 | 44492 | 1400/08/01 | RJ-C4 | [6 empty] | 1400-2294-255291 | 2021-10-31 | 1400/08/09 | 44506 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0433 | 44566 | 1400/10/15 |  |  |  | BK-SUR-ENG-PCS-00-02769 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D00 | [5 empty] | 1400-2294-405206 | 44604 | 1400/11/23 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D00 | [9 empty] | D02 | IFA | T-0940 | 44695 | 1401/02/24 | T-0940 | 44695 | 1401/02/24 | BK-SUR-ENG-PCS-01-04723 | 44727 | 1401/03/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D01 | [5 empty] | 1401-2294-100887 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D01
3 | 2 | 3 | 1 | 5 | 0 | 6 | 3.2.3.1.5 | BK-GCS-PEDCO-120-PR-CN-0006 | Calculation Note For Control Valve Sizing |  | BK-GCS-PEDCO-120-PR-CN-0006 | BK-GCS-PEDCO-120-PR-CN-0006 | BK | GCS | PEDCO | 120 | PR | CN | 0006 | F0Z-708744 | AFD | IFC | 2021-10-10 | 2021-10-31 | 2021-11-06 | 21 | 6 | 27 | IFA | 2022-01-19 | 2022-02-12 | 2022-02-22 | 24 | 10 | 34 | IFA | 2022-05-23 | 2022-06-02 | 2022-06-06 | 10 | 4 | 14 | IFA | 2022-08-13 | 2022-09-11 | 2022-09-13 | 29 | 2 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D03 | IFA | T-1216 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05440 | 44787 | 1401/05/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-219114 | 44815 | 1401/06/20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0122 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01824 | 44492 | 1400/08/01 | RJ-C4 | [6 empty] | 1400-2294-255291 | 2021-10-31 | 1400/08/09 | 44506 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0433 | 44566 | 1400/10/15 |  |  |  | BK-SUR-ENG-PCS-00-02769 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D00 | [5 empty] | 1400-2294-405206 | 44604 | 1400/11/23 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D00 | [9 empty] | D02 | IFA | T-0917 | 44690 | 1401/02/19 | T-0917 | 44690 | 1401/02/19 | BK-SUR-ENG-PCS-01-04505 | 44712 | 1401/03/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D01 | [5 empty] | 1401-2294-87490 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D01 | [9 empty] | D03 | IFA | T-1216 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-PCS-01-05440 | 44787 | 1401/05/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02 | [5 empty] | 1401-2294-219114 | 44815 | 1401/06/20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02
3 | 2 | 3 | 1 | 5 | 0 | 7 | 3.2.3.1.5 | BK-GCS-PEDCO-120-PR-CN-0007 | Calculation Note For Depressurizing (Min. Design Temperature ) |  | BK-GCS-PEDCO-120-PR-CN-0007 | BK-GCS-PEDCO-120-PR-CN-0007 | BK | GCS | PEDCO | 120 | PR | CN | 0007 | F0Z-708745 | AFD | IFC | 2021-12-27 | 2022-01-08 | 2022-01-10 | 12 | 2 | 14 | IFA | 2022-05-09 | 2022-05-22 | 2022-05-23 | 13 | 1 | 14 | IFA | 2022-10-22 | 0 | 0 | -44856 | 0 | -44856 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D02 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0343 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-PCS-00-02501 | 44562 | 1400/10/11 | CM-C3 | [6 empty] | 1400-2294-354591 | 2022-01-08 | 1400/10/18 | 44571 | 1400/10/20 | CM | [10 empty] | D01 | IFA | T-0862 | 44676 | 1401/02/06 |  |  |  | BK-SUR-ENG-PCS-01-04334 | 44702 | 1401/02/31 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D00 | [5 empty] | 1401-2294-70050 | 44703 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D00 | [9 empty] | D02 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D01
3 | 2 | 3 | 1 | 6 | 0 | 0 | 3.2.3.1.6 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 6 | 1 | 0 | 3.2.1.6.1 |  | Fixed Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 6 | 1 | 1 | 3.2.3.1.6.1.1 | BK-GCS-PEDCO-120-PR-DT-0001 | Process Data Sheets For Inlet Gas K.O. Drum |  | BK-GCS-PEDCO-120-PR-DT-0001 | BK-GCS-PEDCO-120-PR-DT-0001 | BK | GCS | PEDCO | 120 | PR | DT | 0001 | F0Z-708746 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-11 | 2022-01-16 | 2022-01-17 | 5 | 1 | 6 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-13 | 33 | 2 | 35 | IFA | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 |  |  | D04 | IFA | T-1523 | 44856 | 1401/07/30 | T-1523 | 44856 | 1401/07/30 | BK-SUR-ENG-PCS-01-06080 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 44528 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 44531 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0392 | 44558 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02643 | 44572 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D00 | [5 empty] | 1400-2294-365761 | 44577 | 1400/10/26 | 44578 | 1400/10/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D00 | [9 empty] | D02 | IFA | T-0839 | 44669 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D01 | [5 empty] | 1401-2294-68573 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D01 | [9 empty] | D03 | IFA | T-1195 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PCS-01-05410 | 44786 | 1401/05/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D02 | [5 empty] | 1401-2294-219178 | 44815 | 1401/06.20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D02 | [9 empty] | D04 | IFA | T-1523 | 44856 | 1401/07/30 | T-1523 | 44856 | 1401/07/30 | BK-SUR-ENG-PCS-01-06080 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D03 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D03
3 | 2 | 3 | 1 | 6 | 1 | 2 | 3.2.3.1.6.1.2 | BK-GCS-PEDCO-120-PR-DT-0002 | Process Data Sheets For 1st Stage G.C. Suction Drums |  | BK-GCS-PEDCO-120-PR-DT-0002 | BK-GCS-PEDCO-120-PR-DT-0002 | BK | GCS | PEDCO | 120 | PR | DT | 0002 | F0Z-708747 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-11 | 2022-01-16 | 2022-01-16 | 5 | 0 | 5 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-13 | 33 | 2 | 35 | AFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-10-18 |  | D04 | AFC | T-1508 | 44852 | 1401/07/26 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 44528 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 44531 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0395 | 44558 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02644 | 44572 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D00 | [5 empty] | 1400-2294-365755 | 44577 | 1400/10/26 | 44577 | 1400/10/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D00 | [9 empty] | D02 | IFA | T-0839 | 44669 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D01 | [5 empty] | 1401-2294-68573 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D01 | [9 empty] | D03 | IFA | T-1195 | 44768 | 1401/05/04 | T-1195 | 44768 | 1401/05/04 | BK-SUR-ENG-PCS-01-05410 | 44786 | 1401/05/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D02 | [5 empty] | 1401-2294-219178 | 44815 | 1401/06.20 | 44817 | 1401/06/22 | Ap | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D02 | [9 empty] | D04 | AFC | T-1508 | 44852 | 1401/07/26 |  |  |  | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D03 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D03
3 | 2 | 3 | 1 | 6 | 1 | 3 | 3.2.3.1.6.1.3 | BK-GCS-PEDCO-120-PR-DT-0003 | Process Data Sheets For 1st Stage Gas Air Coolers |  | BK-GCS-PEDCO-120-PR-DT-0003 | BK-GCS-PEDCO-120-PR-DT-0003 | BK | GCS | PEDCO | 120 | PR | DT | 0003 | F0Z-708748 | AFC | IFC | 2021-11-21 | 2021-11-18 | 2021-11-27 | -3 | 9 | 6 | IFA | 2021-12-21 | 0 | 0 | -44551 | 0 | -44551 | IFA | 2022-07-06 | 2022-07-28 | 2022-08-01 | 22 | 4 | 26 | IFA | 2022-08-20 | 2022-09-20 | 2022-09-19 | 31 | -1 | 30 | IFA | 2022-11-21 | 0 | 0 | -44886 | 0 | -44886 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-07 |  |  | D04 | IFA | T-1580 | 44872 | 1401/08/16 | T-1580 | 44872 | 1401/08/16 | BK-SUR-ENG-PCS-01-06241 | 44887 | 1401/09/01 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0215 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PCS-00-02121 | 44527 | 1400/09/06 | CM-C3 | [6 empty] | 1400-2294-281414 | 2021-11-18 | 1400/08/27 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0302 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PCS-00-02395 | 44551 | 1400/09/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D00 | [9 empty] | D02 | IFA | T-1109 | 44734 | 1401/04/01 |  |  |  | BK-SUR-ENG-PCS-01-05196 | 44761 | 1401/04/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D01 | [5 empty] | 1401-2294-156959 | 44770 | 1401/05/06 | 44774 | 1401/05/10 | CM | [10 empty] | D03 | IFA | T-1252 | 44779 | 1401/05/15 |  |  |  | BK-SUR-ENG-PCS-01-05481 | 44793 | 1401/05/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D02 | [5 empty] | 1401-2294-226250 | 44824 | 1401/06/27 | 44823 | 1401/06/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D02 | [9 empty] | D04 | IFA | T-1580 | 44872 | 1401/08/16 | T-1580 | 44872 | 1401/08/16 | BK-SUR-ENG-PCS-01-06241 | 44887 | 1401/09/01 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D03 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D03
3 | 2 | 3 | 1 | 6 | 1 | 4 | 3.2.3.1.6.1.4 | BK-GCS-PEDCO-120-PR-DT-0004 | Process Data Sheets For 2nd Stage G.C. Suction Drums |  | BK-GCS-PEDCO-120-PR-DT-0004 | BK-GCS-PEDCO-120-PR-DT-0004 | BK | GCS | PEDCO | 120 | PR | DT | 0004 | F0Z-708749 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-11 | 2022-01-16 | 2022-01-16 | 5 | 0 | 5 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-13 | 33 | 2 | 35 | AFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-10-18 |  | D04 | AFC | T-1508 | 44852 | 1401/07/26 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 44528 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 44531 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0395 | 44558 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02644 | 44572 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D00 | [5 empty] | 1400-2294-365755 | 44577 | 1400/10/26 | 44577 | 1400/10/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D00 | [9 empty] | D02 | IFA | T-0839 | 44669 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D01 | [5 empty] | 1401-2294-68573 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D01 | [9 empty] | D03 | IFA | T-1195 | 44768 | 1401/05/04 | T-1195 | 44768 | 1401/05/04 | BK-SUR-ENG-PCS-01-05410 | 44786 | 1401/05/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D02 | [5 empty] | 1401-2294-219178 | 44815 | 1401/06.20 | 44817 | 1401/06/22 | Ap | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D02 | [9 empty] | D04 | AFC | T-1508 | 44852 | 1401/07/26 |  |  |  | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D03 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D03
3 | 2 | 3 | 1 | 6 | 1 | 5 | 3.2.3.1.6.1.5 | BK-GCS-PEDCO-120-PR-DT-0005 | Process Data Sheets For 2nd Stage Gas Air Coolers |  | BK-GCS-PEDCO-120-PR-DT-0005 | BK-GCS-PEDCO-120-PR-DT-0005 | BK | GCS | PEDCO | 120 | PR | DT | 0005 | F0Z-708750 | AFC | IFC | 2021-11-21 | 2021-11-18 | 2021-11-27 | -3 | 9 | 6 | IFA | 2021-12-21 | 0 | 0 | -44551 | 0 | -44551 | IFA | 2022-07-06 | 2022-07-28 | 2022-08-01 | 22 | 4 | 26 | IFA | 2022-08-20 | 2022-09-20 | 2022-09-19 | 31 | -1 | 30 | IFA | 2022-11-21 | 0 | 0 | -44886 | 0 | -44886 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-07 |  |  | D04 | IFA | T-1580 | 44872 | 1401/08/16 | T-1580 | 44872 | 1401/08/16 | BK-SUR-ENG-PCS-01-06241 | 44887 | 1401/09/01 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0215 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PCS-00-02121 | 44527 | 1400/09/06 | CM-C3 | [6 empty] | 1400-2294-281414 | 2021-11-18 | 1400/08/27 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0302 | 44537 | 1400/09/16 |  |  |  | BK-SUR-ENG-PCS-00-02395 | 44551 | 1400/09/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D00 | [9 empty] | D02 | IFA | T-1109 | 44734 | 1401/04/01 |  |  |  | BK-SUR-ENG-PCS-01-05196 | 44761 | 1401/04/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D01 | [5 empty] | 1401-2294-156959 | 44770 | 1401/05/06 | 44774 | 1401/05/10 | CM | [10 empty] | D03 | IFA | T-1252 | 44779 | 1401/05/15 |  |  |  | BK-SUR-ENG-PCS-01-05481 | 44793 | 1401/05/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D02 | [5 empty] | 1401-2294-226250 | 44824 | 1401/06/27 | 44823 | 1401/06/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D02 | [9 empty] | D04 | IFA | T-1580 | 44872 | 1401/08/16 | T-1580 | 44872 | 1401/08/16 | BK-SUR-ENG-PCS-01-06241 | 44887 | 1401/09/01 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D03 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D03
3 | 2 | 3 | 1 | 6 | 1 | 6 | 3.2.3.1.6.1.6 | BK-GCS-PEDCO-120-PR-DT-0006 | Process Data Sheets For Discharge Gas K.O. Drum |  | BK-GCS-PEDCO-120-PR-DT-0006 | BK-GCS-PEDCO-120-PR-DT-0006 | BK | GCS | PEDCO | 120 | PR | DT | 0006 | F0Z-708751 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-11 | 2022-01-16 | 2022-01-16 | 5 | 0 | 5 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-13 | 33 | 2 | 35 | AFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-10-18 |  | D04 | AFC | T-1508 | 44852 | 1401/07/26 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 44528 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 44531 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0395 | 44558 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02644 | 44572 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D00 | [5 empty] | 1400-2294-365755 | 44577 | 1400/10/26 | 44577 | 1400/10/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D00 | [9 empty] | D02 | IFA | T-0839 | 44669 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D01 | [5 empty] | 1401-2294-68573 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D01 | [9 empty] | D03 | IFA | T-1195 | 44768 | 1401/05/04 | T-1195 | 44768 | 1401/05/04 | BK-SUR-ENG-PCS-01-05410 | 44786 | 1401/05/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D02 | [5 empty] | 1401-2294-219178 | 44815 | 1401/06.20 | 44817 | 1401/06/22 | Ap | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D02 | [9 empty] | D04 | AFC | T-1508 | 44852 | 1401/07/26 |  |  |  | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D03 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D03
3 | 2 | 3 | 1 | 6 | 1 | 7 | 3.2.3.1.6.1.7 | BK-GCS-PEDCO-120-PR-DT-0007 | Process Data Sheets For Diesel Oil Drum |  | BK-GCS-PEDCO-120-PR-DT-0007 | BK-GCS-PEDCO-120-PR-DT-0007 | BK | GCS | PEDCO | 120 | PR | DT | 0007 | F0Z-708752 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-01-17 | 2022-01-23 | 5 | 6 | 11 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-13 | 33 | 2 | 35 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 |  |  | D03 | IFA | T-1195 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05410 | 44786 | 1401/05/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-219178 | 44815 | 1401/06.20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 44528 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 44531 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0404 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02657 | 44573 | 1400/10/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D00 | [5 empty] | 1400-2294-368480 | 44578 | 1400/10/27 | 44584 | 1400/11/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D00 | [9 empty] | D02 | IFA | T-0839 | 44669 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D01 | [5 empty] | 1401-2294-68573 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D01 | [9 empty] | D03 | IFA | T-1195 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PCS-01-05410 | 44786 | 1401/05/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D02 | [5 empty] | 1401-2294-219178 | 44815 | 1401/06.20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D02
3 | 2 | 3 | 1 | 6 | 1 | 8 | 3.2.3.1.6.1.8 | BK-GCS-PEDCO-120-PR-DT-0008 | Process Data Sheets For Instrument Air Receiver |  | BK-GCS-PEDCO-120-PR-DT-0008 | BK-GCS-PEDCO-120-PR-DT-0008 | BK | GCS | PEDCO | 120 | PR | DT | 0008 | F0Z-708753 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-01-17 | 2022-01-23 | 5 | 6 | 11 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-13 | 33 | 2 | 35 | AFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-10-18 |  | D04 | AFC | T-1508 | 44852 | 1401/07/26 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 44528 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 44531 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0404 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02657 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D00 | [5 empty] | 1400-2294-368480 | 44578 | 1400/10/27 | 44584 | 1400/11/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D00 | [9 empty] | D02 | IFA | T-0839 | 44669 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D01 | [5 empty] | 1401-2294-68573 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D01 | [9 empty] | D03 | IFA | T-1195 | 44768 | 1401/05/04 | T-1195 | 44768 | 1401/05/04 | BK-SUR-ENG-PCS-01-05410 | 44786 | 1401/05/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D02 | [5 empty] | 1401-2294-219178 | 44815 | 1401/06.20 | 44817 | 1401/06/22 | Ap | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D02 | [9 empty] | D04 | AFC | T-1508 | 44852 | 1401/07/26 |  |  |  | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D03 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D03
3 | 2 | 3 | 1 | 6 | 1 | 9 | 3.2.3.1.6.1.9 | BK-GCS-PEDCO-120-PR-DT-0009 | Process Data Sheets For Nitrogen Receiver |  | BK-GCS-PEDCO-120-PR-DT-0009 | BK-GCS-PEDCO-120-PR-DT-0009 | BK | GCS | PEDCO | 120 | PR | DT | 0009 | F0Z-708754 | AFC | IFC | 2021-11-24 | 2022-10-31 | 2022-06-11 | 341 | -142 | 199 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-14 | 33 | 3 | 36 | AFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-10-18 |  | D02 | AFC | T-1508 | 44852 | 1401/07/26 | T-1508 | 44852 | 1401/07/26 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-229-296922 | 2022-10-31 | 1400/09/08 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1196 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PCS-01-05441 | 44787 | 1401/05/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0009_D00 | [5 empty] | 1401-2294-219332 | 44815 | 1401/06/20 | 44818 | 1401/06/23 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0009_D00 | [9 empty] | D02 | AFC | T-1508 | 44852 | 1401/07/26 | T-1508 | 44852 | 1401/07/26 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0009_D01
3 | 2 | 3 | 1 | 6 | 1 | 10 | 3.2.3.1.6.1.10 | BK-GCS-PEDCO-120-PR-DT-0010 | Process Data Sheets For Close Drain Drum |  | BK-GCS-PEDCO-120-PR-DT-0010 | BK-GCS-PEDCO-120-PR-DT-0010 | BK | GCS | PEDCO | 120 | PR | DT | 0010 | F0Z-708755 | AFC | IFC | 2021-11-24 | 2022-10-31 | 2022-06-11 | 341 | -142 | 199 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-14 | 33 | 3 | 36 | IFA | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 |  |  | D02 | IFA | T-1523 | 44856 | 1401/07/30 | T-1523 | 44856 | 1401/07/30 | BK-SUR-ENG-PCS-01-06080 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0010_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0010_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-229-296922 | 2022-10-31 | 1400/09/08 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1196 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PCS-01-05441 | 44787 | 1401/05/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0010_D00 | [5 empty] | 1401-2294-219332 | 44815 | 1401/06/20 | 44818 | 1401/06/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0010_D00 | [9 empty] | D02 | IFA | T-1523 | 44856 | 1401/07/30 | T-1523 | 44856 | 1401/07/30 | BK-SUR-ENG-PCS-01-06080 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0010_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0010_D01
3 | 2 | 3 | 1 | 6 | 1 | 11 | 3.2.3.1.6.1.11 | BK-GCS-PEDCO-120-PR-DT-0011 | Process Data Sheets For Elevated Potable Water Tank |  | BK-GCS-PEDCO-120-PR-DT-0011 | BK-GCS-PEDCO-120-PR-DT-0011 | BK | GCS | PEDCO | 120 | PR | DT | 0011 | F0Z-708756 | AFC | IFC | 2021-11-24 | 2022-10-31 | 2022-06-11 | 341 | -142 | 199 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-14 | 33 | 3 | 36 | AFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-10-18 |  | D02 | AFC | T-1508 | 44852 | 1401/07/26 | T-1508 | 44852 | 1401/07/26 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-229-296922 | 2022-10-31 | 1400/09/08 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1196 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PCS-01-05441 | 44787 | 1401/05/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0011_D00 | [5 empty] | 1401-2294-219332 | 44815 | 1401/06/20 | 44818 | 1401/06/23 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0011_D00 | [9 empty] | D02 | AFC | T-1508 | 44852 | 1401/07/26 | T-1508 | 44852 | 1401/07/26 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0011_D01
3 | 2 | 3 | 1 | 6 | 1 | 12 | 3.2.3.1.6.1.12 | BK-GCS-PEDCO-120-PR-DT-0012 | Process Data Sheets For Flare K.O. Drum |  | BK-GCS-PEDCO-120-PR-DT-0012 | BK-GCS-PEDCO-120-PR-DT-0012 | BK | GCS | PEDCO | 120 | PR | DT | 0012 | F0Z-708757 | AFC | IFC | 2021-11-24 | 2022-10-31 | 2022-06-11 | 341 | -142 | 199 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-14 | 33 | 3 | 36 | AFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-10-18 |  | D02 | AFC | T-1508 | 44852 | 1401/07/26 | T-1508 | 44852 | 1401/07/26 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0012_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-229-296922 | 2022-10-31 | 1400/09/08 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1196 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PCS-01-05441 | 44787 | 1401/05/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0012_D00 | [5 empty] | 1401-2294-219332 | 44815 | 1401/06/20 | 44818 | 1401/06/23 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0012_D00 | [9 empty] | D02 | AFC | T-1508 | 44852 | 1401/07/26 | T-1508 | 44852 | 1401/07/26 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0012_D01
3 | 2 | 3 | 1 | 6 | 1 | 13 | 3.2.3.1.6.1.13 | BK-GCS-PEDCO-120-PR-DT-0013 | Process Data Sheets For Fuel Gas K.O. Drum |  | BK-GCS-PEDCO-120-PR-DT-0013 | BK-GCS-PEDCO-120-PR-DT-0013 | BK | GCS | PEDCO | 120 | PR | DT | 0013 | F0Z-708758 | AFC | IFC | 2021-11-24 | 2022-10-31 | 2022-06-11 | 341 | -142 | 199 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-14 | 33 | 3 | 36 | IFA | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 |  |  | D02 | IFA | T-1523 | 44856 | 1401/07/30 | T-1523 | 44856 | 1401/07/30 | BK-SUR-ENG-PCS-01-06080 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0013_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0013_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-229-296922 | 2022-10-31 | 1400/09/08 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1196 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PCS-01-05441 | 44787 | 1401/05/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0013_D00 | [5 empty] | 1401-2294-219332 | 44815 | 1401/06/20 | 44818 | 1401/06/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0013_D00 | [9 empty] | D02 | IFA | T-1523 | 44856 | 1401/07/30 | T-1523 | 44856 | 1401/07/30 | BK-SUR-ENG-PCS-01-06080 | 44870 | 1401/08/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0013_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0013_D01
3 | 2 | 3 | 1 | 6 | 1 | 14 | 3.2.3.1.6.1.14 | BK-GCS-PEDCO-120-PR-DT-0014 | Process Data Sheets For Slug Catcher |  | BK-GCS-PEDCO-120-PR-DT-0014 | BK-GCS-PEDCO-120-PR-DT-0014 | BK | GCS | PEDCO | 120 | PR | DT | 0014 | F0Z-708759 | AFC | IFC | 2021-11-24 | 2022-10-31 | 2022-06-11 | 341 | -142 | 199 | IFA | 2022-08-09 | 2022-09-11 | 2022-09-14 | 33 | 3 | 36 | AFC | 2022-11-01 | 0 | 0 | -44866 | 0 | -44866 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 | 2022-10-18 |  | D02 | AFC | T-1508 | 44852 | 1401/07/26 | T-1508 | 44852 | 1401/07/26 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0014_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-229-296922 | 2022-10-31 | 1400/09/08 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1196 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-PCS-01-05441 | 44787 | 1401/05/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0014_D00 | [5 empty] | 1401-2294-219332 | 44815 | 1401/06/20 | 44818 | 1401/06/23 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0014_D00 | [9 empty] | D02 | AFC | T-1508 | 44852 | 1401/07/26 | T-1508 | 44852 | 1401/07/26 | BK-SUR-ENG-PCS-01-06086 | 44871 | 1401/08/15 | CM-C2 | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0014_D01
3 | 2 | 3 | 1 | 6 | 1 | 15 | 3.2.3.1.6.1.15 | BK-GCS-PEDCO-120-PR-DT-0015 | Process Data Sheets For Degassing Vessel |  | BK-GCS-PEDCO-120-PR-DT-0015 | BK-GCS-PEDCO-120-PR-DT-0015 | BK | GCS | PEDCO | 120 | PR | DT | 0015 | F0Z-708760 | AFC | IFC | 2021-11-24 | 2022-10-31 | 2022-06-11 | 341 | -142 | 199 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-10 |  |  | D00 | IFC | T-0228 | 44510 | 1400/08/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02156 | 44530 | 1400/09/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2290-296922 | 44865 | 1400/09/08 | 44723 | 1401/03/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-296922 | 2022-10-31 | 1400/09/08 | 44723 | 1401/03/21 | CM
3 | 2 | 3 | 1 | 6 | 1 | 16 | 3.2.3.1.6.1.16 | BK-GCS-PEDCO-120-PR-DT-0016 | Process Data Sheets For Lean Glycol Storage Tank |  | BK-GCS-PEDCO-120-PR-DT-0016 | BK-GCS-PEDCO-120-PR-DT-0016 | BK | GCS | PEDCO | 120 | PR | DT | 0016 | F0Z-708761 | AFC | IFC | 2021-12-11 | 0 | 0 | -44541 | 0 | -44541 | IFA | 2022-10-23 | 0 | 0 | -44857 | 0 | -44857 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 |  |  | D01 | IFA | T-1466 | 44843 | 1401/07/17 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05973 | 44859 | 1401/08/03 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0271 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PCS-00-02232 | 44538 | 1400/09/17 | CM-C3 | [22 empty] | D01 | IFA | T-1466 | 44843 | 1401/07/17 |  |  |  | BK-SUR-ENG-PCS-01-05973 | 44859 | 1401/08/03 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0016_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0016_D00
3 | 2 | 3 | 1 | 6 | 1 | 17 | 3.2.3.1.6.1.17 | BK-GCS-PEDCO-120-PR-DT-0018 | Process Data Sheets For Slug Storage Tank |  | BK-GCS-PEDCO-120-PR-DT-0018 | BK-GCS-PEDCO-120-PR-DT-0018 | BK | GCS | PEDCO | 120 | PR | DT | 0018 | F0Z-708762 | AFC | IFC | 2021-12-11 | 0 | 0 | -44541 | 0 | -44541 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 |  |  | D00 | IFC | T-0271 | 44527 | 1400/09/06 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02232 | 44538 | 1400/09/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0271 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PCS-00-02232 | 44538 | 1400/09/17 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 18 | 3.2.3.1.6.1.18 | BK-GCS-PEDCO-120-PR-DT-0019 | Process Data Sheets For Glycol Sump Drum |  | BK-GCS-PEDCO-120-PR-DT-0019 | BK-GCS-PEDCO-120-PR-DT-0019 | BK | GCS | PEDCO | 120 | PR | DT | 0019 | F0Z-708763 | AFC | IFC | 2022-01-11 | 2022-01-16 | 2022-01-23 | 5 | 7 | 12 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-28 |  |  | D02 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0396 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02645 | 44572 | 1400/10/22 | CM-C3 | [6 empty] | 1400-2294-366632 | 2022-01-16 | 1400/10/26 | 44584 | 1400/11/03 | CM | [10 empty] | D01 | IFA | T-0839 | 44669 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D00 | [5 empty] | 1401-2294-68573 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D00 | [9 empty] | D02 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D01
3 | 2 | 3 | 1 | 6 | 2 | 0 | 3.2.1.6.2 |  | Rotary Equipment
3 | 2 | 3 | 1 | 6 | 2 | 1 | 3.2.3.1.6.2.1 | BK-GCS-PEDCO-120-PR-DT-0020 | Process Data Sheets For Slug Pumps |  | BK-GCS-PEDCO-120-PR-DT-0020 | BK-GCS-PEDCO-120-PR-DT-0020 | BK | GCS | PEDCO | 120 | PR | DT | 0020 | F0Z-708764 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-10 | 2022-05-07 | 2022-05-09 | 27 | 2 | 29 | IFA | 2022-08-06 | 2022-08-18 | 2022-08-22 | 12 | 4 | 16 | IFA | 2022-11-28 | 0 | 0 | -44893 | 0 | -44893 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-27 |  |  | D03 | IFA | T-1585 | 44879 | 1401/08/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 44605 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0754 | 44647 | 1401/01/07 |  |  |  | BK-SUR-ENG-PCS-01-03942 | 44668 | 1401/01/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D00 | [5 empty] | 1401-2294-49829 | 44688 | 1401/02/17 | 44690 | 1401/02/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D00 | [9 empty] | D02 | IFA | T-1179 | 44765 | 1401/05/01 |  |  |  | BK-SUR-ENG-PCS-01-05338 | 44775 | 1401/05/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D01 | [5 empty] | 1401-2294-183542 | 44791 | 1401/05/27 | 44795 | 1401/05/31 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D01 | [9 empty] | D03 | IFA | T-1585 | 44879 | 1401/08/23 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D02
3 | 2 | 3 | 1 | 6 | 2 | 2 | 3.2.3.1.6.2.2 | BK-GCS-PEDCO-120-PR-DT-0021 | Process Data Sheets For Glycol Transfer Pumps |  | BK-GCS-PEDCO-120-PR-DT-0021 | BK-GCS-PEDCO-120-PR-DT-0021 | BK | GCS | PEDCO | 120 | PR | DT | 0021 | F0Z-708765 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | IFA | 2022-08-24 | 2022-09-22 | 2022-10-02 | 29 | 10 | 39 | AFC | 2022-11-28 | 0 | 0 | -44893 | 0 | -44893 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-28 | 2022-11-14 |  | D03 | AFC | T-1586 | 44879 | 1401/08/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 44605 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0739 | 44648 | 1401/01/08 |  |  |  | BK-SUR-ENG-PCS-01-03899 | 44664 | 1401/01/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D00 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D00 | [9 empty] | D02 | IFA | T-1264 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05519 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D01 | [5 empty] | 1401-2294-233609 | 44826 | 1401/06/31 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D01 | [9 empty] | D03 | AFC | T-1586 | 44879 | 1401/08/23 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D02
3 | 2 | 3 | 1 | 6 | 2 | 3 | 3.2.3.1.6.2.3 | BK-GCS-PEDCO-120-PR-DT-0022 | Process Data Sheets For Glycol Manual Pump |  | BK-GCS-PEDCO-120-PR-DT-0022 | BK-GCS-PEDCO-120-PR-DT-0022 | BK | GCS | PEDCO | 120 | PR | DT | 0022 | F0Z-708766 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | IFA | 2022-08-24 | 2022-10-27 | 2022-10-02 | 64 | -25 | 39 | IFA | 2022-11-29 | 0 | 0 | -44894 | 0 | -44894 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-28 |  |  | D03 | IFA | T-1589 | 44880 | 1401/08/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 44605 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0739 | 44648 | 1401/01/08 |  |  |  | BK-SUR-ENG-PCS-01-03899 | 44664 | 1401/01/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D00 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D00 | [9 empty] | D02 | IFA | T-1265 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05593 | 44808 | 1401/06/13 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D01 | [5 empty] | 1401-2294-238226 | 44861 | 1401/07/05 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D01 | [9 empty] | D03 | IFA | T-1589 | 44880 | 1401/08/24 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D02
3 | 2 | 3 | 1 | 6 | 2 | 4 | 3.2.3.1.6.2.4 | BK-GCS-PEDCO-120-PR-DT-0023 | Process Data Sheets For Closed Drain Pumps |  | BK-GCS-PEDCO-120-PR-DT-0023 | BK-GCS-PEDCO-120-PR-DT-0023 | BK | GCS | PEDCO | 120 | PR | DT | 0023 | F0Z-708767 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | IFA | 2022-08-24 | 2022-09-22 | 2022-10-02 | 29 | 10 | 39 | IFA | 2022-11-28 | 0 | 0 | -44893 | 0 | -44893 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-28 |  |  | D03 | IFA | T-1585 | 44879 | 1401/08/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 44605 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0739 | 44648 | 1401/01/08 |  |  |  | BK-SUR-ENG-PCS-01-03899 | 44664 | 1401/01/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D00 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D00 | [9 empty] | D02 | IFA | T-1264 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05519 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D01 | [5 empty] | 1401-2294-233609 | 44826 | 1401/06/31 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D01 | [9 empty] | D03 | IFA | T-1585 | 44879 | 1401/08/23 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D02
3 | 2 | 3 | 1 | 6 | 2 | 5 | 3.2.3.1.6.2.5 | BK-GCS-PEDCO-120-PR-DT-0024 | Process Data Sheets For Sump Pumps |  | BK-GCS-PEDCO-120-PR-DT-0024 | BK-GCS-PEDCO-120-PR-DT-0024 | BK | GCS | PEDCO | 120 | PR | DT | 0024 | F0Z-708768 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | AFC | 2022-08-24 | 2022-10-27 | 2022-10-02 | 64 | -25 | 39 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-28 |  |  | D02 | AFC | T-1265 | 44783 | 1401/05/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05593 | 44808 | 1401/06/13 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238226 | 44861 | 1401/07/05 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 44605 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0739 | 44648 | 1401/01/08 |  |  |  | BK-SUR-ENG-PCS-01-03899 | 44664 | 1401/01/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D00 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D00 | [9 empty] | D02 | AFC | T-1265 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05593 | 44808 | 1401/06/13 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D01 | [5 empty] | 1401-2294-238226 | 44861 | 1401/07/05 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D01
3 | 2 | 3 | 1 | 6 | 2 | 6 | 3.2.3.1.6.2.6 | BK-GCS-PEDCO-120-PR-DT-0025 | Process Data Sheets For Flare KO Drum Pumps |  | BK-GCS-PEDCO-120-PR-DT-0025 | BK-GCS-PEDCO-120-PR-DT-0025 | BK | GCS | PEDCO | 120 | PR | DT | 0025 | F0Z-708769 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | IFA | 2022-08-24 | 2022-09-22 | 2022-10-02 | 29 | 10 | 39 | IFA | 2022-11-28 | 0 | 0 | -44893 | 0 | -44893 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-28 |  |  | D03 | IFA | T-1585 | 44879 | 1401/08/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 44548 | 1400/09/27 | RJ | [10 empty] | D01 | IFC | T-0739 | 44648 | 1401/01/08 |  |  |  | BK-SUR-ENG-PCS-01-03899 | 44664 | 1401/01/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D00 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D00 | [9 empty] | D02 | IFA | T-1264 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05519 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D01 | [5 empty] | 1401-2294-233609 | 44826 | 1401/06/31 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D01 | [9 empty] | D03 | IFA | T-1585 | 44879 | 1401/08/23 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D02
3 | 2 | 3 | 1 | 6 | 2 | 7 | 3.2.3.1.6.2.7 | BK-GCS-PEDCO-120-PR-DT-0026 | Process Data Sheets For Potable Water Pump |  | BK-GCS-PEDCO-120-PR-DT-0026 | BK-GCS-PEDCO-120-PR-DT-0026 | BK | GCS | PEDCO | 120 | PR | DT | 0026 | F0Z-708770 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | AFC | 2022-08-24 | 2022-10-27 | 2022-10-02 | 64 | -25 | 39 | AFC | 2022-11-28 | 0 | 0 | -44893 | 0 | -44893 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-28 | 2022-11-14 |  | D03 | AFC | T-1586 | 44879 | 1401/08/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 44548 | 1400/09/27 | RJ | [10 empty] | D01 | IFC | T-0739 | 44648 | 1401/01/08 |  |  |  | BK-SUR-ENG-PCS-01-03899 | 44664 | 1401/01/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D00 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D00 | [9 empty] | D02 | AFC | T-1265 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05593 | 44808 | 1401/06/13 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D01 | [5 empty] | 1401-2294-238226 | 44861 | 1401/07/05 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D01 | [9 empty] | D03 | AFC | T-1586 | 44879 | 1401/08/23 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D02
3 | 2 | 3 | 1 | 6 | 2 | 8 | 3.2.3.1.6.2.8 | BK-GCS-PEDCO-120-PR-DT-0027 | Process Data Sheets For Glycol Sump Pumps |  | BK-GCS-PEDCO-120-PR-DT-0027 | [8 empty] | F0Z-708771 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-0275 | 44528 | 1400/09/07 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02245 | 44541 | 1400/09/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-319047 | 44545 | 1400/09/24 | 44548 | 1400/09/27 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 44548 | 1400/09/27 | RJ
3 | 2 | 3 | 1 | 6 | 2 | 9 | 3.2.3.1.6.2.9 | BK-GCS-PEDCO-120-PR-DT-0028 | Process Data Sheets For Glycol Drain Pump |  | BK-GCS-PEDCO-120-PR-DT-0028 | BK-GCS-PEDCO-120-PR-DT-0028 | BK | GCS | PEDCO | 120 | PR | DT | 0028 | F0Z-708772 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | IFA | 2022-08-24 | 2022-10-27 | 2022-10-02 | 64 | -25 | 39 | IFA | 2022-11-29 | 0 | 0 | -44894 | 0 | -44894 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-28 |  |  | D03 | IFA | T-1589 | 44880 | 1401/08/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 44548 | 1400/09/27 | RJ | [10 empty] | D01 | IFC | T-0739 | 44648 | 1401/01/08 |  |  |  | BK-SUR-ENG-PCS-01-03899 | 44664 | 1401/01/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D00 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D00 | [9 empty] | D02 | IFA | T-1265 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05593 | 44808 | 1401/06/13 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D01 | [5 empty] | 1401-2294-238226 | 44861 | 1401/07/05 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D01 | [9 empty] | D03 | IFA | T-1589 | 44880 | 1401/08/24 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D02
[7 empty] | 3.2.3.1.6.2.10 | BK-GCS-PEDCO-120-PR-DT-0029 | Process Data Sheets of Diesel Pump |  | BK-GCS-PEDCO-120-PR-DT-0029 | BK-GCS-PEDCO-120-PR-DT-0029 | BK | GCS | PEDCO | 120 | PR | DT | 0029 | F0Z-708773 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | IFA | 2022-08-24 | 2022-09-22 | 2022-10-02 | 29 | 10 | 39 | IFA | 2022-11-28 | 0 | 0 | -44893 | 0 | -44893 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-28 |  |  | D03 | IFA | T-1585 | 44879 | 1401/08/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 44541 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 44548 | 1400/09/27 | RJ | [10 empty] | D01 | IFC | T-0739 | 44648 | 1401/01/08 |  |  |  | BK-SUR-ENG-PCS-01-03899 | 44664 | 1401/01/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D00 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D00 | [9 empty] | D02 | IFA | T-1264 | 44783 | 1401/05/19 |  |  |  | BK-SUR-ENG-PCS-01-05519 | 44797 | 1401/06/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D01 | [5 empty] | 1401-2294-233609 | 44826 | 1401/06/31 | 44836 | 1401/07/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D01 | [9 empty] | D03 | IFA | T-1585 | 44879 | 1401/08/23 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D02
3 | 2 | 3 | 1 | 6 | 3 | 0 | 3.2.1.6.3 |  | Packaged Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 6 | 3 | 1 | 3.2.3.1.6.3.1 | BK-GCS-PEDCO-120-PR-DT-0030 | Process Data Sheets For Gas Compressors Packages |  | BK-GCS-PEDCO-120-PR-DT-0030 | BK-GCS-PEDCO-120-PR-DT-0030 | BK | GCS | PEDCO | 120 | PR | DT | 0030 | F0Z-708774 | AFC | IFC | 2021-11-21 | 2021-11-18 | 2021-11-27 | -3 | 9 | 6 | IFA | 2022-01-15 | 2022-01-22 | 2022-01-29 | 7 | 7 | 14 | IFA | 2022-04-09 | 2022-05-04 | 2022-05-08 | 25 | 4 | 29 | IFA | 2022-08-20 | 2022-09-19 | 2022-09-20 | 30 | 1 | 31 | IFA | 2022-10-15 | 2022-11-14 | 2022-11-16 | 30 | 2 | 32 | AFC | 2022-12-06 | 0 | 0 | -44901 | 0 | -44901 | [7 empty] | Modify | 2021-11-07 | 2022-11-22 |  | D05 | AFC | T-1596 | 44887 | 1401/09/1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0215 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PCS-00-02121 | 44527 | 1400/09/06 | CM-C3 | [6 empty] | 1400-2294-281414 | 2021-11-18 | 1400/08/27 | 44527 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0412 | 44562 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02668 | 44576 | 1400/10/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030-D00 | [5 empty] | 1400-2294-375064 | 44583 | 1400/11/02 | 44590 | 1400/11/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0030-D00 | [9 empty] | D02 | IFA | T-0744 | 44646 | 1401/01/06 |  |  |  | BK-SUR-ENG-PCS-01-03974 | 44669 | 1401/01/29 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D01 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D01 | [9 empty] | D03 | IFA | T-1256 | 44779 | 1401/05/15 |  |  |  | BK-SUR-ENG-PCS-01-05489 | 44793 | 1401/05/29 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D02 | [5 empty] | 1401-2294-228117 | 44823 | 1401/06/28 | 44824 | 1401/06/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D02 | [9 empty] | D04 | IFA | T-1444 | 44835 | 1401/07/09 | T-1444 | 44835 | 1401/07/09 | BK-SUR-ENG-PCS-01-05886 | 44846 | 1401/07/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D03 | [5 empty] | 1401-2294-311290 | 44879 | 1401/08/23 | 44881 | 1401/08/25 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D03 | [9 empty] | D05 | AFC | T-1596 | 44887 | 1401/09/1 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D04
3 | 2 | 3 | 1 | 6 | 3 | 2 | 3.2.3.1.6.3.2 | BK-GCS-PEDCO-120-PR-DT-0031 | Process Data Sheets For Chemical Injection Packages |  | BK-GCS-PEDCO-120-PR-DT-0031 | BK-GCS-PEDCO-120-PR-DT-0031 | BK | GCS | PEDCO | 120 | PR | DT | 0031 | F0Z-708775 | AFC | IFC | 2022-05-23 | 2022-06-13 | 2022-06-15 | 21 | 2 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-09 |  |  | D00 | IFC | T-0921 | 44690 | 1401/02/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-100891 | 44725 | 1401/03/23 | 44727 | 1401/03/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 |  |  |  | BK-SUR-ENG-PCS-01-04652 | 44723 | 1401/03/21 | CM-C3 | [6 empty] | 1401-2294-100891 | 2022-06-13 | 1401/03/23 | 44727 | 1401/03/25 | CM
3 | 2 | 3 | 1 | 6 | 4 | 0 | 3.2.1.6.4 |  | Instruments
3 | 2 | 3 | 1 | 6 | 4 | 1 | 3.2.3.1.6.4.1 | BK-GCS-PEDCO-120-PR-DT-0032 | Process Data Sheets For Instrument Devices |  | BK-GCS-PEDCO-120-PR-DT-0032 | BK-GCS-PEDCO-120-PR-DT-0032 | BK | GCS | PEDCO | 120 | PR | DT | 0032 | F0Z-708776 | AFC | IFC | 2022-05-04 | 2022-05-21 | 2022-05-23 | 17 | 2 | 19 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-20 |  |  | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0032_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0032_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0848 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-PCS-01-04314 | 44702 | 1401/02/31 | CM-C3 | [6 empty] | 1401-2294-70086 | 2022-05-21 | 1401/02/31 | 44704 | 1401/03/02 | CM | [10 empty] | D01 | IFA | T-1474 | 44844 | 1401/07/18 | T-1474 | 44844 | 1401/07/18 | BK-SUR-ENG-PCS-01-06054 | 44835 | 1401/08/10 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0032_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0032_D00
3 | 2 | 3 | 1 | 7 | 0 | 0 | 3.2.3.1.7 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 7 | 0 | 1 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PF-0001 | Process Flow Diagram (PFD) |  | BK-GCS-PEDCO-120-PR-PF-0001 | BK-GCS-PEDCO-120-PR-PF-0001 | BK | GCS | PEDCO | 120 | PR | PF | 0001 | F2A-708777 | AFC | IFC | 2021-08-28 | 2021-09-01 | 2021-09-06 | 4 | 5 | 9 | IFA | 2021-10-31 | 2021-11-28 | 2021-11-14 | 28 | -14 | 14 | IFA | 2021-12-14 | 2021-12-30 | 2022-01-02 | 16 | 3 | 19 | IFA | 2022-01-22 | 2022-02-12 | 2022-02-22 | 21 | 10 | 31 | IFA | 2022-03-26 | 2022-04-21 | 2022-04-30 | 26 | 9 | 35 | IFA | 2022-10-23 | 0 | 0 | -44857 | 0 | -44857 | [7 empty] | Modify | 2021-08-14 |  |  | D05 | IFA | T-1466 | 44843 | 1401/07/17 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05973 | 44859 | 1401/08/03 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PF-0001 _D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001 _D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0049 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-PCS-00-01445 | 44440 | 1400/06/10 | CM-C3 | [6 empty] | 1400/2294/181163 | 2021-09-01 | 1400/06/10 | 44445 | 1400/06/15 | CM | [10 empty] | D01 | IFA | T-0161 | 44486 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01884 | 44501 | 1400/08/10 | CM-C3 | PEDCO-BK-GCS-PEDCO-120-PR-PF-0001_D00 | [5 empty] | 1400-2294-270371 | 44510 | 1400/08/19 | 44514 | 1400/08/23 | CM | NISOC-BK-GCS-PEDCO-120-PR-PF-0001_D00 | 1400-2290-294976 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D02 | IFA | T-0285 | 44530 | 1400/09/09 |  |  |  | BK-SUR-ENG-PCS-00-02363 | 44549 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D01 | [5 empty] | 1400-2294-342083 | 44560 | 1400/10/09 | 44563 | 1400/10/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D01 | [9 empty] | D03 | IFA | T-0437 | 44569 | 1400/10/18 |  |  |  | BK-SUR-ENG-PCS-00-02784 | 44584 | 1400/11/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D02 | [5 empty] | 1400-2294-405260 | 44604 | 1400/11/23 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D02 | [9 empty] | D04 | IFA | T-0716 | 44632 | 1400/12/21 |  |  |  | BK-SUR-ENG-PCS-01-03873 | 44663 | 1401/01/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D03 | [5 empty] | 1401-2294-33692 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D03 | [9 empty] | D05 | IFA | T-1466 | 44843 | 1401/07/17 |  |  |  | BK-SUR-ENG-PCS-01-05973 | 44859 | 1401/08/03 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PF-0001 _D04 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001 _D04
3 | 2 | 3 | 1 | 7 | 0 | 2 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-UF-0001 | Utility Flow Diagrams (UFD) |  | BK-GCS-PEDCO-120-PR-UF-0001 | BK-GCS-PEDCO-120-PR-UF-0001 | BK | GCS | PEDCO | 120 | PR | UF | 0001 | F2A-708778 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-14 | 27 | -14 | 13 | IFA | 2022-01-12 | 2022-01-17 | 2022-01-23 | 5 | 6 | 11 | IFA | 2022-03-23 | 2022-04-22 | 2022-04-30 | 30 | 8 | 38 | IFA | 2022-08-31 | 2022-10-25 | 2022-10-30 | 55 | 5 | 60 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-10-18 |  |  | D03 | IFA | T-1283 | 44790 | 1401/05/26 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05604 | 44809 | 1401/06/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281110 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0169 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01935 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-270393 | 2021-11-10 | 1400/08/19 | 44514 | 1400/08/23 | CM |  | 1400-2290-294882 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0404 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02657 | 44573 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D00 | [5 empty] | 1400-2294-368480 | 44578 | 1400/10/27 | 44584 | 1400/11/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D00 | [9 empty] | D02 | IFA | T-0702 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03818 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D01 | [5 empty] | 1401-2294-33758 | 44673 | 1401/02/02 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D01 | [9 empty] | D03 | IFA | T-1283 | 44790 | 1401/05/26 |  |  |  | BK-SUR-ENG-PCS-01-05604 | 44809 | 1401/06/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D02 | [5 empty] | 1401-2294-281110 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D02
3 | 2 | 3 | 1 | 7 | 0 | 3 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0001 | Symbol & Legend For PFD and P&ID |  | BK-GCS-PEDCO-120-PR-PI-0001 | BK-GCS-PEDCO-120-PR-PI-0001 | BK | GCS | PEDCO | 120 | PR | PI | 0001 | F2A-708779 | AFC | IFC | 2021-10-18 | 2021-11-09 | 2021-10-30 | 22 | -10 | 12 | IFA | 2022-01-25 | 2022-03-07 | 2022-03-09 | 41 | 2 | 43 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-04 |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0134 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-PCS-00-01867 | 44499 | 1400/08/08 | CM-C3 | PEDCO-CRS- BK-GNRAL-PEDCO-000-PR-PI-0001-D00 | [5 empty] | 1400-2294-269245 | 2021-11-09 | 1400/08/18 | 44499 | 1400/08/08 | CM | NISOC-CRS- BK-GNRAL-PEDCO-000-PR-PI-0001-D00 | [9 empty] | D01 | IFA | T-0450 | 44572 | 1400/10/20 |  |  |  | BK-SUR-ENG-PCS-00-02827 | 44587 | 1400/11/06 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D00 | [5 empty] | 1400-2294-407038 | 44604 | 1400/11/23 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D01 | [5 empty] | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D01
3 | 2 | 3 | 1 | 7 | 0 | 4 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0002 | P&ID - Gas Compression Inlet Gas Pipeline (Binak) |  | BK-GCS-PEDCO-120-PR-PI-0002 | BK-GCS-PEDCO-120-PR-PI-0002 | BK | GCS | PEDCO | 120 | PR | PI | 0002 | F2A-708780 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-25 | 2022-10-30 | 48 | 5 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1307 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 44485 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D00 | [5 empty] | 1400-2294-397290 | 44597 | 1400/11/16 | 44608 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D01 | [5 empty] | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-1087 | 44731 | 1401/03/29 |  |  |  | BK-SSR-ENG-PCS-01-05040 | 44751 | 1401/04/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D02 | [9 empty] | D04 | IFA | T-1307 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D03 | [5 empty] | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D03
3 | 2 | 3 | 1 | 7 | 0 | 5 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0003 | P&ID - Gas Compression Inlet Gas Pipeline (Golkhari) |  | BK-GCS-PEDCO-120-PR-PI-0003 | BK-GCS-PEDCO-120-PR-PI-0003 | BK | GCS | PEDCO | 120 | PR | PI | 0003 | F2A-708781 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-25 | 2022-10-30 | 48 | 5 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1307 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 44485 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D00 | [5 empty] | 1400-2294-397290 | 44597 | 1400/11/16 | 44608 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D01 | [5 empty] | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D01 | [9 empty] | D03 | IFA | T-1087 | 44731 | 1401/03/29 |  |  |  | BK-SSR-ENG-PCS-01-05040 | 44751 | 1401/04/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D02 | [9 empty] | D04 | IFA | T-1307 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D03 | [5 empty] | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D03
3 | 2 | 3 | 1 | 7 | 0 | 6 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0004 | P&ID - Slug Catcher System |  | BK-GCS-PEDCO-120-PR-PI-0004 | BK-GCS-PEDCO-120-PR-PI-0004 | BK | GCS | PEDCO | 120 | PR | PI | 0004 | F2A-708782 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-25 | 2022-10-30 | 48 | 5 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1307 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 44485 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D00 | [5 empty] | 1400-2294-397290 | 44597 | 1400/11/16 | 44608 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D01 | [5 empty] | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D01 | [9 empty] | D03 | IFA | T-1087 | 44731 | 1401/03/29 |  |  |  | BK-SSR-ENG-PCS-01-05040 | 44751 | 1401/04/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D02 | [9 empty] | D04 | IFA | T-1307 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D03 | [5 empty] | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D03
3 | 2 | 3 | 1 | 7 | 0 | 7 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0005 | P&ID - Gas Compression Inlet Knock Out Drum |  | BK-GCS-PEDCO-120-PR-PI-0005 | BK-GCS-PEDCO-120-PR-PI-0005 | BK | GCS | PEDCO | 120 | PR | PI | 0005 | F2A-708783 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-25 | 2022-10-30 | 48 | 5 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1307 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 44485 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D00 | [5 empty] | 1400-2294-397290 | 44597 | 1400/11/16 | 44608 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D01 | [5 empty] | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D01 | [9 empty] | D03 | IFA | T-1087 | 44731 | 1401/03/29 |  |  |  | BK-SSR-ENG-PCS-01-05040 | 44751 | 1401/04/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D02 | [9 empty] | D04 | IFA | T-1307 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D03 | [5 empty] | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D03
3 | 2 | 3 | 1 | 7 | 0 | 8 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0006 | P&ID - 1st Stage Gas Compression Suction Drums |  | BK-GCS-PEDCO-120-PR-PI-0006 | BK-GCS-PEDCO-120-PR-PI-0006 | BK | GCS | PEDCO | 120 | PR | PI | 0006 | F2A-708784 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-25 | 2022-10-30 | 48 | 5 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1307 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 44485 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D00 | [5 empty] | 1400-2294-397290 | 44597 | 1400/11/16 | 44608 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D01 | [5 empty] | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D01 | [9 empty] | D03 | IFA | T-1087 | 44731 | 1401/03/29 |  |  |  | BK-SSR-ENG-PCS-01-05040 | 44751 | 1401/04/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D02 | [9 empty] | D04 | IFA | T-1307 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D03 | [5 empty] | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D03
3 | 2 | 3 | 1 | 7 | 0 | 9 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0007 | P&ID - 1st Stage Gas Compression Compressors |  | BK-GCS-PEDCO-120-PR-PI-0007 | BK-GCS-PEDCO-120-PR-PI-0007 | BK | GCS | PEDCO | 120 | PR | PI | 0007 | F2A-708785 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-25 | 2022-10-30 | 48 | 5 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1307 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 44485 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D00 | [5 empty] | 1400-2294-397290 | 44597 | 1400/11/16 | 44608 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D01 | [5 empty] | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D01 | [9 empty] | D03 | IFA | T-1087 | 44731 | 1401/03/29 |  |  |  | BK-SSR-ENG-PCS-01-05040 | 44751 | 1401/04/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D02 | [9 empty] | D04 | IFA | T-1307 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D03 | [5 empty] | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D03
3 | 2 | 3 | 1 | 7 | 0 | 10 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0008 | P&ID - 1st Stage Gas Compression Air Coolers |  | BK-GCS-PEDCO-120-PR-PI-0008 | BK-GCS-PEDCO-120-PR-PI-0008 | BK | GCS | PEDCO | 120 | PR | PI | 0008 | F2A-708786 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-25 | 2022-10-30 | 48 | 5 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-09-26 |  |  | D04 | IFA | T-1307 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 44485 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 44580 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D00 | [5 empty] | 1400-2294-397290 | 44597 | 1400/11/16 | 44608 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D01 | [5 empty] | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D01 | [9 empty] | D03 | IFA | T-1087 | 44731 | 1401/03/29 |  |  |  | BK-SSR-ENG-PCS-01-05040 | 44751 | 1401/04/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D02 | [9 empty] | D04 | IFA | T-1307 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D03 | [5 empty] | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D03
3 | 2 | 3 | 1 | 7 | 0 | 11 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0009 | P&ID - 2nd Stage Gas Compression Suction Drums |  | BK-GCS-PEDCO-120-PR-PI-0009 | BK-GCS-PEDCO-120-PR-PI-0009 | BK | GCS | PEDCO | 120 | PR | PI | 0009 | F2A-708787 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-25 | 2022-10-30 | 48 | 5 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1307 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 44492 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 44580 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D00 | [5 empty] | 1400-2294-395122 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D01 | [5 empty] | 1401-2294-23096 | 44666 | 1401/01/26 | 44668 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D01 | [9 empty] | D03 | IFA | T-1087 | 44731 | 1401/03/29 |  |  |  | BK-SSR-ENG-PCS-01-05040 | 44751 | 1401/04/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D02 | [9 empty] | D04 | IFA | T-1307 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05694 | 44817 | 1401/06/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D03 | [5 empty] | 1401-2294-281080 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D03
3 | 2 | 3 | 1 | 7 | 0 | 12 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0010 | P&ID - 2nd Stage Gas Compression Compressors |  | BK-GCS-PEDCO-120-PR-PI-0010 | BK-GCS-PEDCO-120-PR-PI-0010 | BK | GCS | PEDCO | 120 | PR | PI | 0010 | F2A-708788 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-10-30 | 52 | 1 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1308 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 44492 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 44580 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D00 | [5 empty] | 1400-2294-395122 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 44656 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D01 | [5 empty] | 1401-2294-31443 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D01 | [9 empty] | D03 | IFA | T-1088 | 44731 | 1401/03/29 |  |  |  | BK-SUR-ENG-PCS-01-05064 | 44753 | 1401/04/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D02 | [9 empty] | D04 | IFA | T-1308 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D03 | [5 empty] | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D03
3 | 2 | 3 | 1 | 7 | 0 | 13 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0011 | P&ID - 2nd Stage Gas Compression Air Coolers |  | BK-GCS-PEDCO-120-PR-PI-0011 | BK-GCS-PEDCO-120-PR-PI-0011 | BK | GCS | PEDCO | 120 | PR | PI | 0011 | F2A-708789 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-10-30 | 52 | 1 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1308 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 44492 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 44580 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D00 | [5 empty] | 1400-2294-395122 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 44656 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D01 | [5 empty] | 1401-2294-31443 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D01 | [9 empty] | D03 | IFA | T-1088 | 44731 | 1401/03/29 |  |  |  | BK-SUR-ENG-PCS-01-05064 | 44753 | 1401/04/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D02 | [9 empty] | D04 | IFA | T-1308 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D03 | [5 empty] | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D03
3 | 2 | 3 | 1 | 7 | 0 | 14 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0012 | P&ID - 2nd Stage Gas Compression Discharge Drum |  | BK-GCS-PEDCO-120-PR-PI-0012 | BK-GCS-PEDCO-120-PR-PI-0012 | BK | GCS | PEDCO | 120 | PR | PI | 0012 | F2A-708790 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-10-30 | 52 | 1 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1308 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 44492 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 44580 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D00 | [5 empty] | 1400-2294-395122 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 44656 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D01 | [5 empty] | 1401-2294-31443 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D01 | [9 empty] | D03 | IFA | T-1088 | 44731 | 1401/03/29 |  |  |  | BK-SUR-ENG-PCS-01-05064 | 44753 | 1401/04/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D02 | [9 empty] | D04 | IFA | T-1308 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D03 | [5 empty] | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D03
3 | 2 | 3 | 1 | 7 | 0 | 15 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0013 | P&ID - Gas Compression Dehydration Package |  | BK-GCS-PEDCO-120-PR-PI-0013 | BK-GCS-PEDCO-120-PR-PI-0013 | BK | GCS | PEDCO | 120 | PR | PI | 0013 | F2A-708791 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-10-30 | 52 | 1 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1308 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 44492 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 44580 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D00 | [5 empty] | 1400-2294-395122 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 44656 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D01 | [5 empty] | 1401-2294-31443 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D01 | [9 empty] | D03 | IFA | T-1088 | 44731 | 1401/03/29 |  |  |  | BK-SUR-ENG-PCS-01-05064 | 44753 | 1401/04/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D02 | [9 empty] | D04 | IFA | T-1308 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D03 | [5 empty] | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D03
3 | 2 | 3 | 1 | 7 | 0 | 16 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0014 | P&ID - Lean Glycol Storage Tank |  | BK-GCS-PEDCO-120-PR-PI-0014 | BK-GCS-PEDCO-120-PR-PI-0014 | BK | GCS | PEDCO | 120 | PR | PI | 0014 | F2A-708792 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-10-30 | 52 | 1 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-09-26 |  |  | D04 | IFA | T-1308 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 44492 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 44563 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 44580 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D00 | [5 empty] | 1400-2294-395122 | 44596 | 1400/11/15 | 44600 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 44656 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D01 | [5 empty] | 1401-2294-31443 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D01 | [9 empty] | D03 | IFA | T-1088 | 44731 | 1401/03/29 |  |  |  | BK-SUR-ENG-PCS-01-05064 | 44753 | 1401/04/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D02 | [9 empty] | D04 | IFA | T-1308 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D03 | [5 empty] | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D03
3 | 2 | 3 | 1 | 7 | 0 | 17 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0015 | P&ID - Instrument & Plant Air System |  | BK-GCS-PEDCO-120-PR-PI-0015 | BK-GCS-PEDCO-120-PR-PI-0015 | BK | GCS | PEDCO | 120 | PR | PI | 0015 | F2A-708793 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFC | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-10-30 | 52 | 1 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-03 |  |  | D04 | IFA | T-1308 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | RJ | [10 empty] | D01 | IFC | T-0418 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D00 | [5 empty] | 1400-2294-401008 | 44599 | 1400/11/18 | 44601 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 44656 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D01 | [5 empty] | 1401-2294-31443 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D01 | [9 empty] | D03 | IFA | T-1088 | 44731 | 1401/03/29 |  |  |  | BK-SUR-ENG-PCS-01-05064 | 44753 | 1401/04/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D02 | [9 empty] | D04 | IFA | T-1308 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D03 | [5 empty] | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D03
3 | 2 | 3 | 1 | 7 | 0 | 18 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0016 | P&ID - Nitrogen Generation System |  | BK-GCS-PEDCO-120-PR-PI-0016 | BK-GCS-PEDCO-120-PR-PI-0016 | BK | GCS | PEDCO | 120 | PR | PI | 0016 | F2A-708794 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-10 | 27 | -18 | 9 | IFC | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-10-30 | 52 | 1 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-03 |  |  | D04 | IFA | T-1308 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | RJ |  | 1400-2290-294882 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFC | T-0418 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D00 | [5 empty] | 1400-2294-401008 | 44599 | 1400/11/18 | 44601 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 44656 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D01 | [5 empty] | 1401-2294-31443 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D01 | [9 empty] | D03 | IFA | T-1088 | 44731 | 1401/03/29 |  |  |  | BK-SUR-ENG-PCS-01-05064 | 44753 | 1401/04/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D02 | [9 empty] | D04 | IFA | T-1308 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D03 | [5 empty] | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D03
3 | 2 | 3 | 1 | 7 | 0 | 19 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0017 | P&ID - Close Drain System |  | BK-GCS-PEDCO-120-PR-PI-0017 | BK-GCS-PEDCO-120-PR-PI-0017 | BK | GCS | PEDCO | 120 | PR | PI | 0017 | F2A-708795 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-10 | 27 | -18 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-10-30 | 52 | 1 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-18 |  |  | D04 | IFA | T-1308 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | CM |  | 1400-2290-294882 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0418 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D00 | [5 empty] | 1400-2294-401008 | 44599 | 1400/11/18 | 44601 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 44656 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D01 | [5 empty] | 1401-2294-31443 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D01 | [9 empty] | D03 | IFA | T-1088 | 44731 | 1401/03/29 |  |  |  | BK-SUR-ENG-PCS-01-05064 | 44753 | 1401/04/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D02 | [9 empty] | D04 | IFA | T-1308 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05636 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D03 | [5 empty] | 1401-2294-283491 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D03
3 | 2 | 3 | 1 | 7 | 0 | 20 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0018 | P&ID - Corrosion Inhibitor Package |  | BK-GCS-PEDCO-120-PR-PI-0018 | BK-GCS-PEDCO-120-PR-PI-0018 | BK | GCS | PEDCO | 120 | PR | PI | 0018 | F2A-708796 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-10 | 2022-10-25 | 2022-10-26 | 45 | 1 | 46 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-18 |  |  | D04 | IFA | T-1314 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05731 | 44824 | 1401/06/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-280775 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0418 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D00 | [5 empty] | 1400-2294-401008 | 44599 | 1400/11/18 | 44601 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 44655 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D01 | [5 empty] | 1401-2294-33690 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D01 | [9 empty] | D03 | IFA | T-1089 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-PCS-01-05107 | 44755 | 1401/04/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D02 | [9 empty] | D04 | IFA | T-1314 | 44800 | 1401/06/05 |  |  |  | BK-SUR-ENG-PCS-01-05731 | 44824 | 1401/06/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D03 | [5 empty] | 1401-2294-280775 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D03
3 | 2 | 3 | 1 | 7 | 0 | 21 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0019 | P&ID - Methanol Injection Package |  | BK-GCS-PEDCO-120-PR-PI-0019 | BK-GCS-PEDCO-120-PR-PI-0019 | BK | GCS | PEDCO | 120 | PR | PI | 0019 | F2A-708797 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-11-01 | 52 | 3 | 55 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-18 |  |  | D04 | IFA | T-1309 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0418 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D00 | [5 empty] | 1400-2294-401008 | 44599 | 1400/11/18 | 44601 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 44655 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D01 | [5 empty] | 1401-2294-33690 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D01 | [9 empty] | D03 | IFA | T-1089 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-PCS-01-05107 | 44755 | 1401/04/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D02 | [9 empty] | D04 | IFA | T-1309 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D03 | [5 empty] | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D03
3 | 2 | 3 | 1 | 7 | 0 | 22 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0020 | P&ID - LP Flare System |  | BK-GCS-PEDCO-120-PR-PI-0020 | BK-GCS-PEDCO-120-PR-PI-0020 | BK | GCS | PEDCO | 120 | PR | PI | 0020 | F2A-708798 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-10 | 27 | -18 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-10 | 2022-10-25 | 2022-10-26 | 45 | 1 | 46 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-18 |  |  | D04 | IFA | T-1314 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05731 | 44824 | 1401/06/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-280775 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | CM |  | 1400-2290-294882 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0419 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D00 | [5 empty] | 1400-2294-402839 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 44655 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D01 | [5 empty] | 1401-2294-33690 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D01 | [9 empty] | D03 | IFA | T-1089 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-PCS-01-05107 | 44755 | 1401/04/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D02 | [9 empty] | D04 | IFA | T-1314 | 44800 | 1401/06/05 |  |  |  | BK-SUR-ENG-PCS-01-05731 | 44824 | 1401/06/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D03 | [5 empty] | 1401-2294-280775 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D03
3 | 2 | 3 | 1 | 7 | 0 | 23 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0021 | P&ID - Oily Water Sewer |  | BK-GCS-PEDCO-120-PR-PI-0021 | BK-GCS-PEDCO-120-PR-PI-0021 | BK | GCS | PEDCO | 120 | PR | PI | 0021 | F2A-708799 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-11-01 | 52 | 3 | 55 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-18 |  |  | D04 | IFA | T-1309 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0419 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D00 | [5 empty] | 1400-2294-402839 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 44655 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D01 | [5 empty] | 1401-2294-33690 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D01 | [9 empty] | D03 | IFA | T-1089 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-PCS-01-05107 | 44755 | 1401/04/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D02 | [9 empty] | D04 | IFA | T-1309 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D03 | [5 empty] | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D03
3 | 2 | 3 | 1 | 7 | 0 | 24 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0022 | P&ID - Fuel Gas System |  | BK-GCS-PEDCO-120-PR-PI-0022 | BK-GCS-PEDCO-120-PR-PI-0022 | BK | GCS | PEDCO | 120 | PR | PI | 0022 | F2A-708800 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-11-01 | 52 | 3 | 55 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-18 |  |  | D04 | IFA | T-1309 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0419 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D00 | [5 empty] | 1400-2294-402839 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 44655 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D01 | [5 empty] | 1401-2294-33690 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D01 | [9 empty] | D03 | IFA | T-1089 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-PCS-01-05107 | 44755 | 1401/04/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D02 | [9 empty] | D04 | IFA | T-1309 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D03 | [5 empty] | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D03
3 | 2 | 3 | 1 | 7 | 0 | 25 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0023 | P&ID - Diesel Oil System |  | BK-GCS-PEDCO-120-PR-PI-0023 | BK-GCS-PEDCO-120-PR-PI-0023 | BK | GCS | PEDCO | 120 | PR | PI | 0023 | F2A-708801 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-10 | 27 | -18 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-11-01 | 52 | 3 | 55 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-18 |  |  | D04 | IFA | T-1309 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | CM |  | 1400-2290-294882 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0419 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D00 | [5 empty] | 1400-2294-402839 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 44655 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D01 | [5 empty] | 1401-2294-33690 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D01 | [9 empty] | D03 | IFA | T-1089 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-PCS-01-05107 | 44755 | 1401/04/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D02 | [9 empty] | D04 | IFA | T-1309 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D03 | [5 empty] | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D03
3 | 2 | 3 | 1 | 7 | 0 | 26 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0024 | P&ID - Potable Water System |  | BK-GCS-PEDCO-120-PR-PI-0024 | BK-GCS-PEDCO-120-PR-PI-0024 | BK | GCS | PEDCO | 120 | PR | PI | 0024 | F2A-708802 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-11-01 | 52 | 3 | 55 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-18 |  |  | D04 | IFA | T-1309 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 44507 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 44510 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0419 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D00 | [5 empty] | 1400-2294-402839 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 44655 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D01 | [5 empty] | 1401-2294-33690 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D01 | [9 empty] | D03 | IFA | T-1089 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-PCS-01-05107 | 44755 | 1401/04/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D02 | [9 empty] | D04 | IFA | T-1309 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D03 | [5 empty] | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D03
3 | 2 | 3 | 1 | 7 | 0 | 27 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-PI-0025 | P&ID - Glycol Sump Drum |  | BK-GCS-PEDCO-120-PR-PI-0025 | BK-GCS-PEDCO-120-PR-PI-0025 | BK | GCS | PEDCO | 120 | PR | PI | 0025 | F2A-708803 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | IFA | 2022-07-03 | 2022-08-14 | 2022-08-16 | 42 | 2 | 44 | IFA | 2022-09-07 | 2022-10-29 | 2022-11-01 | 52 | 3 | 55 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-26 |  |  | D04 | IFA | T-1309 | 44797 | 1401/06/02 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 44492 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/27 | 44495 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0419 | 44564 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 44583 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D00 | [5 empty] | 1400-2294-402839 | 44600 | 1400/11/19 | 44604 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D00 | 1400-2294-438936 | 44627 | 1400/12/16 | 44629 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 44655 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D01 | [5 empty] | 1401-2294-33690 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D01 | [9 empty] | D03 | IFA | T-1089 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-PCS-01-05107 | 44755 | 1401/04/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D02 | [5 empty] | 1401-2294-176998 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D02 | [9 empty] | D04 | IFA | T-1309 | 44797 | 1401/06/02 |  |  |  | BK-SUR-ENG-PCS-01-05610 | 44813 | 1401/06/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D03 | [5 empty] | 1401-2294-285752 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D03
3 | 2 | 3 | 1 | 7 | 0 | 28 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-BD-0001 | ESD Block Diagram |  | BK-GCS-PEDCO-120-PR-BD-0001 | BK-GCS-PEDCO-120-PR-BD-0001 | BK | GCS | PEDCO | 120 | PR | BD | 0001 | F2J-708804 | AFC | IFC | 2022-06-25 | 2022-10-10 | 2022-10-12 | 107 | 2 | 109 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-11 |  |  | D00 | IFC | T-1053 | 44723 | 1401/03/21 | T-1053 | 44723 | 1401/03/21 | BK-SUR-ENG-PCS-01-04989 | 44747 | 1401/04/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255985 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1053 | 2022-06-11 | 1401/03/21 | T-1053 | 44723 | 1401/03/21 | BK-SUR-ENG-PCS-01-04989 | 44747 | 1401/04/14 | CM-C3 | [6 empty] | 1401-2294-255985 | 2022-10-10 | 1401/07/18 | 44846 | 1401/07/20 | CM
3 | 2 | 3 | 1 | 7 | 0 | 29 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-CE-0001 | Cause & Effect Diagram |  | BK-GCS-PEDCO-120-PR-CE-0001 | BK-GCS-PEDCO-120-PR-CE-0001 | BK | GCS | PEDCO | 120 | PR | CE | 0001 | F0Z-708805 | AFC | IFC | 2022-06-13 | 2022-06-22 | 2022-06-22 | 9 | 0 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-30 |  |  | D00 | IFC | T-1022 | 44711 | 1401/03/09 | T-1022 | 44711 | 1401/03/09 | BK-SUR-ENG-PCS-01-04825 | 44723 | 1401/04/01 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-109262 | 44734 | 1401/03/30 | 44734 | 1401/04/01 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1022 | 2022-05-30 | 1401/03/09 | T-1022 | 44711 | 1401/03/09 | BK-SUR-ENG-PCS-01-04825 | 44723 | 1401/04/01 | CM-C3 | [6 empty] | 1401-2294-109262 | 2022-06-22 | 1401/03/30 | 44734 | 1401/04/01 | CM
3 | 2 | 3 | 1 | 7 | 0 | 30 | 3.2.3.1.7 | BK-GCS-PEDCO-120-PR-DG-0001 | Chemical Injection Points Diagram |  | BK-GCS-PEDCO-120-PR-DG-0001 | BK-GCS-PEDCO-120-PR-DG-0001 | BK | GCS | PEDCO | 120 | PR | DG | 0001 | F2A-708806 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 1 | 8 | 0 | 0 | 3.2.3.1.8 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 8 | 0 | 1 | 3.2.3.1.8 | BK-GCS-PEDCO-120-PR-LI-0001 | Process Main Equipment List |  | BK-GCS-PEDCO-120-PR-LI-0001 | BK-GCS-PEDCO-120-PR-LI-0001 | BK | GCS | PEDCO | 120 | PR | LI | 0001 | F0Z-708807 | AFC | IFC | 2022-03-06 | 2022-03-13 | 2022-04-01 | 7 | 19 | 26 | IFA | 2022-06-05 | 2022-06-15 | 2022-06-20 | 10 | 5 | 15 | IFA | 2022-09-25 | 2022-10-29 | 2022-11-01 | 34 | 3 | 37 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-20 |  |  | D02 | IFA | T-1382 | 44815 | 1401/06/20 | T-1382 | 44815 | 1401/06/20 | BK-SUR-ENG-PCS-01-05778 | 44835 | 1401/07/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255978 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D01 | 1401-2294-285786 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 44635 | 1400/12/24 | CM |  | 1400-2294-447187 | 44633 | 1400/12/22 | 44652 | 1401/01/14 | CM |  |  |  | D01 | IFA | T-0990 | 44703 | 1401/03/01 | T-0990 | 44704 | 1401/03/02 | BK-SUR-ENG-PCS-01-04737 | 44730 | 1401/03/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D00 | [5 empty] | 1401-2294-104506 | 44727 | 1401/03/25 | 44732 | 1401/03/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-1382 | 44815 | 1401/06/20 | T-1382 | 44815 | 1401/06/20 | BK-SUR-ENG-PCS-01-05778 | 44835 | 1401/07/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D01 | [5 empty] | 1401-2294-255978 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D01 | 1401-2294-285786 | 44863 | 1401/08/07 | 44866 | 1401/08/10 | CM
3 | 2 | 3 | 1 | 8 | 0 | 2 | 3.2.3.1.8 | BK-GCS-PEDCO-120-PR-LI-0002 | Process Electrical Load List |  | BK-GCS-PEDCO-120-PR-LI-0002 | BK-GCS-PEDCO-120-PR-LI-0002 | BK | GCS | PEDCO | 120 | PR | LI | 0002 | F0Z-708808 | AFC | IFC | 2022-02-02 | 2022-03-10 | 2022-03-12 | 36 | 2 | 38 | IFA | 2022-03-27 | 2022-05-04 | 2022-05-08 | 38 | 4 | 42 | IFA | 2022-08-31 | 2022-10-25 | 2022-10-30 | 55 | 5 | 60 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-19 |  |  | D02 | IFA | T-1283 | 44790 | 1401/05/26 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05604 | 44809 | 1401/06/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0002-D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-281110 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0482 | 2022-01-19 | 1400/10/29 |  |  |  | BK-SUR-ENG-PCS-00-03080 | 44608 | 1400/11/27 | CM-C3 | [6 empty] | 1400-2294-412902 | 2022-02-16 | 1400/11/27 | 44614 | 1400/12/03 | CM |  | 1400-2294-443212 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | CM |  |  |  | D01 | IFA | T-0723 | 44633 | 1400/12/21 |  |  |  | BK-SUR-ENG-PCS-01-03876 | 44663 | 1401/01/23 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0002_D00 | [5 empty] | 1401-2294-48128 | 44685 | 1401/02/14 | 44689 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0002_D00 | [9 empty] | D02 | IFA | T-1283 | 44790 | 1401/05/26 |  |  |  | BK-SUR-ENG-PCS-01-05604 | 44809 | 1401/06/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0002-D01 | [5 empty] | 1401-2294-281110 | 44859 | 1401/08/03 | 44864 | 1401/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0002_D01
3 | 2 | 3 | 1 | 8 | 0 | 3 | 3.2.3.1.8 | BK-GCS-PEDCO-120-PR-LI-0003 | Tie in list |  | BK-GCS-PEDCO-120-PR-LI-0003 | BK-GCS-PEDCO-120-PR-LI-0003 | BK | GCS | PEDCO | 120 | PR | LI | 0003 | F0Z-708809 | AFC | IFC | 2022-03-06 | 2022-03-12 | 2022-03-15 | 6 | 3 | 9 | IFA | 2022-06-05 | 2022-06-15 | 2022-06-20 | 10 | 5 | 15 | IFA | 2022-08-31 | 2022-08-03 | 0 | -28 | -44776 | -44804 | IFA | 2022-11-06 | 0 | 0 | -44871 | 0 | -44871 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-20 |  |  | D03 | IFA | T-1535 | 44857 | 1401/08/01 | T-1535 | 44857 | 1401/08/01 | BK-SUR-ENG-PCS-01-06112 | 44872 | 1401/08/16 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 44635 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0990 | 44703 | 1401/03/01 | T-0990 | 44704 | 1401/03/02 | BK-SUR-ENG-PCS-01-04737 | 44730 | 1401/03/28 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D00 | [5 empty] | 1401-2294-104506 | 44727 | 1401/03/25 | 44732 | 1401/03/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D00 | [9 empty] | D02 | IFA | T-1283 | 44790 | 1401/05/26 |  |  |  | BK-SUR-ENG-PCS-01-05604 | 44809 | 1401/06/14 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D01 | [5 empty] | Comment Sheets\NISOC\صورتجلسه 14010609 - جانمایی دیزل و نهایی سازی نقاط اتصال ایستگاه.pdf | 44776 | 1401/06/12 | 3-AYG-2022 | 1401/06/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D01 | [9 empty] | D03 | IFA | T-1535 | 44857 | 1401/08/01 | T-1535 | 44857 | 1401/08/01 | BK-SUR-ENG-PCS-01-06112 | 44872 | 1401/08/16 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D02
3 | 2 | 3 | 1 | 8 | 0 | 4 | 3.2.3.1.8 | BK-GCS-PEDCO-120-PR-LI-0004 | Line List |  | BK-GCS-PEDCO-120-PR-LI-0004 | BK-GCS-PEDCO-120-PR-LI-0004 | BK | GCS | PEDCO | 120 | PR | LI | 0004 | F0Z-708810 | AFC | IFC | 2022-05-14 | 2022-05-31 | 2022-06-06 | 17 | 6 | 23 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-30 |  |  | D00 | IFC | T-0876 | 44681 | 1401/02/10 | T-0876 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04370 | 44703 | 1401/03/01 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-83263 | 44712 | 1401/03/10 | 44718 | 1401/03/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0876 | 2022-04-30 | 1401/02/10 | T-0876 | 44681 | 1401/02/10 | BK-SUR-ENG-PCS-01-04370 | 44703 | 1401/03/01 | CM-C3 | [6 empty] | 1401-2294-83263 | 2022-05-31 | 1401/03/10 | 44718 | 1401/03/16 | CM
3 | 2 | 3 | 1 | 8 | 0 | 5 | 3.2.3.1.8 | BK-GCS-PEDCO-120-PR-LI-0005 | Chemical Consumption List |  | BK-GCS-PEDCO-120-PR-LI-0005 | BK-GCS-PEDCO-120-PR-LI-0005 | BK | GCS | PEDCO | 120 | PR | LI | 0005 | F0Z-708811 | AFC | IFC | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | IFA | 2022-09-20 | 2022-11-19 | 2022-11-21 | 60 | 2 | 62 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-09 |  |  | D01 | IFA | T-1368 | 44810 | 1401/06/15 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0703 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03869 | 44664 | 1401/01/23 | CM-C3 | [6 empty] | 1401-2294-43236 | 2022-04-29 | 1401/02/09 | 44682 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-1368 | 44810 | 1401/06/15 |  |  |  | BK-SUR-ENG-PCS-01-05762 | 44828 | 1401/07/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0005_D00 | [5 empty] | 1401-2294-318022 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0005_D00
3 | 2 | 3 | 1 | 8 | 0 | 6 | 3.2.3.1.8 | BK-GCS-PEDCO-120-PR-LI-0006 | Utility Consumption List |  | BK-GCS-PEDCO-120-PR-LI-0006 | BK-GCS-PEDCO-120-PR-LI-0006 | BK | GCS | PEDCO | 120 | PR | LI | 0006 | F0Z-708812 | AFC | IFC | 2022-01-11 | 2022-01-16 | 2022-01-23 | 5 | 7 | 12 | IFA | 2022-03-23 | 2022-04-22 | 2022-04-30 | 30 | 8 | 38 | IFA | 2022-09-27 | 0 | 0 | -44831 | 0 | -44831 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-28 |  |  | D02 | IFA | T-1400 | 44817 | 1401/06/22 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-05872 | 44844 | 1401/07/18 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0396 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02645 | 44572 | 1400/10/22 | CM-C3 | [6 empty] | 1400-2294-366632 | 2022-01-16 | 1400/10/26 | 44584 | 1400/11/03 | CM | [10 empty] | D01 | IFA | T-0702 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03818 | 44660 | 1401/01/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D00 | [5 empty] | 1401-2294-33758 | 44673 | 1401/02/02 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D00 | [9 empty] | D02 | IFA | T-1400 | 44817 | 1401/06/22 |  |  |  | BK-SUR-ENG-PCS-01-05872 | 44844 | 1401/07/18 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D01
3 | 2 | 3 | 1 | 8 | 0 | 7 | 3.2.3.1.8 | BK-GCS-PEDCO-120-PR-LI-0007 | Emission and Effluent Summary |  | BK-GCS-PEDCO-120-PR-LI-0007 | BK-GCS-PEDCO-120-PR-LI-0007 | BK | GCS | PEDCO | 120 | PR | LI | 0007 | F0Z-708813 | AFC | IFC | 2022-06-26 | 2022-07-21 | 2022-07-24 | 25 | 3 | 28 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-12 |  |  | D00 | IFC | T-1068 | 44724 | 1401/03/21 | T-1068 | 44724 | 1401/03/22 | BK-SUR-ENG-PCS-01-05011 | 44748 | 1401/04/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-146657 | 44763 | 1401/04/30 | 44766 | 1401/05/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1068 | 2022-06-12 | 1401/03/21 | T-1068 | 44724 | 1401/03/22 | BK-SUR-ENG-PCS-01-05011 | 44748 | 1401/04/15 | CM-C3 | [6 empty] | 1401-2294-146657 | 2022-07-21 | 1401/04/30 | 44766 | 1401/05/02 | CM
3 | 2 | 3 | 1 | 8 | 0 | 8 | 3.2.3.1.8 | BK-GCS-PEDCO-120-PR-LI-0008 | Relief Load Summery |  | BK-GCS-PEDCO-120-PR-LI-0008 | BK-GCS-PEDCO-120-PR-LI-0008 | BK | GCS | PEDCO | 120 | PR | LI | 0008 | F0Z-708814 | AFC | IFC | 2022-02-09 | 2022-02-26 | 2022-02-21 | 17 | -5 | 12 | IFA | 2022-05-23 | 2022-06-02 | 2022-06-06 | 10 | 4 | 14 | IFA | 2022-10-22 | 0 | 0 | -44856 | 0 | -44856 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-26 |  |  | D02 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0513 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-PCS-00-03135 | 44612 | 1400/12/01 | CM-C3 | [6 empty] | 1400-2294-419565 | 2022-02-26 | 1400/12/07 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0917 | 44690 | 1401/02/19 | T-0917 | 44690 | 1401/02/19 | BK-SUR-ENG-PCS-01-04505 | 44712 | 1401/03/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D00 | [5 empty] | 1401-2294-87490 | 44714 | 1401/03/12 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D00 | [9 empty] | D02 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D01
3 | 2 | 3 | 1 | 9 | 0 | 0 | 3.2.3.1.9 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 1 | 9 | 0 | 1 | 3.2.3.1 | BK-GCS-PEDCO-120-PR-RT-0001 | Flare Network Study Report |  | BK-GCS-PEDCO-120-PR-RT-0001 | BK-GCS-PEDCO-120-PR-RT-0001 | BK | GCS | PEDCO | 120 | PR | RT | 0001 | F0Z-708815 | IFI | IFC | 2022-01-19 | 2022-02-12 | 2022-02-22 | 24 | 10 | 34 | IFA | 2022-07-05 | 2022-09-11 | 2022-09-13 | 68 | 2 | 70 | IFA | 2022-10-22 | 0 | 0 | -44856 | 0 | -44856 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-05 |  |  | D02 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0434 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-PCS-00-02801 | 44585 | 1400/11/04 | CM-C3 | [6 empty] | 1400-2294-405516 | 2022-02-12 | 1400/11/23 | 44614 | 1400/12/03 | CM | [10 empty] | D01 | IFA | T-1101 | 44733 | 1401/03/31 | T-1101 | 44733 | 1401/03/31 | BK-SUR-ENG-PCS-01-05191 | 44761 | 1401/04/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0001_D00 | [5 empty] | 1401-2294-218931 | 44815 | 1401/06/20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0001_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0001_D01
3 | 2 | 3 | 1 | 9 | 0 | 2 | 3.2.3.1 | BK-GCS-PEDCO-120-PR-RT-0002 | Flare Radiation & Dispersion Study Report |  | BK-GCS-PEDCO-120-PR-RT-0002 | BK-GCS-PEDCO-120-PR-RT-0002 | BK | GCS | PEDCO | 120 | PR | RT | 0002 | F0Z-708816 | IFI | IFC | 2022-01-19 | 2022-02-12 | 2022-02-22 | 24 | 10 | 34 | IFA | 2022-07-05 | 2022-09-11 | 2022-09-13 | 68 | 2 | 70 | IFA | 2022-10-22 | 0 | 0 | -44856 | 0 | -44856 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-05 |  |  | D02 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0431 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-PCS-00-02802 | 44585 | 1400/11/04 | CM-C3 | [6 empty] | 1400-2294-405516 | 2022-02-12 | 1400/11/23 | 44614 | 1400/12/03 | CM | [10 empty] | D01 | IFA | T-1101 | 44733 | 1401/03/31 | T-1101 | 44733 | 1401/03/31 | BK-SUR-ENG-PCS-01-05191 | 44761 | 1401/04/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0002_D00 | [5 empty] | 1401-2294-218931 | 44815 | 1401/06/20 | 44817 | 1401/06/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0002_D00 | [9 empty] | D02 | IFA | T-1461 | 44842 | 1401/07/16 | T-1461 | 44842 | 1401/07/16 | BK-SUR-ENG-PCS-01-06006 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0002_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0002_D01
3 | 2 | 3 | 1 | 9 | 0 | 3 | 3.2.3.1 | BK-GCS-PEDCO-120-PR-RT-0003 | Process Simulation Report |  | BK-GCS-PEDCO-120-PR-RT-0003 | BK-GCS-PEDCO-120-PR-RT-0003 | BK | GCS | PEDCO | 120 | PR | RT | 0003 | F0Z-708817 | IFI | IFC | 2021-10-31 | 2021-11-28 | 2021-11-14 | 28 | -14 | 14 | IFA | 2021-12-14 | 2021-12-30 | 2022-01-02 | 16 | 3 | 19 | IFA | 2022-01-22 | 2022-02-12 | 2022-02-22 | 21 | 10 | 31 | IFA | 2022-03-22 | 2022-04-21 | 2022-04-30 | 30 | 9 | 39 | IFA | 2022-08-17 | 2022-09-19 | 2022-09-19 | 33 | 0 | 33 | AFD | 2022-10-15 | 2022-11-19 | 2022-11-21 | 35 | 2 | 37 | [7 empty] | Modify | 2021-10-17 | 2022-10-01 |  | D05 | AFD | T-1447 | 44835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D04 | 0 | 0 | 0 | 0 | 0 | 1401-2294-318040 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0162 | 2021-10-17 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01937 | 44507 | 1400/08/16 | CM-C2 | [6 empty] | 1400-2294-270371 | 2021-11-10 | 1400/08/19 | 44514 | 1400/08/23 | CM |  | 1400-2290-294976 | 44528 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0285 | 44530 | 1400/09/09 |  |  |  | BK-SUR-ENG-PCS-00-02363 | 44549 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D00 | [5 empty] | 1400-2294-342083 | 44560 | 1400/10/09 | 44563 | 1400/10/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D00 | [9 empty] | D02 | IFA | T-0437 | 44569 | 1400/10/18 |  |  |  | BK-SUR-ENG-PCS-00-02784 | 44584 | 1400/11/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D01 | [5 empty] | 1400-2294-405260 | 44604 | 1400/11/23 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D01 | [9 empty] | D03 | IFA | T-0700 | 44628 | 1400/12/17 |  |  |  | BK-SUR-ENG-PCS-01-03783 | 44660 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D02 | [5 empty] | 1401-2294-33692 | 44670 | 1401/02/01 | 44681 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D02 | 1401-2294-33692 | 44672 | 1401/02/01 | 44681 | 1401/02/10 | CM |  |  |  | D04 | IFA | T-1247 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-PCS-01-05480 | 44793 | 1401/05/29 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D03 | [5 empty] | 1401-2294-226271 | 44823 | 1401/06/27 | 44823 | 1401/06/28 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0003 _D03 | [9 empty] | D05 | AFD | T-1447 | 44835 | [8 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D04 | [5 empty] | 1401-2294-318040 | 44884 | 1401/08/28 | 44886 | 1401/08/30 | AP
3 | 2 | 3 | 2 | 0 | 0 | 0 | 3.2.3.2 |  | Mechanical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 2 | 1 | 0 | 0 | 3.2.3.2.1 |  | Specification | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 2 | 1 | 1 | 0 | 3.2.2.1.1 |  | Fixed Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 2 | 1 | 1 | 1 | 3.2.3.2.1.1.1 | BK-GCS-PEDCO-120-ME-SP-0001 | Specification For Air Cooled Heat Exchangers |  | BK-GCS-PEDCO-120-ME-SP-0001 | BK-GCS-PEDCO-120-ME-SP-0001 | BK | GCS | PEDCO | 120 | ME | SP | 0001 | F0Z-708818 | AFD | IFC | 2021-08-28 | 0 | 0 | -44436 | 0 | -44436 | AFD | 2022-10-25 | 0 | 0 | -44859 | 0 | -44859 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-14 | 2022-10-11 |  | D01 | AFD | T-1481 | 44845 | 1401/07/19 | T-1481 | 44845 | 1401/07/19 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 44445 | 1400/06/15 | CM-C3 | [22 empty] | D01 | AFD | T-1481 | 44845 | 1401/07/19 | T-1481 | 44845 | 1401/07/19 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0001_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0001_D00
3 | 2 | 3 | 2 | 1 | 1 | 2 | 3.2.3.2.1.1.2 | BK-GCS-PEDCO-120-ME-SP-0010 | Specification For Large Welded Low Pressure Storage Tanks |  | BK-GCS-PEDCO-120-ME-SP-0010 | BK-GCS-PEDCO-120-ME-SP-0010 | BK | GCS | PEDCO | 120 | ME | SP | 0010 | F0Z-708819 | AFD | IFC | 2021-09-07 | 2021-09-15 | 2021-09-26 | 8 | 11 | 19 | IFA | 2021-10-18 | 2021-10-20 | 2021-10-25 | 2 | 5 | 7 | IFA | 2021-11-13 | 2021-11-03 | 2021-11-08 | -10 | 5 | -5 | IFA | 2021-11-24 | 2021-11-18 | 2021-11-24 | -6 | 6 | 0 | AFD | 2022-02-14 | 2022-03-13 | 2022-03-26 | 27 | 13 | 40 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-24 | 2022-01-31 |  | D04 | AFD | T-0528 | 44592 | 1400/11/11 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02920 | 44594 | 1400/11/13 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-447211 | 44633 | 1400/12/22 | 44646 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-200596 | 2021-09-15 | 1400/06/24 | 44465 | 1400/07/04 | CM | [10 empty] | D01 | IFA | T-0133 | 44473 | 1400/07/12 |  |  |  | BK-SUR-ENG-FXE-00-01832 | 44494 | 1400/08/03 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0010-D00 | [5 empty] | 1400-2294-243550 | 44489 | 1400/07/28 | 44494 | 1400/08/03 | CM | NISOC-CRS-BK-GCS-NISOC-120-ME-SP-0010-D00 | [9 empty] | D02 | IFA | T-0196 | 44499 | 1400/08/08 |  |  |  | BK-SUR-ENG-MEC-00-02126 | 44528 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2294-260986 | 44503 | 1400/08/12 | 44508 | 1400/08/17 | CM | NISOC-CRS-BK-GCS-NISOC-120-ME-SP-0010-D01 | [9 empty] | D03 | IFA | T-0231 | 44510 | 1400/08/19 | [13 empty] | 1400-2294-281393 | 44518 | 1400/08/27 | 44524 | 1400/09/03 | AP | NISOC-CRS-BK-GCS-NISOC-120-ME-SP-0010_D02 | [9 empty] | D04 | AFD | T-0528 | 44592 | 1400/11/11 |  |  |  | BK-SUR-ENG-MEC-00-02920 | 44594 | 1400/11/13 | AP | [6 empty] | 1400-2294-447211 | 44633 | 1400/12/22 | 44646 | 1401/01/09 | AP
3 | 2 | 3 | 2 | 1 | 2 | 0 | 3.2.2.1.2 |  | Rotary Equipment
3 | 2 | 3 | 2 | 1 | 2 | 1 | 3.2.3.2.1.2.1 | BK-GCS-PEDCO-120-ME-SP-0002 | Specification For Reciprocating Compressor (API 618) |  | BK-GCS-PEDCO-120-ME-SP-0002 | BK-GCS-PEDCO-120-ME-SP-0002 | BK | GCS | PEDCO | 120 | ME | SP | 0002 | F0Z-708820 | AFD | IFC | 2021-08-28 | 2021-08-31 | 0 | 3 | -44439 | -44436 | IFA | 2021-10-18 | 2021-11-02 | 2021-11-07 | 15 | 5 | 20 | IFA | 2021-11-28 | 2021-12-13 | 2021-12-18 | 15 | 5 | 20 | IFA | 2022-01-12 | 2022-01-20 | 2022-01-24 | 8 | 4 | 12 | IFA | 2022-02-12 | 2022-02-26 | 2022-03-02 | 14 | 4 | 18 | AFD | 2022-03-21 | 0 | 0 | -44641 | 0 | -44641 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-14 | 2022-03-07 |  | D05 | AFD | T-0690 | 44627 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03453 | 44632 | 1400/12/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 44445 | 1400/06/15 | CM-C3 | [6 empty] | 1400/2294/181003 | 2021-08-31 | 1400/06/09 |  |  | CM | [10 empty] | D01 | IFA | T-0135 | 44473 | 1400/07/12 |  |  |  | BK-SUR-ENG-ROE-00-01844 | 44495 | 1400/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0002_D00 | [5 empty] | 1400-2294-259326 | 44502 | 1400/08/11 | 44507 | 1400/08/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0002_D00 | [9 empty] | D02 | IFA | T-0232 | 44514 | 1400/08/23 |  |  |  | BK-SUR-ENG-MEC-00-02102 | 44527 | 1400/09/06 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0002-D01 | [5 empty] | 1400-2294-316960 | 44543 | 1400/09/22 | 44548 | 1400/09/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0002-D01 | [9 empty] | D03 | IFA | T-0400 | 44559 | 1400/10/08 | [13 empty] | 1400-2294-372899 | 44581 | 1400/10/30 | 44585 | 1400/11/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0002_D02 | [9 empty] | D04 | IFA | T-0518 | 44590 | 1400/11/09 | [13 empty] | 1400-2294-426614 | 44618 | 1400/12/07 | 44622 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0002_D03 | [9 empty] | D05 | AFD | T-0690 | 44627 | 1400/12/16 |  |  |  | BK-SUR-ENG-MEC-00-03453 | 44632 | 1400/12/21 | CM-C3
3 | 2 | 3 | 2 | 1 | 2 | 2 | 3.2.3.2.1.2.2 | BK-GCS-PEDCO-120-ME-SP-0003 | Specification For Centrifugal Pumps For Process Services (API610) |  | BK-GCS-PEDCO-120-ME-SP-0003 | BK-GCS-PEDCO-120-ME-SP-0003 | BK | GCS | PEDCO | 120 | ME | SP | 0003 | F0Z-708821 | AFD | IFC | 2021-09-05 | 2021-08-31 | 2021-09-12 | -5 | 12 | 7 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-01-25 | 2022-02-26 | 2022-03-02 | 32 | 4 | 36 | IFA | 2022-03-20 | 2022-04-12 | 2022-04-18 | 23 | 6 | 29 | AFD | 2022-05-03 | 2022-04-28 | 2022-05-01 | -5 | 3 | -2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 | 2022-04-19 |  | D04 | AFD | T-0841 | 44670 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05919 | 44852 | 1401/07/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42947 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0053 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-ROE-00-01493 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400/2294/181002 | 2021-08-31 | 1400/06/09 | 44451 | 1400/06/21 | AP | [10 empty] | D01 | IFA | T-0138 | 44475 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 44499 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0003-D00 | [5 empty] | 1400-2294-257419 | 44559 | 1400/10/10 | 44499 | 1400/08/08 | CM | [10 empty] | D02 | IFA | T-0447 | 44572 | 1400/10/20 |  |  |  | BK-SUR-ENG-MEC-00-02798 | 44585 | 1400/11/04 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0003_D01 | [5 empty] | 1400-2294-426688 | 44618 | 1400/12/07 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0003_D01 | [9 empty] | D03 | IFA | T-0681 | 44626 | 1400/12/15 | [13 empty] | 1401-2294-20728 | 44663 | 1401/01/23 | 44669 | 1401/01/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0003_D02 | [9 empty] | D04 | AFD | T-0841 | 44670 | 1401/01/30 |  |  |  | BK-SUR-ENG-MEC-01-05919 | 44852 | 1401/07/26 | AP | [6 empty] | 1401-2294-42947 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | AP
3 | 2 | 3 | 2 | 1 | 2 | 3 | 3.2.3.2.1.2.3 | BK-GCS-PEDCO-120-ME-SP-0004 | Specification For Centrifugal Pumps For General Services |  | BK-GCS-PEDCO-120-ME-SP-0004 | BK-GCS-PEDCO-120-ME-SP-0004 | BK | GCS | PEDCO | 120 | ME | SP | 0004 | F0Z-708822 | AFD | IFC | 2021-08-28 | 2021-08-31 | 0 | 3 | -44439 | -44436 | IFA | 2021-10-18 | 2021-11-02 | 2021-11-07 | 15 | 5 | 20 | IFA | 2021-11-28 | 2021-12-13 | 2021-12-18 | 15 | 5 | 20 | AFD | 2022-08-29 | 2022-08-18 | 2022-08-14 | -11 | -4 | -15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-14 | 2022-08-15 |  | D03 | AFD | T-1274 | 44788 | 1401/05/23 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05920 | 44852 | 1401/07/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183560 | 44791 | 1401/05/27 | 44787 | 1401/06/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 44445 | 1400/06/15 | CM-C3 | [6 empty] | 1400/2294/181003 | 2021-08-31 | 1400/06/09 |  |  | CM | [10 empty] | D01 | IFA | T-0135 | 44473 | 1400/07/12 |  |  |  | BK-SUR-ENG-ROE-00-01844 | 44495 | 1400/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0004_D00 | [5 empty] | 1400-2294-259326 | 44502 | 1400/08/11 | 44507 | 1400/08/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0004-D00 | [9 empty] | D02 | IFA | T-0232 | 44514 | 1400/08/23 |  |  |  | BK-SUR-ENG-MEC-00-02102 | 44527 | 1400/09/06 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0004_D01 | [5 empty] | 1400-2294-316960 | 44543 | 1400/09/23 | 44548 | 1400/09/27 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0004-D01 | [9 empty] | D03 | AFD | T-1274 | 44788 | 1401/05/23 |  |  |  | BK-SUR-ENG-MEC-01-05920 | 44852 | 1401/07/26 | AP | [6 empty] | 1401-2294-183560 | 44791 | 1401/05/27 | 44787 | 1401/06/02 | AP
3 | 2 | 3 | 2 | 1 | 2 | 4 | 3.2.3.2.1.2.4 | BK-GCS-PEDCO-120-ME-SP-0005 | Specification For Fire Water Pumps |  | BK-GCS-PEDCO-120-ME-SP-0005 | BK-GCS-PEDCO-120-ME-SP-0005 | BK | GCS | PEDCO | 120 | ME | SP | 0005 | F0Z-708823 | AFD | IFC | 2021-09-05 | 2021-08-31 | 2021-09-12 | -5 | 12 | 7 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-01-25 | 2022-02-26 | 2022-03-02 | 32 | 4 | 36 | IFA | 2022-03-20 | 2022-04-12 | 2022-04-18 | 23 | 6 | 29 | AFD | 2022-05-03 | 2022-04-28 | 2022-05-01 | -5 | 3 | -2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 | 2022-04-19 |  | D04 | AFD | T-0841 | 44670 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05919 | 44852 | 1401/07/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42947 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0053 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-ROE-00-01493 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400/2294/181002 | 2021-08-31 | 1400/06/09 | 44451 | 1400/06/21 | AP | [10 empty] | D01 | IFA | T-0138 | 44475 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 44499 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0005-D00 | [5 empty] | 1400-2294-257419 | 44559 | 1400/10/10 | 44499 | 1400/08/08 | CM | [10 empty] | D02 | IFA | T-0447 | 44572 | 1400/10/20 |  |  |  | BK-SUR-ENG-MEC-00-02798 | 44585 | 1400/11/04 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0005_D01 | [5 empty] | 1400-2294-426688 | 44618 | 1400/12/07 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0005_D01 | [9 empty] | D03 | IFA | T-0681 | 44626 | 1400/12/15 | [13 empty] | 1401-2294-20728 | 44663 | 1401/01/23 | 44669 | 1401/01/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0005_D02 | [9 empty] | D04 | AFD | T-0841 | 44670 | 1401/01/30 |  |  |  | BK-SUR-ENG-MEC-01-05919 | 44852 | 1401/07/26 | AP | [6 empty] | 1401-2294-42947 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | AP
3 | 2 | 3 | 2 | 1 | 2 | 5 | 3.2.3.2.1.2.5 | BK-GCS-PEDCO-120-ME-SP-0009 | Specification For Overhead Travelling Cranes |  | BK-GCS-PEDCO-120-ME-SP-0009 | BK-GCS-PEDCO-120-ME-SP-0009 | BK | GCS | PEDCO | 120 | ME | SP | 0009 | F0Z-708824 | AFD | IFC | 2021-08-28 | 0 | 0 | -44436 | 0 | -44436 | AFD | 2022-10-25 | 0 | 0 | -44859 | 0 | -44859 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-08-14 | 2022-10-11 |  | D01 | AFD | T-1481 | 44845 | 1401/07/19 | T-1481 | 44845 | 1401/07/19 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 44445 | 1400/06/15 | CM-C3 | [22 empty] | D01 | AFD | T-1481 | 44845 | 1401/07/19 | T-1481 | 44845 | 1401/07/19 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0009_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0009_D00
3 | 2 | 3 | 2 | 1 | 2 | 6 | 3.2.3.2.1.2.6 | BK-GCS-PEDCO-120-ME-SP-0011 | Specification for Control Volume Pump (API 675) |  | BK-GCS-PEDCO-120-ME-SP-0011 | BK-GCS-PEDCO-120-ME-SP-0011 | BK | GCS | PEDCO | 120 | ME | SP | 0011 | F0Z-708825 | AFD | IFC | 2021-09-07 | 2021-09-15 | 2021-09-26 | 8 | 11 | 19 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-01-25 | 2022-02-26 | 2022-03-02 | 32 | 4 | 36 | IFA | 2022-03-20 | 2022-04-12 | 2022-04-18 | 23 | 6 | 29 | AFD | 2022-05-03 | 2022-04-28 | 2022-05-01 | -5 | 3 | -2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-08-24 | 2022-04-19 |  | D04 | AFD | T-0841 | 44670 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05919 | 44852 | 1401/07/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42947 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-200596 | 2021-09-15 | 1400/06/24 | 44465 | 1400/07/04 | CM | [10 empty] | D01 | IFA | T-0138 | 44475 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 44499 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0011-D00 | [5 empty] | 1400-2294-257419 | 44559 | 1400/10/10 | 44499 | 1400/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0011-D00 | [9 empty] | D02 | IFA | T-0447 | 44572 | 1400/10/20 |  |  |  | BK-SUR-ENG-MEC-00-02798 | 44585 | 1400/11/04 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0011-D01 | [5 empty] | 1400-2294-426688 | 44618 | 1400/12/07 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0011_D01 | [9 empty] | D03 | IFA | T-0681 | 44626 | 1400/12/15 | [13 empty] | 1401-2294-20728 | 44663 | 1401/01/23 | 44669 | 1401/01/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0011_D02 | [9 empty] | D04 | AFD | T-0841 | 44670 | 1401/01/30 |  |  |  | BK-SUR-ENG-MEC-01-05919 | 44852 | 1401/07/26 | AP | [6 empty] | 1401-2294-42947 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | AP
3 | 2 | 3 | 2 | 1 | 2 | 7 | 3.2.3.2.1.2.7 | BK-GCS-PEDCO-120-ME-SP-0012 | Specification For Diesel Engines |  | BK-GCS-PEDCO-120-ME-SP-0012 | BK-GCS-PEDCO-120-ME-SP-0012 | BK | GCS | PEDCO | 120 | ME | SP | 0012 | F0Z-708826 | AFD | IFC | 2021-09-07 | 2021-09-15 | 2021-09-26 | 8 | 11 | 19 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-02-01 | 2022-02-05 | 2022-02-05 | 4 | 0 | 4 | AFD | 2022-03-20 | 2022-03-10 | 2022-03-12 | -10 | 2 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-24 | 2022-03-06 |  | D03 | AFD | T-0678 | 44626 | 1400/12/15 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03528 | 44633 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443202 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-200596 | 2021-09-15 | 1400/06/24 | 44465 | 1400/07/04 | CM | [10 empty] | D01 | IFA | T-0138 | 44475 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 44499 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0012-D00 | [5 empty] | 1400-2294-257419 | 44559 | 1400/10/08 | 44499 | 1400/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0012-D00 | [9 empty] | D02 | IFA | T-0477 | 44579 | 1400/10/28 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0012_D01 | [5 empty] | 1400-2294-397224 | 44597 | 1400/11/16 | 44597 | 1400/11/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0012_D01 | [9 empty] | D03 | AFD | T-0678 | 44626 | 1400/12/15 |  |  |  | BK-SUR-ENG-MEC-00-03528 | 44633 | 1400/12/22 | AP | [6 empty] | 1400-2294-443202 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | AP
3 | 2 | 3 | 2 | 1 | 3 | 0 | 3.2.2.1.3 |  | Packaged Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 2 | 1 | 3 | 1 | 3.2.3.2.1.3.1 | BK-GCS-PEDCO-120-ME-SP-0006 | Specification For Air Compressor Package |  | BK-GCS-PEDCO-120-ME-SP-0006 | BK-GCS-PEDCO-120-ME-SP-0006 | BK | GCS | PEDCO | 120 | ME | SP | 0006 | F0Z-708827 | AFD | IFC | 2021-08-28 | 2021-08-31 | 0 | 3 | -44439 | -44436 | IFA | 2021-10-18 | 2021-11-02 | 2021-11-07 | 15 | 5 | 20 | IFA | 2021-11-28 | 2021-12-13 | 2021-12-18 | 15 | 5 | 20 | IFA | 2022-01-12 | 2022-01-20 | 2022-01-24 | 8 | 4 | 12 | IFA | 2022-02-12 | 2022-02-26 | 2022-03-02 | 14 | 4 | 18 | AFD | 2022-03-21 | 0 | 0 | -44641 | 0 | -44641 | [8 empty] | 2021-08-14 | 2022-03-07 |  | D05 | AFD | T-0690 | 44627 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03453 | 44632 | 1400/12/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 44445 | 1400/06/15 | CM-C3 | [6 empty] | 1400/2294/181003 | 2021-08-31 | 1400/06/09 |  |  | CM | [10 empty] | D01 | IFA | T-0135 | 44473 | 1400/07/12 |  |  |  | BK-SUR-ENG-ROE-00-01844 | 44495 | 1400/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D00 | [5 empty] | 1400-2294-259326 | 44502 | 1400/08/11 | 44507 | 1400/08/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D00 | [9 empty] | D02 | IFA | T-0232 | 44514 | 1400/08/23 |  |  |  | BK-SUR-ENG-MEC-00-02102 | 44527 | 1400/09/06 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D01 | [5 empty] | 1400-2294-316960 | 44543 | 1400/09/22 | 44548 | 1400/09/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0006-D01 | [9 empty] | D03 | IFA | T-0400 | 44559 | 1400/10/08 | [13 empty] | 1400-2294-372899 | 44581 | 1400/10/30 | 44585 | 1400/11/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D02 | [9 empty] | D04 | IFA | T-0518 | 44590 | 1400/11/09 | [13 empty] | 1400-2294-426614 | 44618 | 1400/12/07 | 44622 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D03 | [9 empty] | D05 | AFD | T-0690 | 44627 | 1400/12/16 |  |  |  | BK-SUR-ENG-MEC-00-03453 | 44632 | 1400/12/21 | CM-C3
3 | 2 | 3 | 2 | 1 | 3 | 2 | 3.2.3.2.1.3.2 | BK-GCS-PEDCO-120-ME-SP-0007 | Specification For Air Dryer Package |  | BK-GCS-PEDCO-120-ME-SP-0007 | BK-GCS-PEDCO-120-ME-SP-0007 | BK | GCS | PEDCO | 120 | ME | SP | 0007 | F0Z-708828 | AFD | IFC | 2021-08-28 | 0 | 0 | -44436 | 0 | -44436 | AFD | 2022-10-25 | 0 | 0 | -44859 | 0 | -44859 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-14 | 2022-10-11 |  | D01 | AFD | T-1481 | 44845 | 1401/07/19 | T-1481 | 44845 | 1401/07/19 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 44445 | 1400/06/15 | CM-C3 | [22 empty] | D01 | AFD | T-1481 | 44845 | 1401/07/19 | T-1481 | 44845 | 1401/07/19 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0007_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0007_D00
3 | 2 | 3 | 2 | 1 | 3 | 3 | 3.2.3.2.1.3.3 | BK-GCS-PEDCO-120-ME-SP-0008 | Specification For Chemical Injection Package |  | BK-GCS-PEDCO-120-ME-SP-0008 | BK-GCS-PEDCO-120-ME-SP-0008 | BK | GCS | PEDCO | 120 | ME | SP | 0008 | F0Z-708829 | AFD | IFC | 2021-09-05 | 2021-08-22 | 2022-04-17 | -14 | 238 | 224 | IFA | 2022-08-07 | 2022-09-07 | 2022-09-12 | 31 | 5 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-24 |  |  | D01 | IFA | T-1187 | 44766 | 1401/05/02 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05754 | 44828 | 1401/07/02 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0008_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-210043 | 44811 | 1401/06/13 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0053 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-ROE-00-01493 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-81002 | 2021-08-22 | 1400/06/09 | 44668 | 1401/01/28 | RJ | [10 empty] | D01 | IFA | T-1187 | 44766 | 1401/05/02 |  |  |  | BK-SUR-ENG-MEC-01-05754 | 44828 | 1401/07/02 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0008_D00 | [5 empty] | 1401-2294-210043 | 44811 | 1401/06/13 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0008_D00
3 | 2 | 3 | 2 | 1 | 3 | 4 | 3.2.3.2.1.3.4 | BK-GCS-PEDCO-120-ME-SP-0013 | Specification For Flare Package |  | BK-GCS-PEDCO-120-ME-SP-0013 | BK-GCS-PEDCO-120-ME-SP-0013 | BK | GCS | PEDCO | 120 | ME | SP | 0013 | F0Z-708830 | AFD | IFC | 2021-09-07 | 2021-09-15 | 2021-09-26 | 8 | 11 | 19 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-02-05 | 0 | 0 | -44597 | 0 | -44597 | AFD | 2022-03-23 | 0 | 0 | -44643 | 0 | -44643 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-08-24 | 2022-03-09 |  | D03 | AFD | T-0710 | 44629 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03458 | 44632 | 1400/12/21 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0013_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-200596 | 2021-09-15 | 1400/06/24 | 44465 | 1400/07/04 | CM | [10 empty] | D01 | IFA | T-0138 | 44475 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 44499 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0013-D00 | [5 empty] | 1400-2294-257419 | 44559 | 1400/08/10 | 44499 | 1400/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0013-D00 | [9 empty] | D02 | IFA | T-0493 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03348 | 44625 | 1400/12/14 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0013_D01 | [10 empty] | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0013_D01 | [9 empty] | D03 | AFD | T-0710 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-MEC-00-03458 | 44632 | 1400/12/21 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0013_D02
3 | 2 | 3 | 2 | 1 | 3 | 5 | 3.2.3.2.1.3.5 | BK-GCS-PEDCO-120-ME-SP-0014 | Specification For Nitrogen Package |  | BK-GCS-PEDCO-120-ME-SP-0014 | BK-GCS-PEDCO-120-ME-SP-0014 | BK | GCS | PEDCO | 120 | ME | SP | 0014 | F0Z-708831 | AFD | IFC | 2021-09-07 | 2021-09-22 | 2021-09-26 | 15 | 4 | 19 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-02-21 | 2022-03-01 | 2022-03-05 | 8 | 4 | 12 | IFA | 2022-04-09 | 2022-04-16 | 2022-01-18 | 7 | -88 | -81 | IFA | 2022-05-03 | 2022-04-30 | 2022-05-07 | -3 | 7 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-06 |  |  | D04 | IFA | T-0847 | 44670 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05921 | 44852 | 1401/07/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45435 | 44681 | 1401/02/10 | 44688 | 1401/02/17 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 44451 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-208212 | 2021-09-22 | 1400/06/31 | 44465 | 1400/07/04 | RJ | [10 empty] | D01 | IFA | T-0138 | 44475 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 44499 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0014-D00 | [5 empty] | 1400-2294-257419 | 44559 | 1400/08/10 | 44499 | 1400/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014-D00 | [9 empty] | D02 | IFA | T-0559 | 44599 | 1400/11/18 |  |  |  | BK-SUR-ENG-MEC-00-03350 | 44625 | 1400/12/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D01 | [5 empty] | 1400-2294-430719 | 44621 | 1400/12/10 | 44625 | 1400/12/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D01 | [9 empty] | D03 | IFA | T_0740 | 44646 | 1401/01/06 | [13 empty] | 1401-2294-25146 | 44667 | 1401/01/27 | 44579 | 1401/01/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D02 | [9 empty] | D04 | IFA | T-0847 | 44670 | 1401/01/30 |  |  |  | BK-SUR-ENG-MEC-01-05921 | 44852 | 1401/07/26 | AP | [6 empty] | 1401-2294-45435 | 44681 | 1401/02/10 | 44688 | 1401/02/17 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D03
3 | 2 | 3 | 2 | 2 | 0 | 0 | 3.2.3.2.2 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 2 | 2 | 1 | 0 | 3.2.2.2.1 |  | Fixed Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 2 | 2 | 1 | 1 | 3.2.3.2.2.1.1 | BK-GCS-PEDCO-120-ME-DT-0001 | Mechanical Data Sheets For Inlet Gas K.O. Drum |  | BK-GCS-PEDCO-120-ME-DT-0001 | BK-GCS-PEDCO-120-ME-DT-0001 | BK | GCS | PEDCO | 120 | ME | DT | 0001 | F0Z-708832 | AFC | IFC | 2021-12-21 | 2021-12-20 | 2021-12-27 | -1 | 7 | 6 | IFA | 2022-01-26 | 2022-01-29 | 2022-02-05 | 3 | 7 | 10 | IFA | 2022-09-25 | 2022-10-27 | 2022-10-31 | 32 | 4 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 |  |  | D02 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0306 | 2021-12-07 | 1400/09/17 | [13 empty] | 1400-2294-327362 | 2021-12-20 | 1400/09/29 | 44557 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0456 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-MEC-00-03587 | 44635 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-386693 | 44590 | 1400/11/09 | 44597 | 1400/11/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0001_D00 | [9 empty] | D02 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0001_D01 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0001_D01
3 | 2 | 3 | 2 | 2 | 1 | 2 | 3.2.3.2.2.1.2 | BK-GCS-PEDCO-120-ME-DT-0002 | Mechanical Data Sheets For 1st Stage G.C. Suction Drums |  | BK-GCS-PEDCO-120-ME-DT-0002 | BK-GCS-PEDCO-120-ME-DT-0002 | BK | GCS | PEDCO | 120 | ME | DT | 0002 | F0Z-708833 | AFC | IFC | 2021-12-27 | 2021-12-26 | 2022-01-05 | -1 | 10 | 9 | IFA | 2022-02-01 | 2022-01-29 | 2022-04-19 | -3 | 80 | 77 | IFA | 2022-08-13 | 2022-08-17 | 2022-08-21 | 4 | 4 | 8 | IFA | 2022-09-25 | 2022-10-27 | 2022-10-31 | 32 | 4 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D03 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0002-D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0002-D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0342 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-MEC-00-02543 | 44564 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-336157 | 2021-12-26 | 1400/10/05 | 44566 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0473 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-MEC-00-03607 | 44635 | 1400/12/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0002_D00 | [5 empty] | 1400-2294-386730 | 44590 | 1400/11/09 | 44670 | 1401/01/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0002_D00 | [9 empty] | D02 | IFA | T-1217 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-MEC-01-05422 | 44786 | 1401/05/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0002_D01 | [5 empty] | 1401-2294-183219 | 44790 | 1401/05/26 | 44794 | 1401/05/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0002_D01 | [9 empty] | D03 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0002-D02 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0002-D02
3 | 2 | 3 | 2 | 2 | 1 | 3 | 3.2.3.2.2.1.3 | BK-GCS-PEDCO-120-ME-DT-0003 | Mechanical Data Sheets For 1st Stage Gas Air Coolers |  | BK-GCS-PEDCO-120-ME-DT-0003 | BK-GCS-PEDCO-120-ME-DT-0003 | BK | GCS | PEDCO | 120 | ME | DT | 0003 | F0Z-708834 | AFC | IFC | 2022-01-12 | 2022-01-17 | 2022-06-07 | 5 | 141 | 146 | IFA | 2022-07-03 | 2022-08-18 | 2022-08-27 | 46 | 9 | 55 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-29 |  |  | D02 | IFA | T-1477 | 44844 | 1401/07/18 | T-1477 | 44844 | 1401/07/18 | BK-SUR-ENG-MEC-01-05925 | 44852 | 1401/07/26 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0401 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-MEC-00-02838 | 44590 | 1400/11/09 | CM-C3 | [6 empty] | 1401-2294-372926 | 2022-01-17 | 1400/10/30 | 44719 | 1401/03/17 | CM | [10 empty] | D01 | IFA | T-1093 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-MEC-01-05079 | 44754 | 1401/04/21 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0003_D00 | [5 empty] | 1401-2294-183492 | 44791 | 1401/05/27 | 44800 | 1401/06/05 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0003_D00 | [9 empty] | D02 | IFA | T-1477 | 44844 | 1401/07/18 | T-1477 | 44844 | 1401/07/18 | BK-SUR-ENG-MEC-01-05925 | 44852 | 1401/07/26 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0003_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0003_D01
3 | 2 | 3 | 2 | 2 | 1 | 4 | 3.2.3.2.2.1.4 | BK-GCS-PEDCO-120-ME-DT-0004 | Mechanical Data Sheets For 2nd Stage G.C. Suction Drums |  | BK-GCS-PEDCO-120-ME-DT-0004 | BK-GCS-PEDCO-120-ME-DT-0004 | BK | GCS | PEDCO | 120 | ME | DT | 0004 | F0Z-708835 | AFC | IFC | 2021-12-27 | 2021-12-26 | 2022-01-05 | -1 | 10 | 9 | IFA | 2022-02-01 | 2022-02-24 | 2022-03-02 | 23 | 6 | 29 | IFA | 2022-05-21 | 2022-06-06 | 2022-06-09 | 16 | 3 | 19 | IFA | 2022-09-25 | 2022-10-27 | 2022-10-31 | 32 | 4 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D03 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0004-D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0004-D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0342 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-MEC-00-02543 | 44564 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-336157 | 2021-12-26 | 1400/10/05 | 44566 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0476 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-MEC-00-03539 | 44634 | 1400/12/23 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0004_D00 | [5 empty] | 1400-2294-424206 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0004_D00 | [9 empty] | D02 | IFA | T-0902 | 44688 | 1401/02/17 | T-0902 | 44688 | 1401/02/17 | BK-SUR-ENG-MEC-01-04179 | 44690 | 1401/02/19 | CM-C3 | [6 empty] | 1401-2290-89281 | 44718 | 1401/03/16 | 44721 | 1401/03/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0004_D01 | [9 empty] | D03 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0004-D02 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0004-D02
3 | 2 | 3 | 2 | 2 | 1 | 5 | 3.2.3.2.2.1.5 | BK-GCS-PEDCO-120-ME-DT-0005 | Mechanical Data Sheets For 2nd Stage Gas Air Coolers |  | BK-GCS-PEDCO-120-ME-DT-0005 | BK-GCS-PEDCO-120-ME-DT-0005 | BK | GCS | PEDCO | 120 | ME | DT | 0005 | F0Z-708836 | AFC | IFC | 2022-01-12 | 2022-01-17 | 2022-06-07 | 5 | 141 | 146 | IFA | 2022-07-03 | 2022-08-18 | 2022-08-27 | 46 | 9 | 55 | IFA | 2022-10-23 | 0 | 0 | -44857 | 0 | -44857 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-29 |  |  | D02 | IFA | T-1469 | 44843 | 1401/07/17 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05922 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0005_D01 | BK-SUR-ENG-MEC-01-05924 | 44852 | 1401/07/26 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0401 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-MEC-00-02838 | 44590 | 1400/11/09 | CM-C3 | [6 empty] | 1401-2294-372926 | 2022-01-17 | 1400/10/30 | 44719 | 1401/03/17 | CM | [10 empty] | D01 | IFA | T-1093 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-MEC-01-05079 | 44754 | 1401/04/21 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0005_D00 | [5 empty] | 1401-2294-183492 | 44791 | 1401/05/27 | 44800 | 1401/06/05 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0005_D00 | [9 empty] | D02 | IFA | T-1469 | 44843 | 1401/07/17 |  |  |  | BK-SUR-ENG-MEC-01-05922 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0005_D01 | BK-SUR-ENG-MEC-01-05924 | 44852 | 1401/07/26 | CM-C2 | [7 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0005_D01
3 | 2 | 3 | 2 | 2 | 1 | 6 | 3.2.3.2.2.1.6 | BK-GCS-PEDCO-120-ME-DT-0006 | Mechanical Data Sheets For Discharge Gas K.O. Drum |  | BK-GCS-PEDCO-120-ME-DT-0006 | BK-GCS-PEDCO-120-ME-DT-0006 | BK | GCS | PEDCO | 120 | ME | DT | 0006 | F0Z-708837 | AFC | IFC | 2022-01-10 | 2022-01-03 | 2022-01-04 | -7 | 1 | -6 | IFA | 2022-01-25 | 2022-02-26 | 2022-03-02 | 32 | 4 | 36 | IFA | 2022-09-25 | 2022-10-27 | 2022-10-31 | 32 | 4 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-27 |  |  | D02 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0386 | 2021-12-27 | 1400/10/06 |  |  |  | BK-SUR-ENG-MEC-00-02552 | 44564 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-346502 | 2022-01-03 | 1400/10/13 | 44565 | 1400/10/14 | CM | [10 empty] | D01 | IFA | T-0447 | 44572 | 1400/10/20 |  |  |  | BK-SUR-ENG-MEC-00-02798 | 44585 | 1400/11/04 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D00 | [5 empty] | 1400-2294-426688 | 44618 | 1400/12/07 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D00 | [9 empty] | D02 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D01 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D01
3 | 2 | 3 | 2 | 2 | 1 | 7 | 3.2.3.2.2.1.7 | BK-GCS-PEDCO-120-ME-DT-0007 | Mechanical Data Sheets For Diesel Oil Drum |  | BK-GCS-PEDCO-120-ME-DT-0007 | BK-GCS-PEDCO-120-ME-DT-0007 | BK | GCS | PEDCO | 120 | ME | DT | 0007 | F0Z-708838 | AFC | IFC | 2021-12-27 | 2022-12-21 | 2022-06-11 | 359 | -193 | 166 | IFA | 2022-11-14 | 0 | 0 | -44879 | 0 | -44879 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D01 | IFA | T-1568 | 44865 | 1401/08/09 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-06201 | 44884 | 1401/08/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0338 | 2021-12-13 | 1400/09/23 |  |  |  | BK-SUR-ENG-FXE-00-02541 | 44564 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-329500 | 2022-12-21 | 1400/09/30 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1568 | 44865 | 1401/08/09 |  |  |  | BK-SUR-ENG-MEC-01-06201 | 44884 | 1401/08/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0007_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0007_D00
3 | 2 | 3 | 2 | 2 | 1 | 8 | 3.2.3.2.2.1.8 | BK-GCS-PEDCO-120-ME-DT-0008 | Mechanical Data Sheets For Instrument Air Receiver |  | BK-GCS-PEDCO-120-ME-DT-0008 | BK-GCS-PEDCO-120-ME-DT-0008 | BK | GCS | PEDCO | 120 | ME | DT | 0008 | F0Z-708839 | AFC | IFC | 2021-12-21 | 2022-08-17 | 2022-08-21 | 239 | 4 | 243 | IFA | 2022-09-25 | 2022-10-27 | 2022-10-31 | 32 | 4 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 |  |  | D01 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0008_D00 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0008_D00 | [9 empty] | D00 | IFC | T-0311 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-MEC-00-02824 | 44587 | 1400/11/09 | CM-C3 | [6 empty] | 1401-2294-183214 | 2022-08-17 | 1401/05/26 | 44794 | 1401/05/30 | CM | [10 empty] | D01 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0008_D00 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0008_D00
3 | 2 | 3 | 2 | 2 | 1 | 9 | 3.2.3.2.2.1.9 | BK-GCS-PEDCO-120-ME-DT-0009 | Mechanical Data Sheets For Nitrogen Receiver |  | BK-GCS-PEDCO-120-ME-DT-0009 | BK-GCS-PEDCO-120-ME-DT-0009 | BK | GCS | PEDCO | 120 | ME | DT | 0009 | F0Z-708840 | AFC | IFC | 2021-12-11 | 2021-12-14 | 2021-12-20 | 3 | 6 | 9 | IFA | 2022-01-09 | 2021-12-30 | 2022-01-05 | -10 | 6 | -4 | IFA | 2022-09-25 | 2022-10-27 | 2022-10-31 | 32 | 4 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 |  |  | D02 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0009-D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0009-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 44545 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 44550 | 1400/09/29 | CM | [10 empty] | D01 | IFA | T-0381 | 44556 | 1400/10/05 | T-0381 | 44556 | 1400/10/05 | BK-SUR-ENG-MEC-00-03340 | 44625 | 1400/12/14 | CM-C3 | PEDCO_CRS-BK-GCS-PEDCO-120-ME-DT-0009_D00 | [5 empty] | 1400-2294-342154 | 44560 | 1400/10/09 | 44566 | 1400/10/15 | CM | NISOC_CRS-BK-GCS-PEDCO-120-ME-DT-0009_D00 | [9 empty] | D02 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0009-D01 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0009-D01
3 | 2 | 3 | 2 | 2 | 1 | 10 | 3.2.3.2.2.1.10 | BK-GCS-PEDCO-120-ME-DT-0010 | Mechanical Data Sheets For Close Drain Drum |  | BK-GCS-PEDCO-120-ME-DT-0010 | BK-GCS-PEDCO-120-ME-DT-0010 | BK | GCS | PEDCO | 120 | ME | DT | 0010 | F0Z-708841 | AFC | IFC | 2021-12-27 | 2021-12-22 | 2021-12-27 | -5 | 5 | 0 | IFA | 2022-09-25 | 2022-10-27 | 2022-10-31 | 32 | 4 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-13 |  |  | D01 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0339 | 2021-12-13 | 1400/09/23 |  |  |  | BK-SUR-ENG-MEC-00-02542 | 44564 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-331625 | 2021-12-22 | 1400/10/01 | 44557 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0010_D00 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0010_D00
3 | 2 | 3 | 2 | 2 | 1 | 11 | 3.2.3.2.2.1.11 | BK-GCS-PEDCO-120-ME-DT-0011 | Mechanical Data Sheets For Elevated Potable Water Tank |  | BK-GCS-PEDCO-120-ME-DT-0011 | BK-GCS-PEDCO-120-ME-DT-0011 | BK | GCS | PEDCO | 120 | ME | DT | 0011 | F0Z-708842 | AFC | IFC | 2021-12-11 | 2021-12-14 | 2021-12-20 | 3 | 6 | 9 | IFA | 2022-01-08 | 2022-01-03 | 2022-01-04 | -5 | 1 | -4 | IFA | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 |  |  | D02 | IFA | T-1592 | 44884 | 1401/08/28 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-06240 | 44887 | 1401/09/01 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 44545 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-318813 | 2021-12-14 | 1400/09/23 | 44550 | 1400/09/29 | CM | [10 empty] | D01 | IFA | T-0377 | 44555 | 1400/10/04 |  |  |  | BK-SUR-ENG-MEC-00-03338 | 44625 | 1400/12/14 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D00 | [5 empty] | 1400-2294-347297 | 44564 | 1400/10/13 | 44565 | 1400/10/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D00 | [9 empty] | D02 | IFA | T-1592 | 44884 | 1401/08/28 |  |  |  | BK-SUR-ENG-MEC-01-06240 | 44887 | 1401/09/01 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D01
3 | 2 | 3 | 2 | 2 | 1 | 12 | 3.2.3.2.2.1.12 | BK-GCS-PEDCO-120-ME-DT-0012 | Mechanical Data Sheets For Flare K.O. Drum |  | BK-GCS-PEDCO-120-ME-DT-0012 | BK-GCS-PEDCO-120-ME-DT-0012 | BK | GCS | PEDCO | 120 | ME | DT | 0012 | F0Z-708843 | AFC | IFC | 2022-01-17 | 2022-01-18 | 2022-01-24 | 1 | 6 | 7 | IFA | 2022-09-27 | 0 | 0 | -44831 | 0 | -44831 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-03 |  |  | D01 | IFA | T-1396 | 44817 | 1401/06/22 | T-1396 | 44817 | 1401/06/22 | BK-SUR-ENG-MEC-01-05928 | 44853 | 1401/07/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0012_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0421 | 2022-01-03 | 1400/10/13 | [13 empty] | 1400-2294-368388 | 2022-01-18 | 1400/10/27 | 44585 | 1400/11/04 | CM | [10 empty] | D01 | IFA | T-1396 | 44817 | 1401/06/22 | T-1396 | 44817 | 1401/06/22 | BK-SUR-ENG-MEC-01-05928 | 44853 | 1401/07/27 | CM-C3 | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0012_D00
3 | 2 | 3 | 2 | 2 | 1 | 13 | 3.2.3.2.2.1.13 | BK-GCS-PEDCO-120-ME-DT-0013 | Mechanical Data Sheets For Fuel Gas K.O. Drum |  | BK-GCS-PEDCO-120-ME-DT-0013 | BK-GCS-PEDCO-120-ME-DT-0013 | BK | GCS | PEDCO | 120 | ME | DT | 0013 | F0Z-708844 | AFC | IFC | 2021-12-27 | 2021-12-26 | 2022-01-05 | -1 | 10 | 9 | IFA | 2022-09-25 | 2022-10-27 | 2022-10-31 | 32 | 4 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-13 |  |  | D01 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO_CRS-BK-GCS-PEDCO-120-ME-DT-0013_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0013_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0342 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-MEC-00-02543 | 44564 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-336157 | 2021-12-26 | 1400/10/05 | 44566 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO_CRS-BK-GCS-PEDCO-120-ME-DT-0013_D00 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0013_D00
3 | 2 | 3 | 2 | 2 | 1 | 14 | 3.2.3.2.2.1.14 | BK-GCS-PEDCO-120-ME-DT-0014 | Mechanical Data Sheets For Slug Catcher |  | BK-GCS-PEDCO-120-ME-DT-0014 | BK-GCS-PEDCO-120-ME-DT-0014 | BK | GCS | PEDCO | 120 | ME | DT | 0014 | F0Z-708845 | AFC | IFC | 2022-01-11 | 2021-06-06 | 2022-04-19 | -219 | 317 | 98 | IFA | 2022-09-27 | 0 | 0 | -44831 | 0 | -44831 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-28 |  |  | D01 | IFA | T-1396 | 44817 | 1401/06/22 | T-1396 | 44817 | 1401/06/22 | BK-SUR-ENG-MEC-01-05928 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0014_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0014_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0389 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-MEC-00-03364 | 44626 | 1400/12/15 | CM-C3 | [6 empty] | 1400-2294-352384 | 2021-06-06 | 1400/10/16 | 44670 | 1401/01/30 | CM | [10 empty] | D01 | IFA | T-1396 | 44817 | 1401/06/22 | T-1396 | 44817 | 1401/06/22 | BK-SUR-ENG-MEC-01-05928 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0014_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0014_D00
3 | 2 | 3 | 2 | 2 | 1 | 15 | 3.2.3.2.2.1.15 | BK-GCS-PEDCO-120-ME-DT-0015 | Mechanical Data Sheets For Degassing Vessel |  | BK-GCS-PEDCO-120-ME-DT-0015 | BK-GCS-PEDCO-120-ME-DT-0015 | BK | GCS | PEDCO | 120 | ME | DT | 0015 | F0Z-708846 | AFC | IFC | 2022-03-20 | 2022-03-15 | 2022-03-26 | -5 | 11 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-06 |  |  | D00 | IFC | T-0680 | 44626 | 1400/12/15 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-03746 | 44657 | 1401/01/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-451028 | 44635 | 1400/12/24 | 44646 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0680 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-MEC-01-03746 | 44657 | 1401/01/17 | CM-C3 | [6 empty] | 1400-2294-451028 | 2022-03-15 | 1400/12/24 | 44646 | 1401/01/09 | AP
3 | 2 | 3 | 2 | 2 | 1 | 16 | 3.2.3.2.2.1.16 | BK-GCS-PEDCO-120-ME-DT-0016 | Mechanical Data Sheets For Lean Glycol Storage Tank |  | BK-GCS-PEDCO-120-ME-DT-0016 | BK-GCS-PEDCO-120-ME-DT-0016 | BK | GCS | PEDCO | 120 | ME | DT | 0016 | F0Z-708847 | AFC | IFC | 2021-12-12 | 2021-12-14 | 2021-12-20 | 2 | 6 | 8 | IFA | 2022-01-12 | 2022-01-06 | 2022-01-04 | -6 | -2 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-28 |  |  | D01 | IFA | T-0406 | 44559 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02824 | 44587 | 1400/11/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-352427 | 44567 | 1400/10/16 | 44565 | 1400/10/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0279 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-MEC-00-02303 | 44545 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-318686 | 2021-12-14 | 1400/09/23 | 44550 | 1400/09/29 | CM | [10 empty] | D01 | IFA | T-0406 | 44559 | 1400/10/08 |  |  |  | BK-SUR-ENG-MEC-00-02824 | 44587 | 1400/11/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0016_D00 | [5 empty] | 1400-2294-352427 | 44567 | 1400/10/16 | 44565 | 1400/10/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0016_D00
3 | 2 | 3 | 2 | 2 | 1 | 17 | 3.2.3.2.2.1.17 | BK-GCS-PEDCO-120-ME-DT-0017 | Mechanical Data Sheets For Fire Water Storage Tank |  | BK-GCS-PEDCO-120-ME-DT-0017 | BK-GCS-PEDCO-120-ME-DT-0017 | BK | GCS | PEDCO | 120 | ME | DT | 0017 | F0Z-708848 | AFC | IFC | 2022-07-03 | 2022-08-13 | 2022-08-20 | 41 | 7 | 48 | IFA | 2022-12-03 | 0 | 0 | -44898 | 0 | -44898 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-19 |  |  | D01 | IFA | T-1592 | 44884 | 1401/08/28 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-06240 | 44887 | 1401/09/01 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0017_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0017_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1095 | 2022-06-19 | 1401/03/30 |  |  |  | BK-SUR-ENG-MEC-01-05592 | 44808 | 1401/06/13 | CM-C3 | [6 empty] | 1401-2294-175140 | 2022-08-13 | 1401/05/22 | 44793 | 1401/05/29 | CM | [10 empty] | D01 | IFA | T-1592 | 44884 | 1401/08/28 |  |  |  | BK-SUR-ENG-MEC-01-06240 | 44887 | 1401/09/01 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0017_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0017_D00
3 | 2 | 3 | 2 | 2 | 1 | 18 | 3.2.3.2.2.1.18 | BK-GCS-PEDCO-120-ME-DT-0018 | Mechanical Data Sheets For Slug Storage Tank |  | BK-GCS-PEDCO-120-ME-DT-0018 | BK-GCS-PEDCO-120-ME-DT-0018 | BK | GCS | PEDCO | 120 | ME | DT | 0018 | F0Z-708849 | AFC | IFC | 2021-12-28 | 2021-12-22 | 2021-12-27 | -6 | 5 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-14 |  |  | D00 | IFC | T-0344 | 44544 | 1400/09/23 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02551 | 44564 | 1400/10/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-330580 | 44552 | 1400/10/01 | 44557 | 1400/10/06 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0344 | 2021-12-14 | 1400/09/23 |  |  |  | BK-SUR-ENG-MEC-00-02551 | 44564 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-330580 | 2021-12-22 | 1400/10/01 | 44557 | 1400/10/06 | CM
[8 empty] | BK-GCS-PEDCO-120-ME-DT-0036 | Mechanical Data Sheets For Glycol Drain Pump |  | BK-GCS-PEDCO-120-ME-DT-0036 | [60 empty] | 2022-01-05 |  |  | D01 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0036-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0036_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0436 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-MEC-00-02941 | 44597 | 1400/11/16 | CM-C3 | [6 empty] | 1400-2294-372927 | 2022-06-20 | 1400/10/30 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1384 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | BK-SUR-ENG-MEC-01-05915 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0036-D00 | [5 empty] | 1401-2294-283322 | 44861 | 1401/08/05 | 44865 | 1401/08/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0036_D00
3 | 2 | 3 | 2 | 2 | 2 | 0 | 3.2.2.2.2 |  | Rotary Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 2 | 2 | 2 | 1 | 3.2.3.2.2.2.1 | BK-GCS-PEDCO-120-ME-DT-0019 | Mechanical Data Sheets For Slug Pumps |  | BK-GCS-PEDCO-120-ME-DT-0019 | BK-GCS-PEDCO-120-ME-DT-0019 | BK | GCS | PEDCO | 120 | ME | DT | 0019 | F0Z-708850 | AFC | IFC | 2021-12-21 | 2021-12-20 | 2021-12-27 | -1 | 7 | 6 | IFA | 2022-02-05 | 2022-02-24 | 2022-03-02 | 19 | 6 | 25 | AFC | 2022-04-26 | 0 | 0 | -44677 | 0 | -44677 | AFC | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 | 2022-09-07 |  | D03 | AFC | T-1375 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0306 | 2021-12-07 | 1400/09/17 | [13 empty] | 1400-2294-327362 | 2021-12-20 | 1400/09/29 | 44557 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0493 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03348 | 44625 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-424207 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0019_D00 | [9 empty] | D02 | AFC | T-0811 | 44663 | 1401/01/23 |  |  |  | BK-SUR-ENG-MEC-01-03989 | 44670 | 1401/01/30 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0019_D01 | [21 empty] | D03 | AFC | T-1375 | 44811 | 1401/06/16 |  |  |  | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2
3 | 2 | 3 | 2 | 2 | 2 | 2 | 3.2.3.2.2.2.2 | BK-GCS-PEDCO-120-ME-DT-0020 | Mechanical Data Sheets For Glycol Transfer Pumps |  | BK-GCS-PEDCO-120-ME-DT-0020 | BK-GCS-PEDCO-120-ME-DT-0020 | BK | GCS | PEDCO | 120 | ME | DT | 0020 | F0Z-708851 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-23 | 2022-03-16 | 2022-03-29 | -7 | 13 | 6 | AFC | 2022-04-26 | 2022-05-12 | 2022-05-22 | 16 | 10 | 26 | AFC | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 | 2022-09-07 |  | D04 | AFC | T-1375 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 44550 | 1400/09/29 | CM |  | 1400-2294-327356 | 44550 | 1400/09/29 | 44557 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 44592 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0020_D00 | [5 empty] | 1400-2294-424141 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0020_D00 | [9 empty] | D02 | IFA | T-0706 | 44629 | 1400/12/18 | [13 empty] | 1400-2294-453306 | 44636 | 1400/12/25 | 44649 | 1401/01/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0020_D01 | [9 empty] | D03 | AFC | T-0778 | 44663 | 1401/01/23 | [13 empty] | 1401-2294-59445 | 44693 | 1401/02/22 | 44703 | 1401/03/01 | AP | [10 empty] | D04 | AFC | T-1375 | 44811 | 1401/06/16 |  |  |  | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2
3 | 2 | 3 | 2 | 2 | 2 | 3 | 3.2.3.2.2.2.3 | BK-GCS-PEDCO-120-ME-DT-0021 | Mechanical Data Sheets For Glycol Manual Pump |  | BK-GCS-PEDCO-120-ME-DT-0021 | BK-GCS-PEDCO-120-ME-DT-0021 | BK | GCS | PEDCO | 120 | ME | DT | 0021 | F0Z-708852 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-23 | 2022-03-16 | 2022-03-29 | -7 | 13 | 6 | AFC | 2022-04-26 | 2022-05-12 | 2022-05-22 | 16 | 10 | 26 | AFC | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 | 2022-09-07 |  | D04 | AFC | T-1375 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 44550 | 1400/09/29 | CM |  | 1400-2294-327356 | 44550 | 1400/09/29 | 44557 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 44592 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0021_D00 | [5 empty] | 1400-2294-424141 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0021_D00 | [9 empty] | D02 | IFA | T-0706 | 44629 | 1400/12/18 | [13 empty] | 1400-2294-453306 | 44636 | 1400/12/25 | 44649 | 1401/01/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0021_D01 | [9 empty] | D03 | AFC | T-0778 | 44663 | 1401/01/23 | [13 empty] | 1401-2294-59445 | 44693 | 1401/02/22 | 44703 | 1401/03/01 | AP | [10 empty] | D04 | AFC | T-1375 | 44811 | 1401/06/16 |  |  |  | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2
3 | 2 | 3 | 2 | 2 | 2 | 4 | 3.2.3.2.2.2.4 | BK-GCS-PEDCO-120-ME-DT-0022 | Mechanical Data Sheets For Closed Drain Pumps |  | BK-GCS-PEDCO-120-ME-DT-0022 | BK-GCS-PEDCO-120-ME-DT-0022 | BK | GCS | PEDCO | 120 | ME | DT | 0022 | F0Z-708853 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-22 | 2022-03-23 | 2022-03-26 | 1 | 3 | 4 | IFA | 2022-04-25 | 2022-04-28 | 2022-05-01 | 3 | 3 | 6 | AFC | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-27 | 2022-09-07 |  | D04 | AFC | T-1375 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 44550 | 1400/09/29 | CM |  | 1400-2294-327356 | 44550 | 1400/09/29 | 44557 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 44592 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D00 | [5 empty] | 1400-2294-424141 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D00 | [9 empty] | D02 | IFA | T-0701 | 44628 | 1400/12/17 | [13 empty] | 1401-2294-1324 | 44643 | 1401/01/06 | 44646 | 1401/01/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D01 | 1400-2294-447218 | 44633 | 1400/12/22 | 44646 | 1401/01/09 | AP |  |  |  | D03 | IFA | T-0800 | 44662 | 1401/01/22 |  |  |  | BK-SUR-ENG-MEC-01-03932 | 44667 | 1401/01/27 | CM-C2 | [6 empty] | 1401-2294-42955 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D02 | [9 empty] | D04 | AFC | T-1375 | 44811 | 1401/06/16 |  |  |  | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D03
3 | 2 | 3 | 2 | 2 | 2 | 5 | 3.2.3.2.2.2.5 | BK-GCS-PEDCO-120-ME-DT-0023 | Mechanical Data Sheets For Sump Pumps |  | BK-GCS-PEDCO-120-ME-DT-0023 | BK-GCS-PEDCO-120-ME-DT-0023 | BK | GCS | PEDCO | 120 | ME | DT | 0023 | F0Z-708854 | AFC | IFC | 2021-12-21 | 2021-12-20 | 2021-12-27 | -1 | 7 | 6 | IFA | 2022-02-05 | 2022-02-24 | 2022-03-02 | 19 | 6 | 25 | AFC | 2022-04-10 | 0 | 0 | -44661 | 0 | -44661 | AFC | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 | 2022-09-07 |  | D03 | AFC | T-1375 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0306 | 2021-12-07 | 1400/09/17 | [13 empty] | 1400-2294-327362 | 2021-12-20 | 1400/09/29 | 44557 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0493 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03348 | 44625 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-424207 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0023_D00 | [9 empty] | D02 | AFC | T-0753 | 44647 | 1401/01/07 |  |  |  | BK-SUR-ENG-MEC-01-03729 | 44656 | 1401/01/16 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0023_D01 | [21 empty] | D03 | AFC | T-1375 | 44811 | 1401/06/16 |  |  |  | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2
3 | 2 | 3 | 2 | 2 | 2 | 6 | 3.2.3.2.2.2.6 | BK-GCS-PEDCO-120-ME-DT-0024 | Mechanical Data Sheets For Flare KO Drum Pumps |  | BK-GCS-PEDCO-120-ME-DT-0024 | BK-GCS-PEDCO-120-ME-DT-0024 | BK | GCS | PEDCO | 120 | ME | DT | 0024 | F0Z-708855 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-22 | 2022-03-23 | 2022-03-26 | 1 | 3 | 4 | IFA | 2022-04-25 | 2022-04-28 | 2022-05-01 | 3 | 3 | 6 | AFC | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 | 2022-09-07 |  | D04 | AFC | T-1375 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 44550 | 1400/09/29 | CM |  | 1400-2294-327356 | 44550 | 1400/09/29 | 44557 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 44592 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D00 | [5 empty] | 1400-2294-424141 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D00 | [9 empty] | D02 | IFA | T-0701 | 44628 | 1400/12/17 | [13 empty] | 1401-2294-1324 | 44643 | 1401/01/06 | 44646 | 1401/01/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D01 | 1400-2294-447218 | 44633 | 1400/12/22 | 44646 | 1401/01/09 | AP |  |  |  | D03 | IFA | T-0800 | 44662 | 1401/01/22 |  |  |  | BK-SUR-ENG-MEC-01-03932 | 44667 | 1401/01/27 | CM-C2 | [6 empty] | 1401-2294-42955 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D02 | [9 empty] | D04 | AFC | T-1375 | 44811 | 1401/06/16 |  |  |  | BK-SUR-ENG-MEC-01-05690 | 44818 | 1401/06/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D03
3 | 2 | 3 | 2 | 2 | 2 | 7 | 3.2.3.2.2.2.7 | BK-GCS-PEDCO-120-ME-DT-0025 | Mechanical Data Sheets For Potable Water Pump |  | BK-GCS-PEDCO-120-ME-DT-0025 | BK-GCS-PEDCO-120-ME-DT-0025 | BK | GCS | PEDCO | 120 | ME | DT | 0025 | F0Z-708856 | AFC | IFC | 2021-12-21 | 2021-12-20 | 2021-12-27 | -1 | 7 | 6 | IFA | 2022-02-05 | 2022-02-24 | 2022-03-02 | 19 | 6 | 25 | AFC | 2022-04-09 | 2022-02-24 | 2022-02-24 | -44 | 0 | -44 | AFC | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-07 | 2022-09-07 |  | D03 | AFC | T-1373 | 44811 | 1401/06/16 | T-1373 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05918 | 44852 | 1401/07/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0306 | 2021-12-07 | 1400/09/17 | [13 empty] | 1400-2294-327362 | 2021-12-20 | 1400/09/29 | 44557 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0493 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03348 | 44625 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-424207 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0025_D00 | [9 empty] | D02 | AFC | T-0742 | 44646 | 1401/01/06 |  |  |  | BK-SUR-ENG-MEC-01-03728 | 44656 | 1401/01/16 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0025_D01 | [5 empty] | 1400-2294-424207 | 44616 | 1400/12/05 | 44616 | 1400/12/05 | AP | [10 empty] | D03 | AFC | T-1373 | 44811 | 1401/06/16 | T-1373 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05918 | 44852 | 1401/07/26 | AP
3 | 2 | 3 | 2 | 2 | 2 | 8 | 3.2.3.2.2.2.8 | BK-GCS-PEDCO-120-ME-DT-0026 | Mechanical Data Sheets For Diesel Pump |  | BK-GCS-PEDCO-120-ME-DT-0026 | BK-GCS-PEDCO-120-ME-DT-0026 | BK | GCS | PEDCO | 120 | ME | DT | 0026 | F0Z-708857 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-23 | 2022-03-16 | 2022-03-29 | -7 | 13 | 6 | AFC | 2022-04-26 | 2022-05-12 | 2022-05-22 | 16 | 10 | 26 | AFC | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-27 | 2022-09-07 |  | D04 | AFC | T-1373 | 44811 | 1401/06/16 | T-1373 | 44816 | 1401/06/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 44545 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 44550 | 1400/09/29 | CM |  | 1400-2294-327356 | 44550 | 1400/09/29 | 44557 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 44585 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 44592 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0026_D00 | [5 empty] | 1400-2294-424141 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0026_D00 | [9 empty] | D02 | IFA | T-0706 | 44629 | 1400/12/18 | [13 empty] | 1400-2294-453306 | 44636 | 1400/12/25 | 44649 | 1401/01/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0026_D01 | [9 empty] | D03 | AFC | T-0778 | 44663 | 1401/01/23 |  |  |  | BK-SUR-ENG-MEC-01-05918 | 44852 | 1401/07/26 | AP | [6 empty] | 1401-2294-59445 | 44693 | 1401/02/22 | 44703 | 1401/03/01 | AP | [10 empty] | D04 | AFC | T-1373 | 44811 | 1401/06/16 | T-1373 | 44816 | 1401/06/20
3 | 2 | 3 | 2 | 2 | 2 | 9 | 3.2.3.2.2.2.9 | BK-GCS-PEDCO-120-ME-DT-0027 | Mechanical Data Sheets For Overhead Traveling Cranes |  | BK-GCS-PEDCO-120-ME-DT-0027 | BK-GCS-PEDCO-120-ME-DT-0027 | BK | GCS | PEDCO | 120 | ME | DT | 0027 | F0Z-708858 | AFC | IFC | 2022-02-27 | 2022-03-10 | 2022-03-12 | 11 | 2 | 13 | IFA | 2022-04-09 | 2022-04-16 | 2022-01-18 | 7 | -88 | -81 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-22 | 5 | 13 | 18 | AFC | 2022-07-03 | 2022-08-20 | 2022-08-24 | 48 | 4 | 52 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 |  |  | D03 | AFC | T-1094 | 44731 | 1401/03/30 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-04971 | 44745 | 1401/04/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-135315 | 44752 | 1401/04/19 | 44773 | 1401/05/08 | AP | 0 | 1401-2294-185626 | 44793 | 1401/05/29 | 44797 | 1401/06/02 | CM | 0 | 0 |  | D00 | IFC | T-0591 | 2022-02-13 | 1400/11/24 | [13 empty] | 1400-2294-443255 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/22 | CM | [10 empty] | D01 | IFA | T-0740 | 44646 | 1401/01/06 |  |  |  | BK-SUR-ENG-MEC-01-03895 | 44664 | 1401/01/24 | AP | [6 empty] | 1401-2294-25146 | 44667 | 1401/01/27 | 44579 | 1401/01/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0027_D00 | [9 empty] | D02 | IFA | T-0851 | 44671 | 1401/01/31 |  |  |  | BK-SUR-ENG-MEC-01-04152 | 44688 | 1401/02/17 | AP | [6 empty] | 1401-2294-54998 | 44690 | 1401/02/19 | 44703 | 1401/03/01 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0027_D01 | [9 empty] | D03 | AFC | T-1094 | 44731 | 1401/03/30 |  |  |  | BK-SUR-ENG-MEC-01-04971 | 44745 | 1401/04/12 | AP | [6 empty] | 1401-2294-135315 | 44752 | 1401/04/19 | 44773 | 1401/05/08 | AP |  | 1401-2294-185626 | 44793 | 1401/05/29 | 44797 | 1401/06/02 | CM
3 | 2 | 3 | 2 | 2 | 2 | 10 | 3.2.3.2.2.2.10 | BK-GCS-PEDCO-120-ME-DT-0028 | Mechanical Data Sheets For Fire Water Jockey Pumps |  | BK-GCS-PEDCO-120-ME-DT-0028 | BK-GCS-PEDCO-120-ME-DT-0028 | BK | GCS | PEDCO | 120 | ME | DT | 0028 | F0Z-708859 | AFC | IFC | 2022-03-07 | 2022-03-14 | 2022-03-26 | 7 | 12 | 19 | IFA | 2022-04-30 | 2022-05-09 | 2022-05-22 | 9 | 13 | 22 | IFA | 2022-08-14 | 2022-10-05 | 2022-10-18 | 52 | 13 | 65 | AFC | 2022-11-02 | 2022-11-03 | 2022-11-06 | 1 | 3 | 4 | AFC | 2022-11-21 | 0 | 0 | -44886 | 0 | -44886 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-21 | 2022-11-07 |  | D04 | AFC | T-1578 | 44872 | 1401/08/16 | T-1578 | 44872 | 1401/08/16 | BK-SUR-ENG-MEC-01-06132 | 44873 | 1401/08/17 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0622 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-ENG-MEC-00-03490 | 44633 | 1400/12/22 | CM-C2 | [6 empty] | 1400-2294-448470 | 2022-03-14 | 1400/12/23 | 44646 | 1401/01/09 | CM | [10 empty] | D01 | IFA | T-0815 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-MEC-01-04138 | 44688 | 1401/02/17 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D00 | [5 empty] | 1401-2294-55015 | 44690 | 1401/02/19 | 44703 | 1401/03/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D00 | [9 empty] | D02 | IFA | T-1224 | 44773 | 1401/05/09 |  |  |  | BK-SUR-ENG-MEC-01-05402 | 44783 | 1401/05/19 | AP | [6 empty] | 1401-2294-205811 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D01 | 1401-2294-249369 | 44839 | 1401/07/13 | 44852 | 1401/07/26 | CM |  |  |  | D03 | AFC | T-1512 | 44853 | 1401/07/27 | T-1520 | 44853 | 1401/07/27 | BK-SUR-ENG-MEC-01-06042 | 44865 | 1401/08/09 | CM-C3 | [6 empty] | 1401-2294-294099 | 44868 | 1401/08/12 | 44871 | 1401/08/15 | CM | [10 empty] | D04 | AFC | T-1578 | 44872 | 1401/08/16 | T-1578 | 44872 | 1401/08/16 | BK-SUR-ENG-MEC-01-06132 | 44873 | 1401/08/17 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D03 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D03
3 | 2 | 3 | 2 | 2 | 2 | 11 | 3.2.3.2.2.2.11 | BK-GCS-PEDCO-120-ME-DT-0029 | Mechanical Data Sheets For Fire Water Main Pumps - Elect. Motor Driven |  | BK-GCS-PEDCO-120-ME-DT-0029 | BK-GCS-PEDCO-120-ME-DT-0029 | BK | GCS | PEDCO | 120 | ME | DT | 0029 | F0Z-708860 | AFC | IFC | 2022-03-07 | 2022-04-06 | 2022-04-13 | 30 | 7 | 37 | IFA | 2022-05-31 | 2022-06-14 | 2022-06-20 | 14 | 6 | 20 | IFA | 2022-09-13 | 2022-10-05 | 2022-10-11 | 22 | 6 | 28 | IFA | 2022-11-02 | 0 | 0 | -44867 | 0 | -44867 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-21 |  |  | D03 | IFA | T-1514 | 44853 | 1401/07/27 | T-1514 | 44853 | 1401/07/27 | BK-SUR-ENG-MEC-01-06042 | 44865 | 1401/08/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0614 | 2022-02-21 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03504 | 44633 | 1400/12/22 | CM-C3 | [6 empty] | 1401-2294-13623 | 2022-04-06 | 1401/01/17 | 44664 | 1401/01/24 | CM | [10 empty] | D01 | IFA | T-0964 | 44698 | 1401/02/27 | T-0964 | 44699 | 1401/02/28 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D00 | [5 empty] | 1401-2294-102542 | 44726 | 1401/03/24 | 44732 | 1401/03/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D00 | [9 empty] | D02 | IFA | T-1342 | 44803 | 1401/06/08 |  |  |  | BK-SUR-ENG-MEC-01-05823 | 44837 | 1401/07/11 | CM-C2 | [6 empty] | 1401-2294-249363 | 44839 | 1401/07/13 | 44845 | 1401/07/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D01 | [9 empty] | D03 | IFA | T-1514 | 44853 | 1401/07/27 | T-1514 | 44853 | 1401/07/27 | BK-SUR-ENG-MEC-01-06042 | 44865 | 1401/08/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D02
3 | 2 | 3 | 2 | 2 | 2 | 12 | 3.2.3.2.2.2.12 | BK-GCS-PEDCO-120-ME-DT-0030 | Mechanical Data Sheets For Fire Water Main Pumps - Diesel Engine Driven |  | BK-GCS-PEDCO-120-ME-DT-0030 | BK-GCS-PEDCO-120-ME-DT-0030 | BK | GCS | PEDCO | 120 | ME | DT | 0030 | F0Z-708861 | AFC | IFC | 2022-03-02 | 2022-03-09 | 2022-03-12 | 7 | 3 | 10 | IFA | 2022-04-30 | 2022-05-09 | 2022-05-22 | 9 | 13 | 22 | IFA | 2022-08-14 | 2022-10-05 | 2022-10-18 | 52 | 13 | 65 | IFA | 2022-11-02 | 0 | 0 | -44867 | 0 | -44867 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-16 |  |  | D03 | IFA | T-1514 | 44853 | 1401/07/27 | T-1514 | 44853 | 1401/07/27 | BK-SUR-ENG-MEC-01-06042 | 44865 | 1401/08/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0597 | 2022-02-16 | 1400/11/26 |  |  |  | BK-SUR-ENG-MEC-00-03352 | 44625 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-442060 | 2022-03-09 | 1400/12/18 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0815 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-MEC-01-04138 | 44688 | 1401/02/17 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D00 | [5 empty] | 1401-2294-55015 | 44690 | 1401/02/19 | 44703 | 1401/03/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D00 | [9 empty] | D02 | IFA | T-1224 | 44773 | 1401/05/09 |  |  |  | BK-SUR-ENG-MEC-01-05402 | 44783 | 1401/05/19 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D01 | [5 empty] | 1401-2294-205811 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D01 | 1401-2294-249369 | 44839 | 1401/07/13 | 44852 | 1401/07/26 | CM |  |  |  | D03 | IFA | T-1514 | 44853 | 1401/07/27 | T-1514 | 44853 | 1401/07/27 | BK-SUR-ENG-MEC-01-06042 | 44865 | 1401/08/09 | CM-C3 | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D02
3 | 2 | 3 | 2 | 2 | 3 | 4 | 3.2.3.2.2.3.4 | BK-GCS-PEDCO-120-ME-DT-0034 | Mechanical Data Sheets For Glycol Sump Pumps |  | BK-GCS-PEDCO-120-ME-DT-0034 | BK-GCS-PEDCO-120-ME-DT-0034 | BK | GCS | PEDCO | 120 | ME | DT | 0034 | F0Z-708862 | AFC | IFC | 2021-12-22 | 2021-12-30 | 2022-01-05 | 8 | 6 | 14 | IFA | 2022-02-01 | 2022-02-24 | 2022-03-02 | 23 | 6 | 29 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-08 |  |  | D01 | IFA | T-0476 | 44579 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03539 | 44634 | 1400/12/23 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-424206 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0034_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0319 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-342155 | 2021-12-30 | 1400/10/09 | 44566 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0476 | 44579 | 1400/10/28 |  |  |  | BK-SUR-ENG-MEC-00-03539 | 44634 | 1400/12/23 | CM-C3 | [6 empty] | 1400-2294-424206 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0034_D00
3 | 2 | 3 | 2 | 2 | 3 | 5 | 3.2.3.2.2.3.5 | BK-GCS-PEDCO-120-ME-DT-0035 | Mechanical Data Sheets For Glycol Drain Pump |  | BK-GCS-PEDCO-120-ME-DT-0035 | BK-GCS-PEDCO-120-ME-DT-0035 | BK | GCS | PEDCO | 120 | ME | DT | 0035 | F0Z-708863 | AFC | IFC | 2021-12-22 | 2021-12-30 | 2022-01-05 | 8 | 6 | 14 | IFA | 2022-02-01 | 2022-02-24 | 2022-03-02 | 23 | 6 | 29 | IFA | 2022-03-21 | 2022-05-08 | 2022-05-11 | 48 | 3 | 51 | AFC | 2022-09-21 | 0 | 0 | -44825 | 0 | -44825 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-12-08 | 2022-09-07 |  | D03 | AFC | T-1373 | 44811 | 1401/06/16 | T-1373 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05827 | 44807 | 1401/07/11 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0035_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0319 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-342155 | 2021-12-30 | 1400/10/09 | 44566 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0476 | 44579 | 1400/10/28 | [13 empty] | 1400-2294-424206 | 44616 | 1400/12/05 | 44622 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0035_D00 | [9 empty] | D02 | IFA | T-0694 | 44627 | 1400/12/16 |  |  |  | BK-SUR-ENG-MEC-00-03398 | 44628 | 1400/12/17 | CM-C3 | [6 empty] | 1401-2294-52759 | 44689 | 1401/02/18 | 44692 | 1401/02/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0035_D01 | [9 empty] | D03 | AFC | T-1373 | 44811 | 1401/06/16 | T-1373 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05827 | 44807 | 1401/07/11 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0035_D02
3 | 2 | 3 | 2 | 2 | 3 | 0 | 3.2.2.2.3 |  | Packaged Equipment | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 2 | 2 | 3 | 1 | 3.2.3.2.2.3.1 | BK-GCS-PEDCO-120-ME-DT-0031 | Mechanical Data Sheets For Gas Compressors Packages |  | BK-GCS-PEDCO-120-ME-DT-0031 | BK-GCS-PEDCO-120-ME-DT-0031 | BK | GCS | PEDCO | 120 | ME | DT | 0031 | F0Z-708864 | AFC | IFC | 2021-09-26 | 2021-10-07 | 2021-10-11 | 11 | 4 | 15 | IFA | 2021-10-31 | 2021-11-04 | 2021-11-08 | 4 | 4 | 8 | IFA | 2021-11-28 | 2021-12-14 | 2021-12-20 | 16 | 6 | 22 | IFA | 2022-01-26 | 2022-02-22 | 2022-02-22 | 27 | 0 | 27 | IFA | 2022-03-19 | 2022-03-23 | 2022-03-26 | 4 | 3 | 7 | AFC | 2022-05-04 | 2022-04-28 | 2022-05-01 | -6 | 3 | -3 | [7 empty] | Modify | 2021-09-12 |  |  | D06 | AFC | T-0913 | 44689 | 1401/02/18 | T-0913 | 44689 | 1401/02/18 | BK-SUR-ENG-MEC-01-04470 | 44710 | 1401/03/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70331 | 44702 | 1401/02/31 | 44705 | 1401/03/03 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D05 | 1401-2294-91109 | 44719 | 1401/03/17 | 44721 | 1401/03/19 | CM | 0 | 0 |  | D00 | IFC | T-0088 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ROE-00-01647 | 44471 | 1400/07/10 | RJ-C4 | [6 empty] | 1400-2290-225541 | 2021-10-07 | 1400/07/15 | 44480 | 1400/07/19 | CM | [10 empty] | D01 | IFA | T-0164 | 44486 | 1400/07/25 |  |  |  | BK-SUR-ENG-ROE-00-01848 | 44495 | 1400/08/04 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D00 | [5 empty] | 1400-2294-261501 | 44504 | 1400/08/13 | 44508 | 1400/08/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D00 | [9 empty] | D02 | IFA | T-0233 | 44514 | 1400/08/23 |  |  |  | BK-SUR-ENG-ROE-00-02100 | 44527 | 1400/09/06 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D01 | [5 empty] | 1400-2294-318813 | 44544 | 1400/09/23 | 44550 | 1400/09/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D01 | [9 empty] | D03 | IFA | T-0454 | 44573 | 1400/10/22 |  |  |  | BK-SUR-ENG-MEC-00-02857 | 44591 | 1400/11/10 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D02 | [5 empty] | 1400-2294-421701 | 44614 | 1400/12/03 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D02 | [9 empty] | D04 | IFA | T-0675 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-MEC-00-03410 | 44628 | 1400/12/17 | CM-C3 | [6 empty] | 1401-2294-1309 | 44643 | 1401/01/06 | 44646 | 1401/01/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D03 | [9 empty] | D05 | AFC | T-0818 | 44671 | 1401/01/31 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D04 | [5 empty] | 1401-2299-33757 | 44673 | 1401/02/02 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D04 | 1401-2294-43097 | 44679 | 1401/02/08 | 1-M1Y-2022 | 1401/02/11 | AP |  |  |  | D06 | AFC | T-0913 | 44689 | 1401/02/18 | T-0913 | 44689 | 1401/02/18 | BK-SUR-ENG-MEC-01-04470 | 44710 | 1401/03/08 | AP | [6 empty] | 1401-2294-70331 | 44702 | 1401/02/31 | 44705 | 1401/03/03 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D05 | 1401-2294-91109 | 44719 | 1401/03/17 | 44721 | 1401/03/19 | CM
3 | 2 | 3 | 3 | 0 | 0 | 0 | 3.2.3.3 |  | HVAC/Plumbing
3 | 2 | 3 | 3 | 1 | 0 | 0 | 3.2.3.3.1 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 3 | 1 | 0 | 1 | 3.2.3.3.1 | BK-GCS-PEDCO-120-HV-CN-0001 | HVAC Calculation Note For Control Building |  | BK-GCS-PEDCO-120-HV-CN-0001 | BK-GCS-PEDCO-120-HV-CN-0001 | BK | GCS | PEDCO | 120 | HV | CN | 0001 | F0Z-708865 | AFD | IFC | 2022-04-13 | 2022-04-17 | 2022-04-25 | 4 | 8 | 12 | IFA | 2022-08-02 | 2022-08-10 | 2022-08-15 | 8 | 5 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-30 |  |  | D01 | IFA | T-1171 | 44761 | 1401/04/28 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-05291 | 44773 | 1401/05/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-HV-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-172242 | 44783 | 1401/05/19 | 44788 | 1401/05/24 | AP | NISOK-CRS-BK-GCS-PEDCO-120-HV-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0767 | 2022-03-30 | 1401/01/10 |  |  |  | BK-SUR-ENG-HVC-01-03862 | 44662 | 1401/01/22 | CM-C3 | [6 empty] | 1401-2294-27253 | 2022-04-17 | 1401/01/28 | 44676 | 1401/02/05 | CM | [10 empty] | D01 | IFA | T-1171 | 44761 | 1401/04/28 |  |  |  | BK-SUR-ENG-HVC-01-05291 | 44773 | 1401/05/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-HV-CN-0001_D01 | [5 empty] | 1401-2294-172242 | 44783 | 1401/05/19 | 44788 | 1401/05/24 | AP | NISOK-CRS-BK-GCS-PEDCO-120-HV-CN-0001_D01
3 | 2 | 3 | 3 | 1 | 0 | 2 | 3.2.3.3.1 | BK-GCS-PEDCO-120-HV-CN-0002 | HVAC Calculation Note For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-HV-CN-0002 | BK-GCS-PEDCO-120-HV-CN-0002 | BK | GCS | PEDCO | 120 | HV | CN | 0002 | F0Z-708866 | AFD | IFC | 2022-06-20 | 2022-06-11 | 2022-06-14 | -9 | 3 | -6 | IFA | 2022-10-10 | 0 | 0 | -44844 | 0 | -44844 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-06 |  |  | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-HV-CN-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-HV-CN-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1038 | 2022-06-06 | 1401/03/16 | T-1038 | 44719 | 1401/03/17 | BK-SUR-ENG-HVC-01-04923 | 44741 | 1401/04/08 | CM-C2 | [6 empty] | 1401-2294-96491 | 2022-06-11 | 1401/03/21 | 44726 | 1401/03/24 | CM | [10 empty] | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-HV-CN-0002_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-HV-CN-0002_D00
3 | 2 | 3 | 3 | 2 | 0 | 0 | 3.2.3.3.2 |  | Data Sheets
3 | 2 | 3 | 3 | 2 | 0 | 1 | 3.2.3.3.2 | BK-GCS-PEDCO-120-HV-DT-0001 | Data Sheets For Main HVAC Equipment of Control Building |  | BK-GCS-PEDCO-120-HV-DT-0001 | BK-GCS-PEDCO-120-HV-DT-0001 | BK | GCS | PEDCO | 120 | HV | DT | 0001 | F0Z-708867 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 3 | 2 | 0 | 2 | 3.2.3.3.2 | BK-GCS-PEDCO-120-HV-DT-0002 | Data Sheets For Main HVAC Equipment of Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-HV-DT-0002 | BK-GCS-PEDCO-120-HV-DT-0002 | BK | GCS | PEDCO | 120 | HV | DT | 0002 | F0Z-708868 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 3 | 3 | 0 | 0 | 3.2.3.3.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 3 | 3 | 0 | 1 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-PY-0001 | Plumbing & Sewage Piping Layout For Control Building |  | BK-GCS-PEDCO-120-HV-PY-0001 | BK-GCS-PEDCO-120-HV-PY-0001 | BK | GCS | PEDCO | 120 | HV | PY | 0001 | F4B-708869 | AFC | IFC | 2022-06-21 | 2022-09-27 | 2022-09-27 | 98 | 0 | 98 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-07 |  |  | D00 | IFC | T-1051 | 44719 | 1401/03/17 | T-1051 | 44720 | 1401/03/18 | BK-SUR-ENG-HVC-01-04921 | 44741 | 1401/04/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156737 | 44831 | 1401/05/05 | 44831 | 1401/05/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1051 | 2022-06-07 | 1401/03/17 | T-1051 | 44720 | 1401/03/18 | BK-SUR-ENG-HVC-01-04921 | 44741 | 1401/04/08 | CM-C2 | [6 empty] | 1401-2294-156737 | 2022-09-27 | 1401/05/05 | 44831 | 1401/05/05 | CM
3 | 2 | 3 | 3 | 3 | 0 | 2 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-DG-0001 | HVAC Flow Diagram For Control Building |  | BK-GCS-PEDCO-120-HV-DG-0001 | BK-GCS-PEDCO-120-HV-DG-0001 | BK | GCS | PEDCO | 120 | HV | DG | 0001 | F4A-708870 | AFC | IFC | 2022-06-25 | 2022-06-29 | 2022-07-05 | 4 | 6 | 10 | IFA | 2022-08-06 | 2022-08-09 | 2022-08-13 | 3 | 4 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-11 |  |  | D01 | IFA | T-1181 | 44765 | 1401/05/01 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-05296 | 44773 | 1401/05/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-HV-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171155 | 44782 | 1401/05/18 | 44786 | 1401/05/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-HV-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1056 | 2022-06-11 | 1401/03/21 | T-1056 | 44723 | 1401/03/21 | BK-SUR-ENG-HVC-01-04918 | 44741 | 1401/04/08 | AP | [6 empty] | 1401-2294-122267 | 2022-06-29 | 1401/04/08 | 44747 | 1401/04/14 | CM | [10 empty] | D01 | IFA | T-1181 | 44765 | 1401/05/01 |  |  |  | BK-SUR-ENG-HVC-01-05296 | 44773 | 1401/05/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-HV-DG-0001_D00 | [5 empty] | 1401-2294-171155 | 44782 | 1401/05/18 | 44786 | 1401/05/22 | CM | NISOC-CRS-BK-GCS-PEDCO-120-HV-DG-0001_D00
3 | 2 | 3 | 3 | 3 | 0 | 3 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-PY-0002 | HVAC Room Layout & Section For Control Building |  | BK-GCS-PEDCO-120-HV-PY-0002 | BK-GCS-PEDCO-120-HV-PY-0002 | BK | GCS | PEDCO | 120 | HV | PY | 0002 | F4B-708871 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 3 | 3 | 0 | 4 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-PY-0003 | HVAC System Duct Plan For Control Building |  | BK-GCS-PEDCO-120-HV-PY-0003 | BK-GCS-PEDCO-120-HV-PY-0003 | BK | GCS | PEDCO | 120 | HV | PY | 0003 | F4B-708872 | AFC | IFC | 2022-08-03 | 2022-08-18 | 2022-09-03 | 15 | 16 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-07-20 |  |  | D00 | IFC | T-1175 | 44762 | 1401/04/29 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-05295 | 44773 | 1401/05/09 | CM-C3 | 0 | BK-SUR-ENG-HVC-01-05313 | 44774 | 1401/05/11 | CM | 0 | 1401-2294-183554 | 44791 | 1401/05/27 | 44807 | 1401/06/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1175 | 2022-07-20 | 1401/04/29 |  |  |  | BK-SUR-ENG-HVC-01-05295 | 44773 | 1401/05/09 | CM-C3 |  | BK-SUR-ENG-HVC-01-05313 | 44774 | 1401/05/11 | CM |  | 1401-2294-183554 | 2022-08-18 | 1401/05/27 | 44807 | 1401/06/12 | CM
3 | 2 | 3 | 3 | 3 | 0 | 5 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-PY-0004 | HVAC System Roof Layout For Control Building |  | BK-GCS-PEDCO-120-HV-PY-0004 | BK-GCS-PEDCO-120-HV-PY-0004 | BK | GCS | PEDCO | 120 | HV | PY | 0004 | F4B-708873 | AFC | IFC | 2022-11-06 | 2022-11-03 | 2022-11-07 | -3 | 4 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-23 |  |  | D00 | IFC | T-1531 | 44857 | 1401/08/01 | T-1531 | 44857 | 1401/08/01 | BK-SUR-ENG-HVC-01-05964 | 44858 | 1401/08/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294267 | 44868 | 1401/08/12 | 44872 | 1401/08/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1531 | 2022-10-23 | 1401/08/01 | T-1531 | 44857 | 1401/08/01 | BK-SUR-ENG-HVC-01-05964 | 44858 | 1401/08/02 | CM-C3 | [6 empty] | 1401-2294-294267 | 2022-11-03 | 1401/08/12 | 44872 | 1401/08/16 | CM
3 | 2 | 3 | 3 | 3 | 0 | 6 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-DG-0002 | HVAC I&C Diagram For Control Building |  | BK-GCS-PEDCO-120-HV-DG-0002 | BK-GCS-PEDCO-120-HV-DG-0002 | BK | GCS | PEDCO | 120 | HV | DG | 0002 | F4B-708874 | AFC | IFC | 2022-08-03 | 2022-08-18 | 2022-09-03 | 15 | 16 | 31 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-20 |  |  | D00 | IFC | T-1175 | 44762 | 1401/04/29 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-05295 | 44773 | 1401/05/09 | CM-C3 | 0 | BK-SUR-ENG-HVC-01-05313 | 44774 | 1401/05/11 | CM | 0 | 1401-2294-183554 | 44791 | 1401/05/27 | 44807 | 1401/06/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1175 | 2022-07-20 | 1401/04/29 |  |  |  | BK-SUR-ENG-HVC-01-05295 | 44773 | 1401/05/09 | CM-C3 |  | BK-SUR-ENG-HVC-01-05313 | 44774 | 1401/05/11 | CM |  | 1401-2294-183554 | 2022-08-18 | 1401/05/27 | 44807 | 1401/06/12 | CM
3 | 2 | 3 | 3 | 3 | 0 | 7 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-PY-0005 | Plumbing & Sewage Piping Layout For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-HV-PY-0005 | [8 empty] | F4B-708875 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 3 | 3 | 0 | 8 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-DG-0003 | HVAC Flow Diagram For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-HV-DG-0003 | BK-GCS-PEDCO-120-HV-DG-0003 | BK | GCS | PEDCO | 120 | HV | DG | 0003 | F4A-708876 | AFC | IFC | 2022-06-21 | 2022-09-27 | 2022-09-27 | 98 | 0 | 98 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1051 | 44719 | 1401/03/17 | T-1051 | 44719 | 1401/03/17 | BK-SUR-ENG-HVC-01-04921 | 44741 | 1401/04/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156737 | 44831 | 1401/05/05 | 44831 | 1401/05/05 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1051 | 2022-06-07 | 1401/03/17 | T-1051 | 44719 | 1401/03/17 | BK-SUR-ENG-HVC-01-04921 | 44741 | 1401/04/08 | CM-C2 | [6 empty] | 1401-2294-156737 | 2022-09-27 | 1401/05/05 | 44831 | 1401/05/05 | RJ
3 | 2 | 3 | 3 | 3 | 0 | 9 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-PY-0006 | HVAC System Layout & Section For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-HV-PY-0006 | BK-GCS-PEDCO-120-HV-PY-0006 | BK | GCS | PEDCO | 120 | HV | PY | 0006 | F4B-708877 | AFC | IFC | 2022-06-21 | 2022-09-27 | 2022-09-27 | 98 | 0 | 98 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1051 | 44719 | 1401/03/17 | T-1051 | 44719 | 1401/03/17 | BK-SUR-ENG-HVC-01-04921 | 44741 | 1401/04/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156737 | 44831 | 1401/05/05 | 44831 | 1401/05/05 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1051 | 2022-06-07 | 1401/03/17 | T-1051 | 44719 | 1401/03/17 | BK-SUR-ENG-HVC-01-04921 | 44741 | 1401/04/08 | CM-C2 | [6 empty] | 1401-2294-156737 | 2022-09-27 | 1401/05/05 | 44831 | 1401/05/05 | RJ
3 | 2 | 3 | 3 | 3 | 0 | 10 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-PY-0007 | HVAC System Duct Plan For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-HV-PY-0007 | [8 empty] | F4B-708878 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 3 | 3 | 0 | 11 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-PY-0008 | HVAC System Roof Layout For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-HV-PY-0008 | BK-GCS-PEDCO-120-HV-PY-0008 | BK | GCS | PEDCO | 120 | HV | PY | 0008 | F4B-708879 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 3 | 3 | 0 | 12 | 3.2.3.3.3 | BK-GCS-PEDCO-120-HV-DG-0004 | HVAC I&C Diagram For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-HV-DG-0004 | BK-GCS-PEDCO-120-HV-DG-0004 | BK | GCS | PEDCO | 120 | HV | DG | 0004 | F4B-708880 | AFC | IFC | 2022-06-25 | 2022-06-20 | 2022-06-27 | -5 | 7 | 2 | IFA | 2022-10-10 | 0 | 0 | -44844 | 0 | -44844 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-11 |  |  | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-HV-DG-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-HV-DG-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1058 | 2022-06-11 | 1401/03/21 | T-1058 | 44723 | 1401/03/21 | BK-SUR-ENG-HVC-01-04922 | 44741 | 1401/04/08 | CM-C2 | [6 empty] | 1401-2294-109179 | 2022-06-20 | 1401/03/30 | 44739 | 1401/04/06 | CM | [10 empty] | D01 | IFA | T-1441 | 44830 | 1401/07/04 | T-1441 | 44830 | 1401/07/04 | BK-SUR-ENG-HVC-01-05780 | 44836 | 1401/07/10 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-HV-DG-0004_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-HV-DG-0004_D00
3 | 2 | 3 | 3 | 4 | 0 | 0 | 3.2.3.3.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 3 | 4 | 0 | 1 | 3.2.3.3 | BK-GCS-PEDCO-120-HV-MT-0001 | MTO For HVAC & Plumbing For Control Building |  | BK-GCS-PEDCO-120-HV-MT-0001 | BK-GCS-PEDCO-120-HV-MT-0001 | BK | GCS | PEDCO | 120 | HV | MT | 0001 | F8Z-708881 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 3 | 4 | 0 | 2 | 3.2.3.3 | BK-GCS-PEDCO-120-HV-MT-0002 | MTO For HVAC & Plumbing For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-HV-MT-0002 | BK-GCS-PEDCO-120-HV-MT-0002 | BK | GCS | PEDCO | 120 | HV | MT | 0002 | F8Z-708882 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 4 | 0 | 0 | 0 | 3.2.3.4 |  | Piping | [61 empty] | Deleted
3 | 2 | 3 | 4 | 1 | 0 | 0 | 3.2.3.4.1 |  | Specification | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 4 | 1 | 0 | 1 | 3.2.3.4.1 | BK-GCS-PEDCO-120-PI-SP-0001 | Piping Material Specification |  | BK-GCS-PEDCO-120-PI-SP-0001 | BK-GCS-PEDCO-120-PI-SP-0001 | BK | GCS | PEDCO | 120 | PI | SP | 0001 | F0Z-708883 | AFD | IFC | 2021-12-20 | 0 | 0 | -44550 | 0 | -44550 | IFA | 2022-03-20 | 2022-01-17 | 2022-04-19 | -62 | 92 | 30 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-06 |  |  | D02 | IFA | T-1476 | 44844 | 1401/07/18 | T-1476 | 44844 | 1401/07/18 | BK-SUR-ENG-PIP-01-05962 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0295 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02466 | 44557 | 1400/10/06 | CM-C2 | [22 empty] | D01 | IFA | T-0677 | 44626 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 44634 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D00 | [5 empty] | 1401-2294-27248 | 44578 | 1401/01/28 | 44670 | 1401/01/30 | CM | NOSIC-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D00 | [9 empty] | D02 | IFA | T-1476 | 44844 | 1401/07/18 | T-1476 | 44844 | 1401/07/18 | BK-SUR-ENG-PIP-01-05962 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D01
3 | 2 | 3 | 4 | 2 | 0 | 0 | 3.2.3.4.2 |  | Data Sheets
3 | 2 | 3 | 4 | 2 | 0 | 1 | 3.2.3.4.2 | BK-GCS-PEDCO-120-PI-DT-0001 | Data Sheets For Strainers |  | BK-GCS-PEDCO-120-PI-DT-0001 | BK-GCS-PEDCO-120-PI-DT-0001 | BK | GCS | PEDCO | 120 | PI | DT | 0001 | F0Z-708884 | AFC | IFC | 2022-07-02 | 2022-07-27 | 2022-07-31 | 25 | 4 | 29 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-18 |  |  | D00 | IFC | T-1086 | 44730 | 1401/03/28 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04992 | 44747 | 1401/04/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156732 | 44769 | 1401/05/05 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1086 | 2022-06-18 | 1401/03/28 |  |  |  | BK-SUR-ENG-PIP-01-04992 | 44747 | 1401/04/14 | CM-C3 | [6 empty] | 1401-2294-156732 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM
3 | 2 | 3 | 4 | 2 | 0 | 2 | 3.2.3.4.2 | BK-GCS-PEDCO-120-PI-DT-0002 | Data Sheets For Manual valves |  | BK-GCS-PEDCO-120-PI-DT-0002 | BK-GCS-PEDCO-120-PI-DT-0002 | BK | GCS | PEDCO | 120 | PI | DT | 0002 | F0Z-708885 | AFC | IFC | 2022-08-02 | 2022-09-01 | 2022-09-04 | 30 | 3 | 33 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-19 |  |  | D00 | IFC | T-1172 | 44761 | 1401/04/28 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05261 | 44768 | 1401/05/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205810 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1172 | 2022-07-19 | 1401/04/28 |  |  |  | BK-SUR-ENG-PIP-01-05261 | 44768 | 1401/05/04 | CM-C3 | [6 empty] | 1401-2294-205810 | 2022-09-01 | 1401/06/10 | 44808 | 1401/06/13 | CM
3 | 2 | 3 | 4 | 2 | 0 | 3 | 3.2.3.4.2 | BK-GCS-PEDCO-120-PI-DT-0003 | Data Sheets and MTO For Piping Special Items |  | BK-GCS-PEDCO-120-PI-DT-0003 | BK-GCS-PEDCO-120-PI-DT-0003 | BK | GCS | PEDCO | 120 | PI | DT | 0003 | F0Z-708886 | AFC | IFC | 2022-07-12 | 2022-08-02 | 2022-08-06 | 21 | 4 | 25 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-28 |  |  | D00 | IFC | T-1128 | 44740 | 1401/04/08 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05050 | 44753 | 1401/04/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-165005 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1128 | 2022-06-28 | 1401/04/08 |  |  |  | BK-SUR-ENG-PIP-01-05050 | 44753 | 1401/04/20 | CM-C3 | [6 empty] | 1401-2294-165005 | 2022-08-02 | 1401/05/11 | 44779 | 1401/05/15 | CM
3 | 2 | 3 | 4 | 2 | 0 | 4 | 3.2.3.4.2 | BK-GCS-PEDCO-120-PI-DT-0004 | Data Sheets For Special Pipe Supports |  | BK-GCS-PEDCO-120-PI-DT-0004 | BK-GCS-PEDCO-120-PI-DT-0004 | BK | GCS | PEDCO | 120 | PI | DT | 0004 | F0Z-708887 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 2 | 0 | 5 | 3.2.3.4.2 | BK-GCS-PEDCO-120-PI-DT-0005 | Data Sheets For Piping Insulation Joints |  | BK-GCS-PEDCO-120-PI-DT-0005 | BK-GCS-PEDCO-120-PI-DT-0005 | BK | GCS | PEDCO | 120 | PI | DT | 0005 | F0Z-708888 | AFC | IFC | 2022-06-20 | 2022-06-26 | 2022-06-29 | 6 | 3 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-06 |  |  | D00 | IFC | T-1043 | 44718 | 1401/03/16 | T-1043 | 44719 | 1401/03/17 | BK-SUR-ENG-PIP-01-04774 | 44732 | 1401/03/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-118082 | 44738 | 1401/04/05 | 44741 | 1401/04/08 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1043 | 2022-06-06 | 1401/03/16 | T-1043 | 44719 | 1401/03/17 | BK-SUR-ENG-PIP-01-04774 | 44732 | 1401/03/30 | CM-C2 | [6 empty] | 1401-2294-118082 | 2022-06-26 | 1401/04/05 | 44741 | 1401/04/08 | CM
3 | 2 | 3 | 4 | 2 | 0 | 6 | 3.2.3.4.2 | BK-GCS-PEDCO-120-PI-DT-0006 | Data Sheets For Expansion Joints |  | BK-GCS-PEDCO-120-PI-DT-0006 | BK-GCS-PEDCO-120-PI-DT-0006 | BK | GCS | PEDCO | 120 | PI | DT | 0006 | F0Z-708889 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 3 | 0 | 0 | 3.2.3.4.3 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 4 | 3 | 0 | 1 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-PY-0001 | Unit Plot Plan Drawing |  | BK-GCS-PEDCO-120-PI-PY-0001 | BK-GCS-PEDCO-120-PI-PY-0001 | BK | GCS | PEDCO | 120 | PI | PY | 0001 | F5A-708890 | AFC | IFC | 2021-09-26 | 2021-10-13 | 2021-10-12 | 17 | -1 | 16 | IFA | 2021-12-14 | 2021-12-20 | 2021-12-21 | 6 | 1 | 7 | IFA | 2022-02-05 | 2022-02-24 | 2022-02-28 | 19 | 4 | 23 | AFC | 2022-10-26 | 0 | 0 | -44860 | 0 | -44860 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-12 | 2022-10-12 |  | D03 | AFC | T-1489 | 44846 | 1401/07/20 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05958 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0084 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-PIP-00-01607 | 44465 | 1400/07/04 | CM-C3 | [6 empty] | 1400-2290-225538 | 2021-10-07 | 1400/07/15 | 44481 | 1400/07/20 | CM |  | 1400-2294-234196 | 44482 | 1400/07/21 |  |  | CM |  |  |  | D01 | IFA | T-0283 | 44530 | 1400/09/09 |  |  |  | BK-SUR-ENG-PIP-00-02237 | 44538 | 1400/09/17 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-120-PI-PY-0001-D00 | [5 empty] | 1400-2294-327388 | 44550 | 1400/09/29 | 44551 | 1400/09/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PI-PY-0001-D00 | [9 empty] | D02 | IFA | T-0491 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-PIP-00-02796 | 44585 | 1400/11/04 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D01 | [5 empty] | 1400-2294-424188 | 44616 | 1400/12/05 | 44620 | 1400/12/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D01 | [9 empty] | D03 | AFC | T-1489 | 44846 | 1401/07/20 |  |  |  | BK-SUR-ENG-PIP-01-05958 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D02
3 | 2 | 3 | 4 | 3 | 0 | 2 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DW-0001 | Standard Pipe Support Drawings |  | BK-GCS-PEDCO-120-PI-DW-0001 | BK-GCS-PEDCO-120-PI-DW-0001 | BK | GCS | PEDCO | 120 | PI | DW | 0001 | F1L-708891 | IFI | IFI | 2022-06-25 | 2022-07-28 | 2022-07-31 | 33 | 3 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-11 |  |  | D00 | IFI | T-1057 | 44723 | 1401/03/21 | T-1057 | 44723 | 1401/03/21 | BK-SUR-ENG-PIP-01-04777 | 44732 | 1401/03/30 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156912 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1057 | 2022-06-11 | 1401/03/21 | T-1057 | 44723 | 1401/03/21 | BK-SUR-ENG-PIP-01-04777 | 44732 | 1401/03/30 | CM-C3 | [6 empty] | 1401-2294-156912 | 2022-07-28 | 1401/05/06 | 44773 | 1401/05/09 | CM
3 | 2 | 3 | 4 | 3 | 0 | 3 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DW-0002 | Piping Assembly Drawing |  | BK-GCS-PEDCO-120-PI-DW-0002 | BK-GCS-PEDCO-120-PI-DW-0002 | BK | GCS | PEDCO | 120 | PI | DW | 0002 | F1L-708892 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 3 | 0 | 4 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DW-0003 | Piping Key Plan |  | BK-GCS-PEDCO-120-PI-DW-0003 | BK-GCS-PEDCO-120-PI-DW-0003 | BK | GCS | PEDCO | 120 | PI | DW | 0003 | F5L-708893 | AFC | IFC | 2022-06-28 | 2022-07-10 | 2022-07-30 | 12 | 20 | 32 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-14 |  |  | D00 | IFC | T-1074 | 44726 | 1401/03/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04896 | 44739 | 1401/04/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-135314 | 44752 | 1401/04/19 | 44772 | 1401/05/08 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1074 | 2022-06-14 | 1401/03/24 |  |  |  | BK-SUR-ENG-PIP-01-04896 | 44739 | 1401/04/06 | CM-C2 | [6 empty] | 1401-2294-135314 | 2022-07-10 | 1401/04/19 | 44772 | 1401/05/08 | CM
3 | 2 | 3 | 4 | 3 | 0 | 5 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DW-0004 | A/G Piping Plan |  | BK-GCS-PEDCO-120-PI-DW-0004 | BK-GCS-PEDCO-120-PI-DW-0004 | BK | GCS | PEDCO | 120 | PI | DW | 0004 | F4L-708894 | AFC | IFC | 2022-09-03 | 2022-09-10 | 2022-09-13 | 7 | 3 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1288 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05515 | 44796 | 1401/06/01 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-218274 | 44814 | 1401/06/19 | 44817 | 1401/06/23 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1288 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-PIP-01-05515 | 44796 | 1401/06/01 | CM-C3 | [6 empty] | 1401-2294-218274 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/23 | RJ
3 | 2 | 3 | 4 | 3 | 0 | 6 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DW-0005 | U/G Piping Plan |  | BK-GCS-PEDCO-120-PI-DW-0005 | BK-GCS-PEDCO-120-PI-DW-0005 | BK | GCS | PEDCO | 120 | PI | DW | 0005 | F4L-708895 | AFC | IFC | 2022-07-16 | 2022-07-10 | 2022-07-12 | -6 | 2 | -4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-02 |  |  | D00 | IFC | T-1133 | 44744 | 1401/04/11 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05004 | 44747 | 1401/04/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-135292 | 44752 | 1401/04/19 | 44754 | 1401/04/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1133 | 2022-07-02 | 1401/04/11 |  |  |  | BK-SUR-ENG-PIP-01-05004 | 44747 | 1401/04/14 | CM-C3 | [6 empty] | 1401-2294-135292 | 2022-07-10 | 1401/04/19 | 44754 | 1401/04/21 | CM
3 | 2 | 3 | 4 | 3 | 0 | 7 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DW-0006 | A/G Piping Isometric |  | BK-GCS-PEDCO-120-PI-DW-0006 | BK-GCS-PEDCO-120-PI-DW-0006 | BK | GCS | PEDCO | 120 | PI | DW | 0006 | F2L-708896 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 3 | 0 | 8 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DW-0007 | U/G Piping Isometric |  | BK-GCS-PEDCO-120-PI-DW-0007 | BK-GCS-PEDCO-120-PI-DW-0007 | BK | GCS | PEDCO | 120 | PI | DW | 0007 | F2L-708897 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 3 | 0 | 9 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DW-0008 | Overall Plot Plan Drawing |  | BK-GCS-PEDCO-120-PI-DW-0008 | [8 empty] | F5A-708898 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 3 | 0 | 10 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DW-0009 | Special Pipe Support Drawings |  | BK-GCS-PEDCO-120-PI-DW-0009 | BK-GCS-PEDCO-120-PI-DW-0009 | BK | GCS | PEDCO | 120 | PI | DW | 0009 | F1L-708899 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 3 | 0 | 11 | 3.2.3.4.3 | BK-GCS-PEDCO-120-PI-DG-0001 | Material flow Diagram |  | BK-GCS-PEDCO-120-PI-DG-0001 | BK-GCS-PEDCO-120-PI-DG-0001 | BK | GCS | PEDCO | 120 | PI | DG | 0001 | F2A-708900 | AFC | IFC | 2022-05-25 | 2022-06-30 | 2022-07-05 | 36 | 5 | 41 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-11 |  |  | D00 | IFC | T-0934 | 44692 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04380 | 44704 | 1401/03/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-124157 | 44742 | 1401/04/09 | 44747 | 1401/04/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0934 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04380 | 44704 | 1401/03/02 | CM-C3 | [6 empty] | 1401-2294-124157 | 2022-06-30 | 1401/04/09 | 44747 | 1401/04/14 | CM
3 | 2 | 3 | 4 | 4 | 0 | 0 | 3.2.3.4.4 |  | Procedure/Plan | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 4 | 4 | 0 | 1 | 3.2.3.4.4 | BK-GCS-PEDCO-120-PI-DW-0010 | Piping Hydrostatic Test Diagram - GCS |  | BK-GCS-PEDCO-120-PI-DW-0010 | BK-GCS-PEDCO-120-PI-DW-0010 | BK | GCS | PEDCO | 120 | PI | DW | 0010 | F2L-708901 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 5 | 0 | 0 | 3.2.3.4.5 |  | List
3 | 2 | 3 | 4 | 5 | 0 | 1 | 3.2.3.4.5 | BK-GCS-PEDCO-120-PI-LI-0001 | Critical Line List |  | BK-GCS-PEDCO-120-PI-LI-0001 | BK-GCS-PEDCO-120-PI-LI-0001 | BK | GCS | PEDCO | 120 | PI | LI | 0001 | F0Z-708902 | AFC | IFC | 2022-06-11 | 2022-06-21 | 2022-07-02 | 10 | 11 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-28 |  |  | D00 | IFC | T-1009 | 44709 | 1401/03/07 | T-1009 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04516 | 44713 | 1401/03/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-111570 | 44733 | 1401/03/31 | 44744 | 1401/04/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1009 | 2022-05-28 | 1401/03/07 | T-1009 | 44709 | 1401/03/07 | BK-SUR-ENG-PIP-01-04516 | 44713 | 1401/03/11 | CM-C3 | [6 empty] | 1401-2294-111570 | 2022-06-21 | 1401/03/31 | 44744 | 1401/04/11 | CM
3 | 2 | 3 | 4 | 5 | 0 | 2 | 3.2.3.4.5 | BK-GCS-PEDCO-120-PI-LI-0002 | Pipe Support List |  | BK-GCS-PEDCO-120-PI-LI-0002 | BK-GCS-PEDCO-120-PI-LI-0002 | BK | GCS | PEDCO | 120 | PI | LI | 0002 | F0Z-708903 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 5 | 0 | 3 | 3.2.3.4.5 | BK-GCS-PEDCO-120-PI-LI-0003 | Piping Tie-In Schedule List |  | BK-GCS-PEDCO-120-PI-LI-0003 | BK-GCS-PEDCO-120-PI-LI-0003 | BK | GCS | PEDCO | 120 | PI | LI | 0003 | F0Z-708904 | AFC | IFC | 2022-09-05 | 2022-09-12 | 2022-09-13 | 7 | 1 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-22 |  |  | D00 | IFC | T-1301 | 44795 | 1401/05/31 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05601 | 44809 | 1401/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-221115 | 44816 | 1401/06/21 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1301 | 2022-08-22 | 1401/05/31 |  |  |  | BK-SUR-ENG-PIP-01-05601 | 44809 | 1401/06/14 | CM-C3 | [6 empty] | 1401-2294-221115 | 2022-09-12 | 1401/06/21 | 44817 | 1401/06/22 | CM
3 | 2 | 3 | 4 | 6 | 0 | 0 | 3.2.3.4.6 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 4 | 6 | 0 | 1 | 3.2.3.4.6 | BK-GCS-PEDCO-120-PI-RT-0001 | Piping Corrosion Study & Material Selection Report |  | BK-GCS-PEDCO-120-PI-RT-0001 | BK-GCS-PEDCO-120-PI-RT-0001 | BK | GCS | PEDCO | 120 | PI | RT | 0001 | F0Z-708905 | IFI | IFC | 2021-12-20 | 0 | 0 | -44550 | 0 | -44550 | IFA | 2022-05-21 | 2022-06-02 | 2022-06-07 | 12 | 5 | 17 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-06 |  |  | D02 | IFA | T-1476 | 44844 | 1401/07/18 | T-1476 | 44844 | 1401/07/18 | BK-SUR-ENG-PIP-01-05962 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0295 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02466 | 44557 | 1400/10/06 | CM-C2 | [22 empty] | D01 | IFA | T-0904 | 44688 | 1401/02/17 | T-0904 | 44688 | 1401/02/17 | BK-SUR-ENG-PIP-01-04580 | 44719 | 1401/03/17 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D00 | [5 empty] | 1401-2294-87483 | 44714 | 1401/03/12 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D00 | [9 empty] | D02 | IFA | T-1476 | 44844 | 1401/07/18 | T-1476 | 44844 | 1401/07/18 | BK-SUR-ENG-PIP-01-05962 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D01
3 | 2 | 3 | 4 | 6 | 0 | 2 | 3.2.3.4.6 | BK-GCS-PEDCO-120-PI-RT-0002 | Stress Analysis Calculations Report |  | BK-GCS-PEDCO-120-PI-RT-0002 | BK-GCS-PEDCO-120-PI-RT-0002 | BK | GCS | PEDCO | 120 | PI | RT | 0002 | F0Z-708906 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 6 | 0 | 3 | 3.2.3.4.6 | BK-GCS-PEDCO-120-PI-RT-0003 | PDMS Model Review Report (30%) |  | BK-GCS-PEDCO-120-PI-RT-0003 | BK-GCS-PEDCO-120-PI-RT-0003 | BK | GCS | PEDCO | 120 | PI | RT | 0003 | F0Z-708907 | IFI | IFC | 2022-04-09 | 2022-04-17 | 2022-04-25 | 8 | 8 | 16 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-26 |  |  | D00 | IFC | T-0741 | 44646 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-03858 | 44662 | 1401/01/22 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27190 | 44668 | 1401/01/28 | 44676 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0741 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-PIP-01-03858 | 44662 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-27190 | 2022-04-17 | 1401/01/28 | 44676 | 1401/02/05 | CM
3 | 2 | 3 | 4 | 6 | 0 | 4 | 3.2.3.4.6 | BK-GCS-PEDCO-120-PI-RT-0004 | PDMS Model Review Report (60%)-GCS |  | BK-GCS-PEDCO-120-PI-RT-0004 | BK-GCS-PEDCO-120-PI-RT-0004 | BK | GCS | PEDCO | 120 | PI | RT | 0004 | F0Z-708908 | IFI | IFC | 2022-07-06 | 2022-07-30 | 2022-08-01 | 24 | 2 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-22 |  |  | D00 | IFC | T-1108 | 44734 | 1401/04/01 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05111 | 44755 | 1401/04/22 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-158967 | 44772 | 1401/05/08 | 44774 | 1401/05/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1108 | 2022-06-22 | 1401/04/01 |  |  |  | BK-SUR-ENG-PIP-01-05111 | 44755 | 1401/04/22 | CM-C3 | [6 empty] | 1401-2294-158967 | 2022-07-30 | 1401/05/08 | 44774 | 1401/05/10 | AP
3 | 2 | 3 | 4 | 6 | 0 | 5 | 3.2.3.4.6 | BK-GCS-PEDCO-120-PI-RT-0005 | PDMS Model Review Report (90%) |  | BK-GCS-PEDCO-120-PI-RT-0005 | BK-GCS-PEDCO-120-PI-RT-0005 | BK | GCS | PEDCO | 120 | PI | RT | 0005 | F0Z-708909 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 6 | 0 | 6 | 3.2.3.4.6 | BK-GCS-PEDCO-120-PI-RT-0006 | Wall Thickness Calculation Report |  | BK-GCS-PEDCO-120-PI-RT-0006 | BK-GCS-PEDCO-120-PI-RT-0006 | BK | GCS | PEDCO | 120 | PI | RT | 0006 | F0Z-708910 | IFI | IFC | 2021-12-20 | 0 | 0 | -44550 | 0 | -44550 | IFA | 2022-03-20 | 2022-01-17 | 2022-04-19 | -62 | 92 | 30 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-06 |  |  | D02 | IFA | T-1476 | 44844 | 1401/07/18 | T-1476 | 44844 | 1401/07/18 | BK-SUR-ENG-PIP-01-05962 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0295 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02466 | 44557 | 1400/10/06 | CM-C2 | [22 empty] | D01 | IFA | T-0677 | 44626 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 44634 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D00 | [5 empty] | 1401-2294-27248 | 44578 | 1401/01/28 | 44670 | 1401/01/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D00 | [9 empty] | D02 | IFA | T-1476 | 44844 | 1401/07/18 | T-1476 | 44844 | 1401/07/18 | BK-SUR-ENG-PIP-01-05962 | 44858 | 1401/08/02 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D01
3 | 2 | 3 | 4 | 7 | 0 | 0 | 3.2.3.4.7 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 4 | 7 | 0 | 1 | 3.2.3.4 | BK-GCS-PEDCO-120-PI-MT-0001 | MTO For Pipes |  | BK-GCS-PEDCO-120-PI-MT-0001 | BK-GCS-PEDCO-120-PI-MT-0001 | BK | GCS | PEDCO | 120 | PI | MT | 0001 | F8Z-708911 | IFI | IFI | 2022-07-11 | 2022-07-27 | 2022-07-31 | 16 | 4 | 20 | IFI | 2022-10-31 | 2022-11-01 | 2022-11-06 | 1 | 5 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-27 |  |  | D01 | IFI | T-1507 | 44851 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05977 | 44860 | 1401/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-291189 | 44866 | 1401/08/10 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PI-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1123 | 2022-06-27 | 1401/04/06 |  |  |  | BK-SUR-ENG-PIP-01-05189 | 44759 | 1401/04/26 | CM-C3 | [6 empty] | 1401-2294-156843 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM | [10 empty] | D01 | IFI | T-1507 | 44851 | 1401/07/25 |  |  |  | BK-SUR-ENG-PIP-01-05977 | 44860 | 1401/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-MT-0001_D00 | [5 empty] | 1401-2294-291189 | 44866 | 1401/08/10 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PI-MT-0001_D00
3 | 2 | 3 | 4 | 7 | 0 | 2 | 3.2.3.4 | BK-GCS-PEDCO-120-PI-MT-0002 | MTO For Fittings |  | BK-GCS-PEDCO-120-PI-MT-0002 | BK-GCS-PEDCO-120-PI-MT-0002 | BK | GCS | PEDCO | 120 | PI | MT | 0002 | F8Z-708912 | IFI | IFI | 2022-10-25 | 2022-10-29 | 2022-10-31 | 4 | 2 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-11 |  |  | D00 | IFI | T-1483 | 44845 | 1401/07/19 | T-1483 | 44845 | 1401/07/19 | BK-SUR-ENG-PIP-01-05905 | 44850 | 1401/07/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284199 | 44863 | 1401/08/07 | 44865 | 1401/08/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1483 | 2022-10-11 | 1401/07/19 | T-1483 | 44845 | 1401/07/19 | BK-SUR-ENG-PIP-01-05905 | 44850 | 1401/07/24 | CM-C3 | [6 empty] | 1401-2294-284199 | 2022-10-29 | 1401/08/07 | 44865 | 1401/08/09 | AP
3 | 2 | 3 | 4 | 7 | 0 | 3 | 3.2.3.4 | BK-GCS-PEDCO-120-PI-MT-0003 | MTO For Flanges |  | BK-GCS-PEDCO-120-PI-MT-0003 | BK-GCS-PEDCO-120-PI-MT-0003 | BK | GCS | PEDCO | 120 | PI | MT | 0003 | F8Z-708913 | IFI | IFI | 2022-10-25 | 2022-10-29 | 2022-10-31 | 4 | 2 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-11 |  |  | D00 | IFI | T-1486 | 44845 | 1401/07/19 | T-1483 | 44845 | 1401/07/19 | BK-SUR-ENG-PIP-01-05913 | 44851 | 1401/07/25 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284203 | 44863 | 1401/08/07 | 44865 | 1401/08/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1486 | 2022-10-11 | 1401/07/19 | T-1483 | 44845 | 1401/07/19 | BK-SUR-ENG-PIP-01-05913 | 44851 | 1401/07/25 | CM-C3 | [6 empty] | 1401-2294-284203 | 2022-10-29 | 1401/08/07 | 44865 | 1401/08/09 | AP
3 | 2 | 3 | 4 | 7 | 0 | 4 | 3.2.3.4 | BK-GCS-PEDCO-120-PI-MT-0004 | MTO For Manual Valves |  | BK-GCS-PEDCO-120-PI-MT-0004 | BK-GCS-PEDCO-120-PI-MT-0004 | BK | GCS | PEDCO | 120 | PI | MT | 0004 | F8Z-708914 | IFI | IFI | 2022-10-26 | 2022-10-29 | 2022-10-31 | 3 | 2 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-12 |  |  | D00 | IFI | T-1492 | 44846 | 1401/07/20 | T-1492 | 44846 | 1401/07/20 | BK-SUR-ENG-PIP-01-05926 | 44853 | 1401/07/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284190 | 44863 | 1401/08/07 | 44865 | 1401/08/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1492 | 2022-10-12 | 1401/07/20 | T-1492 | 44846 | 1401/07/20 | BK-SUR-ENG-PIP-01-05926 | 44853 | 1401/07/27 | CM-C3 | [6 empty] | 1401-2294-284190 | 2022-10-29 | 1401/08/07 | 44865 | 1401/08/09 | AP
3 | 2 | 3 | 4 | 7 | 0 | 5 | 3.2.3.4 | BK-GCS-PEDCO-120-PI-MT-0005 | MTO For Gaskets |  | BK-GCS-PEDCO-120-PI-MT-0005 | BK-GCS-PEDCO-120-PI-MT-0005 | BK | GCS | PEDCO | 120 | PI | MT | 0005 | F8Z-708915 | IFI | IFI | 2022-07-11 | 2022-07-27 | 2022-07-31 | 16 | 4 | 20 | IFI | 2022-10-31 | 2022-11-01 | 2022-11-06 | 1 | 5 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-27 |  |  | D01 | IFI | T-1507 | 44851 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05977 | 44860 | 1401/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-MT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-291189 | 44866 | 1401/08/10 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PI-MT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1123 | 2022-06-27 | 1401/04/06 |  |  |  | BK-SUR-ENG-PIP-01-05189 | 44759 | 1401/04/26 | CM-C3 | [6 empty] | 1401-2294-156843 | 2022-07-27 | 1401/05/05 | 44773 | 1401/05/09 | CM | [10 empty] | D01 | IFI | T-1507 | 44851 | 1401/07/25 |  |  |  | BK-SUR-ENG-PIP-01-05977 | 44860 | 1401/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-MT-0005_D00 | [5 empty] | 1401-2294-291189 | 44866 | 1401/08/10 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PI-MT-0005_D00
3 | 2 | 3 | 4 | 7 | 0 | 6 | 3.2.3.4 | BK-GCS-PEDCO-120-PI-MT-0006 | MTO For Bolt & Nuts |  | BK-GCS-PEDCO-120-PI-MT-0006 | BK-GCS-PEDCO-120-PI-MT-0006 | BK | GCS | PEDCO | 120 | PI | MT | 0006 | F8Z-708916 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 7 | 0 | 7 | 3.2.3.4 | BK-GCS-PEDCO-120-PI-MT-0008 | MTO For Insulation |  | BK-GCS-PEDCO-120-PI-MT-0008 | BK-GCS-PEDCO-120-PI-MT-0008 | BK | GCS | PEDCO | 120 | PI | MT | 0008 | F8Z-708917 | IFI | IFI | 2022-08-17 | 2022-09-11 | 2022-09-13 | 25 | 2 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-03 |  |  | D00 | IFI | T-1249 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05428 | 44787 | 1401/05/23 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-220428 | 44815 | 1401/06/20 | 44817 | 1401/06/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1249 | 2022-08-03 | 1401/05/12 |  |  |  | BK-SUR-ENG-PIP-01-05428 | 44787 | 1401/05/23 | CM-C3 | [6 empty] | 1401-2294-220428 | 2022-09-11 | 1401/06/20 | 44817 | 1401/06/23 | CM
3 | 2 | 3 | 4 | 7 | 0 | 8 | 3.2.3.4 | BK-GCS-PEDCO-120-PI-MT-0009 | MTO For Painting |  | BK-GCS-PEDCO-120-PI-MT-0009 | BK-GCS-PEDCO-120-PI-MT-0009 | BK | GCS | PEDCO | 120 | PI | MT | 0009 | F8Z-708918 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 4 | 7 | 0 | 9 | 3.2.3.4 | BK-GCS-PEDCO-120-PI-MT-0010 | MTO For Coating of Underground Piping |  | BK-GCS-PEDCO-120-PI-MT-0010 | BK-GCS-PEDCO-120-PI-MT-0010 | BK | GCS | PEDCO | 120 | PI | MT | 0010 | F8Z-708919 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 5 | 0 | 0 | 0 | 3.2.3.5 |  | Control & Instrumentation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 5 | 1 | 0 | 0 | 3.2.3.5.1 |  | Basis/Criteria | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 5 | 1 | 0 | 1 | 3.2.3.5.1 | BK-GCS-PEDCO-120-IN-DB-0001 | Instrument & Control System Basis of Design |  | BK-GCS-PEDCO-120-IN-DB-0001 | [8 empty] | - |  | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 5 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-22 |  |  | D00 | IFC | T-0060 | 44430 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01427 | 44437 | 1400/06/07 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-200135 | 44454 | 1400/06/24 | 44459 | 1400/06/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0060 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-INS-00-01427 | 44437 | 1400/06/07 | CM-C3 | [6 empty] | 1400-2294-200135 | 2021-09-15 | 1400/06/24 | 44459 | 1400/06/29 | CM
3 | 2 | 3 | 5 | 1 | 0 | 2 | 3.2.3.5.1 | BK-GCS-PEDCO-120-IN-DC-0001 | Fire & Gas Detection Design Criteria |  | BK-GCS-PEDCO-120-IN-DC-0001 | BK-GCS-PEDCO-120-IN-DC-0001 | BK | GCS | PEDCO | 120 | IN | DC | 0001 | F0Z-708920 | AFD | IFC | 2021-09-13 | 2021-10-26 | 2021-10-02 | 43 | -24 | 19 | IFA | 2021-10-25 | 2021-11-21 | 2021-11-27 | 27 | 6 | 33 | IFA | 2022-01-18 | 2022-02-13 | 2022-02-13 | 26 | 0 | 26 | IFA | 2022-06-06 | 2022-08-04 | 2022-08-09 | 59 | 5 | 64 | IFA | 2022-09-17 | 2022-10-04 | 2022-10-31 | 17 | 27 | 44 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-08-30 |  |  | D04 | IFA | T-1348 | 44807 | 1401/06/12 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05712 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249326 | 44838 | 1401/07/12 | 44865 | 1401/08/08 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0071 | 2021-08-30 | 1400/06/08 | [13 empty] | 1400-2294-213820 | 2021-10-26 | 1400/07/04 | 44471 | 1400/07/10 | CM |  | 1400-2294-234028 | 44482 | 1400/07/21 |  |  | CM |  |  |  | D01 | IFA | T-0151 | 44480 | 1400/07/19 |  |  |  | BK-SUR-ENG-INS-00-01859 | 44496 | 1400/08/05 | CM-C3 | [6 empty] | 1400-2294-283466 | 44521 | 1400/08/30 | 44527 | 1400/09/06 | CM | NISOC-BK-GCS-PEDCO-120-IN-DC-0001-D00 | [9 empty] | D02 | IFA | T-0427 | 44565 | 1400/10/14 |  |  |  | BK-SUR-ENG-INS-00-02730 | 44579 | 1400/10/28 | CM-C3 | PEDCO-BK-GCS-PEDCO-120-IN-DC-0001-D01 | [5 empty] | 1400-2294-407520 | 44605 | 1400/11/24 | 44605 | 1400/11/24 | CM | NISOC-BK-GCS-PEDCO-120-IN-DC-0001-D01 | [9 empty] | D03 | IFA | T-0993 | 44704 | 1401/03/02 | T-0993 | 44704 | 1401/03/02 | BK-SUR-ENG-INS-01-04586 | 44719 | 1401/03/17 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D02 | [5 empty] | 1401-2294-167265 | 44777 | 1401/05/13 | 44782 | 1401/05/18 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D02 | [9 empty] | D04 | IFA | T-1348 | 44807 | 1401/06/12 |  |  |  | BK-SUR-ENG-INS-01-05712 | 44822 | 1401/06/27 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D03 | [5 empty] | 1401-2294-249326 | 44838 | 1401/07/12 | 44865 | 1401/08/08 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D03
3 | 2 | 3 | 5 | 1 | 0 | 3 | 3.2.3.5.1 | BK-GCS-PEDCO-120-IN-DC-0002 | Instrument & Control System Design Criteria |  | BK-GCS-PEDCO-120-IN-DC-0002 | BK-GCS-PEDCO-120-IN-DC-0002 | BK | GCS | PEDCO | 120 | IN | DC | 0002 | F0Z-708921 | AFD | IFC | 2022-01-17 | 2022-02-16 | 2022-02-21 | 30 | 5 | 35 | IFA | 2022-05-25 | 2022-06-07 | 2022-06-11 | 13 | 4 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-03 |  |  | D01 | IFA | T-0931 | 44692 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04458 | 44709 | 1401/03/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-92293 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0420 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-INS-00-02625 | 44571 | 1400/10/20 | CM-C3 | [6 empty] | 1400-2294-412682 | 2022-02-16 | 1400/11/27 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0931 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-INS-01-04458 | 44709 | 1401/03/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D00 | [5 empty] | 1401-2294-92293 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D00
3 | 2 | 3 | 5 | 2 | 0 | 0 | 3.2.3.5.2 |  | Data Sheets
3 | 2 | 3 | 5 | 2 | 0 | 1 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0001 | Data Sheets For Pressure & Diff. Pressure Gauge |  | BK-GCS-PEDCO-120-IN-DT-0001 | BK-GCS-PEDCO-120-IN-DT-0001 | BK | GCS | PEDCO | 120 | IN | DT | 0001 | F9Z-708922 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | IFA | 2022-07-27 | 2022-09-06 | 2022-09-13 | 41 | 7 | 48 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-27 |  |  | D01 | IFA | T-1158 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05679 | 44817 | 1401/06/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213884 | 44810 | 1401/06/15 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03950 | 44668 | 1401/01/28 | CM-C3 | [6 empty] | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 44676 | 1401/02/05 | CM | [10 empty] | D01 | IFA | T-1158 | 44755 | 1401/04/22 |  |  |  | BK-SUR-ENG-INS-01-05679 | 44817 | 1401/06/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0001_D00 | [5 empty] | 1401-2294-213884 | 44810 | 1401/06/15 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0001_D00
3 | 2 | 3 | 5 | 2 | 0 | 2 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0002 | Data Sheets For Temperature Gauge |  | BK-GCS-PEDCO-120-IN-DT-0002 | BK-GCS-PEDCO-120-IN-DT-0002 | BK | GCS | PEDCO | 120 | IN | DT | 0002 | F9Z-708923 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | IFA | 2022-07-27 | 2022-09-06 | 2022-09-13 | 41 | 7 | 48 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-27 |  |  | D01 | IFA | T-1158 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05679 | 44817 | 1401/06/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213884 | 44810 | 1401/06/15 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03950 | 44668 | 1401/01/28 | CM-C3 | [6 empty] | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 44676 | 1401/02/05 | CM | [10 empty] | D01 | IFA | T-1158 | 44755 | 1401/04/22 |  |  |  | BK-SUR-ENG-INS-01-05679 | 44817 | 1401/06/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0002_D00 | [5 empty] | 1401-2294-213884 | 44810 | 1401/06/15 | 44817 | 1401/06/22 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0002_D00
3 | 2 | 3 | 5 | 2 | 0 | 3 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0003 | Data Sheets For Level Gauges |  | BK-GCS-PEDCO-120-IN-DT-0003 | BK-GCS-PEDCO-120-IN-DT-0003 | BK | GCS | PEDCO | 120 | IN | DT | 0003 | F9Z-708924 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-05 |  |  | D00 | IFC | T-0776 | 44656 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 44704 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 4 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0004 | Data Sheets For Pressure/Diff. Pressure Transmitter |  | BK-GCS-PEDCO-120-IN-DT-0004 | BK-GCS-PEDCO-120-IN-DT-0004 | BK | GCS | PEDCO | 120 | IN | DT | 0004 | F9Z-708925 | AFC | IFC | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-10 |  |  | D00 | IFC | T-0797 | 44661 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04115 | 44682 | 1401/02/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70032 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0797 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-INS-01-04115 | 44682 | 1401/02/11 | CM-C3 | [6 empty] | 1401-2294-70032 | 2022-05-21 | 1401/02/31 | 44704 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 5 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0005 | Data Sheets For Temperature Transmitter/Switch |  | BK-GCS-PEDCO-120-IN-DT-0005 | BK-GCS-PEDCO-120-IN-DT-0005 | BK | GCS | PEDCO | 120 | IN | DT | 0005 | F9Z-708926 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-27 |  |  | D00 | IFC | T-0750 | 44647 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03950 | 44668 | 1401/01/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27197 | 44668 | 1401/01/28 | 44676 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03950 | 44668 | 1401/01/28 | CM-C3 | [6 empty] | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 44676 | 1401/02/05 | CM
3 | 2 | 3 | 5 | 2 | 0 | 6 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0006 | Data Sheets For Displacer Level Transmitter |  | BK-GCS-PEDCO-120-IN-DT-0006 | BK-GCS-PEDCO-120-IN-DT-0006 | BK | GCS | PEDCO | 120 | IN | DT | 0006 | F9Z-708927 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-05 |  |  | D00 | IFC | T-0776 | 44656 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 44704 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 7 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0007 | Data Sheets For Pressure/ Differential Pressure Switch |  | BK-GCS-PEDCO-120-IN-DT-0007 | [8 empty] | F9Z-708928 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 5 | 2 | 0 | 8 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0008 | Data Sheets For Level Switch |  | BK-GCS-PEDCO-120-IN-DT-0008 | BK-GCS-PEDCO-120-IN-DT-0008 | BK | GCS | PEDCO | 120 | IN | DT | 0008 | F9Z-708929 | AFC | IFC | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | IFA | 2022-10-08 | 2022-11-07 | 2022-11-13 | 30 | 6 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-10 |  |  | D01 | IFA | T-1434 | 44828 | 1401/07/02 | T-1434 | 44828 | 1401/07/02 | BK-SUR-ENG-INS-01-05885 | 44845 | 1401/07/19 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0008_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-298680 | 44872 | 1401/08/16 | 44878 | 1401/08/22 | AP | NISOC-CRS-BK-GCS-NISOC-120-IN-DT-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0797 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-INS-01-04115 | 44682 | 1401/02/11 | CM-C3 | [6 empty] | 1401-2294-70032 | 2022-05-21 | 1401/02/31 | 44704 | 1401/03/02 | CM | [10 empty] | D01 | IFA | T-1434 | 44828 | 1401/07/02 | T-1434 | 44828 | 1401/07/02 | BK-SUR-ENG-INS-01-05885 | 44845 | 1401/07/19 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0008_D00 | [5 empty] | 1401-2294-298680 | 44872 | 1401/08/16 | 44878 | 1401/08/22 | AP | NISOC-CRS-BK-GCS-NISOC-120-IN-DT-0008_D00
3 | 2 | 3 | 5 | 2 | 0 | 9 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0009 | Data Sheets For Pressure & Safety Relief Valves |  | BK-GCS-PEDCO-120-IN-DT-0009 | BK-GCS-PEDCO-120-IN-DT-0009 | BK | GCS | PEDCO | 120 | IN | DT | 0009 | F9Z-708930 | AFC | IFC | 2022-05-31 | 2022-07-14 | 2022-07-17 | 44 | 3 | 47 | IFA | 2022-10-31 | 2022-11-05 | 2022-11-07 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-17 |  |  | D01 | IFA | T-1503 | 44851 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISCO-CRS-BK-GCS-PEDCO-120-IN-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0967 | 2022-05-17 | 1401/02/27 | T-0967 | 44699 | 1401/02/28 | BK-SUR-ENG-INS-01-04510 | 44713 | 1401/03/11 | CM-C3 | [6 empty] | 1401-2294-139962 | 2022-07-14 | 1401/04/23 | 44759 | 1401/04/26 | CM | [10 empty] | D01 | IFA | T-1503 | 44851 | 1401/07/25 |  |  |  | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0009_D00 | [5 empty] | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISCO-CRS-BK-GCS-PEDCO-120-IN-DT-0009_D00
3 | 2 | 3 | 5 | 2 | 0 | 10 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0010 | Data Sheets For ON/OFF & Shutdown Valves |  | BK-GCS-PEDCO-120-IN-DT-0010 | BK-GCS-PEDCO-120-IN-DT-0010 | BK | GCS | PEDCO | 120 | IN | DT | 0010 | F9Z-708931 | AFC | IFC | 2022-05-22 | 2022-05-30 | 2022-06-06 | 8 | 7 | 15 | IFA | 2022-10-31 | 2022-11-05 | 2022-11-07 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-08 |  |  | D01 | IFA | T-1503 | 44851 | 1401/07/25 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0906 | 2022-05-08 | 1401/02/18 | T-0906 | 44689 | 1401/02/18 | BK-SUR-ENG-INS-01-04428 | 44705 | 1401/03/03 | CM-C3 | [6 empty] | 1401-2294-82869 | 2022-05-30 | 1401/03/09 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1503 | 44851 | 1401/07/25 |  |  |  | BK-SUR-ENG-INS-01-06055 | 44866 | 1401/08/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0010_D00 | [5 empty] | 1401-2294-296295 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0010_D00
3 | 2 | 3 | 5 | 2 | 0 | 11 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0011 | Data Sheets For Control/Regulator Valves |  | BK-GCS-PEDCO-120-IN-DT-0011 | BK-GCS-PEDCO-120-IN-DT-0011 | BK | GCS | PEDCO | 120 | IN | DT | 0011 | F9Z-708932 | AFC | IFC | 2022-07-09 | 2022-09-04 | 2022-09-13 | 57 | 9 | 66 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-25 |  |  | D00 | IFC | T-1115 | 44737 | 1401/04/04 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05253 | 44768 | 1401/05/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-210033 | 44808 | 1401/06/13 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1115 | 2022-06-25 | 1401/04/04 |  |  |  | BK-SUR-ENG-INS-01-05253 | 44768 | 1401/05/04 | CM-C3 | [6 empty] | 1401-2294-210033 | 2022-09-04 | 1401/06/13 | 44817 | 1401/06/22 | CM
3 | 2 | 3 | 5 | 2 | 0 | 12 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0012 | Data Sheets For Diff. Pressure Flow Transmitter |  | BK-GCS-PEDCO-120-IN-DT-0012 | BK-GCS-PEDCO-120-IN-DT-0012 | BK | GCS | PEDCO | 120 | IN | DT | 0012 | F9Z-708933 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-05 |  |  | D00 | IFC | T-0776 | 44656 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 44704 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 13 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0013 | Data Sheets For Orifice Plate/Restriction Orifice |  | BK-GCS-PEDCO-120-IN-DT-0013 | BK-GCS-PEDCO-120-IN-DT-0013 | BK | GCS | PEDCO | 120 | IN | DT | 0013 | F9Z-708934 | AFC | IFC | 2022-08-06 | 2022-09-21 | 2022-10-02 | 46 | 11 | 57 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-23 |  |  | D00 | IFC | T-1178 | 44765 | 1401/05/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05365 | 44779 | 1401/05/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233417 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1178 | 2022-07-23 | 1401/05/01 |  |  |  | BK-SUR-ENG-INS-01-05365 | 44779 | 1401/05/15 | CM-C3 | [6 empty] | 1401-2294-233417 | 2022-09-21 | 1401/06/30 | 44836 | 1401/07/10 | CM
3 | 2 | 3 | 5 | 2 | 0 | 14 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0014 | Data Sheets For Corrosion Coupon/ Probe |  | BK-GCS-PEDCO-120-IN-DT-0014 | BK-GCS-PEDCO-120-IN-DT-0014 | BK | GCS | PEDCO | 120 | IN | DT | 0014 | F9Z-708935 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-27 |  |  | D00 | IFC | T-0750 | 44647 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03950 | 44668 | 1401/01/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27197 | 44668 | 1401/01/28 | 44676 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03950 | 44668 | 1401/01/28 | CM-C3 | [6 empty] | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 44676 | 1401/02/05 | CM
3 | 2 | 3 | 5 | 2 | 0 | 15 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0016 | Data Sheets For F&G Detectors & Equipment |  | BK-GCS-PEDCO-120-IN-DT-0016 | BK-GCS-PEDCO-120-IN-DT-0016 | BK | GCS | PEDCO | 120 | IN | DT | 0016 | F9Z-708936 | AFC | IFC | 2022-05-23 | 2022-06-15 | 2022-06-19 | 23 | 4 | 27 | IFA | 2022-10-26 | 0 | 0 | -44860 | 0 | -44860 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-09 |  |  | D01 | IFA | T-1488 | 44846 | 1401/07/20 | T-1488 | 44846 | 1401/07/20 | BK-SUR-ENG-INS-01-05974 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0920 | 2022-05-09 | 1401/02/19 | T-0920 | 44690 | 1401/02/19 | BK-SUR-ENG-INS-01-04457 | 44709 | 1401/03/07 | CM-C3 | [6 empty] | 1401-2294-104549 | 2022-06-15 | 1401/03/25 | 44731 | 1401/03/29 | CM | [10 empty] | D01 | IFA | T-1488 | 44846 | 1401/07/20 | T-1488 | 44846 | 1401/07/20 | BK-SUR-ENG-INS-01-05974 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0016_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0016_D00
3 | 2 | 3 | 5 | 2 | 0 | 16 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0017 | Data Sheets For ESD Console/F&G Matrix Panel |  | BK-GCS-PEDCO-120-IN-DT-0017 | BK-GCS-PEDCO-120-IN-DT-0017 | BK | GCS | PEDCO | 120 | IN | DT | 0017 | F9Z-708937 | AFC | IFC | 2022-05-14 | 2022-06-14 | 2022-06-15 | 31 | 1 | 32 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | #REF! |  |  | D00 | IFC | T-0882 | 44681 | 1401/02/10 | T-0882 | 44681 | 1401/02/10 | BK-SUR-ENG-INS-01-04305 | 44699 | 1401/02/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-100894 | 44726 | 1401/03/23 | 44727 | 1401/03/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0882 | 2022-04-30 | 1401/02/10 | T-0882 | 44681 | 1401/02/10 | BK-SUR-ENG-INS-01-04305 | 44699 | 1401/02/28 | CM-C3 | [6 empty] | 1401-2294-100894 | 2022-06-14 | 1401/03/23 | 44727 | 1401/03/25 | CM
3 | 2 | 3 | 5 | 2 | 0 | 17 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0018 | Data Sheets For Rotameter |  | BK-GCS-PEDCO-120-IN-DT-0018 | BK-GCS-PEDCO-120-IN-DT-0018 | BK | GCS | PEDCO | 120 | IN | DT | 0018 | F9Z-708938 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-05 |  |  | D00 | IFC | T-0776 | 44656 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 44704 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 18 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0019 | Data Sheets For Diff. Pressure Type Level Transmitter |  | BK-GCS-PEDCO-120-IN-DT-0019 | BK-GCS-PEDCO-120-IN-DT-0019 | BK | GCS | PEDCO | 120 | IN | DT | 0019 | F9Z-708939 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-05 |  |  | D00 | IFC | T-0776 | 44656 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 44698 | 1401/02/27 | 44704 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 44704 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 19 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0020 | Data Sheets For CCTV |  | BK-GCS-PEDCO-120-IN-DT-0020 | BK-GCS-PEDCO-120-IN-DT-0020 | BK | GCS | PEDCO | 120 | IN | DT | 0020 | F9Z-708940 | AFC | IFC | 2021-10-27 | 2021-10-27 | 2021-11-07 | 0 | 11 | 11 | IFA | 2022-05-16 | 2022-05-21 | 2022-05-23 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-13 |  |  | D01 | IFA | T-0895 | 44683 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04224 | 44691 | 1401/02/20 | AP | PEDCO-BK-GCS-PEDCO-120-IN-DT-0020_D00 | BK-SUR-ENG-INS-01-04258 | 44695 | 1401/02/24 | AP | 0 | 1401-2294-70035 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP | NISOC-BK-GCS-PEDCO-120-IN-DT-0020_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0158 | 2021-10-13 | 1400/07/21 |  |  |  | BK-SUR-ENG-INS-00-01835 | 44494 | 1400/08/03 | RJ-C4 |  | BK-SUR-ENG-TEL-00-01926 | 44507 | 1400/08/16 | RJ-C4 |  | 1400-2294-251389 | 2021-10-27 | 1400/08/05 | 44507 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0895 | 44683 | 1401/02/12 |  |  |  | BK-SUR-ENG-INS-01-04224 | 44691 | 1401/02/20 | AP | PEDCO-BK-GCS-PEDCO-120-IN-DT-0020_D00 | BK-SUR-ENG-INS-01-04258 | 44695 | 1401/02/24 | AP |  | 1401-2294-70035 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP | NISOC-BK-GCS-PEDCO-120-IN-DT-0020_D00
3 | 2 | 3 | 5 | 2 | 0 | 20 | 3.2.3.5.2 | BK-GCS-PEDCO-120-IN-DT-0021 | Data Sheets For IRP Panel |  | BK-GCS-PEDCO-120-IN-DT-0021 | BK-GCS-PEDCO-120-IN-DT-0021 | BK | GCS | PEDCO | 120 | IN | DT | 0021 | F9Z-708941 | AFC | IFC | 2022-06-27 | 2022-08-13 | 2022-08-20 | 47 | 7 | 54 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-13 |  |  | D00 | IFC | T-1071 | 44725 | 1401/03/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05038 | 44751 | 1401/04/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-175155 | 44786 | 1401/05/22 | 44793 | 1401/05/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1071 | 2022-06-13 | 1401/03/23 |  |  |  | BK-SUR-ENG-INS-01-05038 | 44751 | 1401/04/18 | CM-C3 | [6 empty] | 1401-2294-175155 | 2022-08-13 | 1401/05/22 | 44793 | 1401/05/29 | CM
3 | 2 | 3 | 5 | 3 | 0 | 0 | 3.2.3.5.3 |  | Drawing/Diagram
3 | 2 | 3 | 5 | 3 | 0 | 1 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DW-0001 | Typical Instrument Installation Drawing |  | BK-GCS-PEDCO-120-IN-DW-0001 | BK-GCS-PEDCO-120-IN-DW-0001 | BK | GCS | PEDCO | 120 | IN | DW | 0001 | F2J-708942 | IFI | IFI | 2022-03-23 | 2022-04-04 | 2022-04-09 | 12 | 5 | 17 | IFI | 2022-06-15 | 2022-08-15 | 2022-08-21 | 61 | 6 | 67 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-09 |  |  | D01 | IFI | T-1035 | 44713 | 1401/03/11 | T-1035 | 44713 | 1401/03/11 | BK-SUR-ENG-INS-01-04743 | 44731 | 1401/03/29 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-175161 | 44788 | 1401/05/22 | 44794 | 1401/05/30 | CM | NISCO-CRS-BK-GCS-PEDCO-120-IN-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0709 | 2022-03-09 | 1400/12/18 | [13 empty] | 1401-2294-9656 | 2022-04-04 | 1401/01/15 | 44660 | 1401/01/20 | CM | [10 empty] | D01 | IFI | T-1035 | 44713 | 1401/03/11 | T-1035 | 44713 | 1401/03/11 | BK-SUR-ENG-INS-01-04743 | 44731 | 1401/03/29 | CM-C2 | [6 empty] | 1401-2294-175161 | 44788 | 1401/05/22 | 44794 | 1401/05/30 | CM | NISCO-CRS-BK-GCS-PEDCO-120-IN-DW-0001_D01
3 | 2 | 3 | 5 | 3 | 0 | 2 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-BD-0001 | Control/ESD/F&G System Block Diagram Configuration |  | BK-GCS-PEDCO-120-IN-BD-0001 | BK-GCS-PEDCO-120-IN-BD-0001 | BK | GCS | PEDCO | 120 | IN | BD | 0001 | F2J-708943 | AFC | IFC | 2021-09-13 | 2021-10-26 | 2021-10-02 | 43 | -24 | 19 | IFA | 2021-11-23 | 2021-11-21 | 2021-11-27 | -2 | 6 | 4 | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 | IFA | 2022-04-13 | 2022-05-10 | 2022-05-15 | 27 | 5 | 32 | IFA | 2022-08-14 | 2022-08-31 | 2022-09-13 | 17 | 13 | 30 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-08-30 |  |  | D04 | IFA | T-1225 | 44773 | 1401/05/09 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05466 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205620 | 44804 | 1401/06/09 | 44817 | 1401/09/13 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0071 | 2021-08-30 | 1400/06/08 | [13 empty] | 1400-2294-213820 | 2021-10-26 | 1400/07/04 | 44471 | 1400/07/10 | CM |  | 1400-2294-234028 | 44482 | 1400/07/21 |  |  | CM |  |  |  | D01 | IFA | T-0218 | 44509 | 1400/08/18 |  |  |  | BK-SUR-ENG-INS-00-02067 | 44521 | 1400/08/30 | C4-RJ | [6 empty] | 1400-2294-283482 | 44521 | 1400/08/30 | 44527 | 1400/09/06 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D00 | [9 empty] | D02 | IFA | T-0444 | 44571 | 1400/10/20 |  |  |  | BK-SUR-ENG-INS-00-02815 | 44586 | 1400/11/05 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D01 | [5 empty] | 1400-2294-385430 | 44590 | 1400/11/09 | 44591 | 1400/11/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D01 | [9 empty] | D03 | IFA | T-0765 | 44650 | 1401/01/10 |  |  |  | BK-SUR-ENG-INS-01-03960 | 44668 | 1401/01/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D02 | [5 empty] | 1401-2294-55898 | 44691 | 1401/02/20 | 44696 | 1401/02/24 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D02 | [9 empty] | D04 | IFA | T-1225 | 44773 | 1401/05/09 |  |  |  | BK-SUR-ENG-INS-01-05466 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D03 | [5 empty] | 1401-2294-205620 | 44804 | 1401/06/09 | 44817 | 1401/09/13 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D03
3 | 2 | 3 | 5 | 3 | 0 | 3 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0001 | Instrument Earthing Typical Diagram |  | BK-GCS-PEDCO-120-IN-DG-0001 | BK-GCS-PEDCO-120-IN-DG-0001 | BK | GCS | PEDCO | 120 | IN | DG | 0001 | F2J-708944 | IFI | IFI | 2022-01-12 | 2022-01-13 | 2022-01-15 | 1 | 2 | 3 | IFI | 2022-05-01 | 2022-05-12 | 2022-05-16 | 11 | 4 | 15 | IFI | 2022-08-10 | 2022-09-22 | 2022-10-02 | 43 | 10 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-29 |  |  | D02 | IFI | T-1211 | 44769 | 1401/05/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05456 | 44788 | 1401/05/24 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233554 | 44826 | 1401/06/31 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0408 | 2021-12-29 | 1400/10/08 | [13 empty] | 1400-2294-362541 | 2022-01-13 | 1400/10/23 | 44576 | 1400/10/25 | CM | [10 empty] | D01 | IFI | T-0828 | 44668 | 1401/01/28 |  |  |  | BK-SUR-ENG-INS-01-04154 | 44688 | 1401/02/17 | CM-C2 | [6 empty] | 1401-2294-59512 | 44693 | 1401/02/22 | 44697 | 1401/02/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0001_D00 | [9 empty] | D02 | IFI | T-1211 | 44769 | 1401/05/05 |  |  |  | BK-SUR-ENG-INS-01-05456 | 44788 | 1401/05/24 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0001_D01 | [5 empty] | 1401-2294-233554 | 44826 | 1401/06/31 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0001_D01
3 | 2 | 3 | 5 | 3 | 0 | 4 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0002 | Instrument Hook-up Diagram |  | BK-GCS-PEDCO-120-IN-DG-0002 | BK-GCS-PEDCO-120-IN-DG-0002 | BK | GCS | PEDCO | 120 | IN | DG | 0002 | F2J-708945 | AFC | IFC | 2022-03-16 | 2022-04-19 | 2022-04-30 | 34 | 11 | 45 | IFA | 2022-07-09 | 2022-08-04 | 2022-08-06 | 26 | 2 | 28 | IFA | 2022-10-26 | 0 | 0 | -44860 | 0 | -44860 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-02 |  |  | D02 | IFA | T-1488 | 44846 | 1401/07/20 | T-1488 | 44846 | 1401/07/20 | BK-SUR-ENG-INS-01-05974 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISCO-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0757 | 2022-03-02 | 1401/01/07 |  |  |  | BK-SUR-ENG-INS-01-03980 | 44670 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-31183 | 2022-04-19 | 1401/01/30 | 44681 | 1401/02/10 | CM | [10 empty] | D01 | IFA | T-1116 | 44737 | 1401/04/04 |  |  |  | BK-SUR-ENG-INS-01-05264 | 44772 | 1401/05/08 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D00 | [5 empty] | 1401-2294-167261 | 44777 | 1401/05/13 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D00 | [9 empty] | D02 | IFA | T-1488 | 44846 | 1401/07/20 | T-1488 | 44846 | 1401/07/20 | BK-SUR-ENG-INS-01-05974 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D01 | [11 empty] | NISCO-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D01
3 | 2 | 3 | 5 | 3 | 0 | 5 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0003 | ESD Level Hierarchy |  | BK-GCS-PEDCO-120-IN-DG-0003 | BK-GCS-PEDCO-120-IN-DG-0003 | BK | GCS | PEDCO | 120 | IN | DG | 0003 | F2J-708946 | AFC | IFC | 2022-06-11 | 2022-08-14 | 2022-08-16 | 64 | 2 | 66 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-28 |  |  | D00 | IFC | T-1014 | 44709 | 1401/03/07 | T-1014 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-04678 | 44723 | 1401/03/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177069 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1014 | 2022-05-28 | 1401/03/07 | T-1014 | 44709 | 1401/03/07 | BK-SUR-ENG-INS-01-04678 | 44723 | 1401/03/21 | CM-C3 | [6 empty] | 1401-2294-177069 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM
3 | 2 | 3 | 5 | 3 | 0 | 6 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0004 | ESD System Loop Diagram |  | BK-GCS-PEDCO-120-IN-DG-0004 | BK-GCS-PEDCO-120-IN-DG-0004 | BK | GCS | PEDCO | 120 | IN | DG | 0004 | F2J-708947 | AFC | IFC | 2022-06-20 | 0 | 0 | -44732 | 0 | -44732 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-06 |  |  | D00 | IFC | T-1037 | 44718 | 1401/03/16 | T-1037 | 44719 | 1401/03/17 | BK-SUR-ENG-INS-01-04799 | 44733 | 1401/03/30 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1037 | 2022-06-06 | 1401/03/16 | T-1037 | 44719 | 1401/03/17 | BK-SUR-ENG-INS-01-04799 | 44733 | 1401/03/30 | CM-C3
3 | 2 | 3 | 5 | 3 | 0 | 7 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0005 | Control System Loop Diagram |  | BK-GCS-PEDCO-120-IN-DG-0005 | BK-GCS-PEDCO-120-IN-DG-0005 | BK | GCS | PEDCO | 120 | IN | DG | 0005 | F2J-708948 | AFC | IFC | 2022-06-29 | 2022-08-17 | 2022-08-21 | 49 | 4 | 53 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-15 |  |  | D00 | IFC | T-1080 | 44727 | 1401/03/25 | 44727 | 0 | 0 | BK-SUR-ENG-INS-01-05231 | 44767 | 1401/05/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183423 | 44790 | 1401/05/26 | 44794 | 1401/05/30 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1080 | 2022-06-15 | 1401/03/25 | 44727 |  |  | BK-SUR-ENG-INS-01-05231 | 44767 | 1401/05/03 | CM-C3 | [6 empty] | 1401-2294-183423 | 2022-08-17 | 1401/05/26 | 44794 | 1401/05/30 | CM
3 | 2 | 3 | 5 | 3 | 0 | 8 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0006 | F&G System Loop Diagram |  | BK-GCS-PEDCO-120-IN-DG-0006 | BK-GCS-PEDCO-120-IN-DG-0006 | BK | GCS | PEDCO | 120 | IN | DG | 0006 | F2J-708949 | AFC | IFC | 2022-07-16 | 2022-09-03 | 2022-09-10 | 49 | 7 | 56 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-02 |  |  | D00 | IFC | T-1132 | 44744 | 1401/04/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05311 | 44774 | 1401/05/10 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-208231 | 44807 | 1401/06/12 | 44814 | 1401/06/19 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1132 | 2022-07-02 | 1401/04/11 |  |  |  | BK-SUR-ENG-INS-01-05311 | 44774 | 1401/05/10 | CM-C3 | [6 empty] | 1401-2294-208231 | 2022-09-03 | 1401/06/12 | 44814 | 1401/06/19 | CM
3 | 2 | 3 | 5 | 3 | 0 | 9 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0007 | Instrument Air Piping and Air Header Diagram |  | BK-GCS-PEDCO-120-IN-DG-0007 | BK-GCS-PEDCO-120-IN-DG-0007 | BK | GCS | PEDCO | 120 | IN | DG | 0007 | F2J-708950 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 5 | 3 | 0 | 10 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0008 | Instrument & F&G Junction Box Termination Diagram |  | BK-GCS-PEDCO-120-IN-DG-0008 | BK-GCS-PEDCO-120-IN-DG-0008 | BK | GCS | PEDCO | 120 | IN | DG | 0008 | F2J-708951 | AFC | IFC | 2022-02-27 | 2022-02-27 | 2022-03-05 | 0 | 6 | 6 | IFA | 2022-07-16 | 2022-10-04 | 2022-10-19 | 80 | 15 | 95 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 |  |  | D01 | IFA | T-1131 | 44744 | 1401/04/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05310 | 44774 | 1401/05/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0008_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-208231 | 44807 | 1401/06/12 | 44814 | 1401/06/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0008_D00 | 1401-2294-208227 | 44838 | 1401/06/12 | 44853 | 1401/07/27 | AP | 0 | 0 |  | D00 | IFC | T-0581 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-INS-00-03247 | 44619 | 1400/12/08 | RJ-C4 | [6 empty] | 1400-2294-428474 | 2022-02-27 | 1400/12/08 | 44625 | 1400/12/14 | CM | [10 empty] | D01 | IFA | T-1131 | 44744 | 1401/04/11 |  |  |  | BK-SUR-ENG-INS-01-05310 | 44774 | 1401/05/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0008_D00 | [5 empty] | 1401-2294-208231 | 44807 | 1401/06/12 | 44814 | 1401/06/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0008_D00 | 1401-2294-208227 | 44838 | 1401/06/12 | 44853 | 1401/07/27 | AP
3 | 2 | 3 | 5 | 3 | 0 | 11 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0009 | F&G Cause and Effect Diagram For Process Area |  | BK-GCS-PEDCO-120-IN-DG-0009 | BK-GCS-PEDCO-120-IN-DG-0009 | BK | GCS | PEDCO | 120 | IN | DG | 0009 | F2J-708952 | AFC | IFC | 2022-06-13 | 2022-08-14 | 2022-08-16 | 62 | 2 | 64 | IFA | 2022-10-29 | 0 | 0 | -44863 | 0 | -44863 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-30 |  |  | D01 | IFA | T-1493 | 44849 | 1401/07/23 | T-1493 | 44849 | 1401/07/23 | BK-SUR-ENG-INS-01-05975 | 44859 | 1401/08/03 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1025 | 2022-05-30 | 1401/03/09 | T-1025 | 44712 | 1401/03/10 | [10 empty] | 1401-2294-177038 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM | [10 empty] | D01 | IFA | T-1493 | 44849 | 1401/07/23 | T-1493 | 44849 | 1401/07/23 | BK-SUR-ENG-INS-01-05975 | 44859 | 1401/08/03 | CM-C2 | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0009_D00
3 | 2 | 3 | 5 | 3 | 0 | 12 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-DG-0010 | F&G Cause and Effect Diagram For Buildings |  | BK-GCS-PEDCO-120-IN-DG-0010 | BK-GCS-PEDCO-120-IN-DG-0010 | BK | GCS | PEDCO | 120 | IN | DG | 0010 | F2J-708953 | AFC | IFC | 2022-06-28 | 2022-08-16 | 2022-08-21 | 49 | 5 | 54 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-14 |  |  | D00 | IFC | T-1073 | 44726 | 1401/03/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05597 | 44808 | 1401/06/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-180898 | 44789 | 1401/05/25 | 44794 | 1401/05/30 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1073 | 2022-06-14 | 1401/03/21 |  |  |  | BK-SUR-ENG-INS-01-05597 | 44808 | 1401/06/13 | CM-C3 | [6 empty] | 1401-2294-180898 | 2022-08-16 | 1401/05/25 | 44794 | 1401/05/30 | CM
3 | 2 | 3 | 5 | 3 | 0 | 13 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-LD-0001 | Control System Logic Diagram |  | BK-GCS-PEDCO-120-IN-LD-0001 | BK-GCS-PEDCO-120-IN-LD-0001 | BK | GCS | PEDCO | 120 | IN | LD | 0001 | F1J-708954 | AFC | IFC | 2022-08-06 | 2022-09-21 | 2022-10-02 | 46 | 11 | 57 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-23 |  |  | D00 | IFC | T-1178 | 44765 | 1401/05/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05365 | 44779 | 1401/05/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-233417 | 44825 | 1401/06/30 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1178 | 2022-07-23 | 1401/05/01 |  |  |  | BK-SUR-ENG-INS-01-05365 | 44779 | 1401/05/15 | CM-C3 | [6 empty] | 1401-2294-233417 | 2022-09-21 | 1401/06/30 | 44836 | 1401/07/10 | CM
3 | 2 | 3 | 5 | 3 | 0 | 14 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-LD-0002 | ESD Logic Diagram |  | BK-GCS-PEDCO-120-IN-LD-0002 | BK-GCS-PEDCO-120-IN-LD-0002 | BK | GCS | PEDCO | 120 | IN | LD | 0002 | F1J-708955 | AFC | IFC | 2022-06-26 | 2022-08-11 | 2022-08-15 | 46 | 4 | 50 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-12 |  |  | D00 | IFC | T-1067 | 44724 | 1401/03/22 | T-1067 | 44724 | 1401/03/22 | BK-SUR-ENG-INS-01-05037 | 44751 | 1401/04/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-172901 | 44784 | 1401/05/20 | 44788 | 1401/05/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1067 | 2022-06-12 | 1401/03/22 | T-1067 | 44724 | 1401/03/22 | BK-SUR-ENG-INS-01-05037 | 44751 | 1401/04/18 | CM-C3 | [6 empty] | 1401-2294-172901 | 2022-08-11 | 1401/05/20 | 44788 | 1401/05/24 | CM
3 | 2 | 3 | 5 | 3 | 0 | 15 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-PY-0001 | Control Room Layout & Arrangement Drawing |  | BK-GCS-PEDCO-120-IN-PY-0001 | BK-GCS-PEDCO-120-IN-PY-0001 | BK | GCS | PEDCO | 120 | IN | PY | 0001 | F2J-708956 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-15 | 27 | 0 | 27 | IFA | 2022-06-01 | 2022-07-14 | 2022-07-17 | 43 | 3 | 46 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-02 |  |  | D01 | IFA | T-0973 | 44699 | 1401/02/28 | T-0973 | 44702 | 1401/02/31 | BK-SUR-ENG-INS-01-04517 | 44713 | 1401/03/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-139951 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 44606 | 1400/11/25 | CM-C3 | [6 empty] | 1401-2294-449416 | 2022-03-15 | 1400/12/24 | 44635 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0973 | 44699 | 1401/02/28 | T-0973 | 44702 | 1401/02/31 | BK-SUR-ENG-INS-01-04517 | 44713 | 1401/03/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0001_D00 | [5 empty] | 1401-2294-139951 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0001_D00
3 | 2 | 3 | 5 | 3 | 0 | 16 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-PY-0002 | Control Room Cable Route Layout |  | BK-GCS-PEDCO-120-IN-PY-0002 | BK-GCS-PEDCO-120-IN-PY-0002 | BK | GCS | PEDCO | 120 | IN | PY | 0002 | F2J-708957 | AFC | IFC | 2022-06-06 | 2022-07-14 | 2022-07-17 | 38 | 3 | 41 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-23 |  |  | D00 | IFC | T-0991 | 44704 | 1401/03/02 | T-0991 | 44704 | 1401/03/02 | BK-SUR-ENG-INS-01-04585 | 44719 | 1401/03/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-139947 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0991 | 2022-05-23 | 1401/03/02 | T-0991 | 44704 | 1401/03/02 | BK-SUR-ENG-INS-01-04585 | 44719 | 1401/03/17 | CM-C3 | [6 empty] | 1401-2294-139947 | 2022-07-14 | 1401/04/23 | 44759 | 1401/04/26 | CM
3 | 2 | 3 | 5 | 3 | 0 | 17 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-PY-0003 | Instrument Location Layout |  | BK-GCS-PEDCO-120-IN-PY-0003 | BK-GCS-PEDCO-120-IN-PY-0003 | BK | GCS | PEDCO | 120 | IN | PY | 0003 | F2J-708958 | AFC | IFC | 2022-09-06 | 2022-10-28 | 2022-10-02 | 52 | -26 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-23 |  |  | D00 | IFC | T-1304 | 44796 | 1401/06/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05616 | 44811 | 1401/06/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240307 | 44862 | 1401/07/06 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1304 | 2022-08-23 | 1401/06/01 |  |  |  | BK-SUR-ENG-INS-01-05616 | 44811 | 1401/06/16 | CM-C3 | [6 empty] | 1401-2294-240307 | 2022-10-28 | 1401/07/06 | 44836 | 1401/07/10 | CM
3 | 2 | 3 | 5 | 3 | 0 | 18 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-PY-0004 | Instrument/F&G Cable Trench/Route Layout Drawing |  | BK-GCS-PEDCO-120-IN-PY-0004 | BK-GCS-PEDCO-120-IN-PY-0004 | BK | GCS | PEDCO | 120 | IN | PY | 0004 | F2J-708959 | AFC | IFC | 2022-02-08 | 2022-03-09 | 2022-03-12 | 29 | 3 | 32 | IFA | 2022-08-13 | 2022-09-24 | 2022-10-02 | 42 | 8 | 50 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-25 |  |  | D01 | IFA | T-1220 | 44772 | 1401/05/08 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05462 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-235789 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0509 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-INS-00-03017 | 44601 | 1400/11/20 | CM-C3 | [6 empty] | 1400-2294-442053 | 2022-03-09 | 1400/12/18 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-1220 | 44772 | 1401/05/08 |  |  |  | BK-SUR-ENG-INS-01-05462 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0004_D00 | [5 empty] | 1401-2294-235789 | 44828 | 1401/07/02 | 44836 | 1401/07/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0004_D00
3 | 2 | 3 | 5 | 3 | 0 | 19 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-PY-0005 | F&G Location Layout For Process Area |  | BK-GCS-PEDCO-120-IN-PY-0005 | BK-GCS-PEDCO-120-IN-PY-0005 | BK | GCS | PEDCO | 120 | IN | PY | 0005 | F2J-708960 | AFC | IFC | 2022-02-21 | 2022-05-10 | 2022-03-13 | 78 | -58 | 20 | IFA | 2022-05-22 | 2022-08-02 | 2022-08-06 | 72 | 4 | 76 | IFA | 2022-10-23 | 2022-10-30 | 2022-11-01 | 7 | 2 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-07 |  |  | D02 | IFA | T-1468 | 44843 | 1401/07/17 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05933 | 44853 | 1401/07/27 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-286131 | 44864 | 1401/08/08 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0561 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-INS-00-03136 | 44612 | 1400/12/01 | CM-C3 | [6 empty] | 1400-2294-421738 | 2022-02-22 | 1400/12/03 | 44622 | 1400/12/11 | CM |  | 1400-2294-443233 | 44691 | 1400/12/19 | 44633 | 1400/12/22 | CM |  |  |  | D01 | IFA | T-0914 | 44689 | 1401/02/18 | T-0914 | 44689 | 1401/02/18 | BK-SUR-ENG-INS-01-04431 | 44706 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D00 | [5 empty] | 1401-2294-164864 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D00 | [9 empty] | D02 | IFA | T-1468 | 44843 | 1401/07/17 |  |  |  | BK-SUR-ENG-INS-01-05933 | 44853 | 1401/07/27 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D01 | [5 empty] | 1401-2294-286131 | 44864 | 1401/08/08 | 44866 | 1401/08/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D01
3 | 2 | 3 | 5 | 3 | 0 | 20 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-PY-0006 | F&G Location Layout For Buildings |  | BK-GCS-PEDCO-120-IN-PY-0006 | BK-GCS-PEDCO-120-IN-PY-0006 | BK | GCS | PEDCO | 120 | IN | PY | 0006 | F2J-708961 | AFC | IFC | 2022-05-02 | 2022-05-17 | 2022-05-23 | 15 | 6 | 21 | IFA | 2022-10-18 | 2022-10-25 | 2022-10-26 | 7 | 1 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-18 |  |  | D01 | IFA | T-1459 | 44838 | 1401/07/12 | T-1459 | 44842 | 1401/07/16 | BK-SUR-ENG-INS-01-05931 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-280846 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0836 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-INS-01-04157 | 44688 | 1401/02/17 | CM-C3 | [6 empty] | 1401-2294-65627 | 2022-05-17 | 1401/02/27 | 44704 | 1401/03/02 | CM | [10 empty] | D01 | IFA | T-1459 | 44838 | 1401/07/12 | T-1459 | 44842 | 1401/07/16 | BK-SUR-ENG-INS-01-05931 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0006_D00 | [5 empty] | 1401-2294-280846 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0006_D00
3 | 2 | 3 | 5 | 3 | 0 | 21 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-BD-0002 | Block Diagram For CCTV | Block Diagram For PROCESS CCTV | BK-GCS-PEDCO-120-IN-BD-0002 | BK-GCS-PEDCO-120-IN-BD-0002 | BK | GCS | PEDCO | 120 | IN | BD | 0002 | F2T-708962 | AFC | IFC | 2022-07-11 | 2022-09-28 | 2022-10-02 | 79 | 4 | 83 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-27 |  |  | D00 | IFC | T-1125 | 44739 | 1401/04/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05230 | 44766 | 1401/05/02 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238953 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1125 | 2022-06-27 | 1401/04/06 |  |  |  | BK-SUR-ENG-INS-01-05230 | 44766 | 1401/05/02 | CM-C2 | [6 empty] | 1401-2294-238953 | 2022-09-28 | 1401/07/06 | 44836 | 1401/07/10 | CM
3 | 2 | 3 | 5 | 3 | 0 | 22 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-BD-0003 | Block Diagram For CCTV in Binak DU |  | BK-GCS-PEDCO-120-IN-BD-0003 | BK-GCS-PEDCO-120-IN-BD-0003 | BK | GCS | PEDCO | 120 | IN | BD | 0003 | F2T-708963 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 5 | 3 | 0 | 23 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-PY-0007 | CCTV Equipment Layout For GCS Area | PROCESS CCTV Equipment Layout for GCS Area | BK-GCS-PEDCO-120-IN-PY-0007 | BK-GCS-PEDCO-120-IN-PY-0007 | BK | GCS | PEDCO | 120 | IN | PY | 0007 | F2J-708964 | AFC | IFC | 2022-04-23 | 2022-06-06 | 2022-06-11 | 44 | 5 | 49 | IFA | 2022-07-09 | 2022-09-07 | 2022-09-12 | 60 | 5 | 65 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-09 |  |  | D01 | IFA | T-1117 | 44737 | 1401/04/04 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05266 | 44772 | 1401/05/08 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-210036 | 44811 | 1401/06/13 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0792 | 2022-04-09 | 1401/01/20 |  |  |  | BK-SUR-ENG-INS-01-03896 | 44678 | 1401/02/07 | AP | [6 empty] | 1401-2294-88587 | 2022-06-06 | 1401/03/16 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1117 | 44737 | 1401/04/04 |  |  |  | BK-SUR-ENG-INS-01-05266 | 44772 | 1401/05/08 | CM-C3 | [6 empty] | 1401-2294-210036 | 44811 | 1401/06/13 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0007_D00
3 | 2 | 3 | 5 | 3 | 0 | 24 | 3.2.3.5.3 | BK-GCS-PEDCO-120-IN-PY-0008 | CCTV Equipment Layout For Desalting Unit Area |  | BK-GCS-PEDCO-120-IN-PY-0008 | BK-GCS-PEDCO-120-IN-PY-0008 | BK | GCS | PEDCO | 120 | IN | PY | 0008 | F2J-708965 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 5 | 3 | 0 | 25 | 3.2.3.5.3 | BK-GCS-PEDCO-120-EL-DG-0011 | Wiring Diagram For Interposing Relay Panel (IRP) |  | BK-GCS-PEDCO-120-EL-DG-0011 | BK-GCS-PEDCO-120-EL-DG-0011 | BK | GCS | PEDCO | 120 | EL | DG | 0011 | F2P-708966 | AFC | IFC | 2022-07-04 | 2022-08-11 | 2022-08-14 | 38 | 3 | 41 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-20 |  |  | D00 | IFC | T-1098 | 44732 | 1401/03/30 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04986 | 44747 | 1401/04/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-172868 | 44784 | 1401/05/20 | 44787 | 1401/05/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1098 | 2022-06-20 | 1401/03/30 |  |  |  | BK-SUR-ENG-ELE-01-04986 | 44747 | 1401/04/14 | CM-C3 | [6 empty] | 1401-2294-172868 | 2022-08-11 | 1401/05/20 | 44787 | 1401/05/23 | CM
[8 empty] | BK-GCS-PEDCO-120-IN-PY-0009 | CCTV Equipment Layout Inside CCTV Control Room in Binak DU |  | BK-GCS-PEDCO-120-IN-PY-0009 | BK-GCS-PEDCO-120-IN-PY-0009 | BK | GCS | PEDCO | 120 | IN | PY | 0009 | F2J-709413 | AFC | IFC | 2022-09-03 | 2022-09-01 | 2022-09-05 | -2 | 4 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-20 |  |  | D00 | IFC | T-1286 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05540 | 44800 | 1401/06/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205790 | 44805 | 1401/06/10 | 44809 | 1401/06/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1286 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-INS-01-05540 | 44800 | 1401/06/05 | AP | [6 empty] | 1401-2294-205790 | 2022-09-01 | 1401/06/10 | 44809 | 1401/06/14 | CM
[8 empty] | BK-GCS-PEDCO-120-IN-PY-0010 | CCTV Rack Room Location Layout in Binak PU |  | BK-GCS-PEDCO-120-IN-PY-0010 | BK-GCS-PEDCO-120-IN-PY-0010 | BK | GCS | PEDCO | 120 | IN | PY | 0010 | F2J-709414 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[8 empty] | BK-GCS-PEDCO-120-IN-PY-0013 | CCTV Equipment Layout Inside CCTV Control Room in Binak GCS |  | BK-GCS-PEDCO-120-IN-PY-0013 | [8 empty] | F2J-709418 | AFC | IFC | 2022-09-03 | 2022-09-01 | 2022-09-05 | -2 | 4 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-20 |  |  | D00 | IFC | T-1286 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05540 | 44800 | 1401/06/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205790 | 44805 | 1401/06/10 | 44809 | 1401/06/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1286 | 2022-08-20 | 1401/05/29 |  |  |  | BK-SUR-ENG-INS-01-05540 | 44800 | 1401/06/05 | AP | [6 empty] | 1401-2294-205790 | 2022-09-01 | 1401/06/10 | 44809 | 1401/06/14 | CM
3 | 2 | 3 | 5 | 4 | 0 | 0 | 3.2.3.5.4 |  | List
3 | 2 | 3 | 5 | 4 | 0 | 1 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0001 | Instrument Index |  | BK-GCS-PEDCO-120-IN-LI-0001 | BK-GCS-PEDCO-120-IN-LI-0001 | BK | GCS | PEDCO | 120 | IN | LI | 0001 | F0Z-708967 | AFC | IFC | 2022-05-11 | 2022-05-29 | 2022-06-01 | 18 | 3 | 21 | IFA | 2022-10-04 | 2022-10-30 | 2022-11-01 | 26 | 2 | 28 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-04-27 |  |  | D01 | IFA | T-1425 | 44824 | 1401/06/29 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05864 | 44843 | 1401/07/17 | CM-C2 | PEDCO-CRS_BK-GCS-PEDCO-120-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-286156 | 44864 | 1401/08/08 | 44866 | 1401/08/10 | CM | NISCO-CRS_BK-GCS-PEDCO-120-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0867 | 2022-04-27 | 1401/02/07 | T-0867 | 44678 | 1401/02/07 | BK-SUR-ENG-INS-01-04195 | 44691 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78910 | 2022-05-29 | 1401/03/08 | 44713 | 1401/03/10 | CM | [10 empty] | D01 | IFA | T-1425 | 44824 | 1401/06/29 |  |  |  | BK-SUR-ENG-INS-01-05864 | 44843 | 1401/07/17 | CM-C2 | PEDCO-CRS_BK-GCS-PEDCO-120-IN-LI-0001_D00 | [5 empty] | 1401-2294-286156 | 44864 | 1401/08/08 | 44866 | 1401/08/10 | CM | NISCO-CRS_BK-GCS-PEDCO-120-IN-LI-0001_D00
3 | 2 | 3 | 5 | 4 | 0 | 2 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0002 | I/O List For Control System |  | BK-GCS-PEDCO-120-IN-LI-0002 | BK-GCS-PEDCO-120-IN-LI-0002 | BK | GCS | PEDCO | 120 | IN | LI | 0002 | F0Z-708968 | AFC | IFC | 2022-02-08 | 2022-03-09 | 2022-03-12 | 29 | 3 | 32 | IFA | 2022-05-24 | 2022-06-01 | 2022-05-31 | 8 | -1 | 7 | AFC | 2022-09-28 | 2022-10-04 | 2022-10-08 | 6 | 4 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-25 | 2022-09-14 |  | D02 | AFC | T-1401 | 44818 | 1401/06/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05775 | 44832 | 1401/07/06 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249313 | 44838 | 1401/07/12 | 44842 | 1401/07/16 | AP | NISCO-CRS-BK-GCS-PEDCO-120-IN-LI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0509 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-INS-00-03017 | 44601 | 1400/11/20 | CM-C3 | [6 empty] | 1400-2294-442053 | 2022-03-09 | 1400/12/18 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0926 | 44691 | 1401/02/20 |  |  |  | BK-SUR-ENG-INS-01-04433 | 44705 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0002_D00 | [5 empty] | 1401-2294-78885 | 44713 | 1401/03/08 | 44712 | 1401/03/10 | AP | NISCO-CRS-BK-GCS-NISCO-120-IN-LI-0002_D00 | [9 empty] | D02 | AFC | T-1401 | 44818 | 1401/06/23 |  |  |  | BK-SUR-ENG-INS-01-05775 | 44832 | 1401/07/06 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0002_D01 | [5 empty] | 1401-2294-249313 | 44838 | 1401/07/12 | 44842 | 1401/07/16 | AP | NISCO-CRS-BK-GCS-PEDCO-120-IN-LI-0002_D01
3 | 2 | 3 | 5 | 4 | 0 | 3 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0003 | I/O List For ESD Systems |  | BK-GCS-PEDCO-120-IN-LI-0003 | BK-GCS-PEDCO-120-IN-LI-0003 | BK | GCS | PEDCO | 120 | IN | LI | 0003 | F0Z-708969 | AFC | IFC | 2022-02-08 | 2022-03-09 | 2022-03-12 | 29 | 3 | 32 | IFA | 2022-05-28 | 2022-05-31 | 2022-06-06 | 3 | 6 | 9 | AFC | 2022-09-27 | 0 | 0 | -44831 | 0 | -44831 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-25 | 2022-09-13 |  | D02 | AFC | T-1397 | 44817 | 1401/06/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05707 | 44818 | 1401/06/23 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISCO-CRS-BK-GCS-NISCO-120-IN-LI-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0509 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-INS-00-03017 | 44601 | 1400/11/20 | CM-C3 | [6 empty] | 1400-2294-442053 | 2022-03-09 | 1400/12/18 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0941 | 44695 | 1401/02/24 | T-0941 | 44695 | 1401/02/24 | BK-SUR-ENG-INS-01-04473 | 44710 | 1401/03/08 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0003_D00 | [5 empty] | 1401-2294-85214 | 44712 | 1401/03/10 | 44718 | 1401/03/16 | AP | NISCO-CRS-BK-GCS-NISCO-120-IN-LI-0003_D00 | [9 empty] | D02 | AFC | T-1397 | 44817 | 1401/06/22 |  |  |  | BK-SUR-ENG-INS-01-05707 | 44818 | 1401/06/23 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0003_D01 | [11 empty] | NISCO-CRS-BK-GCS-NISCO-120-IN-LI-0003_D01
3 | 2 | 3 | 5 | 4 | 0 | 4 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0004 | I/O List For F&G Systems |  | BK-GCS-PEDCO-120-IN-LI-0004 | BK-GCS-PEDCO-120-IN-LI-0004 | BK | GCS | PEDCO | 120 | IN | LI | 0004 | F0Z-708970 | AFC | IFC | 2022-02-21 | 2022-05-10 | 2022-03-13 | 78 | -58 | 20 | IFA | 2022-05-25 | 2022-06-07 | 2022-06-11 | 13 | 4 | 17 | IFA | 2022-10-17 | 2022-11-05 | 2022-11-07 | 19 | 2 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-07 |  |  | D02 | IFA | T-1450 | 44837 | 1401/0`7/11 | T-1450 | 44835 | 1401/07/11 | BK-SUR-ENG-INS-01-05923 | 44852 | 1401/07/26 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296403 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0561 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-INS-00-03136 | 44612 | 1400/12/01 | CM-C3 | [6 empty] | 1400-2294-421738 | 2022-02-22 | 1400/12/03 | 44622 | 1400/12/11 | CM |  | 1400-2294-443333 | 44691 | 1400/12/19 | 44633 | 1400/12/22 | CM |  |  |  | D01 | IFA | T-0931 | 44692 | 1401/02/21 |  |  |  | BK-SUR-ENG-INS-01-04458 | 44709 | 1401/03/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D00 | [5 empty] | 1401-2294-92293 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D00 | [9 empty] | D02 | IFA | T-1450 | 44837 | 1401/0`7/11 | T-1450 | 44835 | 1401/07/11 | BK-SUR-ENG-INS-01-05923 | 44852 | 1401/07/26 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D01 | [5 empty] | 1401-2294-296403 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D01
3 | 2 | 3 | 5 | 4 | 0 | 5 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0005 | Panels & Junction Box List |  | BK-GCS-PEDCO-120-IN-LI-0005 | BK-GCS-PEDCO-120-IN-LI-0005 | BK | GCS | PEDCO | 120 | IN | LI | 0005 | F0Z-708971 | AFC | IFC | 2022-02-27 | 2022-03-03 | 2022-03-08 | 4 | 5 | 9 | IFA | 2022-06-26 | 2022-08-09 | 2022-08-14 | 44 | 5 | 49 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 |  |  | D01 | IFA | T-1066 | 44724 | 1401/03/22 | T-1066 | 44724 | 1401/03/22 | BK-SUR-ENG-INS-01-04840 | 44734 | 1401/04/01 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171118 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0587 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-INS-00-03250 | 44619 | 1400/12/08 | RJ-C4 | [6 empty] | 1400-2294-432761 | 2022-03-03 | 1400/12/12 | 44628 | 1400/12/17 | CM | [10 empty] | D01 | IFA | T-1066 | 44724 | 1401/03/22 | T-1066 | 44724 | 1401/03/22 | BK-SUR-ENG-INS-01-04840 | 44734 | 1401/04/01 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0005_D00 | [5 empty] | 1401-2294-171118 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0005_D00
3 | 2 | 3 | 5 | 4 | 0 | 6 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0006 | Set Point & Alarm List |  | BK-GCS-PEDCO-120-IN-LI-0006 | BK-GCS-PEDCO-120-IN-LI-0006 | BK | GCS | PEDCO | 120 | IN | LI | 0006 | F0Z-708972 | AFC | IFC | 2022-05-23 | 2022-06-15 | 2022-06-19 | 23 | 4 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-09 |  |  | D00 | IFC | T-0920 | 44690 | 1401/02/19 | T-0920 | 44690 | 1401/02/19 | BK-SUR-ENG-INS-01-04457 | 44709 | 1401/03/07 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-104549 | 44727 | 1401/03/25 | 44731 | 1401/03/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0920 | 2022-05-09 | 1401/02/19 | T-0920 | 44690 | 1401/02/19 | BK-SUR-ENG-INS-01-04457 | 44709 | 1401/03/07 | CM-C3 | [6 empty] | 1401-2294-104549 | 2022-06-15 | 1401/03/25 | 44731 | 1401/03/29 | CM
3 | 2 | 3 | 5 | 4 | 0 | 7 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0007 | I&C Power Consumption Summary |  | BK-GCS-PEDCO-120-IN-LI-0007 | BK-GCS-PEDCO-120-IN-LI-0007 | BK | GCS | PEDCO | 120 | IN | LI | 0007 | F0Z-708973 | AFC | IFC | 2022-03-09 | 2022-03-16 | 2022-03-27 | 7 | 11 | 18 | IFA | 2022-05-04 | 2022-05-01 | 2022-05-02 | -3 | 1 | -2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-23 |  |  | D01 | IFA | T-0852 | 44671 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04170 | 44689 | 1401/02/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-47232 | 44682 | 1401/02/11 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0633 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-INS-00-03437 | 44629 | 1400/12/18 | CM-C3 | [6 empty] | 1400-2294-453220 | 2022-03-16 | 1400/12/25 | 44647 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-0852 | 44671 | 1401/01/31 |  |  |  | BK-SUR-ENG-INS-01-04170 | 44689 | 1401/02/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D00 | [5 empty] | 1401-2294-47232 | 44682 | 1401/02/11 | 44683 | 1401/02/12 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D00
3 | 2 | 3 | 5 | 4 | 0 | 8 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0008 | F&G Detector List |  | BK-GCS-PEDCO-120-IN-LI-0008 | BK-GCS-PEDCO-120-IN-LI-0008 | BK | GCS | PEDCO | 120 | IN | LI | 0008 | F0Z-708974 | AFC | IFC | 2022-02-21 | 2022-05-10 | 2022-03-13 | 78 | -58 | 20 | IFA | 2022-05-24 | 2022-06-01 | 2022-05-31 | 8 | -1 | 7 | AFC | 2022-10-18 | 2022-10-30 | 2022-10-01 | 12 | -29 | -17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-07 |  |  | D02 | AFC | T-1455 | 44838 | 1401/07/12 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05930 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0008_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-286142 | 44864 | 1401/08/08 | 44835 | 1401/08/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0561 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-INS-00-03136 | 44612 | 1400/12/01 | CM-C3 | [6 empty] | 1400-2294-421738 | 2022-02-22 | 1400/12/03 | 44622 | 1400/12/11 | CM |  | 1400-2294-443233 | 44691 | 1400/12/19 | 44633 | 1400/12/22 | CM |  |  |  | D01 | IFA | T-0926 | 44691 | 1401/02/20 |  |  |  | BK-SUR-ENG-INS-01-04433 | 44705 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0008_D00 | [5 empty] | 1401-2294-78885 | 44713 | 1401/03/08 | 44712 | 1401/03/10 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0008_D00 | [9 empty] | D02 | AFC | T-1455 | 44838 | 1401/07/12 |  |  |  | BK-SUR-ENG-INS-01-05930 | 44853 | 1401/07/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0008_D01 | [5 empty] | 1401-2294-286142 | 44864 | 1401/08/08 | 44835 | 1401/08/10 | CM
3 | 2 | 3 | 5 | 4 | 0 | 9 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0009 | Instrument /F&G Cable List |  | BK-GCS-PEDCO-120-IN-LI-0009 | BK-GCS-PEDCO-120-IN-LI-0009 | BK | GCS | PEDCO | 120 | IN | LI | 0009 | F0Z-708975 | AFC | IFC | 2022-02-27 | 2022-03-03 | 2022-03-08 | 4 | 5 | 9 | IFA | 2022-06-26 | 2022-08-09 | 2022-08-14 | 44 | 5 | 49 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-13 |  |  | D01 | IFA | T-1066 | 44724 | 1401/03/22 | T-1066 | 44724 | 1401/03/22 | BK-SUR-ENG-INS-01-04840 | 44734 | 1401/04/01 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0009_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-171118 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0587 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-INS-00-03250 | 44619 | 1400/12/08 | RJ-C4 | [6 empty] | 1400-2294-432761 | 2022-03-03 | 1400/12/12 | 44628 | 1400/12/17 | CM | [10 empty] | D01 | IFA | T-1066 | 44724 | 1401/03/22 | T-1066 | 44724 | 1401/03/22 | BK-SUR-ENG-INS-01-04840 | 44734 | 1401/04/01 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0009_D00 | [5 empty] | 1401-2294-171118 | 44782 | 1401/05/18 | 44787 | 1401/05/23 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0009_D00
3 | 2 | 3 | 5 | 4 | 0 | 10 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0010 | Cable Schedule For CCTV | Cable Schedule For PROCESS CCTV | BK-GCS-PEDCO-120-IN-LI-0010 | BK-GCS-PEDCO-120-IN-LI-0010 | BK | GCS | PEDCO | 120 | IN | LI | 0010 | F0Z-708976 | AFC | IFC | 2022-07-11 | 2022-09-28 | 2022-10-02 | 79 | 4 | 83 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-27 |  |  | D00 | IFC | T-1125 | 44739 | 1401/04/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05230 | 44766 | 1401/05/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238953 | 44832 | 1401/07/06 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1125 | 2022-06-27 | 1401/04/06 |  |  |  | BK-SUR-ENG-INS-01-05230 | 44766 | 1401/05/02 | AP | [6 empty] | 1401-2294-238953 | 2022-09-28 | 1401/07/06 | 44836 | 1401/07/10 | CM
3 | 2 | 3 | 5 | 4 | 0 | 11 | 3.2.3.5.4 | BK-GCS-PEDCO-120-IN-LI-0011 | Cable Schedule For CCTV in Binak DU Area |  | BK-GCS-PEDCO-120-IN-LI-0011 | BK-GCS-PEDCO-120-IN-LI-0011 | BK | GCS | PEDCO | 120 | IN | LI | 0011 | F0Z-708977 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 5 | 5 | 0 | 0 | 3.2.3.5.5 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 5 | 5 | 0 | 1 | 3.2.3.5 | BK-GCS-PEDCO-120-IN-MT-0001 | MTO for Bulk Item and Installation Accessories |  | BK-GCS-PEDCO-120-IN-MT-0001 | BK-GCS-PEDCO-120-IN-MT-0001 | BK | GCS | PEDCO | 120 | IN | MT | 0001 | F8Z-708978 | IFI | IFI | 2022-07-12 | 2022-08-21 | 2022-08-23 | 40 | 2 | 42 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-28 |  |  | D00 | IFI | T-1130 | 44740 | 1401/04/07 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05337 | 44775 | 1401/05/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-1879769 | 44794 | 1401/05/30 | 44796 | 1401/06/01 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1130 | 2022-06-28 | 1401/04/07 |  |  |  | BK-SUR-ENG-INS-01-05337 | 44775 | 1401/05/11 | CM-C3 | [6 empty] | 1401-2294-1879769 | 2022-08-21 | 1401/05/30 | 44796 | 1401/06/01 | CM
3 | 2 | 3 | 5 | 5 | 0 | 2 | 3.2.3.5 | BK-GCS-PEDCO-120-IN-MT-0002 | MTO For Instrument/F&G Cable |  | BK-GCS-PEDCO-120-IN-MT-0002 | BK-GCS-PEDCO-120-IN-MT-0002 | BK | GCS | PEDCO | 120 | IN | MT | 0002 | F8Z-708979 | IFI | IFI | 2022-06-26 | 2022-08-11 | 2022-08-15 | 46 | 4 | 50 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | T-1069 | 44724 | 1401/03/22 | T-1069 | 44724 | 1401/03/22 | BK-SUR-ENG-INS-01-05637 | 44816 | 1401/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-172902 | 44784 | 1401/05/20 | 44788 | 1401/05/24 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1069 | 2022-06-12 | 1401/03/22 | T-1069 | 44724 | 1401/03/22 | BK-SUR-ENG-INS-01-05637 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-172902 | 2022-08-11 | 1401/05/20 | 44788 | 1401/05/24 | RJ
3 | 2 | 3 | 5 | 5 | 0 | 3 | 3.2.3.5 | BK-GCS-PEDCO-120-IN-MT-0003 | MTO For Instrument/F&G Junction box and Gland |  | BK-GCS-PEDCO-120-IN-MT-0003 | BK-GCS-PEDCO-120-IN-MT-0003 | BK | GCS | PEDCO | 120 | IN | MT | 0003 | F8Z-708980 | IFI | IFI | 2022-07-12 | 2022-08-21 | 2022-08-23 | 40 | 2 | 42 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-28 |  |  | D00 | IFI | T-1130 | 44740 | 1401/04/07 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05337 | 44775 | 1401/05/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-1879769 | 44794 | 1401/05/30 | 44796 | 1401/06/01 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1130 | 2022-06-28 | 1401/04/07 |  |  |  | BK-SUR-ENG-INS-01-05337 | 44775 | 1401/05/11 | CM-C3 | [6 empty] | 1401-2294-1879769 | 2022-08-21 | 1401/05/30 | 44796 | 1401/06/01 | CM
3 | 2 | 3 | 5 | 5 | 0 | 4 | 3.2.3.5 | BK-GCS-PEDCO-120-IN-MT-0004 | MTO For Instrument Tube and Fitting |  | BK-GCS-PEDCO-120-IN-MT-0004 | BK-GCS-PEDCO-120-IN-MT-0004 | BK | GCS | PEDCO | 120 | IN | MT | 0004 | F8Z-708981 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 5 | 5 | 0 | 5 | 3.2.3.5 | BK-GCS-PEDCO-120-IN-MT-0005 | MTO For Instrument Cable Tray/Ladder |  | BK-GCS-PEDCO-120-IN-MT-0005 | BK-GCS-PEDCO-120-IN-MT-0005 | BK | GCS | PEDCO | 120 | IN | MT | 0005 | F8Z-708982 | IFI | IFI | 2022-08-14 | 2022-10-01 | 2022-10-10 | 48 | 9 | 57 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-31 |  |  | D00 | IFI | T-1223 | 44773 | 1401/05/09 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05467 | 44789 | 1401/05/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-242351 | 44835 | 1401/07/09 | 44844 | 1401/07/18 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1223 | 2022-07-31 | 1401/05/09 |  |  |  | BK-SUR-ENG-INS-01-05467 | 44789 | 1401/05/25 | CM-C2 | [6 empty] | 1401-2294-242351 | 2022-10-01 | 1401/07/09 | 44844 | 1401/07/18 | CM
3 | 2 | 3 | 5 | 5 | 0 | 6 | 3.2.3.5 | BK-GCS-PEDCO-120-IN-MT-0006 | MTO For CCTV |  | BK-GCS-PEDCO-120-IN-MT-0006 | BK-GCS-PEDCO-120-IN-MT-0006 | BK | GCS | PEDCO | 120 | IN | MT | 0006 | F8Z-708983 | IFI | IFI | 2021-12-26 | 2021-12-22 | 2021-12-26 | -4 | 4 | 0 | IFI | 2022-02-26 | 2022-02-22 | 2022-02-02 | -4 | -20 | -24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-12 |  |  | D01 | IFI | T-0572 | 44604 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03147 | 44613 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421739 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0329 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-INS-00-02405 | 44552 | 1400/10/01 | AP | [6 empty] | 1400-2294-330916 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFI | T-0572 | 44604 | 1400/11/23 |  |  |  | BK-SUR-ENG-INS-00-03147 | 44613 | 1400/12/02 | AP | [6 empty] | 1400-2294-421739 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MT-0006_D00
3 | 2 | 3 | 5 | 5 | 0 | 7 | 3.2.3.5 | BK-GCS-PEDCO-120-IN-MT-0007 | MTO For CCTV in Binak DU Area |  | BK-GCS-PEDCO-120-IN-MT-0007 | BK-GCS-PEDCO-120-IN-MT-0007 | BK | GCS | PEDCO | 120 | IN | MT | 0007 | F8Z-708984 | IFI | IFI | 2021-12-27 | 2021-12-22 | 2021-12-26 | -5 | 4 | -1 | IFI | 2022-05-16 | 2022-05-21 | 2022-05-23 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D01 | IFI | T-0897 | 44683 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04223 | 44691 | 1401/02/20 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MT-0007_D00 | BK-SUR-ENG-INS-01-04259 | 44695 | 1401/02/24 | AP | 0 | 1401-2294-70041 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0336 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02419 | 44555 | 1400/10/05 | AP | [6 empty] | 1400-2294-330942 | 2021-12-22 | 1400/10/01 | 44556 | 1400/10/05 | CM | [10 empty] | D01 | IFI | T-0897 | 44683 | 1401/02/12 |  |  |  | BK-SUR-ENG-INS-01-04223 | 44691 | 1401/02/20 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MT-0007_D00 | BK-SUR-ENG-INS-01-04259 | 44695 | 1401/02/24 | AP |  | 1401-2294-70041 | 44702 | 1401/02/31 | 44704 | 1401/03/02 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MT-0007_D00
3 | 2 | 3 | 6 | 0 | 0 | 0 | 3.2.3.6 |  | Safety & Fire Fighting | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 6 | 1 | 0 | 0 | 3.2.3.6.1 |  | Basis/Criteria | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 6 | 1 | 0 | 1 | 3.2.3.6.1 | BK-GCS-PEDCO-120-SA-DB-0001 | Active Fire Protection and Safety Concept |  | BK-GCS-PEDCO-120-SA-DB-0001 | BK-GCS-PEDCO-120-SA-DB-0001 | BK | GCS | PEDCO | 120 | SA | DB | 0001 | F0Z-708985 | AFD | IFC | 2021-09-28 | 2021-10-09 | 2021-10-13 | 11 | 4 | 15 | IFA | 2022-10-18 | 2022-11-03 | 2022-11-05 | 16 | 2 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-14 |  |  | D01 | IFA | T-1458 | 44838 | 1401/07/12 | T-1459 | 44842 | 1401/07/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294064 | 44868 | 1401/08/12 | 44870 | 1401/08/15 | AP | NISOC-CRS- BK-GCS-PEDCO-120-SA-DB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0093 | 2021-09-14 | 1400/06/23 | [13 empty] | 1400-2290-225647 | 2021-10-09 | 1400/07/17 | 44482 | 1400/07/21 | CM | [10 empty] | D01 | IFA | T-1458 | 44838 | 1401/07/12 | T-1459 | 44842 | 1401/07/16 | [10 empty] | 1401-2294-294064 | 44868 | 1401/08/12 | 44870 | 1401/08/15 | AP | NISOC-CRS- BK-GCS-PEDCO-120-SA-DB-0001_D00
3 | 2 | 3 | 6 | 2 | 0 | 0 | 3.2.3.6.2 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 6 | 2 | 0 | 1 | 3.2.3.6.2 | BK-GCS-PEDCO-120-SA-CN-0001 | Calculation Note For Total Flooding Demand For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-SA-CN-0001 | BK-GCS-PEDCO-120-SA-CN-0001 | BK | GCS | PEDCO | 120 | SA | CN | 0001 | F0Z-708986 | AFD | IFC | 2022-01-30 | 2022-02-16 | 2022-02-22 | 17 | 6 | 23 | AFD | 2022-03-23 | 2022-03-12 | 2022-03-15 | -11 | 3 | -8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-16 | 2022-03-09 |  | D01 | AFD | T-0704 | 44629 | 1400/12/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445301 | 44632 | 1400/12/21 | 44635 | 1400/12/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0465 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-412869 | 2022-02-16 | 1400/11/27 | 44614 | 1400/12/03 | AP | [10 empty] | D01 | AFD | T-0704 | 44629 | 1400/12/19 | [13 empty] | 1400-2294-445301 | 44632 | 1400/12/21 | 44635 | 1400/12/24 | AP
3 | 2 | 3 | 6 | 2 | 0 | 2 | 3.2.3.6.2 | BK-GCS-PEDCO-120-SA-CN-0002 | Calculation Note For Fire Water Demand |  | BK-GCS-PEDCO-120-SA-CN-0002 | BK-GCS-PEDCO-120-SA-CN-0002 | BK | GCS | PEDCO | 120 | SA | CN | 0002 | F0Z-708987 | AFD | IFC | 2021-12-27 | 2021-01-02 | 2022-01-04 | -359 | 367 | 8 | IFA | 2022-01-29 | 2022-02-16 | 2022-02-22 | 18 | 6 | 24 | IFA | 2022-06-05 | 2022-08-02 | 2022-08-06 | 58 | 4 | 62 | IFA | 2022-09-17 | 2022-11-03 | 2022-11-05 | 47 | 2 | 49 | AFD | 2022-11-22 | 0 | 0 | -44887 | 0 | -44887 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 | 2022-11-08 |  | D04 | AFD | T-1581 | 44873 | 1401/08/17 | T-1581 | 44873 | 1401/08/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0333 | 2021-12-13 | 1400/09/22 | [13 empty] | 1400-2294-345121 | 2021-01-02 | 1400/10/12 | 44565 | 1400/10/14 | CM | [10 empty] | D01 | IFA | T-0457 | 44576 | 1400/10/22 | [13 empty] | 1400-2294-412382 | 44608 | 1400/11/27 | 44614 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-SA-CN-0002_D00 | [9 empty] | D02 | IFA | T-0985 | 44703 | 1401/03/01 | T-0985 | 44704 | 1401/03/02 | [10 empty] | 1401-2294-165031 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-SA-CN-0002_D01 | [9 empty] | D03 | IFA | T-1346 | 44807 | 1401/06/12 | [13 empty] | 1401-2294-294112 | 44868 | 1401/08/12 | 44870 | 1401/08/15 | AP | NISOC-CRS-BK-GCS-PEDCO-120-SA-CN-0002_D02 | [9 empty] | D04 | AFD | T-1581 | 44873 | 1401/08/17 | T-1581 | 44873 | 1401/08/17
3 | 2 | 3 | 6 | 2 | 0 | 3 | 3.2.3.6.2 | BK-GCS-PEDCO-120-SA-CN-0003 | Fire Water Hydraulic Calculation Note |  | BK-GCS-PEDCO-120-SA-CN-0003 | BK-GCS-PEDCO-120-SA-CN-0003 | BK | GCS | PEDCO | 120 | SA | CN | 0003 | F0Z-708988 | AFD | IFC | 2022-06-05 | 2022-08-14 | 2022-08-16 | 70 | 2 | 72 | IFA | 2022-11-20 | 0 | 0 | -44885 | 0 | -44885 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-22 |  |  | D01 | IFA | T-1577 | 44871 | 1401/08/15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-SA-CN-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0986 | 2022-05-22 | 1401/03/01 | T-0986 | 44704 | 1401/03/02 | [10 empty] | 1401-2294-177132 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM | [10 empty] | D01 | IFA | T-1577 | 44871 | 1401/08/15 | [19 empty] | NISOC-CRS-BK-GCS-PEDCO-120-SA-CN-0003_D00
3 | 2 | 3 | 6 | 3 | 0 | 0 | 3.2.3.6.3 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 6 | 3 | 0 | 1 | 3.2.3.6.3 | BK-GCS-PEDCO-120-SA-DT-0002 | Data Sheets For Safety Equipment |  | BK-GCS-PEDCO-120-SA-DT-0002 | BK-GCS-PEDCO-120-SA-DT-0002 | BK | GCS | PEDCO | 120 | SA | DT | 0002 | F0Z-708989 | AFC | IFC | 2022-05-03 | 2022-05-30 | 2022-06-06 | 27 | 7 | 34 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-19 |  |  | D01 | IFA | T-1475 | 44844 | 1401/07/18 | T-1475 | 44844 | 1401/07/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS- BK-GCS-PEDCO-120-SA-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0842 | 2022-04-19 | 1401/01/30 | [13 empty] | 1401-2294-82959 | 2022-05-30 | 1401/03/09 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1475 | 44844 | 1401/07/18 | T-1475 | 44844 | 1401/07/18 | [16 empty] | NISOC-CRS- BK-GCS-PEDCO-120-SA-DT-0002_D00
3 | 2 | 3 | 6 | 3 | 0 | 2 | 3.2.3.6.3 | BK-GCS-PEDCO-120-SA-DT-0003 | Data Sheets For Fire Fighting Equipment |  | BK-GCS-PEDCO-120-SA-DT-0003 | BK-GCS-PEDCO-120-SA-DT-0003 | BK | GCS | PEDCO | 120 | SA | DT | 0003 | F0Z-708990 | AFC | IFC | 2022-05-02 | 2022-05-17 | 2022-05-23 | 15 | 6 | 21 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-18 |  |  | D01 | IFA | T-1475 | 44844 | 1401/07/18 | T-1475 | 44844 | 1401/07/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS- BK-GCS-PEDCO-120-SA-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0837 | 2022-04-18 | 1401/01/29 | [13 empty] | 1401-2294-65658 | 2022-05-17 | 1401/02/27 | 44704 | 1401/03/02 | CM | [10 empty] | D01 | IFA | T-1475 | 44844 | 1401/07/18 | T-1475 | 44844 | 1401/07/18 | [16 empty] | NISOC-CRS- BK-GCS-PEDCO-120-SA-DT-0003_D00
3 | 2 | 3 | 6 | 3 | 0 | 3 | 3.2.3.6.3 | BK-GCS-PEDCO-120-SA-DT-0004 | Data Sheets For Deluge valves |  | BK-GCS-PEDCO-120-SA-DT-0004 | BK-GCS-PEDCO-120-SA-DT-0004 | BK | GCS | PEDCO | 120 | SA | DT | 0004 | F0Z-708991 | AFC | IFC | 2022-01-30 | 2022-02-16 | 2022-02-22 | 17 | 6 | 23 | IFA | 2022-06-05 | 2022-08-02 | 2022-08-06 | 58 | 4 | 62 | IFA | 2022-10-24 | 0 | 0 | -44858 | 0 | -44858 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-16 |  |  | D02 | IFA | T-1475 | 44844 | 1401/07/18 | T-1475 | 44844 | 1401/07/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS- BK-GCS-PEDCO-120-SA-DT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0465 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-412869 | 2022-02-16 | 1400/11/27 | 44614 | 1400/12/03 | CM | [10 empty] | D01 | IFA | T-0985 | 44703 | 1401/03/01 | T-0985 | 44704 | 1401/03/02 | [10 empty] | 1401-2294-165031 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-SA-DT-0004_D00 | [9 empty] | D02 | IFA | T-1475 | 44844 | 1401/07/18 | T-1475 | 44844 | 1401/07/18 | [16 empty] | NISOC-CRS- BK-GCS-PEDCO-120-SA-DT-0004_D00
3 | 2 | 3 | 6 | 3 | 0 | 4 | 3.2.3.6.3 | BK-GCS-PEDCO-120-SA-DT-0005 | Data Sheets For Water Spray Nozzles |  | BK-GCS-PEDCO-120-SA-DT-0005 | BK-GCS-PEDCO-120-SA-DT-0005 | BK | GCS | PEDCO | 120 | SA | DT | 0005 | F0Z-708992 | AFC | IFC | 2022-06-05 | 2022-08-14 | 2022-08-16 | 70 | 2 | 72 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-22 |  |  | D00 | IFC | T-0986 | 44703 | 1401/03/01 | T-0986 | 44704 | 1401/03/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177132 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0986 | 2022-05-22 | 1401/03/01 | T-0986 | 44704 | 1401/03/02 | [10 empty] | 1401-2294-177132 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | AP
3 | 2 | 3 | 6 | 3 | 0 | 5 | 3.2.3.6.3 | BK-GCS-PEDCO-120-SA-DT-0006 | Data Sheets For Safety Sign |  | BK-GCS-PEDCO-120-SA-DT-0006 | BK-GCS-PEDCO-120-SA-DT-0006 | BK | GCS | PEDCO | 120 | SA | DT | 0006 | F0Z-708993 | AFC | IFC | 2021-10-04 | 2021-10-10 | 2021-10-13 | 6 | 3 | 9 | IFA | 2022-10-18 | 2022-11-03 | 2022-11-05 | 16 | 2 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-20 |  |  | D01 | IFA | T-1458 | 44838 | 1401/07/12 | T-1459 | 44842 | 1401/07/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-294064 | 44868 | 1401/08/12 | 44870 | 1401/08/15 | AP | NISOC-CRS- BK-GCS-PEDCO-120-SA-DT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0106 | 2021-09-20 | 1400/06/29 | [13 empty] | 1400-2290-227968 | 2021-10-10 | 1400/07/18 | 44482 | 1400/07/21 | CM | [10 empty] | D01 | IFA | T-1458 | 44838 | 1401/07/12 | T-1459 | 44842 | 1401/07/16 | [10 empty] | 1401-2294-294064 | 44868 | 1401/08/12 | 44870 | 1401/08/15 | AP | NISOC-CRS- BK-GCS-PEDCO-120-SA-DT-0006_D00
3 | 2 | 3 | 6 | 4 | 0 | 0 | 3.2.3.6.4 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 6 | 4 | 0 | 1 | 3.2.3.6.4 | BK-GCS-PEDCO-120-SA-PF-0001 | PFD - Fire Water System |  | BK-GCS-PEDCO-120-SA-PF-0001 | BK-GCS-PEDCO-120-SA-PF-0001 | BK | GCS | PEDCO | 120 | SA | PF | 0001 | F2A-708994 | AFC | IFC | 2021-12-27 | 2021-01-02 | 2022-01-04 | -359 | 367 | 8 | IFA | 2022-11-20 | 0 | 0 | -44885 | 0 | -44885 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D01 | IFA | T-1577 | 44871 | 1401/08/15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-SA-PF-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0333 | 2021-12-13 | 1400/08/22 | [13 empty] | 1400-2294-345121 | 2021-01-02 | 1400/10/12 | 44565 | 1400/10/14 | CM | [10 empty] | D01 | IFA | T-1577 | 44871 | 1401/08/15 | [19 empty] | NISOC-CRS-BK-GCS-PEDCO-120-SA-PF-0001_D00
3 | 2 | 3 | 6 | 4 | 0 | 2 | 3.2.3.6.4 | BK-GCS-PEDCO-120-SA-PI-0001 | P&ID - Fire Water Network |  | BK-GCS-PEDCO-120-SA-PI-0001 | BK-GCS-PEDCO-120-SA-PI-0001 | BK | GCS | PEDCO | 120 | SA | PI | 0001 | F2A-708995 | AFC | IFC | 2022-02-26 | 2022-04-19 | 2022-04-30 | 52 | 11 | 63 | IFA | 2022-06-05 | 2022-08-02 | 2022-08-06 | 58 | 4 | 62 | IFA | 2022-11-20 | 0 | 0 | -44885 | 0 | -44885 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-12 |  |  | D02 | IFA | T-1577 | 44871 | 1401/08/15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-SA-PI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0571 | 2022-02-12 | 1400/11/23 | [13 empty] | 1400-2294-451052 | 2022-03-15 | 1400/12/24 | 44652 | 1401/01/14 | CM |  | 1401-2294-31220 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM |  |  |  | D01 | IFA | T-0985 | 44703 | 1401/03/01 | T-0985 | 44704 | 1401/03/02 | [10 empty] | 1401-2294-165031 | 44775 | 1401/05/11 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-SA-PI-0001_D00 | [9 empty] | D02 | IFA | T-1577 | 44871 | 1401/08/15 | [19 empty] | NISOC-CRS-BK-GCS-PEDCO-120-SA-PI-0001_D00
3 | 2 | 3 | 6 | 4 | 0 | 3 | 3.2.3.6.4 | BK-GCS-PEDCO-120-SA-PI-0002 | P&ID - Total Flooding System For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-SA-PI-0002 | BK-GCS-PEDCO-120-SA-PI-0002 | BK | GCS | PEDCO | 120 | SA | PI | 0002 | F2A-708996 | AFC | IFC | 2022-01-30 | 2022-02-16 | 2022-02-22 | 17 | 6 | 23 | IFA | 2022-04-20 | 2022-05-09 | 2022-05-16 | 19 | 7 | 26 | AFC | 2022-08-14 | 2022-08-18 | 2022-08-21 | 4 | 3 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-16 |  |  | D02 | AFC | T-1226 | 44773 | 1401/05/09 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05867 | 44844 | 1401/07/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183505 | 44791 | 1401/05/27 | 44794 | 1401/05/30 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0465 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-412869 | 2022-02-16 | 1400/11/27 | 44614 | 1400/12/03 | CM | [10 empty] | D01 | IFA | T-0779 | 44657 | 1401/01/17 | [13 empty] | 1401-2294-55024 | 44690 | 1401/02/19 | 44697 | 1401/02/26 | AP | NISOC-CRS-BK-GCS-PEDCO-120-SA-PI-0002-D00 | [9 empty] | D02 | AFC | T-1226 | 44773 | 1401/05/09 |  |  |  | BK-SUR-ENG-INS-01-05867 | 44844 | 1401/07/18 | CM-C3 | [6 empty] | 1401-2294-183505 | 44791 | 1401/05/27 | 44794 | 1401/05/30 | CM
3 | 2 | 3 | 6 | 4 | 0 | 4 | 3.2.3.6.4 | BK-GCS-PEDCO-120-SA-PY-0001 | Fire Water Network Layout |  | BK-GCS-PEDCO-120-SA-PY-0001 | BK-GCS-PEDCO-120-SA-PY-0001 | BK | GCS | PEDCO | 120 | SA | PY | 0001 | F2A-708997 | AFC | IFC | 2021-12-27 | 2021-01-02 | 2022-01-04 | -359 | 367 | 8 | IFA | 2022-05-11 | 2022-06-30 | 2022-07-05 | 50 | 5 | 55 | IFA | 2022-10-23 | 0 | 0 | -44857 | 0 | -44857 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D02 | IFA | T-1467 | 44843 | 1401/07/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0333 | 2021-12-13 | 1400/08/22 | [13 empty] | 1400-2294-345121 | 2021-01-02 | 1400/10/12 | 44565 | 1400/10/14 | CM | [10 empty] | D01 | IFA | T-0865 | 44678 | 1401/02/07 | T-0865 | 44678 | 1401/02/07 | [10 empty] | 1401-2294-124173 | 44742 | 1401/04/09 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0001_D00 | [9 empty] | D02 | IFA | T-1467 | 44843 | 1401/07/17 | [19 empty] | NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0001_D01
3 | 2 | 3 | 6 | 4 | 0 | 5 | 3.2.3.6.4 | BK-GCS-PEDCO-120-SA-PY-0002 | Hazardous Area Classification Layout |  | BK-GCS-PEDCO-120-SA-PY-0002 | BK-GCS-PEDCO-120-SA-PY-0002 | BK | GCS | PEDCO | 120 | SA | PY | 0002 | F2L-708998 | AFC | IFC | 2022-03-26 | 2022-04-13 | 2022-04-16 | 18 | 3 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-12 |  |  | D00 | IFC | T-0715 | 44632 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16831 | 44661 | 1401/01/21 | 44662 | 1401/01/22 | CM | 0 | 1401-2294-22713 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | CM | 0 | 0 |  | D00 | IFC | T-0715 | 2022-03-12 | 1400/12/21 | [13 empty] | 1401-2294-16831 | 2022-04-10 | 1401/01/21 | 44662 | 1401/01/22 | CM |  | 1401-2294-22713 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | CM
3 | 2 | 3 | 6 | 4 | 0 | 6 | 3.2.3.6.4 | BK-GCS-PEDCO-120-SA-PY-0003 | Fire Proofing Zone Layout |  | BK-GCS-PEDCO-120-SA-PY-0003 | BK-GCS-PEDCO-120-SA-PY-0003 | BK | GCS | PEDCO | 120 | SA | PY | 0003 | F2L-708999 | AFC | IFC | 2022-06-05 | 2022-08-14 | 2022-08-16 | 70 | 2 | 72 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-22 |  |  | D00 | IFC | T-0986 | 44703 | 1401/03/01 | T-0986 | 44704 | 1401/03/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177132 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0986 | 2022-05-22 | 1401/03/01 | T-0986 | 44704 | 1401/03/02 | [10 empty] | 1401-2294-177132 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM
3 | 2 | 3 | 6 | 4 | 0 | 7 | 3.2.3.6.4 | BK-GCS-PEDCO-120-SA-PY-0004 | Safety & Fire Fighting Equipment Location Layout |  | BK-GCS-PEDCO-120-SA-PY-0004 | BK-GCS-PEDCO-120-SA-PY-0004 | BK | GCS | PEDCO | 120 | SA | PY | 0004 | F2L-709000 | AFC | IFC | 2022-02-26 | 2022-04-19 | 2022-04-30 | 52 | 11 | 63 | IFA | 2022-05-28 | 2022-08-14 | 2022-08-16 | 78 | 2 | 80 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-12 |  |  | D01 | IFA | T-0943 | 44695 | 1401/02/24 | T-0943 | 44695 | 1401/02/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-176982 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0571 | 2022-02-12 | 1400/11/23 | [13 empty] | 1400-2294-451052 | 2022-03-15 | 1400/12/24 | 44652 | 1401/01/14 | CM |  | 1401-2294-31220 | 44670 | 1401/01/30 | 44681 | 1401/02/10 | CM |  |  |  | D01 | IFA | T-0943 | 44695 | 1401/02/24 | T-0943 | 44695 | 1401/02/24 | [10 empty] | 1401-2294-176982 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0004_D00
3 | 2 | 3 | 6 | 4 | 0 | 8 | 3.2.3.6.4 | BK-GCS-PEDCO-120-SA-PY-0005 | Escape Route & Safety Sign Layout |  | BK-GCS-PEDCO-120-SA-PY-0005 | BK-GCS-PEDCO-120-SA-PY-0005 | BK | GCS | PEDCO | 120 | SA | PY | 0005 | F2L-709001 | AFC | IFC | 2022-05-24 | 2022-06-10 | 2022-06-20 | 17 | 10 | 27 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-10 |  |  | D00 | IFC | T-0923 | 44691 | 1401/02/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94639 | 44722 | 1401/03/20 | 44732 | 1401/03/30 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0923 | 2022-05-10 | 1401/02/20 | [13 empty] | 1401-2294-94639 | 2022-06-10 | 1401/03/20 | 44732 | 1401/03/30 | CM
3 | 2 | 3 | 6 | 5 | 0 | 0 | 3.2.3.6.5 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 6 | 5 | 0 | 1 | 3.2.3.6.5 | BK-GCS-PEDCO-120-SA-LI-0001 | Hazard Source List |  | BK-GCS-PEDCO-120-SA-LI-0001 | BK-GCS-PEDCO-120-SA-LI-0001 | BK | GCS | PEDCO | 120 | SA | LI | 0001 | F0Z-709002 | AFC | IFC | 2022-03-09 | 2022-04-07 | 2022-04-07 | 29 | 0 | 29 | IFA | 2022-09-25 | 2022-11-20 | 2022-11-20 | 56 | 0 | 56 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-23 |  |  | D01 | IFA | T-1399 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-316902 | 44885 | 1401/08/29 | 44885 | 1401/08/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-SA-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0634 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-CIV-00-03328 | 44625 | 1400/12/14 | AP | [6 empty] | 1401-2294-13860 | 2022-04-07 | 1401/01/18 | 44658 | 1401/01/18 | CM | [10 empty] | D01 | IFA | T-1399 | 44815 | 1401/06/20 | T-1384 | 44816 | 1401/06/21 | [10 empty] | 1401-2294-316902 | 44885 | 1401/08/29 | 44885 | 1401/08/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-SA-LI-0001_D00
3 | 2 | 3 | 6 | 5 | 0 | 2 | 3.2.3.6.5 | BK-GCS-PEDCO-120-SA-LI-0002 | Fire Fighting Line List |  | BK-GCS-PEDCO-120-SA-LI-0002 | BK-GCS-PEDCO-120-SA-LI-0002 | BK | GCS | PEDCO | 120 | SA | LI | 0002 | F0Z-709003 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 6 | 6 | 0 | 0 | 3.2.3.6.6 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 6 | 6 | 0 | 1 | 3.2.3.6.6 | BK-GCS-PEDCO-120-SA-RT-0003 | Consequence Modeling Report |  | BK-GCS-PEDCO-120-SA-RT-0003 | BK-GCS-PEDCO-120-SA-RT-0003 | BK | GCS | PEDCO | 120 | SA | RT | 0003 | F0Z-709004 | IFI | IFC | 2021-12-05 | 2021-12-15 | 2021-12-18 | 10 | 3 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-21 |  |  | D00 | IFC | T-0261 | 44521 | 1400/08/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-319725 | 44545 | 1400/09/24 | 44548 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0261 | 2021-11-21 | 1400/08/30 | [13 empty] | 1400-2294-319725 | 2021-12-15 | 1400/09/24 | 44548 | 1400/09/27 | AP
3 | 2 | 3 | 6 | 7 | 0 | 0 | 3.2.3.6.7 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 6 | 7 | 0 | 1 | 3.2.3.6 | BK-GCS-PEDCO-120-SA-MT-0001 | MTO For Safety & Fire Fighting Equipment |  | BK-GCS-PEDCO-120-SA-MT-0001 | BK-GCS-PEDCO-120-SA-MT-0001 | BK | GCS | PEDCO | 120 | SA | MT | 0001 | F8Z-709005 | IFI | IFI | 2022-06-05 | 2022-07-07 | 2022-07-11 | 32 | 4 | 36 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-22 |  |  | D00 | IFI | T-0987 | 44703 | 1401/03/01 | T-0987 | 44704 | 1401/03/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-132731 | 44749 | 1401/04/16 | 44753 | 1401/04/20 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0987 | 2022-05-22 | 1401/03/01 | T-0987 | 44704 | 1401/03/02 | [10 empty] | 1401-2294-132731 | 2022-07-07 | 1401/04/16 | 44753 | 1401/04/20 | CM
3 | 2 | 3 | 6 | 7 | 0 | 2 | 3.2.3.6 | BK-GCS-PEDCO-120-SA-MT-0002 | MTO For Safety Sign |  | BK-GCS-PEDCO-120-SA-MT-0002 | BK-GCS-PEDCO-120-SA-MT-0002 | BK | GCS | PEDCO | 120 | SA | MT | 0002 | F8Z-709006 | IFI | IFI | 2022-05-29 | 2022-06-10 | 2022-06-11 | 12 | 1 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-15 |  |  | D00 | IFI | T-0952 | 44696 | 1401/02/25 | T-0952 | 44696 | 1401/02/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94605 | 44722 | 1401/03/20 | 44723 | 1401/03/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0952 | 2022-05-15 | 1401/02/25 | T-0952 | 44696 | 1401/02/25 | [10 empty] | 1401-2294-94605 | 2022-06-10 | 1401/03/20 | 44723 | 1401/03/21 | CM
3 | 2 | 3 | 7 | 0 | 0 | 0 | 3.2.3.7 |  | Electrical | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 7 | 1 | 0 | 0 | 3.2.3.7.1 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 7 | 1 | 0 | 1 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0001 | Calculation Note For Outdoor Area Lighting System |  | BK-GCS-PEDCO-120-EL-CN-0001 | BK-GCS-PEDCO-120-EL-CN-0001 | BK | GCS | PEDCO | 120 | EL | CN | 0001 | F0Z-709007 | AFD | IFC | 2022-07-06 | 2022-07-10 | 2022-07-23 | 4 | 13 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-22 |  |  | D00 | IFC | T-1107 | 44734 | 1401/04/01 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05009 | 44748 | 1401/04/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-135326 | 44752 | 1401/04/19 | 44765 | 1401/05/01 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1107 | 2022-06-22 | 1401/04/01 |  |  |  | BK-SUR-ENG-ELE-01-05009 | 44748 | 1401/04/15 | CM-C3 | [6 empty] | 1401-2294-135326 | 2022-07-10 | 1401/04/19 | 44765 | 1401/05/01 | CM
3 | 2 | 3 | 7 | 1 | 0 | 2 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0002 | Calculation Note For Indoor Area Lighting System |  | BK-GCS-PEDCO-120-EL-CN-0002 | BK-GCS-PEDCO-120-EL-CN-0002 | BK | GCS | PEDCO | 120 | EL | CN | 0002 | F0Z-709008 | AFD | IFC | 2022-05-11 | 2022-05-30 | 2022-06-06 | 19 | 7 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-27 |  |  | D00 | IFC | T-0873 | 44678 | 1401/02/07 | T-0873 | 44678 | 1401/02/07 | BK-SUR-ENG-ELE-01-04184 | 44690 | 1401/02/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-82853 | 44711 | 1401/03/09 | 44718 | 1401/03/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0873 | 2022-04-27 | 1401/02/07 | T-0873 | 44678 | 1401/02/07 | BK-SUR-ENG-ELE-01-04184 | 44690 | 1401/02/19 | CM-C3 | [6 empty] | 1401-2294-82853 | 2022-05-30 | 1401/03/09 | 44718 | 1401/03/16 | CM
3 | 2 | 3 | 7 | 1 | 0 | 3 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0003 | Calculation Note For Cable Sizing |  | BK-GCS-PEDCO-120-EL-CN-0003 | BK-GCS-PEDCO-120-EL-CN-0003 | BK | GCS | PEDCO | 120 | EL | CN | 0003 | F0Z-709009 | AFD | IFC | 2022-06-20 | 2022-07-03 | 2022-07-05 | 13 | 2 | 15 | IFA | 2022-10-18 | 2022-10-25 | 2022-10-29 | 7 | 4 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-06 |  |  | D01 | IFA | T-1456 | 44838 | 1401/07/12 | T-1456 | 44838 | 1401/07/12 | BK-SUR-ENG-ELE-01-05917 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-280883 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1041 | 2022-06-06 | 1401/03/16 | T-1041 | 44719 | 1401/03/17 | BK-SUR-ENG-ELE-01-04755 | 44732 | 1401/03/30 | CM-C2 | [6 empty] | 1401-2294-128509 | 2022-07-03 | 1401/04/12 | 44747 | 1401/04/14 | CM | [10 empty] | D01 | IFA | T-1456 | 44838 | 1401/07/12 | T-1456 | 44838 | 1401/07/12 | BK-SUR-ENG-ELE-01-05917 | 44852 | 1401/07/26 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0003_D00 | [5 empty] | 1401-2294-280883 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0003_D00
3 | 2 | 3 | 7 | 1 | 0 | 4 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0004 | Calculation Note For UPS System |  | BK-GCS-PEDCO-120-EL-CN-0004 | BK-GCS-PEDCO-120-EL-CN-0004 | BK | GCS | PEDCO | 120 | EL | CN | 0004 | F0Z-709010 | AFD | IFC | 2021-12-06 | 2021-12-17 | 2021-12-18 | 11 | 1 | 12 | IFA | 2022-01-09 | 2022-01-22 | 2022-01-25 | 13 | 3 | 16 | IFA | 2022-05-09 | 2022-06-07 | 2022-06-08 | 29 | 1 | 30 | IFA | 2022-08-17 | 2022-08-31 | 2022-09-04 | 14 | 4 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-22 |  |  | D03 | IFA | T-1237 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0266 | 2021-11-22 | 1400/09/01 |  |  |  | BK-SUR-ENG-ELE-00-02183 | 44534 | 1400/09/13 | CM-C2 | [6 empty] | 1400-2294-320825 | 2021-12-17 | 1400/09/26 | 44548 | 1400/09/27 | CM | [10 empty] | D01 | IFA | T-0379 | 44556 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02560 | 44565 | 1400/10/14 | CM-C3 | PEDCO-CRS- BK-GCS-PEDCO-120-EL-CN-0004_D00 | [5 empty] | 1400-2294-375310 | 44583 | 1400/11/02 | 44586 | 1400/11/05 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D00 | [9 empty] | D02 | IFA | T-0861 | 44676 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04178 | 44690 | 1401/02/19 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D01 | [5 empty] | 1401-2294-91107 | 44719 | 1401/03/17 | 44720 | 1401/03/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D01 | [9 empty] | D03 | IFA | T-1237 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D02 | [5 empty] | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D02
3 | 2 | 3 | 7 | 1 | 0 | 5 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0005 | Calculation Note For DC Charger System |  | BK-GCS-PEDCO-120-EL-CN-0005 | BK-GCS-PEDCO-120-EL-CN-0005 | BK | GCS | PEDCO | 120 | EL | CN | 0005 | F0Z-709011 | AFD | IFC | 2021-12-29 | 2022-01-06 | 2022-01-08 | 8 | 2 | 10 | IFA | 2022-02-02 | 2022-02-16 | 2022-02-21 | 14 | 5 | 19 | IFA | 2022-06-12 | 2022-06-25 | 2022-07-03 | 13 | 8 | 21 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-15 |  |  | D02 | IFA | T-1018 | 44710 | 1401/03/08 | T-1018 | 44710 | 1401/03/08 | BK-SUR-ENG-ELE-01-04640 | 44723 | 1401/03/21 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-122076 | 44737 | 1401/04/04 | 44745 | 1401/04/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0346 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-ELE-00-02432 | 44556 | 1400/10/05 | CM-C3 | [6 empty] | 1400-2294-352428 | 2022-01-06 | 1400/10/16 | 44569 | 1400/10/18 | CM | [10 empty] | D01 | IFA | T-0481 | 44580 | 1400/10/29 |  |  |  | BK-SUR-ENG-ELE-00-02888 | 44592 | 1400/11/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D00 | [5 empty] | 1400-2294-412403 | 44608 | 1400/11/27 | 44613 | 1400/11/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0005-D00 | [9 empty] | D02 | IFA | T-1018 | 44710 | 1401/03/08 | T-1018 | 44710 | 1401/03/08 | BK-SUR-ENG-ELE-01-04640 | 44723 | 1401/03/21 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D01 | [5 empty] | 1401-2294-122076 | 44737 | 1401/04/04 | 44745 | 1401/04/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D01
3 | 2 | 3 | 7 | 1 | 0 | 6 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0006 | Calculation Note For Earthing & Lightning System |  | BK-GCS-PEDCO-120-EL-CN-0006 | BK-GCS-PEDCO-120-EL-CN-0006 | BK | GCS | PEDCO | 120 | EL | CN | 0006 | F0Z-709012 | AFD | IFC | 2022-05-14 | 2022-05-30 | 2022-06-06 | 16 | 7 | 23 | IFA | 2022-10-05 | 2022-10-25 | 2022-10-29 | 20 | 4 | 24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-30 |  |  | D01 | IFA | T-1429 | 44825 | 1401/06/30 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05860 | 44842 | 1401/07/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279683 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0879 | 2022-04-30 | 1401/02/10 | T-0879 | 44681 | 1401/02/10 | BK-SUR-ENG-ELE-01-04215 | 44691 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-82854 | 2022-05-30 | 1401/03/09 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1429 | 44825 | 1401/06/30 |  |  |  | BK-SUR-ENG-ELE-01-05860 | 44842 | 1401/07/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0006_D00 | [5 empty] | 1401-2294-279683 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0006_D00
3 | 2 | 3 | 7 | 1 | 0 | 7 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0007 | Calculation Note For Diesel Generator Sizing |  | BK-GCS-PEDCO-120-EL-CN-0007 | BK-GCS-PEDCO-120-EL-CN-0007 | BK | GCS | PEDCO | 120 | EL | CN | 0007 | F0Z-709013 | AFD | IFC | 2021-11-30 | 2022-02-07 | 2022-02-13 | 69 | 6 | 75 | IFA | 2022-09-12 | 2022-09-14 | 2022-09-20 | 2 | 6 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-16 |  |  | D01 | IFA | T-1338 | 44802 | 1401/06/07 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05638 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-225829 | 44818 | 1401/06/23 | 44824 | 1401/06/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0255 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-ELE-00-02130 | 44528 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-312153 | 2021-12-11 | 1400/09/20 | 44542 | 1400/09/21 | CM |  | 1400-2294-400926 | 44599 | 1400/11/18 | 44605 | 1400/11/24 | CM |  |  |  | D01 | IFA | T-1338 | 44802 | 1401/06/07 |  |  |  | BK-SUR-ENG-ELE-01-05638 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0007_D00 | [5 empty] | 1401-2294-225829 | 44818 | 1401/06/23 | 44824 | 1401/06/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0007_D00
3 | 2 | 3 | 7 | 1 | 0 | 8 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0008 | Calculation Note For Cathodic Protection System |  | BK-GCS-PEDCO-120-EL-CN-0008 | BK-GCS-PEDCO-120-EL-CN-0008 | BK | GCS | PEDCO | 120 | EL | CN | 0008 | F0Z-709014 | AFD | IFC | 2022-05-15 | 2022-06-21 | 2022-07-02 | 37 | 11 | 48 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-01 |  |  | D00 | IFC | T-0891 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04253 | 44695 | 1401/02/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-82985 | 44711 | 1401/03/09 | 44718 | 1401/03/16 | CM | 0 | 1401-2294-111572 | 44733 | 1401/03/31 | 44744 | 1401/04/11 | CM | 0 | 0 |  | D00 | IFC | T-0891 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ELE-01-04253 | 44695 | 1401/02/24 | CM-C3 | [6 empty] | 1401-2294-82985 | 2022-05-30 | 1401/03/09 | 44718 | 1401/03/16 | CM |  | 1401-2294-111572 | 44733 | 1401/03/31 | 44744 | 1401/04/11 | CM
3 | 2 | 3 | 7 | 1 | 0 | 9 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0009 | Calculation Note For NGR Sizing |  | BK-GCS-PEDCO-120-EL-CN-0009 | BK-GCS-PEDCO-120-EL-CN-0009 | BK | GCS | PEDCO | 120 | EL | CN | 0009 | F0Z-709015 | AFD | IFC | 2022-04-25 | 2022-04-19 | 2022-04-25 | -6 | 6 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-11 |  |  | D00 | IFC | T-0804 | 44662 | 1401/01/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04013 | 44675 | 1401/01/04 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31345 | 44670 | 1401/01/30 | 44676 | 1401/02/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0804 | 2022-04-11 | 1401/01/22 |  |  |  | BK-SUR-ENG-ELE-01-04013 | 44675 | 1401/01/04 | AP | [6 empty] | 1401-2294-31345 | 2022-04-19 | 1401/01/30 | 44676 | 1401/02/05 | AP
3 | 2 | 3 | 7 | 1 | 0 | 10 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0010 | Calculation Note for UPS of CCTV in Desalting, Production & CS Unit |  | BK-GCS-PEDCO-120-EL-CN-0010 | [8 empty] | F0Z-709016 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 1 | 0 | 11 | 3.2.3.7.1 | BK-GCS-PEDCO-120-EL-CN-0011 | Calculation Note for Capacitor Banks |  | BK-GCS-PEDCO-120-EL-CN-0011 | BK-GCS-PEDCO-120-EL-CN-0011 | BK | GCS | PEDCO | 120 | EL | CN | 0011 | F0Z-709017 | AFD | IFC | 2021-12-06 | 2021-12-17 | 2021-12-18 | 11 | 1 | 12 | IFA | 2022-02-27 | 2022-02-28 | 2022-03-05 | 1 | 5 | 6 | IFA | 2022-08-17 | 2022-08-31 | 2022-09-04 | 14 | 4 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-22 |  |  | D02 | IFA | T-1237 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0266 | 2021-11-22 | 1400/09/01 |  |  |  | BK-SUR-ENG-ELE-00-02183 | 44534 | 1400/09/13 | CM-C3 | [6 empty] | 1400-2294-320825 | 2021-12-17 | 1400/09/26 | 44548 | 1400/09/27 | CM | [10 empty] | D01 | IFA | T-0590 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03236 | 44619 | 1400/12/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D00 | [5 empty] | 1400-2294-430282 | 44620 | 1400/12/09 | 44625 | 1400/12/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D00 | [9 empty] | D02 | IFA | T-1237 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D01 | [5 empty] | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D01
3 | 2 | 3 | 7 | 2 | 0 | 0 | 3.2.3.7.2 |  | Data Sheets
3 | 2 | 3 | 7 | 2 | 0 | 1 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0001 | Data Sheets For UPS |  | BK-GCS-PEDCO-120-EL-DT-0001 | BK-GCS-PEDCO-120-EL-DT-0001 | BK | GCS | PEDCO | 120 | EL | DT | 0001 | F0Z-709018 | AFC | IFC | 2022-01-09 | 2022-01-22 | 2022-01-25 | 13 | 3 | 16 | IFA | 2022-05-09 | 2022-06-07 | 2022-06-08 | 29 | 1 | 30 | IFA | 2022-08-17 | 2022-08-31 | 2022-09-04 | 14 | 4 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-26 |  |  | D02 | IFA | T-1237 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0379 | 2021-12-26 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02560 | 44565 | 1400/10/14 | CM-C3 | [6 empty] | 1400-2294-375310 | 2022-01-22 | 1400/11/02 | 44586 | 1400/11/05 | CM | [10 empty] | D01 | IFA | T-0861 | 44676 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04178 | 44690 | 1401/02/19 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D00 | [5 empty] | 1401-2294-91107 | 44719 | 1401/03/17 | 44720 | 1401/03/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D00 | [9 empty] | D02 | IFA | T-1237 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D01 | [5 empty] | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D01
3 | 2 | 3 | 7 | 2 | 0 | 2 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0002 | Data Sheets For DC Charger |  | BK-GCS-PEDCO-120-EL-DT-0002 | BK-GCS-PEDCO-120-EL-DT-0002 | BK | GCS | PEDCO | 120 | EL | DT | 0002 | F0Z-709019 | AFC | IFC | 2022-01-02 | 2021-01-06 | 2022-01-08 | -361 | 367 | 6 | IFA | 2022-02-02 | 2022-02-16 | 2022-02-21 | 14 | 5 | 19 | IFA | 2022-08-17 | 2022-08-31 | 2022-09-04 | 14 | 4 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-19 |  |  | D02 | IFA | T-1237 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0366 | 2021-12-19 | 1400/09/28 |  |  |  | BK-SUR-ENG-ELE-00-02474 | 44558 | 1400/10/07 | CM-C3 | [6 empty] | 1400-2294-352432 | 2021-01-06 | 1400/10/16 | 44569 | 1400/10/18 | CM | [10 empty] | D01 | IFA | T-0481 | 44580 | 1400/10/29 |  |  |  | BK-SUR-ENG-ELE-00-02888 | 44592 | 1400/11/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D00 | [5 empty] | 1400-2294-412403 | 44608 | 1400/12/02 | 44613 | 1400/11/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D00 | [9 empty] | D02 | IFA | T-1237 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D01 | [5 empty] | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D01
3 | 2 | 3 | 7 | 2 | 0 | 3 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0003 | Data Sheets For Diesel Generator |  | BK-GCS-PEDCO-120-EL-DT-0003 | BK-GCS-PEDCO-120-EL-DT-0003 | BK | GCS | PEDCO | 120 | EL | DT | 0003 | F0Z-709020 | AFC | IFC | 2022-06-14 | 2022-06-21 | 2022-07-02 | 7 | 11 | 18 | IFA | 2022-09-12 | 2022-09-14 | 2022-09-20 | 2 | 6 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-31 |  |  | D01 | IFA | T-1338 | 44802 | 1401/06/07 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05638 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-225829 | 44818 | 1401/06/23 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1026 | 2022-05-31 | 1401/03/10 | T-1026 | 44712 | 1401/03/10 | BK-SUR-ENG-ELE-01-04696 | 44726 | 1401/03/24 | CM-C3 | [6 empty] | 1401-2294-111571 | 2022-06-21 | 1401/03/31 | 44744 | 1401/04/11 | CM | [10 empty] | D01 | IFA | T-1338 | 44802 | 1401/06/07 |  |  |  | BK-SUR-ENG-ELE-01-05638 | 44816 | 1401/06/21 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0003_D00 | [5 empty] | 1401-2294-225829 | 44818 | 1401/06/23 | 44824 | 1401/06/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0003_D00
3 | 2 | 3 | 7 | 2 | 0 | 4 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0004 | Data Sheets For Expansion of MV Switchgear |  | BK-GCS-PEDCO-120-EL-DT-0004 | BK-GCS-PEDCO-120-EL-DT-0004 | BK | GCS | PEDCO | 120 | EL | DT | 0004 | F0Z-709021 | AFC | IFC | 2022-02-05 | 2022-02-06 | 2022-03-21 | 1 | 43 | 44 | IFA | 2022-03-23 | 2022-04-09 | 2022-04-13 | 17 | 4 | 21 | IFA | 2022-07-31 | 2022-08-18 | 2022-08-20 | 18 | 2 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-22 |  |  | D02 | IFA | T-1166 | 44759 | 1401/04/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0488 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-ELE-00-02906 | 44593 | 1400/11/12 | CM-C2 | [6 empty] | 1400-2294-399223 | 2022-02-06 | 1400/11/17 | 44641 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0705 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03635 | 44636 | 1400/12/25 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0004_D00 | [5 empty] | 1401-2294-16105 | 44660 | 1401/01/20 | 44664 | 1401/01/24 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0004_D00 | [9 empty] | D02 | IFA | T-1166 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | [6 empty] | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0004_D01
3 | 2 | 3 | 7 | 2 | 0 | 5 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0005 | Data Sheets For LV Switchgear |  | BK-GCS-PEDCO-120-EL-DT-0005 | BK-GCS-PEDCO-120-EL-DT-0005 | BK | GCS | PEDCO | 120 | EL | DT | 0005 | F0Z-709022 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-06-07 | 2022-06-11 | 2022-06-13 | 4 | 2 | 6 | IFA | 2022-07-31 | 2022-08-18 | 2022-08-20 | 18 | 2 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-19 |  |  | D02 | IFA | T-1166 | 44759 | 1401/04/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0601 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-ELE-00-03320 | 44625 | 1400/12/14 | CM-C2 | [6 empty] | 1400-2294-443157 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0998 | 44705 | 1401/03/03 | T-0998 | 44709 | 1401/03/07 | BK-SUR-ENG-ELE-01-04499 | 44713 | 1401/03/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0005_D00 | [5 empty] | 1401-2294-96604 | 44723 | 1401/03/21 | 44725 | 1401/03/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0005_D00 | [9 empty] | D02 | IFA | T-1166 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | [6 empty] | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0005_D01
3 | 2 | 3 | 7 | 2 | 0 | 6 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0006 | Data Sheets For Local Control Stations (LCS) |  | BK-GCS-PEDCO-120-EL-DT-0006 | BK-GCS-PEDCO-120-EL-DT-0006 | BK | GCS | PEDCO | 120 | EL | DT | 0006 | F0Z-709023 | AFC | IFC | 2022-02-20 | 2022-02-24 | 2022-02-28 | 4 | 4 | 8 | IFA | 2022-06-04 | 2022-06-14 | 2022-06-19 | 10 | 5 | 15 | AFC | 2022-07-19 | 2022-07-28 | 2022-07-31 | 9 | 3 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-06 | 2022-07-05 |  | D02 | AFC | T-1139 | 44747 | 1401/04/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05113 | 44758 | 1401/04/25 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156953 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0554 | 2022-02-06 | 1400/11/17 |  |  |  | BK-SUR-ENG-ELE-00-03087 | 44611 | 1400/11/30 | CM-C3 | [6 empty] | 1400-2294-424218 | 2022-02-24 | 1400/12/05 | 44620 | 1400/12/09 | CM | [10 empty] | D01 | IFA | T-0975 | 44702 | 1401/02/31 | T-0975 | 44702 | 1401/02/31 | BK-SUR-ENG-ELE-01-04489 | 44710 | 1401/03/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0006_D00 | [5 empty] | 1401-2294-102597 | 44726 | 1401/03/24 | 44731 | 1401/03/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0006_D00 | [9 empty] | D02 | AFC | T-1139 | 44747 | 1401/04/14 |  |  |  | BK-SUR-ENG-ELE-01-05113 | 44758 | 1401/04/25 | AP | [6 empty] | 1401-2294-156953 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP
3 | 2 | 3 | 7 | 2 | 0 | 7 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0007 | Data Sheets For Capacitor Bank |  | BK-GCS-PEDCO-120-EL-DT-0007 | BK-GCS-PEDCO-120-EL-DT-0007 | BK | GCS | PEDCO | 120 | EL | DT | 0007 | F0Z-709024 | AFC | IFC | 2022-03-13 | 2022-03-03 | 2022-03-26 | -10 | 23 | 13 | IFA | 2022-08-17 | 2022-08-31 | 2022-09-04 | 14 | 4 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-27 |  |  | D01 | IFA | T-1237 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0652 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-ELE-00-03418 | 44628 | 1400/12/17 | CM-C3 | [6 empty] | 1400-2294-447230 | 2022-03-03 | 1400/12/22 | 44646 | 1401/01/06 | CM | [10 empty] | D01 | IFA | T-1237 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0007_D00 | [5 empty] | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0007_D00
3 | 2 | 3 | 7 | 2 | 0 | 8 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0008 | Data Sheets For LV Induction Motors |  | BK-GCS-PEDCO-120-EL-DT-0008 | BK-GCS-PEDCO-120-EL-DT-0008 | BK | GCS | PEDCO | 120 | EL | DT | 0008 | F0Z-709025 | AFC | IFC | 2021-09-26 | 2021-09-28 | 2021-10-02 | 2 | 4 | 6 | IFA | 2022-02-21 | 2022-03-10 | 2022-03-12 | 17 | 2 | 19 | IFA | 2022-06-11 | 2022-06-15 | 2022-06-19 | 4 | 4 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-09-12 |  |  | D02 | IFA | T-1011 | 44709 | 1400/03/07 | T-1011 | 44709 | 1400/03/07 | BK-SUR-ENG-ELE-01-04611 | 44720 | 1401/01/18 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-103760 | 44727 | 1401/03/25 | 44731 | 1401/03/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0087 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ELE-00-01560 | 44464 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-213958 | 2021-09-28 | 1400/07/05 | 44471 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0558 | 44599 | 1400/11/18 |  |  |  | BK-SUR-ENG-ELE-00-03090 | 44611 | 1400/11/30 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D00 | [5 empty] | 1400-2294-443253 | 44630 | 1400/12/19 | 44632 | 1400/12/21 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D00 | [9 empty] | D02 | IFA | T-1011 | 44709 | 1400/03/07 | T-1011 | 44709 | 1400/03/07 | BK-SUR-ENG-ELE-01-04611 | 44720 | 1401/01/18 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D01 | [5 empty] | 1401-2294-103760 | 44727 | 1401/03/25 | 44731 | 1401/03/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D01
3 | 2 | 3 | 7 | 2 | 0 | 9 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0009 | Data Sheets For MV Induction Motors |  | BK-GCS-PEDCO-120-EL-DT-0009 | BK-GCS-PEDCO-120-EL-DT-0009 | BK | GCS | PEDCO | 120 | EL | DT | 0009 | F0Z-709026 | AFC | IFC | 2021-09-26 | 2021-09-28 | 2021-10-02 | 2 | 4 | 6 | IFA | 2022-02-22 | 2022-02-24 | 2022-02-28 | 2 | 4 | 6 | IFA | 2022-06-11 | 2022-06-15 | 2022-06-19 | 4 | 4 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-09-12 |  |  | D02 | IFA | T-1011 | 44709 | 1400/03/07 | T-1011 | 44709 | 1400/03/07 | BK-SUR-ENG-ELE-01-04611 | 44720 | 1401/01/18 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-103760 | 44727 | 1401/03/25 | 44731 | 1401/03/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0087 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ELE-00-01560 | 44464 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-213958 | 2021-09-28 | 1400/07/05 | 44471 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0563 | 44600 | 1400/11/19 |  |  |  | BK-SUR-ENG-ELE-00-03126 | 44612 | 1400/12/01 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D00 | [5 empty] | 1400-2294-424217 | 44616 | 1400/12/05 | 44620 | 1400/12/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D00 | [9 empty] | D02 | IFA | T-1011 | 44709 | 1400/03/07 | T-1011 | 44709 | 1400/03/07 | BK-SUR-ENG-ELE-01-04611 | 44720 | 1401/01/18 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D01 | [5 empty] | 1401-2294-103760 | 44727 | 1401/03/25 | 44731 | 1401/03/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D01
3 | 2 | 3 | 7 | 2 | 0 | 10 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0010 | Data Sheets For Power & Control Cables |  | BK-GCS-PEDCO-120-EL-DT-0010 | BK-GCS-PEDCO-120-EL-DT-0010 | BK | GCS | PEDCO | 120 | EL | DT | 0010 | F0Z-709027 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-06-04 | 2022-06-14 | 2022-06-19 | 10 | 5 | 15 | IFA | 2022-07-19 | 2022-07-28 | 2022-07-31 | 9 | 3 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-19 |  |  | D02 | IFA | T-1140 | 44747 | 1401/04/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05114 | 44758 | 1401/04/25 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156952 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0010_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0601 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-ELE-00-03320 | 44625 | 1400/12/14 | CM-C2 | [6 empty] | 1400-2294-443157 | 2022-03-10 | 1400/12/19 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0975 | 44702 | 1401/02/31 | T-0975 | 44702 | 1401/02/31 | BK-SUR-ENG-ELE-01-04489 | 44710 | 1401/03/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0010_D00 | [5 empty] | 1401-2294-102597 | 44726 | 1401/03/24 | 44731 | 1401/03/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0010_D00 | [9 empty] | D02 | IFA | T-1140 | 44747 | 1401/04/14 |  |  |  | BK-SUR-ENG-ELE-01-05114 | 44758 | 1401/04/25 | AP | [6 empty] | 1401-2294-156952 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0010_D01
3 | 2 | 3 | 7 | 2 | 0 | 11 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0011 | Data Sheets For Power Transformers |  | BK-GCS-PEDCO-120-EL-DT-0011 | BK-GCS-PEDCO-120-EL-DT-0011 | BK | GCS | PEDCO | 120 | EL | DT | 0011 | F0Z-709028 | AFC | IFC | 2022-02-16 | 2022-03-09 | 2022-03-12 | 21 | 3 | 24 | IFA | 2022-06-04 | 2022-06-14 | 2022-06-19 | 10 | 5 | 15 | IFA | 2022-07-19 | 2022-07-28 | 2022-07-31 | 9 | 3 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-02-02 |  |  | D02 | IFA | T-1140 | 44747 | 1401/04/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05114 | 44758 | 1401/04/25 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156952 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0541 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-ELE-00-03060 | 44606 | 1400/11/25 | [7 empty] | 1400-2294-442066 | 2022-03-09 | 1400/12/18 | 44632 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0975 | 44702 | 1401/02/31 | T-0975 | 44702 | 1401/02/31 | BK-SUR-ENG-ELE-01-04489 | 44710 | 1401/03/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0011_D00 | [5 empty] | 1401-2294-102597 | 44726 | 1401/03/24 | 44731 | 1401/03/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0011_D00 | [9 empty] | D02 | IFA | T-1140 | 44747 | 1401/04/14 |  |  |  | BK-SUR-ENG-ELE-01-05114 | 44758 | 1401/04/25 | AP | [6 empty] | 1401-2294-156952 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0011_D01
3 | 2 | 3 | 7 | 2 | 0 | 12 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0012 | Data Sheets For Cathodic Protection System |  | BK-GCS-PEDCO-120-EL-DT-0012 | [8 empty] | F0Z-709029 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 2 | 0 | 13 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0013 | Data Sheets For NGR |  | BK-GCS-PEDCO-120-EL-DT-0013 | BK-GCS-PEDCO-120-EL-DT-0013 | BK | GCS | PEDCO | 120 | EL | DT | 0013 | F0Z-709030 | AFC | IFC | 2022-04-25 | 2022-04-19 | 2022-04-25 | -6 | 6 | 0 | AFC | 2022-07-19 | 2022-07-28 | 2022-07-31 | 9 | 3 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-11 | 2022-07-05 |  | D01 | AFC | T-1139 | 44747 | 1401/04/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05113 | 44758 | 1401/04/25 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0013_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156953 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0804 | 2022-04-11 | 1401/01/22 |  |  |  | BK-SUR-ENG-ELE-01-04013 | 44675 | 1401/01/04 | CM-C2 | [6 empty] | 1401-2294-31345 | 2022-04-19 | 1401/01/30 | 44676 | 1401/02/05 | AP | [10 empty] | D01 | AFC | T-1139 | 44747 | 1401/04/14 |  |  |  | BK-SUR-ENG-ELE-01-05113 | 44758 | 1401/04/25 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0013_D00 | [5 empty] | 1401-2294-156953 | 44770 | 1401/05/06 | 44773 | 1401/05/09 | AP
3 | 2 | 3 | 7 | 2 | 0 | 14 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0015 | Data Sheets For Remote Control Panel |  | BK-GCS-PEDCO-120-EL-DT-0015 | BK-GCS-PEDCO-120-EL-DT-0015 | BK | GCS | PEDCO | 120 | EL | DT | 0015 | F0Z-709031 | AFC | IFC | 2022-06-15 | 2022-06-21 | 2022-07-02 | 6 | 11 | 17 | IFA | 2022-08-02 | 2022-08-03 | 2022-08-08 | 1 | 5 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-01 |  |  | D01 | IFA | T-1169 | 44761 | 1401/04/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05289 | 44773 | 1401/05/09 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0015_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-167065 | 44776 | 1401/05/12 | 44781 | 1401/05/18 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0015_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1030 | 2022-06-01 | 1401/03/11 | T-1030 | 44713 | 1401/03/11 | BK-SUR-ENG-ELE-01-04717 | 44727 | 1401/03/25 | AP | [6 empty] | 1401-2294-111560 | 2022-06-21 | 1401/03/31 | 44744 | 1401/04/11 | CM | [10 empty] | D01 | IFA | T-1169 | 44761 | 1401/04/28 |  |  |  | BK-SUR-ENG-ELE-01-05289 | 44773 | 1401/05/09 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0015_D00 | [5 empty] | 1401-2294-167065 | 44776 | 1401/05/12 | 44781 | 1401/05/18 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0015_D00
3 | 2 | 3 | 7 | 2 | 0 | 15 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0016 | Data Sheets For Distribution & Lighting Panels |  | BK-GCS-PEDCO-120-EL-DT-0016 | BK-GCS-PEDCO-120-EL-DT-0016 | BK | GCS | PEDCO | 120 | EL | DT | 0016 | F0Z-709032 | AFC | IFC | 2022-05-31 | 2022-06-08 | 2022-06-11 | 8 | 3 | 11 | IFA | 2022-08-02 | 2022-08-03 | 2022-08-08 | 1 | 5 | 6 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-17 |  |  | D01 | IFA | T-1169 | 44761 | 1401/04/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05289 | 44773 | 1401/05/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-167065 | 44776 | 1401/05/12 | 44781 | 1401/05/18 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0965 | 2022-05-17 | 1401/02/26 | T-0965 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04477 | 44710 | 1401/03/08 | CM-C2 | [6 empty] | 1401-2294-93978 | 2022-06-08 | 1401/03/18 | 44723 | 1401/03/21 | CM | [10 empty] | D01 | IFA | T-1169 | 44761 | 1401/04/28 |  |  |  | BK-SUR-ENG-ELE-01-05289 | 44773 | 1401/05/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0016_D00 | [5 empty] | 1401-2294-167065 | 44776 | 1401/05/12 | 44781 | 1401/05/18 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0016_D00
3 | 2 | 3 | 7 | 2 | 0 | 16 | 3.2.3.7.2 | BK-GCS-PEDCO-120-EL-DT-0017 | Data Sheet for UPS of CCTV in Desalting, Production & CS Unit |  | BK-GCS-PEDCO-120-EL-DT-0017 | BK-GCS-PEDCO-120-EL-DT-0017 | BK | GCS | PEDCO | 120 | EL | DT | 0017 | F0Z-709033 | AFC | IFC | 2022-03-16 | 2022-04-09 | 2022-04-13 | 24 | 4 | 28 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-03-02 |  |  | D00 | IFC | T-0662 | 44622 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03469 | 44632 | 1400/12/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16106 | 44660 | 1401/01/20 | 44664 | 1401/01/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0662 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-ELE-00-03469 | 44632 | 1400/12/21 | CM-C2 | [6 empty] | 1401-2294-16106 | 2022-04-09 | 1401/01/20 | 44664 | 1401/01/24 | AP
3 | 2 | 3 | 7 | 3 | 0 | 0 | 3.2.3.7.3 |  | Drawing/Diagram
3 | 2 | 3 | 7 | 3 | 0 | 1 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0001 | Electrical Overall Single Line Diagram |  | BK-GCS-PEDCO-120-EL-SL-0001 | BK-GCS-PEDCO-120-EL-SL-0001 | BK | GCS | PEDCO | 120 | EL | SL | 0001 | F2P-709034 | AFC | IFC | 2022-02-07 | 2022-02-12 | 2022-02-21 | 5 | 9 | 14 | IFA | 2022-04-30 | 2022-05-09 | 2022-05-18 | 9 | 9 | 18 | IFA | 2022-05-31 | 2022-06-08 | 2022-06-11 | 8 | 3 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Moved to IN | 2022-01-24 |  |  | D02 | IFA | T-0966 | 44698 | 1401/02/27 | T-0966 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04478 | 44710 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94378 | 44720 | 1401/03/18 | 44723 | 1401/03/21 | CM | NISCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0498 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-ELE-00-02907 | 44593 | 1400/11/13 | CM-C2 | [6 empty] | 1400-2294-406648 | 2022-02-12 | 1400/11/23 | 44613 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0817 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-ELE-01-04067 | 44677 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D00 | [5 empty] | 1401-2294-43191 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D00 | 1401-2294-54910 | 44690 | 1401/02/19 | 44699 | 1401/02/28 | CM |  |  |  | D02 | IFA | T-0966 | 44698 | 1401/02/27 | T-0966 | 44699 | 1401/02/28 | BK-SUR-ENG-ELE-01-04478 | 44710 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D01 | [5 empty] | 1401-2294-94378 | 44720 | 1401/03/18 | 44723 | 1401/03/21 | CM | NISCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D01
3 | 2 | 3 | 7 | 3 | 0 | 2 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0002 | LV Switchgear/MCC Single Line Diagram |  | BK-GCS-PEDCO-120-EL-SL-0002 | BK-GCS-PEDCO-120-EL-SL-0002 | BK | GCS | PEDCO | 120 | EL | SL | 0002 | F2P-709035 | AFC | IFC | 2022-01-10 | 2022-02-17 | 2022-02-20 | 38 | 3 | 41 | IFA | 2022-04-23 | 2022-04-19 | 2022-04-25 | -4 | 6 | 2 | IFA | 2022-05-30 | 2022-06-12 | 2022-06-15 | 13 | 3 | 16 | IFA | 2022-09-03 | 2022-09-08 | 2022-09-12 | 5 | 4 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-27 |  |  | D03 | IFA | T-1292 | 44793 | 1401/05/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05544 | 44801 | 1401/06/06 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216125 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0385 | 2021-12-27 | 1400/10/06 |  |  |  | BK-SUR-ENG-ELE-00-02611 | 44570 | 1400/10/19 | CM-C3 | [6 empty] | 1400-2294-368606 | 2021-01-17 | 1400/10/27 | 44582 | 1400/11/01 | CM |  | 1400-2294-413210 | 44609 | 1400/11/28 | 44612 | 1400/12/02 | CM |  |  |  | D01 | IFA | T-0788 | 44660 | 1401/01/20 |  |  |  | BK-SUR-ENG-ELE-01-03999 | 44671 | 1400/01/31 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D00 | [5 empty] | 1401-2294-31358 | 44670 | 1401/01/30 | 44676 | 1401/02/05 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D00 | [9 empty] | D02 | IFA | T-0957 | 44697 | 1401/02/26 | T-0957 | 44697 | 1401/02/26 | BK-SUR-ENG-ELE-01-04466 | 44710 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D01 | [5 empty] | 1401-2294-99024 | 44724 | 1401/03/22 | 44727 | 1401/03/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D01 | [9 empty] | D03 | IFA | T-1292 | 44793 | 1401/05/29 |  |  |  | BK-SUR-ENG-ELE-01-05544 | 44801 | 1401/06/06 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0002_D02 | [5 empty] | 1401-2294-216125 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0002_D02
3 | 2 | 3 | 7 | 3 | 0 | 3 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0003 | Existent MV Switchgear Expansion Single Line Diagram |  | BK-GCS-PEDCO-120-EL-SL-0003 | BK-GCS-PEDCO-120-EL-SL-0003 | BK | GCS | PEDCO | 120 | EL | SL | 0003 | F2P-709036 | AFC | IFC | 2022-01-26 | 2022-02-17 | 2022-02-20 | 22 | 3 | 25 | IFA | 2022-03-23 | 2022-04-09 | 2022-04-13 | 17 | 4 | 21 | IFA | 2022-05-14 | 2022-05-31 | 2022-06-06 | 17 | 6 | 23 | IFA | 2022-07-31 | 2022-08-18 | 2022-08-20 | 18 | 2 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-12 |  |  | D03 | IFA | T-1166 | 44759 | 1401/04/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0452 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-ELE-00-02785 | 44584 | 1400/11/03 | CM-C2 | [6 empty] | 1400-2294-413209 | 2022-02-17 | 1400/11/28 | 44612 | 1400/12/01 | CM | [10 empty] | D01 | IFA | T-0705 | 44629 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03635 | 44636 | 1400/12/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D00 | [5 empty] | 1401-2294-16105 | 44660 | 1401/01/20 | 44664 | 1401/01/24 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D00 | [9 empty] | D02 | IFA | T-0880 | 44681 | 1401/02/10 | T-0880 | 44681 | 1401/02/10 | BK-SUR-ENG-ELE-01-04218 | 44691 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D01 | [5 empty] | 1401-2294-85203 | 44712 | 1401/03/10 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D01 | [9 empty] | D03 | IFA | T-1166 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-ELE-01-05269 | 44772 | 1401/08/05 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D02 | [5 empty] | 1401-2294-183479 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D02
3 | 2 | 3 | 7 | 3 | 0 | 4 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0004 | Distribution and Lighting Panels Single Line Diagram |  | BK-GCS-PEDCO-120-EL-SL-0004 | BK-GCS-PEDCO-120-EL-SL-0004 | BK | GCS | PEDCO | 120 | EL | SL | 0004 | F2P-709037 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 3 | 0 | 5 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0005 | UPS Single Line Diagram |  | BK-GCS-PEDCO-120-EL-SL-0005 | BK-GCS-PEDCO-120-EL-SL-0005 | BK | GCS | PEDCO | 120 | EL | SL | 0005 | F2P-709038 | AFC | IFC | 2022-01-09 | 2022-01-22 | 2022-01-25 | 13 | 3 | 16 | IFA | 2022-08-17 | 2022-08-31 | 2022-09-04 | 14 | 4 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-26 |  |  | D01 | IFA | T-1237 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0379 | 2021-12-26 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02560 | 44565 | 1400/10/14 | CM-C3 | [6 empty] | 1400-2294-375310 | 2022-01-22 | 1400/11/02 | 44586 | 1400/11/05 | CM | [10 empty] | D01 | IFA | T-1237 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0005_D00 | [5 empty] | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0005_D00
3 | 2 | 3 | 7 | 3 | 0 | 6 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0006 | DC Charger Single Line Diagram |  | BK-GCS-PEDCO-120-EL-SL-0006 | BK-GCS-PEDCO-120-EL-SL-0006 | BK | GCS | PEDCO | 120 | EL | SL | 0006 | F2P-709039 | AFC | IFC | 2022-01-01 | 2022-01-06 | 2022-01-08 | 5 | 2 | 7 | IFA | 2022-02-02 | 2022-02-21 | 2022-02-16 | 19 | -5 | 14 | IFA | 2022-08-17 | 2022-08-28 | 2022-09-04 | 11 | 7 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-18 |  |  | D02 | IFA | T-1248 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05479 | 44790 | 1401/05/26 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-198988 | 44801 | 1401/06/06 | 44808 | 1401/06/13 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0357 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-ELE-00-02471 | 44558 | 1400/10/07 | CM-C3 | [6 empty] | 1400-2294-352430 | 2022-01-06 | 1400/10/16 | 44569 | 1400/10/18 | CM | [10 empty] | D01 | IFA | T-0481 | 44580 | 1400/10/29 |  |  |  | BK-SUR-ENG-ELE-00-02888 | 44592 | 1400/11/11 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D00 | [5 empty] | 1400-2294-412403 | 44613 | 1400/11/27 | 44608 | 1400/12/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D00 | [9 empty] | D02 | IFA | T-1248 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05479 | 44790 | 1401/05/26 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D01 | [5 empty] | 1401-2294-198988 | 44801 | 1401/06/06 | 44808 | 1401/06/13 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D01
3 | 2 | 3 | 7 | 3 | 0 | 7 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-DG-0001 | Electrical Typical Schematic Diagrams For MV panel |  | BK-GCS-PEDCO-120-EL-DG-0001 | BK-GCS-PEDCO-120-EL-DG-0001 | BK | GCS | PEDCO | 120 | EL | DG | 0001 | F2P-709040 | IFI | IFI | 2022-01-26 | 2022-02-17 | 2022-02-20 | 22 | 3 | 25 | IFI | 2022-03-22 | 2022-04-09 | 2022-04-13 | 18 | 4 | 22 | IFI | 2022-05-14 | 2022-05-31 | 2022-06-06 | 17 | 6 | 23 | IFI | 2022-07-31 | 2022-09-13 | 2022-09-18 | 44 | 5 | 49 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-01-12 |  |  | D03 | IFI | T-1168 | 44759 | 1401/04/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05282 | 44772 | 1401/05/08 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-222997 | 44817 | 1401/06/22 | 44822 | 1401/06/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0453 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-ELE-00-02786 | 44584 | 1400/11/03 | CM-C2 | [6 empty] | 1400-2294-413208 | 2022-02-17 | 1400/11/28 | 44612 | 1400/12/01 | CM | [10 empty] | D01 | IFI | T-0697 | 44628 | 1400/12/17 |  |  |  | BK-SUR-ENG-ELE-00-03606 | 44635 | 1400/12/24 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D00 | [5 empty] | 1401-2294-16099 | 44660 | 1401/01/20 | 44664 | 1401/01/24 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D00 | [9 empty] | D02 | IFI | T-0884 | 44681 | 1401/02/10 | T-0884 | 44681 | 1401/02/10 | BK-SUR-ENG-ELE-01-04237 | 44692 | 1401/02/21 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D01 | [5 empty] | 1401-2294-85216 | 44712 | 1401/03/10 | 44718 | 1401/03/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D01 | [9 empty] | D03 | IFI | T-1168 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-ELE-01-05282 | 44772 | 1401/05/08 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D02 | [5 empty] | 1401-2294-222997 | 44817 | 1401/06/22 | 44822 | 1401/06/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D02
3 | 2 | 3 | 7 | 3 | 0 | 8 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-DG-0002 | Electrical Typical Schematic Diagrams For LV panel |  | BK-GCS-PEDCO-120-EL-DG-0002 | BK-GCS-PEDCO-120-EL-DG-0002 | BK | GCS | PEDCO | 120 | EL | DG | 0002 | F2P-709041 | IFI | IFI | 2021-12-27 | 2022-02-02 | 2022-02-08 | 37 | 6 | 43 | IFI | 2022-04-23 | 2022-05-01 | 2022-05-02 | 8 | 1 | 9 | IFI | 2022-05-29 | 2022-06-07 | 2022-06-11 | 9 | 4 | 13 | IFI | 2022-07-31 | 2022-09-13 | 2022-09-18 | 44 | 5 | 49 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D03 | IFI | T-1168 | 44759 | 1401/04/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05282 | 44772 | 1401/05/08 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-222997 | 44817 | 1401/06/22 | 44822 | 1401/06/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0340 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-ELE-00-02412 | 44556 | 1400/10/05 | RJ-C4 | [6 empty] | 1400-2294-393495 | 2022-02-02 | 1400/11/13 | 44600 | 1400/11/19 | CM | [10 empty] | D01 | IFI | T-0789 | 44660 | 1401/01/20 |  |  |  | BK-SUR-ENG-ELE-00-02412 | 44920 | 1401/10/04 | C4-RJ | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D00 | [5 empty] | 1401-2294-47908 | 44682 | 1401/02/11 | 44683 | 1401/02/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D00 | [9 empty] | D02 | IFI | T-0949 | 44696 | 1401/02/25 | T-0949 | 44696 | 1401/02/25 | BK-SUR-ENG-ELE-01-04447 | 44709 | 1401/03/07 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D01 | [5 empty] | 1401-2294-92391 | 44719 | 1401/03/17 | 44723 | 1401/03/21 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D01 | [9 empty] | D03 | IFI | T-1168 | 44759 | 1401/04/26 |  |  |  | BK-SUR-ENG-ELE-01-05282 | 44772 | 1401/05/08 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D02 | [5 empty] | 1401-2294-222997 | 44817 | 1401/06/22 | 44822 | 1401/06/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D02
3 | 2 | 3 | 7 | 3 | 0 | 9 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-DG-0003 | Interconnection Wiring Diagram |  | BK-GCS-PEDCO-120-EL-DG-0003 | BK-GCS-PEDCO-120-EL-DG-0003 | BK | GCS | PEDCO | 120 | EL | DG | 0003 | F2P-709042 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 3 | 0 | 10 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-DG-0005 | Wiring Diagram For Remote Control Panel (RCP) |  | BK-GCS-PEDCO-120-EL-DG-0005 | BK-GCS-PEDCO-120-EL-DG-0005 | BK | GCS | PEDCO | 120 | EL | DG | 0005 | F2P-709043 | AFC | IFC | 2022-09-21 | 2022-10-05 | 2022-10-08 | 14 | 3 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Moved to IN | 2022-09-07 |  |  | D00 | IFC | T-1371 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05735 | 44825 | 1401/06/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249354 | 44839 | 1401/07/13 | 44842 | 1401/07/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1371 | 2022-09-07 | 1401/06/16 |  |  |  | BK-SUR-ENG-ELE-01-05735 | 44825 | 1401/06/30 | AP | [6 empty] | 1401-2294-249354 | 2022-10-05 | 1401/07/13 | 44842 | 1401/07/16 | AP
3 | 2 | 3 | 7 | 3 | 0 | 11 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-DG-0006 | Wiring Diagrams For Cathodic Protection Systems |  | BK-GCS-PEDCO-120-EL-DG-0006 | [8 empty] | F2P-709044 | AFC | [49 empty] | Moved to IN | 0
3 | 2 | 3 | 7 | 3 | 0 | 12 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-LD-0001 | Control Logic Diagram For LV Incomers and bus tie |  | BK-GCS-PEDCO-120-EL-LD-0001 | BK-GCS-PEDCO-120-EL-LD-0001 | BK | GCS | PEDCO | 120 | EL | LD | 0001 | F2P-709045 | AFC | IFC | 2022-01-30 | 2022-02-23 | 2022-02-27 | 24 | 4 | 28 | IFA | 2022-04-30 | 2022-05-09 | 2022-05-18 | 9 | 9 | 18 | IFA | 2022-08-20 | 2022-10-10 | 2022-10-15 | 51 | 5 | 56 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-16 |  |  | D02 | IFA | T-1254 | 44779 | 1401/05/15 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05488 | 44793 | 1401/05/29 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-255788 | 44844 | 1401/07/23 | 44849 | 1401/07/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0463 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-ELE-00-02840 | 44590 | 1400/11/09 | CM-C2 | [6 empty] | 1400-2294-423219 | 2022-02-23 | 1400/12/04 | 44619 | 1400/12/08 | CM | [10 empty] | D01 | IFA | T-0817 | 44667 | 1401/01/27 |  |  |  | BK-SUR-ENG-ELE-01-04067 | 44677 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D00 | [5 empty] | 1401-2294-43191 | 44679 | 1401/02/08 | 44682 | 1401/02/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D00 | 1401-2294-54910 | 44690 | 1401/02/19 | 44699 | 1401/02/28 | CM |  |  |  | D02 | IFA | T-1254 | 44779 | 1401/05/15 |  |  |  | BK-SUR-ENG-ELE-01-05488 | 44793 | 1401/05/29 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D01 | [5 empty] | 1401-2294-255788 | 44844 | 1401/07/23 | 44849 | 1401/07/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D01
3 | 2 | 3 | 7 | 3 | 0 | 13 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0001 | Overall Earthing Layout |  | BK-GCS-PEDCO-120-EL-PY-0001 | BK-GCS-PEDCO-120-EL-PY-0001 | BK | GCS | PEDCO | 120 | EL | PY | 0001 | F4P-709046 | AFC | IFC | 2022-10-17 | 0 | 0 | -44851 | 0 | -44851 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-03 |  |  | D00 | IFC | T-1451 | 44837 | 1401/07/11 | T-1451 | 44837 | 1401/07/11 | BK-SUR-ENG-ELE-01-05900 | 44849 | 1401/07/23 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1451 | 2022-10-03 | 1401/07/11 | T-1451 | 44837 | 1401/07/11 | BK-SUR-ENG-ELE-01-05900 | 44849 | 1401/07/23 | CM-C3
3 | 2 | 3 | 7 | 3 | 0 | 14 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0002 | Earthing & Lightning Layout For Building & Shelter |  | BK-GCS-PEDCO-120-EL-PY-0002 | BK-GCS-PEDCO-120-EL-PY-0002 | BK | GCS | PEDCO | 120 | EL | PY | 0002 | F2P-709047 | AFC | IFC | 2022-11-08 | 2022-11-17 | 2022-11-19 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-25 |  |  | D00 | IFC | T-1547 | 44859 | 1401/08/03 | T-1547 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06133 | 44873 | 1401/08/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-315872 | 44882 | 1401/08/26 | 44884 | 1401/8/28 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1547 | 2022-10-25 | 1401/08/03 | T-1547 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06133 | 44873 | 1401/08/17 | CM-C3 | [6 empty] | 1401-2294-315872 | 2022-11-17 | 1401/08/26 | 44884 | 1401/8/28 | CM
3 | 2 | 3 | 7 | 3 | 0 | 15 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0003 | Area Lighting & Small Power Layout |  | BK-GCS-PEDCO-120-EL-PY-0003 | BK-GCS-PEDCO-120-EL-PY-0003 | BK | GCS | PEDCO | 120 | EL | PY | 0003 | F2P-709048 | AFC | IFC | 2022-07-06 | 2022-07-10 | 2022-07-23 | 4 | 13 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-22 |  |  | D00 | IFC | T-1107 | 44734 | 1401/04/01 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05009 | 44748 | 1401/04/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-135326 | 44752 | 1401/04/19 | 44765 | 1401/05/01 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1107 | 2022-06-22 | 1401/04/01 |  |  |  | BK-SUR-ENG-ELE-01-05009 | 44748 | 1401/04/15 | CM-C3 | [6 empty] | 1401-2294-135326 | 2022-07-10 | 1401/04/19 | 44765 | 1401/05/01 | CM
3 | 2 | 3 | 7 | 3 | 0 | 16 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0004 | Lighting & Small Power Layout For Building & Shelter |  | BK-GCS-PEDCO-120-EL-PY-0004 | BK-GCS-PEDCO-120-EL-PY-0004 | BK | GCS | PEDCO | 120 | EL | PY | 0004 | F2P-709049 | AFC | IFC | 2022-05-29 | 2022-06-10 | 2022-06-12 | 12 | 2 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-15 |  |  | D00 | IFC | T-0950 | 44696 | 1401/02/25 | T-0950 | 44696 | 1401/02/25 | BK-SUR-ENG-ELE-01-04448 | 44709 | 1401/03/07 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-94635 | 44722 | 1401/03/20 | 44724 | 1401/03/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0950 | 2022-05-15 | 1401/02/25 | T-0950 | 44696 | 1401/02/25 | BK-SUR-ENG-ELE-01-04448 | 44709 | 1401/03/07 | CM-C3 | [6 empty] | 1401-2294-94635 | 2022-06-10 | 1401/03/20 | 44724 | 1401/03/22 | CM
3 | 2 | 3 | 7 | 3 | 0 | 17 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0005 | Area Electrical Cable Route & Section Layout |  | BK-GCS-PEDCO-120-EL-PY-0005 | BK-GCS-PEDCO-120-EL-PY-0005 | BK | GCS | PEDCO | 120 | EL | PY | 0005 | F2P-709050 | AFC | IFC | 2022-07-27 | 2022-08-11 | 2022-10-03 | 15 | 53 | 68 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Moved to IN | 2022-07-13 |  |  | D00 | IFC | T-1159 | 44755 | 1401/04/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05263 | 44769 | 1401/05/05 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-172867 | 44784 | 1401/05/20 | 44837 | 1401/07/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1159 | 2022-07-13 | 1401/04/22 |  |  |  | BK-SUR-ENG-ELE-01-05263 | 44769 | 1401/05/05 | CM-C3 | [6 empty] | 1401-2294-172867 | 2022-08-11 | 1401/05/20 | 44837 | 1401/07/11 | CM
3 | 2 | 3 | 7 | 3 | 0 | 18 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0006 | Electrical Cable Route & Section Layout For Building & Shelter |  | BK-GCS-PEDCO-120-EL-PY-0006 | BK-GCS-PEDCO-120-EL-PY-0006 | BK | GCS | PEDCO | 120 | EL | PY | 0006 | F2P-709051 | AFC | IFC | 2022-08-08 | 2022-08-18 | 2022-08-21 | 10 | 3 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Moved to IN | 2022-07-25 |  |  | D00 | IFC | T-1192 | 44767 | 1401/05/03 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05335 | 44775 | 1401/05/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183486 | 44791 | 1401/05/27 | 44794 | 1401/05/30 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1192 | 2022-07-25 | 1401/05/03 |  |  |  | BK-SUR-ENG-ELE-01-05335 | 44775 | 1401/05/11 | CM-C3 | [6 empty] | 1401-2294-183486 | 2022-08-18 | 1401/05/27 | 44794 | 1401/05/30 | CM
3 | 2 | 3 | 7 | 3 | 0 | 19 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0007 | HVAC Power Cabling Arrangement Layout For Building |  | BK-GCS-PEDCO-120-EL-PY-0007 | BK-GCS-PEDCO-120-EL-PY-0007 | BK | GCS | PEDCO | 120 | EL | PY | 0007 | F2P-709052 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 3 | 0 | 20 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0008 | Electrical Equipment Arrangement Layout For Building |  | BK-GCS-PEDCO-120-EL-PY-0008 | BK-GCS-PEDCO-120-EL-PY-0008 | BK | GCS | PEDCO | 120 | EL | PY | 0008 | F2P-709053 | AFC | IFC | 2022-05-23 | 2022-05-28 | 2022-05-29 | 5 | 1 | 6 | IFA | 2022-10-25 | 2022-10-25 | 2022-10-29 | 0 | 4 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-09 |  |  | D01 | IFA | T-1484 | 44845 | 1401/07/19 | T-1484 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05972 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-PY-0008_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279715 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | CM | NISOCE-CRS-BK-GCS-PEDCO-120-EL-PY-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0915 | 2022-05-09 | 1401/02/19 | T-0915 | 44690 | 1401/02/19 | BK-SUR-ENG-ELE-01-04330 | 44702 | 1401/02/31 | CM-C3 | [6 empty] | 1401-2294-78935 | 2022-05-28 | 1401/03/08 | 44710 | 1401/03/09 | CM | [10 empty] | D01 | IFA | T-1484 | 44845 | 1401/07/19 | T-1484 | 44845 | 1401/07/19 | BK-SUR-ENG-ELE-01-05972 | 44859 | 1401/08/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-PY-0008_D00 | [5 empty] | 1401-2294-279715 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | CM | NISOCE-CRS-BK-GCS-PEDCO-120-EL-PY-0008_D00
3 | 2 | 3 | 7 | 3 | 0 | 21 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0009 | Cathodic Protection System Layout |  | BK-GCS-PEDCO-120-EL-PY-0009 | [8 empty] | F2P-709054 | AFC | [50 empty] | 0
3 | 2 | 3 | 7 | 3 | 0 | 22 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0007 | Capacitor Banks Single Line Diagram |  | BK-GCS-PEDCO-120-EL-SL-0007 | BK-GCS-PEDCO-120-EL-SL-0007 | BK | GCS | PEDCO | 120 | EL | SL | 0007 | F2P-709055 | AFC | IFC | 2022-03-16 | 2022-04-09 | 2022-04-13 | 24 | 4 | 28 | IFA | 2022-08-17 | 2022-08-31 | 2022-09-04 | 14 | 4 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Moved to IN | 2022-03-02 |  |  | D01 | IFA | T-1237 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0662 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-ELE-00-03469 | 44632 | 1400/12/21 | CM-C2 | [6 empty] | 1401-2294-16106 | 2022-04-09 | 1401/01/20 | 44664 | 1401/01/24 | CM | [10 empty] | D01 | IFA | T-1237 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05478 | 44789 | 1401/05/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0007_D00 | [5 empty] | 1401-2294-205602 | 44804 | 1401/06/09 | 44808 | 1401/06/12 | AP | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0007_D00
3 | 2 | 3 | 7 | 3 | 0 | 23 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-DG-0007 | Power & Control Cables Termination Diagrams |  | BK-GCS-PEDCO-120-EL-DG-0007 | BK-GCS-PEDCO-120-EL-DG-0007 | BK | GCS | PEDCO | 120 | EL | DG | 0007 | F2P-709056 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 3 | 0 | 24 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0009 | Single Line Diagram for UPS of CCTV in Desalting, Production & CS Unit |  | BK-GCS-PEDCO-120-EL-SL-0009 | [8 empty] | F2P-709057 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 3 | 0 | 25 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0008 | SLD for Supplying UPS of CCTV Panel in Desalting Unit |  | BK-GCS-PEDCO-120-EL-SL-0008 | BK-GCS-PEDCO-120-EL-SL-0008 | BK | GCS | PEDCO | 120 | EL | SL | 0008 | F2P-709058 | AFC | IFC | 2022-08-29 | 2022-09-08 | 2022-09-12 | 10 | 4 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-15 |  |  | D00 | IFC | T-1273 | 44788 | 1401/05/23 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05514 | 44796 | 1401/06/01 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216129 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1273 | 2022-08-15 | 1401/05/23 |  |  |  | BK-SUR-ENG-ELE-01-05514 | 44796 | 1401/06/01 | CM-C2 | [6 empty] | 1401-2294-216129 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | CM
3 | 2 | 3 | 7 | 3 | 0 | 26 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-SL-0010 | SLD for Supplying UPS of CCTV Panel in Production Unit |  | BK-GCS-PEDCO-120-EL-SL-0010 | BK-GCS-PEDCO-120-EL-SL-0010 | BK | GCS | PEDCO | 120 | EL | SL | 0010 | F2P-709059 | AFC | IFC | 2022-08-29 | 2022-09-08 | 2022-09-12 | 10 | 4 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Moved to IN | 2022-08-15 |  |  | D00 | IFC | T-1273 | 44788 | 1401/05/23 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05514 | 44796 | 1401/06/01 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216129 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1273 | 2022-08-15 | 1401/05/23 |  |  |  | BK-SUR-ENG-ELE-01-05514 | 44796 | 1401/06/01 | CM-C2 | [6 empty] | 1401-2294-216129 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | CM
3 | 2 | 3 | 7 | 3 | 0 | 27 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0010 | Equipment Arrangement Layout for UPS of CCTV in Desalting Unit |  | BK-GCS-PEDCO-120-EL-PY-0010 | BK-GCS-PEDCO-120-EL-PY-0010 | BK | GCS | PEDCO | 120 | EL | PY | 0010 | F2P-709060 | AFC | IFC | 2022-09-11 | 2022-09-08 | 2022-09-12 | -3 | 4 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Moved to IN | 2022-08-28 |  |  | D00 | IFC | T-1325 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05620 | 44814 | 1401/06/19 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216073 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1325 | 2022-08-28 | 1401/06/06 |  |  |  | BK-SUR-ENG-ELE-01-05620 | 44814 | 1401/06/19 | CM-C2 | [6 empty] | 1401-2294-216073 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | AP
3 | 2 | 3 | 7 | 3 | 0 | 28 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0011 | Equipment Arrangement Layout for UPS of CCTV in Production Unit |  | BK-GCS-PEDCO-120-EL-PY-0011 | BK-GCS-PEDCO-120-EL-PY-0011 | BK | GCS | PEDCO | 120 | EL | PY | 0011 | F2P-709061 | AFC | IFC | 2022-09-11 | 2022-09-08 | 2022-09-12 | -3 | 4 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-28 |  |  | D00 | IFC | T-1325 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05620 | 44814 | 1401/06/19 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216073 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1325 | 2022-08-28 | 1401/06/06 |  |  |  | BK-SUR-ENG-ELE-01-05620 | 44814 | 1401/06/19 | CM-C2 | [6 empty] | 1401-2294-216073 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | AP
3 | 2 | 3 | 7 | 3 | 0 | 29 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0012 | Cable Route Layout for Desalting Unit |  | BK-GCS-PEDCO-120-EL-PY-0012 | BK-GCS-PEDCO-120-EL-PY-0012 | BK | GCS | PEDCO | 120 | EL | PY | 0012 | F4P-709062 | AFC | IFC | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-22 |  |  | D00 | IFC | T-1526 | 44856 | 1401/07/30 | T-1526 | 44856 | 1401/07/30 | BK-SUR-ENG-ELE-01-06083 | 44870 | 1401/08/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1526 | 2022-10-22 | 1401/07/30 | T-1526 | 44856 | 1401/07/30 | BK-SUR-ENG-ELE-01-06083 | 44870 | 1401/08/14 | CM-C3
3 | 2 | 3 | 7 | 3 | 0 | 30 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0013 | Cable Route layout for Production Unit |  | BK-GCS-PEDCO-120-EL-PY-0013 | BK-GCS-PEDCO-120-EL-PY-0013 | BK | GCS | PEDCO | 120 | EL | PY | 0013 | F4P-709063 | AFC | IFC | 2022-11-05 | 0 | 0 | -44870 | 0 | -44870 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-22 |  |  | D00 | IFC | T-1526 | 44856 | 1401/07/30 | T-1526 | 44856 | 1401/07/30 | BK-SUR-ENG-ELE-01-06083 | 44870 | 1401/08/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1526 | 2022-10-22 | 1401/07/30 | T-1526 | 44856 | 1401/07/30 | BK-SUR-ENG-ELE-01-06083 | 44870 | 1401/08/14 | CM-C3
3 | 2 | 3 | 7 | 3 | 0 | 31 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0014 | Earthing Layout for Desalting Unit |  | BK-GCS-PEDCO-120-EL-PY-0014 | BK-GCS-PEDCO-120-EL-PY-0014 | BK | GCS | PEDCO | 120 | EL | PY | 0014 | F2P-709064 | AFC | IFC | 2022-11-08 | 2022-11-17 | 2022-11-19 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-25 |  |  | D00 | IFC | T-1547 | 44859 | 1401/08/03 | T-1547 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06133 | 44873 | 1401/08/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-315872 | 44882 | 1401/08/26 | 44884 | 1401/8/28 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1547 | 2022-10-25 | 1401/08/03 | T-1547 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06133 | 44873 | 1401/08/17 | CM-C3 | [6 empty] | 1401-2294-315872 | 2022-11-17 | 1401/08/26 | 44884 | 1401/8/28 | CM
3 | 2 | 3 | 7 | 3 | 0 | 32 | 3.2.3.7.3 | BK-GCS-PEDCO-120-EL-PY-0015 | Earthing Layout for Production Unit |  | BK-GCS-PEDCO-120-EL-PY-0015 | BK-GCS-PEDCO-120-EL-PY-0015 | BK | GCS | PEDCO | 120 | EL | PY | 0015 | F2P-709065 | AFC | IFC | 2022-11-08 | 2022-11-17 | 2022-11-19 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-10-25 |  |  | D00 | IFC | T-1555 | 44859 | 1401/08/03 | T-1555 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06138 | 44873 | 1401/08/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-315870 | 44882 | 1401/08/26 | 44884 | 1401/08/28 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1555 | 2022-10-25 | 1401/08/03 | T-1555 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06138 | 44873 | 1401/08/17 | CM-C3 | [6 empty] | 1401-2294-315870 | 2022-11-17 | 1401/08/26 | 44884 | 1401/08/28 | CM
3 | 2 | 3 | 7 | 4 | 0 | 0 | 3.2.3.7.4 |  | List
3 | 2 | 3 | 7 | 4 | 0 | 1 | 3.2.3.7.4 | BK-GCS-PEDCO-120-EL-LI-0001 | Electrical Load List |  | BK-GCS-PEDCO-120-EL-LI-0001 | BK-GCS-PEDCO-120-EL-LI-0001 | BK | GCS | PEDCO | 120 | EL | LI | 0001 | F0Z-709066 | AFC | IFC | 2021-11-30 | 2021-11-28 | 2021-12-01 | -2 | 3 | 1 | IFA | 2022-02-16 | 2022-02-16 | 2022-02-21 | 0 | 5 | 5 | IFA | 2022-04-09 | 2022-04-05 | 2022-04-09 | -4 | 4 | 0 | IFA | 2022-05-30 | 2022-06-12 | 2022-06-15 | 13 | 3 | 16 | IFA | 2022-08-08 | 2022-08-18 | 2022-08-21 | 10 | 3 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-16 |  |  | D04 | IFA | T-1193 | 44767 | 1401/05/03 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05358 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183483 | 44791 | 1401/05/27 | 44794 | 1401/05/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0250 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-ELE-00-02157 | 44530 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-294877 | 2021-11-28 | 1400/09/07 | 44531 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0532 | 44594 | 1400/11/13 |  |  |  | BK-SUR-ENG-ELE-00-03082 | 44608 | 1400/11/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D00 | [5 empty] | 1400-2294-412906 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D00 | [9 empty] | D02 | IFA | T-0736 | 44646 | 1401/01/06 |  |  |  | BK-SUR-ENG-ELE-01-03789 | 44660 | 1401/01/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D01 | [5 empty] | 1401-2294-13858 | 44656 | 1401/01/18 | 44660 | 1401/01/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D01 | [9 empty] | D03 | IFA | T-0957 | 44697 | 1401/02/26 | T-0957 | 44697 | 1401/02/26 | BK-SUR-ENG-ELE-01-04466 | 44710 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D02 | [5 empty] | 1401-2294-99024 | 44724 | 1401/03/22 | 44727 | 1401/03/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D02 | [9 empty] | D04 | IFA | T-1193 | 44767 | 1401/05/03 |  |  |  | BK-SUR-ENG-ELE-01-05358 | 44779 | 1401/05/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D03 | [5 empty] | 1401-2294-183483 | 44791 | 1401/05/27 | 44794 | 1401/05/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D03
3 | 2 | 3 | 7 | 4 | 0 | 2 | 3.2.3.7.4 | BK-GCS-PEDCO-120-EL-LI-0002 | Electrical Power & Control Cable Schedule |  | BK-GCS-PEDCO-120-EL-LI-0002 | BK-GCS-PEDCO-120-EL-LI-0002 | BK | GCS | PEDCO | 120 | EL | LI | 0002 | F0Z-709067 | AFC | IFC | 2022-06-29 | 2022-08-11 | 2022-08-14 | 43 | 3 | 46 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-15 |  |  | D00 | IFC | T-1082 | 44727 | 1401/03/25 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04835 | 44734 | 1401/04/01 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-172876 | 44784 | 1401/05/20 | 44787 | 1401/05/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1082 | 2022-06-15 | 1401/03/25 |  |  |  | BK-SUR-ENG-ELE-01-04835 | 44734 | 1401/04/01 | CM-C3 | [6 empty] | 1401-2294-172876 | 2022-08-11 | 1401/05/20 | 44787 | 1401/05/23 | CM
3 | 2 | 3 | 7 | 4 | 0 | 3 | 3.2.3.7.4 | BK-GCS-PEDCO-120-EL-LI-0003 | Electrical Power & Control Drum Schedule & Cutting List |  | BK-GCS-PEDCO-120-EL-LI-0003 | BK-GCS-PEDCO-120-EL-LI-0003 | BK | GCS | PEDCO | 120 | EL | LI | 0003 | F0Z-709068 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 4 | 0 | 4 | 3.2.3.7.4 | BK-GCS-PEDCO-120-EL-LI-0004 | Cable Schedule For Cathodic Protection System |  | BK-GCS-PEDCO-120-EL-LI-0004 | [8 empty] | F0Z-709069 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 4 | 0 | 5 | 3.2.3.7.4 | BK-GCS-PEDCO-120-EL-LI-0005 | Electrical I/O Signal List |  | BK-GCS-PEDCO-120-EL-LI-0005 | BK-GCS-PEDCO-120-EL-LI-0005 | BK | GCS | PEDCO | 120 | EL | LI | 0005 | F0Z-709070 | AFC | IFC | 2022-07-04 | 2022-08-18 | 2022-08-20 | 45 | 2 | 47 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-20 |  |  | D00 | IFC | T-1099 | 44732 | 1401/03/30 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04993 | 44747 | 1401/04/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-183482 | 44791 | 1401/05/27 | 44793 | 1401/05/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1099 | 2022-06-20 | 1401/03/30 |  |  |  | BK-SUR-ENG-ELE-01-04993 | 44747 | 1401/04/14 | CM-C3 | [6 empty] | 1401-2294-183482 | 2022-08-18 | 1401/05/27 | 44793 | 1401/05/29 | CM
3 | 2 | 3 | 7 | 5 | 0 | 0 | 3.2.3.7.5 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 7 | 5 | 0 | 1 | 3.2.3.7.5 | BK-GCS-PEDCO-120-EL-RT-0001 | Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report |  | BK-GCS-PEDCO-120-EL-RT-0001 | BK-GCS-PEDCO-120-EL-RT-0001 | BK | GCS | PEDCO | 120 | EL | RT | 0001 | F0Z-709071 | IFI | IFC | 2022-06-29 | 2022-08-11 | 2022-08-14 | 43 | 3 | 46 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-15 |  |  | D00 | IFC | T-1082 | 44727 | 1401/03/25 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04835 | 44734 | 1401/04/01 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-172876 | 44784 | 1401/05/20 | 44787 | 1401/05/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1082 | 2022-06-15 | 1401/03/25 |  |  |  | BK-SUR-ENG-ELE-01-04835 | 44734 | 1401/04/01 | CM-C3 | [6 empty] | 1401-2294-172876 | 2022-08-11 | 1401/05/20 | 44787 | 1401/05/23 | CM
3 | 2 | 3 | 7 | 5 | 0 | 2 | 3.2.3.7.5 | BK-GCS-PEDCO-120-EL-RT-0002 | Relay Coordination & Setting Study Report |  | BK-GCS-PEDCO-120-EL-RT-0002 | BK-GCS-PEDCO-120-EL-RT-0002 | BK | GCS | PEDCO | 120 | EL | RT | 0002 | F0Z-709072 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 7 | 6 | 0 | 0 | 3.2.3.7.6 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 7 | 6 | 0 | 1 | 3.2.3.7 | BK-GCS-PEDCO-120-EL-MT-0001 | MTO For Earthing & Lightning Systems |  | BK-GCS-PEDCO-120-EL-MT-0001 | BK-GCS-PEDCO-120-EL-MT-0001 | BK | GCS | PEDCO | 120 | EL | MT | 0001 | F8Z-709073 | IFI | IFI | 2022-11-08 | 2022-11-17 | 2022-11-19 | 9 | 2 | 11 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-25 |  |  | D00 | IFI | T-1549 | 44859 | 1401/08/03 | T-1549 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06139 | 44873 | 1401/08/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-315869 | 44882 | 1401/08/26 | 44884 | 1401/08/28 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1549 | 2022-10-25 | 1401/08/03 | T-1549 | 44859 | 1401/08/03 | BK-SUR-ENG-ELE-01-06139 | 44873 | 1401/08/17 | CM-C3 | [6 empty] | 1401-2294-315869 | 2022-11-17 | 1401/08/26 | 44884 | 1401/08/28 | CM
3 | 2 | 3 | 7 | 6 | 0 | 2 | 3.2.3.7 | BK-GCS-PEDCO-120-EL-MT-0002 | MTO For Lighting & Small Powers |  | BK-GCS-PEDCO-120-EL-MT-0002 | BK-GCS-PEDCO-120-EL-MT-0002 | BK | GCS | PEDCO | 120 | EL | MT | 0002 | F8Z-709074 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 7 | 6 | 0 | 3 | 3.2.3.7 | BK-GCS-PEDCO-120-EL-MT-0003 | MTO For Power & Control Cables |  | BK-GCS-PEDCO-120-EL-MT-0003 | BK-GCS-PEDCO-120-EL-MT-0003 | BK | GCS | PEDCO | 120 | EL | MT | 0003 | F8Z-709075 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 7 | 6 | 0 | 4 | 3.2.3.7 | BK-GCS-PEDCO-120-EL-MT-0004 | MTO For Tray/Ladder and Accessories |  | BK-GCS-PEDCO-120-EL-MT-0004 | BK-GCS-PEDCO-120-EL-MT-0004 | BK | GCS | PEDCO | 120 | EL | MT | 0004 | F8Z-709076 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 7 | 6 | 0 | 5 | 3.2.3.7 | BK-GCS-PEDCO-120-EL-MT-0005 | MTO For Cathodic Protection System |  | BK-GCS-PEDCO-120-EL-MT-0005 | [8 empty] | F8Z-709077 | IFI | IFI | 2022-05-15 | 2022-05-30 | 2022-06-06 | 15 | 7 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-01 |  |  | D00 | IFI | T-0892 | 44682 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04255 | 44695 | 1401/02/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-82983 | 44711 | 1401/03/09 | 44718 | 1401/03/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0892 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ELE-01-04255 | 44695 | 1401/02/24 | CM-C3 | [6 empty] | 1401-2294-82983 | 2022-05-30 | 1401/03/09 | 44718 | 1401/03/16 | CM
3 | 2 | 3 | 7 | 6 | 0 | 6 | 3.2.3.7 | BK-GCS-PEDCO-120-EL-MT-0006 | MTO For Electrical Bulk Items |  | BK-GCS-PEDCO-120-EL-MT-0006 | BK-GCS-PEDCO-120-EL-MT-0006 | BK | GCS | PEDCO | 120 | EL | MT | 0006 | F8Z-709078 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 8 | 0 | 0 | 0 | 3.2.3.8 |  | Intercom. & Telecomm. | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 8 | 1 | 0 | 0 | 3.2.3.8.1 |  | Data Sheets | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 8 | 1 | 0 | 1 | 3.2.3.8.1 | BK-GCS-PEDCO-120-TE-DT-0001 | Data Sheets For CCTV |  | BK-GCS-PEDCO-120-TE-DT-0001 | [8 empty] | - |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 8 | 1 | 0 | 2 | 3.2.3.8.1 | BK-GCS-PEDCO-120-TE-DT-0002 | Data Sheets For PABX |  | BK-GCS-PEDCO-120-TE-DT-0002 | BK-GCS-PEDCO-120-TE-DT-0002 | BK | GCS | PEDCO | 120 | TE | DT | 0002 | F0Z-709079 | AFC | IFC | 2021-10-27 | 2021-11-04 | 2021-11-07 | 8 | 3 | 11 | IFA | 2021-11-30 | 2022-01-27 | 2022-01-31 | 58 | 4 | 62 | AFC | 2022-02-16 | 2022-02-22 | 2022-02-21 | 6 | -1 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-13 | 2022-02-02 |  | D02 | AFC | T-0536 | 44594 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-411808 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP | 0 | 1400-2294-421733 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | 0 | 0 |  | D00 | IFC | T-0157 | 2021-10-13 | 1400/07/21 | [13 empty] | 1400-2294-261488 | 2021-11-04 | 1400/08/12 | 44507 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0253 | 44516 | 1400/08/25 |  |  |  | BK-SUR-ENG-TEL-00-02392 | 44551 | 1400/09/30 | AP | [6 empty] | 1400-2294-384188 | 44588 | 1400/11/07 | 44592 | 1400/11/11 | AP | NISOC-BK-GCS-PEDCO-120-TE-DT-0002_D00 | [9 empty] | D02 | AFC | T-0536 | 44594 | 1400/11/13 | [13 empty] | 1400-2294-411808 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP |  | 1400-2294-421733 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP
3 | 2 | 3 | 8 | 1 | 0 | 3 | 3.2.3.8.1 | BK-GCS-PEDCO-120-TE-DT-0003 | Data Sheets For PAGA |  | BK-GCS-PEDCO-120-TE-DT-0003 | BK-GCS-PEDCO-120-TE-DT-0003 | BK | GCS | PEDCO | 120 | TE | DT | 0003 | F0Z-709080 | AFC | IFC | 2021-10-27 | 2021-11-04 | 2021-11-07 | 8 | 3 | 11 | IFA | 2021-11-30 | 2022-01-27 | 2022-01-31 | 58 | 4 | 62 | AFC | 2022-02-27 | 2022-02-22 | 2022-02-02 | -5 | -20 | -25 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-10-13 | 2022-02-13 |  | D02 | AFC | T-0584 | 44605 | 1400/11/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421732 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0157 | 2021-10-13 | 1400/07/21 | [13 empty] | 1400-2294-261488 | 2021-11-04 | 1400/08/12 | 44507 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0253 | 44516 | 1400/08/25 |  |  |  | BK-SUR-ENG-TEL-00-02392 | 44551 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2294-384188 | 44588 | 1400/11/07 | 44592 | 1400/11/11 | AP | NISOC-BK-GCS-PEDCO-120-TE-DT-0003_D00 | [9 empty] | D02 | AFC | T-0584 | 44605 | 1400/11/24 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-DT-0003_D01 | [5 empty] | 1400-2294-421732 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0003_D01
3 | 2 | 3 | 8 | 1 | 0 | 4 | 3.2.3.8.1 | BK-GCS-PEDCO-120-TE-DT-0004 | Data Sheets For Radio |  | BK-GCS-PEDCO-120-TE-DT-0004 | BK-GCS-PEDCO-120-TE-DT-0004 | BK | GCS | PEDCO | 120 | TE | DT | 0004 | F0Z-709081 | AFC | IFC | 2021-12-05 | 2021-12-03 | 2022-01-05 | -2 | 33 | 31 | IFA | 2022-01-24 | 2022-01-26 | 2022-01-31 | 2 | 5 | 7 | AFC | 2022-02-16 | 2022-02-22 | 2022-02-21 | 6 | -1 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-11-21 | 2022-02-02 |  | D02 | AFC | T-0536 | 44594 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-411808 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP | 0 | 1400-2294-421733 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | 0 | 0 |  | D00 | IFC | T-0263 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-TEL-00-02393 | 44551 | 1400/09/30 | AP | [6 empty] | 1400-2294-348118 | 2021-12-03 | 1400/10/13 | 44566 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0445 | 44571 | 1400/10/20 |  |  |  | BK-SUR-ENG-TEL-00-02618 | 44571 | 1400/10/20 | AP | [6 empty] | 1400-2294-383245 | 44587 | 1400/11/06 | 44592 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0004_D00 | [9 empty] | D02 | AFC | T-0536 | 44594 | 1400/11/13 | [13 empty] | 1400-2294-411808 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP |  | 1400-2294-421733 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP
3 | 2 | 3 | 8 | 1 | 0 | 5 | 3.2.3.8.1 | BK-GCS-PEDCO-120-TE-DT-0005 | Data Sheets For Telecom. Cable |  | BK-GCS-PEDCO-120-TE-DT-0005 | BK-GCS-PEDCO-120-TE-DT-0005 | BK | GCS | PEDCO | 120 | TE | DT | 0005 | F0Z-709082 | AFC | IFC | 2021-10-27 | 2021-11-04 | 2021-11-07 | 8 | 3 | 11 | IFA | 2021-12-01 | 2022-01-29 | 2022-01-31 | 59 | 2 | 61 | AFC | 2022-02-16 | 2022-02-22 | 2022-02-21 | 6 | -1 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-10-13 | 2022-02-02 |  | D02 | AFC | T-0536 | 44594 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-411808 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP | 0 | 1400-2294-421733 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | 0 | 0 |  | D00 | IFC | T-0156 | 2021-10-13 | 1400/07/21 | [13 empty] | 1400-2294-261481 | 2021-11-04 | 1400/08/13 | 44507 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0251 | 44517 | 1400/08/26 |  |  |  | BK-SUR-ENG-TEL-00-02391 | 44551 | 1400/09/30 | AP | [6 empty] | 1400-2294-386717 | 44590 | 1400/11/09 | 44592 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0005 | [9 empty] | D02 | AFC | T-0536 | 44594 | 1400/11/13 | [13 empty] | 1400-2294-411808 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP |  | 1400-2294-421733 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP
3 | 2 | 3 | 8 | 1 | 0 | 6 | 3.2.3.8.1 | BK-GCS-PEDCO-120-TE-DT-0006 | Data Sheets For Telecommunication Tower |  | BK-GCS-PEDCO-120-TE-DT-0006 | BK-GCS-PEDCO-120-TE-DT-0006 | BK | GCS | PEDCO | 120 | TE | DT | 0006 | F0Z-709083 | AFC | IFC | 2021-10-27 | 2021-11-04 | 2021-11-07 | 8 | 3 | 11 | IFA | 2021-12-01 | 2022-01-29 | 2022-01-31 | 59 | 2 | 61 | AFC | 2022-02-16 | 2022-02-22 | 2022-02-21 | 6 | -1 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-10-13 | 2022-02-02 |  | D02 | AFC | T-0536 | 44594 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-411808 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP | 0 | 1400-2294-421733 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | 0 | 0 |  | D00 | IFC | T-0156 | 2021-10-13 | 1400/07/21 | [13 empty] | 1400-2294-261481 | 2021-11-04 | 1400/08/13 | 44507 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0251 | 44517 | 1400/08/26 |  |  |  | BK-SUR-ENG-TEL-00-02391 | 44551 | 1400/09/30 | AP | [6 empty] | 1400-2294-386717 | 44590 | 1400/11/09 | 44592 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0006 | [9 empty] | D02 | AFC | T-0536 | 44594 | 1400/11/13 | [13 empty] | 1400-2294-411808 | 44608 | 1400/11/27 | 44613 | 1400/12/02 | AP |  | 1400-2294-421733 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP
3 | 2 | 3 | 8 | 2 | 0 | 0 | 3.2.3.8.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 8 | 2 | 0 | 1 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-BD-0001 | Telecom Overall Block Diagram |  | BK-GCS-PEDCO-120-TE-BD-0001 | BK-GCS-PEDCO-120-TE-BD-0001 | BK | GCS | PEDCO | 120 | TE | BD | 0001 | F2T-709084 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 8 | 2 | 0 | 2 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-DW-0001 | Typical Installation Details & Notes For Telecommunication Tower |  | BK-GCS-PEDCO-120-TE-DW-0001 | [8 empty] | F2T-709085 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 8 | 2 | 0 | 3 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-BD-0002 | Block Diagram For CCTV |  | BK-GCS-PEDCO-120-TE-BD-0002 | [8 empty] | - | [51 empty] | 0
3 | 2 | 3 | 8 | 2 | 0 | 4 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-BD-0003 | Block Diagram For CCTV in Binak DU |  | BK-GCS-PEDCO-120-TE-BD-0003 | [8 empty] | - | [51 empty] | 0
3 | 2 | 3 | 8 | 2 | 0 | 5 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-BD-0004 | Block Diagram For PABX |  | BK-GCS-PEDCO-120-TE-BD-0004 | BK-GCS-PEDCO-120-TE-BD-0004 | BK | GCS | PEDCO | 120 | TE | BD | 0004 | F2T-709086 | AFC | IFC | 2021-08-11 | 2021-09-12 | 2021-09-14 | 32 | 2 | 34 | IFA | 2021-10-05 | 2021-10-06 | 2021-10-10 | 1 | 4 | 5 | IFA | 2021-11-15 | 2021-12-28 | 2021-12-05 | 43 | -23 | 20 | AFC | 2022-03-09 | 2022-03-06 | 2022-03-01 | -3 | -5 | -8 | AFC | 2022-03-22 | 2022-03-14 | 2022-04-01 | -8 | 18 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2022-03-08 |  | D04 | AFC | T-0699 | 44628 | 1400/12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448924 | 44634 | 1400/12/23 | 44652 | 1401/01/14 | AP | NISOC-BK-GCS-PEDCO-120-TE-BD-0004_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0019 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-TEL-00-01305 | 44418 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/194238 | 2021-09-12 | 1400/06/21 | 44453 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0112 | 44460 | 1400/06/30 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-BD-0004_D00 | [5 empty] | 1400-2290-223856 | 44475 | 1400/07/14 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-BD-0004_D00 | [9 empty] | D02 | IFA | T-0200 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-TEL-00-02390 | 44551 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2290-294875 | 44558 | 1400/09/07 | 44535 | 1400/09/14 | AP | NISOC-CRS-D01-BK-GCS-PEDCO-120-TE-BD-0004_D01 | [9 empty] | D03 | AFC | T-0631 | 44615 | 1400/12/04 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-BD-0004_D02 | [5 empty] | 1400-2294-430787 | 44626 | 1400/12/15 | 44621 | 1400/12/10 | CM | [10 empty] | D04 | AFC | T-0699 | 44628 | 1400/12/17 | [13 empty] | 1400-2294-448924 | 44634 | 1400/12/23 | 44652 | 1401/01/14 | AP | NISOC-BK-GCS-PEDCO-120-TE-BD-0004_D03
3 | 2 | 3 | 8 | 2 | 0 | 6 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-BD-0005 | Block Diagram For PAGA |  | BK-GCS-PEDCO-120-TE-BD-0005 | BK-GCS-PEDCO-120-TE-BD-0005 | BK | GCS | PEDCO | 120 | TE | BD | 0005 | F2T-709087 | AFC | IFC | 2021-08-11 | 2021-09-12 | 2021-09-14 | 32 | 2 | 34 | IFA | 2021-10-05 | 2021-10-06 | 2021-10-10 | 1 | 4 | 5 | IFA | 2021-11-15 | 2021-12-28 | 2021-12-05 | 43 | -23 | 20 | AFC | 2022-03-08 | 2022-03-06 | 2022-03-01 | -2 | -5 | -7 | AFC | 2022-03-22 | 2022-03-14 | 2022-04-01 | -8 | 18 | 10 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2022-03-08 |  | D04 | AFC | T-0699 | 44628 | 1400/12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448924 | 44634 | 1400/12/23 | 44652 | 1401/01/14 | AP | NISOC-BK-GCS-PEDCO-120-TE-BD-0005_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0019 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-TEL-00-01305 | 44418 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/194238 | 2021-09-12 | 1400/06/21 | 44453 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0112 | 44460 | 1400/06/30 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-BD-0005_D00 | [5 empty] | 1400-2290-223856 | 44475 | 1400/07/14 | 44479 | 1400/07/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-BD-0005_D00 | [9 empty] | D02 | IFA | T-0200 | 44501 | 1400/08/10 |  |  |  | BK-SUR-ENG-TEL-00-02390 | 44551 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2290-294875 | 44558 | 1400/09/07 | 44535 | 1400/09/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-BD-0005-D01 | [9 empty] | D03 | AFC | T-0626 | 44614 | 1400/12/03 | [13 empty] | 1400-2294-430786 | 44626 | 1400/12/15 | 44621 | 1400/12/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-BD-0005_D02 | [9 empty] | D04 | AFC | T-0699 | 44628 | 1400/12/17 | [13 empty] | 1400-2294-448924 | 44634 | 1400/12/23 | 44652 | 1401/01/14 | AP | NISOC-BK-GCS-PEDCO-120-TE-BD-0005_D03
3 | 2 | 3 | 8 | 2 | 0 | 7 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-BD-0006 | Block Diagram For Radio |  | BK-GCS-PEDCO-120-TE-BD-0006 | BK-GCS-PEDCO-120-TE-BD-0006 | BK | GCS | PEDCO | 120 | TE | BD | 0006 | F2T-709088 | AFC | IFC | 2021-08-11 | 2021-09-12 | 2021-09-14 | 32 | 2 | 34 | AFC | 2021-10-09 | 2021-10-09 | 2021-10-12 | 0 | 3 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-07-28 | 2021-09-25 |  | D01 | AFC | T-0118 | 44464 | 1400/07/03 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-02387 | 44551 | 1400/09/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2290-227454 | 44478 | 1400/07/17 | 44481 | 1400/07/20 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0019 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-TEL-00-01305 | 44418 | 1400/05/19 | AP | [6 empty] | 1400/2294/194238 | 2021-09-12 | 1400/06/21 | 44453 | 1400/06/23 | AP | [10 empty] | D01 | AFC | T-0118 | 44464 | 1400/07/03 |  |  |  | BK-SUR-ENG-TEL-00-02387 | 44551 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2290-227454 | 44478 | 1400/07/17 | 44481 | 1400/07/20 | AP
3 | 2 | 3 | 8 | 2 | 0 | 8 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-PY-0001 | Telecomm. Equipment Layout For Electrical Building |  | BK-GCS-PEDCO-120-TE-PY-0001 | BK-GCS-PEDCO-120-TE-PY-0001 | BK | GCS | PEDCO | 120 | TE | PY | 0001 | F2T-709089 | AFC | IFC | 2022-05-01 | 2022-04-28 | 2022-05-01 | -3 | 3 | 0 | IFA | 2022-05-22 | 2022-05-29 | 2022-06-08 | 7 | 10 | 17 | AFC | 2022-07-11 | 2022-07-01 | 2022-07-05 | -10 | 4 | -6 | AFC | 2022-10-08 | 0 | 0 | -44842 | 0 | -44842 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-17 | 2022-09-24 |  | D03 | AFC | T-1437 | 44828 | 1401/07/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0833 | 2022-04-17 | 1401/01/28 |  |  |  | BK-SUR-ENG-TEL-01-03971 | 44669 | 1401/01/29 | RJ-C4 | [6 empty] | 1401-2294-42934 | 2022-04-28 | 1401/02/08 | 44682 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-0912 | 44689 | 1401/02/18 | T-0912 | 44689 | 1401/02/18 | BK-SUR-ENG-TEL-01-04214 | 44691 | 1401/02/20 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0001_D00 | [5 empty] | 1401-2294-78843 | 44710 | 1401/03/08 | 44720 | 1401/03/18 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0001_D00 | [9 empty] | D02 | AFC | T-1122 | 44739 | 1401/04/06 |  |  |  | BK-SUR-ENG-TEL-01-05979 | 44860 | 1401/08/4 | AP | [6 empty] | 1401-2294-124364 | 44743 | 1401/04/10 | 44747 | 1401/04/14 | CM | [10 empty] | D03 | AFC | T-1437 | 44828 | 1401/07/02 | [19 empty] | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0001_D02
3 | 2 | 3 | 8 | 2 | 0 | 9 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-PY-0002 | Telecomm. Equipment Layout For Control Building |  | BK-GCS-PEDCO-120-TE-PY-0002 | BK-GCS-PEDCO-120-TE-PY-0002 | BK | GCS | PEDCO | 120 | TE | PY | 0002 | F2T-709090 | AFC | IFC | 2022-06-25 | 2022-06-21 | 2022-06-25 | -4 | 4 | 0 | IFA | 2022-10-08 | 0 | 0 | -44842 | 0 | -44842 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-11 |  |  | D01 | IFA | T-1437 | 44828 | 1401/07/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-NISOC-120-TE-PY-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1054 | 2022-06-11 | 1401/03/21 | T-1054 | 44723 | 1401/03/21 | BK-SUR-ENG-TEL-01-04881 | 44737 | 1401/04/04 | CM-C2 | [6 empty] | 1401-2294-111532 | 2022-06-21 | 1401/03/31 | 44737 | 1401/04/04 | CM | [10 empty] | D01 | IFA | T-1437 | 44828 | 1401/07/02 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0002_D00 | [11 empty] | NISOC-CRS-BK-GCS-NISOC-120-TE-PY-0002_D00
3 | 2 | 3 | 8 | 2 | 0 | 10 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-PY-0003 | CCTV Equipment Layout For Area |  | BK-GCS-PEDCO-120-TE-PY-0003 | [8 empty] | - |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 8 | 2 | 0 | 11 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-PY-0004 | CCTV Equipment Layout For Desalting Unit Area |  | BK-GCS-PEDCO-120-TE-PY-0004 | [8 empty] | - |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 8 | 2 | 0 | 12 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-PY-0005 | Telecomm Equipment Layout For Area |  | BK-GCS-PEDCO-120-TE-PY-0005 | BK-GCS-PEDCO-120-TE-PY-0005 | BK | GCS | PEDCO | 120 | TE | PY | 0005 | F2T-709091 | AFC | IFC | 2022-04-18 | 2022-04-28 | 2022-05-01 | 10 | 3 | 13 | IFA | 2022-05-22 | 2022-05-29 | 2022-06-08 | 7 | 10 | 17 | IFA | 2022-07-10 | 2022-07-01 | 2022-07-05 | -9 | 4 | -5 | IFA | 2022-10-04 | 2022-10-11 | 2022-10-12 | 7 | 1 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-04 |  |  | D03 | IFA | T-1422 | 44824 | 1401/06/29 | 0 | 0 | 0 | BK-SUR-ENG-TEL-01-05734 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-257251 | 44845 | 1401/07/19 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0775 | 2022-04-04 | 1401/01/15 | [13 empty] | 1401-2294-42940 | 2022-04-28 | 1401/02/08 | 44682 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-0912 | 44689 | 1401/02/18 | T-0912 | 44689 | 1401/02/18 | BK-SUR-ENG-TEL-01-04214 | 44691 | 1401/02/20 | AP |  | BK-SUR-ENG-TEL-01-04594 | 44720 | 1401/03/18 | CM |  | 1401-2294-78843 | 44710 | 1401/03/08 | 44720 | 1401/03/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D00 | [9 empty] | D02 | IFA | T-1118 | 44738 | 1401/04/05 |  |  |  | BK-SUR-ENG-TEL-01-04994 | 44747 | 1401/04/14 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D01 | [5 empty] | 1401-2294-124365 | 44743 | 1401/04/10 | 44747 | 1401/04/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D01 | [9 empty] | D03 | IFA | T-1422 | 44824 | 1401/06/29 |  |  |  | BK-SUR-ENG-TEL-01-05734 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D02 | [5 empty] | 1401-2294-257251 | 44845 | 1401/07/19 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D02
3 | 2 | 3 | 8 | 2 | 0 | 13 | 3.2.3.8.2 | BK-GCS-PEDCO-120-TE-PY-0006 | PAGA Equipment Layout For Area |  | BK-GCS-PEDCO-120-TE-PY-0006 | BK-GCS-PEDCO-120-TE-PY-0006 | BK | GCS | PEDCO | 120 | TE | PY | 0006 | F2T-709092 | AFC | IFC | 2022-04-20 | 2022-04-28 | 2022-05-01 | 8 | 3 | 11 | IFA | 2022-05-29 | 2022-06-11 | 2022-06-18 | 13 | 7 | 20 | IFA | 2022-10-04 | 2022-10-11 | 2022-10-12 | 7 | 1 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-06 |  |  | D02 | IFA | T-1422 | 44824 | 1401/06/29 | 0 | 0 | 0 | BK-SUR-ENG-TEL-01-05734 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-257251 | 44845 | 1401/07/19 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0784 | 2022-04-06 | 1401/01/17 |  |  |  | BK-SUR-ENG-TEL-01-03852 | 44662 | 1401/01/22 | RJ-C4 | [6 empty] | 1401-2294-43096 | 2022-04-28 | 1401/02/08 | 44682 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-0954 | 44696 | 1401/02/25 | T-0954 | 44696 | 1401/02/25 | BK-SUR-ENG-TEL-01-04610 | 44720 | 1401/03/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0006_D00 | [5 empty] | 1401-2294-96473 | 44723 | 1401/03/21 | 44730 | 1401/03/28 | CM | NISOC-CRS-BK-GCS-NISOC-120-TE-PY-0006_D00 | [9 empty] | D02 | IFA | T-1422 | 44824 | 1401/06/29 |  |  |  | BK-SUR-ENG-TEL-01-05734 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0006_D01 | [5 empty] | 1401-2294-257251 | 44845 | 1401/07/19 | 44846 | 1401/07/20 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0006_D01
3 | 2 | 3 | 8 | 3 | 0 | 0 | 3.2.3.8.3 |  | List | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 8 | 3 | 0 | 1 | 3.2.3.8.3 | BK-GCS-PEDCO-120-TE-LI-0001 | Cable Schedule For CCTV |  | BK-GCS-PEDCO-120-TE-LI-0001 | [8 empty] | - |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 8 | 3 | 0 | 3 | 3.2.3.8.3 | BK-GCS-PEDCO-120-TE-LI-0003 | Cable Schedule For PABX |  | BK-GCS-PEDCO-120-TE-LI-0003 | BK-GCS-PEDCO-120-TE-LI-0003 | BK | GCS | PEDCO | 120 | TE | LI | 0003 | F0Z-709093 | AFC | IFC | 2022-06-21 | 2022-07-03 | 2022-07-05 | 12 | 2 | 14 | IFA | 2022-10-15 | 2022-10-25 | 2022-10-29 | 10 | 4 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-07 |  |  | D01 | IFA | T-1446 | 44835 | 1401/07/01 | 0 | 0 | 0 | BK-SUR-ENG-TEL-01-05782 | 44836 | 1401/07/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-LI-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279705 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-LI-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1045 | 2022-06-07 | 1401/03/17 | T-1045 | 44719 | 1401/03/17 | BK-SUR-ENG-TEL-01-04876 | 44737 | 1401/04/04 | AP | [6 empty] | 1401-2294-128504 | 2022-07-03 | 1401/04/12 | 44747 | 1401/04/14 | CM | [10 empty] | D01 | IFA | T-1446 | 44835 | 1401/07/01 |  |  |  | BK-SUR-ENG-TEL-01-05782 | 44836 | 1401/07/10 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-LI-0003_D00 | [5 empty] | 1401-2294-279705 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-LI-0003_D00
3 | 2 | 3 | 8 | 3 | 0 | 4 | 3.2.3.8.3 | BK-GCS-PEDCO-120-TE-LI-0004 | Cable Schedule For PAGA |  | BK-GCS-PEDCO-120-TE-LI-0004 | BK-GCS-PEDCO-120-TE-LI-0004 | BK | GCS | PEDCO | 120 | TE | LI | 0004 | F0Z-709094 | AFC | IFC | 2022-06-21 | 2022-07-03 | 2022-07-05 | 12 | 2 | 14 | IFA | 2022-10-15 | 2022-10-25 | 2022-10-29 | 10 | 4 | 14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-07 |  |  | D01 | IFA | T-1446 | 44835 | 1401/07/01 | 0 | 0 | 0 | BK-SUR-ENG-TEL-01-05782 | 44836 | 1401/07/10 | AP | PEDCO-CRS-K-GCS-PEDCO-120-TE-LI-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279705 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-K-GCS-PEDCO-120-TE-LI-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1045 | 2022-06-07 | 1401/03/17 | T-1045 | 44719 | 1401/03/17 | BK-SUR-ENG-TEL-01-04876 | 44737 | 1401/04/04 | CM-C3 | [6 empty] | 1401-2294-128504 | 2022-07-03 | 1401/04/12 | 44747 | 1401/04/14 | CM | [10 empty] | D01 | IFA | T-1446 | 44835 | 1401/07/01 |  |  |  | BK-SUR-ENG-TEL-01-05782 | 44836 | 1401/07/10 | AP | PEDCO-CRS-K-GCS-PEDCO-120-TE-LI-0004_D00 | [5 empty] | 1401-2294-279705 | 44859 | 1401/08/03 | 44863 | 1401/08/07 | AP | NISOC-CRS-K-GCS-PEDCO-120-TE-LI-0004_D00
3 | 2 | 3 | 8 | 4 | 0 | 0 | 3.2.3.8.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 8 | 4 | 0 | 1 | 3.2.3.8 | BK-GCS-PEDCO-120-TE-MT-0001 | MTO For CCTV |  | BK-GCS-PEDCO-120-TE-MT-0001 | [8 empty] | - |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 8 | 4 | 0 | 2 | 3.2.3.8 | BK-GCS-PEDCO-120-TE-MT-0002 | MTO For CCTV in Binak DU Area |  | BK-GCS-PEDCO-120-TE-MT-0002 | [8 empty] | - |  | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 8 | 4 | 0 | 3 | 3.2.3.8 | BK-GCS-PEDCO-120-TE-MT-0003 | MTO For PABX |  | BK-GCS-PEDCO-120-TE-MT-0003 | BK-GCS-PEDCO-120-TE-MT-0003 | BK | GCS | PEDCO | 120 | TE | MT | 0003 | F8Z-709095 | IFI | IFI | 2022-06-08 | 2022-06-13 | 2022-06-25 | 5 | 12 | 17 | IFI | 2022-10-04 | 0 | 0 | -44838 | 0 | -44838 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-25 |  |  | D01 | IFI | T-1423 | 44824 | 1401/06/29 | 0 | 0 | 0 | BK-SUR-ENG-TEL-01-05740 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-MT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-TE-MT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1004 | 2022-05-25 | 1401/03/04 | T-1004 | 44709 | 1401/03/07 | BK-SUR-ENG-TEL-01-04603 | 44720 | 1401/03/18 | CM-C3 | [6 empty] | 1401-2294-100876 | 2022-06-13 | 1401/03/23 | 44737 | 1401/04/04 | CM | [10 empty] | D01 | IFI | T-1423 | 44824 | 1401/06/29 |  |  |  | BK-SUR-ENG-TEL-01-05740 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-MT-0003_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-TE-MT-0003_D00
3 | 2 | 3 | 8 | 4 | 0 | 4 | 3.2.3.8 | BK-GCS-PEDCO-120-TE-MT-0004 | MTO For PAGA |  | BK-GCS-PEDCO-120-TE-MT-0004 | BK-GCS-PEDCO-120-TE-MT-0004 | BK | GCS | PEDCO | 120 | TE | MT | 0004 | F8Z-709096 | IFI | IFI | 2022-06-08 | 2022-06-13 | 2022-06-25 | 5 | 12 | 17 | IFI | 2022-10-04 | 0 | 0 | -44838 | 0 | -44838 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-25 |  |  | D01 | IFI | T-1423 | 44824 | 1401/06/29 | 0 | 0 | 0 | BK-SUR-ENG-TEL-01-05740 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-MT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-TE-MT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1004 | 2022-05-25 | 1401/03/04 | T-1004 | 44709 | 1401/03/07 | BK-SUR-ENG-TEL-01-04603 | 44720 | 1401/03/18 | AP | [6 empty] | 1401-2294-100876 | 2022-06-13 | 1401/03/23 | 44737 | 1401/04/04 | CM | [10 empty] | D01 | IFI | T-1423 | 44824 | 1401/06/29 |  |  |  | BK-SUR-ENG-TEL-01-05740 | 44825 | 1401/06/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-MT-0004_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-TE-MT-0004_D00
3 | 2 | 3 | 8 | 4 | 0 | 5 | 3.2.3.8 | BK-GCS-PEDCO-120-TE-MT-0005 | MTO For Radio |  | BK-GCS-PEDCO-120-TE-MT-0005 | BK-GCS-PEDCO-120-TE-MT-0005 | BK | GCS | PEDCO | 120 | TE | MT | 0005 | F8Z-709097 | IFI | IFI | 2021-12-27 | 2022-01-03 | 2022-01-05 | 7 | 2 | 9 | IFI | 2022-01-23 | 2022-01-26 | 2022-01-31 | 3 | 5 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-13 |  |  | D01 | IFI | T-0443 | 44570 | 1400/10/19 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-02617 | 44571 | 1400/10/20 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-382553 | 44587 | 1400/11/06 | 44592 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-MT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0337 | 2021-12-13 | 1400/09/22 | [13 empty] | 1400-2294-348051 | 2022-01-03 | 1400/10/13 | 44566 | 1400/10/15 | CM | [10 empty] | D01 | IFI | T-0443 | 44570 | 1400/10/19 |  |  |  | BK-SUR-ENG-TEL-00-02617 | 44571 | 1400/10/20 | AP | [6 empty] | 1400-2294-382553 | 44587 | 1400/11/06 | 44592 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-MT-0005_D00
3 | 2 | 3 | 8 | 4 | 0 | 6 | 3.2.3.8 | BK-GCS-PEDCO-120-TE-MT-0006 | MTO For Telecom. Cable |  | BK-GCS-PEDCO-120-TE-MT-0006 | BK-GCS-PEDCO-120-TE-MT-0006 | BK | GCS | PEDCO | 120 | TE | MT | 0006 | F8Z-709098 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 9 | 0 | 0 | 0 | 3.2.3.9 |  | Architecture | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 9 | 1 | 0 | 0 | 3.2.3.9.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 9 | 1 | 0 | 1 | 3.2.3.9.1 | BK-GCS-PEDCO-120-AR-DW-0001 | Architectural Detail Drawing For Control Building |  | BK-GCS-PEDCO-120-AR-DW-0001 | BK-GCS-PEDCO-120-AR-DW-0001 | BK | GCS | PEDCO | 120 | AR | DW | 0001 | F4B-709099 | AFD | IFC | 2021-12-27 | 2021-12-23 | 2021-12-26 | -4 | 3 | -1 | IFC | 2022-02-05 | 2022-01-31 | 2022-02-02 | -5 | 2 | -3 | IFC | 2022-04-09 | 2022-07-31 | 2022-07-31 | 113 | 0 | 113 | IFA | 2022-08-17 | 2022-08-28 | 2022-09-04 | 11 | 7 | 18 | IFA | 2022-10-17 | 0 | 0 | -44851 | 0 | -44851 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-03 |  |  | D04 | IFA | T-1452 | 44837 | 1401/07/11 | T-1452 | 44837 | 1401/07/11 | BK-SUR-ENG-ARC-01-05883 | 44845 | 1401/07/19 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0341 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-ARC-00-02364 | 44548 | 1400/09/27 | CM-C2 | [6 empty] | 1400-2294-331874 | 2021-12-23 | 1400/10/02 | 44556 | 1400/10/05 | RJ | [10 empty] | D01 | IFC | T-0480 | 44583 | 1400/11/02 |  |  |  | BK-SUR-ENG-ARC-00-02799 | 44585 | 1400/11/04 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0001-D00 | [5 empty] | 1400-2294-390554 | 44592 | 1400/11/11 | 44594 | 1400/11/13 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0001-D00 | [9 empty] | D02 | IFC | T-0734 | 44646 | 1401/01/06 |  |  |  | BK-SUR-ENG-ARC-01-03743 | 44658 | 1401/01/17 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D01 | [5 empty] | 1401-2294-22850 | 44664 | 1401/01/24 | 44667 | 1401/01/27 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D01 | Comment Sheets\NISOC\6376\6376 | 44773 | 1401/05/09 | 44773 | 1401/05/09 | CM |  |  |  | D03 | IFA | T-1236 | 44776 | 1400/05/12 |  |  |  | BK-SUR-ENG-ARC-01-05405 | 44783 | 1401/05/19 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D02 | [5 empty] | 1401-2294-197468 | 44801 | 1401/06/06 | 44808 | 1401/06/13 | CM | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D02 | [9 empty] | D04 | IFA | T-1452 | 44837 | 1401/07/11 | T-1452 | 44837 | 1401/07/11 | BK-SUR-ENG-ARC-01-05883 | 44845 | 1401/07/19 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D03 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D03
3 | 2 | 3 | 9 | 1 | 0 | 2 | 3.2.3.9.1 | BK-GCS-PEDCO-120-AR-DW-0002 | Architectural Detail Drawing For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-AR-DW-0002 | BK-GCS-PEDCO-120-AR-DW-0002 | BK | GCS | PEDCO | 120 | AR | DW | 0002 | F4B-709100 | AFD | IFC | 2022-01-29 | 2022-01-26 | 2022-01-23 | -3 | -3 | -6 | IFA | 2022-04-23 | 2022-04-19 | 2022-04-24 | -4 | 5 | 1 | IFA | 2022-09-10 | 2022-09-14 | 2022-09-19 | 4 | 5 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-01-15 |  |  | D02 | IFA | T-1318 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-05567 | 44804 | 1401/06/09 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-224113 | 44818 | 1401/06/23 | 44823 | 1401/06/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0459 | 2022-01-15 | 1400/10/25 |  |  |  | BK-SUR-ENG-ARC-00-02755 | 44583 | 1400/11/01 | CM-C2 |  | BK-SUR-ENG-ARC-00-02818 | 44587 | 1400/11/06 | CM |  | 1400-2294-377543 | 2022-01-26 | 1400/11/06 | 44584 | 1400/11/03 | CM | [10 empty] | D01 | IFA | T-0786 | 44660 | 1401/01/20 |  |  |  | BK-SUR-ENG-ARC-01-03902 | 44664 | 1401/01/24 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D00 | [5 empty] | 1401-2294-31077 | 44670 | 1401/01/30 | 44675 | 1401/01/04 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D00 | [9 empty] | D02 | IFA | T-1318 | 44800 | 1401/06/05 |  |  |  | BK-SUR-ENG-ARC-01-05567 | 44804 | 1401/06/09 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D01 | [5 empty] | 1401-2294-224113 | 44818 | 1401/06/23 | 44823 | 1401/06/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D01
3 | 2 | 3 | 9 | 1 | 0 | 3 | 3.2.3.9.1 | BK-GCS-PEDCO-120-AR-DW-0003 | Architectural Drawing For Gas Compressors Shelter |  | BK-GCS-PEDCO-120-AR-DW-0003 | BK-GCS-PEDCO-120-AR-DW-0003 | BK | GCS | PEDCO | 120 | AR | DW | 0003 | F4K-709101 | AFD | IFC | 2022-06-25 | 2022-06-21 | 2022-06-25 | -4 | 4 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-11 |  |  | D00 | IFC | T-1064 | 44723 | 1401/03/21 | T-1064 | 44723 | 1401/03/21 | BK-SUR-ENG-ARC-01-04732 | 44730 | 1401/03/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-111567 | 44733 | 1401/03/31 | 44737 | 1401/04/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1064 | 2022-06-11 | 1401/03/21 | T-1064 | 44723 | 1401/03/21 | BK-SUR-ENG-ARC-01-04732 | 44730 | 1401/03/28 | CM-C3 | [6 empty] | 1401-2294-111567 | 2022-06-21 | 1401/03/31 | 44737 | 1401/04/04 | CM
3 | 2 | 3 | 9 | 1 | 0 | 4 | 3.2.3.9.1 | BK-GCS-PEDCO-120-AR-DW-0004 | Architectural Drawing For Chemical Inj. Packages/Chemical Storage Shelter |  | BK-GCS-PEDCO-120-AR-DW-0004 | BK-GCS-PEDCO-120-AR-DW-0004 | BK | GCS | PEDCO | 120 | AR | DW | 0004 | F4B-709102 | AFD | IFC | 2022-09-17 | 2022-09-18 | 2022-09-20 | 1 | 2 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1347 | 44807 | 1401/06/12 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-05634 | 44816 | 1401/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-227958 | 44822 | 1401/06/27 | 44824 | 1401/06/29 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1347 | 2022-09-03 | 1401/06/12 |  |  |  | BK-SUR-ENG-ARC-01-05634 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-227958 | 2022-09-18 | 1401/06/27 | 44824 | 1401/06/29 | RJ
3 | 2 | 3 | 9 | 1 | 0 | 5 | 3.2.3.9.1 | BK-GCS-PEDCO-120-AR-DW-0005 | Architectural Drawing For Utility Shelter |  | BK-GCS-PEDCO-120-AR-DW-0005 | BK-GCS-PEDCO-120-AR-DW-0005 | BK | GCS | PEDCO | 120 | AR | DW | 0005 | F4B-709103 | AFD | IFC | 2022-09-28 | 2022-09-28 | 2022-10-02 | 0 | 4 | 4 | IFC | 2022-11-09 | 0 | 0 | -44874 | 0 | -44874 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-10-26 |  |  | D01 | IFC | T-1560 | 44860 | 1401/08/04 | T-1560 | 44860 | 1401/08/04 | BK-SUR-ENG-ARC-01-06095 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1406 | 2022-09-14 | 1401/06/23 | T-1406 | 44818 | 1401/06/23 | BK-SUR-ENG-ARC-01-05732 | 44825 | 1401/06/30 | CM-C2 | [6 empty] | 1401-2294-238589 | 2022-09-28 | 1401/07/06 | 44836 | 1401/07/10 | RJ | [10 empty] | D01 | IFC | T-1560 | 44860 | 1401/08/04 | T-1560 | 44860 | 1401/08/04 | BK-SUR-ENG-ARC-01-06095 | 44871 | 1401/08/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0005_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0005_D00
3 | 2 | 3 | 9 | 1 | 0 | 6 | 3.2.3.9.1 | BK-GCS-PEDCO-120-AR-DW-0006 | Architectural Drawing For Fire Water Pumps Shelter |  | BK-GCS-PEDCO-120-AR-DW-0006 | BK-GCS-PEDCO-120-AR-DW-0006 | BK | GCS | PEDCO | 120 | AR | DW | 0006 | F4B-709104 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 9 | 1 | 0 | 7 | 3.2.3.9.1 | BK-GCS-PEDCO-120-AR-DW-0007 | Architectural Drawing For Fire Shed |  | BK-GCS-PEDCO-120-AR-DW-0007 | BK-GCS-PEDCO-120-AR-DW-0007 | BK | GCS | PEDCO | 120 | AR | DW | 0007 | F4B-709105 | AFD | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | IFA | 2022-10-29 | 0 | 0 | -44863 | 0 | -44863 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-01 |  |  | D01 | IFA | T-1494 | 44849 | 1401/07/23 | T-1494 | 44849 | 1401/07/23 | BK-SUR-ENG-ARC-01-05943 | 44856 | 1401/07/30 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 44691 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 44697 | 1401/02/26 | CM | [10 empty] | D01 | IFA | T-1494 | 44849 | 1401/07/23 | T-1494 | 44849 | 1401/07/23 | BK-SUR-ENG-ARC-01-05943 | 44856 | 1401/07/30 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0007_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0007_D00
[7 empty] | 3.2.3.9.2 | BK-GCS-PEDCO-120-AR-DW-0008 | Architectural Drawing For CCTV Control Room- Binak GCS |  | BK-GCS-PEDCO-120-AR-DW-0008 | BK-GCS-PEDCO-120-AR-DW-0008 | BK | GCS | PEDCO | 120 | AR | DW | 0008 | F4B-709396 | AFD | IFC | 2022-07-12 | 2022-07-09 | 2022-07-11 | -3 | 2 | -1 | IFA | 2022-11-07 | 2022-11-05 | 2022-11-06 | -2 | 1 | -1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-28 |  |  | D01 | IFA | T-1538 | 44858 | 1401/08/02 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-05998 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0008_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296558 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1129 | 2022-06-28 | 1401/04/07 |  |  |  | BK-SUR-ENG-ARC-01-05042 | 44751 | 1401/04/18 | CM-C2 | [6 empty] | 1401-2294-134792 | 2022-07-09 | 1401/04/18 | 44753 | 1401/04/20 | CM | [10 empty] | D01 | IFA | T-1538 | 44858 | 1401/08/02 |  |  |  | BK-SUR-ENG-ARC-01-05998 | 44863 | 1401/08/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0008_D00 | [5 empty] | 1401-2294-296558 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0008_D00
[7 empty] | 3.2.3.9.3 | BK-GCS-PEDCO-120-AR-DW-0009 | Architectural Drawing For CCTV Control Room- Binak DU |  | BK-GCS-PEDCO-120-AR-DW-0009 | BK-GCS-PEDCO-120-AR-DW-0009 | BK | GCS | PEDCO | 120 | AR | DW | 0009 | F4B-709397 | AFD | IFC | 2022-07-11 | 2022-07-09 | 2022-07-11 | -2 | 2 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-06-27 |  |  | D00 | IFC | T-1119 | 44739 | 1401/04/06 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-05041 | 44751 | 1401/04/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-134795 | 44751 | 1401/04/18 | 44753 | 1401/04/20 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1119 | 2022-06-27 | 1401/04/06 |  |  |  | BK-SUR-ENG-ARC-01-05041 | 44751 | 1401/04/18 | CM-C2 | [6 empty] | 1401-2294-134795 | 2022-07-09 | 1401/04/18 | 44753 | 1401/04/20 | CM
[7 empty] | 3.2.3.9.4 | BK-GCS-PEDCO-120-AR-DW-0010 | Architectural Drawing For CCTV Rack Room- Binak PU |  | BK-GCS-PEDCO-120-AR-DW-0010 | BK-GCS-PEDCO-120-AR-DW-0010 | BK | GCS | PEDCO | 120 | AR | DW | 0010 | F4B-709398 | AFD | IFC | 2022-09-10 | 2022-09-28 | 2022-10-02 | 18 | 4 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-27 |  |  | D00 | IFC | T-1319 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-05570 | 44804 | 1401/06/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-240288 | 44832 | 1401/07/06 | 44836 | 1401/07/010 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1319 | 2022-08-27 | 1401/06/05 |  |  |  | BK-SUR-ENG-ARC-01-05570 | 44804 | 1401/06/09 | CM-C2 | [6 empty] | 1401-2294-240288 | 2022-09-28 | 1401/07/06 | 44836 | 1401/07/010 | CM
3 | 2 | 3 | 9 | 2 | 0 | 0 | 3.2.3.9.2 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 9 | 2 | 0 | 1 | 3.2.3.9 | BK-GCS-PEDCO-120-AR-MT-0001 | MTO For Architectural Works |  | BK-GCS-PEDCO-120-AR-MT-0001 | BK-GCS-PEDCO-120-AR-MT-0001 | BK | GCS | PEDCO | 120 | AR | MT | 0001 | F8Z-709106 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 9 | 2 | 0 | 2 | 3.2.3.9 | BK-GCS-PEDCO-120-AR-MT-0002 | MTO For Blast Proof Doors |  | BK-GCS-PEDCO-120-AR-MT-0002 | BK-GCS-PEDCO-120-AR-MT-0002 | BK | GCS | PEDCO | 120 | AR | MT | 0002 | F8Z-709107 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 10 | 0 | 0 | 0 | 3.2.3.10 |  | Civil | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 10 | 1 | 0 | 0 | 3.2.3.10.1 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 10 | 1 | 0 | 1 | 3.2.3.10.1 | BK-GCS-PEDCO-120-CV-PY-0001 | Site Sewarage System Layout & Details |  | BK-GCS-PEDCO-120-CV-PY-0001 | BK-GCS-PEDCO-120-CV-PY-0001 | BK | GCS | PEDCO | 120 | CV | PY | 0001 | F4S-709108 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 10 | 1 | 0 | 2 | 3.2.3.10.1 | BK-GCS-PEDCO-120-CV-PY-0002 | Cable Trench and Duct Bank Layout |  | BK-GCS-PEDCO-120-CV-PY-0002 | BK-GCS-PEDCO-120-CV-PY-0002 | BK | GCS | PEDCO | 120 | CV | PY | 0002 | F4S-709109 | AFC | IFC | 2022-08-08 | 2022-08-14 | 2022-08-17 | 6 | 3 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-25 |  |  | D00 | IFC | T-1190 | 44767 | 1401/05/03 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05325 | 44774 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177091 | 44787 | 1401/05/23 | 44790 | 1401/05/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1190 | 2022-07-25 | 1401/05/03 |  |  |  | BK-SUR-ENG-CIV-01-05325 | 44774 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-177091 | 2022-08-14 | 1401/05/23 | 44790 | 1401/05/26 | CM
3 | 2 | 3 | 10 | 1 | 0 | 3 | 3.2.3.10.1 | BK-GCS-PEDCO-120-CV-PY-0003 | Oil Contaminated Water System Layout |  | BK-GCS-PEDCO-120-CV-PY-0003 | BK-GCS-PEDCO-120-CV-PY-0003 | BK | GCS | PEDCO | 120 | CV | PY | 0003 | F4S-709110 | AFC | IFC | 2022-06-12 | 2022-06-02 | 2022-06-08 | -10 | 6 | -4 | IFC | 2022-10-02 | 2022-09-26 | 2022-10-02 | -6 | 6 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-29 |  |  | D01 | IFC | T-1409 | 44822 | 1401/06/27 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05742 | 44825 | 1401/06/30 | CM-C2 | PEDCO-BK-GCS-PEDCO-120-CV-PY-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238114 | 44830 | 1401/07/04 | 44836 | 1401/07/10 | CM | NISOC-BK-GCS-PEDCO-120-CV-PY-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1019 | 2022-05-29 | 1401/03/08 | T-1019 | 44710 | 1401/03/08 | BK-SUR-ENG-CIV-01-04581 | 44719 | 1401/03/17 | CM-C2 | [6 empty] | 1401-2294-87503 | 2022-06-02 | 1401/03/12 | 44720 | 1401/03/18 | CM | [10 empty] | D01 | IFC | T-1409 | 44822 | 1401/06/27 |  |  |  | BK-SUR-ENG-CIV-01-05742 | 44825 | 1401/06/30 | CM-C2 | PEDCO-BK-GCS-PEDCO-120-CV-PY-0003_D00 | [5 empty] | 1401-2294-238114 | 44830 | 1401/07/04 | 44836 | 1401/07/10 | CM | NISOC-BK-GCS-PEDCO-120-CV-PY-0003_D00
3 | 2 | 3 | 10 | 1 | 0 | 4 | 3.2.3.10.1 | BK-GCS-PEDCO-120-CV-PY-0004 | Plant Clean Water Drainage System Layout & Details |  | BK-GCS-PEDCO-120-CV-PY-0004 | BK-GCS-PEDCO-120-CV-PY-0004 | BK | GCS | PEDCO | 120 | CV | PY | 0004 | F4S-709111 | AFC | IFC | 2022-06-14 | 2022-06-14 | 2022-06-15 | 0 | 1 | 1 | IFA | 2022-10-25 | 2022-10-29 | 2022-10-30 | 4 | 1 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-31 |  |  | D01 | IFA | T-1479 | 44845 | 1401/07/19 | T-1479 | 44845 | 1401/07/19 | BK-SUR-ENG-CIV-01-05939 | 44856 | 1401/07/30 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-PY-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-284599 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-CV-PY-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1027 | 2022-05-31 | 1401/03/10 | T-1027 | 44712 | 1401/03/10 | BK-SUR-ENG-CIV-01-04583 | 44719 | 1401/03/17 | CM-C2 | [6 empty] | 1401-2294-101255 | 2022-06-14 | 1401/03/24 | 44727 | 1401/03/25 | CM | [10 empty] | D01 | IFA | T-1479 | 44845 | 1401/07/19 | T-1479 | 44845 | 1401/07/19 | BK-SUR-ENG-CIV-01-05939 | 44856 | 1401/07/30 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-PY-0004_D00 | [5 empty] | 1401-2294-284599 | 44863 | 1401/08/07 | 44864 | 1401/08/08 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-CV-PY-0004_D00
3 | 2 | 3 | 10 | 1 | 0 | 5 | 3.2.3.10.1 | BK-GCS-PEDCO-120-CV-PY-0005 | Road, Paving And Plant Finish Grading Layout & Sections |  | BK-GCS-PEDCO-120-CV-PY-0005 | BK-GCS-PEDCO-120-CV-PY-0005 | BK | GCS | PEDCO | 120 | CV | PY | 0005 | F4S-709112 | AFC | IFC | 2022-10-05 | 2022-10-10 | 2022-10-12 | 5 | 2 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1432 | 44825 | 1401/06/30 | T-1432 | 44830 | 1401/07/04 | BK-SUR-ENG-CIV-01-05833 | 44838 | 1401/07/12 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-256168 | 44844 | 1401/07/18 | 44846 | 1401/07/20 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1432 | 2022-09-21 | 1401/06/30 | T-1432 | 44830 | 1401/07/04 | BK-SUR-ENG-CIV-01-05833 | 44838 | 1401/07/12 | CM-C2 | [6 empty] | 1401-2294-256168 | 2022-10-10 | 1401/07/18 | 44846 | 1401/07/20 | RJ
3 | 2 | 3 | 10 | 1 | 0 | 6 | 3.2.3.10.1 | BK-GCS-PEDCO-120-CV-PY-0006 | Plant Underground Composite Layout |  | BK-GCS-PEDCO-120-CV-PY-0006 | BK-GCS-PEDCO-120-CV-PY-0006 | BK | GCS | PEDCO | 120 | CV | PY | 0006 | F4S-709113 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[7 empty] | 3.2.3.10.2 | BK-GCS-PEDCO-120-CV-PY-0007 | Rough Grading Plan and Details |  | BK-GCS-PEDCO-120-CV-PY-0007 | BK-GCS-PEDCO-120-CV-PY-0007 | BK | GCS | PEDCO | 120 | CV | PY | 0007 | F5S-709395 | AFC | IFC | 2022-06-06 | 2022-06-01 | 2022-06-07 | -5 | 6 | 1 | IFA | 2022-08-31 | 2022-08-31 | 2022-09-05 | 0 | 5 | 5 | IFA | 2022-10-05 | 2022-10-10 | 2022-10-17 | 5 | 7 | 12 | IFA | 2022-11-02 | 2022-11-05 | 2022-11-06 | 3 | 1 | 4 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-23 |  |  | D03 | IFA | T-1515 | 44853 | 1401/07/27 | T-1515 | 44853 | 1401/07/27 | BK-SUR-ENG-CIV-01-06038 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-PY-0007_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296586 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-GCS-PEDCO-120-CV-PY-0007_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0995 | 2022-05-23 | 1401/03/02 |  |  |  | BK-SUR-ENG-CIV-01-04533 | 44718 | 1401/03/16 | CM-C3 | [6 empty] | 1401-2294-87169 | 2022-06-01 | 1401/03/11 | 44719 | 1401/03/17 | CM | [10 empty] | D01 | IFA | T-1285 | 44790 | 1401/05/26 |  |  |  | BK-SUR-ENG-CIV-01-05554 | 44802 | 1401/06/07 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-PY-0007_D00 | [5 empty] | 1401-2294-205616 | 44804 | 1401/06/09 | 44809 | 1401/06/14 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-CV-PY-0007_D00 | [9 empty] | D02 | IFA | T-1428 | 44825 | 1401/06/30 |  |  |  | BK-SUR-ENG-CIV-01-05783 | 44836 | 1401/07/10 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-PY-0007_D01 | [5 empty] | 1401-2294-260292 | 44844 | 1401/07/20 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-CV-PY-0007_D01 | [9 empty] | D03 | IFA | T-1515 | 44853 | 1401/07/27 | T-1515 | 44853 | 1401/07/27 | BK-SUR-ENG-CIV-01-06038 | 44865 | 1401/08/09 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-PY-0007_D02 | [5 empty] | 1401-2294-296586 | 44870 | 1401/08/14 | 44871 | 1401/08/15 | AP | NISOC-CRS-BK-GCS-PEDCO-120-CV-PY-0007_D02
3 | 2 | 3 | 10 | 2 | 0 | 0 | 3.2.3.10.2 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 10 | 2 | 0 | 1 | 3.2.3.10.2 | BK-GCS-PEDCO-120-CV-CN-0001 | Calculation Note For Inside Surface Water Drainage Channels |  | BK-GCS-PEDCO-120-CV-CN-0001 | BK-GCS-PEDCO-120-CV-CN-0001 | BK | GCS | PEDCO | 120 | CV | CN | 0001 | F0Z-709114 | AFC | IFC | 2022-09-05 | 2022-09-07 | 2022-09-13 | 2 | 6 | 8 | IFA | 2022-10-08 | 2022-10-12 | 2022-10-17 | 4 | 5 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-22 |  |  | D01 | IFA | T-1435 | 44828 | 1401/07/02 | T-1435 | 44828 | 1401/07/02 | BK-SUR-ENG-CIV-01-05834 | 44838 | 1401/07/12 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-260525 | 44846 | 1401/07/20 | 44851 | 1401/07/25 | AP | NISOC-CRS-BK-GCS-PEDCO-120-CV-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1300 | 2022-08-22 | 1401/05/31 |  |  |  | BK-SUR-ENG-CIV-01-05556 | 36767 | 1401/06/07 | CM-C3 | [6 empty] | 1401-2294-210053 | 2022-09-07 | 1401/06/13 | 44817 | 1401/06/21 | CM | [10 empty] | D01 | IFA | T-1435 | 44828 | 1401/07/02 | T-1435 | 44828 | 1401/07/02 | BK-SUR-ENG-CIV-01-05834 | 44838 | 1401/07/12 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-CN-0001_D00 | [5 empty] | 1401-2294-260525 | 44846 | 1401/07/20 | 44851 | 1401/07/25 | AP | NISOC-CRS-BK-GCS-PEDCO-120-CV-CN-0001_D00
3 | 2 | 3 | 10 | 2 | 0 | 2 | 3.2.3.10.2 | BK-GCS-PEDCO-120-CV-CN-0002 | Calculation Note for offsite flood control system |  | BK-GCS-PEDCO-120-CV-CN-0002 | BK-GCS-PEDCO-120-CV-CN-0002 | BK | GCS | PEDCO | 120 | CV | CN | 0002 | F0Z-709115 | AFC | IFC | 2022-08-03 | 2022-08-02 | 2022-08-09 | -1 | 7 | 6 | IFA | 2022-09-04 | 2022-08-31 | 2022-09-04 | -4 | 4 | 0 | IFA | 2022-10-08 | 2022-10-12 | 2022-10-17 | 4 | 5 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-20 |  |  | D02 | IFA | T-1435 | 44828 | 1401/07/02 | T-1435 | 44828 | 1401/07/02 | BK-SUR-ENG-CIV-01-05834 | 44838 | 1401/07/12 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-CN-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-260525 | 44846 | 1401/07/20 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-CV-CN-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1173 | 2022-07-20 | 1401/04/29 |  |  |  | BK-SUR-ENG-CIV-01-05241 | 44768 | 1401/05/04 | CM-C2 | [6 empty] | 1401-2294-164801 | 2022-08-02 | 1401/05/11 | 44782 | 1401/05/18 | CM | [10 empty] | D01 | IFA | T-1294 | 44794 | 1401/05/30 |  |  |  | BK-SUR-ENG-CIV-01-05555 | 44802 | 1401/06/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-CN-0002_D00 | [5 empty] | 1401-2294-205623 | 44804 | 1401/06/09 | 44808 | 1401/06/13 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-CV-CN-0002_D00 | [9 empty] | D02 | IFA | T-1435 | 44828 | 1401/07/02 | T-1435 | 44828 | 1401/07/02 | BK-SUR-ENG-CIV-01-05834 | 44838 | 1401/07/12 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-CN-0002_D02 | [5 empty] | 1401-2294-260525 | 44846 | 1401/07/20 | 44851 | 1401/07/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-CV-CN-0002_D02
3 | 2 | 3 | 10 | 2 | 0 | 2 | 3.2.3.10.2 | BK-GCS-PEDCO-120-CV-CN-0002 | Calculation Note For Oily Contaminated Water Drainage Channels |  | BK-GCS-PEDCO-120-CV-CN-0003 | BK-GCS-PEDCO-120-CV-CN-0002 | BK | GCS | PEDCO | 120 | CV | CN | 0002 | F0Z-709115 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 10 | 3 | 0 | 0 | 3.2.3.10.3 |  | Report | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 10 | 3 | 0 | 1 | 3.2.3.10.3 | BK-GCS-PEDCO-120-CV-RT-0001 | Site Visit Report (Civil Work) - GCS |  | BK-GCS-PEDCO-120-CV-RT-0001 | BK-GCS-PEDCO-110-CV-RT-0001 | BK | GCS | PEDCO | 110 | CV | RT | 0001 | F0Z-709116 | IFI | IFC | 2022-03-27 | 2022-03-16 | 2022-03-25 | -11 | 9 | -2 | IFI | 2022-08-09 | 2022-08-28 | 2022-08-31 | 19 | 3 | 22 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-13 |  |  | D01 | IFI | T-1204 | 44768 | 1401/05/04 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-05346 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-197427 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-CV-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0722 | 2022-03-13 | 1400/12/21 |  |  |  | BK-SUR-ENG-CIV-00-03622 | 44636 | 1400/12/25 | CM-C2 | [6 empty] | 1400-2294-452219 | 2022-03-16 | 1400/12/25 | 44645 | 1401/01/08 | CM | [10 empty] | D01 | IFI | T-1204 | 44768 | 1401/05/04 |  |  |  | BK-SUR-ENG-CIV-01-05346 | 44776 | 1401/05/12 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-CV-RT-0001_D01 | [5 empty] | 1401-2294-197427 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-CV-RT-0001_D01
3 | 2 | 3 | 10 | 4 | 0 | 0 | 3.2.3.10.4 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 10 | 4 | 0 | 1 | 3.2.3.10 | BK-GCS-PEDCO-120-CV-MT-0001 | MTO For Civil Work |  | BK-GCS-PEDCO-120-CV-MT-0001 | BK-GCS-PEDCO-120-CV-MT-0001 | BK | GCS | PEDCO | 120 | CV | MT | 0001 | F8Z-709117 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 0 | 0 | 0 | 3.2.3.11 |  | Structure | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 11 | 1 | 0 | 0 | 3.2.3.11.1 |  | Calculation | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 11 | 1 | 0 | 1 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0002 | Structural Calculation Note For Control Building |  | BK-GCS-PEDCO-120-ST-CN-0002 | BK-GCS-PEDCO-120-ST-CN-0002 | BK | GCS | PEDCO | 120 | ST | CN | 0002 | F0Z-709118 | AFD | IFC | 2022-10-29 | 2022-10-25 | 2022-10-26 | -4 | 1 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1498 | 44849 | 1401/07/23 | T-1498 | 44849 | 1401/07/23 | BK-SUR-ENG-STR-01-05992 | 44860 | 1401/08/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279776 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1498 | 2022-10-15 | 1401/07/23 | T-1498 | 44849 | 1401/07/23 | BK-SUR-ENG-STR-01-05992 | 44860 | 1401/08/04 | CM | [6 empty] | 1401-2294-279776 | 2022-10-25 | 1401/08/03 | 44860 | 1401/08/04 | RJ
3 | 2 | 3 | 11 | 1 | 0 | 2 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0003 | Calculation Report for Gas Compressors Shelter |  | BK-GCS-PEDCO-120-ST-CN-0003 | BK-GCS-PEDCO-120-ST-CN-0003 | BK | GCS | PEDCO | 120 | ST | CN | 0003 | F0Z-709119 | AFD | IFC | 2022-08-06 | 2022-08-28 | 2022-08-31 | 22 | 3 | 25 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1177 | 44765 | 1401/05/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-198818 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1177 | 2022-07-23 | 1401/05/01 | [13 empty] | 1401-2294-198818 | 2022-08-28 | 1401/06/06 | 44804 | 1401/06/09 | RJ
3 | 2 | 3 | 11 | 1 | 0 | 3 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0005 | Calculation Report for Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-ST-CN-0005 | BK-GCS-PEDCO-120-ST-CN-0005 | BK | GCS | PEDCO | 120 | ST | CN | 0005 | F0Z-709120 | AFD | IFC | 2022-09-19 | 2022-09-14 | 2022-09-19 | -5 | 5 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1359 | 44809 | 1401/06/14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-224914 | 44818 | 1401/06/23 | 44823 | 1401/06/28 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1359 | 2022-09-05 | 1401/06/14 | [13 empty] | 1401-2294-224914 | 2022-09-14 | 1401/06/23 | 44823 | 1401/06/28 | RJ
3 | 2 | 3 | 11 | 1 | 0 | 4 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0006 | Calculation Note for Gas Compressors Foundation |  | BK-GCS-PEDCO-120-ST-CN-0006 | BK-GCS-PEDCO-120-ST-CN-0006 | BK | GCS | PEDCO | 120 | ST | CN | 0006 | F0Z-709121 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 5 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0007 | Calculation Note for Tank Foundation (TK-2301 A/B) |  | BK-GCS-PEDCO-120-ST-CN-0007 | BK-GCS-PEDCO-120-ST-CN-0007 | BK | GCS | PEDCO | 120 | ST | CN | 0007 | F0Z-709122 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 6 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0008 | Calculation Note for Utility Shelter |  | BK-GCS-PEDCO-120-ST-CN-0008 | BK-GCS-PEDCO-120-ST-CN-0008 | BK | GCS | PEDCO | 120 | ST | CN | 0008 | F0Z-709123 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 7 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0009 | Calculation Note for Fire Water Pump Shelter |  | BK-GCS-PEDCO-120-ST-CN-0009 | BK-GCS-PEDCO-120-ST-CN-0009 | BK | GCS | PEDCO | 120 | ST | CN | 0009 | F0Z-709124 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 8 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0010 | Calculation Note for Foundation of Slug Catcher Drum (V-2104) |  | BK-GCS-PEDCO-120-ST-CN-0010 | BK-GCS-PEDCO-120-ST-CN-0010 | BK | GCS | PEDCO | 120 | ST | CN | 0010 | F0Z-709125 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 9 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0011 | Calculation Note for Foundation of Dehydration Package (PK-2101) |  | BK-GCS-PEDCO-120-ST-CN-0011 | BK-GCS-PEDCO-120-ST-CN-0011 | BK | GCS | PEDCO | 120 | ST | CN | 0011 | F0Z-709126 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 10 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0012 | Calculation Note for Close Drain Sump Pit (SU-2201 A) |  | BK-GCS-PEDCO-120-ST-CN-0012 | BK-GCS-PEDCO-120-ST-CN-0012 | BK | GCS | PEDCO | 120 | ST | CN | 0012 | F0Z-709127 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 11 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0013 | Calculation Note for Oily Water Sump Pit (SU-2201 B) |  | BK-GCS-PEDCO-120-ST-CN-0013 | BK-GCS-PEDCO-120-ST-CN-0013 | BK | GCS | PEDCO | 120 | ST | CN | 0013 | F0Z-709128 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 12 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0014 | Calculation Note For Compressor Area Main Sleepers |  | BK-GCS-PEDCO-120-ST-CN-0014 | BK-GCS-PEDCO-120-ST-CN-0014 | BK | GCS | PEDCO | 120 | ST | CN | 0014 | F0Z-709129 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 13 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0015 | Calculation Note For Flare Area Sleepers |  | BK-GCS-PEDCO-120-ST-CN-0015 | BK-GCS-PEDCO-120-ST-CN-0015 | BK | GCS | PEDCO | 120 | ST | CN | 0015 | F0Z-709130 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 14 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0016 | Calculation Note For Special Pipe Supports |  | BK-GCS-PEDCO-120-ST-CN-0016 | BK-GCS-PEDCO-120-ST-CN-0016 | BK | GCS | PEDCO | 120 | ST | CN | 0016 | F0Z-709131 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 15 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0017 | Calculation Note for1st Stage Air Coolers (AE-2101 A/B/C) |  | BK-GCS-PEDCO-120-ST-CN-0017 | BK-GCS-PEDCO-120-ST-CN-0017 | BK | GCS | PEDCO | 120 | ST | CN | 0017 | F0Z-709132 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 16 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0018 | Calculation Note for 2nd Stage Air Coolers (AE-2102 A/B/C) |  | BK-GCS-PEDCO-120-ST-CN-0018 | BK-GCS-PEDCO-120-ST-CN-0018 | BK | GCS | PEDCO | 120 | ST | CN | 0018 | F0Z-709133 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 17 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0019 | Calculation Note for Elevated Potable Water Tank (TK-2209) |  | BK-GCS-PEDCO-120-ST-CN-0019 | BK-GCS-PEDCO-120-ST-CN-0019 | BK | GCS | PEDCO | 120 | ST | CN | 0019 | F0Z-709134 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 18 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0020 | Calculation Note for Lean Glycol Storage Tank (TK-2102) |  | BK-GCS-PEDCO-120-ST-CN-0020 | BK-GCS-PEDCO-120-ST-CN-0020 | BK | GCS | PEDCO | 120 | ST | CN | 0020 | F0Z-709135 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 19 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0021 | Calculation Note for Nitrogen Package (PK-2204A/B) |  | BK-GCS-PEDCO-120-ST-CN-0021 | BK-GCS-PEDCO-120-ST-CN-0021 | BK | GCS | PEDCO | 120 | ST | CN | 0021 | F0Z-709136 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 20 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0022 | Calculation Note for Glycol Sump Pit (SU-2101) |  | BK-GCS-PEDCO-120-ST-CN-0022 | BK-GCS-PEDCO-120-ST-CN-0022 | BK | GCS | PEDCO | 120 | ST | CN | 0022 | F0Z-709137 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 21 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0023 | Calculation Note for Slug Pumps (P-2101A/B) |  | BK-GCS-PEDCO-120-ST-CN-0023 | BK-GCS-PEDCO-120-ST-CN-0023 | BK | GCS | PEDCO | 120 | ST | CN | 0023 | F0Z-709138 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 22 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0024 | Calculation Note for Utility Area Sleepers |  | BK-GCS-PEDCO-120-ST-CN-0024 | BK-GCS-PEDCO-120-ST-CN-0024 | BK | GCS | PEDCO | 120 | ST | CN | 0024 | F0Z-709139 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 23 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0025 | Calculation Note for Pipe rack |  | BK-GCS-PEDCO-120-ST-CN-0025 | BK-GCS-PEDCO-120-ST-CN-0025 | BK | GCS | PEDCO | 120 | ST | CN | 0025 | F0Z-709140 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 1 | 0 | 24 | 3.2.3.11.1 | BK-GCS-PEDCO-120-ST-CN-0026 | Calculation Note for Chemical Injection and Storage Shelter |  | BK-GCS-PEDCO-120-ST-CN-0026 | BK-GCS-PEDCO-120-ST-CN-0026 | BK | GCS | PEDCO | 120 | ST | CN | 0026 | F0Z-709141 | AFD | IFC | 2022-09-11 | 2022-09-06 | 2022-09-12 | -5 | 6 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1323 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-05633 | 44816 | 1401/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213890 | 44810 | 1401/06/15 | 44816 | 1401/06/21 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1323 | 2022-08-28 | 1401/06/06 |  |  |  | BK-SUR-ENG-STR-01-05633 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-213890 | 2022-09-06 | 1401/06/15 | 44816 | 1401/06/21 | RJ
[8 empty] | BK-GCS-PEDCO-120-ST-CN-0027 | Calculation Note For CCTV Control Room- Binak GCS |  | BK-GCS-PEDCO-120-ST-CN-0027 | BK-GCS-PEDCO-120-ST-CN-0027 | BK | GCS | PEDCO | 120 | ST | CN | 0027 | F0Z-709399 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[8 empty] | BK-GCS-PEDCO-120-ST-CN-0028 | Calculation Note for CCTV Control Room- Binak DU |  | BK-GCS-PEDCO-120-ST-CN-0028 | BK-GCS-PEDCO-120-ST-CN-0028 | BK | GCS | PEDCO | 120 | ST | CN | 0028 | F0Z-709400 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[8 empty] | BK-GCS-PEDCO-120-ST-CN-0029 | Calculation Note For CCTV Rack Room- Binak PU |  | BK-GCS-PEDCO-120-ST-CN-0029 | BK-GCS-PEDCO-120-ST-CN-0029 | BK | GCS | PEDCO | 120 | ST | CN | 0029 | F0Z-709401 | AFD | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 0 | 3.2.3.11.2 |  | Drawing/Diagram | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 11 | 2 | 0 | 1 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0003 | Foundation Location Plan |  | BK-GCS-PEDCO-120-ST-DW-0003 | BK-GCS-PEDCO-120-ST-DW-0003 | BK | GCS | PEDCO | 120 | ST | DW | 0003 | F4Q-709142 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 2 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0004 | Foundation Drawing For 1st Stage Gas Compressor (C-2101A/B/C) |  | BK-GCS-PEDCO-120-ST-DW-0004 | BK-GCS-PEDCO-120-ST-DW-0004 | BK | GCS | PEDCO | 120 | ST | DW | 0004 | F4Q-709143 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 3 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0005 | Foundation Drawing For 2nd Stage Gas Compressor (C-2102A/B/C) |  | BK-GCS-PEDCO-120-ST-DW-0005 | BK-GCS-PEDCO-120-ST-DW-0005 | BK | GCS | PEDCO | 120 | ST | DW | 0005 | F4Q-709144 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 4 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0007 | Foundation Drawing For 1st Stage Air Coolers (AE-2101 A/B/C) |  | BK-GCS-PEDCO-120-ST-DW-0007 | BK-GCS-PEDCO-120-ST-DW-0007 | BK | GCS | PEDCO | 120 | ST | DW | 0007 | F4Q-709145 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 5 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0008 | Foundation Drawing For 2nd Stage Air Coolers (AE-2102 A/B/C) |  | BK-GCS-PEDCO-120-ST-DW-0008 | BK-GCS-PEDCO-120-ST-DW-0008 | BK | GCS | PEDCO | 120 | ST | DW | 0008 | F4Q-709146 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 6 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0009 | Foundation Drawing For Inlet Gas K.O. Drum (V-2105) |  | BK-GCS-PEDCO-120-ST-DW-0009 | BK-GCS-PEDCO-120-ST-DW-0009 | BK | GCS | PEDCO | 120 | ST | DW | 0009 | F4Q-709147 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 7 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0010 | Foundation Drawing For For 1st Stage G.C. Suction Drums (V-2101 A/B/C) |  | BK-GCS-PEDCO-120-ST-DW-0010 | BK-GCS-PEDCO-120-ST-DW-0010 | BK | GCS | PEDCO | 120 | ST | DW | 0010 | F4Q-709148 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 8 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0011 | Foundation Drawing For For 2nd Stage G.C. Suction Drums (V-2102 A/B/C) |  | BK-GCS-PEDCO-120-ST-DW-0011 | BK-GCS-PEDCO-120-ST-DW-0011 | BK | GCS | PEDCO | 120 | ST | DW | 0011 | F4Q-709149 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 9 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0012 | Foundation Drawing For 2nd Stage G.C. Discharge Drum (V-2103) |  | BK-GCS-PEDCO-120-ST-DW-0012 | BK-GCS-PEDCO-120-ST-DW-0012 | BK | GCS | PEDCO | 120 | ST | DW | 0012 | F4Q-709150 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 10 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0013 | Foundation Drawing For Fuel Oil Drum (V-2206) |  | BK-GCS-PEDCO-120-ST-DW-0013 | BK-GCS-PEDCO-120-ST-DW-0013 | BK | GCS | PEDCO | 120 | ST | DW | 0013 | F4Q-709151 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 11 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0014 | Foundation Drawing For Instrument Air Receiver (V-2203) |  | BK-GCS-PEDCO-120-ST-DW-0014 | BK-GCS-PEDCO-120-ST-DW-0014 | BK | GCS | PEDCO | 120 | ST | DW | 0014 | F4Q-709152 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 12 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0015 | Foundation Drawing For Elevated Potable Water Tank (TK-2209) |  | BK-GCS-PEDCO-120-ST-DW-0015 | BK-GCS-PEDCO-120-ST-DW-0015 | BK | GCS | PEDCO | 120 | ST | DW | 0015 | F4Q-709153 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 13 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0016 | Structural Drawing For Close Drain Sump Pit (SU-2201 A) |  | BK-GCS-PEDCO-120-ST-DW-0016 | BK-GCS-PEDCO-120-ST-DW-0016 | BK | GCS | PEDCO | 120 | ST | DW | 0016 | F4M-709154 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 14 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0017 | Foundation Drawing For Fuel Gas K.O Drum (V-2205) |  | BK-GCS-PEDCO-120-ST-DW-0017 | BK-GCS-PEDCO-120-ST-DW-0017 | BK | GCS | PEDCO | 120 | ST | DW | 0017 | F4Q-709155 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 15 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0018 | Foundation Drawing For Slug Catcher Drum (V-2104) |  | BK-GCS-PEDCO-120-ST-DW-0018 | BK-GCS-PEDCO-120-ST-DW-0018 | BK | GCS | PEDCO | 120 | ST | DW | 0018 | F4Q-709156 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 16 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0019 | Foundation Drawing For Degassing Drum (V-2106) |  | BK-GCS-PEDCO-120-ST-DW-0019 | BK-GCS-PEDCO-120-ST-DW-0019 | BK | GCS | PEDCO | 120 | ST | DW | 0019 | F4Q-709157 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 17 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0020 | Foundation Drawing For Nitrogen Receiver Drum (V-2204) |  | BK-GCS-PEDCO-120-ST-DW-0020 | BK-GCS-PEDCO-120-ST-DW-0020 | BK | GCS | PEDCO | 120 | ST | DW | 0020 | F4Q-709158 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 18 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0021 | Structural Drawing For Oily Water Sump Pit (SU-2201 B) |  | BK-GCS-PEDCO-120-ST-DW-0021 | BK-GCS-PEDCO-120-ST-DW-0021 | BK | GCS | PEDCO | 120 | ST | DW | 0021 | F4M-709159 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 19 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0023 | Foundation Drawing For Lean Glycol Storage Tank (TK-2102) |  | BK-GCS-PEDCO-120-ST-DW-0023 | BK-GCS-PEDCO-120-ST-DW-0023 | BK | GCS | PEDCO | 120 | ST | DW | 0023 | F4Q-709160 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 20 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0024 | Foundation Drawing For Fire Water Storage Tanks (TK-2301A/B) |  | BK-GCS-PEDCO-120-ST-DW-0024 | BK-GCS-PEDCO-120-ST-DW-0024 | BK | GCS | PEDCO | 120 | ST | DW | 0024 | F4Q-709161 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 21 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0025 | Foundation Drawing For Slug Storage Tank (TK-2101) |  | BK-GCS-PEDCO-120-ST-DW-0025 | BK-GCS-PEDCO-120-ST-DW-0025 | BK | GCS | PEDCO | 120 | ST | DW | 0025 | F4Q-709162 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 22 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0026 | Foundation Drawing For Dehydration Package (PK-2101) |  | BK-GCS-PEDCO-120-ST-DW-0026 | BK-GCS-PEDCO-120-ST-DW-0026 | BK | GCS | PEDCO | 120 | ST | DW | 0026 | F4Q-709163 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 23 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0027 | Foundation Drawing For Diesel Generator (PK-2206) |  | BK-GCS-PEDCO-120-ST-DW-0027 | BK-GCS-PEDCO-120-ST-DW-0027 | BK | GCS | PEDCO | 120 | ST | DW | 0027 | F4Q-709164 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 24 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0028 | Foundation Drawing For Instrument & Plant Air Package (PK-C-2203A/B) |  | BK-GCS-PEDCO-120-ST-DW-0028 | BK-GCS-PEDCO-120-ST-DW-0028 | BK | GCS | PEDCO | 120 | ST | DW | 0028 | F4Q-709165 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 25 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0029 | Foundation Drawing For Corrosion Inhibitor Injection Package (PK-2207) |  | BK-GCS-PEDCO-120-ST-DW-0029 | BK-GCS-PEDCO-120-ST-DW-0029 | BK | GCS | PEDCO | 120 | ST | DW | 0029 | F4Q-709166 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 26 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0030 | Foundation Drawing For Methanol Injection Package (PK-2208) |  | BK-GCS-PEDCO-120-ST-DW-0030 | BK-GCS-PEDCO-120-ST-DW-0030 | BK | GCS | PEDCO | 120 | ST | DW | 0030 | F4Q-709167 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 27 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0031 | Foundation Drawing For LP Flare Package (PK-2201) |  | BK-GCS-PEDCO-120-ST-DW-0031 | BK-GCS-PEDCO-120-ST-DW-0031 | BK | GCS | PEDCO | 120 | ST | DW | 0031 | F4Q-709168 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 28 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0032 | Foundation Drawing For Nitrogen Package (PK-2204A/B) |  | BK-GCS-PEDCO-120-ST-DW-0032 | BK-GCS-PEDCO-120-ST-DW-0032 | BK | GCS | PEDCO | 120 | ST | DW | 0032 | F4Q-709169 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 29 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0033 | Dike Wall Drawing For Lean Glycol Storage Tank (TK-2102) |  | BK-GCS-PEDCO-120-ST-DW-0033 | BK-GCS-PEDCO-120-ST-DW-0033 | BK | GCS | PEDCO | 120 | ST | DW | 0033 | F4M-709170 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 30 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0034 | Dike Wall Drawing For Slug Storage Tank (TK-2101) |  | BK-GCS-PEDCO-120-ST-DW-0034 | BK-GCS-PEDCO-120-ST-DW-0034 | BK | GCS | PEDCO | 120 | ST | DW | 0034 | F4M-709171 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 31 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0035 | Foundation Drawing For Glycol Sump Pit (SU-2101) |  | BK-GCS-PEDCO-120-ST-DW-0035 | BK-GCS-PEDCO-120-ST-DW-0035 | BK | GCS | PEDCO | 120 | ST | DW | 0035 | F4Q-709172 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 32 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0036 | Foundation Drawing For Glycol Transfer Pumps (P-2103 A/B) |  | BK-GCS-PEDCO-120-ST-DW-0036 | BK-GCS-PEDCO-120-ST-DW-0036 | BK | GCS | PEDCO | 120 | ST | DW | 0036 | F4Q-709173 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 33 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0037 | Foundation Drawing For Glycol Manual Pump (P-2102) |  | BK-GCS-PEDCO-120-ST-DW-0037 | BK-GCS-PEDCO-120-ST-DW-0037 | BK | GCS | PEDCO | 120 | ST | DW | 0037 | F4Q-709174 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 34 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0038 | Foundation Drawing For Fire Water Jockey Pumps (P-2302A/B) |  | BK-GCS-PEDCO-120-ST-DW-0038 | BK-GCS-PEDCO-120-ST-DW-0038 | BK | GCS | PEDCO | 120 | ST | DW | 0038 | F4Q-709175 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 35 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0039 | Foundation Drawing For Fire Water Electrical Pump (P-2301 A) |  | BK-GCS-PEDCO-120-ST-DW-0039 | BK-GCS-PEDCO-120-ST-DW-0039 | BK | GCS | PEDCO | 120 | ST | DW | 0039 | F4Q-709176 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 36 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0040 | Foundation Drawing For Fire Water Diesel Pumps (P-2302 B/C) |  | BK-GCS-PEDCO-120-ST-DW-0040 | BK-GCS-PEDCO-120-ST-DW-0040 | BK | GCS | PEDCO | 120 | ST | DW | 0040 | F4Q-709177 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 37 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0041 | Foundation Drawing For Potable Water Pump (P-2209) |  | BK-GCS-PEDCO-120-ST-DW-0041 | BK-GCS-PEDCO-120-ST-DW-0041 | BK | GCS | PEDCO | 120 | ST | DW | 0041 | F4Q-709178 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 38 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0042 | Foundation Drawing For Fuel Oil Pump (P-2206) |  | BK-GCS-PEDCO-120-ST-DW-0042 | BK-GCS-PEDCO-120-ST-DW-0042 | BK | GCS | PEDCO | 120 | ST | DW | 0042 | F4Q-709179 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 39 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0043 | Foundation Drawing For Slug Pumps (P-2101A/B) |  | BK-GCS-PEDCO-120-ST-DW-0043 | BK-GCS-PEDCO-120-ST-DW-0043 | BK | GCS | PEDCO | 120 | ST | DW | 0043 | F4Q-709180 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 40 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0044 | Foundation Drawing For Compressor Area Main Sleepers |  | BK-GCS-PEDCO-120-ST-DW-0044 | BK-GCS-PEDCO-120-ST-DW-0044 | BK | GCS | PEDCO | 120 | ST | DW | 0044 | F4Q-709181 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 41 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0045 | Foundation Drawing For Compressor Area Secondary Sleepers |  | BK-GCS-PEDCO-120-ST-DW-0045 | BK-GCS-PEDCO-120-ST-DW-0045 | BK | GCS | PEDCO | 120 | ST | DW | 0045 | F4Q-709182 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 42 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0046 | Foundation Drawing For Utility Area Sleepers |  | BK-GCS-PEDCO-120-ST-DW-0046 | BK-GCS-PEDCO-120-ST-DW-0046 | BK | GCS | PEDCO | 120 | ST | DW | 0046 | F4Q-709183 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 43 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0047 | Foundation Drawing For Flare Area Sleepers |  | BK-GCS-PEDCO-120-ST-DW-0047 | BK-GCS-PEDCO-120-ST-DW-0047 | BK | GCS | PEDCO | 120 | ST | DW | 0047 | F4Q-709184 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 44 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0048 | Foundation Drawing For Transformer & Shelters |  | BK-GCS-PEDCO-120-ST-DW-0048 | BK-GCS-PEDCO-120-ST-DW-0048 | BK | GCS | PEDCO | 120 | ST | DW | 0048 | F4Q-709185 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 45 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0049 | Foundation Drawing For Pipe Supports |  | BK-GCS-PEDCO-120-ST-DW-0049 | BK-GCS-PEDCO-120-ST-DW-0049 | BK | GCS | PEDCO | 120 | ST | DW | 0049 | F4Q-709186 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 46 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0050 | Structural Drawing For Special Pipe Supports |  | BK-GCS-PEDCO-120-ST-DW-0050 | BK-GCS-PEDCO-120-ST-DW-0050 | BK | GCS | PEDCO | 120 | ST | DW | 0050 | F4M-709187 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 47 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0051 | Culvert Detail Drawing |  | BK-GCS-PEDCO-120-ST-DW-0051 | BK-GCS-PEDCO-120-ST-DW-0051 | BK | GCS | PEDCO | 120 | ST | DW | 0051 | F4M-709188 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 48 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0052 | Foundation Drawing For Access Platforms |  | BK-GCS-PEDCO-120-ST-DW-0052 | BK-GCS-PEDCO-120-ST-DW-0052 | BK | GCS | PEDCO | 120 | ST | DW | 0052 | F4Q-709189 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 49 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0053 | Structural Drawing For Access Platforms |  | BK-GCS-PEDCO-120-ST-DW-0053 | BK-GCS-PEDCO-120-ST-DW-0053 | BK | GCS | PEDCO | 120 | ST | DW | 0053 | F4M-709190 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 50 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0054 | Foundation Drawing For Pipe rack |  | BK-GCS-PEDCO-120-ST-DW-0054 | BK-GCS-PEDCO-120-ST-DW-0054 | BK | GCS | PEDCO | 120 | ST | DW | 0054 | F4Q-709191 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 51 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0055 | Structural Drawing For Pipe rack |  | BK-GCS-PEDCO-120-ST-DW-0055 | BK-GCS-PEDCO-120-ST-DW-0055 | BK | GCS | PEDCO | 120 | ST | DW | 0055 | F4M-709192 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 52 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0056 | Foundation Drawing For Lighting Poles and Towers |  | BK-GCS-PEDCO-120-ST-DW-0056 | BK-GCS-PEDCO-120-ST-DW-0056 | BK | GCS | PEDCO | 120 | ST | DW | 0056 | F4Q-709193 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 53 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0057 | Foundation Drawing For Chemical Injection and Storage Shelter |  | BK-GCS-PEDCO-120-ST-DW-0057 | BK-GCS-PEDCO-120-ST-DW-0057 | BK | GCS | PEDCO | 120 | ST | DW | 0057 | F4Q-709194 | AFC | IFC | 2022-09-11 | 2022-09-06 | 2022-09-12 | -5 | 6 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFC | T-1323 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-05633 | 44816 | 1401/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213890 | 44810 | 1401/06/15 | 44816 | 1401/06/21 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1323 | 2022-08-28 | 1401/06/06 |  |  |  | BK-SUR-ENG-STR-01-05633 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-213890 | 2022-09-06 | 1401/06/15 | 44816 | 1401/06/21 | RJ
3 | 2 | 3 | 11 | 2 | 0 | 54 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0058 | Structural Drawing For Chemical Injection and Storage Shelter |  | BK-GCS-PEDCO-120-ST-DW-0058 | BK-GCS-PEDCO-120-ST-DW-0058 | BK | GCS | PEDCO | 120 | ST | DW | 0058 | F4M-709195 | AFC | IFC | 2022-09-11 | 2022-09-06 | 2022-09-12 | -5 | 6 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFC | T-1323 | 44801 | 1401/06/06 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-05633 | 44816 | 1401/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-213890 | 44810 | 1401/06/15 | 44816 | 1401/06/21 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1323 | 2022-08-28 | 1401/06/06 |  |  |  | BK-SUR-ENG-STR-01-05633 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-213890 | 2022-09-06 | 1401/06/15 | 44816 | 1401/06/21 | RJ
3 | 2 | 3 | 11 | 2 | 0 | 55 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0059 | Foundation Drawing For Gas Compressor Shelter |  | BK-GCS-PEDCO-120-ST-DW-0059 | BK-GCS-PEDCO-120-ST-DW-0059 | BK | GCS | PEDCO | 120 | ST | DW | 0059 | F4Q-709196 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 56 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0060 | Structural Drawing For Gas Compressor Shelter |  | BK-GCS-PEDCO-120-ST-DW-0060 | BK-GCS-PEDCO-120-ST-DW-0060 | BK | GCS | PEDCO | 120 | ST | DW | 0060 | F4M-709197 | AFC | IFC | 2022-08-06 | 2022-08-28 | 2022-08-31 | 22 | 3 | 25 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFC | T-1177 | 44765 | 1401/05/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-198818 | 44801 | 1401/06/06 | 44804 | 1401/06/09 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1177 | 2022-07-23 | 1401/05/01 | [13 empty] | 1401-2294-198818 | 2022-08-28 | 1401/06/06 | 44804 | 1401/06/09 | RJ
3 | 2 | 3 | 11 | 2 | 0 | 57 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0061 | Foundation Drawing For Control Building |  | BK-GCS-PEDCO-120-ST-DW-0061 | BK-GCS-PEDCO-120-ST-DW-0061 | BK | GCS | PEDCO | 120 | ST | DW | 0061 | F4Q-709198 | AFC | IFC | 2022-10-29 | 2022-10-25 | 2022-10-26 | -4 | 1 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1498 | 44849 | 1401/07/23 | T-1498 | 44849 | 1401/07/23 | BK-SUR-ENG-STR-01-05992 | 44860 | 1401/08/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279776 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1498 | 2022-10-15 | 1401/07/23 | T-1498 | 44849 | 1401/07/23 | BK-SUR-ENG-STR-01-05992 | 44860 | 1401/08/04 | CM | [6 empty] | 1401-2294-279776 | 2022-10-25 | 1401/08/03 | 44860 | 1401/08/04 | RJ
3 | 2 | 3 | 11 | 2 | 0 | 58 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0062 | Structural Drawing For Control Building |  | BK-GCS-PEDCO-120-ST-DW-0062 | BK-GCS-PEDCO-120-ST-DW-0062 | BK | GCS | PEDCO | 120 | ST | DW | 0062 | F4M-709199 | AFC | IFC | 2022-10-29 | 2022-10-25 | 2022-10-26 | -4 | 1 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFC | T-1498 | 44849 | 1401/07/23 | T-1498 | 44849 | 1401/07/23 | BK-SUR-ENG-STR-01-05992 | 44860 | 1401/08/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-279776 | 44859 | 1401/08/03 | 44860 | 1401/08/04 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1498 | 2022-10-15 | 1401/07/23 | T-1498 | 44849 | 1401/07/23 | BK-SUR-ENG-STR-01-05992 | 44860 | 1401/08/04 | CM | [6 empty] | 1401-2294-279776 | 2022-10-25 | 1401/08/03 | 44860 | 1401/08/04 | RJ
3 | 2 | 3 | 11 | 2 | 0 | 59 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0063 | Foundation Drawing For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-ST-DW-0063 | BK-GCS-PEDCO-120-ST-DW-0063 | BK | GCS | PEDCO | 120 | ST | DW | 0063 | F4Q-709200 | AFC | IFC | 2022-09-19 | 2022-09-14 | 2022-09-19 | -5 | 5 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0 |  |  | D00 | IFC | T-1359 | 44809 | 1401/06/14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-224914 | 44818 | 1401/06/23 | 44823 | 1401/06/28 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1359 | 2022-09-05 | 1401/06/14 | [13 empty] | 1401-2294-224914 | 2022-09-14 | 1401/06/23 | 44823 | 1401/06/28 | RJ
3 | 2 | 3 | 11 | 2 | 0 | 60 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0064 | Structural Drawing For Extension of Existing Elect. Building |  | BK-GCS-PEDCO-120-ST-DW-0064 | BK-GCS-PEDCO-120-ST-DW-0064 | BK | GCS | PEDCO | 120 | ST | DW | 0064 | F4M-709201 | AFC | IFC | 2022-09-19 | 2022-09-14 | 2022-09-19 | -5 | 5 | 0 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFC | T-1359 | 44809 | 1401/06/14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-224914 | 44818 | 1401/06/23 | 44823 | 1401/06/28 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1359 | 2022-09-05 | 1401/06/14 | [13 empty] | 1401-2294-224914 | 2022-09-14 | 1401/06/23 | 44823 | 1401/06/28 | RJ
3 | 2 | 3 | 11 | 2 | 0 | 61 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0065 | Foundation Drawing For Fire Water Pump Shelter |  | BK-GCS-PEDCO-120-ST-DW-0065 | BK-GCS-PEDCO-120-ST-DW-0065 | BK | GCS | PEDCO | 120 | ST | DW | 0065 | F4Q-709202 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 62 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0066 | Structural Drawing For Fire Water Pump Shelter |  | BK-GCS-PEDCO-120-ST-DW-0066 | BK-GCS-PEDCO-120-ST-DW-0066 | BK | GCS | PEDCO | 120 | ST | DW | 0066 | F4M-709203 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 63 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0067 | Foundation Drawing For Utility Shelter |  | BK-GCS-PEDCO-120-ST-DW-0067 | BK-GCS-PEDCO-120-ST-DW-0067 | BK | GCS | PEDCO | 120 | ST | DW | 0067 | F4Q-709204 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 64 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0068 | Structural Drawing For Utility Shelter |  | BK-GCS-PEDCO-120-ST-DW-0068 | BK-GCS-PEDCO-120-ST-DW-0068 | BK | GCS | PEDCO | 120 | ST | DW | 0068 | F4M-709205 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 65 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0069 | Foundation Drawing For Air Dryer Packages (PK-D-2203A/B) |  | BK-GCS-PEDCO-120-ST-DW-0069 | BK-GCS-PEDCO-120-ST-DW-0069 | BK | GCS | PEDCO | 120 | ST | DW | 0069 | F4Q-709206 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 66 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0070 | Foundation Drawing For Pig Launcher (PL-3101) |  | BK-GCS-PEDCO-120-ST-DW-0070 | BK-GCS-PEDCO-120-ST-DW-0070 | BK | GCS | PEDCO | 120 | ST | DW | 0070 | F4Q-709207 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 2 | 0 | 67 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0071 | Foundation Drawing For Ignition Package |  | BK-GCS-PEDCO-120-ST-DW-0071 | BK-GCS-PEDCO-120-ST-DW-0071 | BK | GCS | PEDCO | 120 | ST | DW | 0071 | F4Q-709208 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 3 | 11 | 2 | 0 | 68 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0072 | Foundation Drawing For Fire Shed |  | BK-GCS-PEDCO-120-ST-DW-0072 | BK-GCS-PEDCO-120-ST-DW-0072 | BK | GCS | PEDCO | 120 | ST | DW | 0072 | F4Q-709209 | AFC | IFC | 2022-02-13 | 2022-02-03 | 2022-02-13 | -10 | 10 | 0 | IFA | 2022-03-21 | 2022-03-12 | 2022-03-14 | -9 | 2 | -7 | IFA | 2022-04-27 | 2022-04-17 | 2022-04-19 | -10 | 2 | -8 | IFA | 2022-06-07 | 2022-06-01 | 2022-06-07 | -6 | 6 | 0 | IFA | 2022-06-25 | 2022-06-14 | 2022-06-15 | -11 | 1 | -10 | AFC | 2022-07-05 | 2022-07-14 | 2022-07-17 | 9 | 3 | 12 | [8 empty] | 2022-03-07 | 2022-06-21 |  | D05 | AFC | T-1102 | 44733 | 1401/03/31 | T-1102 | 44733 | 1401/03/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-139997 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0522 | 2022-01-30 | 1400/11/10 |  |  |  | BK-SUR-ENG-STR-00-02949 | 44598 | 1400/11/17 | RJ-C4 | [6 empty] | 1400-2294-395081 | 2022-02-03 | 1400/11/14 | 44605 | 1400/11/13 | RJ | [10 empty] | D01 | IFA | T-0689 | 44627 | 1400/12/16 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D00 | [5 empty] | 1400-2294-445295 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D00 | [9 empty] | D02 | IFA | T-0812 | 44664 | 1401/01/24 |  |  |  | BK-SUR-ENG-STR-01-03988 | 44671 | 1401/01/31 | CM-C3 | [6 empty] | 1401-2294-27199 | 44668 | 1401/01/28 | 44670 | 1401/01/30 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D01 | [9 empty] | D03 | IFA | T-1000 | 44705 | 1401/03/03 | T-1000 | 44709 | 1401/03/07 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D02 | [5 empty] | 1401-2294-85911 | 44713 | 1401/03/11 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D02 | [9 empty] | D04 | IFA | T-1055 | 44723 | 1401/03/21 | T-1055 | 44723 | 1401/03/21 | [10 empty] | 1401-2294-102023 | 44726 | 1401/03/24 | 44727 | 1401/03/25 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D03 | [9 empty] | D05 | AFC | T-1102 | 44733 | 1401/03/31 | T-1102 | 44733 | 1401/03/31 | [10 empty] | 1401-2294-139997 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | AP
3 | 2 | 3 | 11 | 2 | 0 | 69 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0073 | Structural Drawing For Fire Shed |  | BK-GCS-PEDCO-120-ST-DW-0073 | BK-GCS-PEDCO-120-ST-DW-0073 | BK | GCS | PEDCO | 120 | ST | DW | 0073 | F4M-709210 | AFC | IFC | 2022-02-13 | 2022-02-03 | 2022-02-13 | -10 | 10 | 0 | IFA | 2022-03-21 | 2022-03-12 | 2022-03-14 | -9 | 2 | -7 | IFA | 2022-04-27 | 2022-04-17 | 2022-04-19 | -10 | 2 | -8 | IFA | 2022-06-07 | 2022-06-01 | 2022-06-07 | -6 | 6 | 0 | IFA | 2022-06-25 | 2022-06-14 | 2022-06-15 | -11 | 1 | -10 | AFC | 2022-07-05 | 2022-07-14 | 2022-07-17 | 9 | 3 | 12 | [8 empty] | 2022-03-07 | 2022-06-21 |  | D05 | AFC | T-1102 | 44733 | 1401/03/31 | T-1102 | 44733 | 1401/03/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-139997 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0522 | 2022-01-30 | 1400/11/10 |  |  |  | BK-SUR-ENG-STR-00-02949 | 44598 | 1400/11/17 | RJ-C4 | [6 empty] | 1400-2294-395081 | 2022-02-03 | 1400/11/14 | 44605 | 1400/11/13 | RJ | [10 empty] | D01 | IFA | T-0689 | 44627 | 1400/12/16 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D00 | [5 empty] | 1400-2294-445295 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D00 | [9 empty] | D02 | IFA | T-0812 | 44664 | 1401/01/24 |  |  |  | BK-SUR-ENG-STR-01-03988 | 44671 | 1401/01/31 | CM-C3 | [6 empty] | 1401-2294-27199 | 44668 | 1401/01/28 | 44670 | 1401/01/30 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D01 | [9 empty] | D03 | IFA | T-1000 | 44705 | 1401/03/03 | T-1000 | 44709 | 1401/03/07 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D02 | [5 empty] | 1401-2294-85911 | 44713 | 1401/03/11 | 44719 | 1401/03/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D02 | [9 empty] | D04 | IFA | T-1055 | 44723 | 1401/03/21 | T-1055 | 44723 | 1401/03/21 | [10 empty] | 1401-2294-102023 | 44726 | 1401/03/24 | 44727 | 1401/03/25 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D03 | [9 empty] | D05 | AFC | T-1102 | 44733 | 1401/03/31 | T-1102 | 44733 | 1401/03/31 | [10 empty] | 1401-2294-139997 | 44756 | 1401/04/23 | 44759 | 1401/04/26 | AP
3 | 2 | 3 | 11 | 2 | 0 | 70 | 3.2.3.11.2 | BK-GCS-PEDCO-120-ST-DW-0074 | Structural Drawing For Shelter of Transformers |  | BK-GCS-PEDCO-120-ST-DW-0074 | BK-GCS-PEDCO-120-ST-DW-0074 | BK | GCS | PEDCO | 120 | ST | DW | 0074 | F4M-709211 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[7 empty] | 3.2.3.11.3 | BK-GCS-PEDCO-120-ST-DW-0075 | Foundation Drawing For CCTV Control Room- Binak GCS |  | BK-GCS-PEDCO-120-ST-DW-0075 | BK-GCS-PEDCO-120-ST-DW-0075 | BK | GCS | PEDCO | 120 | ST | DW | 0075 | F4Q-709402 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
[7 empty] | 3.2.3.11.4 | BK-GCS-PEDCO-120-ST-DW-0076 | Structural Drawing For CCTV Control Room- Binak GCS |  | BK-GCS-PEDCO-120-ST-DW-0076 | BK-GCS-PEDCO-120-ST-DW-0076 | BK | GCS | PEDCO | 120 | ST | DW | 0076 | F4M-709403 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[7 empty] | 3.2.3.11.5 | BK-GCS-PEDCO-120-ST-DW-0077 | Foundation Drawing For CCTV Control Room- Binak DU |  | BK-GCS-PEDCO-120-ST-DW-0077 | BK-GCS-PEDCO-120-ST-DW-0077 | BK | GCS | PEDCO | 120 | ST | DW | 0077 | F4Q-709404 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
[7 empty] | 3.2.3.11.6 | BK-GCS-PEDCO-120-ST-DW-0078 | Structural Drawing For CCTV Control Room- Binak DU |  | BK-GCS-PEDCO-120-ST-DW-0078 | BK-GCS-PEDCO-120-ST-DW-0078 | BK | GCS | PEDCO | 120 | ST | DW | 0078 | F4M-709405 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
[7 empty] | 3.2.3.11.7 | BK-GCS-PEDCO-120-ST-DW-0079 | Foundation Drawing For CCTV Rack Room- Binak PU |  | BK-GCS-PEDCO-120-ST-DW-0079 | BK-GCS-PEDCO-120-ST-DW-0079 | BK | GCS | PEDCO | 120 | ST | DW | 0079 | F4Q-709406 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
[7 empty] | 3.2.3.11.8 | BK-GCS-PEDCO-120-ST-DW-0080 | Structural Drawing For CCTV Rack Room- Binak PU |  | BK-GCS-PEDCO-120-ST-DW-0080 | BK-GCS-PEDCO-120-ST-DW-0080 | BK | GCS | PEDCO | 120 | ST | DW | 0080 | F4M-709407 | AFC | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 3 | 0 | 0 | 3.2.3.11.3 |  | MTO | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 11 | 3 | 0 | 1 | 3.2.3.11 | BK-GCS-PEDCO-120-ST-MT-0001 | MTO For Steel Structures Works |  | BK-GCS-PEDCO-120-ST-MT-0001 | BK-GCS-PEDCO-120-ST-MT-0001 | BK | GCS | PEDCO | 120 | ST | MT | 0001 | F8Z-709212 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 11 | 3 | 0 | 2 | 3.2.3.11 | BK-GCS-PEDCO-120-ST-MT-0002 | MTO For Structural Concrete Works |  | BK-GCS-PEDCO-120-ST-MT-0002 | BK-GCS-PEDCO-120-ST-MT-0002 | BK | GCS | PEDCO | 120 | ST | MT | 0002 | F8Z-709213 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 3 | 12 | 0 | 0 | 0 | 3.2.3.12 |  | Survey (Topography) & Geotechnic/Geoelectric | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 3 | 12 | 1 | 0 | 0 | 3.2.3.12.1 |  | Survey (Topography)
3 | 2 | 3 | 12 | 1 | 0 | 1 | 3.2.3.12.1 | BK-GCS-PEDCO-120-SU-MP-0001 | Topographical Map |  | BK-GCS-PEDCO-120-SU-MP-0001 | BK-GCS-PEDCO-120-SU-MP-0001 | BK | GCS | PEDCO | 120 | SU | MP | 0001 | F0A-709214 | IFI | IFI | 2022-05-14 | 2022-05-08 | 2022-05-11 | -6 | 3 | -3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-04-30 |  |  | D00 | IFI | T-0881 | 44681 | 1401/02/10 | T-0881 | 44681 | 1401/02/10 | BK-SUR-ENG-CIV-01-04279 | 44696 | 1401/02/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52724 | 44689 | 1401/02/18 | 44692 | 1401/02/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0881 | 2022-04-30 | 1401/02/10 | T-0881 | 44681 | 1401/02/10 | BK-SUR-ENG-CIV-01-04279 | 44696 | 1401/02/25 | CM-C2 | [6 empty] | 1401-2294-52724 | 2022-05-08 | 1401/02/18 | 44692 | 1401/02/21 | AP
3 | 2 | 3 | 12 | 2 | 0 | 0 | 3.2.3.12.2 |  | Geotechnic
3 | 2 | 3 | 12 | 2 | 1 | 0 | 3.2.12.2.1 |  | Procedure/Plan
3 | 2 | 3 | 12 | 2 | 1 | 1 | 3.2.3.12.2.1.1 | BK-GCS-PEDCO-120-GT-PR-0001 | Geotechnical Investigation Plan for Compressor Station |  | BK-GCS-PEDCO-120-GT-PR-0001 | BK-GCS-PEDCO-120-GT-PR-0001 | BK | GCS | PEDCO | 120 | GT | PR | 0001 | F0Z-709215 | AFC | IFC | 2022-01-02 | 2021-12-27 | 2021-12-29 | -6 | 2 | -4 | IFA | 2022-01-23 | 2022-01-12 | 2022-01-15 | -11 | 3 | -8 | AFC | 2022-02-01 | 2022-03-12 | 2022-03-14 | 39 | 2 | 41 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-19 | 2022-01-18 |  | D02 | AFC | T-0479 | 44579 | 1400/10/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445100 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0361 | 2021-12-19 | 1400/09/28 |  |  |  | BK-SUR-ENG-CIV-00-02384 | 44550 | 1400/09/29 | CM-C2 | [6 empty] | 1400-2294-338029 | 2021-12-27 | 1400/10/06 | 44559 | 1400/10/08 | CM | [10 empty] | D01 | IFA | T-0442 | 44570 | 1400/10/19 |  |  |  | BK-SUR-ENG-GEN-00-02686 | 44576 | 1400/10/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D00 | [5 empty] | 1400-2294-362348 | 44573 | 1400/10/22 | 44576 | 1400/10/25 | AP | NISOC-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D00 | [9 empty] | D02 | AFC | T-0479 | 44579 | 1400/10/28 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D01 | [5 empty] | 1400-2294-445100 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D01
3 | 2 | 3 | 12 | 2 | 2 | 0 | 3.2.12.2.2 |  | Report
3 | 2 | 3 | 12 | 2 | 2 | 1 | 3.2.3.12.2.2.1 | BK-GCS-PEDCO-120-GT-RT-0001 | Geotechnical Investigation Report for Compressor Station |  | BK-GCS-PEDCO-120-GT-RT-0001 | BK-GCS-PEDCO-120-GT-RT-0001 | BK | GCS | PEDCO | 120 | GT | RT | 0001 | F0Z-709216 | IFI | IFC | 2022-05-31 | 2022-05-31 | 2022-06-06 | 0 | 6 | 6 | IFA | 2022-11-07 | 2022-11-17 | 2022-11-19 | 10 | 2 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-17 |  |  | D01 | IFA | T-1539 | 44858 | 1401/08/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-120-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-315918 | 44882 | 1401/08/26 | 44884 | 1401/08/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-120-GT-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0963 | 2022-05-17 | 1401/02/27 | T-0963 | 44699 | 1401/02/28 | BK-SUR-ENG-CIV-01-04492 | 44712 | 1401/03/10 | CM-C3 | [6 empty] | 1401-2294-85269 | 2022-05-31 | 1401/03/10 | 44718 | 1401/03/16 | CM | [10 empty] | D01 | IFA | T-1539 | 44858 | 1401/08/02 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-120-GT-RT-0001_D00 | [5 empty] | 1401-2294-315918 | 44882 | 1401/08/26 | 44884 | 1401/08/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-120-GT-RT-0001_D00
3 | 2 | 4 | 0 | 0 | 0 | 0 | 3.2.4 |  | Procurement Engineering
3 | 2 | 4 | 1 | 0 | 0 | 0 | 3.2.4.1 |  | Mechanical
3 | 2 | 4 | 1 | 1 | 0 | 0 | 3.2.4.1.1 |  | Gas Compressors
3 | 2 | 4 | 1 | 1 | 1 | 0 | 3.2.1.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 1 | 1 | 1 | 1 | 3.2.4.1.1.1.1 | BK-GCS-PEDCO-120-ME-MR-0001 | PMR For Gas Compressors |  | BK-GCS-PEDCO-120-ME-MR-0001 | BK-GCS-PEDCO-120-ME-MR-0001 | BK | GCS | PEDCO | 120 | ME | MR | 0001 | F0Z-709217 | IFI | IFC | 2021-12-12 | 2021-12-13 | 2021-12-15 | 1 | 2 | 3 | IFI | 2022-01-18 | 2021-01-15 | 2022-01-30 | -368 | 380 | 12 | IFI | 2022-02-27 | 2022-03-01 | 2022-03-05 | 2 | 4 | 6 | IFI | 2022-06-20 | 2022-07-28 | 2022-08-06 | 38 | 9 | 47 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2021-11-28 |  |  | D03 | IFI | T-1031 | 44718 | 1401/03/16 | T-1031 | 44719 | 1401/03/17 | BK-SUR-ENG-MEC-01-04910 | 44740 | 1401/04/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156970 | 44770 | 1401/05/06 | 44779 | 1401/05/15 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0277 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-MEC-00-02300 | 44545 | 1400/09/24 | AP | [6 empty] | 1400-2294-315112 | 2021-12-13 | 1400/09/21 | 44545 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0429 | 44565 | 1400/10/14 |  |  |  | BK-SUR-ENG-MEC-00-02803 | 44586 | 1400/11/05 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D00 | [5 empty] | 1400-2294-365715 | 44211 | 1400/10/26 | 44591 | 1400/11/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D00 | [9 empty] | D02 | IFI | T-0582 | 44605 | 1400/11/24 |  |  |  | BK-SUR-ENG-MEC-00-03353 | 44625 | 1400/12/14 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D01 | [5 empty] | 1400-2294-430723 | 44621 | 1400/12/10 | 44625 | 1400/12/14 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D01 | [9 empty] | D03 | IFI | T-1031 | 44718 | 1401/03/16 | T-1031 | 44719 | 1401/03/17 | BK-SUR-ENG-MEC-01-04910 | 44740 | 1401/04/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D02 | [5 empty] | 1401-2294-156970 | 44770 | 1401/05/06 | 44779 | 1401/05/15 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D02
3 | 2 | 4 | 1 | 1 | 2 | 0 | 3.2.1.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 1 | 1 | 2 | 1 | 3.2.4.1.1.2.1 | BK-GCS-PEDCO-120-ME-TB-0001 | TBE For Gas Compressors |  | BK-GCS-PEDCO-120-ME-TB-0001 | BK-GCS-PEDCO-120-ME-TB-0001 | BK | GCS | PEDCO | 120 | ME | TB | 0001 | F0Z-709218 | IFI | IFI | 2022-02-16 | 2022-02-23 | 2022-02-27 | 7 | 4 | 11 | IFI | 2022-03-19 | 2022-05-01 | 2022-05-07 | 43 | 6 | 49 | IFI | 2022-06-25 | 2022-06-22 | 2022-06-27 | -3 | 5 | 2 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-02-02 |  |  | D02 | IFI | T-1065 | 44723 | 1401/03/21 | T-1065 | 44723 | 1401/03/21 | BK-SUR-ENG-MEC-01-05547 | 44801 | 1401/06/06 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-111977 | 44734 | 1401/04/01 | 44739 | 1401/04/06 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0540 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-ROE-00-03258 | 44619 | 1400/12/08 | CM-C3 | [6 empty] | 1400-2294-421986 | 2022-02-23 | 1400/12/04 | 44619 | 1400/12/08 | CM | [10 empty] | D01 | IFI | T-0676 | 44625 | 1400/12/14 |  |  |  | BK-SUR-ENG-MEC-00-03608 | 44635 | 1400/12/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D00 | [5 empty] | 1401-2294-47400 | 44682 | 1401/02/11 | 44683 | 1401/02/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D00 | 1401-2294-47400 | 44682 | 1401/02/11 | 44688 | 1401/02/17 | CM |  |  |  | D02 | IFI | T-1065 | 44723 | 1401/03/21 | T-1065 | 44723 | 1401/03/21 | BK-SUR-ENG-MEC-01-05547 | 44801 | 1401/06/06 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D01 | [5 empty] | 1401-2294-111977 | 44734 | 1401/04/01 | 44739 | 1401/04/06 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D01
3 | 2 | 4 | 1 | 2 | 0 | 0 | 3.2.4.1.2 |  | Gas Dehydration Package
3 | 2 | 4 | 1 | 2 | 1 | 0 | 3.2.1.2.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 2 | 1 | 1 | 3.2.4.1.2.1.1 | BK-GCS-PEDCO-120-ME-MR-0002 | PMR For Gas Dehydration Package |  | BK-GCS-PEDCO-120-ME-MR-0002 | BK-GCS-PEDCO-120-ME-MR-0002 | BK | GCS | PEDCO | 120 | ME | MR | 0002 | F0Z-709219 | IFI | IFI | 2022-01-02 | 2021-12-27 | 2022-01-05 | -6 | 9 | 3 | IFI | 2022-02-09 | 2022-03-12 | 2022-03-14 | 31 | 2 | 33 | IFI | 2022-10-03 | 2022-10-05 | 2022-10-11 | 2 | 6 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-19 |  |  | D02 | IFI | T-1414 | 44823 | 1401/06/28 | T-1414 | 44823 | 1401/06/28 | BK-SUR-ENG-MEC-01-05750 | 44828 | 1401/07/02 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249364 | 44839 | 1401/07/19 | 44845 | 1401/07/13 | AP | NISOC-CRS-BK-PPL-PEDCO-120-ME-MR-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0362 | 2021-12-19 | 1400/09/28 | [13 empty] | 1400-2294-336397 | 2021-12-27 | 1400/10/06 | 44566 | 1400/10/15 | CM | [10 empty] | D01 | IFI | T-0512 | 44587 | 1400/11/06 |  |  |  | BK-SUR-ENG-MEC-01-05749 | 44828 | 1401/07/02 | CM-C3 | [6 empty] | 1400-2294-445084 | 44632 | 1400/12/21 | 44634 | 1400/12/23 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0002_D00 | [9 empty] | D02 | IFI | T-1414 | 44823 | 1401/06/28 | T-1414 | 44823 | 1401/06/28 | BK-SUR-ENG-MEC-01-05750 | 44828 | 1401/07/02 | CM-C2 | [6 empty] | 1401-2294-249364 | 44839 | 1401/07/19 | 44845 | 1401/07/13 | AP | NISOC-CRS-BK-PPL-PEDCO-120-ME-MR-0002_D01
3 | 2 | 4 | 1 | 2 | 2 | 0 | 3.2.1.2.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 2 | 2 | 1 | 3.2.4.1.2.2.1 | BK-GCS-PEDCO-120-ME-TB-0002 | TBE For Gas Dehydration Package |  | BK-GCS-PEDCO-120-ME-TB-0002 | BK-GCS-PEDCO-120-ME-TB-0002 | BK | GCS | PEDCO | 120 | ME | TB | 0002 | F0Z-709220 | IFI | IFI | 2022-04-11 | 2022-04-28 | 2022-05-01 | 17 | 3 | 20 | IFI | 2022-06-20 | 2022-07-28 | 2022-08-06 | 38 | 9 | 47 | IFI | 2022-08-28 | 2022-09-01 | 2022-09-04 | 4 | 3 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-03-28 |  |  | D02 | IFI | T-1272 | 44787 | 1401/05/23 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05546 | 44801 | 1401/06/06 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205791 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-TB-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0759 | 2022-03-28 | 1401/01/08 |  |  |  | BK-SUR-ENG-MEC-01-04047 | 44676 | 1401/02/05 | CM-C3 | [6 empty] | 1401-2294-43107 | 2022-04-28 | 1401/02/08 | 44682 | 1401/02/11 | CM | [10 empty] | D01 | IFI | T-1031 | 44718 | 1401/03/16 | T-1031 | 44718 | 1401/03/16 | BK-SUR-ENG-MEC-01-04910 | 44740 | 1401/04/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0002_D00 | [5 empty] | 1401-2294-156970 | 44770 | 1401/05/06 | 44779 | 1401/05/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-TB-0002_D00 | [9 empty] | D02 | IFI | T-1272 | 44787 | 1401/05/23 |  |  |  | BK-SUR-ENG-MEC-01-05546 | 44801 | 1401/06/06 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0002_D01 | [5 empty] | 1401-2294-205791 | 44805 | 1401/06/10 | 44808 | 1401/06/13 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-TB-0002_D01
3 | 2 | 4 | 1 | 3 | 0 | 0 | 3.2.4.1.3 |  | Pressure Vessels
3 | 2 | 4 | 1 | 3 | 1 | 0 | 3.2.1.3.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 3 | 1 | 1 | 3.2.4.1.3.1.1 | BK-GCS-PEDCO-120-ME-MR-0003 | PMR For Pressure Vessels |  | BK-GCS-PEDCO-120-ME-MR-0003 | BK-GCS-PEDCO-120-ME-MR-0003 | BK | GCS | PEDCO | 120 | ME | MR | 0003 | F0Z-709221 | IFI | IFI | 2022-03-08 | 2022-03-07 | 2022-03-09 | -1 | 2 | 1 | IFI | 2022-10-02 | 2022-10-05 | 2022-10-11 | 3 | 6 | 9 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-18 |  |  | D01 | IFI | T-1408 | 44822 | 1401/06/27 | T-1408 | 44822 | 1401/06/27 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-249425 | 44839 | 1401/07/13 | 44845 | 1401/07/19 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0623 | 2022-02-22 | 1400/12/03 |  |  |  | BK-SUR-ENG-MEC-00-03301 | 44622 | 1400/12/11 | CM-C3 | [6 empty] | 1400-2294-438942 | 2022-03-07 | 1400/12/16 | 44629 | 1400/12/18 | RJ | [10 empty] | D01 | IFI | T-1408 | 44822 | 1401/06/27 | T-1408 | 44822 | 1401/06/27 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0003_D00 | [5 empty] | 1401-2294-249425 | 44839 | 1401/07/13 | 44845 | 1401/07/19 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0003_D00
3 | 2 | 4 | 1 | 3 | 2 | 0 | 3.2.1.3.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 3 | 2 | 1 | 3.2.4.1.3.2.1 | BK-GCS-PEDCO-120-ME-TB-0003 | TBE For Pressure Vessels |  | BK-GCS-PEDCO-120-ME-TB-0003 | BK-GCS-PEDCO-120-ME-TB-0003 | BK | GCS | PEDCO | 120 | ME | TB | 0003 | F0Z-709222 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 1 | 4 | 0 | 0 | 3.2.4.1.4 |  | Gas Air Coolers
3 | 2 | 4 | 1 | 4 | 1 | 0 | 3.2.1.4.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 4 | 1 | 1 | 3.2.4.1.4.1.1 | BK-GCS-PEDCO-120-ME-MR-0004 | PMR For Gas Air Coolers |  | BK-GCS-PEDCO-120-ME-MR-0004 | BK-GCS-PEDCO-120-ME-MR-0004 | BK | GCS | PEDCO | 120 | ME | MR | 0004 | F0Z-709223 | IFI | IFI | 2022-03-05 | 2022-03-07 | 2022-03-09 | 2 | 2 | 4 | IFI | 2022-08-17 | 2022-09-08 | 2022-09-12 | 22 | 4 | 26 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-03 |  |  | D01 | IFI | T-1246 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05825 | 44837 | 1401/07/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216173 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0603 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-MEC-00-03257 | 44619 | 1400/12/08 | CM-C2 | [6 empty] | 1400-2294-438865 | 2022-03-07 | 1400/12/16 | 44629 | 1400/12/18 | RJ | [10 empty] | D01 | IFI | T-1246 | 44776 | 1401/05/12 |  |  |  | BK-SUR-ENG-MEC-01-05825 | 44837 | 1401/07/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0004_D00 | [5 empty] | 1401-2294-216173 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0004_D00
3 | 2 | 4 | 1 | 4 | 2 | 0 | 3.2.1.4.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 4 | 2 | 1 | 3.2.4.1.4.2.1 | BK-GCS-PEDCO-120-ME-TB-0004 | TBE For Gas Air Coolers |  | BK-GCS-PEDCO-120-ME-TB-0004 | BK-GCS-PEDCO-120-ME-TB-0004 | BK | GCS | PEDCO | 120 | ME | TB | 0004 | F0Z-709224 | IFI | IFI | 2022-09-12 | 2022-10-12 | 2022-10-16 | 30 | 4 | 34 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-29 |  |  | D00 | IFI | T-1341 | 44802 | 1401/06/07 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05862 | 44842 | 1401/07/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-260325 | 44846 | 1401/07/20 | 44850 | 1401/07/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1341 | 2022-08-29 | 1401/06/07 |  |  |  | BK-SUR-ENG-MEC-01-05862 | 44842 | 1401/07/16 | CM-C3 | [6 empty] | 1401-2294-260325 | 2022-10-12 | 1401/07/20 | 44850 | 1401/07/24 | CM
3 | 2 | 4 | 1 | 5 | 0 | 0 | 3.2.4.1.5 |  | Storage Tanks
3 | 2 | 4 | 1 | 5 | 1 | 0 | 3.2.1.5.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 5 | 1 | 1 | 3.2.4.1.5.1.1 | BK-GCS-PEDCO-120-ME-MR-0005 | PMR For Storage Tanks |  | BK-GCS-PEDCO-120-ME-MR-0005 | BK-GCS-PEDCO-120-ME-MR-0005 | BK | GCS | PEDCO | 120 | ME | MR | 0005 | F0Z-709225 | IFI | IFI | 2022-02-21 | 2022-03-01 | 2022-03-05 | 8 | 4 | 12 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0 |  |  | D00 | IFI | T-0562 | 44599 | 1400/11/18 | 0 | 0 | 0 | BK-SUR-ENG-000-00-03256 | 44619 | 1400/12/08 | CM-C3 | 0 | BK-SUR-ENG-MEC-00-03351 | 44625 | 1400/12/15 | CM-C3 | 0 | 1400-2294-430776 | 44621 | 1400/12/14 | 44625 | 1400/12/14 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0562 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-000-00-03256 | 44619 | 1400/12/08 | CM-C3 |  | BK-SUR-ENG-MEC-00-03351 | 44625 | 1400/12/15 | CM-C3 |  | 1400-2294-430776 | 2022-03-01 | 1400/12/14 | 44625 | 1400/12/14 | RJ
3 | 2 | 4 | 1 | 5 | 2 | 0 | 3.2.1.5.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 5 | 2 | 1 | 3.2.4.1.5.2.1 | BK-GCS-PEDCO-120-ME-TB-0005 | TBE For Storage Tanks |  | BK-GCS-PEDCO-120-ME-TB-0005 | BK-GCS-PEDCO-120-ME-TB-0005 | BK | GCS | PEDCO | 120 | ME | TB | 0005 | F0Z-709226 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 1 | 6 | 0 | 0 | 3.2.4.1.6 |  | Instrument/Plant Air & Nitrogen Packages
3 | 2 | 4 | 1 | 6 | 1 | 0 | 3.2.1.6.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 6 | 1 | 1 | 3.2.4.1.6.1.1 | BK-GCS-PEDCO-120-ME-MR-0006 | PMR For Instrument/Plant Air & Nitrogen Packages |  | BK-GCS-PEDCO-120-ME-MR-0006 | BK-GCS-PEDCO-120-ME-MR-0006 | BK | GCS | PEDCO | 120 | ME | MR | 0006 | F0Z-709227 | IFI | IFI | 2022-08-23 | 2022-09-13 | 2022-09-14 | 21 | 1 | 22 | IFI | 2022-11-19 | 0 | 0 | -44884 | 0 | -44884 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-09 |  |  | D01 | IFI | T-1573 | 44870 | 1401/08/14 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-06096 | 44871 | 1401/08/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1258 | 2022-08-09 | 1401/05/18 |  |  |  | BK-SUR-ENG-MEC-01-05916 | 44852 | 1401/07/26 | CM-C3 | [6 empty] | 1401-2294-222891 | 2022-09-13 | 1401/06/22 | 44818 | 1401/06/23 | CM | [10 empty] | D01 | IFI | T-1573 | 44870 | 1401/08/14 |  |  |  | BK-SUR-ENG-MEC-01-06096 | 44871 | 1401/08/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0006_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0006_D00
3 | 2 | 4 | 1 | 6 | 2 | 0 | 3.2.1.6.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 6 | 2 | 1 | 3.2.4.1.6.2.1 | BK-GCS-PEDCO-120-ME-TB-0006 | TBE For Instrument/Plant Air & Nitrogen Packages |  | BK-GCS-PEDCO-120-ME-TB-0006 | BK-GCS-PEDCO-120-ME-TB-0006 | BK | GCS | PEDCO | 120 | ME | TB | 0006 | F0Z-709228 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 1 | 7 | 0 | 0 | 3.2.4.1.7 |  | Chemical Injection Packages
3 | 2 | 4 | 1 | 7 | 1 | 0 | 3.2.1.7.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 7 | 1 | 1 | 3.2.4.1.7.1.1 | BK-GCS-PEDCO-120-ME-MR-0008 | PMR For Chemical Injection Packages |  | BK-GCS-PEDCO-120-ME-MR-0008 | BK-GCS-PEDCO-120-ME-MR-0008 | BK | GCS | PEDCO | 120 | ME | MR | 0008 | F0Z-709229 | IFI | IFI | 2022-08-23 | 2022-09-13 | 2022-09-14 | 21 | 1 | 22 | IFI | 2022-11-19 | 0 | 0 | -44884 | 0 | -44884 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-09 |  |  | D01 | IFI | T-1575 | 44870 | 1401/08/14 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-06099 | 44871 | 1401/08/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1258 | 2022-08-09 | 1401/05/18 |  |  |  | BK-SUR-ENG-MEC-01-05916 | 44852 | 1401/07/26 | CM-C3 | [6 empty] | 1401-2294-222891 | 2022-09-13 | 1401/06/22 | 44818 | 1401/06/23 | CM | [10 empty] | D01 | IFI | T-1575 | 44870 | 1401/08/14 |  |  |  | BK-SUR-ENG-MEC-01-06099 | 44871 | 1401/08/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0008_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0008_D00
3 | 2 | 4 | 1 | 7 | 2 | 0 | 3.2.1.7.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 7 | 2 | 1 | 3.2.4.1.7.2.1 | BK-GCS-PEDCO-120-ME-TB-0008 | TBE For Chemical Injection Packages |  | BK-GCS-PEDCO-120-ME-TB-0008 | BK-GCS-PEDCO-120-ME-TB-0008 | BK | GCS | PEDCO | 120 | ME | TB | 0008 | F0Z-709230 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 1 | 8 | 0 | 0 | 3.2.4.1.8 |  | Pumps - Process Services
3 | 2 | 4 | 1 | 8 | 1 | 0 | 3.2.1.8.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 8 | 1 | 1 | 3.2.4.1.8.1.1 | BK-GCS-PEDCO-120-ME-MR-0009 | PMR For Centrifugal Pumps For Process Services |  | BK-GCS-PEDCO-120-ME-MR-0009 | BK-GCS-PEDCO-120-ME-MR-0009 | BK | GCS | PEDCO | 120 | ME | MR | 0009 | F0Z-709231 | IFI | IFI | 2022-02-27 | 2022-03-01 | 2022-03-24 | 2 | 23 | 25 | IFI | 2022-09-25 | 2022-09-20 | 2022-10-08 | -5 | 18 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-11 |  |  | D01 | IFI | T-1385 | 44815 | 1401/06/20 | T-1385 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05836 | 44838 | 1401/07/12 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0009_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-231560 | 44824 | 1401/06/29 | 44842 | 1401/07/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0588 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-MEC-00-03354 | 44625 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-430725 | 2022-03-01 | 1400/12/10 | 44644 | 1400/12/05 | RJ | [10 empty] | D01 | IFI | T-1385 | 44815 | 1401/06/20 | T-1385 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05836 | 44838 | 1401/07/12 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0009_D00 | [5 empty] | 1401-2294-231560 | 44824 | 1401/06/29 | 44842 | 1401/07/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0009_D00
3 | 2 | 4 | 1 | 8 | 2 | 0 | 3.2.1.8.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 8 | 2 | 1 | 3.2.4.1.8.2.1 | BK-GCS-PEDCO-120-ME-TB-0009 | TBE For Centrifugal Pumps For Process Services |  | BK-GCS-PEDCO-120-ME-TB-0009 | BK-GCS-PEDCO-120-ME-TB-0009 | BK | GCS | PEDCO | 120 | ME | TB | 0009 | F0Z-709232 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 1 | 9 | 0 | 0 | 3.2.4.1.9 |  | Pumps - General Services
3 | 2 | 4 | 1 | 9 | 1 | 0 | 3.2.1.9.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 9 | 1 | 1 | 3.2.4.1.9.1.1 | BK-GCS-PEDCO-120-ME-MR-0010 | PMR For Centrifugal Pumps For General Services |  | BK-GCS-PEDCO-120-ME-MR-0010 | BK-GCS-PEDCO-120-ME-MR-0010 | BK | GCS | PEDCO | 120 | ME | MR | 0010 | F0Z-709233 | IFI | IFI | 2022-03-02 | 2022-03-09 | 2022-03-09 | 7 | 0 | 7 | IFI | 2022-09-25 | 2022-09-20 | 2022-10-08 | -5 | 18 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-11 |  |  | D01 | IFI | T-1385 | 44815 | 1401/06/20 | T-1385 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05836 | 44838 | 1401/07/12 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-231560 | 44824 | 1401/06/29 | 44842 | 1401/07/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0599 | 2022-02-16 | 1400/11/27 | [13 empty] | 1400-2294-432765 | 2022-03-09 | 1400/12/12 | 44629 | 1400/12/18 | RJ | [10 empty] | D01 | IFI | T-1385 | 44815 | 1401/06/20 | T-1385 | 44815 | 1401/06/20 | BK-SUR-ENG-MEC-01-05836 | 44838 | 1401/07/12 | CM-C3 | [6 empty] | 1401-2294-231560 | 44824 | 1401/06/29 | 44842 | 1401/07/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0010_D00
3 | 2 | 4 | 1 | 9 | 2 | 0 | 3.2.1.9.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 9 | 2 | 1 | 3.2.4.1.9.2.1 | BK-GCS-PEDCO-120-ME-TB-0010 | TBE For Centrifugal Pumps For General Services |  | BK-GCS-PEDCO-120-ME-TB-0010 | BK-GCS-PEDCO-120-ME-TB-0010 | BK | GCS | PEDCO | 120 | ME | TB | 0010 | F0Z-709234 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 1 | 10 | 0 | 0 | 3.2.4.1.10 |  | Fire Water Pumps
3 | 2 | 4 | 1 | 10 | 1 | 0 | 3.2.1.10.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 10 | 1 | 1 | 3.2.4.1.10.1.1 | BK-GCS-PEDCO-120-ME-MR-0011 | PMR For Fire Water Pump |  | BK-GCS-PEDCO-120-ME-MR-0011 | BK-GCS-PEDCO-120-ME-MR-0011 | BK | GCS | PEDCO | 120 | ME | MR | 0011 | F0Z-709235 | IFI | IFI | 2022-03-05 | 2022-03-07 | 2022-03-09 | 2 | 2 | 4 | IFI | 2022-08-14 | 2022-09-06 | 2022-09-12 | 23 | 6 | 29 | IFI | 2022-11-06 | 2022-11-05 | 2022-11-07 | -1 | 2 | 1 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-07-31 |  |  | D02 | IFI | T-1536 | 44857 | 1401/08/01 | T-1536 | 44857 | 1401/08/01 | BK-SUR-ENG-MEC-01-06044 | 44865 | 1401/08/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-296598 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0603 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-MEC-00-03257 | 44619 | 1400/12/08 | CM-C2 | [6 empty] | 1400-2294-438865 | 2022-03-07 | 1400/12/16 | 44629 | 1400/12/18 | RJ | [10 empty] | D01 | IFI | T-1227 | 44773 | 1401/05/09 |  |  |  | BK-SUR-ENG-MEC-01-05341 | 44776 | 1401/05/12 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0011_D00 | [5 empty] | 1401-2294-213921 | 44810 | 1401/06/15 | 44816 | 1401/06/21 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0011_D00 | [9 empty] | D02 | IFI | T-1536 | 44857 | 1401/08/01 | T-1536 | 44857 | 1401/08/01 | BK-SUR-ENG-MEC-01-06044 | 44865 | 1401/08/09 | CM-C3 | [6 empty] | 1401-2294-296598 | 44870 | 1401/08/14 | 44872 | 1401/08/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0011_D01
3 | 2 | 4 | 1 | 10 | 2 | 0 | 3.2.1.10.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 10 | 2 | 1 | 3.2.4.1.10.2.1 | BK-GCS-PEDCO-120-ME-TB-0011 | TBE For Fire Water Pump |  | BK-GCS-PEDCO-120-ME-TB-0011 | BK-GCS-PEDCO-120-ME-TB-0011 | BK | GCS | PEDCO | 120 | ME | TB | 0011 | F0Z-709236 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 1 | 11 | 0 | 0 | 3.2.4.1.11 |  | Flare Packages
3 | 2 | 4 | 1 | 11 | 1 | 0 | 3.2.1.11.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 11 | 1 | 1 | 3.2.4.1.11.1.1 | BK-GCS-PEDCO-120-ME-MR-0012 | PMR For Flare Packages |  | BK-GCS-PEDCO-120-ME-MR-0012 | BK-GCS-PEDCO-120-ME-MR-0012 | BK | GCS | PEDCO | 120 | ME | MR | 0012 | F0Z-709237 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 1 | 11 | 2 | 0 | 3.2.1.11.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 11 | 2 | 1 | 3.2.4.1.11.2.1 | BK-GCS-PEDCO-120-ME-TB-0012 | TBE For Flare Packages |  | BK-GCS-PEDCO-120-ME-TB-0012 | BK-GCS-PEDCO-120-ME-TB-0012 | BK | GCS | PEDCO | 120 | ME | TB | 0012 | F0Z-709238 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 1 | 12 | 0 | 0 | 3.2.4.1.12 |  | Overhead Travelling Cranes
3 | 2 | 4 | 1 | 12 | 1 | 0 | 3.2.1.12.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 12 | 1 | 1 | 3.2.4.1.12.1.1 | BK-GCS-PEDCO-120-ME-MR-0013 | PMR For Overhead Travelling Cranes |  | BK-GCS-PEDCO-120-ME-MR-0013 | BK-GCS-PEDCO-120-ME-MR-0013 | BK | GCS | PEDCO | 120 | ME | MR | 0013 | F0Z-709239 | IFI | IFI | 2022-09-21 | 2022-09-20 | 2022-10-08 | -1 | 18 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-07 |  |  | D00 | IFI | T-1376 | 44811 | 1401/06/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-05751 | 44828 | 1401/07/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-231584 | 44824 | 1401/06/29 | 44842 | 1401/07/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1376 | 2022-09-07 | 1401/06/16 |  |  |  | BK-SUR-ENG-MEC-01-05751 | 44828 | 1401/07/02 | CM-C3 | [6 empty] | 1401-2294-231584 | 2022-09-20 | 1401/06/29 | 44842 | 1401/07/16 | CM
3 | 2 | 4 | 1 | 12 | 2 | 0 | 3.2.1.12.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 12 | 2 | 1 | 3.2.4.1.12.2.1 | BK-GCS-PEDCO-120-ME-TB-0013 | TBE For Overhead Travelling Cranes |  | BK-GCS-PEDCO-120-ME-TB-0013 | BK-GCS-PEDCO-120-ME-TB-0013 | BK | GCS | PEDCO | 120 | ME | TB | 0013 | F0Z-709240 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 2 | 0 | 0 | 0 | 3.2.4.2 |  | HVAC
3 | 2 | 4 | 2 | 1 | 0 | 0 | 3.2.4.2.1 |  | Main HVAC Equipment
3 | 2 | 4 | 2 | 1 | 1 | 0 | 3.2.2.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 2 | 1 | 1 | 1 | 3.2.4.2.1.1.1 | BK-GCS-PEDCO-120-HV-MR-0001 | PMR For Main HVAC Equipment |  | BK-GCS-PEDCO-120-HV-MR-0001 | BK-GCS-PEDCO-120-HV-MR-0001 | BK | GCS | PEDCO | 120 | HV | MR | 0001 | F0Z-709241 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 2 | 1 | 2 | 0 | 3.2.2.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 2 | 1 | 2 | 1 | 3.2.4.2.1.2.1 | BK-GCS-PEDCO-120-HV-TB-0001 | TBE For Main HVAC Equipment |  | BK-GCS-PEDCO-120-HV-TB-0001 | BK-GCS-PEDCO-120-HV-TB-0001 | BK | GCS | PEDCO | 120 | HV | TB | 0001 | F0Z-709242 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 0 | 0 | 0 | 3.2.4.3 |  | Piping
3 | 2 | 4 | 3 | 1 | 0 | 0 | 3.2.4.3.1 |  | Pipes
3 | 2 | 4 | 3 | 1 | 1 | 0 | 3.2.3.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 1 | 1 | 1 | 3.2.4.3.1.1.1 | BK-GCS-PEDCO-120-PI-MR-0001 | PMR For Pipes |  | BK-GCS-PEDCO-120-PI-MR-0001 | BK-GCS-PEDCO-120-PI-MR-0001 | BK | GCS | PEDCO | 120 | PI | MR | 0001 | F0Z-709243 | IFI | IFI | 2022-12-05 | 0 | 0 | -44900 | 0 | -44900 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-11-21 |  |  | D00 | IFI | T-1594 | 44886 | 1401/08/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1594 | 2022-11-21 | 1401/08/30
3 | 2 | 4 | 3 | 1 | 2 | 0 | 3.2.3.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 1 | 2 | 1 | 3.2.4.3.1.2.1 | BK-GCS-PEDCO-120-PI-TB-0001 | TBE For Pipes |  | BK-GCS-PEDCO-120-PI-TB-0001 | BK-GCS-PEDCO-120-PI-TB-0001 | BK | GCS | PEDCO | 120 | PI | TB | 0001 | F0Z-709244 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 2 | 0 | 0 | 3.2.4.3.2 |  | Fittings
3 | 2 | 4 | 3 | 2 | 1 | 0 | 3.2.3.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 2 | 1 | 1 | 3.2.4.3.2.1.1 | BK-GCS-PEDCO-120-PI-MR-0002 | PMR For Fittings |  | BK-GCS-PEDCO-120-PI-MR-0002 | BK-GCS-PEDCO-120-PI-MR-0002 | BK | GCS | PEDCO | 120 | PI | MR | 0002 | F0Z-709245 | IFI | IFI | 2022-12-05 | 0 | 0 | -44900 | 0 | -44900 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-11-21 |  |  | D00 | IFI | T-1594 | 44886 | 1401/08/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1594 | 2022-11-21 | 1401/08/30
3 | 2 | 4 | 3 | 2 | 2 | 0 | 3.2.3.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 2 | 2 | 1 | 3.2.4.3.2.2.1 | BK-GCS-PEDCO-120-PI-TB-0002 | TBE For Fitting |  | BK-GCS-PEDCO-120-PI-TB-0002 | BK-GCS-PEDCO-120-PI-TB-0002 | BK | GCS | PEDCO | 120 | PI | TB | 0002 | F0Z-709246 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 3 | 0 | 0 | 3.2.4.3.3 |  | Flanges
3 | 2 | 4 | 3 | 3 | 1 | 0 | 3.2.3.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 3 | 1 | 1 | 3.2.4.3.3.1.1 | BK-GCS-PEDCO-120-PI-MR-0003 | PMR For Flanges |  | BK-GCS-PEDCO-120-PI-MR-0003 | BK-GCS-PEDCO-120-PI-MR-0003 | BK | GCS | PEDCO | 120 | PI | MR | 0003 | F0Z-709247 | IFI | IFI | 2022-12-05 | 0 | 0 | -44900 | 0 | -44900 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-11-21 |  |  | D00 | IFI | T-1594 | 44886 | 1401/08/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1594 | 2022-11-21 | 1401/08/30
3 | 2 | 4 | 3 | 3 | 2 | 0 | 3.2.3.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 3 | 2 | 1 | 3.2.4.3.3.2.1 | BK-GCS-PEDCO-120-PI-TB-0003 | TBE For Flanges |  | BK-GCS-PEDCO-120-PI-TB-0003 | BK-GCS-PEDCO-120-PI-TB-0003 | BK | GCS | PEDCO | 120 | PI | TB | 0003 | F0Z-709248 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 4 | 0 | 0 | 3.2.4.3.4 |  | Manual Valves
3 | 2 | 4 | 3 | 4 | 1 | 0 | 3.2.3.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 4 | 1 | 1 | 3.2.4.3.4.1.1 | BK-GCS-PEDCO-120-PI-MR-0004 | PMR For Manual Valves |  | BK-GCS-PEDCO-120-PI-MR-0004 | BK-GCS-PEDCO-120-PI-MR-0004 | BK | GCS | PEDCO | 120 | PI | MR | 0004 | F0Z-709249 | IFI | IFI | 2022-12-05 | 0 | 0 | -44900 | 0 | -44900 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-11-21 |  |  | D00 | IFI | T-1594 | 44886 | 1401/08/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1594 | 2022-11-21 | 1401/08/30
3 | 2 | 4 | 3 | 4 | 2 | 0 | 3.2.3.4.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 4 | 2 | 1 | 3.2.4.3.4.2.1 | BK-GCS-PEDCO-120-PI-TB-0004 | TBE For Manual Valves |  | BK-GCS-PEDCO-120-PI-TB-0004 | BK-GCS-PEDCO-120-PI-TB-0004 | BK | GCS | PEDCO | 120 | PI | TB | 0004 | F0Z-709250 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 5 | 0 | 0 | 3.2.4.3.5 |  | Gaskets
3 | 2 | 4 | 3 | 5 | 1 | 0 | 3.2.3.5.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 5 | 1 | 1 | 3.2.4.3.5.1.1 | BK-GCS-PEDCO-120-PI-MR-0005 | PMR For Gaskets |  | BK-GCS-PEDCO-120-PI-MR-0005 | BK-GCS-PEDCO-120-PI-MR-0005 | BK | GCS | PEDCO | 120 | PI | MR | 0005 | F0Z-709251 | IFI | IFI | 2022-12-05 | 0 | 0 | -44900 | 0 | -44900 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-11-21 |  |  | D00 | IFI | T-1594 | 44886 | 1401/08/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1594 | 2022-11-21 | 1401/08/30
3 | 2 | 4 | 3 | 5 | 2 | 0 | 3.2.3.5.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 5 | 2 | 1 | 3.2.4.3.5.2.1 | BK-GCS-PEDCO-120-PI-TB-0005 | TBE For Gaskets |  | BK-GCS-PEDCO-120-PI-TB-0005 | BK-GCS-PEDCO-120-PI-TB-0005 | BK | GCS | PEDCO | 120 | PI | TB | 0005 | F0Z-709252 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 6 | 0 | 0 | 3.2.4.3.6 |  | Bolt & Nuts
3 | 2 | 4 | 3 | 6 | 1 | 0 | 3.2.3.6.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 6 | 1 | 1 | 3.2.4.3.6.1.1 | BK-GCS-PEDCO-120-PI-MR-0006 | PMR For Bolt/Nuts |  | BK-GCS-PEDCO-120-PI-MR-0006 | BK-GCS-PEDCO-120-PI-MR-0006 | BK | GCS | PEDCO | 120 | PI | MR | 0006 | F0Z-709253 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 6 | 2 | 0 | 3.2.3.6.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 6 | 2 | 1 | 3.2.4.3.6.2.1 | BK-GCS-PEDCO-120-PI-TB-0006 | TBE For Bolt/Nuts | PMR For Bolt/Nuts | BK-GCS-PEDCO-120-PI-TB-0006 | BK-GCS-PEDCO-120-PI-TB-0006 | BK | GCS | PEDCO | 120 | PI | TB | 0006 | F0Z-709254 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 7 | 0 | 0 | 3.2.4.3.7 |  | Insulation Joints
3 | 2 | 4 | 3 | 7 | 1 | 0 | 3.2.3.7.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 7 | 1 | 1 | 3.2.4.3.7.1.1 | BK-GCS-PEDCO-120-PI-MR-0007 | PMR For Insulation Joints |  | BK-GCS-PEDCO-120-PI-MR-0007 | BK-GCS-PEDCO-120-PI-MR-0007 | BK | GCS | PEDCO | 120 | PI | MR | 0007 | F0Z-709255 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 7 | 2 | 0 | 3.2.3.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 7 | 2 | 1 | 3.2.4.3.7.2.1 | BK-GCS-PEDCO-120-PI-TB-0007 | TBE For Insulation Joints |  | BK-GCS-PEDCO-120-PI-TB-0007 | BK-GCS-PEDCO-120-PI-TB-0007 | BK | GCS | PEDCO | 120 | PI | TB | 0007 | F0Z-709256 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 8 | 0 | 0 | 3.2.4.3.8 |  | Strainers
3 | 2 | 4 | 3 | 8 | 1 | 0 | 3.2.3.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 8 | 1 | 1 | 3.2.4.3.8.1.1 | BK-GCS-PEDCO-120-PI-MR-0008 | PMR For Strainers |  | BK-GCS-PEDCO-120-PI-MR-0008 | BK-GCS-PEDCO-120-PI-MR-0008 | BK | GCS | PEDCO | 120 | PI | MR | 0008 | F0Z-709257 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 8 | 2 | 0 | 3.2.3.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 8 | 2 | 1 | 3.2.4.3.8.2.1 | BK-GCS-PEDCO-120-PI-TB-0008 | TBE For Strainers |  | BK-GCS-PEDCO-120-PI-TB-0008 | BK-GCS-PEDCO-120-PI-TB-0008 | BK | GCS | PEDCO | 120 | PI | TB | 0008 | F0Z-709258 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 9 | 0 | 0 | 3.2.4.3.9 |  | Special Pipe Supports
3 | 2 | 4 | 3 | 9 | 1 | 0 | 3.2.3.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 9 | 1 | 1 | 3.2.4.3.9.1.1 | BK-GCS-PEDCO-120-PI-MR-0009 | PMR For Special Pipe Supports |  | BK-GCS-PEDCO-120-PI-MR-0009 | BK-GCS-PEDCO-120-PI-MR-0009 | BK | GCS | PEDCO | 120 | PI | MR | 0009 | F0Z-709259 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 9 | 2 | 0 | 3.2.3.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 9 | 2 | 1 | 3.2.4.3.9.2.1 | BK-GCS-PEDCO-120-PI-TB-0009 | TBE For Special Pipe Supports |  | BK-GCS-PEDCO-120-PI-TB-0009 | BK-GCS-PEDCO-120-PI-TB-0009 | BK | GCS | PEDCO | 120 | PI | TB | 0009 | F0Z-709260 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 10 | 0 | 0 | 3.2.4.3.10 |  | Insulation
3 | 2 | 4 | 3 | 10 | 1 | 0 | 3.2.3.10.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 10 | 1 | 1 | 3.2.4.3.10.1.1 | BK-GCS-PEDCO-120-PI-MR-0010 | PMR For Insulation |  | BK-GCS-PEDCO-120-PI-MR-0010 | BK-GCS-PEDCO-120-PI-MR-0010 | BK | GCS | PEDCO | 120 | PI | MR | 0010 | F0Z-709261 | IFI | IFI | 2022-08-24 | 2022-09-12 | 2022-09-13 | 19 | 1 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-10 |  |  | D00 | IFI | T-1269 | 44783 | 1401/05/19 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-05474 | 44728 | 1401/05/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-221101 | 44816 | 1401/06/21 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1269 | 2022-08-10 | 1401/05/19 |  |  |  | BK-SUR-ENG-PIP-01-05474 | 44728 | 1401/05/25 | CM-C2 | [6 empty] | 1401-2294-221101 | 2022-09-12 | 1401/06/21 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 3 | 10 | 2 | 0 | 3.2.3.10.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 10 | 2 | 1 | 3.2.4.3.10.2.1 | BK-GCS-PEDCO-120-PI-TB-0010 | TBE For Insulation |  | BK-GCS-PEDCO-120-PI-TB-0010 | BK-GCS-PEDCO-120-PI-TB-0010 | BK | GCS | PEDCO | 120 | PI | TB | 0010 | F0Z-709262 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 11 | 0 | 0 | 3.2.4.3.11 |  | Painting
3 | 2 | 4 | 3 | 11 | 1 | 0 | 3.2.3.11.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 11 | 1 | 1 | 3.2.4.3.11.1.1 | BK-GCS-PEDCO-120-PI-MR-0011 | PMR For Painting |  | BK-GCS-PEDCO-120-PI-MR-0011 | BK-GCS-PEDCO-120-PI-MR-0011 | BK | GCS | PEDCO | 120 | PI | MR | 0011 | F0Z-709263 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 11 | 2 | 0 | 3.2.3.11.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 11 | 2 | 1 | 3.2.4.3.11.2.1 | BK-GCS-PEDCO-120-PI-TB-0011 | TBE For Painting |  | BK-GCS-PEDCO-120-PI-TB-0011 | BK-GCS-PEDCO-120-PI-TB-0011 | BK | GCS | PEDCO | 120 | PI | TB | 0011 | F0Z-709264 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 12 | 0 | 0 | 3.2.4.3.12 |  | Coating of Underground Piping
3 | 2 | 4 | 3 | 12 | 1 | 0 | 3.2.3.12.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 12 | 1 | 1 | 3.2.4.3.12.1.1 | BK-GCS-PEDCO-120-PI-MR-0012 | PMR For Coating of Underground Piping |  | BK-GCS-PEDCO-120-PI-MR-0012 | BK-GCS-PEDCO-120-PI-MR-0012 | BK | GCS | PEDCO | 120 | PI | MR | 0012 | F0Z-709265 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 3 | 12 | 2 | 0 | 3.2.3.12.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 3 | 12 | 2 | 1 | 3.2.4.3.12.2.1 | BK-GCS-PEDCO-120-PI-TB-0012 | TBE For Coating of Underground Piping |  | BK-GCS-PEDCO-120-PI-TB-0012 | BK-GCS-PEDCO-120-PI-TB-0012 | BK | GCS | PEDCO | 120 | PI | TB | 0012 | F0Z-709266 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 0 | 0 | 0 | 3.2.4.4 |  | Control & Instrumentation
3 | 2 | 4 | 4 | 1 | 0 | 0 | 3.2.4.4.1 |  | Control System/Console/Furniture | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 1 | 1 | 0 | 3.2.4.1.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 1 | 1 | 1 | 3.2.4.4.1.1.1 | BK-GCS-PEDCO-120-IN-MR-0001 | PMR For Control System/Console/Furniture |  | BK-GCS-PEDCO-120-IN-MR-0001 | BK-GCS-PEDCO-120-IN-MR-0001 | BK | GCS | PEDCO | 120 | IN | MR | 0001 | F0Z-709267 | IFI | IFI | 2022-09-05 | 2022-09-08 | 2022-09-13 | 3 | 5 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-22 |  |  | D00 | IFI | T-1299 | 44795 | 1401/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05602 | 44809 | 1401/06/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216179 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1299 | 2022-08-22 | 1401/05/31 |  |  |  | BK-SUR-ENG-INS-01-05602 | 44809 | 1401/06/04 | CM-C3 | [6 empty] | 1401-2294-216179 | 2022-09-08 | 1401/06/17 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 1 | 2 | 0 | 3.2.4.1.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 1 | 2 | 1 | 3.2.4.4.1.2.1 | BK-GCS-PEDCO-120-IN-TB-0001 | TBE For Control System/Console/Furniture |  | BK-GCS-PEDCO-120-IN-TB-0001 | BK-GCS-PEDCO-120-IN-TB-0001 | BK | GCS | PEDCO | 120 | IN | TB | 0001 | F0Z-709268 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 2 | 0 | 0 | 3.2.4.4.2 |  | ESD System | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 2 | 1 | 0 | 3.2.4.2.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 2 | 1 | 1 | 3.2.4.4.2.1.1 | BK-GCS-PEDCO-120-IN-MR-0002 | PMR For ESD System |  | BK-GCS-PEDCO-120-IN-MR-0002 | BK-GCS-PEDCO-120-IN-MR-0002 | BK | GCS | PEDCO | 120 | IN | MR | 0002 | F0Z-709269 | IFI | IFI | 2022-09-05 | 2022-09-08 | 2022-09-13 | 3 | 5 | 8 | IFI | 2022-10-17 | 2022-10-17 | 2022-10-22 | 0 | 5 | 5 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-22 |  |  | D01 | IFI | T-1453 | 44837 | 1401/07/11 | T-1453 | 44837 | 1401/07/11 | BK-SUR-ENG-INS-01-05927 | 44853 | 1401/07/27 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-267488 | 44851 | 1401/07/25 | 44856 | 1401/07/30 | CM-HOLD | NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1299 | 2022-08-22 | 1401/05/31 |  |  |  | BK-SUR-ENG-INS-01-05602 | 44809 | 1401/06/04 | CM-C3 | [6 empty] | 1401-2294-216179 | 2022-09-08 | 1401/06/17 | 44817 | 1401/06/22 | CM | [10 empty] | D01 | IFI | T-1453 | 44837 | 1401/07/11 | T-1453 | 44837 | 1401/07/11 | BK-SUR-ENG-INS-01-05927 | 44853 | 1401/07/27 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0002_D00 | [5 empty] | 1401-2294-267488 | 44851 | 1401/07/25 | 44856 | 1401/07/30 | CM-HOLD | NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0002_D00
3 | 2 | 4 | 4 | 2 | 2 | 0 | 3.2.4.2.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 2 | 2 | 1 | 3.2.4.4.2.2.1 | BK-GCS-PEDCO-120-IN-TB-0002 | TBE For ESD System |  | BK-GCS-PEDCO-120-IN-TB-0002 | BK-GCS-PEDCO-120-IN-TB-0002 | BK | GCS | PEDCO | 120 | IN | TB | 0002 | F0Z-709270 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 3 | 0 | 0 | 3.2.4.4.3 |  | F&G System | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 3 | 1 | 0 | 3.2.4.3.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 3 | 1 | 1 | 3.2.4.4.3.1.1 | BK-GCS-PEDCO-120-IN-MR-0003 | PMR For F&G System |  | BK-GCS-PEDCO-120-IN-MR-0003 | BK-GCS-PEDCO-120-IN-MR-0003 | BK | GCS | PEDCO | 120 | IN | MR | 0003 | F0Z-709271 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 3 | 2 | 0 | 3.2.4.3.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 3 | 2 | 1 | 3.2.4.4.3.2.1 | BK-GCS-PEDCO-120-IN-TB-0003 | TBE For F&G System |  | BK-GCS-PEDCO-120-IN-TB-0003 | BK-GCS-PEDCO-120-IN-TB-0003 | BK | GCS | PEDCO | 120 | IN | TB | 0003 | F0Z-709272 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 4 | 0 | 0 | 3.2.4.4.4 |  | ON/OFF & Shutdown Valves | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 4 | 1 | 0 | 3.2.4.4.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 4 | 1 | 1 | 3.2.4.4.4.1.1 | BK-GCS-PEDCO-120-IN-MR-0004 | PMR For On/off & Shutdown Valves |  | BK-GCS-PEDCO-120-IN-MR-0004 | BK-GCS-PEDCO-120-IN-MR-0004 | BK | GCS | PEDCO | 120 | IN | MR | 0004 | F0Z-709273 | IFI | IFI | 2022-09-06 | 2022-09-10 | 2022-09-13 | 4 | 3 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-23 |  |  | D00 | IFI | T-1306 | 44796 | 1401/06/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05631 | 44816 | 1401/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216521 | 44814 | 1401/06/19 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1306 | 2022-08-23 | 1401/06/01 |  |  |  | BK-SUR-ENG-INS-01-05631 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-216521 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 4 | 2 | 0 | 3.2.4.4.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 4 | 2 | 1 | 3.2.4.4.4.2.1 | BK-GCS-PEDCO-120-IN-TB-0004 | TBE For On/off & Shutdown Valves |  | BK-GCS-PEDCO-120-IN-TB-0004 | BK-GCS-PEDCO-120-IN-TB-0004 | BK | GCS | PEDCO | 120 | IN | TB | 0004 | F0Z-709274 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 5 | 0 | 0 | 3.2.4.4.5 |  | Control Valves | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 5 | 1 | 0 | 3.2.4.5.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 5 | 1 | 1 | 3.2.4.4.5.1.1 | BK-GCS-PEDCO-120-IN-MR-0005 | PMR For Control Valves |  | BK-GCS-PEDCO-120-IN-MR-0005 | BK-GCS-PEDCO-120-IN-MR-0005 | BK | GCS | PEDCO | 120 | IN | MR | 0005 | F0Z-709275 | IFI | IFI | 2022-09-05 | 2022-09-08 | 2022-09-13 | 3 | 5 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-22 |  |  | D00 | IFI | T-1299 | 44795 | 1401/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05602 | 44809 | 1401/06/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216179 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1299 | 2022-08-22 | 1401/05/31 |  |  |  | BK-SUR-ENG-INS-01-05602 | 44809 | 1401/06/04 | CM-C3 | [6 empty] | 1401-2294-216179 | 2022-09-08 | 1401/06/17 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 5 | 2 | 0 | 3.2.4.5.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 5 | 2 | 1 | 3.2.4.4.5.2.1 | BK-GCS-PEDCO-120-IN-TB-0005 | TBE For Control Valves |  | BK-GCS-PEDCO-120-IN-TB-0005 | BK-GCS-PEDCO-120-IN-TB-0005 | BK | GCS | PEDCO | 120 | IN | TB | 0005 | F0Z-709276 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 6 | 0 | 0 | 3.2.4.4.6 |  | Pressure Safety Valves (PSV) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 6 | 1 | 0 | 3.2.4.6.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 6 | 1 | 1 | 3.2.4.4.6.1.1 | BK-GCS-PEDCO-120-IN-MR-0006 | PMR For Pressure Safety Valves (PSV) |  | BK-GCS-PEDCO-120-IN-MR-0006 | BK-GCS-PEDCO-120-IN-MR-0006 | BK | GCS | PEDCO | 120 | IN | MR | 0006 | F0Z-709277 | IFI | IFI | 2022-09-05 | 2022-09-08 | 2022-09-13 | 3 | 5 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-22 |  |  | D00 | IFI | T-1299 | 44795 | 1401/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05602 | 44809 | 1401/06/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216179 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1299 | 2022-08-22 | 1401/05/31 |  |  |  | BK-SUR-ENG-INS-01-05602 | 44809 | 1401/06/04 | CM-C3 | [6 empty] | 1401-2294-216179 | 2022-09-08 | 1401/06/17 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 6 | 2 | 0 | 3.2.4.6.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 6 | 2 | 1 | 3.2.4.4.6.2.1 | BK-GCS-PEDCO-120-IN-TB-0006 | TBE For Pressure Safety Valves (PSV) |  | BK-GCS-PEDCO-120-IN-TB-0006 | BK-GCS-PEDCO-120-IN-TB-0006 | BK | GCS | PEDCO | 120 | IN | TB | 0006 | F0Z-709278 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 7 | 0 | 0 | 3.2.4.4.7 |  | F&G Devices | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 7 | 1 | 0 | 3.2.4.7.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 7 | 1 | 1 | 3.2.4.4.7.1.1 | BK-GCS-PEDCO-120-IN-MR-0007 | PMR For F&G Devices |  | BK-GCS-PEDCO-120-IN-MR-0007 | BK-GCS-PEDCO-120-IN-MR-0007 | BK | GCS | PEDCO | 120 | IN | MR | 0007 | F0Z-709279 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 7 | 2 | 0 | 3.2.4.7.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 7 | 2 | 1 | 3.2.4.4.7.2.1 | BK-GCS-PEDCO-120-IN-TB-0007 | TBE For F&G Devices |  | BK-GCS-PEDCO-120-IN-TB-0007 | BK-GCS-PEDCO-120-IN-TB-0007 | BK | GCS | PEDCO | 120 | IN | TB | 0007 | F0Z-709280 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 8 | 0 | 0 | 3.2.4.4.8 |  | Corrosion Probe/Coupon | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 8 | 1 | 0 | 3.2.4.8.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 8 | 1 | 1 | 3.2.4.4.8.1.1 | BK-GCS-PEDCO-120-IN-MR-0008 | PMR For Corrosion Probe/Coupon |  | BK-GCS-PEDCO-120-IN-MR-0008 | BK-GCS-PEDCO-120-IN-MR-0008 | BK | GCS | PEDCO | 120 | IN | MR | 0008 | F0Z-709281 | IFI | IFI | 2022-09-12 | 2022-09-26 | 2022-10-02 | 14 | 6 | 20 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-29 |  |  | D00 | IFI | T-1340 | 44802 | 1401/06/07 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05661 | 44816 | 1401/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-238108 | 44830 | 1401/07/04 | 44836 | 1401/07/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1340 | 2022-08-29 | 1401/06/07 |  |  |  | BK-SUR-ENG-INS-01-05661 | 44816 | 1401/06/21 | CM-C3 | [6 empty] | 1401-2294-238108 | 2022-09-26 | 1401/07/04 | 44836 | 1401/07/10 | CM
3 | 2 | 4 | 4 | 8 | 2 | 0 | 3.2.4.8.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 8 | 2 | 1 | 3.2.4.4.8.2.1 | BK-GCS-PEDCO-120-IN-TB-0008 | TBE For Corrosion Probe/Coupon |  | BK-GCS-PEDCO-120-IN-TB-0008 | BK-GCS-PEDCO-120-IN-TB-0008 | BK | GCS | PEDCO | 120 | IN | TB | 0008 | F0Z-709282 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 9 | 0 | 0 | 3.2.4.4.9 |  | Orifice and Restriction Orifice Plate | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 9 | 1 | 0 | 3.2.4.9.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 9 | 1 | 1 | 3.2.4.4.9.1.1 | BK-GCS-PEDCO-120-IN-MR-0009 | PMR For Orifice and Restriction Orifice Plate |  | BK-GCS-PEDCO-120-IN-MR-0009 | BK-GCS-PEDCO-120-IN-MR-0009 | BK | GCS | PEDCO | 120 | IN | MR | 0009 | F0Z-709283 | IFI | IFI | 2022-09-10 | 2022-09-10 | 2022-09-13 | 0 | 3 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-27 |  |  | D00 | IFI | T-1315 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216495 | 44814 | 1401/06/19 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1315 | 2022-08-27 | 1401/06/05 |  |  |  | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | [6 empty] | 1401-2294-216495 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 9 | 2 | 0 | 3.2.4.9.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 9 | 2 | 1 | 3.2.4.4.9.2.1 | BK-GCS-PEDCO-120-IN-TB-0009 | TBE For Orifice and Restriction Orifice Plate |  | BK-GCS-PEDCO-120-IN-TB-0009 | BK-GCS-PEDCO-120-IN-TB-0009 | BK | GCS | PEDCO | 120 | IN | TB | 0009 | F0Z-709284 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 10 | 0 | 0 | 3.2.4.4.10 |  | Differential Pressure/Pressure Gauge | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 10 | 1 | 0 | 3.2.4.10.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 10 | 1 | 1 | 3.2.4.4.10.1.1 | BK-GCS-PEDCO-120-IN-MR-0010 | PMR For Differential Pressure/Pressure Gauge |  | BK-GCS-PEDCO-120-IN-MR-0010 | BK-GCS-PEDCO-120-IN-MR-0010 | BK | GCS | PEDCO | 120 | IN | MR | 0010 | F0Z-709285 | IFI | IFI | 2022-09-10 | 2022-09-10 | 2022-09-13 | 0 | 3 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-27 |  |  | D00 | IFI | T-1315 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216495 | 44814 | 1401/06/19 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1315 | 2022-08-27 | 1401/06/05 |  |  |  | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | [6 empty] | 1401-2294-216495 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 10 | 2 | 0 | 3.2.4.10.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 10 | 2 | 1 | 3.2.4.4.10.2.1 | BK-GCS-PEDCO-120-IN-TB-0010 | TBE For Differential Pressure/Pressure Gauge |  | BK-GCS-PEDCO-120-IN-TB-0010 | BK-GCS-PEDCO-120-IN-TB-0010 | BK | GCS | PEDCO | 120 | IN | TB | 0010 | F0Z-709286 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 11 | 0 | 0 | 3.2.4.4.11 |  | Flow/Level /Pressure/Diff. Pressure Transmitter | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 11 | 1 | 0 | 3.2.4.11.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 11 | 1 | 1 | 3.2.4.4.11.1.1 | BK-GCS-PEDCO-120-IN-MR-0011 | PMR For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter |  | BK-GCS-PEDCO-120-IN-MR-0011 | BK-GCS-PEDCO-120-IN-MR-0011 | BK | GCS | PEDCO | 120 | IN | MR | 0011 | F0Z-709287 | IFI | IFI | 2022-09-06 | 2022-09-10 | 2022-09-13 | 4 | 3 | 7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-23 |  |  | D00 | IFI | T-1305 | 44796 | 1401/06/01 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05611 | 44811 | 1401/06/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216512 | 44814 | 1401/06/19 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1305 | 2022-08-23 | 1401/06/01 |  |  |  | BK-SUR-ENG-INS-01-05611 | 44811 | 1401/06/16 | CM-C3 | [6 empty] | 1401-2294-216512 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 11 | 2 | 0 | 3.2.4.11.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 11 | 2 | 1 | 3.2.4.4.11.2.1 | BK-GCS-PEDCO-120-IN-TB-0011 | TBE For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter" |  | BK-GCS-PEDCO-120-IN-TB-0011 | BK-GCS-PEDCO-120-IN-TB-0011 | BK | GCS | PEDCO | 120 | IN | TB | 0011 | F0Z-709288 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 12 | 0 | 0 | 3.2.4.4.12 |  | Pressure/ Differential Pressure Switch | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 12 | 1 | 0 | 3.2.4.12.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 12 | 1 | 1 | 3.2.4.4.12.1.1 | BK-GCS-PEDCO-120-IN-MR-0012 | PMR For Pressure/ Differential Pressure Switch |  | BK-GCS-PEDCO-120-IN-MR-0012 | [8 empty] | F0Z-709289 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 12 | 2 | 0 | 3.2.4.12.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 12 | 2 | 1 | 3.2.4.4.12.2.1 | BK-GCS-PEDCO-120-IN-TB-0012 | TBE For Pressure/ Differential Pressure Switch |  | BK-GCS-PEDCO-120-IN-TB-0012 | [8 empty] | F0Z-709290 | IFI | [50 empty] | 0
3 | 2 | 4 | 4 | 13 | 0 | 0 | 3.2.4.4.13 |  | Temperature Gauge | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 13 | 1 | 0 | 3.2.4.13.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 13 | 1 | 1 | 3.2.4.4.13.1.1 | BK-GCS-PEDCO-120-IN-MR-0013 | PMR For Temperature Gauge |  | BK-GCS-PEDCO-120-IN-MR-0013 | BK-GCS-PEDCO-120-IN-MR-0013 | BK | GCS | PEDCO | 120 | IN | MR | 0013 | F0Z-709291 | IFI | IFI | 2022-09-10 | 2022-09-10 | 2022-09-13 | 0 | 3 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-27 |  |  | D00 | IFI | T-1315 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216495 | 44814 | 1401/06/19 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1315 | 2022-08-27 | 1401/06/05 |  |  |  | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | [6 empty] | 1401-2294-216495 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 13 | 2 | 0 | 3.2.4.13.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 13 | 2 | 1 | 3.2.4.4.13.2.1 | BK-GCS-PEDCO-120-IN-TB-0013 | TBE For Temperature Gauge |  | BK-GCS-PEDCO-120-IN-TB-0013 | BK-GCS-PEDCO-120-IN-TB-0013 | BK | GCS | PEDCO | 120 | IN | TB | 0013 | F0Z-709292 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 14 | 0 | 0 | 3.2.4.4.14 |  | Temperature Transmitter/Switch
3 | 2 | 4 | 4 | 14 | 1 | 0 | 3.2.4.14.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 14 | 1 | 1 | 3.2.4.4.14.1.1 | BK-GCS-PEDCO-120-IN-MR-0014 | PMR For Temperature Transmitter/Switch |  | BK-GCS-PEDCO-120-IN-MR-0014 | BK-GCS-PEDCO-120-IN-MR-0014 | BK | GCS | PEDCO | 120 | IN | MR | 0014 | F0Z-709293 | IFI | IFI | 2022-09-10 | 2022-09-10 | 2022-09-13 | 0 | 3 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-27 |  |  | D00 | IFI | T-1315 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216495 | 44814 | 1401/06/19 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1315 | 2022-08-27 | 1401/06/05 |  |  |  | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | [6 empty] | 1401-2294-216495 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 14 | 2 | 0 | 3.2.4.14.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 14 | 2 | 1 | 3.2.4.4.14.2.1 | BK-GCS-PEDCO-120-IN-TB-0014 | TBE For Temperature Transmitter/Switch |  | BK-GCS-PEDCO-120-IN-TB-0014 | BK-GCS-PEDCO-120-IN-TB-0014 | BK | GCS | PEDCO | 120 | IN | TB | 0014 | F0Z-709294 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 15 | 0 | 0 | 3.2.4.4.15 |  | Level Gauge
3 | 2 | 4 | 4 | 15 | 1 | 0 | 3.2.4.15.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 15 | 1 | 1 | 3.2.4.4.15.1.1 | BK-GCS-PEDCO-120-IN-MR-0015 | PMR For Level Gauge |  | BK-GCS-PEDCO-120-IN-MR-0015 | BK-GCS-PEDCO-120-IN-MR-0015 | BK | GCS | PEDCO | 120 | IN | MR | 0015 | F0Z-709295 | IFI | IFI | 2022-09-10 | 2022-09-10 | 2022-09-13 | 0 | 3 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-27 |  |  | D00 | IFI | T-1315 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216495 | 44814 | 1401/06/19 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1315 | 2022-08-27 | 1401/06/05 |  |  |  | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | [6 empty] | 1401-2294-216495 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 15 | 2 | 0 | 3.2.4.15.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 15 | 2 | 1 | 3.2.4.4.15.2.1 | BK-GCS-PEDCO-120-IN-TB-0015 | TBE For Level Gauge |  | BK-GCS-PEDCO-120-IN-TB-0015 | BK-GCS-PEDCO-120-IN-TB-0015 | BK | GCS | PEDCO | 120 | IN | TB | 0015 | F0Z-709296 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 16 | 0 | 0 | 3.2.4.4.16 |  | Level Switch
3 | 2 | 4 | 4 | 16 | 1 | 0 | 3.2.4.16.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 16 | 1 | 1 | 3.2.4.4.16.1.1 | BK-GCS-PEDCO-120-IN-MR-0016 | PMR For Level Switch |  | BK-GCS-PEDCO-120-IN-MR-0016 | BK-GCS-PEDCO-120-IN-MR-0016 | BK | GCS | PEDCO | 120 | IN | MR | 0016 | F0Z-709297 | IFI | IFI | 2022-09-10 | 2022-09-10 | 2022-09-13 | 0 | 3 | 3 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-27 |  |  | D00 | IFI | T-1315 | 44800 | 1401/06/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216495 | 44814 | 1401/06/19 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1315 | 2022-08-27 | 1401/06/05 |  |  |  | BK-SUR-ENG-INS-01-05623 | 44814 | 1401/06/19 | CM-C3 | [6 empty] | 1401-2294-216495 | 2022-09-10 | 1401/06/19 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 16 | 2 | 0 | 3.2.4.16.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 16 | 2 | 1 | 3.2.4.4.16.2.1 | BK-GCS-PEDCO-120-IN-TB-0016 | TBE For Level Switch |  | BK-GCS-PEDCO-120-IN-TB-0016 | BK-GCS-PEDCO-120-IN-TB-0016 | BK | GCS | PEDCO | 120 | IN | TB | 0016 | F0Z-709298 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 17 | 0 | 0 | 3.2.4.4.17 |  | Displacer Level Transmitter
3 | 2 | 4 | 4 | 17 | 1 | 0 | 3.2.4.17.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 17 | 1 | 1 | 3.2.4.4.17.1.1 | BK-GCS-PEDCO-120-IN-MR-0017 | PMR For Displacer Level Transmitter |  | BK-GCS-PEDCO-120-IN-MR-0017 | BK-GCS-PEDCO-120-IN-MR-0017 | BK | GCS | PEDCO | 120 | IN | MR | 0017 | F0Z-709299 | IFI | IFI | 2022-09-05 | 2022-09-08 | 2022-09-13 | 3 | 5 | 8 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-22 |  |  | D00 | IFI | T-1299 | 44795 | 1401/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05602 | 44809 | 1401/06/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216179 | 44812 | 1401/06/17 | 44817 | 1401/06/22 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1299 | 2022-08-22 | 1401/05/31 |  |  |  | BK-SUR-ENG-INS-01-05602 | 44809 | 1401/06/04 | CM-C3 | [6 empty] | 1401-2294-216179 | 2022-09-08 | 1401/06/17 | 44817 | 1401/06/22 | CM
3 | 2 | 4 | 4 | 17 | 2 | 0 | 3.2.4.17.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 17 | 2 | 1 | 3.2.4.4.17.2.1 | BK-GCS-PEDCO-120-IN-TB-0017 | TBE For Displacer Level Transmitter |  | BK-GCS-PEDCO-120-IN-TB-0017 | BK-GCS-PEDCO-120-IN-TB-0017 | BK | GCS | PEDCO | 120 | IN | TB | 0017 | F0Z-709300 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 18 | 0 | 0 | 3.2.4.4.18 |  | Rotameter
3 | 2 | 4 | 4 | 18 | 1 | 0 | 3.2.4.18.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 18 | 1 | 1 | 3.2.4.4.18.1.1 | BK-GCS-PEDCO-120-IN-MR-0019 | PMR For Rotameter |  | BK-GCS-PEDCO-120-IN-MR-0019 | BK-GCS-PEDCO-120-IN-MR-0019 | BK | GCS | PEDCO | 120 | IN | MR | 0019 | F0Z-709301 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 18 | 2 | 0 | 3.2.4.18.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 4 | 18 | 2 | 1 | 3.2.4.4.18.2.1 | BK-GCS-PEDCO-120-IN-TB-0019 | TBE For Rotameter |  | BK-GCS-PEDCO-120-IN-TB-0019 | BK-GCS-PEDCO-120-IN-TB-0019 | BK | GCS | PEDCO | 120 | IN | TB | 0019 | F0Z-709302 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 4 | 19 | 0 | 0 | 3.2.4.4.19 |  | Instrument/F&G Cable
3 | 2 | 4 | 4 | 19 | 1 | 0 | 3.2.4.19.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 19 | 1 | 1 | 3.2.4.4.19.1.1 | BK-GCS-PEDCO-120-IN-MR-0020 | PMR For Instrument/F&G cable |  | BK-GCS-PEDCO-120-IN-MR-0020 | BK-GCS-PEDCO-120-IN-MR-0020 | BK | GCS | PEDCO | 120 | IN | MR | 0020 | F0Z-709303 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 19 | 2 | 0 | 3.2.4.19.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 19 | 2 | 1 | 3.2.4.4.19.2.1 | BK-GCS-PEDCO-120-IN-TB-0020 | TBE For Instrument/F&G cable |  | BK-GCS-PEDCO-120-IN-TB-0020 | BK-GCS-PEDCO-120-IN-TB-0020 | BK | GCS | PEDCO | 120 | IN | TB | 0020 | F0Z-709304 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 20 | 0 | 0 | 3.2.4.4.20 |  | Instrument Cable Tray
3 | 2 | 4 | 4 | 20 | 1 | 0 | 3.2.4.20.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 20 | 1 | 1 | 3.2.4.4.20.1.1 | BK-GCS-PEDCO-120-IN-MR-0021 | PMR For Instrument Cable Tray |  | BK-GCS-PEDCO-120-IN-MR-0021 | BK-GCS-PEDCO-120-IN-MR-0021 | BK | GCS | PEDCO | 120 | IN | MR | 0021 | F0Z-709305 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 20 | 2 | 0 | 3.2.4.20.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 20 | 2 | 1 | 3.2.4.4.20.2.1 | BK-GCS-PEDCO-120-IN-TB-0021 | TBE For Instrument Cable Tray |  | BK-GCS-PEDCO-120-IN-TB-0021 | BK-GCS-PEDCO-120-IN-TB-0021 | BK | GCS | PEDCO | 120 | IN | TB | 0021 | F0Z-709306 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 21 | 0 | 0 | 3.2.4.4.21 |  | Instrument/F&G Junction box and Gland
3 | 2 | 4 | 4 | 21 | 1 | 0 | 3.2.4.21.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 21 | 1 | 1 | 3.2.4.4.21.1.1 | BK-GCS-PEDCO-120-IN-MR-0022 | PMR For Instrument/F&G Junction box and Gland |  | BK-GCS-PEDCO-120-IN-MR-0022 | BK-GCS-PEDCO-120-IN-MR-0022 | BK | GCS | PEDCO | 120 | IN | MR | 0022 | F0Z-709307 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 21 | 2 | 0 | 3.2.4.21.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 21 | 2 | 1 | 3.2.4.4.21.2.1 | BK-GCS-PEDCO-120-IN-TB-0022 | TBE For Instrument/F&G Junction box and Gland |  | BK-GCS-PEDCO-120-IN-TB-0022 | BK-GCS-PEDCO-120-IN-TB-0022 | BK | GCS | PEDCO | 120 | IN | TB | 0022 | F0Z-709308 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 22 | 0 | 0 | 3.2.4.4.22 |  | Instrument Tube and Fitting
3 | 2 | 4 | 4 | 22 | 1 | 0 | 3.2.4.22.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 22 | 1 | 1 | 3.2.4.4.22.1.1 | BK-GCS-PEDCO-120-IN-MR-0023 | PMR For Instrument Tube and Fitting |  | BK-GCS-PEDCO-120-IN-MR-0023 | BK-GCS-PEDCO-120-IN-MR-0023 | BK | GCS | PEDCO | 120 | IN | MR | 0023 | F0Z-709309 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 22 | 2 | 0 | 3.2.4.22.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 22 | 2 | 1 | 3.2.4.4.22.2.1 | BK-GCS-PEDCO-120-IN-TB-0023 | TBE For Instrument Tube and Fitting |  | BK-GCS-PEDCO-120-IN-TB-0023 | BK-GCS-PEDCO-120-IN-TB-0023 | BK | GCS | PEDCO | 120 | IN | TB | 0023 | F0Z-709310 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 23 | 0 | 0 | 3.2.4.4.23 |  | Instrument Installation Accessories
3 | 2 | 4 | 4 | 23 | 1 | 0 | 3.2.4.23.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 23 | 1 | 1 | 3.2.4.4.23.1.1 | BK-GCS-PEDCO-120-IN-MR-0024 | PMR For Instrument Installation Accessories |  | BK-GCS-PEDCO-120-IN-MR-0024 | BK-GCS-PEDCO-120-IN-MR-0024 | BK | GCS | PEDCO | 120 | IN | MR | 0024 | F0Z-709311 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 23 | 2 | 0 | 3.2.4.23.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 23 | 2 | 1 | 3.2.4.4.23.2.1 | BK-GCS-PEDCO-120-IN-TB-0024 | TBE For Instrument Installation Accessories |  | BK-GCS-PEDCO-120-IN-TB-0024 | BK-GCS-PEDCO-120-IN-TB-0024 | BK | GCS | PEDCO | 120 | IN | TB | 0024 | F0Z-709312 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 24 | 0 | 0 | 3.2.4.4.24 |  | CCTV System
3 | 2 | 4 | 4 | 24 | 1 | 0 | 3.2.4.24.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 24 | 1 | 1 | 3.2.4.4.24.1.1 | BK-GCS-PEDCO-120-IN-MR-0025 | PMR For CCTV System |  | BK-GCS-PEDCO-120-IN-MR-0025 | BK-GCS-PEDCO-120-IN-MR-0025 | BK | GCS | PEDCO | 120 | IN | MR | 0025 | F0Z-709313 | IFI | IFI | 2022-01-03 | 2021-12-30 | 2022-01-02 | -4 | 3 | -1 | IFI | 2022-02-26 | 2022-02-22 | 2022-02-02 | -4 | -20 | -24 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2021-12-20 |  |  | D01 | IFI | T-0578 | 44604 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03148 | 44613 | 1400/12/02 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0025_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421740 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0025_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0371 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-INS-00-02496 | 44562 | 1400/10/11 | RJ-C4 | [6 empty] | 1400-2294-342126 | 2021-12-30 | 1400/10/09 | 44563 | 1400/10/12 | CM | [10 empty] | D01 | IFI | T-0578 | 44604 | 1400/11/23 |  |  |  | BK-SUR-ENG-INS-00-03148 | 44613 | 1400/12/02 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0025_D00 | [5 empty] | 1400-2294-421740 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0025_D00
3 | 2 | 4 | 4 | 24 | 2 | 0 | 3.2.4.24.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 24 | 2 | 1 | 3.2.4.4.24.2.1 | BK-GCS-PEDCO-120-IN-TB-0025 | TBE For CCTV System |  | BK-GCS-PEDCO-120-IN-TB-0025 | BK-GCS-PEDCO-120-IN-TB-0025 | BK | GCS | PEDCO | 120 | IN | TB | 0025 | F0Z-709314 | IFI | IFI | 2022-05-16 | 2022-05-12 | 2022-05-16 | -4 | 4 | 0 | IFI | 2022-07-19 | 2022-07-30 | 2022-08-01 | 11 | 2 | 13 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-05-02 |  |  | D01 | IFI | T-1143 | 44747 | 1401/04/14 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-05229 | 44766 | 1401/02/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-159135 | 44772 | 1401/05/08 | 44774 | 1401/05/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-TB-0025_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0901 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-INS-01-04222 | 44691 | 1401/02/0 | AP | [6 empty] | 1401-2294-59528 | 2022-05-12 | 1401/02/22 | 44697 | 1401/02/26 | CM | [10 empty] | D01 | IFI | T-1143 | 44747 | 1401/04/14 |  |  |  | BK-SUR-ENG-INS-01-05229 | 44766 | 1401/02/05 | AP | [6 empty] | 1401-2294-159135 | 44772 | 1401/05/08 | 44774 | 1401/05/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-TB-0025_D00
3 | 2 | 4 | 4 | 25 | 0 | 0 | 3.2.4.4.25 |  | IRP Panel
3 | 2 | 4 | 4 | 25 | 1 | 0 | 3.2.4.25.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 25 | 1 | 1 | 3.2.4.4.25.1.1 | BK-GCS-PEDCO-120-IN-MR-0026 | PMR For IRP Panel |  | BK-GCS-PEDCO-120-IN-MR-0026 | BK-GCS-PEDCO-120-IN-MR-0026 | BK | GCS | PEDCO | 120 | IN | MR | 0026 | F0Z-709315 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 4 | 25 | 2 | 0 | 3.2.4.25.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 25 | 2 | 1 | 3.2.4.4.25.2.1 | BK-GCS-PEDCO-120-IN-TB-0026 | TBE For IRP Panel |  | BK-GCS-PEDCO-120-IN-TB-0026 | BK-GCS-PEDCO-120-IN-TB-0026 | BK | GCS | PEDCO | 120 | IN | TB | 0026 | F0Z-709316 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 5 | 0 | 0 | 0 | 3.2.4.5 |  | Safety & Fire Fighting
3 | 2 | 4 | 5 | 1 | 0 | 0 | 3.2.4.5.1 |  | Total Flooding System
3 | 2 | 4 | 5 | 1 | 1 | 0 | 3.2.5.1.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 1 | 1 | 1 | 3.2.4.5.1.1.1 | BK-GCS-PEDCO-120-SA-MR-0001 | PMR For Total Flooding System |  | BK-GCS-PEDCO-120-SA-MR-0001 | BK-GCS-PEDCO-120-SA-MR-0001 | BK | GCS | PEDCO | 120 | SA | MR | 0001 | F0Z-709317 | IFI | IFI | 2022-05-28 | 2022-10-12 | 2022-10-17 | 137 | 5 | 142 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-05-14 |  |  | D00 | IFI | T-0942 | 44695 | 1401/02/24 | T-0942 | 44695 | 1401/02/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-113874 | 44735 | 1401/04/02 | 44744 | 1401/04/11 | AP | 0 | 1401-2294-260506 | 44846 | 1401/07/20 | 44851 | 1401/07/25 | AP | 0 | 0 |  | D00 | IFI | T-0942 | 2022-05-14 | 1401/02/24 | T-0942 | 44695 | 1401/02/24 | [10 empty] | 1401-2294-113874 | 2022-06-23 | 1401/04/02 | 44744 | 1401/04/11 | AP |  | 1401-2294-260506 | 44846 | 1401/07/20 | 44851 | 1401/07/25 | AP
3 | 2 | 4 | 5 | 1 | 2 | 0 | 3.2.5.1.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 1 | 2 | 1 | 3.2.4.5.1.2.1 | BK-GCS-PEDCO-120-SA-TB-0001 | TBE For Total Flooding System |  | BK-GCS-PEDCO-120-SA-TB-0001 | BK-GCS-PEDCO-120-SA-TB-0001 | BK | GCS | PEDCO | 120 | SA | TB | 0001 | F0Z-709318 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 5 | 2 | 0 | 0 | 3.2.4.5.2 |  | Deluge Valve & Water Spray
3 | 2 | 4 | 5 | 2 | 1 | 0 | 3.2.5.2.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 2 | 1 | 1 | 3.2.4.5.2.1.1 | BK-GCS-PEDCO-120-SA-MR-0002 | PMR For Deluge Valve & Water Spray |  | BK-GCS-PEDCO-120-SA-MR-0002 | BK-GCS-PEDCO-120-SA-MR-0002 | BK | GCS | PEDCO | 120 | SA | MR | 0002 | F0Z-709319 | IFI | IFI | 2022-06-28 | 2022-08-14 | 2022-08-16 | 47 | 2 | 49 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-14 |  |  | D00 | IFI | T-1076 | 44726 | 1401/03/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177134 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1076 | 2022-06-14 | 1401/03/24 | [13 empty] | 1401-2294-177134 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM
3 | 2 | 4 | 5 | 2 | 2 | 0 | 3.2.5.2.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 2 | 2 | 1 | 3.2.4.5.2.2.1 | BK-GCS-PEDCO-120-SA-TB-0002 | TBE For Deluge Valve & Water Spray |  | BK-GCS-PEDCO-120-SA-TB-0002 | BK-GCS-PEDCO-120-SA-TB-0002 | BK | GCS | PEDCO | 120 | SA | TB | 0002 | F0Z-709320 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 5 | 3 | 0 | 0 | 3.2.4.5.3 |  | Safety Equipment
3 | 2 | 4 | 5 | 3 | 1 | 0 | 3.2.5.3.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 3 | 1 | 1 | 3.2.4.5.3.1.1 | BK-GCS-PEDCO-120-SA-MR-0003 | PMR For Safety Equipment |  | BK-GCS-PEDCO-120-SA-MR-0003 | BK-GCS-PEDCO-120-SA-MR-0003 | BK | GCS | PEDCO | 120 | SA | MR | 0003 | F0Z-709321 | IFI | IFI | 2022-06-28 | 2022-08-14 | 2022-08-16 | 47 | 2 | 49 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-14 |  |  | D00 | IFI | T-1076 | 44726 | 1401/03/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177134 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1076 | 2022-06-14 | 1401/03/24 | [13 empty] | 1401-2294-177134 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM
3 | 2 | 4 | 5 | 3 | 2 | 0 | 3.2.5.3.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 3 | 2 | 1 | 3.2.4.5.3.2.1 | BK-GCS-PEDCO-120-SA-TB-0003 | TBE For Safety Equipment |  | BK-GCS-PEDCO-120-SA-TB-0003 | BK-GCS-PEDCO-120-SA-TB-0003 | BK | GCS | PEDCO | 120 | SA | TB | 0003 | F0Z-709322 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 5 | 4 | 0 | 0 | 3.2.4.5.4 |  | Fire Fighting Equipment
3 | 2 | 4 | 5 | 4 | 1 | 0 | 3.2.5.4.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 4 | 1 | 1 | 3.2.4.5.4.1.1 | BK-GCS-PEDCO-120-SA-MR-0004 | PMR For Fire Fighting Equipment |  | BK-GCS-PEDCO-120-SA-MR-0004 | BK-GCS-PEDCO-120-SA-MR-0004 | BK | GCS | PEDCO | 120 | SA | MR | 0004 | F0Z-709323 | IFI | IFI | 2022-06-25 | 2022-08-14 | 2022-08-16 | 50 | 2 | 52 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-11 |  |  | D00 | IFI | T-1062 | 44723 | 1401/03/21 | T-1062 | 44723 | 1401/03/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177133 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1062 | 2022-06-11 | 1401/03/21 | T-1062 | 44723 | 1401/03/21 | [10 empty] | 1401-2294-177133 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM
3 | 2 | 4 | 5 | 4 | 2 | 0 | 3.2.5.4.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 4 | 2 | 1 | 3.2.4.5.4.2.1 | BK-GCS-PEDCO-120-SA-TB-0004 | TBE For Fire Fighting Equipment |  | BK-GCS-PEDCO-120-SA-TB-0004 | BK-GCS-PEDCO-120-SA-TB-0004 | BK | GCS | PEDCO | 120 | SA | TB | 0004 | F0Z-709324 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 5 | 5 | 0 | 0 | 3.2.4.5.5 |  | Safety Signs
3 | 2 | 4 | 5 | 5 | 1 | 0 | 3.2.5.5.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 5 | 1 | 1 | 3.2.4.5.5.1.1 | BK-GCS-PEDCO-120-SA-MR-0005 | PMR For Safety Signs |  | BK-GCS-PEDCO-120-SA-MR-0005 | BK-GCS-PEDCO-120-SA-MR-0005 | BK | GCS | PEDCO | 120 | SA | MR | 0005 | F0Z-709325 | IFI | IFI | 2022-06-28 | 2022-08-14 | 2022-08-16 | 47 | 2 | 49 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-14 |  |  | D00 | IFI | T-1076 | 44726 | 1401/03/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-177134 | 44787 | 1401/05/23 | 44789 | 1401/05/25 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1076 | 2022-06-14 | 1401/03/24 | [13 empty] | 1401-2294-177134 | 2022-08-14 | 1401/05/23 | 44789 | 1401/05/25 | CM
3 | 2 | 4 | 5 | 5 | 2 | 0 | 3.2.5.5.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 5 | 5 | 2 | 1 | 3.2.4.5.5.2.1 | BK-GCS-PEDCO-120-SA-TB-0005 | TBE For Safety Signs |  | BK-GCS-PEDCO-120-SA-TB-0005 | BK-GCS-PEDCO-120-SA-TB-0005 | BK | GCS | PEDCO | 120 | SA | TB | 0005 | F0Z-709326 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 0 | 0 | 0 | 3.2.4.6 |  | Electrical
3 | 2 | 4 | 6 | 1 | 0 | 0 | 3.2.4.6.1 |  | Transformers | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 1 | 1 | 0 | 3.2.6.1.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 1 | 1 | 1 | 3.2.4.6.1.1.1 | BK-GCS-PEDCO-120-EL-MR-0001 | PMR For Transformers |  | BK-GCS-PEDCO-120-EL-MR-0001 | BK-GCS-PEDCO-120-EL-MR-0001 | BK | GCS | PEDCO | 120 | EL | MR | 0001 | F0Z-709327 | IFI | IFI | 2022-08-23 | 2022-08-31 | 2022-08-04 | 8 | -27 | -19 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-09 |  |  | D00 | IFI | T-1260 | 44782 | 1401/05/18 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05506 | 44796 | 1401/06/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-205596 | 44804 | 1401/06/09 | 44777 | 1401/06/13 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1260 | 2022-08-09 | 1401/05/18 |  |  |  | BK-SUR-ENG-ELE-01-05506 | 44796 | 1401/06/01 | AP | [6 empty] | 1401-2294-205596 | 2022-08-31 | 1401/06/09 | 44777 | 1401/06/13 | CM
3 | 2 | 4 | 6 | 1 | 2 | 0 | 3.2.6.1.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 1 | 2 | 1 | 3.2.4.6.1.2.1 | BK-GCS-PEDCO-120-EL-TB-0001 | TBE For Transformers |  | BK-GCS-PEDCO-120-EL-TB-0001 | BK-GCS-PEDCO-120-EL-TB-0001 | BK | GCS | PEDCO | 120 | EL | TB | 0001 | F0Z-709328 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 2 | 0 | 0 | 3.2.4.6.2 |  | LV Switchgear & MCC | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 2 | 1 | 0 | 3.2.6.2.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 2 | 1 | 1 | 3.2.4.6.2.1.1 | BK-GCS-PEDCO-120-EL-MR-0002 | PMR For LV Switchgear, MCC |  | BK-GCS-PEDCO-120-EL-MR-0002 | BK-GCS-PEDCO-120-EL-MR-0002 | BK | GCS | PEDCO | 120 | EL | MR | 0002 | F0Z-709329 | IFI | IFI | 2022-09-19 | 2022-09-08 | 2022-09-12 | -11 | 4 | -7 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-09-05 |  |  | D00 | IFI | T-1357 | 44809 | 1401/06/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05692 | 44817 | 1401/06/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-216049 | 44812 | 1401/06/17 | 44816 | 1401/06/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1357 | 2022-09-05 | 1401/06/14 |  |  |  | BK-SUR-ENG-ELE-01-05692 | 44817 | 1401/06/22 | AP | [6 empty] | 1401-2294-216049 | 2022-09-08 | 1401/06/17 | 44816 | 1401/06/21 | CM
3 | 2 | 4 | 6 | 2 | 2 | 0 | 3.2.6.2.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 2 | 2 | 1 | 3.2.4.6.2.2.1 | BK-GCS-PEDCO-120-EL-TB-0002 | TBE For LV Switchgear, MCC |  | BK-GCS-PEDCO-120-EL-TB-0002 | BK-GCS-PEDCO-120-EL-TB-0002 | BK | GCS | PEDCO | 120 | EL | TB | 0002 | F0Z-709330 | IFI | [50 empty] | 0
3 | 2 | 4 | 6 | 3 | 0 | 0 | 3.2.4.6.3 |  | Existent MV Switchgear Expansion | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 3 | 1 | 0 | 3.2.6.3.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 3 | 1 | 1 | 3.2.4.6.3.1.1 | BK-GCS-PEDCO-120-EL-MR-0003 | PMR For Existent MV Switchgear Expansion & RCP |  | BK-GCS-PEDCO-120-EL-MR-0003 | BK-GCS-PEDCO-120-EL-MR-0003 | BK | GCS | PEDCO | 120 | EL | MR | 0003 | F0Z-709331 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 3 | 2 | 0 | 3.2.6.3.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 3 | 2 | 1 | 3.2.4.6.3.2.1 | BK-GCS-PEDCO-120-EL-TB-0003 | TBE For Existent MV Switchgear Expansion & RCP |  | BK-GCS-PEDCO-120-EL-TB-0003 | BK-GCS-PEDCO-120-EL-TB-0003 | BK | GCS | PEDCO | 120 | EL | TB | 0003 | F0Z-709332 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 4 | 0 | 0 | 3.2.4.6.4 |  | Emergency Diesel Generator | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 4 | 1 | 0 | 3.2.6.4.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 4 | 1 | 1 | 3.2.4.6.4.1.1 | BK-GCS-PEDCO-120-EL-MR-0004 | PMR For Emergency Diesel Generator |  | BK-GCS-PEDCO-120-EL-MR-0004 | BK-GCS-PEDCO-120-EL-MR-0004 | BK | GCS | PEDCO | 120 | EL | MR | 0004 | F0Z-709333 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 4 | 2 | 0 | 3.2.6.4.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 4 | 2 | 1 | 3.2.4.6.4.2.1 | BK-GCS-PEDCO-120-EL-TB-0004 | TBE For Emergency Diesel Generator |  | BK-GCS-PEDCO-120-EL-TB-0004 | BK-GCS-PEDCO-120-EL-TB-0004 | BK | GCS | PEDCO | 120 | EL | TB | 0004 | F0Z-709334 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 5 | 0 | 0 | 3.2.4.6.5 |  | UPS System | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 5 | 1 | 0 | 3.2.6.5.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 5 | 1 | 1 | 3.2.4.6.5.1.1 | BK-GCS-PEDCO-120-EL-MR-0005 | PMR For UPS System |  | BK-GCS-PEDCO-120-EL-MR-0005 | BK-GCS-PEDCO-120-EL-MR-0005 | BK | GCS | PEDCO | 120 | EL | MR | 0005 | F0Z-709335 | IFI | IFI | 2022-08-17 | 2022-08-28 | 2022-09-03 | 11 | 6 | 17 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 2022-08-03 |  |  | D00 | IFI | T-1242 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05453 | 44788 | 1401/05/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-198994 | 44801 | 1401/06/06 | 44807 | 1401/06/13 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1242 | 2022-08-03 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05453 | 44788 | 1401/05/24 | AP | [6 empty] | 1401-2294-198994 | 2022-08-28 | 1401/06/06 | 44807 | 1401/06/13 | CM
3 | 2 | 4 | 6 | 5 | 2 | 0 | 3.2.6.5.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 5 | 2 | 1 | 3.2.4.6.5.2.1 | BK-GCS-PEDCO-120-EL-TB-0005 | TBE For UPS System |  | BK-GCS-PEDCO-120-EL-TB-0005 | BK-GCS-PEDCO-120-EL-TB-0005 | BK | GCS | PEDCO | 120 | EL | TB | 0005 | F0Z-709336 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 6 | 0 | 0 | 3.2.4.6.6 |  | DC Charger
3 | 2 | 4 | 6 | 6 | 1 | 0 | 3.2.6.6.1 |  | Purchase Material Requisition (PMR) | [61 empty] | Moved to IN
3 | 2 | 4 | 6 | 6 | 1 | 1 | 3.2.4.6.6.1.1 | BK-GCS-PEDCO-120-EL-MR-0006 | PMR For DC Charger |  | BK-GCS-PEDCO-120-EL-MR-0006 | BK-GCS-PEDCO-120-EL-MR-0006 | BK | GCS | PEDCO | 120 | EL | MR | 0006 | F0Z-709337 | IFI | IFI | 2022-08-17 | 2022-08-28 | 2022-09-04 | 11 | 7 | 18 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-08-03 |  |  | D00 | IFI | T-1244 | 44776 | 1401/05/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05454 | 44788 | 1401/05/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-199021 | 44801 | 1401/06/06 | 44808 | 1401/06/13 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1244 | 2022-08-03 | 1401/05/12 |  |  |  | BK-SUR-ENG-ELE-01-05454 | 44788 | 1401/05/24 | AP | [6 empty] | 1401-2294-199021 | 2022-08-28 | 1401/06/06 | 44808 | 1401/06/13 | AP
3 | 2 | 4 | 6 | 6 | 2 | 0 | 3.2.6.6.2 |  | Technical Bid Evaluation (TBE) | [61 empty] | Moved to IN
3 | 2 | 4 | 6 | 6 | 2 | 1 | 3.2.4.6.6.2.1 | BK-GCS-PEDCO-120-EL-TB-0006 | TBE For DC Charger |  | BK-GCS-PEDCO-120-EL-TB-0006 | BK-GCS-PEDCO-120-EL-TB-0006 | BK | GCS | PEDCO | 120 | EL | TB | 0006 | F0Z-709338 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 7 | 0 | 0 | 3.2.4.6.7 |  | Lighting & Distribution Panels
3 | 2 | 4 | 6 | 7 | 1 | 0 | 3.2.6.7.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 7 | 1 | 1 | 3.2.4.6.7.1.1 | BK-GCS-PEDCO-120-EL-MR-0007 | PMR For Lighting & Distribution Panels |  | BK-GCS-PEDCO-120-EL-MR-0007 | BK-GCS-PEDCO-120-EL-MR-0007 | BK | GCS | PEDCO | 120 | EL | MR | 0007 | F0Z-709339 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 7 | 2 | 0 | 3.2.6.7.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 7 | 2 | 1 | 3.2.4.6.7.2.1 | BK-GCS-PEDCO-120-EL-TB-0007 | TBE For Lighting & Distribution Panels |  | BK-GCS-PEDCO-120-EL-TB-0007 | BK-GCS-PEDCO-120-EL-TB-0007 | BK | GCS | PEDCO | 120 | EL | TB | 0007 | F0Z-709340 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 8 | 0 | 0 | 3.2.4.6.8 |  | Lighting and Small Power Equipment
3 | 2 | 4 | 6 | 8 | 1 | 0 | 3.2.6.8.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 8 | 1 | 1 | 3.2.4.6.8.1.1 | BK-GCS-PEDCO-120-EL-MR-0008 | PMR For Lighting and Small Power Equipment |  | BK-GCS-PEDCO-120-EL-MR-0008 | BK-GCS-PEDCO-120-EL-MR-0008 | BK | GCS | PEDCO | 120 | EL | MR | 0008 | F0Z-709341 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 8 | 2 | 0 | 3.2.6.8.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 8 | 2 | 1 | 3.2.4.6.8.2.1 | BK-GCS-PEDCO-120-EL-TB-0008 | TBE For Lighting and Small Power Equipment |  | BK-GCS-PEDCO-120-EL-TB-0008 | BK-GCS-PEDCO-120-EL-TB-0008 | BK | GCS | PEDCO | 120 | EL | TB | 0008 | F0Z-709342 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 9 | 0 | 0 | 3.2.4.6.9 |  | Earthing & Lightning System
3 | 2 | 4 | 6 | 9 | 1 | 0 | 3.2.6.9.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 9 | 1 | 1 | 3.2.4.6.9.1.1 | BK-GCS-PEDCO-120-EL-MR-0009 | PMR For Earthing & Lightning System |  | BK-GCS-PEDCO-120-EL-MR-0009 | BK-GCS-PEDCO-120-EL-MR-0009 | BK | GCS | PEDCO | 120 | EL | MR | 0009 | F0Z-709343 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 9 | 2 | 0 | 3.2.6.9.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 9 | 2 | 1 | 3.2.4.6.9.2.1 | BK-GCS-PEDCO-120-EL-TB-0009 | TBE For Earthing & Lightning System |  | BK-GCS-PEDCO-120-EL-TB-0009 | BK-GCS-PEDCO-120-EL-TB-0009 | BK | GCS | PEDCO | 120 | EL | TB | 0009 | F0Z-709344 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 10 | 0 | 0 | 3.2.4.6.10 |  | Local Control Station (LCS)
3 | 2 | 4 | 6 | 10 | 1 | 0 | 3.2.6.10.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 10 | 1 | 1 | 3.2.4.6.10.1.1 | BK-GCS-PEDCO-120-EL-MR-0010 | PMR For Local Control Station (LCS) |  | BK-GCS-PEDCO-120-EL-MR-0010 | BK-GCS-PEDCO-120-EL-MR-0010 | BK | GCS | PEDCO | 120 | EL | MR | 0010 | F0Z-709345 | IFI | IFI | 2022-07-11 | 2022-07-27 | 2022-07-30 | 16 | 3 | 19 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 2022-06-27 |  |  | D00 | IFI | T-1124 | 44739 | 1401/04/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-05049 | 44753 | 1401/04/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-156672 | 44769 | 1401/05/05 | 44772 | 1401/05/08 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1124 | 2022-06-27 | 1401/04/06 |  |  |  | BK-SUR-ENG-ELE-01-05049 | 44753 | 1401/04/20 | CM-C3 | [6 empty] | 1401-2294-156672 | 2022-07-27 | 1401/05/05 | 44772 | 1401/05/08 | CM
3 | 2 | 4 | 6 | 10 | 2 | 0 | 3.2.6.10.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 10 | 2 | 1 | 3.2.4.6.10.2.1 | BK-GCS-PEDCO-120-EL-TB-0010 | TBE For Local Control Station (LCS) |  | BK-GCS-PEDCO-120-EL-TB-0010 | BK-GCS-PEDCO-120-EL-TB-0010 | BK | GCS | PEDCO | 120 | EL | TB | 0010 | F0Z-709346 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 11 | 0 | 0 | 3.2.4.6.11 |  | Capacitor Bank
3 | 2 | 4 | 6 | 11 | 1 | 0 | 3.2.6.11.1 |  | Purchase Material Requisition (PMR) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 11 | 1 | 1 | 3.2.4.6.11.1.1 | BK-GCS-PEDCO-120-EL-MR-0011 | PMR For Capacitor Bank |  | BK-GCS-PEDCO-120-EL-MR-0011 | BK-GCS-PEDCO-120-EL-MR-0011 | BK | GCS | PEDCO | 120 | EL | MR | 0011 | F0Z-709347 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 11 | 2 | 0 | 3.2.6.11.2 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 11 | 2 | 1 | 3.2.4.6.11.2.1 | BK-GCS-PEDCO-120-EL-TB-0011 | TBE For Capacitor Bank |  | BK-GCS-PEDCO-120-EL-TB-0011 | BK-GCS-PEDCO-120-EL-TB-0011 | BK | GCS | PEDCO | 120 | EL | TB | 0011 | F0Z-709348 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 12 | 0 | 0 | 3.2.4.6.12 |  | NGR System
3 | 2 | 4 | 6 | 12 | 1 | 0 | 3.2.6.12.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 12 | 1 | 1 | 3.2.4.6.12.1.1 | BK-GCS-PEDCO-120-EL-MR-0012 | PMR For NGR |  | BK-GCS-PEDCO-120-EL-MR-0012 | BK-GCS-PEDCO-120-EL-MR-0012 | BK | GCS | PEDCO | 120 | EL | MR | 0012 | F0Z-709349 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 12 | 2 | 0 | 3.2.6.12.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 12 | 2 | 1 | 3.2.4.6.12.2.1 | BK-GCS-PEDCO-120-EL-TB-0012 | TBE For NGR |  | BK-GCS-PEDCO-120-EL-TB-0012 | BK-GCS-PEDCO-120-EL-TB-0012 | BK | GCS | PEDCO | 120 | EL | TB | 0012 | F0Z-709350 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 13 | 0 | 0 | 3.2.4.6.13 |  | Cathodic Protection System
3 | 2 | 4 | 6 | 13 | 1 | 0 | 3.2.6.13.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 13 | 1 | 1 | 3.2.4.6.13.1.1 | BK-GCS-PEDCO-120-EL-MR-0013 | PMR For Cathodic Protection System |  | BK-GCS-PEDCO-120-EL-MR-0013 | [8 empty] | F0Z-709351 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 13 | 2 | 0 | 3.2.6.13.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 13 | 2 | 1 | 3.2.4.6.13.2.1 | BK-GCS-PEDCO-120-EL-TB-0013 | TBE For Cathodic Protection System |  | BK-GCS-PEDCO-120-EL-TB-0013 | [8 empty] | F0Z-709352 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 14 | 0 | 0 | 3.2.4.6.14 |  | Power & Control Cables
3 | 2 | 4 | 6 | 14 | 1 | 0 | 3.2.6.14.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 14 | 1 | 1 | 3.2.4.6.14.1.1 | BK-GCS-PEDCO-120-EL-MR-0014 | PMR For Power & Control Cables |  | BK-GCS-PEDCO-120-EL-MR-0014 | BK-GCS-PEDCO-120-EL-MR-0014 | BK | GCS | PEDCO | 120 | EL | MR | 0014 | F0Z-709353 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 14 | 2 | 0 | 3.2.6.14.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 14 | 2 | 1 | 3.2.4.6.14.2.1 | BK-GCS-PEDCO-120-EL-TB-0014 | TBE For Power & Control Cables |  | BK-GCS-PEDCO-120-EL-TB-0014 | BK-GCS-PEDCO-120-EL-TB-0014 | BK | GCS | PEDCO | 120 | EL | TB | 0014 | F0Z-709354 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 15 | 0 | 0 | 3.2.4.6.15 |  | Tray/Ladder and Accessories
3 | 2 | 4 | 6 | 15 | 1 | 0 | 3.2.6.15.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 15 | 1 | 1 | 3.2.4.6.15.1.1 | BK-GCS-PEDCO-120-EL-MR-0015 | PMR For Tray/Ladder and Accessories |  | BK-GCS-PEDCO-120-EL-MR-0015 | BK-GCS-PEDCO-120-EL-MR-0015 | BK | GCS | PEDCO | 120 | EL | MR | 0015 | F0Z-709355 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 15 | 2 | 0 | 3.2.6.15.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 15 | 2 | 1 | 3.2.4.6.15.2.1 | BK-GCS-PEDCO-120-EL-TB-0015 | TBE For Tray/Ladder and Accessories |  | BK-GCS-PEDCO-120-EL-TB-0015 | BK-GCS-PEDCO-120-EL-TB-0015 | BK | GCS | PEDCO | 120 | EL | TB | 0015 | F0Z-709356 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [8 empty] | 0
3 | 2 | 4 | 6 | 16 | 0 | 0 | 3.2.4.6.16 |  | Electrical Bulk Items | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 16 | 1 | 0 | 3.2.6.16.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 16 | 1 | 1 | 3.2.4.6.16.1.1 | BK-GCS-PEDCO-120-EL-MR-0016 | PMR For Electrical Bulk Items |  | BK-GCS-PEDCO-120-EL-MR-0016 | BK-GCS-PEDCO-120-EL-MR-0016 | BK | GCS | PEDCO | 120 | EL | MR | 0016 | F0Z-709357 | IFI | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify | 0
3 | 2 | 4 | 6 | 16 | 2 | 0 | 3.2.6.16.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 16 | 2 | 1 | 3.2.4.6.16.2.1 | BK-GCS-PEDCO-120-EL-TB-0016 | TBE For Electrical Bulk Items |  | BK-GCS-PEDCO-120-EL-TB-0016 | BK-GCS-PEDCO-120-EL-TB-0016 | BK | GCS | PEDCO | 120 | EL | TB | 0016 | F0Z-709358 | IFI | [50 empty] | 0
3 | 2 | 4 | 6 | 16 | 2 | 2 | 3.2.4.6.16.2.2 |  | Telecomm UPS | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 16 | 2 | 3 | 3.2.4.6.16.2.3 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 16 | 2 | 4 | 3.2.4.6.16.2.4 | BK-GCS-PEDCO-120-EL-MR-0017 | PMR For UPS of CCTV in Desalting, Production & CS Unit |  | BK-GCS-PEDCO-120-EL-MR-0017 | [8 empty] | F0Z-709359 | IFI | [49 empty] | Moved to Field | 0
3 | 2 | 4 | 6 | 16 | 2 | 5 | 3.2.4.6.16.2.5 |  | Technical Bid Evaluation (TBE) | [12 empty] | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | [7 empty] | Modify
3 | 2 | 4 | 6 | 16 | 2 | 6 | 3.2.4.6.16.2.6 | BK-GCS-PEDCO-120-EL-TB-0017 | TBE for UPS of CCTV in Desalting, Production & CS Unit |  | BK-GCS-PEDCO-120-EL-TB-0017 | [8 empty] | F0Z-709360 | IFI | [50 empty] | 0
3 | 2 | 4 | 7 | 0 | 0 | 0 | 3.2.4.7 |  | Intercom. & Telecomm.
3 | 2 | 4 | 7 | 1 | 0 | 0 | 3.2.4.7.1 |  | CCTV System
3 | 2 | 4 | 7 | 1 | 1 | 0 | 3.2.7.1.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 1 | 1 | 1 | 3.2.4.7.1.1.1 | BK-GCS-PEDCO-120-TE-MR-0001 | PMR For CCTV System |  | BK-GCS-PEDCO-120-TE-MR-0001 | [8 empty] | - | [51 empty] | 0
3 | 2 | 4 | 7 | 1 | 2 | 0 | 3.2.7.1.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 1 | 2 | 1 | 3.2.4.7.1.2.1 | BK-GCS-PEDCO-120-TE-TB-0001 | TBE For CCTV System |  | BK-GCS-PEDCO-120-TE-TB-0001 | [8 empty] | - | [51 empty] | 0
3 | 2 | 4 | 7 | 2 | 0 | 0 | 3.2.4.7.2 |  | PAGA System
3 | 2 | 4 | 7 | 2 | 1 | 0 | 3.2.7.2.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 2 | 1 | 1 | 3.2.4.7.2.1.1 | BK-GCS-PEDCO-120-TE-MR-0002 | PMR For PAGA System |  | BK-GCS-PEDCO-120-TE-MR-0002 | BK-GCS-PEDCO-120-TE-MR-0002 | BK | GCS | PEDCO | 120 | TE | MR | 0002 | F0Z-709361 | IFI | [50 empty] | 0
3 | 2 | 4 | 7 | 2 | 2 | 0 | 3.2.7.2.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 2 | 2 | 1 | 3.2.4.7.2.2.1 | BK-GCS-PEDCO-120-TE-TB-0002 | TBE For PAGA System |  | BK-GCS-PEDCO-120-TE-TB-0002 | BK-GCS-PEDCO-120-TE-TB-0002 | BK | GCS | PEDCO | 120 | TE | TB | 0002 | F0Z-709362 | IFI | [50 empty] | 0
3 | 2 | 4 | 7 | 3 | 0 | 0 | 3.2.4.7.3 |  | PABX System
3 | 2 | 4 | 7 | 3 | 1 | 0 | 3.2.7.3.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 3 | 1 | 1 | 3.2.4.7.3.1.1 | BK-GCS-PEDCO-120-TE-MR-0003 | PMR For PABX System |  | BK-GCS-PEDCO-120-TE-MR-0003 | BK-GCS-PEDCO-120-TE-MR-0003 | BK | GCS | PEDCO | 120 | TE | MR | 0003 | F0Z-709363 | IFI | [50 empty] | 0
3 | 2 | 4 | 7 | 3 | 2 | 0 | 3.2.7.3.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 3 | 2 | 1 | 3.2.4.7.3.2.1 | BK-GCS-PEDCO-120-TE-TB-0003 | TBE For PABX System |  | BK-GCS-PEDCO-120-TE-TB-0003 | BK-GCS-PEDCO-120-TE-TB-0003 | BK | GCS | PEDCO | 120 | TE | TB | 0003 | F0Z-709364 | IFI | [50 empty] | 0
3 | 2 | 4 | 7 | 4 | 0 | 0 | 3.2.4.7.4 |  | Radio System
3 | 2 | 4 | 7 | 4 | 1 | 0 | 3.2.7.4.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 4 | 1 | 1 | 3.2.4.7.4.1.1 | BK-GCS-PEDCO-120-TE-MR-0004 | PMR For Radio System |  | BK-GCS-PEDCO-120-TE-MR-0004 | BK-GCS-PEDCO-120-TE-MR-0004 | BK | GCS | PEDCO | 120 | TE | MR | 0004 | F0Z-709365 | IFI | [50 empty] | 2021-12-20 |  |  | D01 | IFI | T-0573 | 44604 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-03038 | 44605 | 1400/11/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421706 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-MR-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0370 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-TEL-00-02394 | 44551 | 1400/09/30 | AP | [6 empty] | 1400-2294-368603 | 2022-01-17 | 1400/10/27 | 44583 | 1400/11/22 | CM | [10 empty] | D01 | IFI | T-0573 | 44604 | 1400/11/23 |  |  |  | BK-SUR-ENG-TEL-00-03038 | 44605 | 1400/11/24 | AP | [6 empty] | 1400-2294-421706 | 44614 | 1400/12/03 | 44594 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-MR-0004_D00
3 | 2 | 4 | 7 | 4 | 2 | 0 | 3.2.7.4.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 4 | 2 | 1 | 3.2.4.7.4.2.1 | BK-GCS-PEDCO-120-TE-TB-0004 | TBE For Radio System |  | BK-GCS-PEDCO-120-TE-TB-0004 | BK-GCS-PEDCO-120-TE-TB-0004 | BK | GCS | PEDCO | 120 | TE | TB | 0004 | F0Z-709366 | IFI | [50 empty] | 0
3 | 2 | 4 | 7 | 5 | 0 | 0 | 3.2.4.7.5 |  | Telecomm. Cable
3 | 2 | 4 | 7 | 5 | 1 | 0 | 3.2.7.5.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 5 | 1 | 1 | 3.2.4.7.5.1.1 | BK-GCS-PEDCO-120-TE-MR-0005 | PMR For Telecomm. Cable |  | BK-GCS-PEDCO-120-TE-MR-0005 | BK-GCS-PEDCO-120-TE-MR-0005 | BK | GCS | PEDCO | 120 | TE | MR | 0005 | F0Z-709367 | IFI | [50 empty] | 0
3 | 2 | 4 | 7 | 5 | 2 | 0 | 3.2.7.5.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 5 | 2 | 1 | 3.2.4.7.5.2.1 | BK-GCS-PEDCO-120-TE-TB-0005 | TBE For Telecomm. Cable |  | BK-GCS-PEDCO-120-TE-TB-0005 | BK-GCS-PEDCO-120-TE-TB-0005 | BK | GCS | PEDCO | 120 | TE | TB | 0005 | F0Z-709368 | IFI | [50 empty] | 0
3 | 2 | 4 | 7 | 6 | 0 | 0 | 3.2.4.7.6 |  | Telecommunication Tower
3 | 2 | 4 | 7 | 6 | 1 | 0 | 3.2.7.6.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 6 | 1 | 1 | 3.2.4.7.6.1.1 | BK-GCS-PEDCO-120-TE-MR-0006 | PMR For Telecommunication Tower |  | BK-GCS-PEDCO-120-TE-MR-0006 | BK-GCS-PEDCO-120-TE-MR-0006 | BK | GCS | PEDCO | 120 | TE | MR | 0006 | F0Z-709369 | IFI | [50 empty] | 0
3 | 2 | 4 | 7 | 6 | 2 | 0 | 3.2.7.6.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 6 | 2 | 1 | 3.2.4.7.6.2.1 | BK-GCS-PEDCO-120-TE-TB-0006 | TBE For Telecommunication Tower |  | BK-GCS-PEDCO-120-TE-TB-0006 | BK-GCS-PEDCO-120-TE-TB-0006 | BK | GCS | PEDCO | 120 | TE | TB | 0006 | F0Z-709370 | IFI | [50 empty] | 0
3 | 2 | 4 | 8 | 0 | 0 | 0 | 3.2.4.8 |  | Structure
3 | 2 | 4 | 8 | 1 | 0 | 0 | 3.2.4.8.1 |  | Steel Structure
3 | 2 | 4 | 8 | 1 | 1 | 0 | 3.2.8.1.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 8 | 1 | 1 | 1 | 3.2.4.8.1.1.1 | BK-GCS-PEDCO-120-ST-MR-0001 | PMR For Steel Structure Items |  | BK-GCS-PEDCO-120-ST-MR-0001 | BK-GCS-PEDCO-120-ST-MR-0001 | BK | GCS | PEDCO | 120 | ST | MR | 0001 | F0Z-709371 | IFI | [50 empty] | 0
3 | 2 | 4 | 8 | 1 | 2 | 0 | 3.2.8.1.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 8 | 1 | 2 | 1 | 3.2.4.8.1.2.1 | BK-GCS-PEDCO-120-ST-TB-0001 | TBE For Steel Structure Items |  | BK-GCS-PEDCO-120-ST-TB-0001 | BK-GCS-PEDCO-120-ST-TB-0001 | BK | GCS | PEDCO | 120 | ST | TB | 0001 | F0Z-709372 | IFI | [50 empty] | 0
3 | 2 | 4 | 8 | 2 | 0 | 0 | 3.2.4.8.2 |  | Anchor Bolts
3 | 2 | 4 | 8 | 2 | 1 | 0 | 3.2.8.2.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 8 | 2 | 1 | 1 | 3.2.4.8.2.1.1 | BK-GCS-PEDCO-120-ST-MR-0002 | PMR For Anchor Bolts |  | BK-GCS-PEDCO-120-ST-MR-0002 | BK-GCS-PEDCO-120-ST-MR-0002 | BK | GCS | PEDCO | 120 | ST | MR | 0002 | F0Z-709373 | IFI | [50 empty] | 0
3 | 2 | 4 | 8 | 2 | 2 | 0 | 3.2.8.2.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 8 | 2 | 2 | 1 | 3.2.4.8.2.2.1 | BK-GCS-PEDCO-120-ST-TB-0002 | TBE For Anchor Bolts |  | BK-GCS-PEDCO-120-ST-TB-0002 | BK-GCS-PEDCO-120-ST-TB-0002 | BK | GCS | PEDCO | 120 | ST | TB | 0002 | F0Z-709374 | IFI | [50 empty] | 0
3 | 2 | 4 | 8 | 3 | 0 | 0 | 3.2.4.8.3 |  | Blast Proof Doors
3 | 2 | 4 | 8 | 3 | 1 | 0 | 3.2.8.3.1 |  | Purchase Material Requisition (PMR)
3 | 2 | 4 | 8 | 3 | 1 | 1 | 3.2.4.8.3.1.1 | BK-GCS-PEDCO-120-ST-MR-0003 | PMR For Blast Proof Doors |  | BK-GCS-PEDCO-120-ST-MR-0003 | BK-GCS-PEDCO-120-ST-MR-0003 | BK | GCS | PEDCO | 120 | ST | MR | 0003 | F0Z-709375 | IFI | [50 empty] | 0
3 | 2 | 4 | 8 | 3 | 2 | 0 | 3.2.8.3.2 |  | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 8 | 3 | 2 | 1 | 3.2.4.8.3.2.1 | BK-GCS-PEDCO-120-ST-TB-0003 | TBE For Blast Proof Doors |  | BK-GCS-PEDCO-120-ST-TB-0003 | BK-GCS-PEDCO-120-ST-TB-0003 | BK | GCS | PEDCO | 120 | ST | TB | 0003 | F0Z-709376 | IFI | [50 empty] | 0
3 | 2 | 5 | 0 | 0 | 0 | 0 | 3.2.5 |  | Commissioning Engineering
3 | 2 | 5 | 0 | 1 | 0 | 0 | 3.2.5.1 |  | Procedure/Plan
3 | 2 | 5 | 0 | 1 | 0 | 1 | 3.2.5 | BK-GCS-PEDCO-120-CO-PR-0001 | Pre-Commissioning, Commissioning & Startup Procedure |  | BK-GCS-PEDCO-120-CO-PR-0001 | BK-GCS-PEDCO-120-CO-PR-0001 | BK | GCS | PEDCO | 120 | CO | PR | 0001 | F0Z-709377 | AFC | [50 empty] | 0
3 | 2 | 6 | 0 | 0 | 0 | 0 | 3.2.6 |  | Field Engineering
3 | 2 | 6 | 0 | 1 | 0 | 0 | 3.2.6.1 |  | Query
3 | 2 | 6 | 0 | 1 | 0 | 1 | 3.2.6.1.1 | BK-GCS-PEDCO-120-GE-TQ-0001 | Technical/Site Queries |  | BK-GCS-PEDCO-120-GE-TQ-0001 | BK-GCS-PEDCO-120-GE-TQ-0001 | BK | GCS | PEDCO | 120 | GE | TQ | 0001 | F0Z-709378 | AFC | [50 empty] | 0
3 | 2 | 6 | 0 | 2 | 0 | 0 | 3.2.6.2 |  | Dossier
3 | 2 | 6 | 0 | 2 | 0 | 1 | 3.2.6 | BK-GCS-PEDCO-120-GE-DO-0001 | As-Built Document Booklets |  | BK-GCS-PEDCO-120-GE-DO-0001 | BK-GCS-PEDCO-120-GE-DO-0001 | BK | GCS | PEDCO | 120 | GE | DO | 0001 | F0Z-709379 | AB-A | [50 empty] | 0
3 | 2 | 7 | 0 | 0 | 0 | 0 | 3.2.7 |  | Engineering Final Documentation
3 | 2 | 7 | 0 | 1 | 0 | 0 | 3.2.7.1 |  | Manual
3 | 2 | 7 | 0 | 1 | 0 | 1 | 3.2.7.1.1 | BK-GCS-PEDCO-120-GE-ML-0001 | Operating Manual |  | BK-GCS-PEDCO-120-GE-ML-0001 | BK-GCS-PEDCO-120-GE-ML-0001 | BK | GCS | PEDCO | 120 | GE | ML | 0001 | F0Z-709380 | IFI | [50 empty] | 0
3 | 2 | 7 | 0 | 2 | 0 | 0 | 3.2.7.2 |  | Dossier
3 | 2 | 7 | 0 | 2 | 0 | 1 | 3 | BK-GCS-PEDCO-120-GE-DO-0001 | As-Built Document Booklets |  | BK-GCS-PEDCO-120-GE-DO-0001 | [8 empty] | F0Z-709379 | [51 empty] | 0
3 | 2 | 7 | 0 | 2 | 0 | 2 | 3 | BK-GCS-PEDCO-120-GE-DO-0002 | Final Engineering Dossier |  | BK-GCS-PEDCO-120-GE-DO-0002 | BK-GCS-PEDCO-120-GE-DO-0002 | BK | GCS | PEDCO | 120 | GE | DO | 0002 | F0Z-709381 | AB-A | [50 empty] | 0
0
0
Formulas:
Issue+14 = [PEDCO Comment Date (Farsi)]+14
Issue+14 = [Issue Date]+14
NISOC Date = MAX([NISOC Comment Date],[D06])
NISOC Date = MAX([NISOC Comment Date],[NISOC Comment Date])
Email Date = MAX([EMAIL DATE],[Last POI])
Email Date = MAX([EMAIL DATE],[EMAIL DATE])
Status = [Last POI]

## NISOC Delay-DOCS (hidden)
|  |  |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 |  | 33 | 34 | 35 | 36 | 37 | 38 | 39 |  | 40 | 41 | 42 | 43 | 44 | 45 | 46 |  | 47 | 48 | 49 | 50 | 51 | 52 | 53 |  | 54 | 55 | 56 | 57 | 58 | 59 | 60
شماره (ID A s) | نام بسته كاري | نام فعالیت اصلی | Doc code | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Note | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Note | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Note | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Note | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Note | 6 | 6 | 6 | 6 | 6 | 6 | 6
|  |  |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | Total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | Total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay
P12-EPC-E1000 | ايستگاه گاز | Endorsement Report For Basic Design & Scope of Work | BK-GNRAL-PEDCO-000-PM-RT-0001 | IFC | 2021-08-14 | 2021-08-28 | 2021-09-07 | 14 | 24 | 24 |  | AFD | 2021-10-03 | 2021-10-06 | 2021-10-26 | 3 | 20 | 23 | [9 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Endorsement Report For Basic Design & Scope of Work
P12-EPC-E1570 | ايستگاه گاز | Process Flow Diagram (PFD) | BK-GCS-PEDCO-120-PR-PF-0001 | IFC | 2021-08-28 | 2021-09-01 | 2021-09-06 | 4 | 9 | 9 |  | IFA | 2021-10-31 | 2021-11-28 | 2021-11-14 | 28 | -14 | 14 | 14 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFA | 2021-12-14 | 2021-12-30 | 2022-01-02 | 16 | 3 | 19 |  | IFA | 2022-01-22 | 2022-02-12 | 2022-02-22 | 21 | 10 | 31 |  | IFA | 2022-03-26 | 2022-04-21 | 2022-04-30 | 26 | 9 | 35 |  | IFA |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Process Flow Diagram (PFD)
P12-EPC-E1540 | ايستگاه گاز | Process Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-PR-DT-0030 | IFC | 2021-11-21 | 2021-11-18 | 2021-11-27 | -3 | 6 | 6 |  | IFA | 2022-01-15 | 2022-01-22 | 2022-01-29 | 7 | 7 | 14 |  | IFA | 2022-04-09 | 2022-05-04 | 2022-05-08 | 25 | 4 | 29 |  | IFA | 2022-08-20 | 2022-09-19 | 2022-09-20 | 30 | 1 | 31 |  | IFA | [7 empty] | AFC |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Process Data Sheets For Gas Compressors Packages
P12-EPC-E2480 | ايستگاه گاز | Mechanical Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-ME-DT-0031 | IFC | 2021-09-26 | 2021-10-07 | 2021-10-11 | 11 | 15 | 15 |  | IFA | 2021-10-31 | 2021-11-04 | 2021-11-08 | 4 | 4 | 8 |  | IFA | 2021-11-28 | 2021-12-14 | 2021-12-20 | 16 | 6 | 22 |  | IFA | 2022-01-26 | 2022-02-22 | 2022-02-22 | 27 | 0 | 27 |  | IFA | 2022-03-19 | 2022-03-23 | 2022-03-26 | 4 | 3 | 7 |  | AFC | 2022-05-04 | 2022-04-28 | 2022-05-01 | -6 | 3 | -3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mechanical Data Sheets For Gas Compressors Packages
P12-EPC-E7980 | ايستگاه گاز | TBE For Gas Compressors | BK-GCS-PEDCO-120-ME-TB-0001 | IFI | 2022-02-16 | 2022-02-23 | 2022-02-27 | 7 | 11 | 11 |  | IFI | 2022-03-19 | 2022-05-01 | 2022-05-07 | 43 | 6 | 49 |  | IFI | 2022-06-25 | 2022-06-22 | 2022-06-27 | -3 | 5 | 2 | 25 روز هست که ویرایش جدید تولید نشده است | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TBE For Gas Compressors
P12-EPC-E7970 | ايستگاه گاز | PMR For Gas Compressors | BK-GCS-PEDCO-120-ME-MR-0001 | IFC | 2021-12-12 | 2021-12-13 | 2021-12-15 | 1 | 3 | 3 |  | IFI | 2022-01-18 | 2021-01-15 | 2022-01-30 | -368 | 380 | 12 | تاریخ کامنت نیسوک یک سال قبل از ارسال است | IFI | 2022-02-27 | 2022-03-01 | 2022-03-05 | 2 | 4 | 6 |  | IFI | 2022-06-20 | 2022-07-28 | 2022-08-06 | 38 | 9 | 47 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PMR For Gas Compressors
P01-EPC-E1060 | چاه شماره 18 | Process Flow Diagram - W018S | BK-W018S-PEDCO-110-PR-PF-0001 | IFC | 2021-08-18 | 2021-08-30 | 2021-09-07 | 12 | 20 | 20 |  | IFC | 2021-11-16 | 2022-06-02 | 2022-06-06 | 198 | 4 | 202 |  | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 |  | 0 | [7 empty] | 0 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Process Flow Diagram - W018S
P01-EPC-E1370 | چاه شماره 18 | Plot Plan Drawing - W018S | BK-W018S-PEDCO-110-PI-PY-0001 | IFC | 2021-09-05 | 2021-09-26 | 2021-09-29 | 21 | 24 | 24 |  | IFA | 2021-11-29 | 2021-12-08 | 2021-12-12 | 9 | 4 | 13 |  | IFA | 2022-02-14 | 2022-02-26 | 2022-03-05 | 12 | 7 | 19 |  | 0 | [7 empty] | 0 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plot Plan Drawing - W018S
P01-EPC-E1860 | چاه شماره 18 | Specification For WHCP/HPU-W018S | BK-SSGRL-PEDCO-110-IN-SP-0001 | IFC | 2021-08-22 | 2021-09-18 | 2021-09-14 | 27 | 23 | 23 | 4 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFA | 2021-10-24 | 2021-12-30 | 2022-01-02 | 67 | 3 | 70 |  | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 |  | AFD | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 |  | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Specification For WHCP/HPU-W018S
P01-EPC-E2470 | چاه شماره 18 | Rough Grading Plans -W018S | BK-W018S-PEDCO-110-CV-DW-0001 | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | -4 | -4 |  | IFC | 2021-11-13 | 2021-11-02 | 2021-11-06 | -11 | 4 | -7 |  | IFA | 2022-01-29 | 2022-01-20 | 2022-01-22 | -9 | 2 | -7 |  | IFA | 2022-03-12 | 2022-03-02 | 2022-03-05 | -10 | 3 | -7 |  | AFC | 2022-03-27 | 2022-03-16 | 2022-03-27 | -11 | 11 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rough Grading Plans -W018S
P01-EPC-E1070 | چاه شماره 18 | P&ID - W018S | BK-W018S-PEDCO-110-PR-PI-0001 | IFC | 2021-08-23 | 2021-08-30 | 2021-09-06 | 7 | 14 | 14 |  | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 |  | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 |  | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 |  | IFA | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P&ID - W018S
P01-EPC-E1300 | چاه شماره 18 | Piping Material Specification-W018S | BK-GNRAL-PEDCO-000-PI-SP-0017 | IFC | 2021-09-07 | 2021-09-12 | 2021-09-14 | 5 | 7 | 7 |  | IFA | 2021-10-18 | 2021-12-04 | 2021-11-08 | 47 | -26 | 21 | 26 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | AFD | 2021-12-29 | 0 | 0 | -44559 | 0 | -44559 | تایید روی AFD از کارفرما دریافت نشده است | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Piping Material Specification-W018S
P01-EPC-E1870 | چاه شماره 18 | Data Sheets For WHCP/HPU - Wellheads-W018S | BK-SSGRL-PEDCO-110-IN-DT-0001 | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 15 | 15 |  | IFA | 2021-11-23 | 2021-11-21 | 2021-11-27 | -2 | 6 | 4 |  | IFA | 2022-01-04 | 2022-01-06 | 2022-01-08 | 2 | 2 | 4 |  | IFA | 2022-07-02 | 2022-08-28 | 2022-08-25 | 57 | -3 | 54 |  | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Data Sheets For WHCP/HPU - Wellheads-W018S
P01-EPC-E2460 | چاه شماره 18 | Civil and Structural drawings - W018S | BK-W018S-PEDCO-110-CV-PY-0002 | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | -4 | -4 |  | IFA | 2022-01-18 | 2022-01-08 | 2022-01-11 | -10 | 3 | -7 |  | AFC | 2022-11-22 | 0 | 0 | -44887 | 0 | -44887 | تایید روی AFC از کارفرما دریافت نشده است | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Civil and Structural drawings - W018S
P01-EPC-E2450 | چاه شماره 18 | General Civil Layout - W018S | BK-W018S-PEDCO-110-CV-PY-0001 | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | -4 | -4 |  | IFA | 2021-09-11 | 2021-08-29 | 2021-09-04 | -13 | 6 | -7 |  | IFA | 2021-09-27 | 2021-09-18 | 2021-09-18 | -9 | 0 | -9 |  | IFA | 2021-11-06 | 2021-10-29 | 2021-11-02 | -8 | 4 | -4 |  | AFC | 2021-12-04 | 2021-11-23 | 2021-11-27 | -11 | 4 | -7 |  | AFC | 2022-01-10 | 2021-12-30 | 2022-01-02 | -11 | 3 | -8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | General Civil Layout - W018S
P01-EPC-E1810 | چاه شماره 18 | Pipeline Corrosion Study & Material Selection Report-W018S | BK-SSGRL-PEDCO-110-PL-RT-0001 | IFC | 2021-11-10 | 2021-11-16 | 2021-11-21 | 6 | 11 | 11 |  | IFA | 2021-12-18 | 0 | 0 | -44548 | 0 | -44548 | تاریخی بابت کامنت نیسوک ثبت نشده است (ویرایش بعدی ارسال شده است) | IFA | 2022-03-14 | 2022-03-16 | 2022-04-01 | 2 | 16 | 18 | [9 empty] | AFD | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pipeline Corrosion Study & Material Selection Report-W018S
P01-EPC-E3590 | چاه شماره 18 | PMR For WHCP/HPU - W018S | BK-W018S-PEDCO-110-IN-MR-0001 | IFI | 2021-11-29 | 2021-12-17 | 2021-12-07 | 18 | 8 | 8 | 10 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFI | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 |  | IFI | 2022-07-04 | 2022-08-14 | 2022-08-16 | 41 | 2 | 43 |  | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PMR For WHCP/HPU - W018S
P01-EPC-E3560 | چاه شماره 18 | PMR For Line pipes - W018S | BK-W018S-PEDCO-110-PL-MR-0001 | IFI | 2021-12-20 | 2021-12-13 | 2021-12-15 | -7 | -5 | -5 |  | IFI | [15 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PMR For Line pipes - W018S
P02-EPC-E1060 | چاه شماره 28 | Process Flow Diagram - W028 | BK-W028-PEDCO-110-PR-PF-0001 | IFC | 2021-08-28 | 2021-08-30 | 2021-09-06 | 2 | 9 | 9 |  | IFC | 2021-11-16 | 2022-06-02 | 2022-06-06 | 198 | 4 | 202 |  | IFA | 2022-08-24 | 2022-09-24 | 2022-10-02 | 31 | 8 | 39 |  | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Process Flow Diagram - W028
P02-EPC-E1380 | چاه شماره 28 | Plot Plan Drawing - W028 | BK-W028-PEDCO-110-PI-DW-0001 | IFC | 2022-02-16 | 2022-04-16 | 2022-04-25 | 59 | 68 | 68 |  | 0 | [6 empty] | نسخه جدیدی از مدرک از فرودین ماه ارسال نشده است | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 |  | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plot Plan Drawing - W028
P02-EPC-E1860 | چاه شماره 28 | Specification For WHCP/HPU - W028 | BK-SSGRL-PEDCO-110-IN-SP-0001 | IFC | 2021-08-22 | 2021-09-18 | 2021-09-14 | 27 | 23 | 23 | 4 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFA | 2021-10-24 | 2021-12-30 | 2022-01-02 | 67 | 3 | 70 |  | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 |  | AFD | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Specification For WHCP/HPU - W028
P02-EPC-E2460 | چاه شماره 28 | General Civil Layout -W028 | BK-W028-PEDCO-110-CV-PY-0001 | IFC | 2021-11-02 | 2021-10-25 | 2021-11-22 | -8 | 20 | 20 |  | IFA | 2022-03-26 | 2022-03-15 | 2022-03-25 | -11 | 10 | -1 |  | IFA | 2022-06-15 | 2022-06-08 | 2022-06-11 | -7 | 3 | -4 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | General Civil Layout -W028
P02-EPC-E2470 | چاه شماره 28 | Civil and Structural drawings -W028 | BK-W028-PEDCO-110-CV-PY-0002 | IFC | 2021-11-02 | 0 | 0 | -44502 | -44502 | -44502 | تاریخی بابت کامنت نیسوک ثبت نشده است (ویرایش بعدی ارسال شده است) | IFA | 2021-12-04 | 2021-11-29 | 2021-12-01 | -5 | 2 | -3 |  | IFA | 2022-03-28 | 2022-03-30 | 2022-04-03 | 2 | 4 | 6 |  | IFA | 2022-06-21 | 2022-06-14 | 2022-06-15 | -7 | 1 | -6 |  | IFA | 2022-07-02 | 2022-06-25 | 2022-06-29 | -7 | 4 | -3 |  | IFA | 2022-07-31 | 2022-07-28 | 2022-08-01 | -3 | 4 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Civil and Structural drawings -W028
P02-EPC-E2480 | چاه شماره 28 | Rough Grading Plans -W028 | BK-W028-PEDCO-110-CV-DW-0001 | IFC | 2021-10-25 | 2021-10-16 | 2021-10-18 | -9 | -7 | -7 |  | IFA | 2022-02-20 | 2022-02-19 | 2022-02-12 | -1 | -7 | -8 |  | IFA | 2022-03-28 | 2022-03-30 | 2022-04-03 | 2 | 4 | 6 |  | AFC | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 |  | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rough Grading Plans -W028
P02-EPC-E3530 | چاه شماره 28 | PMR For Line Pipes - W028 | BK-W028-PEDCO-110-PL-MR-0001 | IFI | 2021-12-20 | 2021-12-13 | 2021-12-15 | -7 | -5 | -5 |  | IFI | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PMR For Line Pipes - W028
P02-EPC-E1070 | چاه شماره 28 | P&ID - W028 | BK-W028-PEDCO-110-PR-PI-0001 | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 3 | 3 |  | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 |  | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 |  | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 |  | IFA | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P&ID - W028
P02-EPC-E1880 | چاه شماره 28 | Data Sheets For WHCP/HPU - Wellheads - W028 | BK-SSGRL-PEDCO-110-IN-DT-0001 | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 15 | 15 |  | IFA | 2021-11-23 | 2021-11-21 | 2021-11-27 | -2 | 6 | 4 |  | IFA | 2022-01-04 | 2022-01-06 | 2022-01-08 | 2 | 2 | 4 |  | IFA | 2022-07-02 | 2022-08-28 | 2022-08-25 | 57 | -3 | 54 |  | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Data Sheets For WHCP/HPU - Wellheads - W028
P02-EPC-E1820 | چاه شماره 28 | Pipeline Corrosion Study & Material Selection Report - W028 | BK-SSGRL-PEDCO-110-PL-RT-0001 | IFC | 2021-11-10 | 2021-11-16 | 2021-11-21 | 6 | 11 | 11 |  | IFA | 2021-12-18 | 0 | 0 | -44548 | 0 | -44548 | تاریخی بابت کامنت نیسوک ثبت نشده است (ویرایش بعدی ارسال شده است) | IFA | 2022-03-14 | 2022-03-16 | 2022-04-01 | 2 | 16 | 18 |  | AFD | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pipeline Corrosion Study & Material Selection Report - W028
P02-EPC-E3590 | چاه شماره 28 | PMR For WHCP/HPU - W028 | BK-W028-PEDCO-110-IN-MR-0001 | IFI | 2021-11-29 | 2021-12-17 | 2021-12-07 | 18 | 8 | 8 | 10 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFI | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 | [40 empty] | PMR For WHCP/HPU - W028
P02-EPC-E1180 | چاه شماره 28 | Piping Material Specification - W028 | BK-SSGRL-PEDCO-110-PI-SP-0001 | IFC | 2021-12-12 | 2021-12-22 | 2021-12-26 | 10 | 14 | 14 |  | IFA | 2022-04-13 | 2022-05-29 | 2022-05-30 | 46 | 1 | 47 | تاریخی بابت کامنت نیسوک ثبت نشده است (50 روز گذشته است) | [39 empty] | Piping Material Specification - W028
P07-EPC-E2580 | چاه شماره 14 | General Civil Layout - BK14 | BK-BK14-PEDCO-110-CV-PY-0001 | IFC | 2022-10-03 | 2022-09-26 | 2022-10-02 | -7 | -1 | -1 |  | IFA | 2022-10-25 | 2022-10-29 | 2022-10-30 | 4 | 1 | 5 | [40 empty] | General Civil Layout - BK14

## Gas (hidden)
Activity ID | P | A | BK Document Number | Total Float | Activity Name | Original Duration | Start | Finish | Budgeted Nonlabor Units | Actual Start | Actual Finish | % |  | Actual Start | Actual Finish | doc No.
P12-EPC-E1000 | P12-EPC-E1000P | P12-EPC-E1000A | BK-GNRAL-PEDCO-000-PM-RT-0001 | 0 | Endorsement Report For Basic Design & Scope of Work | 30 | 2021-06-23 | 2021-07-22 | 98017 | 2021-07-31 | 2021-07-31 | 100% | BK-GNRAL-PEDCO-000-PM-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2022-12-20 | BK-GNRAL-PEDCO-000-PM-RT-0001
P12-EPC-E1570 | P12-EPC-E1570P | P12-EPC-E1570A | BK-GCS-PEDCO-120-PR-PF-0001 | 0 | Process Flow Diagram (PFD) | 54 | 2021-07-04 | 2021-08-26 | 2203 | 2021-08-14 | 2021-11-30 | 80% | BK-GCS-PEDCO-120-PR-PF-0001Process Flow Diagram (PFD) | 2021-08-14 | 2022-12-20 | BK-GCS-PEDCO-120-PR-PF-0001
P12-EPC-E1050 | P12-EPC-E1050P | P12-EPC-E1050A | BK-GNRAL-PEDCO-000-PR-DC-0001 | 0 | Process Design Criteria | 35 | 2021-07-23 | 2021-08-26 | 103 | 2021-07-27 | 2021-07-27 | 80% | BK-GNRAL-PEDCO-000-PR-DC-0001Process Design Criteria | 2021-07-27 | 2022-01-01 | BK-GNRAL-PEDCO-000-PR-DC-0001
P12-EPC-E1540 | P12-EPC-E1540P | P12-EPC-E1540A | BK-GCS-PEDCO-120-PR-DT-0030 | 0 | Process Data Sheets For Gas Compressors Packages | 44 | 2021-07-31 | 2021-09-12 | 2757 | 2021-11-07 | 2022-03-26 | 60% | BK-GCS-PEDCO-120-PR-DT-0030Process Data Sheets For Gas Compressors Packages | 2021-11-07 | 2022-12-20 | BK-GCS-PEDCO-120-PR-DT-0030
P12-EPC-P1000 | P12-EPC-P1000P | P12-EPC-P1000A |  | 0 | Tendering & Selection For Gas Compressors | 60 | 2021-08-11 | 2021-10-09 | 555269 | 1400/12/07 |  | 0% | Tendering & Selection For Gas Compressors | 2022-02-26 | 2022-07-22 | 0
P12-EPC-E2480 | P12-EPC-E2480P | P12-EPC-E2480A | BK-GCS-PEDCO-120-ME-DT-0031 | 0 | Mechanical Data Sheets For Gas Compressors Packages | 49 | 2021-08-12 | 2021-09-29 | 1829 | 2021-09-12 | 2021-09-12 | 80% | BK-GCS-PEDCO-120-ME-DT-0031Mechanical Data Sheets For Gas Compressors Packages | 2021-09-12 | 2022-07-22 | BK-GCS-PEDCO-120-ME-DT-0031
P12-EPC-E7980 | P12-EPC-E7980P | P12-EPC-E7980A | BK-GCS-PEDCO-120-ME-TB-0001 | 0 | TBE For Gas Compressors | 45 | 2021-08-16 | 2021-09-29 | 2638 | 2022-02-02 | 2022-03-05 | 0% | BK-GCS-PEDCO-120-ME-TB-0001TBE For Gas Compressors | 2022-02-02 | 2022-07-22 | BK-GCS-PEDCO-120-ME-TB-0001
P12-EPC-E7970 | P12-EPC-E7970P | P12-EPC-E7970A | BK-GCS-PEDCO-120-ME-MR-0001 | 0 | PMR For Gas Compressors | 10 | 2021-09-03 | 2021-09-13 | 1759 | 2021-11-28 | 2022-02-13 | 100% | BK-GCS-PEDCO-120-ME-MR-0001PMR For Gas Compressors | 2021-11-28 | 2022-07-22 | BK-GCS-PEDCO-120-ME-MR-0001
P12-EPC-P1010 | P12-EPC-P1010P | P12-EPC-P1010A |  | 0 | Contract Effectiveness / PO For Gas Compressors | 30 | 2021-10-10 | 2021-11-08 | 832903 |  |  | 0% | Contract Effectiveness / PO For Gas Compressors
P12-EPC-P1020 | P12-EPC-P1020P | P12-EPC-P1020A |  | 0 | Manufacturing / Fabrication / Supply For Gas Compressors | 420 | 2021-11-09 | 2023-01-02 | 12493543 |  |  | 0% | Manufacturing / Fabrication / Supply For Gas Compressors
Formulas:
Actual Start = VLOOKUP([BK Document Number],'S&F'!B:D,3,0)
Actual Finish = VLOOKUP([BK Document Number],'S&F'!B:E,4,0)

## Well-18 (hidden)
Activity ID | P | A | BK Document Number | Total Float | Activity Name | Original Duration | Start | Finish | Budgeted Nonlabor Units | Actual Start | Actual Finish | % |  | Actual Start | Actual Finish | doc No. | 2022-05-25
P01-EPC-E1000 | P01-EPC-E1000P | P01-EPC-E1000A | BK-GNRAL-PEDCO-000-PM-RT-0001 | 0 | Endorsement Report For Basic Design & Scope of Work -W018S | 30 | 2021-06-23 | 2021-07-22 | 1131 | 2021-07-31 | 2021-07-31 | 100% | BK-GNRAL-PEDCO-000-PM-RT-0001Endorsement Report For Basic Design & Scope of Work -W018S | 2021-07-31 | 2022-12-20 | BK-GNRAL-PEDCO-000-PM-RT-0001
P01-EPC-E1060 | P01-EPC-E1060P | P01-EPC-E1060A | BK-W018S-PEDCO-110-PR-PF-0001 | 39 | Process Flow Diagram - W018S | 45 | 2021-07-23 | 2021-09-05 | 193 | 2021-11-02 | 0 | 60% | BK-W018S-PEDCO-110-PR-PF-0001Process Flow Diagram - W018S | 2021-11-02 | 2022-12-20 | BK-W018S-PEDCO-110-PR-PF-0001
P01-EPC-E1370 | P01-EPC-E1370P | P01-EPC-E1370A | BK-W018S-PEDCO-110-PI-PY-0001 | 14 | Plot Plan Drawing - W018S | 40 | 2021-07-23 | 2021-08-31 | 172 | 2021-08-22 | 2022-01-31 | 80% | BK-W018S-PEDCO-110-PI-PY-0001Plot Plan Drawing - W018S | 2021-08-22 | 2022-12-20 | BK-W018S-PEDCO-110-PI-PY-0001
P01-EPC-E1860 | P01-EPC-E1860P | P01-EPC-E1860A | BK-SSGRL-PEDCO-110-IN-SP-0001 | 22 | Specification For WHCP/HPU-W018S | 38 | 2021-07-23 | 2021-08-29 | 147 | 2021-08-08 | 2021-08-08 | 80% | BK-SSGRL-PEDCO-110-IN-SP-0001Specification For WHCP/HPU-W018S | 2021-08-08 | 2022-03-27 | BK-SSGRL-PEDCO-110-IN-SP-0001
P01-EPC-E2470 | P01-EPC-E2470P | P01-EPC-E2470A | BK-W018S-PEDCO-110-CV-DW-0001 | 9 | Rough Grading Plans -W018S | 40 | 2021-07-28 | 2021-09-05 | 232 | 2021-10-30 | 2021-07-28 | 60% | BK-W018S-PEDCO-110-CV-DW-0001Rough Grading Plans -W018S | 2021-10-30 | 2022-03-13 | BK-W018S-PEDCO-110-CV-DW-0001
P01-EPC-E1070 | P01-EPC-E1070P | P01-EPC-E1070A | BK-W018S-PEDCO-110-PR-PI-0001 | 39 | P&ID - W018S | 45 | 2021-08-02 | 2021-09-15 | 103 | 2021-11-01 | 2021-12-15 | 80% | BK-W018S-PEDCO-110-PR-PI-0001P&ID - W018S | 2021-11-01 | 2022-12-20 | BK-W018S-PEDCO-110-PR-PI-0001
P01-EPC-E1300 | P01-EPC-E1300P | P01-EPC-E1300A | BK-GNRAL-PEDCO-000-PI-SP-0017 | 153 | Piping Material Specification-W018S | 30 | 2021-08-02 | 2021-08-31 | 84 | 2021-08-24 | 2021-08-24 | 100% | BK-GNRAL-PEDCO-000-PI-SP-0017Piping Material Specification-W018S | 2021-08-24 | 2021-12-15 | BK-GNRAL-PEDCO-000-PI-SP-0017
P01-EPC-E1870 | P01-EPC-E1870P | P01-EPC-E1870A | BK-SSGRL-PEDCO-110-IN-DT-0001 | 22 | Data Sheets For WHCP/HPU - Wellheads-W018S | 30 | 2021-08-02 | 2021-08-31 | 28 | 2021-08-22 | 2021-12-21 | 80% | BK-SSGRL-PEDCO-110-IN-DT-0001Data Sheets For WHCP/HPU - Wellheads-W018S | 2021-08-22 | 2022-12-20 | BK-SSGRL-PEDCO-110-IN-DT-0001
P01-EPC-E2460 | P01-EPC-E2460P | P01-EPC-E2460A | BK-W018S-PEDCO-110-CV-PY-0002 | 16 | Civil and Structural drawings - W018S | 40 | 2021-08-07 | 2021-09-15 | 358 | 2021-07-28 | 2021-07-28 | 60% | BK-W018S-PEDCO-110-CV-PY-0002Civil and Structural drawings - W018S | 2021-07-28 | 2022-11-08 | BK-W018S-PEDCO-110-CV-PY-0002
P01-EPC-E2450 | P01-EPC-E2450P | P01-EPC-E2450A | BK-W018S-PEDCO-110-CV-PY-0001 | 14 | General Civil Layout - W018S | 20 | 2021-08-12 | 2021-08-31 | 358 | 2021-07-28 | 2021-07-28 | 100% | BK-W018S-PEDCO-110-CV-PY-0001General Civil Layout - W018S | 2021-07-28 | 2021-12-27 | BK-W018S-PEDCO-110-CV-PY-0001
P01-EPC-E1810 | P01-EPC-E1810P | P01-EPC-E1810A | BK-SSGRL-PEDCO-110-PL-RT-0001 | 192 | Pipeline Corrosion Study & Material Selection Report-W018S | 44 | 2021-08-22 | 2021-10-04 | 59 | 2021-10-27 | 2022-02-28 | 0% | BK-SSGRL-PEDCO-110-PL-RT-0001Pipeline Corrosion Study & Material Selection Report-W018S | 2021-10-27 | 2022-10-19 | BK-SSGRL-PEDCO-110-PL-RT-0001
P01-EPC-C1060 | P01-EPC-C1060P | P01-EPC-C1060A |  | 9 | Site Preparation W018S | 10 | 2021-08-27 | 2021-09-05 | 9358 | 1400/05/15 | 1400/06/25 | 92.96% | Site Preparation W018S | 2021-08-06 | 2021-09-16 | 0
P01-EPC-E3590 | P01-EPC-E3590P | P01-EPC-E3590A | BK-W018S-PEDCO-110-IN-MR-0001 | 22 | PMR For WHCP/HPU - W018S | 7 | 2021-08-30 | 2021-09-05 | 27 | 2021-11-15 | 2022-01-16 | 100% | BK-W018S-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W018S | 2021-11-15 | 2022-12-20 | BK-W018S-PEDCO-110-IN-MR-0001
P01-EPC-E3560 | P01-EPC-E3560P | P01-EPC-E3560A | BK-W018S-PEDCO-110-PL-MR-0001 | 40 | PMR For Line pipes - W018S | 5 | 2021-10-06 | 2021-10-10 | 7 | 0 | 0 | 100% | BK-W018S-PEDCO-110-PL-MR-0001PMR For Line pipes - W018S | 2021-12-06 | 2022-12-20 | BK-W018S-PEDCO-110-PL-MR-0001
P01-EPC-P1670 | P01-EPC-P1670P | P01-EPC-P1670A |  | 22 | Tendering & Selection- W018S-WHCP | 10 | 2021-09-23 | 2021-10-02 | 1814 | 1400/12/24 | #N/A | 0% | Tendering & Selection- W018S-WHCP | 2022-03-15 | 2022-05-25 | 0
P01-EPC-P1550 | P01-EPC-P1550P | P01-EPC-P1550A |  | 26 | Tendering & Selection- W018S- Line pipe | 7 | 2021-10-01 | 2021-10-07 | 7555 | #N/A | #N/A | 0% | Tendering & Selection- W018S- Line pipe |  |  | 0
P01-EPC-P1680 | P01-EPC-P1680P | P01-EPC-P1680A |  | 22 | Contract Effectiveness / PO- W018S- WHCP | 5 | 2021-10-03 | 2021-10-07 | 2722 | #N/A | #N/A | 0% | Contract Effectiveness / PO- W018S- WHCP | 2022-05-29 | 2022-06-12 | 0
P01-EPC-P1560 | P01-EPC-P1560P | P01-EPC-P1560A |  | 26 | Contract Effectiveness / PO- W018S-Line pipe | 5 | 2021-10-08 | 2021-10-12 | 11332 | #N/A | #N/A | 0% | Contract Effectiveness / PO- W018S-Line pipe |  |  | 0
P01-EPC-P1690 | P01-EPC-P1690P | P01-EPC-P1690A |  | 22 | Manufacturing / Fabrication / Supply- W018S-WHCP | 90 | 2021-10-08 | 2022-01-05 | 22680 | #N/A | #N/A | 0% | Manufacturing / Fabrication / Supply- W018S-WHCP | 2022-06-13 |  | 0
P01-EPC-C1330 | P01-EPC-C1330P | P01-EPC-C1330A |  | 94 | Construction of Right of Way- W018S | 20 | 2021-10-09 | 2021-10-28 | 23368 |  |  | 0% | Construction of Right of Way- W018S |  |  | 0
P01-EPC-P1570 | P01-EPC-P1570P | P01-EPC-P1570A |  | 26 | Manufacturing / Fabrication / Supply- W018S-Line pipe | 70 | 2021-10-13 | 2021-12-21 | 94436 | #N/A | #N/A | 0% | Manufacturing / Fabrication / Supply- W018S-Line pipe |  |  | 0
P01-EPC-C1340 | P01-EPC-C1340P | P01-EPC-C1340A |  | 57 | Construction of Steel Works(Wellhead Facilities)- W018S | 15 | 2021-12-05 | 2021-12-19 | 5297 |  |  | 0% | Construction of Steel Works(Wellhead Facilities)- W018S |  |  | 0
P01-EPC-P1580 | P01-EPC-P1580P | P01-EPC-P1580A |  | 26 | Final Inspection- W018S-Line pipe | 7 | 2021-12-22 | 2021-12-28 | 18887 | #N/A | #N/A | 0% | Final Inspection- W018S-Line pipe |  |  | 0
P01-EPC-C1150 | P01-EPC-C1150P | P01-EPC-C1150A |  | 12 | Supply & Installation sealling Layer of Mud pit- W018S | 12 | 2021-09-20 | 2021-09-27 | 34529 | 1400/05/29 | 1400/09/18 |  |  | 2021-09-20 | 2021-12-09 | 0
P01-EPC-C1330 | P01-EPC-C1330P | P01-EPC-C1330A |  | 94 | Right of Way-W018S | 94 | 2021-10-09 | 2021-10-28 | 23368 | [6 empty] | 0
P01-EPC-C1350 | P01-EPC-C1350P | P01-EPC-C1350A |  | 57 | Construction & Installation of Shelter for Wellhead Control Panel-W018S | 57 | 2021-12-20 | 2022-01-03 | 1558 | [6 empty] | 0
Formulas:
Actual Start = VLOOKUP([BK Document Number],'S&F'!$B:$E,3,0)
Actual Finish = VLOOKUP([BK Document Number],'S&F'!$B:$E,4,0)

## Well-28 (hidden)
Activity ID | P | A | BK Document Number | Total Float | Activity Name | Original Duration | Start | Finish | Budgeted Nonlabor Units | Actual Start | Actual Finish | % |  | Actual Start | Actual Finish | doc No. | 2022-05-25
P02-EPC-C1170 | P02-EPC-C1170P | P02-EPC-C1170A |  | 0 | Site Preparation W028 | 20 | 2021-08-17 | 2021-09-05 | 104403 | 1400/06/24 |  | 53% |  | 2021-09-15 |  | 0
P02-EPC-E1060 | P02-EPC-E1060P | P02-EPC-E1060A | BK-W028-PEDCO-110-PR-PF-0001 | 44 | Process Flow Diagram - W028 | 40 | 2021-07-23 | 2021-08-31 | 192 | 2021-11-02 | 0 | 60% | BK-W028-PEDCO-110-PR-PF-0001Process Flow Diagram - W028 | 2021-11-02 | 2022-12-20 | BK-W028-PEDCO-110-PR-PF-0001
P02-EPC-E1070 | P02-EPC-E1070P | P02-EPC-E1070A | BK-W028-PEDCO-110-PR-PI-0001 | 44 | P&ID - W028 | 40 | 2021-08-02 | 2021-09-10 | 102 | 2021-11-01 | 2021-12-15 | 80% | BK-W028-PEDCO-110-PR-PI-0001P&ID - W028 | 2021-11-01 | 2022-12-20 | BK-W028-PEDCO-110-PR-PI-0001
P02-EPC-E1180 | P02-EPC-E1180P | P02-EPC-E1180A | BK-SSGRL-PEDCO-110-PI-SP-0001 | 111 | Piping Material Specification - W028 | 64 | 2021-10-22 | 2021-12-24 | 85 | 2021-11-28 | 0 | 60% | BK-SSGRL-PEDCO-110-PI-SP-0001Piping Material Specification - W028 | 2021-11-28 | 0 | BK-SSGRL-PEDCO-110-PI-SP-0001
P02-EPC-E1380 | P02-EPC-E1380P | P02-EPC-E1380A | BK-W028-PEDCO-110-PI-DW-0001 | 44 | Plot Plan Drawing - W028 | 30 | 2021-07-23 | 2021-08-21 | 173 | 2022-02-02 | 0 | 0% | BK-W028-PEDCO-110-PI-DW-0001Plot Plan Drawing - W028 | 2022-02-02 | 2022-12-20 | BK-W028-PEDCO-110-PI-DW-0001
P02-EPC-E1860 | P02-EPC-E1860P | P02-EPC-E1860A | BK-SSGRL-PEDCO-110-IN-SP-0001 | 197 | Specification For WHCP/HPU - W028 | 38 | 2021-07-23 | 2021-08-29 | 148 | 2021-08-08 | 2021-08-08 | 80% | BK-SSGRL-PEDCO-110-IN-SP-0001Specification For WHCP/HPU - W028 | 2021-08-08 | 2022-03-27 | BK-SSGRL-PEDCO-110-IN-SP-0001
P02-EPC-E1880 | P02-EPC-E1880P | P02-EPC-E1880A | BK-SSGRL-PEDCO-110-IN-DT-0001 | 197 | Data Sheets For WHCP/HPU - Wellheads - W028 | 49 | 2021-08-12 | 2021-09-29 | 28 | 2021-08-22 | 2021-12-21 | 80% | BK-SSGRL-PEDCO-110-IN-DT-0001Data Sheets For WHCP/HPU - Wellheads - W028 | 2021-08-22 | 2022-12-20 | BK-SSGRL-PEDCO-110-IN-DT-0001
P02-EPC-E2460 | P02-EPC-E2460P | P02-EPC-E2460A | BK-W028-PEDCO-110-CV-PY-0001 | 0 | General Civil Layout -W028 | 25 | 2021-07-23 | 2021-08-16 | 393 | 2021-10-19 | 0 | 60% | BK-W028-PEDCO-110-CV-PY-0001General Civil Layout -W028 | 2021-10-19 | 2022-12-20 | BK-W028-PEDCO-110-CV-PY-0001
P02-EPC-E2470 | P02-EPC-E2470P | P02-EPC-E2470A | BK-W028-PEDCO-110-CV-PY-0002 | 181 | Civil and Structural drawings -W028 | 45 | 2021-07-23 | 2021-09-05 | 393 | 2021-10-19 | 2022-03-14 | 80% | BK-W028-PEDCO-110-CV-PY-0002Civil and Structural drawings -W028 | 2021-10-19 | 2022-12-20 | BK-W028-PEDCO-110-CV-PY-0002
P02-EPC-E2480 | P02-EPC-E2480P | P02-EPC-E2480A | BK-W028-PEDCO-110-CV-DW-0001 | 0 | Rough Grading Plans -W028 | 25 | 2021-07-23 | 2021-08-16 | 261 | 2021-10-11 | 2021-10-11 | 60% | BK-W028-PEDCO-110-CV-DW-0001Rough Grading Plans -W028 | 2021-10-11 | 2022-04-10 | BK-W028-PEDCO-110-CV-DW-0001
P02-EPC-E3530 | P02-EPC-E3530P | P02-EPC-E3530A | BK-W028-PEDCO-110-PL-MR-0001 | 50 | PMR For Line Pipes - W028 | 10 | 2021-07-30 | 2021-08-08 | 7 | 2021-12-06 | 0 | 100% | BK-W028-PEDCO-110-PL-MR-0001PMR For Line Pipes - W028 | 2021-12-06 | 2022-12-20 | BK-W028-PEDCO-110-PL-MR-0001
P02-EPC-E3590 | P02-EPC-E3590P | P02-EPC-E3590A | BK-W028-PEDCO-110-IN-MR-0001 | 45 | PMR For WHCP/HPU - W028 | 10 | 2021-09-01 | 2021-09-10 | 27 | 2021-11-15 | 2022-01-16 | 100% | BK-W028-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W028 | 2021-11-15 | 2022-12-20 | BK-W028-PEDCO-110-IN-MR-0001
P02-EPC-P1550 | P02-EPC-P1550P | P02-EPC-P1550A |  | 50 | Tendering & Selection- W028 - Line pipe | 7 | 2021-08-19 | 2021-08-25 | 11460 | #N/A | #N/A | 0% |  | 2022-03-15 | 2022-05-25 | 0
P02-EPC-P1560 | P02-EPC-P1560P | P02-EPC-P1560A |  | 50 | Contract Effectiveness / PO- W028 - Line pipe | 5 | 2021-08-26 | 2021-08-30 | 17189 | #N/A | #N/A | 0% |  |  |  | 0
P02-EPC-P1570 | P02-EPC-P1570P | P02-EPC-P1570A |  | 50 | Manufacturing / Fabrication / Supply- W028 - Line pipe | 110 | 2021-08-31 | 2021-12-18 | 143244 | #N/A | #N/A | 0% |  |  |  | 0
P02-EPC-P1580 | P02-EPC-P1580P | P02-EPC-P1580A |  | 50 | Final Inspection- W028 - Line pipe | 7 | 2021-12-19 | 2021-12-25 | 28649 | #N/A | #N/A | 0% |  |  |  | 0
P02-EPC-P1670 | P02-EPC-P1670P | P02-EPC-P1670A |  | 45 | Tendering & Selection- W028 - WHCP | 10 | 2021-09-23 | 2021-10-02 | 2359 | 1400/12/24 | #N/A | 0% |  | 2022-03-15 | 2022-05-25 | 0
P02-EPC-P1680 | P02-EPC-P1680P | P02-EPC-P1680A |  | 45 | Contract Effectiveness / PO- W028 - WHCP | 5 | 2021-10-03 | 2021-10-07 | 3538 | #N/A | #N/A | 0% |  | 2022-05-29 | 2022-06-12 | 0
P02-EPC-P1690 | P02-EPC-P1690P | P02-EPC-P1690A |  | 45 | Manufacturing / Fabrication / Supply- W028 - WHCP | 90 | 2021-10-08 | 2022-01-05 | 29486 | #N/A | #N/A | 0% |  | 2022-06-13 |  | 0
P02-EPC-C1440 | P02-EPC-C1440P | P02-EPC-C1440A |  | 131 | Construction of Right of Way - W028 | 15 | 2021-10-11 | 2021-10-25 | 37246 |  |  | 0% |  |  |  | 0
P02-EPC-C1450 | P02-EPC-C1450P | P02-EPC-C1450A |  | 131 | Construction of Steel Works(Wellhead Facilities) - W028 | 10 | 2021-10-26 | 2021-11-04 | 8442 |  |  | 0% |  |  |  | 0
P02-EPC-E1000 | P02-EPC-E1000P | P02-EPC-E1000A | BK-GNRAL-PEDCO-000-PM-RT-0001 | 0 | Endorsement Report For Basic Design & Scope of Work - W028 | 30 | 2021-06-23 | 2021-07-22 | 1131 | 2021-07-31 | 2021-07-31 | 100% | BK-GNRAL-PEDCO-000-PM-RT-0001Endorsement Report For Basic Design & Scope of Work - W028 | 2021-07-31 | 2022-12-20 | BK-GNRAL-PEDCO-000-PM-RT-0001
P02-EPC-E1820 | P02-EPC-E1820P | P02-EPC-E1820A | BK-SSGRL-PEDCO-110-PL-RT-0001 | 192 | Pipeline Corrosion Study & Material Selection Report - W028 | 44 | 2021-08-22 | 2021-10-04 | 59 | 2021-10-27 | 2022-02-28 | 0% | BK-SSGRL-PEDCO-110-PL-RT-0001Pipeline Corrosion Study & Material Selection Report - W028 | 2021-10-27 | 2022-10-19 | BK-SSGRL-PEDCO-110-PL-RT-0001
P02-EPC-C1240 | P02-EPC-C1240P | P02-EPC-C1240A |  | 25 | Excavation of Mud Channel- W028 | 7 | 2021-08-30 | 2021-09-05 | 1790 |  |  |  | Excavation of Mud Channel- W028 | 2022-02-28 | 2022-03-28 | 0
P02-EPC-C1310 | P02-EPC-C1310P | P02-EPC-C1310A |  | 37 | Installation sealling Layer of Mud Pit- W028 | 6 | 2021-08-29 | 2021-09-04 | 13423 | 1401/02/10 |  |  | Installation sealling Layer of Mud Pit- W028 |  |  | 0
P02-EPC-C1460 | P02-EPC-C1460P | P02-EPC-C1460A |  | 131 | Construction & Installation of Shelter for Wellhead Control Panel- W028 | 5 | 2021-11-05 | 2021-11-09 | 2483 |  |  |  | Construction & Installation of Shelter for Wellhead Control Panel- W028 |  |  | 0
Formulas:
Actual Start = VLOOKUP([BK Document Number],'S&F'!$B:$E,3,0)
Actual Finish = VLOOKUP([BK Document Number],'S&F'!$B:$E,4,0)

## Well-14 (hidden)
Activity ID | P | A | BK Document Number | Total Float | Activity Name | Original Duration | Start | Finish | Budgeted Nonlabor Units | Actual Start | Actual Finish | % |  | Actual Start | Actual Finish | doc No. | 2022-05-25
P07-EPC-C1210 | P07-EPC-C1210P | P07-EPC-C1210A |  | 0 | Site Preparation BK14 | 20 | 2021-08-17 | 2021-09-05 | 104403 | 1400/06/24 |  | 53% |  | 2021-09-15 |  | 0
P07-EPC-E1290 | P07-EPC-E1290P | P07-EPC-E1290A | BK-SSGRL-PEDCO-110-PI-SP-0001 | 111 | Piping Material Specification - BK14 | 64 | 2021-10-22 | 2021-12-24 | 85 | 2021-11-28 | 0 | 60% | BK-SSGRL-PEDCO-110-PI-SP-0001Piping Material Specification - BK14 | 2021-11-28 | 0 | BK-SSGRL-PEDCO-110-PI-SP-0001
P07-EPC-E2580 | P07-EPC-E2580P | P07-EPC-E2580A | BK-BK14-PEDCO-110-CV-PY-0001 | 346 | General Civil Layout - BK14 | 24 | 2021-07-23 | 2021-08-16 | 393 | 2021-10-19 | 0 | 60% | BK-BK14-PEDCO-110-CV-PY-0001 | 2022-09-19 | 2022-12-20 | BK-BK14-PEDCO-110-CV-PY-0001
P07-EPC-E2570 | P07-EPC-E2570P | P07-EPC-E2570A | BK-BK14-PEDCO-110-CV-DW-0001 | 350 | Civil and Structural drawings - BK14 | 24 | 2021-07-23 | 2021-09-05 | 393 | 2021-10-19 | 2022-03-14 | 80% | BK-BK14-PEDCO-110-CV-DW-0001 | 2022-10-18 | 2022-12-20 | BK-BK14-PEDCO-110-CV-DW-0001
P07-EPC-E2590 | P07-EPC-E2590P | P07-EPC-E2590A | BK-BK14-PEDCO-110-CV-PY-0003 | 346 | Rough Grading Plans -BK14 | 24 | 2021-07-23 | 2021-08-16 | 261 | 2021-10-11 | 2021-10-11 | 60% | BK-BK14-PEDCO-110-CV-PY-0003Rough Grading Plans -BK14 | 0 | 2022-12-20 | BK-BK14-PEDCO-110-CV-PY-0003
P07-EPC-E1000 | P07-EPC-E1000P | P07-EPC-E1000A | BK-GNRAL-PEDCO-000-PM-RT-0001 | 0 | Endorsement Report For Basic Design & Scope of Work - W028 | 30 | 2021-06-23 | 2021-07-22 | 1131 | 2021-07-31 | 2021-07-31 | 100% | BK-GNRAL-PEDCO-000-PM-RT-0001Endorsement Report For Basic Design & Scope of Work - W028 | 2021-07-31 | 2022-12-20 | BK-GNRAL-PEDCO-000-PM-RT-0001
P07-EPC-C1330 | P07-EPC-C1330P | P07-EPC-C1330A |  | 366 | Excavation & Repair - BK14 | 4 | 2021-08-30 | 2021-09-05 | 1790 |  |  |  | Excavation & Repair - BK14 |  |  | 0
P07-EPC-C1360 | P07-EPC-C1360P | P07-EPC-C1360A |  | 358 | Supply & Installation sealling Layer - W028 | 6 | 2021-08-29 | 2021-09-04 | 13423 | 1401/02/10 |  |  | Supply & Installation sealling Layer - W028 |  |  | 0
Formulas:
Actual Start = VLOOKUP([BK Document Number],'S&F'!$B:$E,3,0)
Actual Finish = VLOOKUP([BK Document Number],'S&F'!$B:$E,4,0)
Actual Finish = VLOOKUP([BK Document Number],'S&F'!B:E,4,0)