## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-BK15-PEDCO-110-PI-MT-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1545 |  |  | Transmital Date: 25/OCT/2022
Document Title: MTO FOR PIPE– BK15 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1545 |  |  | Transmital Date: 25/OCT/2022
[5 empty] | CRS No: NISOC-CRS-BK-BK15-PEDCO-110-PI-MT-0001_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | از آنجا که مشخصات کالای مندرج در این مدرک می بایست مطابق با PMS مدارک محاسبه ضخامت و دیگر مدارک مربوطه باشد لذا ضروری است این مدرک به مدارک مربوطه ارجاع گردد. |  | 01/2294/340870 | 13/09/1401 | احتراما PMS و مدرک محاسبه ضخامت طی جلسه با کارفرما نهایی شده و این مدرک مطابق با آن به روز رسانی گردید.
2 | کلاس مربوط به کالا (مطابق با PMS ) در مدرک قید گردد. |  | 01/2294/340870 | 13/09/1401 | احتراما اعمال گردید.
3 | مدرک MTO می بایست پس از تدوین و نهایی شدن کلیه موارد مهندسی تفضیلی مربوطه تولید گردد. لذا از آنجا که تا کنون مدارک پیش گفته نهایی نشده اند صحه گذاری و تایید این مدرک به لحاظ جنس متریال و مشخصات فنی اقلام در شرایط کنونی از سوی این امور میسر نیست. |  | 01/2294/340870 | 13/09/1401 | احتراما مدارک پایه طی جلسه با کارفرما نهایی شده و این مدرک مطابق با آن به روز رسانی گردید. لازم به توضیح است چاه BK-12 جزو چاه های تعمیراتی می باشد.
4 | با استناد به وضعیت مدارک ارسالی( IFI) مسئولیت کامل تطابق متریال مندرج در این مدرک صدرالذکر (مشخصات فنی و یا متریال ) بر عهده آن پیمانکار است. |  | 01/2294/340870 | 13/09/1401 | احتراما نقطه نظر مد نظر قرار خواهد گرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh M. Torkaman | Signature |  |  |  | Clarified By: | Signature | M.Fakharian
| Date: |  |  |  |  | A.Dabiri