## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-BK12-PEDCO-110-PI-MT-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1545 |  |  | Transmital Date:25-Oct-2022
Document Title: MTO For Pipes-BK12 |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No:PEDCO-CRS-BK-BK12-PEDCO-110-PI-MT-0001-D00 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نهايي شدن مدارك پيش نياز مانند PMS و Piping Wall Thickness Calculation و آيزومتريكهاي مربوط به سر چاه قبل از ارسال اين مدرك ضروري مي باشد. لذا از آنجا كه مدارك پيش نياز اين مدرك هنوز نهايي نشده است تائيد نهايي اين مدرك به لحاظ جنس متريال و مشخصات فني و متراژ لوله پس از نهايي شدن مدارك ذكر شده مقدور مي باشد. بديهي است مسئوليت كامل تطابق متريال و مشخصات فني با PMS مورد تأييد پروژه و مسئوليت درستي متراژ لوله و هرگونه كسري متريال بر عهده آن پيمانكار مي باشد. |  | BK-SUR-ENG-PIP-01-06077 | 2022-11-02 | احتراما مدارک پیش نیاز متریالی طی جلسه ای با کارفرما نهایی شده اند. ضمنا با توجه به تعمیراتی بودن این چاه ها مدارک آیزومتریک در لیست مدارک این پیمانکار نمی باشد.
2 | در مدرك ارسالي فقط لوله هاي 4" مربوط به Burn Pit در كلاس AN15 ليست شده است كه البته ضخامت لوله ها در PMS پروژه SCH.40 يعني 6.02mm مي باشد كه در MTO ضخامت بيشتر يعني 7.1mm ذكر شده كه قابل پذيرش مي باشد. با توجه به عنوان مدرك در ويراپش بعدي بايستي تمامي لوله هاي مورد نياز سرچاهي با مشخصات كامل بهمراه كلاس مربوطه ليست شود. |  | BK-SUR-ENG-PIP-01-06077 | 2022-11-02 | احتراما ضخامت لوله اصلاح شد و لازم به توضیح است جاه 12 تعمیراتی بوده و PIPING آن موجود است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 2.Nov.2022 |  |  |  |  | Date: 2.Nov.2022