## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: Data Sheets For WHCP/HPU - Wellheads |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1768 |  |  | Transmital Date: 8 Jan 2023
Document Title: BK-SSGRL-PEDCO-110-IN-DT-0001_D04 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1768 |  |  | Transmital Date: 8 Jan 2023
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات این امور بر ویرایش چهارم مدرک فوق طی نامه 1944443 مورخ 1401/06/03 اعلام گردیده ولیکن پس از گذشت حدود 4 ماه ویرایش پنجم مدرک، با تاخیرات بسیار صادر و ارسال گردیده است. با توجه به مشخص بودن سازنده و گذشت زمان زیادی از شروع ساخت(جلسات PIM و KOM مورخ 1401/04/26) چرا در این مرحله موارد VTC و VTA نام کارخانه سازنده، مدل دستگاه / پنل و ..... مشخص نگردیده است ؟ |  | 01/2294/408747 | 1401/10/26 | نظر کار فرمای محترم با توجه به نهایی شدن خرید پکیج دو چاه W018S و W008N ، در مدرک اعمال گردید.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: