## Sheet1
N.I.S.O.C |  |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-CV-DW-0018 | [5 empty] | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1298 |  |  | Transmital Date: 22 Aug 2022
Document Title: STANDARD DRAWING FOR FIRE HYDRANT PAD | [5 empty] | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-CV-TR-1298 |  |  | Transmital Date: 22 Aug 2022
[6 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | برای چندمین مرتبه اعلام می‌گردد، تمامی تغییرات انجام شده در مدارک، نسبت به ترانسمیتال پیشین خود می بایست با REV Mark مشخص گردند که در این مدرک رعایت نشده است مقتضی است دقت عمل بیشتری صورت پذیرد. |  |  | 01-2294-210052 | 1401/06/13 | ویرایش شماره 2 بدلیل تغییرات زیاد نسبت به ویرایش اول بصورت Totally Revised ارائه گردیده بود بهمین دلیل بر روی قسمت های تغییر یافته ریویژن مارک نداشت.
2 | پاسخ آن پیمانکار به ردیف 1 از Clarification(By EPC Contractor) مورد تایید نمی باشد. مطابق با نقشه، جنس پایه های درون بتن از نوع کربن استیل با سایز 6 اینچ می باشد و توضیحات آن شرکت در رابطه با موضوع دیگری است که ارتباطی با نقطه نظرات گفته شده ندارد. لذا مقتضی است مطابق با نامه شماره 452344 مورخ 1400/12/25 ردیف های 4 و 6 اقدام و مدرک اصلاح گردد. |  |  | 01-2294-210052 | 1401/06/13 | اعمال گردید.
| 4 | برای گیرداری لوله بکار برده شده در بتن درجا، لوله‌ها، شاخک گذاری شده، نمایش داده شوند. |  | 01-2294-452344 | 1400/12/25 | لوله با بتن پیرامونی گیردار شده و جزئیات مربوطه تحت عنوان "Detail 5" به مدرک اضافه گردید.
| 6 | استفاده از Water proof primer برای سطوح بتنی در تماس با خاک قید شود. |  | 01-2294-452344 | 1400/12/25 | اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) | [5 empty] | EPC Contractor
| Commented By: |  | Signature |  |  |  | Clarified By: | Signature
| Date: | [5 empty] | Date: