## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-SU-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1291 |  |  | Transmital Date: 20-AUG-2022
Document Title: Flow line Plan & Profile Drawings - W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SU-TR-1291 |  |  | Transmital Date: 20-AUG-2022
[5 empty] | CRS No: NISOC-CRS-BK-W028-PEDCO-110-SU-DW-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | از آنجا که مسیر پیشنهادی مذکور پیشتر در اسناد پیمان گنجانده شده است لذا ضروری است ابتدا مدارک مذکور صحه گذاری شده و یا انحراف از آنها اعلام گردد. |  | 01-2294-220543 | 1401/06/21 | مسیر نسبت به مسیر اسناد پیمان تغییرات عمده ندارد و کلیت مسیر حفظ شده است تنها بدلیل نقشه برداری جدید و بررسی های صورت گرفته، در بخش هایی از مسیر جهت اجتناب از ورود به مناطق تپه ماهور و کاهش تعداد تقاطع با جاده ها و مسیر های آب تغییراتی صورت گرفته است.
2 | مقیاس نقشه های ارائه شده در اسناد پیمان در مرحله پایه 1:1000 بوده اما نقشه های این مدرک 1:1000 می باشد. مقتضی است با SC=1:500 تهیه نمایند. |  | 01-2294-220543 | 1401/06/21 | اصلاح شد.
3 | مقایسه و بررسی مدارک ارائه شده با اسناد پیمان با توجه به فقدان اطلاعات مکفی امکانپذیر نیست. |  | 01-2294-220543 | 1401/06/21 | مسیر خط لوله مطابق با اسناد پیمان می باشد و تغییرات جزئی است همچنین اطلاعات نقشه برداری تکمیل گردیده است.
4 | در پروفیل ارسالی شیب های (%24.03-) و (%27.43+) و ... وجود دارد که مغایر با استاندارد طراحی است. |  | 01-2294-220543 | 1401/06/21 | اصلاح شد.
5 | پروفیل طولی ارائه شده نسبت به نقشه های مندرج در اسناد پایه دارای مغایرت است. به عنوان نمونه قوس های مسیر کوتاه تر بوده و طول خط لوله نیز 427 متر کوتاه تر طراحی شده است. |  | 01-2294-220543 | 1401/06/21 | طول خط لوله حدود 100 متر بدلیل موارد ذکر شده در بند اول بیشتر شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: