## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-AR-SP-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0781 |  |  | Transmital Date:4/6/2022
Document Title: Buildings General Specification |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-TR-0781 |  |  | Transmital Date:4/6/2022
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-AR-SP-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بخش Abbreviation به شرح زیر تکمیل شود |  | 1401-2294-16799 | 1401/01/21 | اعمال شد
2 | استانداردهای زیر به بخش مربوطه افزوده گردند. |  | 1401-2294-16799 | 1401/01/21 | اعمال شد
3 | در بخش Masonry به تفکیک برای سرفصل‌های زیر توضیحات مورد نیاز افزوده گردند. |  | 1401-2294-16799 | 1401/01/21 | اعمال شد
4 | فصل Metal Cladding به این مدرک افزوده گردد. |  | 1401-2294-16799 | 1401/01/21 | اعمال شد
5 | در بخش Door توضیحات ذیل افزوده گردد. |  | 1401-2294-16799 | 1401/01/21 | اعمال شد
6 | موارد به شرح ذیل به عنوان سرفصل به این مدرک افزوده گردد. |  | 1401-2294-16799 | 1401/01/21 | اعمال شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021