## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-DW-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1624 |  |  | Transmital Date: 11/28/2022
Document Title: Civil and Structural drawings - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1624 |  |  | Transmital Date: 11/28/2022
[5 empty] | CRS No: NISOC-CRS-BK-BK14-PEDCO-110-CV-DW-0001-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-361967 | 1401/09/26 | پلات پلن کلیه چاهها پس از برگزاری جلسات بازنگری مدل (Model Review) ارسال گردیده است.
2 |  |  | 1401-2294-361967 | 1401/09/26 | نامگذاری اصلاح شد
3 |  |  | 1401-2294-361967 | 1401/09/26 | مدارک اسپک و جزئیات استاندارد به رفرنس نقشه ها اضافه گردید
4 |  |  | 1401-2294-361967 | 1401/09/26 | با توجه به در نظر گرفتن طرح مدیریت پسماند جدید ، نقشه ها مورد بازنگری قرارگرفت
5 |  |  | 1401-2294-361967 | 1401/09/26 | با توجه به در نظر گرفتن طرح مدیریت پسماند جدید، نقشه ها مورد بازنگری قرارگرفت
6 |  |  | 1401-2294-361967 | 1401/09/26 | با توجه به در نظر گرفتن طرح مدیریت پسماند جدید ، نقشه ها مورد بازنگری قرارگرفت
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: