## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0014_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1636 |  |  | Transmital Date: 28 Nov 2022
Document Title: Data Sheets For Corrosion Coupon/ Probe |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1636 |  |  | Transmital Date: 28 Nov 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0014_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ذكر گردد كه مطالعات wake frequencies بايد توسط وندور انجام شود. |  | BK-SUR-ENG-INS-01-06417 | 2022-12-17 | در Note 2 صفحه های 6 تا 8 مدرک به وضوع به همین نکته اشاره شده است.
2 | مشخص شود كه محل تست گيري coupon كجا قرار گيرد. |  | BK-SUR-ENG-INS-01-06417 | 2022-12-17 | در ردیف 52 و Note 6 ذکر شده است.
3 | اين مدرك با مدرك Index، تناقض دارد. موارد مجددا بررسي و ارائه گردد. |  | BK-SUR-ENG-INS-01-06417 | 2022-12-17 | با نوجه به کامنت کارفرما و مطابق آخرین نسخه INDEX ، مدرک اصلاح گردید.
4 | دبی جرمی درج شده برای CC-2102 و CC-2111 بر مبنای حداکثر دبی دریافتی ایستگاه در حالت پیکرانی درج گردد. |  | BK-SUR-ENG-INS-01-06417 | 2022-12-17 | مدرک با توجه به کامنت کارفرمای محترم اصلاح گردید.
5 | آخرين مدرك P&ID، نسخه D05 مي باشد. |  | BK-SUR-ENG-INS-01-06417 | 2022-12-17 | با نوجه به کامنت کارفرما و مطابق آخرين مدرك P&ID ( نسخه D05 )، مدرک اصلاح گردید.
6
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 17 Dec 2022 |  |  |  |  | Date: