## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-LI-0009_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1875 |  |  | Transmital Date: 15 Feb 2023
Document Title: Instrument /F&G Cable List - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1875 |  |  | Transmital Date: 15 Feb 2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0009_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم اعمال نظرات این امور، مدرک قابل ارسال نمی باشد. |  | 01/2204/485353 | 1401/12/20 | همانطور که در محتوی مدرک قابل ملاحظه است ُ‌ ساختمان کنترل، سویچگیر و باتری که در این پروژه ادوات جدید به آن اضافه میشود توسط سیستم FACP مونیتور میشود. مدرک مطابق اخرین توافقات و مدارک به روز رسانی شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 1 Mar 2023 |  |  |  |  | Date: