## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0025_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1373 |  |  | Transmital Date: 07/11/2022
Document Title: Mechanical Data Sheets For Potable Water Pump |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0107-ME-TR-1373 |  |  | Transmital Date: 07/11/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0025_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Please be informed that some of the comments have considered as "NOTED" but it has not been implemented in the datasheet, so it has been requested to confirm that "these comments shall be followed by the Hirgan in technical clarification"; so there is no need to issue the documents again. |  | BK-SUR-ENG-MEC-01-05918 | 2022-10-18 | Noted but it should be noted that the MDS for Potable water pump has been confirmed by PEDCO in revision D02. Also all of the comments by PEDCO on revision D01 had been implemented by EPC contractor. This document will be issued with revision D04 by implementing NISOC comments.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 10/18/2022 |  |  |  |  | Date: 03/27/2023