## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DT-0010_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1835 |  |  | Transmital Date: 31 Jan 2023
Document Title: Data Sheets For F&G Devices - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1835 |  |  | Transmital Date: 31 Jan 2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0010_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-06945 | 2023-02-15 | ملاحظه گردید.
2 | نقطه نظرات بر روي مدرك Layout بر روي اين مدرك نيز در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-06945 | 2023-02-15 | مدرک مطابق آخرین نسخه از مدرک layout ارائه گردید.
3 | عنوان صفحه 7 اصلاح گردد. |  | BK-SUR-ENG-INS-01-06945 | 2023-02-15 | اصلاح گردید.
4 | Area Classification براي MAC-2201 اصلاح گردد. |  | BK-SUR-ENG-INS-01-06945 | 2023-02-15 | مدرک مطابق آخرین نسخه از مدرک layout ارائه گردید.
5 | Area Classification براي SD-2201 اصلاح گردد. |  | BK-SUR-ENG-INS-01-06945 | 2023-02-15 | در محدوده safe می باشد.
6 | تگ HD-22301 اصلاح گردد |  | BK-SUR-ENG-INS-01-06945 | 2023-02-15 | اصلاح گردید.
7 | Area Classification براي MAC-2303 اصلاح گردد. |  | BK-SUR-ENG-INS-01-06945 | 2023-02-15 | مدرک مطابق آخرین نسخه از مدرک layout ارائه گردید.
8 | نقطه نظرات ذي نفع اصلي بر روي اين مدرك در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-06945 | 2023-02-15 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 14 Feb 2023 |  |  |  |  | Date: