## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-CV-PY-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1428 |  |  | Transmital Date: 22-SEP-22
Document Title: Rough Grading Plan and Details |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1428 |  |  | Transmital Date: 22-SEP-22
[5 empty] | CRS No: PEDCO-CRS -D00- BK-GCS-PEDCO-120-CV-PY-0007_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کلیه کامنتهای موجود در فایل PDF |  | BK-SUR-ENG-CIV-01-06038 | 2022-10-31 | نقطه نظر کارفرمای محترم به نحو مقتضی اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H. Omani | Signature
| Date: |  |  |  |  | Date: 20/09/2021