## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-RT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1666 |  |  | Transmital Date:12/7/2022
Document Title: Flare Network Study Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1666 |  |  | Transmital Date: 12/7/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Back Pressure مندرج در جدول شماره یک مدرک برای شیرهای PSV در سناریو های Fire Area 1,2,3 اصلاح گردد. |  | 1401-2294-470891 | 1401/12/09 | Back Pressure مندرج در جدول شماره یک مدرک برای شیرهای PSV در سناریو های Fire Area 1,2,3 بر اساس آخرین تغییرات شبکه فلر اصلاح گردید.
2 | باتوجه به فایل شبیه سازی ارسالی پیمانکار و بااعمال شرایط طراحی شبکه، سایز 8 اینچ یرای Tail Pipe مربوط به شیر PSV-2113-2114 کفایت می کند. بر این اساس لازم است محاسبات مورد بازنگری قرار گیرد. |  | 1401-2294-470891 | 1401/12/09 | اصلاح گردید.
3 | با وجود پاسخ "اصلاح گردید" توسط پیمانکار در بند 13 مدرک داده برگ پاسخ ، اصلاح مورد نظر در مدرک اعمال نشده است. |  | 1401-2294-470891 | 1401/12/09 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021