## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-SP-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1665 |  |  | Transmital Date: 12/7/2022
Document Title: Duty Specification for LP Flare Package (PK-2201) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1665 |  |  | Transmital Date: 12/7/2022
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0003_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است مبنای Sulfur Content مندرج در جدول بخش 4.1.2.3 ارائه گردد. |  | 1401-2294-415389 | 1401/11/01 | سناریو Fire Wetted بر اساس خوراک ورودی به V-2104 در زمان پیگرانی در نظر گرفته شده است. در این سناریو با توجه به اینکه Latent Heat مقدار پایینتری نسبت به سناریو نرمال عملیاتی دارد لذا سنارویو اشاره شده بدترین سناریو Fire Wetted می باشد که این پیمانکار در محاسبات لحاظ نموده است. با توجه به نامه دریافتی از کارفرمای محترم به شماره 200607-2294-00 مورخ 1400.06.26 ترکیب درصد سیال ورودی از خط لوله گلخاری ارائه شده است. با توجه به اینکه در سایزینگ PSV-2111 سناریو FIRE WETTED سناریو غالب می باشد لذا ترکیب درصد سناریو صدرالذکر به عنوان سیال ورودی به فلر در نظر گرفته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021