## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-IN-DT-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1220 |  |  | Transmital Date: 30 Jul 2022
Document Title: Data Sheets For Pressure Gauge - Wellheads |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1220 |  |  | Transmital Date: 30 Jul 2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-16 | ملاحظه شد
2 | شماره مدرك در تمامي صفحات اصلاح گردد. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-16 | اصلاح شد.
3 | Conn. Rating Class مطابق PMS اصلاح گردد. (مطابق مدرك API 6000 در نظر گيرد) |  | BK-SUR-ENG-INS-01-05462 | 2022-08-16 | اصلاح شد.
4 | ويرايش مدارك ذكر گردد. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-16 | اصلاح شد.
5 | پايپينگ: با توجه به اينكه فشار و دماي طراحي براي كلاس LN15 مطابق با PMS پروژه حدود 207 barg و دماي طراحي 85سانتيگراد مي باشد لذا فشار و دماي طراحي طراحي مجددا" بررسي شده و با PMS پروژه مطابق باشد. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-16 | مطابق آخرین مدارک فرایندی اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 15 Aug 2022 |  |  |  |  | Date: