## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-CN-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1665 |  |  | Transmital Date: 12/7/2022
Document Title: Calculation Note For Depressurizing (Min. Design Temperature ) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1665 |  |  | Transmital Date: 12/7/2022
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات این امور در بند اول مدرک پاسخ برگ ارسالی اعمال نشده است. در این خصوص آخرین نسخه فایل Native محاسبات ارسال گردد. لازم به ذکر است فایل Native ارسالی مربوط به ویرایش D01 می باشد. |  | 1401-2294-415389 | 1401/11/01 | فایل محاسباتی Native با توجه به آخرین تغییرات اعمال شده در ایستگاه تقویت فشار بینک ویرایش و ارسال به پیوست ارسال می گردد. لازم به ذکر است به دلیل افزایش حجم V-2104 و مطابق بند 5.2 مدرک فوق ، میزان دبی جرمی محبوس معادل ، بیشتر از 2 تن C4 محاسبه شده است لذا تابپ شیر XV-2110 به BDV-210 تغییر یافت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021