## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MT-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1306 |  |  | Transmital Date: 23 Aug 2022
Document Title: MTO For Instrument Cable Tray/Ladder - W007S & Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR- 1306 |  |  | Transmital Date: 23 Aug 2022
[5 empty] | CRS No: ٔNISOC-CRS-BK-W007S-PEDCO-110-IN-MT-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد ۵ تا ۹ قبل از عقد قرارداد مشخص شود. |  | 01/2294/216521 | 1401/06/19 | مطابق نظر کارفرمای محترم اصلاح شد.
2 | تسمه و متعلقات اتصال ارتینگ سینیها کابل در نظر گرفته شود. |  | 01/2294/216521 | 1401/06/19 | مطابق نظر کارفرمای محترم اصلاح شد.
3 | پیچ و مهره مناسب اتصال سینی کابل در نظر گفته شود |  | 01/2294/216521 | 1401/06/19 | مطابق نظر کارفرمای محترم اصلاح شد.
4 | مدرک/مدارک مرتبط با این مدرک بعنوان مرجع ذکر گردد. |  | 01/2294/216521 | 1401/06/19 | مطابق نظر کارفرمای محترم اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 12 sep 2022 |  |  |  |  | Date: