## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0020_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1562 |  |  | Transmital Date: 26 Oct 2022
Document Title: PMR FOR FIELD INSTRUMENTATIONS - W007S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1562 |  |  | Transmital Date: 26 Oct 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0020_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-06136 | 2022-11-08 | ملاحظه شد.
2 | با توجه به اينكه مدارك پيش نياز نهايي نيست، موارد در صورت تغيير در اين مدرك اعمال گردد. |  | BK-SUR-ENG-INS-01-06136 | 2022-11-08 | اخرین نسخه مدارک درپیوستها جایگزین شد.
3 | در بند 6، مدرك به شماره E&C-QC-INSP-1 منسوخ شده است. لذا از ليست مدارك مرجع حذف گردد. |  | BK-SUR-ENG-INS-01-06189 | 2022-11-16 | اصلاح شد.
4 | عبارت "NOTE: List of Documents will be Finalized in VDLS." از انتهاي پيوست 1 به انتهاي پيوست 2 انتقال يابد. |  | BK-SUR-ENG-INS-01-06189 | 2022-11-16 | اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 8 Nov 2022 |  |  |  |  | Date: