## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-SU-DW-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0745 |  |  | Transmital Date: 26-March-2022
Document Title: Over Head Line Plan and Profile - W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0102-SU-TR-0745 |  |  | Transmital Date: 26-March-2022
[5 empty] | CRS No: PEDCO-CRS-BK-W046S-PEDCO-110-SU-DW-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در مسیر پیشنهادی، حریم ایمنی موقعیت BK-007SB رعایت نشده است. به پیوست جهت تسریع در تولید مدرک، نقشه شماره 88216 و با فرمت PDF با رعایت حریم ایمنی موقعیت فوق الذکر در ضمیمه نامه ارسال می گردد. توضیح اینکه نقشه های ارسالی فاقد استانداردهای نقشه برداری است، لذا ضروری است نقشه یکپارچه مسیر در UTM و به صورت Georefence ارسال شود. ضمنا به پیوست فایل DWG نقشه مذکور نیز در قالب یک عدد لوح فشرده ارسال می گردد. هماهنگی لازم جهت دریافت لوح فشرده از دفتر مهندسی به عمل آید. |  | 1401-2294-43154 | 1401-02-08 | با توجه به تغییر مسیر چاه 46، تمامی موارد مرتفع گردید. همچنین از فایل پیوست نیز استفاده گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 29-May-2022 |  |  |  |  | Date: