## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PI-SP-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1344 |  |  | Transmital Date: 9/4/2022
Document Title:Piping Material Specification |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0201-IN-TR-1344 |  |  | Transmital Date:9/4/2022
[5 empty] | CRS No:NISOC-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به مندرجات صورتجلسه مورخ 1401/05/26 ضروری است ابتدا مدارک پیش نیاز مانند P&ID تهیه و ارسال گردد. لازم به ذکر است تعریف و نامگذاری خطوط نیز می بایست مجددا صورت پذیرد. همچنین به جهت سهولت بررسی مدرک، مدارک مرتبط تایید شده مانند P&ID به همراه ترنسمیتال ارسال گردد. |  | 01/2294/231558 | 1401/06/29 | احتراما مدارک پیش نیاز تهیه و ارسال شده است. و نام گذاری ها با مدارک پایه یکسان می باشد.
2 | پیرو بند 4 صورتجلسه مورخ 1401/05/26 ضروری است محاسبات برای تحمل فشار بر اساس API6A ارسال گردد. |  | 01/2294/231558 | 1401/06/29 | موارد مطابق صورتجلسه مورخ 1401/11/11 اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 14/09/2022 |  |  |  |  | Date: 14/09/2022