## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PI-CN-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1344 |  |  | Transmital Date: 04/SEP/2022
Document Title: Piping Wall Thickness Calculation |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0201-IN-TR-1344 |  |  | Transmital Date: 04/SEP/2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | براي كلاسهاي LN17 و MN17 در فايل اكسل محاسبات در بالاي جدول Corrosion Allowance مقدار 6mm نوشته شود. |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | اعمال شد
2 | فشار طراحي در كلاس AS00 مطابق PMS برابر 13.9 Psi مي باشد ولي در جدول محاسبات ضخامت 15.9 Psi در نظر گرفته شده است. اصلاحات لازم انجام شود. |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | اعمال شد
3 | در كلاس CS00 فشار طراحي اصلاح شده و محاسبات ضخامت بر آن اساس بازنگري شود. نمي تواند فشار طراحي با كلاس AS00 يكي باشد. در مدرك مهندسي پايه فشار كلاس CS00 برابر با 44 bar ذكر شده است. |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | فشار طراحی بر مبنای مدارک پایه فرایندی و مطابق PMS اعمال شده است. ضمنا فشار طراحی این کلاس با کلاس AS00 متفاوت می باشد.
4 | در صفحه 12 فشار تست كلاس 5000 مطابق API 6A معادل 10000 Psi در نظر گرفته شود و ضخامت بر آن اساس اصلاح گردد. |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | همانطور که مستحضر می باشید و مطابق فرمول های ارائه شده در مدرک، جهت محاسبه ضخامت خط از فشار تست استفاده نمی گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 14/09/2022 |  |  |  |  | Date: 14/09/2022