## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PI-SP-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1344 |  |  | Transmital Date: 4/SEP/2022
Document Title: Piping Material Specification |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0201-IN-TR-1344 |  |  | Transmital Date: 4/SEP/2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش 3.2 استانداردهاي زير اضافه گردند: - ASME B36.10M - ASME B36.19M - ASME B16.20 - ASTM Standards - BS EN 10204 - NACE TM-0284 Standard Test Method - Evaluation Of Pipeline And Pressure Vessel Steels For Resistance To Hydrogen-Induced Cracking NACE TM-0177 Laboratory Testing Of Metals For Resistance To Sulfide Stress Cracking And Stress Corrosion Cracking In H2s Environments |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | احتراما نقطه نظر اعمال گردید.
2 | در كلاس CS00 فشار طراحي بايستي اصلاح شده و ضخامت ها بر آن اساس بازنگري شود. نمي تواند فشار طراحي با كلاس AS00 يكي باشد. در مدرك مهندسي پايه فشار كلاس CS00 برابر با 44 bar ذكر شده است. |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | احتراما فشار طراحی بر مبنای مدارک پایه فرایندی در مدرک اعمال شده است.
3 | در كلاس MN17 براي فلنج و گسكت در ستون Description به اشتباه API 3000 نوشته شده است. اصلاح گردد. |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | احتراما نقطه نظر اعمال گردید.
4 | در تمامي كلاسهاي NACE براي تمامي آيتمها در قسمت استاندارد NACE MR-0175/ ISO 15156 اضافه گردد. |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | احتراما الزام استاندارد مذکور در کلیه کلاس ها در یک cell جداگانه مورد تاکید قرار گرفته است.
5 | مطابق نظر كارفرما براي Ball Valveهاي زير 2 اينچ استاندارد BS5351 منقضي شده است. بجاي آن مي توان به استاندارد ISO 17292 اشاره نمود. |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | احتراما نقطه نظر اعمال گردید.
6 | در كلاس MN17 ضخامت لوله هاي زير 2 اينچ ذكر گردد. |  | BK-SUR-ENG-PIP-01-05699 | 2022-09-14 | احتراما با توجه به عدم وجود خطوط با این سایز ها در پروژه نیازی به اضافه کردن این موارد نیست.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 14/09/2022 |  |  |  |  | Date: 14/09/2022