## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1656 |  |  | Transmital Date: 12/6/2022
Document Title: P&ID - Gas Compression Inlet Knock Out Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1656 |  |  | Transmital Date: 12/6/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو نظرات قبلی این امور در نامه 1401/2294/415389 (1401/11/01) بر روی مدرک "CALCULATION NOTE FOR PSV SIZING" ضمن اصلاح دمای RELIEF شیرهای PSV-2122/2123 در سناریوی BLOCKED OUTLET (در نظر گرفتن دمای SOURCE شیر به عنوان دمای RELIEF) سایز شیرهای مذکور به فرض غالب بودن سناریو BLOCKED OUTLET مورد بازنگری و اصلاح قرار گیرد. |  | 1401-2294-448340 | 1401/11/24 | در مدرک "CALCULATION NOTE FOR PSV SIZING" اصلاح گردید.
2 | با توجه به تغییر سایز خط خروخی از شیر PSV-2114 برای اتصال به TAIL PIPE شبکه هدر، کاهنده سایز خط (REDUCER) برای آن در نظر گرفته شود. |  | 1401-2294-448340 | 1401/11/24 | اعمال گردید
3 | با توجه به محاسبات ارایه شده در مدرک "FLARE NETWORK STUDY REPORT" سایز 8 اینچ برای خط ارسالی از هر دو شیر PSV-2113/2114 به هدر شبکه فلر مورد بازنگری قرار گیرد. |  | 1401-2294-448340 | 1401/11/24 | در مدرک "FLARE NETWORK STUDY REPORT" اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: