## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1656 |  |  | Transmital Date: 12/6/2022
Document Title: P&ID - 1st Stage Gas Compression Compressors |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1656 |  |  | Transmital Date: 12/6/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شیر ESDV-2121 میبایست در شرایط عملیاتی نرمال بسته بوده و Failure Mode آن از FC به FO اصلاح شود. |  | 1401-2294-448340 | 1401/11/24 | اعمال گردید.
2 | دمای طراحی کمپرسور C-2101 با توجه به جدول بخش 4-1-5 "PROCESS DESIGN CRITERIA" مورد بازنگری قرار گیرد. |  | 1401-2294-448340 | 1401/11/24 | ماکزیمم دمای حروجی از کمپرسورهای مرحله اوله برابر با 125 درجه سانتیگراد می باشد که بر اساس بند 4.1.5 مدرک "PROCESS DESIGN CRITERIA" دمای طراحی برابر با 150 درجه سانتیگراد محسبه گردید.
3 | با توجه به بند دوم نامه این امور 1401/2294/415389 (1401/11/01) بر روی مدرک "CALCULATION NOTE FOR PSV SIZING" ضمن اصلاح دمای RELIEF شیرهای PSV-2122/2123 در سناریوی BLOCKED OUTLET (در نظر گرفتن دمای SOURCE شیر به عنوان دمای RELIEF) سایز شیرهای مذکور به فرض غالب بودن سناریو BLOCKED OUTLET مورد بازنگری و اصلاح قرار گیرد. |  | 1401-2294-448340 | 1401/11/24 | بر روی مدرک "CALCULATION NOTE FOR PSV SIZING" اصلاح گردید.
4 | مکان NOTE 17 در نقشه P&ID مشخص شود. |  | 1401-2294-448340 | 1401/11/24 | اصلاح و اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: