## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0011 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1657 |  |  | Transmital Date: 12/6/2022
Document Title: P&ID - 2nd Stage Gas Compression Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1657 |  |  | Transmital Date: 12/6/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پاسخ ارایه شده در داده برگ ارسالی در خصوص نظرات پیشین این امور در بند 4 , 5 و 6 نامه 1401/2294/283491(1401/08/07) بروی ویرایش قبلی مدرک مورد قبول نمی باشد و لازم است کلاس فشاری شیر BDV-2132 از 300# به 600# و کلاس فشاری PCV-2135 در مدرک درج گردد. همچنین ضروریست کلاس فشاری شیر XV-2133 با توجه به کلاس خط متصل به آن، به 600# مورد بازنگری قرار گیرد |  | 1401-2294-448441 | 1401/11/30 | اصلاح گردید.
2 | سایز شیر PCV-2135 پس از دریافت مدارک محاسباتی سازنده،نهایی خواهد شد. |  | 1401-2294-448441 | 1401/11/30 | پس از دریافت محاسبات از سازنده مدرک فوق بازنگری خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: