## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0025 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1658 |  |  | Transmital Date: 12/6/2022
Document Title: P&ID - Glycol Sump Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1658 |  |  | Transmital Date: 12/6/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو نظرات قبلی این امور در بند سوم نامه 1401/2294/285752 (1401/08/7) بروی ویرایش قبلی مدرک فوق، Pset مربوط به شیرهای PRV-2291 و PRV-2292 جا به جا درج شده اند.لذا میباید Pset شیر PRV-2291 برابر با 10 mbarg و Pset شیر PRV-2292 برابر با 50 mbarg لحاظ گردد. |  | 1401-2294-452886 | 1401/11/26 | فرضیات از منظر این مشاور بر مینای این است که ورودی گاز نیتروژن به منظور Blanketing با Pset برابر با 50 mbarg مناسب بوده و در مسیر خروجی گاز نیتروژن به اتمسفر می بایست Pset برابر با 10 mbarg در نظر گرفته شود. در صورتی که آن کارفرمای محترم نقطه نظری در این خصوص دارند لطفا شرح مورد فوق را ابلاغ نمایند.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: