## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0023 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1658 |  |  | Transmital Date: 12/6/2022
Document Title: P&ID - Diesel Oil System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1658 |  |  | Transmital Date: 12/6/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-PI-0023_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | سایز همه شیرها، Reducer ها و نازلهای مخزن، در نقشه درج گردد. |  | BK-SUR-ENG-PCS-01-06518 | 2022-12-24 | اعمال گردید.
| برای خط پایین دست TSV، شیب در نظر گرفته شود. |  | BK-SUR-ENG-PCS-01-06518 | 2022-12-24 | در ویرایش قبلی این مورد در نظر گرفته شده است.
| برای تمامی شیرهای با سایز کم تر از 2 اینچ، Blind ها به صورت Cap نمایش داده شود. |  | BK-SUR-ENG-PCS-01-06518 | 2022-12-24 | اعمال گردید.
| توضیحات ارائه شده در خصوص دلیل حذف ESD-3 از پمپ هاي P-2206A/B شفاف نمی باشد. |  | BK-SUR-ENG-PCS-01-06518 | 2022-12-24 | تغییرات پمپ مذکور باتوجه به پیشنهادات مطرح شده در جلسات Hazap/Hazid صورت گرفته است. لازم است توضیحات ذکر شده مشخصا بیان گردد تا شفاف سازی آن میسر باشد.
| ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06518 | 2022-12-24 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: