## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1682 |  |  | Transmital Date:12/11/2022
Document Title:P&ID - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1682 |  |  | Transmital Date:12/11/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به نهایی سازی سایز کنترل ولوها پس از نهایی سازی سازنده در این مقطع نظر خاصی نمی باشد. |  | 01/2294/473450 | 1401/12/10 | با توجه به نهایی سازی سایز توسط فروشندگان و اخذ تاییدیه از آن کارفرمای محترم ، مدرک مورد نظر براساس همین سایزها بازبینی و برای اخذتاییدیه ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 25/12/2022 |  |  |  |  | Date: