## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-IN-DC-0001-D02 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-0414 |  |  | Transmital Date: 1400/11/06
Document Title: FIRE & GAS DETECTION DESIGN CRITERIA |  |  |  |  | PEDCO Tr. No.:BK-GNRAL-PEDCO-000-IN-DC-0001-D02 |  |  | Transmital Date: 1400/11/06
[5 empty] | CRS No:NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DC-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پس از حذف عبارت If Any از تمام مدرک ، در این برهه و با توجه به مفاد ماده 13 شرایط عمومی پیمان ، نظر خاصی مطرح نمی باشد و پیشبرد گام بعدی مهندسی بلامانع است. |  | 00/2294/382426 | 1400/11/06 | احتراما با توجه به اینکه در بخش منیفولد و سرچاهی بسیاری از عنوان ها مانند Detector های داخل محوطه فرایندی در محدوده کاری این بسته نمی باشد لذا حذف عبارت IF ANY ممکن نیست. لازم به ذکر است مدرک با این محتوا توسط بخش های مختلف و ادارات بررسی و تایید شده است و پیشنهاد میشود تغییری در محتوای مدرک ایجاد نشود. این مدرک با حذف هایلایت ها مجدد ارسال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: