## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W018S-PEDCO-110-IN-MT-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0451 |  |  | Transmital Date: 12 Jan 2022
Document Title: MTO For Instrument Cable Tray - W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0010-IN-TR-0451 |  |  | Transmital Date: 12 Jan 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W018S-PEDCO-110-IN-MT-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده وي است. |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | ملاحظه گردید.
2 | با توجه به اينكه مدارك مرجع هنوز داراي كامنت مي باشد و نهايي نشده است و با در نظر گرفتن ماهيت اين مدرك، تمامي مسئوليت هاي مالي و زماني آن بعهده پيمانكار پروژه مي باشد. در صورت تغيير مدارك پيشنياز موارد در اين مدرك لحاظ گردد. |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | مدرک با توجه به مدارک مرجع بروزرسانی شده ، تهیه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 26 Jan 2022 |  |  |  |  | Date: