## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W018S-PEDCO-110-IN-TB-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1136 |  |  | Transmital Date: 04 Jul 2022
Document Title: TBE/TBA For WHCP/HPU - W018S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1136 |  |  | Transmital Date: 04 Jul 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به كامنت هاي پيشين فايل ورد براي انتخاب سازنده در نظر گرفته شود. اين مورد براي تمامي TBE ها در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-05364 | 2022-08-06 | با احترام ، مدرک TBE در زمان خود صرفا جهت معرفی سازندگان و پیشنهادات آنها به کارفرمای اصلی صادر شد و با توجه به صلاح دید پروژه ، مراحل قرارداد و ساخت این پکیج تسریع شد و پس از آن تغییرات و توافقات در صورت جلسات ، قرارداد با سازنده و مدارک ارسالی سازنده قابل پیگیری می باشد. لذا در این مقطع مدرک TBE مرجع اطلاعات سازنده نیست و نیاز به تغییر در آن نمی باشد.
2 | با توجه به اينكه، جلسات KOM و PIM قبل از نهايي شدن TBE به درخواست پيمانكار و تاييد كارفرما برگزار شد. لازم به ذكر است كه براي خريد هاي آتي رويه متناسب با پروژه در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-05364 | 2022-08-06
3 | اطلاعات فرآيندي مربوط به SSV و SSSV طبق آخرين اطلاعات ارسال شده تكميل گردد. |  | BK-SUR-ENG-INS-01-05364 | 2022-08-06
4 | موارد بر اساس آخرين نقطه نظرات تاييد شده توسط كارفرما در صورتجلسه PIM و KOM مربوط به WHCP برگزار شده در شركت كاردانان شرق در تاريخ 26/04/1401 نهايي گردد. |  | BK-SUR-ENG-INS-01-05364 | 2022-08-06
5 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار است. |  | BK-SUR-ENG-INS-01-05364 | 2022-08-06
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 26 Jul 2022 |  |  |  |  | Date: