## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-CN-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1693 |  |  | Transmital Date: 12/14/2022
Document Title: Calculation Note For Control Valve Sizing |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1693 |  |  | Transmital Date: 12/14/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شماره صفحه، دبی و سایز خط PCV-2201 اصلاح گردد. |  | BK-SUR-ENG-PCS-01-06598 | 2023-01-02 | شماره P&ID و سایز خط به درستی درج شده است،دبی سیال مطابق با آخرین تغییرات اصلاح گردید.
2 | سایز خط PCV-2201 اصلاح گردد. |  | BK-SUR-ENG-PCS-01-06598 | 2023-01-02 | سایز خط صحیح می باشد.
3 | لازم است محاسبات مربوطه پس از انتخاب سازنده، توسط سازنده نيز مجددا صورت پذيرد. |  | BK-SUR-ENG-PCS-01-06598 | 2023-01-02 | محاسبات لازم توسط سازنده انجام خواهد شد.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06598 | 2023-01-02 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: