## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1669 |  |  | Transmital Date: 12/6/2022
Document Title: Symbol & Legend For PFD and P&ID |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1669 |  |  | Transmital Date: 12/6/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جهت UCP های کمپرسور لازم است Symbol متفاوت از سیستهای DCS و ESD واحد تعریف گردد و سیگنالهای مربوطه به آن ارسال گردد. |  | 1401-2294-471724 | 1401/12/09 | در ویرایش قبلی Symbol ها به همین ترتیب در نظر گرفته شده است. مراجعه شود به صفحه 4 از 8 مدرک.
| لازم است جهت پنل های کنترل و توقف اضطراری تمام پکیج ها،سیمبل مستقل در نظر گرفته شود و در نقشه نشان داده شود. |  | 1401-2294-471724 | 1401/12/09 | در ویرایش قبلی Symbol ها به همین ترتیب در نظر گرفته شده است. مراجعه شود به صفحه 4 از 8 مدرک.
| شماتیک کوار هوایی به صورت Induced Draft Type Air Coooler به مدرک اضافه گردد. |  | 1401-2294-471724 | 1401/12/09 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: