## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-PI-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1737 |  |  | Transmital Date:12/28/2022
Document Title:P&ID - Condensate Pipeline (to Binak PU) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1737 |  |  | Transmital Date:12/28/2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظر (شماره2) پیشین این امور طی نامه 1401/2294/300274 مورخ 1401/08/16 در مدرک اعمال نشده است. |  | 1401-2294-447699 | 1401/11/24 | آیتم ذکر شده (توصیه شماره 14) در خصوص شیر ایزولاسیون ورودی به V-2104 می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021