## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PH-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1629 |  |  | Transmital Date: 11/28/2022
Document Title: Drainage Philosophy |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1629 |  |  | Transmital Date: 11/28/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | كامنت پيشين (سومین بار): آیتم 4.3.3 بر اساس مشخصات مندرج در طراحی پایه تصحیح شده و مدت زمان بارش و استفاده از آب آتش نشانی مطابق با مهندسی پایه درج گردد. |  | BK-SUR-ENG-PCS-01-06418 | 2022-12-17 | پیرو مذاکرات شفاهی با کارفرمای اصلی پروژه و تایید مدرک فوق از جانب NISOC زمان بارش مطابق با آیتم 4.3.3 در مدرک فوق مورد تایید می باشد.
2 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06418 | 2022-12-17 | مورد تایید است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021