## Sheet1
N.I.S.O.C |  |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-CV-DW-0001 | [5 empty] | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1653 |  |  | Transmital Date: 4-DEC-2022
Document Title: Rough Grading Plans -W046S | [5 empty] | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1653 |  |  | Transmital Date: 4-DEC-2022
[6 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-CV-DW-0001-D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
بر اساس صورتجلسه مورخ 30-01-1402 وضعیت نقشه AFC میگردد
1 | در کلیه ترنزمیتال ها پوشه History حاوی مکاتبات قبلی و صورتجلسات مربوطه اضافه گردد. |  |  | 01/2294/467294 | 1401/12/07 | اعمال شد.
2 | ابعاد Wastepit و حجم نوشته شده بر آن با یکدیگر مطابقت ندارد. بررسی گردد. |  |  | 01/2294/467294 | 1401/12/07 | اصلاح شد.
3 |  |  |  | 01/2294/467294 | 1401/12/07 | طرح پسماند مورد تایید قرار گرفته است و در ضمائم قرار داده شده است.
4 |  |  |  | 01/2294/467294 | 1401/12/07 | اعمال شد.
5 |  |  |  | 01/2294/467294 | 1401/12/07 | اصلاح شد.
6 |  |  |  | 01/2294/467294 | 1401/12/07 | فایل Native در پیوست قرار داده شد.
7 |  |  |  | 01/2294/467294 | 1401/12/07 | گودال سوخت بر اساس اسناد پیمان طراحی شده است.
8 |  |  |  | 01/2294/467294 | 1401/12/07 | مختصات محل گودال سوخت بر اساس صورتجلسه اصلاح شد.
9 |  |  |  | 01/2294/467294 | 1401/12/07 | با لحاظ کردن کامنت شماره 15 اصلاح شد.
10 |  |  |  | 01/2294/467294 | 1401/12/07 | رنگهای زرد و سبز با فرض مشکی بودن رنگ پس زمینه انتخاب شده است.
11 |  |  |  | 01/2294/467294 | 1401/12/07 | درج گردید
12 |  |  |  | 01/2294/467294 | 1401/12/07 | اعمال شد.
13 |  |  |  | 01/2294/467294 | 1401/12/07 | با توجه به وجود Oil Trap در انتهای کانال، افزایش شیب طولی مانع انجام عملیات تفکیک آب و روغن می گردد لذا بر این اساس و طی هماهنگی صورت گرفته با بخش حفاری و تاییدیه طرح پسماند شیب طولی حدود نیم درصد کافی می باشد. از طرف دیگر کانال آب و گل مرتبا تمیزکاری می گردد.
14 |  |  |  | 01/2294/467294 | 1401/12/07 | اصلاح شد.
15 |  |  |  | 01/2294/467294 | 1401/12/07 | اعمال شد.
16 |  |  |  | 01/2294/467294 | 1401/12/07 | اعمال شد.
17 |  |  |  | 01/2294/467294 | 1401/12/07 | اعمال شد.
18 |  |  |  | 01/2294/467294 | 1401/12/07 | اعمال شد.
19 |  |  |  | 01/2294/467294 | 1401/12/07 | اصلاح شد.
20 |  |  |  | 01/2294/467294 | 1401/12/07 | اقدام مقتضی انجام خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) | [5 empty] | EPC Contractor
| Commented By: |  | Signature |  |  |  | Clarified By: | Signature
| Date: | [5 empty] | Date: