## Sheet1
N.I.S.O.C |  |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-CV-PY-0001 | [5 empty] | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1919 |  |  | Transmital Date: 01-Mar-2023
Document Title: General Civil Layout -W046S | [5 empty] | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1919 |  |  | Transmital Date: 01-Mar-2023
[6 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-CV-PY-0001-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
بر اساس صورتجلسه مورخ 30-01-1402 وضعیت نقشه AFC میگردد
1 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد.
2 |  |  |  | 02/2294/6804 | 1402/01/09 | اصلاح شد.
3 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد.
4 |  |  |  | 02/2294/6804 | 1402/01/09 | اصلاح شد.
5 |  |  |  | 02/2294/6804 | 1402/01/09 | اصلاح شد.
6 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد. هم چنین رفرنس و توضیح لازم در بخش NOTES اضافه شد.
7 |  |  |  | 02/2294/6804 | 1402/01/09 | مختصات محل گودال سوخت بر اساس صورتجلسه اصلاح شد.
8 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد. تراز پیرامون گودال سوخت 56 و تراز کف آن 52 است. (طبق نقشه های گودال سوخت و پروفیل طولی جاده دسترسی گودال سوخت)
9و10 |  |  |  | 02/2294/6804 | 1402/01/09 | با لحاظ کردن کامنت شماره 17 اصلاح شد.
11 |  |  |  | 02/2294/6804 | 1402/01/09 | رنگهای زرد و سبز با فرض مشکی بودن رنگ پس زمینه انتخاب شده است.
12 |  |  |  | 02/2294/6804 | 1402/01/09 | مورد قبول است.
13 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد.
14 |  |  |  | 02/2294/6804 | 1402/01/09 | تراز لوکیشن به نحوی طراحی شده است که در تمام محوطه بتنی صرفا عملیات خاکبرداری انجام شود، هم چنین عرض کانال سمت 17 متری به دلیل اینکه نقش جمع آوری کننده (Collector) دارد، 70 سانتی متری در نظر گرفته شده است.
15 |  |  |  | 02/2294/6804 | 1402/01/09 | اصلاح شد.
16 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد.
17 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد.
18 |  |  |  | 02/2294/6804 | 1402/01/09 | طراحی بر اساس اسناد پیمان صورت گرفته است. ضمن آنکه خودروهای سنگین جهت گردش از محوطه چاه استفاده می کنند. علاوه بر این در محل اتصال جاده دسترسی به گودالها به جاده دسترسی به چاه امکان گردش فراهم است.
19 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد.
20 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد.
21 |  |  |  | 02/2294/6804 | 1402/01/09 | تعداد و فواصل ساپورت ها در نقشه های بخش پاییپینگ دیده می شود و نت شماره 8 بدین منظور در بخش NOTES درج گردید.
22 |  |  |  | 02/2294/6804 | 1402/01/09 | نت شماره 7 بدین منظور درج گردید.
23 |  |  |  | 02/2294/6804 | 1402/01/09 | اعمال شد.
24 |  |  |  | 02/2294/6804 | 1402/01/09 | به دلیل اینکه کف کانال با کف جاده پیرامونی هم تراز است (به دلیل استفاده از حجم Waste Pit ) لذا امکان احداث کالورت نیست. ضمن آنکه محدوده پشت کانال غیرفعال است و دسترسی هم از طریق جاده پیرامونی تامین شده است.
25 |  |  |  | 02/2294/6804 | 1402/01/09 | تغییراتی اندک و جزئی به دلیل انطباق حداکثری با توپوگرافی، تدقیق محل کالورتها و بهینه سازی احجام خاکی در محور و تراز راه اعمال شده است. از این بابت کلیه تبعات فنی و مالی مورد پذیرش پیمانکار بوده و هیچ ادعایی در این خصوص ندارد.
26 |  |  |  | 02/2294/6804 | 1402/01/09 | کلیه تقاطع های فلولاین در مدرک پلان-پروفیل خط درج گردیده که در بخش رفرنس ها اضافه شد.
27 |  |  |  | 02/2294/6804 | 1402/01/09 | اقدام مقتضی انجام خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) | [5 empty] | EPC Contractor
| Commented By: |  | Signature |  |  |  | Clarified By: | Signature
| Date: | [5 empty] | Date: