## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-CN-0007_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1724 |  |  | Transmital Date: 24-Dec-2022
Document Title: Calculation Note For Earthing & Lightning System of Well Pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0110-EL-TR-1724 |  |  | Transmital Date: 24-Dec-2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0007_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در این مقطع نظر خاصی مطرح نبوده، ولیکن پیرو نامه شماره 298756 مورخ 16/08/1401 با توجه به نهایی نشدن مدرک مطالعات ژئوتکنیک در صورت تغییر در مقادیر مقاومت ویژه خاک مدرک محاسبات می بایست به روزرسانی شود. |  | 1401-2294-414697 | 1401-11-01 | در صورت وجود هر گونه تغییر در مدرک مطالعات خاک، و مقاومت ویژه آن، این مدرک به روزرسانی می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 03-Jan-23 |  |  |  |  | Date: