## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W046S-PEDCO-110-PR-PF-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1705 |  |  | Transmital Date: 12/17/2022
Document Title:Process Flow Diagram - W0046S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1705 |  |  | Transmital Date: 12/17/2022
[5 empty] | CRS No:NISOC-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص کامنت بیان شده به آن پیمانکار می رساند ، این مهم بیش از برگزاری جلسات HAZOP , HAZID طی نامه شماره 43234 مورخ 01/02/09 ، به اطلاع آن پیمانکار رسانده شده است و همچنین در مدارک پایه از شیر دروازه ای استفاده شده است لذا پاسخ پیمانکار در خصوص تبعات مالی و زمانی مورد قبول نمی باشد . |  | 1401-2294-378125 | 1401/10/05 | پیرو توافقات صورت گرفته در صورتجلسه مورخ 1401.11.11 در خصوص بررسی و نهایی سازی مدارک مهندسی سطح الارض میدان بینک، مدارک سرچاهی از جمله نقشه های P&ID اصلاح و به کارفرمای اصلی پروژه ارائه گردیده است. در خصوص کامنت اشاره شده آن کارفرمای محترم، شیر دروازه ای بر اساس مدرک P&ID در نقشه فوق نمایش داده شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: