## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0012-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1946 |  |  | Transmital Date: 06-Mar.-2023
Document Title: Specification For Flexibility Analysis |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1946 |  |  | Transmital Date:06-Mar.-2023
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0012-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات بصورت مارك شده در مدرك به پيوست ارسال مي گردد. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | احتراما پاسخ نقطه نظرات به پیوست ارسال می گردد. |  |  | See Item 2
2 | در Appendix A صفحات 14 و 15 مدرك شكل هاي FIG #1 و FIG #2 از چارت هاي ارائه شده در مدرك استاندارد IPS-E-PI-200 (1) استفاده شود و نوت هاي مربوطه در صفحه 15 نيز بطور مناسبي اصلاح گردد. |  | BK-SUR-ENG-PIP-01-07181 | 2023-03-13 | احتراما مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date:13-Mar.-2023 |  |  |  |  | Date:13-Mar.-2023