## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-PY-0011-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1325 |  |  | Transmital Date: 28-Aug-2022
Document Title: Equipment Arrangement Layout for UPS of CCTV in Production Unit |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-EL-TR-1325 |  |  | Transmital Date: 28-Aug-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-EL-PY-0011-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | The UPS shall be located in rack room, not gurad house room. |  | BK-SUR-ENG-ELE-01-05620 | 2022-09-10 | اعمال گردید.
2 | Battery cainet shall be shown as part of UPS system. Battery cabinet shown in the table with letter "G" but it missed in the drawing. |  | BK-SUR-ENG-ELE-01-05620 | 2022-09-10 | همانطور که بیان گردید، کابینت باتری بخشی از خود سیستم UPS می باشد، که بر این اساس حرف "H" به "G" اصلاح گردید.
3 | This document shall be revised after finalizing prerequisit document and vendor data (If required). |  | BK-SUR-ENG-ELE-01-05620 | 2022-09-10 | در صورت نیاز و تکمیل ابعاد از طرف وندور، این مدرک به روزرسانی خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 10-Sep-22 |  |  |  |  | Date: