## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-EL-LI-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1024 |  |  | Transmital Date: 30-May-2022
Document Title: Electrical Load List in Siahmakan Gas Injection |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-EL-TR-1024 |  |  | Transmital Date: 30-May-2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-EL-LI-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | According to our telephone conversation and scope of work, power supply of reciever station in siahmakan gas injection shall be done by exisiting LV switchgear. It shall be rechecked and modified (If required). |  | BK-SUR-ENG-ELE-01-04683 | 2022-06-12 | مطابق با مذاکرات انجام شده، ترانس رکتیفایر از فیدر L11 با آمپر 63 بر روس باسبار موجود تغذیه خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 12-Jun-22 |  |  |  |  | Date: