## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PR-PH-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1753 |  |  | Transmital Date: 1/2/2023
Document Title: Control Philosophy |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1753 |  |  | Transmital Date: 1/2/2023
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش 4 مدرک، به سوییچهای فشار و Pressure Sensing Line ها اشاره ای نشده است. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | اعمال گردید.
2 | در بخش 4.2 مدرک، درج گردد که داده های این بخش بر اساس داده های نهایی سازندگان شیرهای SSV و SSSV نهایی خواهد شد. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | اعمال گردید.
3 | در بخش 4.5 به فلسفه کنترل Sump Pump اشاره نشده است. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | اعمال گردید.
4 | توضیحات مندرج در پاراگراف دوم بخش 4.5 نیاز به تصحیح و شفاف سازی دارد. به عنوان نمونه عبارت Signal to be removed based on P و یا اشاره به کنترل فشار منیفولد توسط شیرهای کنترل دبی چند راهه می بایست شفاف سازی گردد. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | اصلاح گردید.
5 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021