## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PR-PH-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1748 |  |  | Transmital Date: 1/1/2023
Document Title: ESD Philosophy |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1748 |  |  | Transmital Date: 1/1/2023
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در فلسفه توقف، به فشار LL بالادست چوک نفت به عنوان یکی از دلایل بسته شدن SSSV اشاره شود. |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-18 | در زمان فعال شدن PSLL در WHCP شیر SSV چاه بسته شده و سیال ورودی به خط لوله جریانی قطع می شود.با توجه به توضیحات فوق باز بودن و یا بسته شدن شیر ESDV موجود در منیفولد تاثیری در عملکرد تفکیکگرهای موجود در منیفولد نخواهد داشت.لذا از منظر این پیمانکار نقطه نظر ذکر شده وجه اجرایی ندارد.
2 | در بخش Cause های تاسیسات سرچاهی، به PSHH بالادست و پایین دست چوک خط نفت، اشاره ای نشده است |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-18 | اعمال گردید.
3 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-18 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: